## Master List
Master Project List — Every Capital Plan Scope (all properties)
Every project/scope across all properties — completion + how billed. Filter/sort any column (e.g. by Acquired to see one cohort, by Status to see what's open).
Property | Acquired | Project | Scope of Work | GL Code | Owner | Type | Budget | Spent | Remaining | % Billed | Status
Emerald Pointe | 2015 | Pool Furniture Replacement | New Pool Furniture ($5,000) | 51010-00 | PMC | Project | 5000 | 12 | 4988 |  | In Progress
Emerald Pointe | 2015 | Pool Deck Repair | Seal Cracks Pool Deck ($700) Cracks were observed on the clubhouse pool deck. It appeared that there were attempts of re | 51021-00 | GC | Project | 700 | 700 | 0 |  | Completed
Emerald Pointe | 2015 | Pool Resurfacing | Resurface Pool Decks ($42,500) | 51023-00 | GC | Project | 42500 | 42500 | 0 |  | Completed
Emerald Pointe | 2015 | Court Resurfacing | Repair Basketball Court Cracks ($500) Asphalt pavement cracks was observed throughout the basketball court. Resealing cr | 51027-00 | GC | Project | 500 | 500 | 0 |  | Completed
Emerald Pointe | 2015 | Tree Trimming/Pruning & Removal | Tree Trimming ($25,000) | 51043-00 | PMC | Project | 25000 | 59 | 24941 |  | In Progress
Emerald Pointe | 2015 | Landscape Upgrades | Repair/Improve Landscape ($7,500) Many of the landscaping sprinkler systems are broken in multiple areas of theProperty. | 51045-00 | PMC | Project | 7500 | 18 | 7482 |  | In Progress
Emerald Pointe | 2015 | Irrigation System | Irrigation Repairs ($25,000) | 51046-00 | GC | Project | 25000 | 25000 | 0 |  | Completed
Emerald Pointe | 2015 | Roof Repairs | Roof Repairs ($15,000) | 51062-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
Emerald Pointe | 2015 | Roof Cleaning | Roof Inspection & Cleaning ($10,000) | 51063-00 | GC | Project | 10000 | 10000 | 0 |  | Completed
Emerald Pointe | 2015 | Fence Repair/Replacement | Remove Pergolas ($15,000) | 51076-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
Emerald Pointe | 2015 | Trim/Doors | Repair Damaged Door ($750) The maintenance room door located near the north pool was observed to bedamaged. Repairing th | 51082-00 | GC | Project | 750 | 750 | 0 |  | Completed
Emerald Pointe | 2015 | Decks/Balconies/Patio Repairs | Repair Deteriorating Wood on Patios ($15,000) | 51083-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
Emerald Pointe | 2015 | Railings & Fences | Replace Landing Railings ($60,000) | 51084-00 | GC | Project | 60000 | 60000 | 0 |  | Completed
Emerald Pointe | 2015 | Concrete/Foundation | Repair Concrete Pavement Cracks ($500) Concrete cracks were observed at the concrete pavement located adjacent to the ba | 51090-00 | GC | Project | 500 | 500 | 0 |  | Completed
Emerald Pointe | 2015 | Sidewalk/Curb Repair/Replacement | Repair Sidewalk Tripping Hazards ($2,500) | 51091-00 | GC | Project | 2500 | 2500 | 0 |  | Completed
Emerald Pointe | 2015 | Sidewalk/Curb Repair/Replacement | Repair Sidewalk Cracks ($700) A couple of the Subject's concrete sidewalk sections exhibit cracks. These conditions were | 51091-00 | GC | Project | 700 | 700 | 0 |  | Completed
Emerald Pointe | 2015 | Boiler Replacement | Repair Water Heater Leaks - Building 3 ($500) The water heater was leaking in Building 3 at the time of the assessment. | 51110-00 | PMC | Project | 500 | 1 | 499 |  | In Progress
Emerald Pointe | 2015 | Electrical Replacement | Replace Zinsco Electrical Subpanels ($525,000) Zinsco breakers were observed in the electrical subpanels inside all the | 51140-00 | GC | Project | 587000 | 587000 | 0 |  | Completed
Emerald Pointe | 2015 | Wiring | Repair Aluminum Wiring - Allowance ($225,000) Aluminum wiring was observed in the residential units. To mitigate aluminu | 51143-00 | GC | Project | 225000 | 225000 | 0 |  | Completed
Emerald Pointe | 2015 | Carpentry/Sheetrock | Repair Damaged Breezeway Ceiling ($1,000) A limited damaged of exterior breezeway ceiling finishes located by Building 2 | 51159-00 | GC | Project | 1000 | 1000 | 0 |  | Completed
Emerald Pointe | 2015 | Termite/Pest Control | Termite Remediation ($249,500) WDI infestation noted at rafter tail, water heater closet door jam, and water heater clos | 51992-00 | GC | Project | 249500 | 249500 | 0 |  | Completed
Emerald Pointe | 2015 | Capital Plan |  | Capital Plan | Unmarked | Project | 1288650 | 3033 | 1285617 |  | In Progress
Emerald Pointe | 2015 | Contingency Amount | Contingency | 51180-00 | GC | Contingency | 64432 | 64432 | 0 |  | Reserve
Emerald Pointe | 2015 | Construction Supervision Expense | CM Fees | 51190-00 | GC | Project | 67654 | 67654 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Storm sewer piping | Clean storm sewer basins | 84432 | GC | Project | 3000 | 3000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Asphalt & Pavement | Mill cement stabilize and repave asphalt part of drive esles and repair concrete potholes on phase two Repair concrete | 84204 | GC | Project | 400000 | 400000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Stripe parking areas | Stripe Parking | 84201 | GC | Project | 12000 | 12000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Sidewalks | Repair trip Hazards | 84115 | GC | Project | 12000 | 12000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Erosion control | Add soil to eroded areas Repair erosion at drainage channel - Minor erosion was observed in the drainage channel at the | 84517 | GC | Project | 1200 | 1200 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Fences & gates - site perimeter | Replace perimater fence on three sides of community Repair perimeter fencing - Collapsed fence panels were observed alon | 84205 | GC | Project | 95000 | 95000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Tree Trimming - Landscaping | Tree trim | 84303 | GC | Project | 15000 | 15000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Fences & gates - swimming pool | Rerair and paint pool fence | 84095 | GC | Project | 8500 | 8500 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Pergola court | Repair and paint purgola in culdasac | 84105 | GC | Project | 8000 | 8000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Dumpster enclosures | repair and paint | 84111 | GC | Project | 9800 | 9800 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Concrete Repairs - Repair washed out walkway at unit 23 | Repair wash out walkway at unit 2301 - The front entry concrete walkway to unit 2301 was noted as damaged from flooding | 84221 | PMC | Project | 750 | 750 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Repair ADA accessway and wheel stop | Repair ADA accessway and wheel stop - the accessway from the ADA parking lot, between Crescent Village 1 and 2 on the no | 84221 | GC | Project | 1800 | 1800 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Repair patio/balcony railings | secure all patio railings Repair exterior railings on east side of the property - Peeling and flaking paint was specifi | 84121 | GC | Project | 6500 | 6500 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Expansion Joints | Building Expansion Joints | 84206 | GC | Project | 8000 | 8000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Gutters & downspouts | Replace damaged gutter and downspouts, Clean, re-pitch remaining | 84202 | GC | Project | 9800 | 9800 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Roof Flashing | replace damaged flashing | 84433 | GC | Project | 4000 | 4000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Roof - Sealants & caulking | Roof Sealants | 84433 | GC | Project | 6000 | 6000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Replace AC condenser | Install installation and separate condensing units | 84220 | GC | Project | 9500 | 9500 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Electrical distribution | repair lighting control system | 84210 | GC | Project | 6000 | 6000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Common area light fixtures | repair /replace leaning or broken poles and pole lights throughout the community | 84210 | GC | Project | 32000 | 32000 | 0 |  | Completed
Viewcrest Village | 2021 | Grind Sidewalk Trip Hazard | Trip hazards were specifically observed by Buildings 3342, 3423, 3412, 3413, 3430, 1542, 3427. | 84221.0 | PMC | Project | 3062 | 765 | 2297 |  | In Progress
Viewcrest Village | 2021 | Sidewalk - Seal Concrete Cracks | Limited areas of concrete sidewalk were observed with cracks. These area were specifically were observed by Units 3472C | 84221.0 | PMC | Project | 750 | 187 | 563 |  | In Progress
Viewcrest Village | 2021 | Concrete Crack - Building 8 | Sidewalk exhibiting crack in concrete | 84221.0 | PMC | Project | 625 | 156 | 469 |  | In Progress
Viewcrest Village | 2021 | Leasing office | Spot reno (new FF&E) | 84116.0 | PMC | Project | 35000 | 8746 | 26254 |  | In Progress
Viewcrest Village | 2021 | Meter Boxes - Repair/replace meter/cable housing | Replace on all buildings | 84210.0 | PMC | Project | 25000 | 6247 | 18753 |  | In Progress
Viewcrest Village | 2021 | Roof Replacement | Replace 12 roofs | 84433.0 | GC | Project | 372000 | 372000 | 0 |  | Completed
Viewcrest Village | 2021 | Gutters & downspouts | Repair and replace damaged or missing gutters | 84202.0 | GC | Project | 25000 | 25000 | 0 |  | Completed
Viewcrest Village | 2021 | Flashing | Replace flashing on 12 remaining roofs | 84433.0 | GC | Project | 15000 | 15000 | 0 |  | Completed
Viewcrest Village | 2021 | Roof Repairs - Repair/replace sofits | Repair/replace missing or poorly maintained sofits to improve airflow | 84433.0 | GC | Project | 12500 | 12500 | 0 |  | Completed
Viewcrest Village | 2021 | Repair / replace vinyl siding | Replace failing siding as needed | 84206.0 | GC | Project | 20000 | 20000 | 0 |  | Completed
Viewcrest Village | 2021 | Exterior painting | Community Paint | 84101.0 | GC | Project | 375000 | 375000 | 0 |  | Completed
Viewcrest Village | 2021 | Repair / replace wood trim | Replace bad areas of Fascia | 84105.0 | GC | Project | 20000 | 20000 | 0 |  | Completed
Viewcrest Village | 2021 | HVAC Repair - Heating System | Cadet wall heaters were observed in 3-BR units. | 84217.0 | PMC | Project | 3188 | 796 | 2391 |  | In Progress
Viewcrest Village | 2021 | Fire System Work - Clear Fire Department Violations | The fire inspection report dated March 27, 2023, cited violations, including extension cords hanging from the ceiling an | 84211.0 | PMC | Project | 375 | 94 | 281 |  | In Progress
Viewcrest Village | 2021 | Electrical Panels - Replace FPE Stab-Lok Panels | It was reported that approximately 20% of the units still have FPE stab-lok panels. | 84330.0 | GC | Project | 126000 | 126000 | 0 |  | Completed
Viewcrest Village | 2021 | Electrical Meters - Electrical audit and grounding repa | Audit meters for proper housing, mounting and grounding and repair/replace as needed | 84210.0 | GC | Project | 51000 | 51000 | 0 |  | Completed
Viewcrest Village | 2021 | Appliances - Repair Washer/Dryer Hookups | Approximately 10-15 units have improperly installed hookups. | 82480.0 | PMC | Project | 9375 | 2343 | 7032 |  | In Progress
Viewcrest Village | 2021 | Interior Other - Bathroom tub mold | Mold at the bottom of the tub surround was observed at Unit 3412, 1512, 1538B, 1579, 4 out of 30 units that were inspect | 83160.0 | PMC | Project | 2500 | 625 | 1875 |  | In Progress
Viewcrest Village | 2021 | Pest Control - Interior pest control | Two vacant units, 3419B and 1512B have been found to have fleas throughout. Pest control treatment has been scheduled fo | 83170.0 | PMC | Project | 2000 | 500 | 1500 |  | In Progress
Encore Crossing | 2022 | Storm sewer piping |  | 0200 - Site Utilities & Improvements | GC | Project | 25000 | 25000 | 0 |  | Completed
Encore Crossing | 2022 | Concrete pavement | Repair | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
Encore Crossing | 2022 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Project | 8000 | 8000 | 0 |  | Completed
Encore Crossing | 2022 | Parking equipment | add 10 speed bumps | 0200 - Site Utilities & Improvements | GC | Project | 26000 | 26000 | 0 |  | Completed
Encore Crossing | 2022 | Parking Lot | Install 27 car stops in front of iron fencing Phase 1 | 0200 - Site Utilities & Improvements | GC | Project | 4050 | 4050 | 0 |  | Completed
Encore Crossing | 2022 | Sidewalks | repair cracked concrete | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
Encore Crossing | 2022 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Project | 26000 | 26000 | 0 |  | Completed
Encore Crossing | 2022 | Fences & gates - site perimeter | $40k = Repair wood fence and paint, $40k = Repair (3) entrance gates. $15k iron fence repairs Phase 1 | 0200 - Site Utilities & Improvements | GC | Project | 95000 | 95000 | 0 |  | Completed
Encore Crossing | 2022 | Landscaping | remove dead shrubs and change entrance island shrubs. DD $60k placeholder for landscape enhancement | 0200 - Site Utilities & Improvements | GC | Project | 110000 | 110000 | 0 |  | Completed
Encore Crossing | 2022 | Resurface swimming pool | Resurface Phase I | 0200 - Site Utilities & Improvements | GC | Project | 28000 | 28000 | 0 |  | Completed
Encore Crossing | 2022 | Replace swimming pool coping | replace deck-o-seal in both pools | 0200 - Site Utilities & Improvements | GC | Project | 9200 | 9200 | 0 |  | Completed
Encore Crossing | 2022 | Replace swimming pool deck | Pressure wash and coat pool deck in phase two | 0200 - Site Utilities & Improvements | GC | Project | 18900 | 18900 | 0 |  | Completed
Encore Crossing | 2022 | Repair / replace swimming pool pumps | Phase 2 pool fountain repair | 0200 - Site Utilities & Improvements | GC | Project | 5000 | 5000 | 0 |  | Completed
Encore Crossing | 2022 | Fences & gates - swimming pool | repair dog park and Pool fences and paint | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
Encore Crossing | 2022 | Pool Area Enhancement | Value-add enhancement to pool area, to inlcude turf installation, outdoor kitchen, fire pit area | 0200 - Site Utilities & Improvements | GC | Project | 50000 | 50000 | 0 |  | Completed
Encore Crossing | 2022 | Dumpster enclosures | Repair Dumpsters and paint | 0200 - Site Utilities & Improvements | GC | Project | 8000 | 8000 | 0 |  | Completed
Encore Crossing | 2022 | Building entrance | Entrance upgrade | 0200 - Site Utilities & Improvements | GC | Project | 40000 | 40000 | 0 |  | Completed
Encore Crossing | 2022 | Carports / Garages | Replace 10 garage doors | 0200 - Site Utilities & Improvements | GC | Project | 45000 | 45000 | 0 |  | Completed
Encore Crossing | 2022 | Carports / Garages | Repair/replace 15 garage door openers/ placeholder for purchase of openers | 0200 - Site Utilities & Improvements | GC | Project | 12000 | 12000 | 0 |  | Completed
Encore Crossing | 2022 | Dog Park | Placeholder for upgrade of equipment in dog park | 0200 - Site Utilities & Improvements | GC | Project | 10000 | 10000 | 0 |  | Completed
Encore Crossing | 2022 | Wall framing |  | 0400 - Structure | GC | Project | 8200 | 8200 | 0 |  | Completed
Encore Crossing | 2022 | Repair exterior stair railings |  | 0400 - Structure | GC | Project | 7000 | 7000 | 0 |  | Completed
Encore Crossing | 2022 | Repair balcony framing & decking |  | 0400 - Structure | GC | Project | 18500 | 18500 | 0 |  | Completed
Encore Crossing | 2022 | Repair patio/balcony railings |  | 0400 - Structure | GC | Project | 7000 | 7000 | 0 |  | Completed
Encore Crossing | 2022 | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | 0700 - Roofing | GC | Project | 20000 | 20000 | 0 |  | Completed
Encore Crossing | 2022 | Gutters & downspouts | clean and repin | 0700 - Roofing | GC | Project | 10000 | 10000 | 0 |  | Completed
Encore Crossing | 2022 | Flashing |  | 0700 - Roofing | GC | Project | 5600 | 5600 | 0 |  | Completed
Encore Crossing | 2022 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Project | 5600 | 5600 | 0 |  | Completed
Encore Crossing | 2022 | Repair / replace wood siding | Added $8000 for paint to match | 0800 - Exterior Wall | GC | Project | 25200 | 25200 | 0 |  | Completed
Encore Crossing | 2022 | Dryer Vents | Clean 256 dryer vents ($35 per) and replace (100) dryer vents | 0800 - Exterior Wall | GC | Project | 13960 | 13960 | 0 |  | Completed
Encore Crossing | 2022 | Tuck-pointing |  | 0800 - Exterior Wall | GC | Project | 3800 | 3800 | 0 |  | Completed
Encore Crossing | 2022 | Repair / replace wood trim | Added $8000 for paint to match | 0800 - Exterior Wall | GC | Project | 26900 | 26900 | 0 |  | Completed
Encore Crossing | 2022 | Shutters | Replace missing shutters and paint to match | 0800 - Exterior Wall | GC | Project | 10200 | 10200 | 0 |  | Completed
Encore Crossing | 2022 | Interior Update Placeholder |  | 0900 - FF&E in Units | PMC | Project | 960000 | 332 | 959668 |  | In Progress
Encore Crossing | 2022 | Range Queen |  | 0900 - FF&E in Units | PMC | Project | 32040 | 0 | 32040 |  | Not Started
Encore Crossing | 2022 | Signage - site | Front monument sign & lighting | 1100- Specialties, Equipment & Furnishings | PMC | Project | 25000 | 29319 | -4319 |  | Completed
Encore Crossing | 2022 | Signage - building identification | New signage throughout, includes logo design and all new collateral | 1100- Specialties, Equipment & Furnishings | PMC | Project | 20000 | 23455 | -3455 |  | Completed
Encore Crossing | 2022 | Clubhouse / Office Remodel | Per Mark, placeholder for office redecoration x 2 (Includes adding sliding glass doors out to pool and opening up wall t | 1100- Specialties, Equipment & Furnishings | GC | Project | 125000 | 125000 | 0 |  | Completed
Encore Crossing | 2022 | Clubhouse / Office Redecorate (FFE) | Office redecoration placeholder | 1100- Specialties, Equipment & Furnishings | PMC | Project | 50000 | 131158 | -81158 |  | Completed
Encore Crossing | 2022 | Audio systems | Audio system for 2 pool areas | 1100- Specialties, Equipment & Furnishings | GC | Project | 25000 | 25000 | 0 |  | Completed
Encore Crossing | 2022 | Video systems | Installation of new system (placeholder) | 1100- Specialties, Equipment & Furnishings | PMC | Project | 75000 | 0 | 75000 |  | Not Started
Encore Crossing | 2022 | Fitness Equipment | New fitness equipment | 1100- Specialties, Equipment & Furnishings | PMC | Project | 50000 | 67319 | -17319 |  | Completed
Encore Crossing | 2022 | Pool furniture | New pool furniture (2 pools) | 1100- Specialties, Equipment & Furnishings | PMC | Project | 60000 | 206 | 59794 |  | In Progress
Encore Crossing | 2022 | Fitness center renovation | Install new gym floor phase 2 and paint | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Encore Crossing | 2022 | Golf Cart | Repair (2) golf carts- changed to 3 new golf carts | 1100- Specialties, Equipment & Furnishings | PMC | Project | 10000 | 69808 | -59808 |  | Completed
Encore Crossing | 2022 | Electrical distribution |  | 1600 - Electrical | GC | Project | 6600 | 6600 | 0 |  | Completed
Encore Crossing | 2022 | Common area light fixtures | replace garage light fixtures | 1600 - Electrical | GC | Project | 22000 | 22000 | 0 |  | Completed
Encore Crossing | 2022 | Replace breezeway lights | Replace breezeway fixtures with led | 1600 - Electrical | GC | Project | 28600 | 28600 | 0 |  | Completed
Island Villas | 2022 | Storm sewer piping |  | 0200 - Site Utilities & Improvements | GC | Project | 16000 | 16000 | 0 |  | Completed
Island Villas | 2022 | Concrete pavement | Repair | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
Island Villas | 2022 | Stripe parking areas | Includes $5k for painting curbs at closing | 0200 - Site Utilities & Improvements | GC | Project | 13000 | 13000 | 0 |  | Completed
Island Villas | 2022 | Parking equipment | add 10 speed bumps | 0200 - Site Utilities & Improvements | GC | Project | 28000 | 28000 | 0 |  | Completed
Island Villas | 2022 | Sidewalks | repair cracked concrete | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
Island Villas | 2022 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Project | 26000 | 26000 | 0 |  | Completed
Island Villas | 2022 | Erosion control | replace dirt missing due to erosion | 0200 - Site Utilities & Improvements | GC | Project | 45000 | 45000 | 0 |  | Completed
Island Villas | 2022 | Fences & gates - site perimeter | Replace wood fence and paint | 0200 - Site Utilities & Improvements | GC | Project | 154000 | 154000 | 0 |  | Completed
Island Villas | 2022 | Retaining walls | build retaining wall at site exit | 0200 - Site Utilities & Improvements | GC | Project | 60000 | 60000 | 0 |  | Completed
Island Villas | 2022 | Landscaping | remove dead shrubs and change entrance island shrubs, landscaping around pool and planters for 2nd pool. Installation of | 0200 - Site Utilities & Improvements | GC | Project | 100000 | 100000 | 0 |  | Completed
Island Villas | 2022 | Resurface swimming pool | resurface pool by office | 0200 - Site Utilities & Improvements | GC | Project | 41000 | 41000 | 0 |  | Completed
Island Villas | 2022 | Replace swimming pool coping | replace deck-o-seal in both pools | 0200 - Site Utilities & Improvements | GC | Project | 9600 | 9600 | 0 |  | Completed
Island Villas | 2022 | Replace swimming pool deck | Replace pool deck w/ stamp stain concrete (main pool) and repairs to 2nd pool deck | 0200 - Site Utilities & Improvements | GC | Project | 80000 | 80000 | 0 |  | Completed
Island Villas | 2022 | Fences & gates - swimming pool | repair dog park and Pool fences and paint | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
Island Villas | 2022 | Pool Area | Install (2) pool cabanas, turf in outdoor kitchen area | 0200 - Site Utilities & Improvements | GC | Project | 45000 | 45000 | 0 |  | Completed
Island Villas | 2022 | Dumpster enclosures | Repair Dumpsters and paint | 0200 - Site Utilities & Improvements | GC | Project | 12000 | 12000 | 0 |  | Completed
Island Villas | 2022 | Carports / Garages | Replace 6 garage doors and paint garages | 0200 - Site Utilities & Improvements | GC | Project | 28000 | 28000 | 0 |  | Completed
Island Villas | 2022 | Wall framing |  | 0400 - Structure | GC | Project | 5000 | 5000 | 0 |  | Completed
Island Villas | 2022 | Repair exterior stair railings | Minor repairs to balconies | 0400 - Structure | GC | Project | 7000 | 7000 | 0 |  | Completed
Island Villas | 2022 | Repair balcony framing & decking | Fill cracks in decking | 0400 - Structure | GC | Project | 18500 | 18500 | 0 |  | Completed
Island Villas | 2022 | Repair patio/balcony railings | resecure | 0400 - Structure | GC | Project | 7000 | 7000 | 0 |  | Completed
Island Villas | 2022 | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | 0700 - Roofing | GC | Project | 20000 | 20000 | 0 |  | Completed
Island Villas | 2022 | Cleaning Blue Algae | Treating/cleaning blue algae on roofs ($4k per building) | 0700 - Roofing | GC | Project | 60000 | 60000 | 0 |  | Completed
Island Villas | 2022 | Gutters & downspouts | replace missing elbows and splash blocks | 0700 - Roofing | GC | Project | 12000 | 12000 | 0 |  | Completed
Island Villas | 2022 | Flashing |  | 0700 - Roofing | GC | Project | 5600 | 5600 | 0 |  | Completed
Island Villas | 2022 | Sealants & caulking and paint | Seal all face nails in siding | 0700 - Roofing | GC | Project | 67200 | 67200 | 0 |  | Completed
Island Villas | 2022 | Repair / replace wood siding | Added $8000 for paint to match | 0800 - Exterior Wall | GC | Project | 24000 | 24000 | 0 |  | Completed
Island Villas | 2022 | Dryer Vents | clean all dryer vents | 0800 - Exterior Wall | GC | Project | 11760 | 11760 | 0 |  | Completed
Island Villas | 2022 | Repair / replace wood trim | Added $7500 for paint to match | 0800 - Exterior Wall | GC | Project | 22500 | 22500 | 0 |  | Completed
Island Villas | 2022 | Shutters | Added $3000 for paint to match | 0800 - Exterior Wall | GC | Project | 10200 | 10200 | 0 |  | Completed
Island Villas | 2022 | Interior Update Placeholder |  | 0900 - FF&E in Units | PMC | Project | 749760 | 592172 | 157588 |  | In Progress
Island Villas | 2022 | Range Queen |  | 0900 - FF&E in Units | PMC | Project | 30240 | 0 | 30240 |  | Not Started
Island Villas | 2022 | Signage - entry | New Monument Sign at corner | 1100- Specialties, Equipment & Furnishings | PMC | Project | 25000 | 7329 | 17671 |  | In Progress
Island Villas | 2022 | Signage - site | Bldg ID signs, common area signage | 1100- Specialties, Equipment & Furnishings | PMC | Project | 15000 | 4397 | 10603 |  | In Progress
Island Villas | 2022 | Clubhouse / Office Remodel | Re-paint / new flooring for office | 1100- Specialties, Equipment & Furnishings | GC | Project | 50000 | 50000 | 0 |  | Completed
Island Villas | 2022 | Clubhouse / Office Redecorate (FFE) |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 35000 | 53745 | -18745 |  | Completed
Island Villas | 2022 | Security/ fire alarm systems | Placeholder for installation of cameras | 1100- Specialties, Equipment & Furnishings | PMC | Project | 60000 | 30339 | 29661 |  | In Progress
Island Villas | 2022 | Audio systems | Speaker system for main pool area | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Island Villas | 2022 | Fitness Equipment | New gym equipment | 1100- Specialties, Equipment & Furnishings | PMC | Project | 30000 | 19034 | 10966 |  | In Progress
Island Villas | 2022 | Pool furniture | Include additional tables/sitting areas | 1100- Specialties, Equipment & Furnishings | PMC | Project | 30000 | 4650 | 25350 |  | In Progress
Island Villas | 2022 | Fitness center renovation | Remove wall to enlarge gym area & install flooring/paint | 1100- Specialties, Equipment & Furnishings | GC | Project | 25000 | 25000 | 0 |  | Completed
Island Villas | 2022 | Electrical distribution | repair outside GFCI'S | 1600 - Electrical | GC | Project | 16000 | 16000 | 0 |  | Completed
Island Villas | 2022 | Common area light fixtures | replace garage light fixtures and wall packs | 1600 - Electrical | GC | Project | 36000 | 36000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Concrete pavement |  | 83221 | GC | Project | 18000 | 18000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Stripe parking areas |  | 83201 | GC | Project | 16000 | 16000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | ADA parking & curb cuts |  | 83520 | GC | Project | 6500 | 6500 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Landscape irrigation | inspect and repair irrigation | 83300 | GC | Project | 34000 | 34000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Fences & gates - site perimeter | Remove vines, repair fence and paint fence | 83205 | GC | Project | 60000 | 60000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Landscaping | Landscaping for curb and pool (place Holder) | 83303 | GC | Project | 150000 | 150000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Resurface swimming pool | Resurface pool, Replace tile | 83100 | GC | Project | 58000 | 58000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Replace swimming pool coping | Replace deck-o-seal on pool and repair coping | 83100 | GC | Project | 21000 | 21000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Replace swimming pool deck | Clean and recoat pool deck | 83100 | GC | Project | 45000 | 45000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Fences & gates - swimming pool | Repair and paint pool fence | 83205 | GC | Project | 9500 | 9500 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Pergola | repair and stain all pergola | 83206 | GC | Project | 18000 | 18000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Carport and garage | Repair carport damage and paint | 83219 | GC | Project | 29000 | 29000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Dumpster enclosures | Repair dumpster enclosures | 83111 | GC | Project | 15000 | 15000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair exterior stair railings | secure railings | 83114 | GC | Project | 8300 | 8300 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair balcony framing & decking | repair balcony band boards | 83104 | GC | Project | 18000 | 18000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair patio/balcony railings | secure railings | 83114 | GC | Project | 8300 | 8300 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Expansion Joints | clean and seal expansion joints | 83206 | GC | Project | 15000 | 15000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Asphalt composite shingle roofing | minor roof repairs | 83202 | GC | Project | 23000 | 23000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Gutters & downspouts | Clean down spouts and gutters | 83439 | GC | Project | 23000 | 23000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Sealants & caulking |  | 83206 | GC | Project | 18000 | 18000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair / replace cement fiber siding | repair damaged siding |  | GC | Project | 10000 | 10000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair stucco |  |  | GC | Project | 20000 | 20000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies |  | GC | Project | 23000 | 23000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Exterior building | Paint community |  | GC | Project | 328000 | 328000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair / replace wood trim |  |  | GC | Project | 23000 | 23000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Shutters | Replace bad shutters |  | GC | Project | 28000 | 28000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGc | 684sqft, 1BR 1BA |  | GC | Project | 352224 | 352224 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGe | 773sqft, 1BR 1BA |  | GC | Project | 540512 | 540512 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGg | 894sqft, 1BR 1BA |  | GC | Project | 50764 | 50764 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AZh | 946sqft, 1BR 1BA |  | GC | Project | 249588 | 249588 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGl | 1117sqft, 2BR 2BA |  | GC | Project | 270127 | 270127 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn | 1247sqft, 2BR 2BA |  | GC | Project | 36836 | 36836 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn1 | 1256sqft, 2BR 2BA |  | GC | Project | 24734 | 24734 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn2 | 1259sqft, 2BR 2BA |  | GC | Project | 24866 | 24866 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn3 | 1271sqft, 2BR 2BA |  | GC | Project | 37596 | 37596 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGo1 | 1376sqft, 2BR 2BA |  | GC | Project | 26058 | 26058 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 3CGo | 1381sqft, 3BR 2BA |  | GC | Project | 39307 | 39307 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 3CGp | 1477sqft, 3BR 2BA |  | GC | Project | 27022 | 27022 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Ceiling Fans | Add to all living rooms |  | GC | Project | 90200 | 90200 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Clubhouse / Office Remodel | Replace carpet tile, some paint and finish refresh |  | GC | Project | 50000 | 50000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Clubhouse / Office Redecorate (FFE) |  |  | Unmarked | Project | 80000 | 63309 | 16691 |  | In Progress
Amalfi at Tuscan Lakes | 2023 | Model Unit | Allowance for small additions/refresh |  | Unmarked | Project | 4000 | 8256 | -4256 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Computers | Not needed, allowance for 1 |  | Unmarked | Project | 1500 | 1817 | -317 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Mailboxes | Package locker or Fetch system needed |  | Unmarked | Project | 20000 | 0 | 20000 |  | Not Started
Amalfi at Tuscan Lakes | 2023 | Fountain area Remodel | Address planter- either fill with rocks or fix irrigation Look at cabanas or shade over benches by reflecting pond Lock |  | GC | Project | 14000 | 14000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Security Camera System | Need at least for entry drive, clubhouse, and amenity coverage |  | Unmarked | Project | 20000 | 7426 | 12574 |  | In Progress
Amalfi at Tuscan Lakes | 2023 | EV Chargers | Likely will be no-cost to property, but providing allowance |  | Unmarked | Project | 8000 | 0 | 8000 |  | Not Started
Amalfi at Tuscan Lakes | 2023 | Pool Remodel | New vertical tile on side of pool wall to replace aged blue Fire pit in raised area if feasible New grill area with cou |  | GC | Project | 100000 | 100000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Fitness Equipment | 2 Ellipticals, other allowance for repairs and new equipment |  | Unmarked | Project | 18000 | 11961 | 6039 |  | In Progress
Amalfi at Tuscan Lakes | 2023 | Pool furniture | New furniture for pool, repurpose and re-sling existing and move to Sorrento |  | Unmarked | Project | 45000 | 28892 | 16108 |  | In Progress
Amalfi at Tuscan Lakes | 2023 | Fitness center renovation | Add mirrors, 1-2 TVs |  | GC | Project | 10000 | 10000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Golf Cart | Utility/Maintenance Cart |  | Unmarked | Project | 8000 | 0 | 8000 |  | Not Started
Amalfi at Tuscan Lakes | 2023 | Dryer Vent cleaning |  |  | GC | Project | 24600 | 24600 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Electrical distribution |  |  | GC | Project | 8500 | 8500 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Fire and Sprinklers | replace emergency lights |  | GC | Project | 18560 | 18560 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Common area light fixtures | Replace all wall packs |  | GC | Project | 38640 | 38640 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Replace breezeway lights | Replace breezeway, Garage and landscaping lights |  | GC | Project | 49860 | 49860 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Contingency |  |  | Unmarked | Contingency | 108322 | 0 | 108322 |  | Reserve
Amalfi at Tuscan Lakes | 2023 | Construction Management Fee |  |  | Unmarked | Contingency | 171121 | 0 | 171121 |  | Reserve
Avila | 2023 | Storm sewer piping |  |  | GC | Project | 38800 | 38800 | 0 |  | Completed
Avila | 2023 | Parking Equipment- wheel stops |  |  | GC | Project | 750 | 750 | 0 |  | Completed
Avila | 2023 | Pavement |  |  | GC | Project | 150000 | 150000 | 0 |  | Completed
Avila | 2023 | Stripe parking areas |  |  | GC | Project | 13000 | 13000 | 0 |  | Completed
Avila | 2023 | Asphalt coating |  |  | GC | Project | 98000 | 98000 | 0 |  | Completed
Avila | 2023 | ADA parking & curb cuts |  |  | GC | Project | 6800 | 6800 | 0 |  | Completed
Avila | 2023 | Sidewalks |  |  | GC | Project | 8400 | 8400 | 0 |  | Completed
Avila | 2023 | Landscape irrigation |  |  | GC | Project | 49000 | 49000 | 0 |  | Completed
Avila | 2023 | Erosion control |  |  | GC | Project | 30000 | 30000 | 0 |  | Completed
Avila | 2023 | Retaining walls |  |  | GC | Project | 14000 | 14000 | 0 |  | Completed
Avila | 2023 | Replace swimming pool coping |  |  | GC | Project | 8600 | 8600 | 0 |  | Completed
Avila | 2023 | Repair / replace swimming pool pumps |  |  | GC | Project | 6800 | 6800 | 0 |  | Completed
Avila | 2023 | Fences & gates |  |  | GC | Project | 9600 | 9600 | 0 |  | Completed
Avila | 2023 | Carport and garage |  |  | GC | Project | 31000 | 31000 | 0 |  | Completed
Avila | 2023 | Dumpster enclosures |  |  | GC | Project | 21000 | 21000 | 0 |  | Completed
Avila | 2023 | Maintenance Structure |  |  | GC | Project | 2500 | 2500 | 0 |  | Completed
Avila | 2023 | Jack & underpin foundations |  |  | GC | Project | 72000 | 72000 | 0 |  | Completed
Avila | 2023 | Concrete deck / floor fill |  |  | GC | Project | 18000 | 18000 | 0 |  | Completed
Avila | 2023 | Wall framing |  |  | GC | Project | 1500 | 1500 | 0 |  | Completed
Avila | 2023 | Repair exterior stair treads and stringers |  |  | GC | Project | 30000 | 30000 | 0 |  | Completed
Avila | 2023 | Repair exterior stair railings |  |  | GC | Project | 30000 | 30000 | 0 |  | Completed
Avila | 2023 | Repair balcony framing & decking |  |  | GC | Project | 20000 | 20000 | 0 |  | Completed
Avila | 2023 | Repair patio/balcony railings |  |  | GC | Project | 6500 | 6500 | 0 |  | Completed
Avila | 2023 | Asphalt composite shingle roofing |  |  | GC | Project | 23000 | 23000 | 0 |  | Completed
Avila | 2023 | Gutters & downspouts |  |  | GC | Project | 23000 | 23000 | 0 |  | Completed
Avila | 2023 | Flashing |  |  | GC | Project | 11000 | 11000 | 0 |  | Completed
Avila | 2023 | Sealants & caulking and paint |  |  | GC | Project | 7500 | 7500 | 0 |  | Completed
Avila | 2023 | Repair / replace wood siding |  |  | GC | Project | 66000 | 66000 | 0 |  | Completed
Avila | 2023 | Tuck-pointing |  |  | GC | Project | 23000 | 23000 | 0 |  | Completed
Avila | 2023 | Exterior building |  |  | GC | Project | 400000 | 400000 | 0 |  | Completed
Avila | 2023 | Repair / replace wood trim |  |  | GC | Project | 28000 | 28000 | 0 |  | Completed
Avila | 2023 | storage room doors - exterior |  |  | GC | Project | 20000 | 20000 | 0 |  | Completed
Avila | 2023 | Unit Repair |  |  | GC | Project | 1500 | 1500 | 0 |  | Completed
Avila | 2023 | Fire protection | 327 |  | GC | Project | 24525 | 24525 | 0 |  | Completed
Avila | 2023 | Clubhouse / Office Redecorate (FFE) |  |  | GC | Project | 15000 | 15000 | 0 |  | Completed
Avila | 2023 | Picnic Area Renovation |  |  | GC | Project | 150000 | 150000 | 0 |  | Completed
Avila | 2023 | Pool 1 (West) Renovation |  |  | GC | Project | 10000 | 10000 | 0 |  | Completed
Avila | 2023 | Old Pool House by Pool 1 (West) |  |  | GC | Project | 30000 | 30000 | 0 |  | Completed
Avila | 2023 | Pool 2 (East) Renovation |  |  | GC | Project | 5000 | 5000 | 0 |  | Completed
Avila | 2023 | Dog Park |  |  | GC | Project | 20000 | 20000 | 0 |  | Completed
Avila | 2023 | Electrical distribution |  |  | GC | Project | 22800 | 22800 | 0 |  | Completed
Avila | 2023 | Common area light fixtures |  |  | GC | Project | 32400 | 32400 | 0 |  | Completed
Collin Creek | 2023 | Storm sewer piping | clean out storm drain boxes | 0200 - Site Utilities & Improvements | GC | Project | 8600 | 8600 | 0 |  | Completed
Collin Creek | 2023 | Concrete pavement | repair pot holes and broken sidewalks | 0200 - Site Utilities & Improvements | GC | Project | 39000 | 39000 | 0 |  | Completed
Collin Creek | 2023 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Project | 9500 | 9500 | 0 |  | Completed
Collin Creek | 2023 | ADA parking & curb cuts |  | 0200 - Site Utilities & Improvements | GC | Project | 6500 | 6500 | 0 |  | Completed
Collin Creek | 2023 | Sidewalks |  | 0200 - Site Utilities & Improvements | GC | Project | 26000 | 26000 | 0 |  | Completed
Collin Creek | 2023 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Project | 26000 | 26000 | 0 |  | Completed
Collin Creek | 2023 | Erosion control |  | 0200 - Site Utilities & Improvements | GC | Project | 31000 | 31000 | 0 |  | Completed
Collin Creek | 2023 | Retaining walls | Replace railroad tie retaining walls | 0200 - Site Utilities & Improvements | GC | Project | 120000 | 120000 | 0 |  | Completed
Collin Creek | 2023 | Landscaping | Trim Trees and sod building with erosion | 0200 - Site Utilities & Improvements | GC | Project | 72000 | 72000 | 0 |  | Completed
Collin Creek | 2023 | Landscaping- Primary pool area | Turf or other plants instead of brown mulch and boxwood hedges in planters | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
Collin Creek | 2023 | Landscaping- Secondary pool area | Areas by pool- new sod | 0200 - Site Utilities & Improvements | GC | Project | 10000 | 10000 | 0 |  | Completed
Collin Creek | 2023 | Resurface swimming pool | resurface pool | 0200 - Site Utilities & Improvements | GC | Project | 31000 | 31000 | 0 |  | Completed
Collin Creek | 2023 | Replace swimming pool coping | Replace deck-o-seal on pool | 0200 - Site Utilities & Improvements | GC | Project | 8600 | 8600 | 0 |  | Completed
Collin Creek | 2023 | Replace swimming pool deck- Primary pool | New decking to replace aggregate | 0200 - Site Utilities & Improvements | GC | Project | 70000 | 70000 | 0 |  | Completed
Collin Creek | 2023 | Fences & gates - swimming pool | Repair and paint pool fences | 0200 - Site Utilities & Improvements | GC | Project | 5600 | 5600 | 0 |  | Completed
Collin Creek | 2023 | Pergola | repair and stain all pergola | 0200 - Site Utilities & Improvements | GC | Project | 3100 | 3100 | 0 |  | Completed
Collin Creek | 2023 | Playground equipment | Replace Fall zone in play ground | 0200 - Site Utilities & Improvements | GC | Project | 9800 | 9800 | 0 |  | Completed
Collin Creek | 2023 | Picnic areas | replace 2 grills | 0200 - Site Utilities & Improvements | GC | Project | 8800 | 8800 | 0 |  | Completed
Collin Creek | 2023 | Dumpster enclosures | Dumpster enclosures are scrubs replace with fencing and repair gates | 0200 - Site Utilities & Improvements | GC | Project | 21000 | 21000 | 0 |  | Completed
Collin Creek | 2023 | Radon Remediation from lender report | Radon mitigation should be completed by a Texas-licensed contractor. When radon remains elevated over the EPA Action Lev | 0200 - Site Utilities & Improvements | PMC | Project | 10000 | 40580 | -30580 |  | Completed
Collin Creek | 2023 | Jack & underpin foundations | Place holder for 5 building that show signs of foundation movement | 0300 - Excavation & Foundations | GC | Project | 150000 | 150000 | 0 |  | Completed
Collin Creek | 2023 | Foundations | Additional scope identified by TAM | 0300 - Excavation & Foundations | GC | Project | 172728 | 172728 | 0 |  | Completed
Collin Creek | 2023 | Wall framing | Replace damaged gable vents and balcony structure | 0400 - Structure | GC | Project | 43000 | 43000 | 0 |  | Completed
Collin Creek | 2023 | Roof deck | replace bad decking on roofs | 0400 - Structure | GC | Project | 25000 | 25000 | 0 |  | Completed
Collin Creek | 2023 | Repair exterior stair railings | secure railings | 0400 - Structure | GC | Project | 4200 | 4200 | 0 |  | Completed
Collin Creek | 2023 | Repair balcony framing & decking | repair balcony band boards | 0400 - Structure | GC | Project | 9700 | 9700 | 0 |  | Completed
Collin Creek | 2023 | Repair patio/balcony railings | secure railings | 0400 - Structure | GC | Project | 4200 | 4200 | 0 |  | Completed
Collin Creek | 2023 | Expansion joints | clean and seal expansion joints | 0400 - Structure | GC | Project | 12000 | 12000 | 0 |  | Completed
Collin Creek | 2023 | Asphalt composite shingle roofing | minor roof repairs | 0700 - Roofing | GC | Project | 36000 | 36000 | 0 |  | Completed
Collin Creek | 2023 | Gutters & downspouts | Clean down spouts and gutters | 0700 - Roofing | GC | Project | 20000 | 20000 | 0 |  | Completed
Collin Creek | 2023 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Project | 9000 | 9000 | 0 |  | Completed
Collin Creek | 2023 | Repair / replace cement fiber siding | repair damaged siding | 0800 - Exterior Wall | GC | Project | 12000 | 12000 | 0 |  | Completed
Collin Creek | 2023 | Tuck-pointing |  | 0800 - Exterior Wall | GC | Project | 14000 | 14000 | 0 |  | Completed
Collin Creek | 2023 | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | 0800 - Exterior Wall | GC | Project | 6800 | 6800 | 0 |  | Completed
Collin Creek | 2023 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Project | 320000 | 320000 | 0 |  | Completed
Collin Creek | 2023 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Project | 51000 | 51000 | 0 |  | Completed
Collin Creek | 2023 | Interior Update- Classic to Gold | Test smaller initial qty | 0900 - FF&E in Units | PMC | Project | 500000 | 255167 | 244833 |  | In Progress
Collin Creek | 2023 | Interior Update- Silver to Gold | Test smaller initial qty | 0900 - FF&E in Units | PMC | Project | 450000 | 229651 | 220349 |  | In Progress
Collin Creek | 2023 | Range Queen |  | 0900 - FF&E in Units | GC | Project | 29830 | 29830 | 0 |  | Completed
Collin Creek | 2023 | Gym Fitness Equipment | Upgraded package from Comm FIT, Basic also available fo $20k | 1100- Specialties, Equipment & Furnishings | PMC | Project | 34000 | 13734 | 20266 |  | In Progress
Collin Creek | 2023 | Gym Flooring | Fitdek 8mm roll with install- Quotation # S07142 from Comm FIT | 1100- Specialties, Equipment & Furnishings | PMC | Project | 11000 | 1957 | 9043 |  | In Progress
Collin Creek | 2023 | Pool furniture- Primary Pool |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 25000 | 27009 | -2009 |  | Completed
Collin Creek | 2023 | Pool enhancements- Primary Pool | 110 & 55 sqft of turf 2 corn hole boards w/custom logo chess/checkers shade structure Budget | 1100- Specialties, Equipment & Furnishings | PMC | Project | 36000 | 2899 | 33101 |  | In Progress
Collin Creek | 2023 | Pool enhancements- Secondary Pool | New grill New fire pit Convert planters next to pool to turf or pavers | 1100- Specialties, Equipment & Furnishings | PMC | Project | 30000 | 2415 | 27585 |  | In Progress
Collin Creek | 2023 | Pool area lighting fixtures | Update pole lighting- new fixtures on top and straighten poles | 1100- Specialties, Equipment & Furnishings | GC | Project | 6000 | 6000 | 0 |  | Completed
Collin Creek | 2023 | Fitness center renovation | New exterior windows New flooring-rubber tiles Paint Ventilation/fans Electrical to doors for key Relocate TV above aero | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 40000 | 0 |  | Completed
Collin Creek | 2023 | Laundry room | Built in table instead of floating tables Replace broken window | 1100- Specialties, Equipment & Furnishings | GC | Project | 1500 | 1500 | 0 |  | Completed
Collin Creek | 2023 | Laundry room furniture | Furniture in waiting area | 1100- Specialties, Equipment & Furnishings | PMC | Project | 2000 | 0 | 2000 |  | Not Started
Collin Creek | 2023 | Dog Park upgrades | Move square dog jump paint jumps Wash station for dogs | 1100- Specialties, Equipment & Furnishings | GC | Project | 5000 | 5000 | 0 |  | Completed
Collin Creek | 2023 | Dog Park entrance area | Convert entry area to concrete. Adjust entry level to avoid erosion/wash out and raise gate to avoid contact with ground | 1100- Specialties, Equipment & Furnishings | GC | Project | 17000 | 17000 | 0 |  | Completed
Collin Creek | 2023 | Package lockers | Luxer one- from Texas Package Solutions | 1100- Specialties, Equipment & Furnishings | PMC | Project | 70000 | 0 | 70000 |  | Not Started
Collin Creek | 2023 | Sport court surfacing |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 11000 | 11000 | 0 |  | Completed
Collin Creek | 2023 | Gym hallway & Restrooms | Paint Toilets/fixtures New cove base Base | 1100- Specialties, Equipment & Furnishings | GC | Project | 8000 | 8000 | 0 |  | Completed
Collin Creek | 2023 | Electrical distribution |  | 1600 - Electrical | GC | Project | 6000 | 6000 | 0 |  | Completed
Collin Creek | 2023 | Common area light fixtures |  | 1600 - Electrical | GC | Project | 29000 | 29000 | 0 |  | Completed
Collin Creek | 2023 | Replace breezeway lights |  | 1600 - Electrical | GC | Project | 26000 | 26000 | 0 |  | Completed
Collin Creek | 2023 | Contingency- Deferred Maintenance |  | Contingency | Unmarked | Contingency | 290000 | 0 | 290000 |  | Reserve
Collin Creek | 2023 | Contingency- Amenities |  | Contingency | Unmarked | Contingency | 104542 | 0 | 104542 |  | Reserve
Collin Creek | 2023 | Contingency- Unit Upgrades |  | Contingency | PMC | Contingency | 610000 | 0 | 610000 |  | Reserve
Las Colinas Heights | 2023 | Storm sewer piping | clear storm drains, repair drains around pool two, clean and service lift pumps, install drainage is sub-terrain units | 0200 - Site Utilities & Improvements | GC | Project | 225000 | 225000 | 0 |  | Completed
Las Colinas Heights | 2023 | Concrete pavement | Repair concrete drive From PCA- $3,750- Isolated sections of the concrete pavement were observed to be cracked, settled, | 0200 - Site Utilities & Improvements | GC | Project | 94000 | 94000 | 0 |  | Completed
Las Colinas Heights | 2023 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Project | 14000 | 14000 | 0 |  | Completed
Las Colinas Heights | 2023 | Parking equipment | add parking stops by fencing | 0200 - Site Utilities & Improvements | GC | Project | 22000 | 22000 | 0 |  | Completed
Las Colinas Heights | 2023 | ADA parking & curb cuts | add proper signage | 0200 - Site Utilities & Improvements | GC | Project | 5600 | 5600 | 0 |  | Completed
Las Colinas Heights | 2023 | Curbs & gutters | Sections of the concrete curbing were noted to be chipped, spalled, and damaged. Such sections were noted by the mainten | 0200 - Site Utilities & Improvements | GC | Project | 1500 | 1500 | 0 |  | Completed
Las Colinas Heights | 2023 | Sidewalks | replace missing expansion boards in sidewalks From PCA- $7,000- Several of the Subject's concrete sidewalk sections hav | 0200 - Site Utilities & Improvements | GC | Project | 75000 | 75000 | 0 |  | Completed
Las Colinas Heights | 2023 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Project | 45000 | 45000 | 0 |  | Completed
Las Colinas Heights | 2023 | Erosion control | add dirt around each building | 0200 - Site Utilities & Improvements | GC | Project | 60000 | 60000 | 0 |  | Completed
Las Colinas Heights | 2023 | Fences & gates - site perimeter | Repair fence, columns and paint From PCA- $1,000- The concrete fencing on the southwest side was observed to be damaged | 0200 - Site Utilities & Improvements | GC | Project | 51300 | 51300 | 0 |  | Completed
Las Colinas Heights | 2023 | Fences & gates - site perimeter | Fix Entrance Gates & Access Control | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
Las Colinas Heights | 2023 | Access Control | Need more fobs, repair hardware & need software to program | 0200 - Site Utilities & Improvements | GC | Project | 5000 | 5000 | 0 |  | Completed
Las Colinas Heights | 2023 | Retaining walls | repair cracks in retaining walls From PCA- $1,000- The retaining walls are in generally good condition, but there are se | 0200 - Site Utilities & Improvements | GC | Project | 35600 | 35600 | 0 |  | Completed
Las Colinas Heights | 2023 | Landscaping | Tree trim | 0200 - Site Utilities & Improvements | GC | Project | 42000 | 42000 | 0 |  | Completed
Las Colinas Heights | 2023 | Resurface swimming pool | resurface two of four pools | 0200 - Site Utilities & Improvements | GC | Project | 61000 | 61000 | 0 |  | Completed
Las Colinas Heights | 2023 | Replace swimming pool coping | replace deck-o-seal on four pools | 0200 - Site Utilities & Improvements | GC | Project | 25000 | 25000 | 0 |  | Completed
Las Colinas Heights | 2023 | Replace swimming pool deck | Remove and replace pool deck on two of four pools add missing expansion boards on remaining two pools | 0200 - Site Utilities & Improvements | GC | Project | 160000 | 160000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair / replace swimming pool pumps | inspect and repair/replace pool pumps | 0200 - Site Utilities & Improvements | GC | Project | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Fences & gates - swimming pool | Repair Pool fence and paint | 0200 - Site Utilities & Improvements | GC | Project | 24000 | 24000 | 0 |  | Completed
Las Colinas Heights | 2023 | Pool Area repairs | From PCA- $7,000- The walls and ceilings of the swimming pool equipment rooms were observed to be damaged. The restrooms | 0200 - Site Utilities & Improvements | GC | Project | 7000 | 7000 | 0 |  | Completed
Las Colinas Heights | 2023 | WDO Treatment | From PCA- Subsequent to the Site Visit a WDO inspection was conducted by Terminix Commercial on 2/3/23. Evidence of acti | 0200 - Site Utilities & Improvements | PMC | Project | 51112 | 15586 | 35526 |  | In Progress
Las Colinas Heights | 2023 | Dumpster enclosures | Repair Dumpsters and paint | 0200 - Site Utilities & Improvements | GC | Project | 19800 | 19800 | 0 |  | Completed
Las Colinas Heights | 2023 | Carports / Garages | repair Car ports From PCA- $750- The metal carport by building #12 was observed to be damaged. | 0200 - Site Utilities & Improvements | GC | Project | 36000 | 36000 | 0 |  | Completed
Las Colinas Heights | 2023 | Las Colinas Association Estoppel Repairs | See list on separate tab | 0200 - Site Utilities & Improvements | GC | Project | 330550 | 330550 | 0 |  | Completed
Las Colinas Heights | 2023 | Creek | Clean, and service fountain's in creek | 0200 - Site Utilities & Improvements | GC | Project | 100000 | 100000 | 0 |  | Completed
Las Colinas Heights | 2023 | Jack & underpin foundations | Buildings 5,11,14,21,19,36,24,6,9,13,19,26 From PCA- $5,000- The foundation exhibits settlement/step cracking in the ext | 0300 - Excavation & Foundations | GC | Project | 199985 | 199985 | 0 |  | Completed
Las Colinas Heights | 2023 | Concrete deck / floor fill | fill cracks in breezeways | 0400 - Structure | GC | Project | 29000 | 29000 | 0 |  | Completed
Las Colinas Heights | 2023 | Roof pad |  | 0400 - Structure | GC | Project | 20000 | 20000 | 0 |  | Completed
Las Colinas Heights | 2023 | Roof framing |  | 0400 - Structure | GC | Project | 12000 | 12000 | 0 |  | Completed
Las Colinas Heights | 2023 | Roof deck | replace decking and underlayment on roofs | 0400 - Structure | GC | Project | 17500 | 17500 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair exterior stair treads and stringers |  | 0400 - Structure | GC | Project | 29000 | 29000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair exterior stair railings |  | 0400 - Structure | GC | Project | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair balcony framing & decking | repair 5 balconies | 0400 - Structure | GC | Project | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair patio/balcony railings | secure all railings | 0400 - Structure | GC | Project | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Tile roofing | remove and reset or replace clay tiles on 30 buildings | 0700 - Roofing | GC | Project | 65000 | 65000 | 0 |  | Completed
Las Colinas Heights | 2023 | Gutters & downspouts | clean and repin From PCA- $2,000- some of the metal gutters and the metal leaders of building #26 were observed to be d | 0700 - Roofing | GC | Project | 29000 | 29000 | 0 |  | Completed
Las Colinas Heights | 2023 | Flashing | replace rotted flashing on doghouse meter rooms | 0700 - Roofing | GC | Project | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Project | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Soffit repairs | repair damaged soffits | 0800 - Exterior Wall | GC | Project | 29000 | 29000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair stucco | repair cracked stucco | 0800 - Exterior Wall | GC | Project | 45000 | 45000 | 0 |  | Completed
Las Colinas Heights | 2023 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Project | 595000 | 595000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair / replace wood trim | From PCA- $1,000- The wood siding at buildings #10 and #12 was observed to be damaged. | 0800 - Exterior Wall | GC | Project | 45000 | 45000 | 0 |  | Completed
Las Colinas Heights | 2023 | Platinum upgrades |  | 0900 - FF&E in Units | PMC | Project | 650000 | 886629 | -236629 |  | Completed
Las Colinas Heights | 2023 | PFC Units |  | 0900 - FF&E in Units | PMC | Project | 1600000 | 0 | 1600000 |  | Not Started
Las Colinas Heights | 2023 | Repair Leaking at Unit Interiors | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 676 - evidence of a major lea | 0900 - FF&E in Units | PMC | Project | 8500 | 56593 | -48093 |  | Completed
Las Colinas Heights | 2023 | Fix Broken handrail in Unit 4425 | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 4425 - Handrail is broken and | 0900 - FF&E in Units | PMC | Project | 500 | 0 | 500 |  | Not Started
Las Colinas Heights | 2023 | Remove interior mold | From PCA- $2,000- CBRE observed conspicuous mold growth in the areas identified as walls and ceiling of the living room | 0900 - FF&E in Units | PMC | Project | 2000 | 13316 | -11316 |  | Completed
Las Colinas Heights | 2023 | Remove Interior Mold in Unit 3951 | From PCA- $1,000- Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 3951 - majo | 0900 - FF&E in Units | PMC | Project | 1000 | 6658 | -5658 |  | Completed
Las Colinas Heights | 2023 | Down Units | From PCA- $10,000- At the time of the site visit, 1 down unit (unit #4335) was observed due to subflooring damage accord | 0900 - FF&E in Units | GC | Project | 10000 | 10000 | 0 |  | Completed
Las Colinas Heights | 2023 | Dryer Vents | Clean dryer vents | 0900 - FF&E in Units | GC | Project | 23175 | 23175 | 0 |  | Completed
Las Colinas Heights | 2023 | Range Queen | Fire stops | 0900 - FF&E in Units | GC | Project | 50985 | 50985 | 0 |  | Completed
Las Colinas Heights | 2023 | Install GFCI outlet in wet areas | From PCA- $11,750- 50% of the bathrooms of 2-bedroom units had Non-GFCI outlets. | 0900 - FF&E in Units | GC | Project | 17625 | 17625 | 0 |  | Completed
Las Colinas Heights | 2023 | Clubhouse / Office Remodel | repair and stain office catwalk balcony | 1100- Specialties, Equipment & Furnishings | GC | Project | 12000 | 12000 | 0 |  | Completed
Las Colinas Heights | 2023 | Clubhouse Renovation | Hide cabling Look at replacing hexagonal mirrored tile on walls Kitchen upgrades? | 1100- Specialties, Equipment & Furnishings | PMC | Project | 25000 | 1720 | 23280 |  | In Progress
Las Colinas Heights | 2023 | Clubhouse Furniture |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 40000 | 2946 | 37054 |  | In Progress
Las Colinas Heights | 2023 | Audio systems |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 30000 | 0 | 30000 |  | Not Started
Las Colinas Heights | 2023 | Fitness Equipment |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 50000 | 50321 | -321 |  | Completed
Las Colinas Heights | 2023 | Pool furniture | To include installation of cabanas | 1100- Specialties, Equipment & Furnishings | PMC | Project | 40000 | 0 | 40000 |  | Not Started
Las Colinas Heights | 2023 | Pool area amenities- 2 pools |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 100000 | 4808 | 95192 |  | In Progress
Las Colinas Heights | 2023 | Fitness center renovation | New flooring- rubber or epoxy | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 20000 | 0 |  | Completed
Las Colinas Heights | 2023 | Plumbing- General | 6 buildings with leaks | 1400 - Plumbing | GC | Project | 30000 | 30000 | 0 |  | Completed
Las Colinas Heights | 2023 | Electrical distribution | From PCA- $1,000- The Electrical Panel in the swimming pool equipment by the leasing office was observed to be without c | 1600 - Electrical | GC | Project | 5200 | 5200 | 0 |  | Completed
Las Colinas Heights | 2023 | Switchgear/metering | From PCA- $700- The Electrical Panels in the swimming pool equipment by the leasing office and in the electrical room of | 1600 - Electrical | GC | Project | 700 | 700 | 0 |  | Completed
Las Colinas Heights | 2023 | Fix/ test the fire riser | From PCA- $2,000- The fire sprinkler riser in building #10 has a red inspection tag. | 1600 - Electrical | GC | Project | 2000 | 2000 | 0 |  | Completed
Las Colinas Heights | 2023 | Fix the fire alarm panel | From PCA- $1,000- A trouble indicator light was noted at the fire alarm panel of building #5. | 1600 - Electrical | GC | Project | 1000 | 1000 | 0 |  | Completed
Las Colinas Heights | 2023 | Install CO Detector | From PCA- $12,950- Carbon Monoxide detectors were not observed as required. | 1600 - Electrical | GC | Project | 23310 | 23310 | 0 |  | Completed
Las Colinas Heights | 2023 | Fire suppression | From PCA- $2,000- No fire extinguishers were observed in any visited units. | 1600 - Electrical | GC | Project | 2500 | 2500 | 0 |  | Completed
Las Colinas Heights | 2023 | Common area light fixtures | Change all 8 ft pole lights to LED | 1600 - Electrical | GC | Project | 36000 | 36000 | 0 |  | Completed
Las Colinas Heights | 2023 | Replace breezeway lights | change breezeway lights to LED | 1600 - Electrical | GC | Project | 42000 | 42000 | 0 |  | Completed
Las Colinas Heights | 2023 | Contingency- Other |  | Contingency | Unmarked | Contingency | 162465 | 0 | 162465 |  | Reserve
Oak Forest | 2023 | Storm sewer piping | clean out storm drain boxes | 0200 - Site Utilities & Improvements | GC | Project | 14000 | 14000 | 0 |  | Completed
Oak Forest | 2023 | Concrete pavement | repair pot holes and broken sidewalks | 0200 - Site Utilities & Improvements | GC | Project | 62000 | 62000 | 0 |  | Completed
Oak Forest | 2023 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Project | 14000 | 14000 | 0 |  | Completed
Oak Forest | 2023 | ADA parking & curb cuts |  | 0200 - Site Utilities & Improvements | GC | Project | 6500 | 6500 | 0 |  | Completed
Oak Forest | 2023 | Sidewalks | From PCA- $5,000- The concrete sidewalks and flatwork were observed to be in overall fair to good condition. Blackstone | 0200 - Site Utilities & Improvements | GC | Project | 24000 | 24000 | 0 |  | Completed
Oak Forest | 2023 | Landscape irrigation | Inspect and repair irrigation. From PCA- $34,000- The landscaping and irrigation systems appeared to be in fair to ave | 0200 - Site Utilities & Improvements | GC | Project | 34000 | 34000 | 0 |  | Completed
Oak Forest | 2023 | Erosion control | From PCA- $25,500- Management reported erosion repairs in 2022, and Blackstone observed new rock groundcover at several | 0200 - Site Utilities & Improvements | GC | Project | 31000 | 31000 | 0 |  | Completed
Oak Forest | 2023 | Fences & gates - site perimeter | Repair and paint wooden fence and replace sections of damaged metal fence, Repair gate operators and ped gate closers | 0200 - Site Utilities & Improvements | GC | Project | 185000 | 185000 | 0 |  | Completed
Oak Forest | 2023 | Retaining walls | Tuck Point retaining walls From PCA- $5,000- Blackstone observed cracking and/or missing stone components at retaining w | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
Oak Forest | 2023 | Landscaping | Trim Trees and remove dead bushes | 0200 - Site Utilities & Improvements | GC | Project | 85000 | 85000 | 0 |  | Completed
Oak Forest | 2023 | Resurface swimming pool | Resurface three pools with pebble tech plaster | 0200 - Site Utilities & Improvements | GC | Project | 81000 | 81000 | 0 |  | Completed
Oak Forest | 2023 | Replace swimming pool coping | Replace deck-o-seal on pools | 0200 - Site Utilities & Improvements | GC | Project | 21000 | 21000 | 0 |  | Completed
Oak Forest | 2023 | Fences & gates - swimming pool | Repair and paint pool fences | 0200 - Site Utilities & Improvements | GC | Project | 16000 | 16000 | 0 |  | Completed
Oak Forest | 2023 | Pergola | repair and stain all pergolas | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
Oak Forest | 2023 | Playground equipment | Replace Fall zone in play ground | 0200 - Site Utilities & Improvements | GC | Project | 14000 | 14000 | 0 |  | Completed
Oak Forest | 2023 | Picnic areas | replace 8 grills | 0200 - Site Utilities & Improvements | GC | Project | 31000 | 31000 | 0 |  | Completed
Oak Forest | 2023 | Carport and garage | Repair carport damage | 0200 - Site Utilities & Improvements | GC | Project | 39000 | 39000 | 0 |  | Completed
Oak Forest | 2023 | Dumpster enclosures | Repair dumpster enclosures | 0200 - Site Utilities & Improvements | GC | Project | 15000 | 15000 | 0 |  | Completed
Oak Forest | 2023 | Wall framing | Replace damaged gable vents and balcony structure | 0400 - Structure | GC | Project | 62000 | 62000 | 0 |  | Completed
Oak Forest | 2023 | Roof deck | replace bad decking on roofs | 0400 - Structure | GC | Project | 10000 | 10000 | 0 |  | Completed
Oak Forest | 2023 | Repair exterior stair railings | secure railings | 0400 - Structure | GC | Project | 8300 | 8300 | 0 |  | Completed
Oak Forest | 2023 | Repair balcony framing & decking | repair balcony band boards | 0400 - Structure | GC | Project | 18000 | 18000 | 0 |  | Completed
Oak Forest | 2023 | Repair patio/balcony railings | secure railings | 0400 - Structure | GC | Project | 8300 | 8300 | 0 |  | Completed
Oak Forest | 2023 | Repair catwalks | clean and seal expansion joints | 0400 - Structure | GC | Project | 14000 | 14000 | 0 |  | Completed
Oak Forest | 2023 | Asphalt composite shingle roofing | minor roof repairs | 0700 - Roofing | GC | Project | 38000 | 38000 | 0 |  | Completed
Oak Forest | 2023 | Gutters & downspouts | Clean down spouts and gutters | 0700 - Roofing | GC | Project | 38000 | 38000 | 0 |  | Completed
Oak Forest | 2023 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Project | 18000 | 18000 | 0 |  | Completed
Oak Forest | 2023 | Repair / replace wood siding | repair damaged siding | 0800 - Exterior Wall | GC | Project | 12000 | 12000 | 0 |  | Completed
Oak Forest | 2023 | Dryer Vents | Clean dryer vents ($45@) & Vent cover replacements as needed ($3000) | 0800 - Exterior Wall | GC | Project | 34000 | 34000 | 0 |  | Completed
Oak Forest | 2023 | Tuck-pointing |  | 0800 - Exterior Wall | GC | Project | 12000 | 12000 | 0 |  | Completed
Oak Forest | 2023 | Repair stucco |  | 0800 - Exterior Wall | GC | Project | 38000 | 38000 | 0 |  | Completed
Oak Forest | 2023 | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | 0800 - Exterior Wall | GC | Project | 32000 | 32000 | 0 |  | Completed
Oak Forest | 2023 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Project | 686000 | 686000 | 0 |  | Completed
Oak Forest | 2023 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Project | 48000 | 48000 | 0 |  | Completed
Oak Forest | 2023 | Mold remediation | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan c | 0900 - FF&E in Units | GC | Project | 2000 | 2000 | 0 |  | Completed
Oak Forest | 2023 | Radon Mitigation Systems: | Lender Mandate- In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the | 0900 - FF&E in Units | PMC | Project | 10500 | 0 | 10500 |  | Not Started
Oak Forest | 2023 | Range Queen | Fire stops | 0900 - FF&E in Units | GC | Project | 66120 | 66120 | 0 |  | Completed
Oak Forest | 2023 | Washer/dryer |  | 0900 - FF&E in Units | PMC | Project | 130000 | 0 | 130000 |  | Not Started
Oak Forest | 2023 | Clubhouse / Office Remodel | Paint accent walls Create built in desk/counter Add glass wall and door to back right office for tenant discussions | 1100- Specialties, Equipment & Furnishings | GC | Project | 50000 | 50000 | 0 |  | Completed
Oak Forest | 2023 | Clubhouse / Office Redecorate (FFE) | New clubhouse furniture | 1100- Specialties, Equipment & Furnishings | PMC | Project | 80000 | 59297 | 20703 |  | In Progress
Oak Forest | 2023 | Video systems |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 250000 | 40715 | 209285 |  | In Progress
Oak Forest | 2023 | Fitness Equipment |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 30000 | 42136 | -12136 |  | Completed
Oak Forest | 2023 | Pool furniture- Office Pool | New furniture for office pool area only, repurpose existing good furniture to other 2 pools | 1100- Specialties, Equipment & Furnishings | PMC | Project | 30000 | 49605 | -19605 |  | Completed
Oak Forest | 2023 | Pool area enhancements | Address pool inspection items, upgraded pool deck | 1100- Specialties, Equipment & Furnishings | PMC | Project | 80000 | 23295 | 56705 |  | In Progress
Oak Forest | 2023 | Pool area enhancements | Activities, turf, etc | 1100- Specialties, Equipment & Furnishings | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Oak Forest | 2023 | Fitness center renovation | Close 2-3 wall openings between gym and bathroom hallway | 1100- Specialties, Equipment & Furnishings | GC | Project | 5000 | 5000 | 0 |  | Completed
Oak Forest | 2023 | Fitness center adjacent restroom upgrades | Repair/replace partitions, touch up paint and base | 1100- Specialties, Equipment & Furnishings | GC | Project | 5000 | 5000 | 0 |  | Completed
Oak Forest | 2023 | Fire and Sprinklers | replace painted heads in units From PCA- $68,000- The fire and life safety system appeared to be in overall fair to ave | 1600 - Electrical | GC | Project | 68000 | 68000 | 0 |  | Completed
Oak Forest | 2023 | Contingency- Deferred Maintenance |  | Contingency | Unmarked | Contingency | 466000 | 0 | 466000 |  | Reserve
Oak Forest | 2023 | Contingency- Amenities |  | Contingency | Unmarked | Contingency | 100000 | 0 | 100000 |  | Reserve
Oak Forest | 2023 | Contingency- Unit Upgrades |  | Contingency | Unmarked | Contingency | 2784000 | 0 | 2784000 |  | Reserve
Oak Forest | 2023 | Contingency- Other |  | Contingency | Unmarked | Contingency | 996280 | 0 | 996280 |  | Reserve
Oak Park | 2023 | Club House/Leasing Center Addition/Alteration | Need to replace front door to meet ADA 10k. 20k per post PNA to replace some other doors and update bathroom | Admin/Marketing | Unmarked | Project | 35000 | 38925 | -3925 |  | Completed
Oak Park | 2023 | Computers | do we need computer? | Admin/Marketing | Unmarked | Project | 10000 | 1985 | 8015 |  | In Progress
Oak Park | 2023 | Fitness Center & Equipment | Site has new equipment and new floors room has repair needs and still needs paint,Add TVs lights/fans water despenser 15 | Admin/Marketing | Unmarked | Project | 28000 | 8979 | 19021 |  | In Progress
Oak Park | 2023 | Model Furniture/Finishes | model furniture discussed 15k spaceholder | Admin/Marketing | Unmarked | Project | 20000 | 7163 | 12837 |  | In Progress
Oak Park | 2023 | Monument Sign | Monument looked good. All building signage looks old and drab. Space holder 15k to replace bldg signs at $85ea | Admin/Marketing | Unmarked | Project | 8300 | 2042 | 6258 |  | In Progress
Oak Park | 2023 | Office Furniture/Finishes | Refresh on furnitre per Post | Admin/Marketing | Unmarked | Project | 85000 | 6260 | 78740 |  | In Progress
Oak Park | 2023 | Vehicles/Carts | Have 3 working maint, 1 leasing, budgeting for 2 gators, 1 leasing and 1 maintenance (used) | Admin/Marketing | Unmarked | Project | 48000 | 125664 | -77664 |  | Completed
Oak Park | 2023 | Common Corridors Rehab | Power wash breezeways - has valet waste | Common Area | Unmarked | Project | 50000 | 0 | 50000 |  | Not Started
Oak Park | 2023 | Laundry Center | Has two laundry center need to refresh both 5k ea. | Common Area | Unmarked | Project | 10000 | 5620 | 4380 |  | In Progress
Oak Park | 2023 | Mailboxes | Wish list item from PM, new mail boxes there are 7 mail rooms, Budgteing for 2 replacements 55k. And some in out yrs. A | Common Area | Unmarked | Project | 50000 | 0 | 50000 |  | Not Started
Oak Park | 2023 | Pool Area Repairs & Equipment | Replaster both pools at leasing offfice pool, refresh grill/pergola area, and repair expansion joints on deck replace gr | Common Area | Unmarked | Project | 342164 | 454979 | -112815 |  | Completed
Oak Park | 2023 | Pool Furniture/Finishes | Pool furniture needed at leasing pool- space holder 25k | Common Area | Unmarked | Project | 45000 | 58118 | -13118 |  | Completed
Oak Park | 2023 | Asphalt Milling/Paving/Sealcoat | Restripe some areas in Y1. Y2 fix major potholes and restripe after | Exterior Building & Site Work | Unmarked | Project | 243500 | 105364 | 138136 |  | In Progress
Oak Park | 2023 | Balconies | Rebuild 12 balconies called out by gc $68k. Pick and pull other balcony and land structural members including replacemen | Exterior Building & Site Work | Unmarked | Project | 243600 | 148350 | 95250 |  | In Progress
Oak Park | 2023 | Brick Repair/Point-Up | Per bid from Norman. | Exterior Building & Site Work | Unmarked | Project | 15000 | 310 | 14690 |  | In Progress
Oak Park | 2023 | Concrete Curb/Sidewalk | Sidewalk repairs and grinding 49k per bid from Sunland. Per Post PNA -ADA acess to common areas 16k. Includes $5k in le | Exterior Building & Site Work | Unmarked | Project | 95000 | 750 | 94250 |  | In Progress
Oak Park | 2023 | Controlled Access Systems | Site uses Gate Wise Need to check Mo. Operating cost Call box is Linear and does not work and needs replaced. Also sev | Exterior Building & Site Work | Unmarked | Project | 90000 | 20147 | 69853 |  | In Progress
Oak Park | 2023 | Covered Parking & Misc Parking Items | Repair handful of carports in Y1, and then 1 or 2 a year in outyears. | Exterior Building & Site Work | Unmarked | Project | 55000 | 57741 | -2741 |  | Completed
Oak Park | 2023 | Dog Park | Ali numbers are high ($9K for refresh + $35K for new dogpark). FCP believes they can do add new park for $15K and refres | Exterior Building & Site Work | Unmarked | Project | 20000 | 34842 | -14842 |  | Completed
Oak Park | 2023 | Dumpster Enclosures | Per bid from Norman. Repair and stain dumpster enclosures | Exterior Building & Site Work | Unmarked | Project | 32000 | 7966 | 24034 |  | In Progress
Oak Park | 2023 | Erosion Control/Drainage | Repair drainage and add swell back side bldgs. 11-13 $11k. Clean out and test all french drains through out property $15 | Exterior Building & Site Work | Unmarked | Project | 89000 | 101269 | -12269 |  | Completed
Oak Park | 2023 | Exterior Doors (Other) | Replace Misc mech rm doors | Exterior Building & Site Work | Unmarked | Project | 5000 | 10036 | -5036 |  | Completed
Oak Park | 2023 | Exterior Lighting | Replace all metal halo building lights and fix 25% of carport lights | Exterior Building & Site Work | Unmarked | Project | 198710 | 143010 | 55700 |  | In Progress
Oak Park | 2023 | Exterior Paint, Carpentry & Misc Repairs | Bldg. paint looks to be in good shape. Last painted 2017. Need to paint all metal except doors yr1 $201k. Pick and pull | Exterior Building & Site Work | Unmarked | Project | 1059500 | 938581 | 120919 |  | In Progress
Oak Park | 2023 | Exterior Stairs | ~20% of switch backs on ph2 were replaced. Additional needing replacement. Rebuild 6 SWB landing 60k per Crest. 10k for | Exterior Building & Site Work | Unmarked | Project | 60000 | 49795 | 10205 |  | In Progress
Oak Park | 2023 | Fireplace & Flue | 95/ unit, need to confirm FP count 608 budgeted | Exterior Building & Site Work | Unmarked | Project | 173280 | 34688 | 138592 |  | In Progress
Oak Park | 2023 | Foundations & Site Grading | Install Exterior peirs buildings 1,8,6.24 Watch list 2,13,15,26,31 | Exterior Building & Site Work | Unmarked | Project | 92000 | 0 | 92000 |  | Not Started
Oak Park | 2023 | General Site Fencing | Repair wood perim fencing. Replace middle pool fencing for $24.5K | Exterior Building & Site Work | Unmarked | Project | 74500 | 124690 | -50190 |  | Completed
Oak Park | 2023 | Grill Station | Refresh of pool grilling areas including replacement of grills included line 24. Removal of gazebo on line 94.This is t | Exterior Building & Site Work | Unmarked | Project | 40000 | 109552 | -69552 |  | Completed
Oak Park | 2023 | Gutters & Downspouts | Gutter tune up($23k) and add Raindrop gutter guard($131k)to prevent future damage or maintance needs | Exterior Building & Site Work | Unmarked | Project | 63000 | 35600 | 27400 |  | In Progress
Oak Park | 2023 | Handrail/Railings | Fixing balcony handrails and misc metal fencing repairs | Exterior Building & Site Work | Unmarked | Project | 76000 | 55360 | 20640 |  | In Progress
Oak Park | 2023 | Concrete Steps - Handrails | Lender mandate- Blackstone observed concrete steps with four or more risers and no handrails at Buildings 9 and 14. Blac | Exterior Building & Site Work | Unmarked | Project | 3000 | 0 | 3000 |  | Not Started
Oak Park | 2023 | Irrigation | Per Superior Edge evaluated system and found 10k in repairs. Per bid. Includes $34k in lender mandates- The landscaping | Exterior Building & Site Work | Unmarked | Project | 10000 | 29287 | -19287 |  | Completed
Oak Park | 2023 | Landscape Enhancements | Updgrade front curb appeal, office, pools, and entry drive fence line | Exterior Building & Site Work | Unmarked | Project | 50000 | 143923 | -93923 |  | Completed
Oak Park | 2023 | Patio Doors/Sliders | replace 5 sliders per yr | Exterior Building & Site Work | Unmarked | Project | 77000 | 85 | 76915 |  | In Progress
Oak Park | 2023 | Playground & Site Furniture | Top off existing playground. 5k. See line 53 for new playground on Sport court. | Exterior Building & Site Work | Unmarked | Project | 5000 | 7250 | -2250 |  | Completed
Oak Park | 2023 | Retaining Walls | general tuck point repairs to retaining walls Includes $5k in lender mandates- Blackstone observed cracking and/or miss | Exterior Building & Site Work | Unmarked | Project | 52000 | 41380 | 10620 |  | In Progress
Oak Park | 2023 | Roof Replacements/Repairs | Roof PM needed on all bldgs- PM also includes fix dryer vent termination on roof, repair busted roof trust in attics- PH | Exterior Building & Site Work | Unmarked | Project | 156000 | 231180 | -75180 |  | Completed
Oak Park | 2023 | Sports Court | See sports court taband add $25K for iron fence between soccer field and social area | Exterior Building & Site Work | Unmarked | Project | 227000 | 514328 | -287328 |  | Completed
Oak Park | 2023 | Storm Water Management/Retention Ponds | Maintain storm drains | Exterior Building & Site Work | Unmarked | Project | 40000 | 17205 | 22795 |  | In Progress
Oak Park | 2023 | Tree/Plant Removal | Cut life safety trees for $60K. All trees removed are bid to be replaced w/ sod. Class B trim and removal of dead limbs | Exterior Building & Site Work | Unmarked | Project | 202000 | 223962 | -21962 |  | Completed
Oak Park | 2023 | Windows | As needed replacements. Single pain windows | Exterior Building & Site Work | Unmarked | Project | 35000 | 14100 | 20900 |  | In Progress
Oak Park | 2023 | Vacant Unit Deferred Maintenance |  | Interior Units | Unmarked | Project | 500000 | 117730 | 382270 |  | In Progress
Oak Park | 2023 | Washers/Dryers |  | Interior Units | Unmarked | Project | 123000 | 0 | 123000 |  | Not Started
Oak Park | 2023 | Apparent Mold Growth - Unit 110 | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan c | Interior Units | Unmarked | Project | 2000 | 38 | 1962 |  | In Progress
Oak Park | 2023 | CO/Smoke Detectors | Verify if we need CO detectors for code. 471 have smoke detectors. $35 / unit | MEP | Unmarked | Project | 16450 | 21264 | -4814 |  | Completed
Oak Park | 2023 | Domestic Water Boilers/Heat Exchangers & Related Work | Replace boiler 1 near building 14, 48.3k PM other 2 boilers 7k Bid from SRT | MEP | Unmarked | Project | 85300 | 93981 | -8681 |  | Completed
Oak Park | 2023 | Domestic Water Heaters | As needed replacements on PH2&3 review unit walks | MEP | Unmarked | Project | 105000 | 4620 | 100380 |  | In Progress
Oak Park | 2023 | Drain Clean/Jet Lines/Video | Scrape and clean cast iron sewers in ph1&2 19k. Hyrdo jet all of Ph3 2k | MEP | Unmarked | Project | 67000 | 42606 | 24394 |  | In Progress
Oak Park | 2023 | Fire Extinguishers | missing or dischaged 5lb fire extinguisher. | MEP | Unmarked | Project | 16650 | 233339 | -216689 |  | Completed
Oak Park | 2023 | Fire Life Safety Work | Ph3 only PM Riser closets 5k. Panels are still using pots lines to communicate, recommend canceling these to save mone | MEP | Unmarked | Project | 10000 | 41243 | -31243 |  | Completed
Oak Park | 2023 | Fire Safety Systems | The fire and life safety system appeared to be in overall fair to average condition. The AFSS risers were last inspected | MEP | Unmarked | Project | 68000 | 5711 | 62289 |  | In Progress
Oak Park | 2023 | HVAC Equipment (HVAC FULL NEW REPLACEMENT) | Based on eval from SRT there are 368 R22/Mixed refrigerant systems. Researching run rates for MT and AW I came up with a | MEP | Unmarked | Project | 646160 | 639431 | 6729 |  | In Progress
Oak Park | 2023 | HVAC PM | Dryer vent cleaning 75/unit $45k. Replace dryer vents 65 ea. PM all a/c units $120k this include pm service and some par | MEP | Unmarked | Project | 341470 | 110179 | 231291 |  | In Progress
Oak Park | 2023 | Panel Replacement/GFCI | PH2 has Zinsco panels in all units. Need to replace breakers $346k. Per bid from Shields Electrical Services. 296 units | MEP | Unmarked | Project | 346005 | 383245 | -37240 |  | Completed
Oak Park | 2023 | PM/Clean Meter Stack | Repalced main meter panels as needed through out hold | MEP | Unmarked | Project | 35000 | 0 | 35000 |  | Not Started
Oak Park | 2023 | Sewer Systems | Repairs sewer blockages and breaks. bldgs1,2,4,5,6,7,10,12,13,14,15,16,21,26 Bid from SRT. Also researched run rates on | MEP | Unmarked | Project | 253000 | 2334 | 250666 |  | In Progress
Oak Park | 2023 | Sprinkler Systems | Ph 3 dry heads due for10yr UL testing next yr. if replacement needed after testing 800 ea including SRR @64k waiting met | MEP | Unmarked | Project | 76000 | 0 | 76000 |  | Not Started
Oak Park | 2023 | Water Piping & Plumbing | Replace (27 pairs) building valves that are barried, rusted, and don’t work $46k. unit 516 had an external repipe that n | MEP | Unmarked | Project | 401000 | 198926 | 202074 |  | In Progress
Oak Park | 2023 | Wiring | Wiring PM/Cleanup throughout property includes securing meter banks | MEP | Unmarked | Project | 20000 | 21812 | -1812 |  | Completed
Oak Park | 2023 | Environmental - Asbestos Abatement | For as needed abatement Ph1 only | Miscellaneous | Unmarked | Project | 210000 | 122414 | 87586 |  | In Progress
Oak Park | 2023 | Environmental - Pest Control Extermination | Waiting on bid for treatment. 35/unit space holder and 15k spaceholder for termite | Miscellaneous | Unmarked | Project | 21295 | 48447 | -27152 |  | Completed
Oak Park | 2023 | Lead Paint/Radon Remediation | To maintain paint on all ph1 balcony handrails. Yr 1 plan is to paint all railings in the exterior scope. | Miscellaneous | Unmarked | Project | 70000 | 0 | 70000 |  | Not Started
Oak Park | 2023 | Radon Mitigation Systems | In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the subject propert | Miscellaneous | Unmarked | Project | 10500 | 0 | 10500 |  | Not Started
Oak Park | 2023 | Maintenance Shop | Clean up maintence shop and storages | Miscellaneous | Unmarked | Project | 15000 | 0 | 15000 |  | Not Started
Oak Park | 2023 | Structural Repairs | LS Repairs- Fill in potholes in yards 16k.TM to sure up LS balconies includes labor/super/estimated material needed $30k | Miscellaneous | Unmarked | Project | 46000 | 0 | 46000 |  | Not Started
Oak Park | 2023 | Tools/Miscellaneous Equipment | Misc tools | Miscellaneous | Unmarked | Project | 10000 | 37248 | -27248 |  | Completed
Oak Park | 2023 | Video Surveillance System | 19 new cameras replacing NVR and reusing some of existing 35k. 25 cameras and NRV per Post PNA | Miscellaneous | Unmarked | Project | 35150 | 84704 | -49554 |  | Completed
Oak Park | 2023 | Contingency |  | Contingency and Fees | Unmarked | Contingency | 572778 | 0 | 572778 |  | Reserve
Oak Park | 2023 | FCP CM Fees |  | Contingency and Fees | Unmarked | CM Fee | 534592 | 245052 | 289541 |  | Reserve
Sorrento at Tuscan Lakes | 2023 | Concrete pavement | repair pot holes and broken sidewalks | 0200 - Site Utilities & Improvements | GC | Project | 22000 | 22000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Project | 10500 | 10500 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | ADA parking & curb cuts |  | 0200 - Site Utilities & Improvements | GC | Project | 4800 | 4800 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Project | 26000 | 26000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Fences & gates - site perimeter | Remove vegitation from fence repair and Paint | 0200 - Site Utilities & Improvements | GC | Project | 51000 | 51000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Landscaping | Curb appeal is bad and dated (place Holder) | 0200 - Site Utilities & Improvements | GC | Project | 150000 | 150000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Resurface swimming pool | resurface pool | 0200 - Site Utilities & Improvements | GC | Project | 38000 | 38000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Replace swimming pool coping | Replace deck-o-seal on pools | 0200 - Site Utilities & Improvements | GC | Project | 8200 | 8200 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Replace swimming pool deck | Crack Fill and clean | 0200 - Site Utilities & Improvements | GC | Project | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Fences & gates - swimming pool | Repair and paint pool fence | 0200 - Site Utilities & Improvements | GC | Project | 8900 | 8900 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Pergola | repair and stain all pergolas | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Carport and garage | Repair carport damage and paint | 0200 - Site Utilities & Improvements | GC | Project | 39000 | 39000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Dumpster enclosures | Repair dumpster enclosures and paint | 0200 - Site Utilities & Improvements | GC | Project | 15000 | 15000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Roof deck | replace bad decking on roofs | 0400 - Structure | GC | Project | 10000 | 10000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair exterior stair railings | secure railings | 0400 - Structure | GC | Project | 8300 | 8300 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair balcony framing & decking | repair balcony band boards | 0400 - Structure | GC | Project | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair patio/balcony railings | secure railings | 0400 - Structure | GC | Project | 8300 | 8300 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Expansion Joints | clean and seal expansion joints | 0400 - Structure | GC | Project | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Asphalt composite shingle roofing | minor roof repairs | 0700 - Roofing | GC | Project | 15000 | 15000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Gutters & downspouts | Clean down spouts and gutters | 0700 - Roofing | GC | Project | 13000 | 13000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Sealants & caulking | Seal where windows meet stucco | 0700 - Roofing | GC | Project | 18000 | 18000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair / replace cement fiber siding | repair damaged siding | 0800 - Exterior Wall | GC | Project | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Masonry repairs | Presure wash Stone walls | 0800 - Exterior Wall | GC | Project | 18000 | 18000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair stucco |  | 0800 - Exterior Wall | GC | Project | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | 0800 - Exterior Wall | GC | Project | 18000 | 18000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Project | 210000 | 210000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Project | 36000 | 36000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Shutters | Replace bad shutters | 0800 - Exterior Wall | GC | Project | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGc | 683sqft, 1BR 1BA | 0900 - FF&E in Units | GC | Project | 259134 | 259134 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGe | 779sqft, 1BR 1BA | 0900 - FF&E in Units | GC | Project | 162437 | 162437 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGg | 894sqft, 1BR 1BA | 0900 - FF&E in Units | GC | Project | 22726 | 22726 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AZh | 946sqft, 1BR 1BA | 0900 - FF&E in Units | GC | Project | 128310 | 128310 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGl | 1117sqft, 2BR 2BA | 0900 - FF&E in Units | GC | Project | 455418 | 455418 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn | 1259sqft, 2BR 2BA | 0900 - FF&E in Units | GC | Project | 70140 | 70140 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn1 | 1271sqft, 2BR 2BA | 0900 - FF&E in Units | GC | Project | 42546 | 42546 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGo | 1367sqft, 2BR 2BA | 0900 - FF&E in Units | GC | Project | 14646 | 14646 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 3CGo | 1381sqft, 3BR 2BA | 0900 - FF&E in Units | GC | Project | 75687 | 75687 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Ceiling Fans | Add to all living rooms | 0900 - FF&E in Units | GC | Project | 56100 | 56100 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Clubhouse / Office Remodel | New flooring at a minimum, preferably new paint as well Remove window curtains Convert business center counter to booth | 1100- Specialties, Equipment & Furnishings | GC | Project | 90000 | 90000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Clubhouse / Office Redecorate (FFE) | Most or all furniture will need to be replaced, it is very dated | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 90000 | 108179 | -18179 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Model Unit | Allowance for small additions/refresh | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 4000 | 8799 | -4799 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Computers | Not needed, allowance for 1 | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 1500 | 2913 | -1413 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Mailboxes | Package locker or Fetch system needed | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 15000 | 0 | 15000 |  | Not Started
Sorrento at Tuscan Lakes | 2023 | Security Camera System | Need at least for entry drive, clubhouse, and amenity coverage | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 20000 | 7426 | 12574 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Pool Remodel | Allowance, the pool area was in decent shape | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 20000 | 10113 | 9887 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Fitness Equipment | In good shape, allowance for minor equipment repairs & replacements | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 10000 | 4664 | 5336 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Pool furniture | Move furniture from Amalfi, supplement with bistro tables/chairs, sectionals, other seating, cabanas | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 30000 | 12636 | 17364 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Fitness center renovation | Allowance, not much needed | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 10000 | 4664 | 5336 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Golf Cart | Repair & replace battery in old leasing cart from Amalfi | 1100- Specialties, Equipment & Furnishings | Unmarked | Project | 2000 | 1793 | 207 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Dryer Vent cleaning |  | 1500- HVAC | GC | Project | 15300 | 15300 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Electrical distribution | repair electric issues with lights | 1600 - Electrical | GC | Project | 6000 | 6000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Fire and Sprinklers | replace emergency lights | 1600 - Electrical | GC | Project | 9500 | 9500 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Common area light fixtures | Change wall Packs | 1600 - Electrical | GC | Project | 18720 | 18720 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Replace breezeway lights | Change breezeway lights, landscape lights | 1600 - Electrical | GC | Project | 32570 | 32570 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Contingency |  | Contingency & Fees | Unmarked | Contingency | 77226 | 0 | 77226 |  | Reserve
Sorrento at Tuscan Lakes | 2023 | Construction Management Fee |  | Contingency & Fees | Unmarked | CM Fee | 127848 | 0 | 127848 |  | Reserve
The Grand at Hill Street | 2023 | Pavement |  | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Parking Lot | 26 | 0200 - Site Utilities & Improvements | GC | Project | 130000 | 130000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Project | 5000 | 5000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Look at sealing cedar/wood wall partitions |  | 0800 - Exterior Wall | GC | Project | 10000 | 10000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Fire protection | 200 | 0900 - FF&E in Units | GC | Project | 21000 | 21000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Turf Upgrade |  | 0900 - FF&E in Units | GC | Project | 80000 | 80000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Signage - entry |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 40000 | 74976 | -34976 |  | Completed
The Grand at Hill Street | 2023 | Signage - site |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 20000 | 37488 | -17488 |  | Completed
The Grand at Hill Street | 2023 | Clubhouse / Office Remodel |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 3000 | 3000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Clubhouse / Office Remodel |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 40000 | 0 |  | Completed
The Grand at Hill Street | 2023 | ADA compliance |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 50 | 0 | 50 |  | Not Started
The Grand at Hill Street | 2023 | Convert Conference room to package room |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 65000 | 65000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Package Room Conversion |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 10000 | 10000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Dog Park |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 5000 | 5000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Fire Sprinklers |  | 1600 - Electrical | GC | Project | 3000 | 3000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Fire extinguishers |  | 1600 - Electrical | GC | Project | 1000 | 1000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Fire alarms |  | 1600 - Electrical | GC | Project | 3000 | 3000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Landscape irrigation | Irrigation drip line look to be questionable in multiple areas test and repair lines | 0200 - Site Utilities & Improvements | GC | Project | 22000 | 22000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Erosion control | down spouts empty onto river rock drainage, some are short others are long storm water has already caused erosion in so | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Landscaping | the new shrubs look to be struggling to take root, some will need to be replace this summer | 0200 - Site Utilities & Improvements | GC | Project | 25000 | 25000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Fire Stops |  | 0900 - FF&E in Units | GC | Project | 37000 | 37000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Signage - entry | Monument Sign | 1100- Specialties, Equipment & Furnishings | PMC | Project | 30000 | 46414 | -16414 |  | Completed
The Hightone (Allora Denton) | 2023 | Signage - site | Rebrand signage | 1100- Specialties, Equipment & Furnishings | PMC | Project | 20000 | 108353 | -88353 |  | Completed
The Hightone (Allora Denton) | 2023 | Trash Compactor (Determine Upon Stabilization) | Look at adding to reduce trash collection fees | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 40000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Fitness Equipment (Determine Upon Stabilization) | Add rowing machine | 1100- Specialties, Equipment & Furnishings | PMC | Project | 4000 | 237 | 3763 |  | In Progress
The Hightone (Allora Denton) | 2023 | Pool furniture (Determine Upon Stabilization) | Budget for new chaises since all are wicker, Cabanas, umbrellas | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 40000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Carports (Determine Upon Stabilization) | Tenants have requested covered parking, consider as value add | 1100- Specialties, Equipment & Furnishings | GC | Project | 50000 | 50000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Retest and Mitigate as needed |  | Radon | GC | Project | 123000 | 123000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Downspout repairs and gutter installations | Rout downspouts away from the building and onto grass landscaping or concrete sidewalks / pavements to prevent erosion o | Roofing Systems | GC | Project | 68500 | 68500 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 |  | Reconfigure the walkway accessing the western and southwestern dumpster enclosures to provide a 60-inch turning radius P | Fair Housing | GC | Project | 17000 | 17000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Dog Park | Dog Park refresh- sail shades, benches, water station | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Storm sewer piping | add stone around storm drains | 0200 - Site Utilities & Improvements | GC | Project | 6000 | 6000 | 0 |  | Completed
Allora Bella Terra | 2024 | Landscape irrigation | inspect and repair Irrigation | 0200 - Site Utilities & Improvements | GC | Project | 22600 | 22600 | 0 |  | Completed
Allora Bella Terra | 2024 | Fences & gates - site perimeter | Paint perimeter fence | 0200 - Site Utilities & Improvements | GC | Project | 26500 | 26500 | 0 |  | Completed
Allora Bella Terra | 2024 | Landscaping | Add landscaping in planters around pool. Look at hardier fan palms, can be smaller to reduce cost. | 0200 - Site Utilities & Improvements | GC | Project | 50000 | 50000 | 0 |  | Completed
Allora Bella Terra | 2024 | Landscaping- entry & in front of office | PCA- $19,500- Address bare areas throughout property Add seasonal color, add turf where needed | 0200 - Site Utilities & Improvements | GC | Project | 35000 | 35000 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair / replace swimming pool pumps | anti entrapment devices | 0200 - Site Utilities & Improvements | GC | Project | 12800 | 12800 | 0 |  | Completed
Allora Bella Terra | 2024 | Fences & gates - swimming pool | Paint pool fence | 0200 - Site Utilities & Improvements | GC | Project | 6800 | 6800 | 0 |  | Completed
Allora Bella Terra | 2024 | Outdoor Fireplaces | Repair 2 outdoor fireplaces | 0200 - Site Utilities & Improvements | GC | Project | 5000 | 5000 | 0 |  | Completed
Allora Bella Terra | 2024 | Carports / Garages | Repair and paint Garages | 0200 - Site Utilities & Improvements | GC | Project | 22000 | 22000 | 0 |  | Completed
Allora Bella Terra | 2024 | Dumpster enclosures | PCA- $1,500- Repair/replace gate as required Paint enclosure | 0200 - Site Utilities & Improvements | GC | Project | 6500 | 6500 | 0 |  | Completed
Allora Bella Terra | 2024 | Pet yards | paint pet yard fencing | 0200 - Site Utilities & Improvements | GC | Project | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair exterior stair railings | Secure railings | 0400 - Structure | GC | Project | 7500 | 7500 | 0 |  | Completed
Allora Bella Terra | 2024 | Expansion Joints | Seal expansion joints | 0400 - Structure | GC | Project | 7500 | 7500 | 0 |  | Completed
Allora Bella Terra | 2024 | Asphalt composite shingle roofing | Roof inspection and minor repairs | 0700 - Roofing | GC | Project | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Tile roofing | Repairs to clay tile roofs | 0700 - Roofing | GC | Project | 4500 | 4500 | 0 |  | Completed
Allora Bella Terra | 2024 | Flashing | Repair flashing over clay tile | 0700 - Roofing | GC | Project | 4500 | 4500 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair / replace cement fiber siding |  | 0800 - Exterior Wall | GC | Project | 7500 | 7500 | 0 |  | Completed
Allora Bella Terra | 2024 | Interior Hallway painting | Breezeway paint | 0800 - Exterior Wall | GC | Project | 45000 | 45000 | 0 |  | Completed
Allora Bella Terra | 2024 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Project | 345000 | 345000 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair / replace wood trim | minor trim replacement | 0800 - Exterior Wall | GC | Project | 7500 | 7500 | 0 |  | Completed
Allora Bella Terra | 2024 | Flooring | Replace carpet throughout with LVP | 0900 - FF&E in Units | GC | Project | 272700 | 272700 | 0 |  | Completed
Allora Bella Terra | 2024 | Pet yard enclosures | About 10 units we could add yards to | 0900 - FF&E in Units | GC | Project | 58000 | 58000 | 0 |  | Completed
Allora Bella Terra | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 0900 - FF&E in Units | GC | Project | 36338 | 36338 | 0 |  | Completed
Allora Bella Terra | 2024 | Unit deferred maintenance | Painted sprinkler heads (82 total sprinklers observed in 42 units) | 0900 - FF&E in Units | GC | Project | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 1100- Specialties, Equipment & Furnishings | GC | Project | 5000 | 5000 | 0 |  | Completed
Allora Bella Terra | 2024 | Clubhouse / Office Remodel | Iif we are ok with the tuscan, somewhat dated look, there is minimal scope ($10k). | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 40000 | 0 |  | Completed
Allora Bella Terra | 2024 | Clubhouse / Office Furniture | Same as the renovation scope, this can either be minimal (need to reupholster some items) if we keep the theme, or it wi | 1100- Specialties, Equipment & Furnishings | GC | Project | 30000 | 30000 | 0 |  | Completed
Allora Bella Terra | 2024 | Fitness Center Remodel | Misc needs, fitness center looked good | 1100- Specialties, Equipment & Furnishings | GC | Project | 3000 | 3000 | 0 |  | Completed
Allora Bella Terra | 2024 | Fitness Equipment | Good equipment currently, request for cross fit equipment | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Pool Area Remodel | Pool speaker needs repair, add lights in 6 planters. Turf around perimeter, bigger TV under gazebo | 1100- Specialties, Equipment & Furnishings | GC | Project | 30000 | 30000 | 0 |  | Completed
Allora Bella Terra | 2024 | Pool Furniture & Games | Need 4-6 new in pool loungers, lounge seating, games, lounge seating needed by fire place | 1100- Specialties, Equipment & Furnishings | GC | Project | 60000 | 60000 | 0 |  | Completed
Allora Bella Terra | 2024 | Dog Park | Rubber matting for dog wash room, water station, shade structure, benches | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 20000 | 0 |  | Completed
Allora Bella Terra | 2024 | Unit Model Update | Add model furniture in 1 br unit, outside stepping stones in yard? | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 20000 | 0 |  | Completed
Allora Bella Terra | 2024 | Package Lockers | No need, have fetch, but can look at adding package lockers outside of mail area | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 40000 | 0 |  | Completed
Allora Bella Terra | 2024 | Car wash area equipment | Hose or vacuum replacement, misc items | 1100- Specialties, Equipment & Furnishings | GC | Project | 2000 | 2000 | 0 |  | Completed
Allora Bella Terra | 2024 | EV Chargers | Look at level 1 chargers for garages, manager feels they can upcharge | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 20000 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair or Repalce the Fire Extinguisher Cabinets | From MEP Report- The fire extinguisher cabinets throughout the residentail building breezeways are corroding. | 1100- Specialties, Equipment & Furnishings | GC | Project | 30000 | 30000 | 0 |  | Completed
Allora Bella Terra | 2024 | Water pressure regulator / back-flow preventer | Inspect and repair PVB's | 1400 - Plumbing | GC | Project | 3500 | 3500 | 0 |  | Completed
Allora Bella Terra | 2024 | Scope and Clear the Sewer Lines | From MEP Report- Maintenance records were not provided before the report delvery date | 1400 - Plumbing | GC | Project | 5000 | 5000 | 0 |  | Completed
Allora Bella Terra | 2024 | Inspect and Clean Oil-Water Separator | From MEP Report- Maintenance records were not supplied prior to the report delivery date. Therefore, Partner recommends | 1400 - Plumbing | GC | Project | 3500 | 3500 | 0 |  | Completed
Allora Bella Terra | 2024 | Inspect and Repair Condenser Electrical Connection | From MEP Report- There were multiple electrical connections observed at condensing units where the weather tight flexibl | 1500- HVAC | GC | Project | 2000 | 2000 | 0 |  | Completed
Allora Bella Terra | 2024 | Replace the Refrigerant Line Insulation | From MEP Report- The insulation on the refrigerant lines at nearly all of the condensing units is deteriorated and at on | 1500- HVAC | GC | Project | 5000 | 5000 | 0 |  | Completed
Allora Bella Terra | 2024 | Electrical distribution | inspect and repair electric to pole lights | 1600 - Electrical | GC | Project | 6500 | 6500 | 0 |  | Completed
Allora Bella Terra | 2024 | Perform Infrared (IR) Scanning | From MEP Report- The facility staff was not aware of IR scanning having been performed at the property. | 1600 - Electrical | GC | Project | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Common area light fixtures | Replace pole lights with LED | 1600 - Electrical | GC | Project | 31000 | 31000 | 0 |  | Completed
Allora Bella Terra | 2024 | Contingency |  | Contingency & Fees | GC | Contingency | 802262 | 802262 | 0 |  | Reserve
Allora Bella Terra | 2024 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 111150 | 111150 | 0 |  | Reserve
Avonmora | 2024 | Storm sewer piping | Regrade area for proper drainage south west of creek | 84385 | GC | Project | 25000 | 25000 | 0 |  | Completed
Avonmora | 2024 | ADA parking & curb cuts | strip and repaint ADA ramps | 84201 | GC | Project | 7800 | 7800 | 0 |  | Completed
Avonmora | 2024 | Sidewalks | repair trip hazards | 84221 | GC | Project | 21000 | 21000 | 0 |  | Completed
Avonmora | 2024 | Retaining walls | Repair three retaining walls | 84434 | GC | Project | 16000 | 16000 | 0 |  | Completed
Avonmora | 2024 | Erosion | Backfill areas of erosion in Dog park, and throughout property | 84517 | GC | Project | 30000 | 30000 | 0 |  | Completed
Avonmora | 2024 | Perimeter fencing access control | Add thorny Pyracantha hedges alongside the fence which will grow into a natural barrier Shrubs are $80-$165 each install | 84303 | GC | Project | 160000 | 160000 | 0 |  | Completed
Avonmora | 2024 | Landscaping | Landscape enhancements in office area and front entrances and 13-8 buildings on Wickersham Zeroscape | 84303 | GC | Project | 85000 | 85000 | 0 |  | Completed
Avonmora | 2024 | Repair / replace swimming pool pumps | remove splash pad and fill, add turf for sitting area | 84361 | GC | Project | 35000 | 35000 | 0 |  | Completed
Avonmora | 2024 | Fences & gates - swimming pool | Pool fence replacement | 84361 | GC | Project | 30000 | 30000 | 0 |  | Completed
Avonmora | 2024 | Pool Deck | Replace pool deck with new stamped stained concrete | 84361 | GC | Project | 85000 | 85000 | 0 |  | Completed
Avonmora | 2024 | Maintenance Shop Structure | Add Shop for golf carts | 84219 | GC | Project | 50000 | 50000 | 0 |  | Completed
Avonmora | 2024 | Carports / Garages | repair car ports | 84219 | GC | Project | 15000 | 15000 | 0 |  | Completed
Avonmora | 2024 | Dumpster enclosures | dumpster repairs | 84111 | GC | Project | 10000 | 10000 | 0 |  | Completed
Avonmora | 2024 | Jack & underpin foundations | Foundations on 3 buildings | 84435 | GC | Project | 93000 | 93000 | 0 |  | Completed
Avonmora | 2024 | Repair exterior stair treads and stringers | replace 80 stair treads | 84114 | GC | Project | 9250 | 9250 | 0 |  | Completed
Avonmora | 2024 | Repair exterior stair railings | repair and secure stair rails | 84121 | GC | Project | 5000 | 5000 | 0 |  | Completed
Avonmora | 2024 | Repair balcony framing & decking | rebuild three balcony towers | 84104 | GC | Project | 46000 | 46000 | 0 |  | Completed
Avonmora | 2024 | Asphalt composite shingle roofing | Replace all roofs. Metal, flash, vents, and ridge | 84433 | GC | Project | 1344500 | 1344500 | 0 |  | Completed
Avonmora | 2024 | Gutters & downspouts | Repair and replace damaged or missing gutters | 84202 | GC | Project | 8300 | 8300 | 0 |  | Completed
Avonmora | 2024 | Sealants & caulking and paint | sealant for stucco expansion joints | 84433 | GC | Project | 5300 | 5300 | 0 |  | Completed
Avonmora | 2024 | Repair / replace wood siding | repair loose siding | 84105 | GC | Project | 18000 | 18000 | 0 |  | Completed
Avonmora | 2024 | Repair stucco | repair damaged stucco | 84206 | GC | Project | 10000 | 10000 | 0 |  | Completed
Avonmora | 2024 | Exterior painting | repaint buildings 100% paintable | 84101 | GC | Project | 260000 | 260000 | 0 |  | Completed
Avonmora | 2024 | Repair / replace soffits | repair stairwell soffit | 84113 | GC | Project | 14500 | 14500 | 0 |  | Completed
Avonmora | 2024 | Repair / replace wood trim | wood replacement | 84105 | GC | Project | 10000 | 10000 | 0 |  | Completed
Avonmora | 2024 | Shutters | replace 50 pairs of shutters | 84206 | GC | Project | 9000 | 9000 | 0 |  | Completed
Avonmora | 2024 | Interior Update Placeholder | Paint cabinets and new hardware, Flooring, resurface counters Appliances if possible | 84207 | PMC | Project | 1140000 | 0 | 1140000 |  | Not Started
Avonmora | 2024 | Sub Floor Repairs | Sub Floors | 84304 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Avonmora | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 84905 | PMC | Project | 1000 | 0 | 1000 |  | Not Started
Avonmora | 2024 | Clubhouse / Office Remodel | Sitting area by leasing- New lounge furniture, replace shelving with art and TVs. Doors out to pool, pergola outside, s | 84116 | GC | Project | 20000 | 20000 | 0 |  | Completed
Avonmora | 2024 | Pool Area Remodel | Add plants or metal art in planters Landscape enhancements | 84361 | GC | Project | 30000 | 30000 | 0 |  | Completed
Avonmora | 2024 | Pool Furniture | All new pool furniture and games | 84360 | PMC | Project | 35000 | 0 | 35000 |  | Not Started
Avonmora | 2024 | Dog Park | Add benches and table | 84130 | GC | Project | 4000 | 4000 | 0 |  | Completed
Avonmora | 2024 | Common area light fixtures | exterior building security lighting are pole lights and need new fixtures | 84112 | GC | Project | 38000 | 38000 | 0 |  | Completed
Avonmora | 2024 | exterior lights | replace pool lights and correct electric for pool lights | 84112 | GC | Project | 20000 | 20000 | 0 |  | Completed
Avonmora | 2024 | Contingency | Contingency Amount | 84510 | GC | Contingency | 20000 | 20000 | 0 |  | Reserve
Bridgepoint | 2024 | Storm sewer piping | Clean out yard drains PCA Item- It was reported that storm water ponds around Building 2 and 6. Partner observed sandbag | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
Bridgepoint | 2024 | concrete pavement | Patch and repair damaged areas, replace existing speed bumps with monolithic speed bumps PCA Item- Linear cracking was o | 0200 - Site Utilities & Improvements | GC | Project | 70000 | 70000 | 0 |  | Completed
Bridgepoint | 2024 | Stripe parking areas | Entire property | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
Bridgepoint | 2024 | ADA parking & curb cuts | Repair damaged curbs | 0200 - Site Utilities & Improvements | GC | Project | 9300 | 9300 | 0 |  | Completed
Bridgepoint | 2024 | Sidewalks | Mortar expansion joints between curb and sidewalk PCA Item- Differential settlement between the curb and the sidewalk w | 0200 - Site Utilities & Improvements | GC | Project | 36000 | 36000 | 0 |  | Completed
Bridgepoint | 2024 | Landscape irrigation | Inspect and repair Irrigation | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
Bridgepoint | 2024 | Erosion control |  | 0200 - Site Utilities & Improvements | GC | Project | 25500 | 25500 | 0 |  | Completed
Bridgepoint | 2024 | Fences & gates - site perimeter | Straighten and add additional side to wooden privacy fence between communities | 0200 - Site Utilities & Improvements | GC | Project | 35000 | 35000 | 0 |  | Completed
Bridgepoint | 2024 | Landscaping | remove dead tree stumps on site | 0200 - Site Utilities & Improvements | GC | Project | 10000 | 10000 | 0 |  | Completed
Bridgepoint | 2024 | Landscaping | Add river rock in high visibility bare areas Add french drains to address areas with flooding, particularly flooded uni | 0200 - Site Utilities & Improvements | GC | Project | 50000 | 50000 | 0 |  | Completed
Bridgepoint | 2024 | Resurface swimming pool | resurface | 0200 - Site Utilities & Improvements | GC | Project | 38000 | 38000 | 0 |  | Completed
Bridgepoint | 2024 | Replace swimming pool coping | retile pool | 0200 - Site Utilities & Improvements | GC | Project | 9500 | 9500 | 0 |  | Completed
Bridgepoint | 2024 | Replace swimming pool deck | pressure wash, replace expansion joint materials and deck o seal | 0200 - Site Utilities & Improvements | GC | Project | 12000 | 12000 | 0 |  | Completed
Bridgepoint | 2024 | Fences & gates - swimming pool | paint and repair | 0200 - Site Utilities & Improvements | GC | Project | 9300 | 9300 | 0 |  | Completed
Bridgepoint | 2024 | Pergola court | repair, stain and seal pergolas over grill areas | 0200 - Site Utilities & Improvements | GC | Project | 12000 | 12000 | 0 |  | Completed
Bridgepoint | 2024 | Dog Park | Replace 225 ft of fencing, replace bench with moveable bench | 0200 - Site Utilities & Improvements | GC | Project | 17400 | 17400 | 0 |  | Completed
Bridgepoint | 2024 | Carports / Garages | Repair and paint | 0200 - Site Utilities & Improvements | GC | Project | 18000 | 18000 | 0 |  | Completed
Bridgepoint | 2024 | Dumpster enclosures | Repair door and paint | 0200 - Site Utilities & Improvements | GC | Project | 9500 | 9500 | 0 |  | Completed
Bridgepoint | 2024 | Compactor door out of place | TAM team has bid to repair | 0200 - Site Utilities & Improvements | GC | Project | 1500 | 1500 | 0 |  | Completed
Bridgepoint | 2024 | Jack & underpin foundations | Placeholder for foundation repairs on "2 buildings" | 0300 - Excavation & Foundations | GC | Project | 70000 | 70000 | 0 |  | Completed
Bridgepoint | 2024 | Concrete deck / floor fill |  | 0400 - Structure | GC | Project | 17000 | 17000 | 0 |  | Completed
Bridgepoint | 2024 | Wall framing | seal penetrations in landings | 0400 - Structure | GC | Project | 1700 | 1700 | 0 |  | Completed
Bridgepoint | 2024 | Repair exterior stair treads and stringers | replace 140 stair treads across property | 0400 - Structure | GC | Project | 18900 | 18900 | 0 |  | Completed
Bridgepoint | 2024 | Repair exterior stair railings | secure stair railings | 0400 - Structure | GC | Project | 5100 | 5100 | 0 |  | Completed
Bridgepoint | 2024 | Gutters & downspouts | repitch and clean | 0700 - Roofing | GC | Project | 17000 | 17000 | 0 |  | Completed
Bridgepoint | 2024 | Flashing | siding flashing | 0700 - Roofing | GC | Project | 17000 | 17000 | 0 |  | Completed
Bridgepoint | 2024 | Sealants & caulking |  | 0700 - Roofing | GC | Project | 8000 | 8000 | 0 |  | Completed
Bridgepoint | 2024 | Repair / replace cement fiber siding |  | 0800 - Exterior Wall | GC | Project | 3400 | 3400 | 0 |  | Completed
Bridgepoint | 2024 | Dryer Vents | Just cleaned, no cleaning needed. Need to replace some flappers | 0800 - Exterior Wall | GC | Project | 3000 | 3000 | 0 |  | Completed
Bridgepoint | 2024 | Exterior building | paint community | 0800 - Exterior Wall | GC | Project | 209000 | 209000 | 0 |  | Completed
Bridgepoint | 2024 | Repair / replace wood trim | replace rotted trim/fascia/band boards | 0800 - Exterior Wall | GC | Project | 17000 | 17000 | 0 |  | Completed
Bridgepoint | 2024 | Replace unit entry doors - exterior | Placeholder to replace up to 50 doors throughout property | 0800 - Exterior Wall | GC | Project | 31500 | 31500 | 0 |  | Completed
Bridgepoint | 2024 | bps1 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 174599 | 174599 | 0 |  | Completed
Bridgepoint | 2024 | bps1u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 40336 | 40336 | 0 |  | Completed
Bridgepoint | 2024 | bpa1 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 160560 | 160560 | 0 |  | Completed
Bridgepoint | 2024 | bpa1u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 38813 | 38813 | 0 |  | Completed
Bridgepoint | 2024 | bpa2 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 524112 | 524112 | 0 |  | Completed
Bridgepoint | 2024 | bpa2u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 153398 | 153398 | 0 |  | Completed
Bridgepoint | 2024 | bpb1 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 260843 | 260843 | 0 |  | Completed
Bridgepoint | 2024 | bpb1u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 127272 | 127272 | 0 |  | Completed
Bridgepoint | 2024 | bpb2 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 192250 | 192250 | 0 |  | Completed
Bridgepoint | 2024 | bpb2u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Project | 113914 | 113914 | 0 |  | Completed
Bridgepoint | 2024 | Washers & Dryers- Basic front load | From Grid report 28 have connections, 115 have full size W/D, 45 don’t have connections | 0900 - FF&E in Units | GC | Project | 109250 | 109250 | 0 |  | Completed
Bridgepoint | 2024 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 0900 - FF&E in Units | GC | Project | 9570 | 9570 | 0 |  | Completed
Bridgepoint | 2024 | Pet Yards | Test 4 per yards on tour path- turf with vinyl or iron fence and privacy screen | 0900 - FF&E in Units | GC | Project | 24000 | 24000 | 0 |  | Completed
Bridgepoint | 2024 | Down Unit | PCA Item- Unit 514 was observed to be down due to a recent fire that was started by a candle in the bathroom of the unit | 0900 - FF&E in Units | GC | Project | 8000 | 8000 | 0 |  | Completed
Bridgepoint | 2024 | Signage - Entry Monument | Explore adding monument sign | 1100- Specialties, Equipment & Furnishings | GC | Project | 25000 | 25000 | 0 |  | Completed
Bridgepoint | 2024 | Signage - Building identification | New to match paint | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 1100- Specialties, Equipment & Furnishings | GC | Project | 5000 | 5000 | 0 |  | Completed
Bridgepoint | 2024 | Clubhouse / Office Remodel | Work with designer on options for Repaint Other finishes including backsplash and counters New art on walls New TV above | 1100- Specialties, Equipment & Furnishings | GC | Project | 30000 | 30000 | 0 |  | Completed
Bridgepoint | 2024 | Clubhouse / Office Furniture | Office chairs and other miscellaneous Items | 1100- Specialties, Equipment & Furnishings | GC | Project | 8000 | 8000 | 0 |  | Completed
Bridgepoint | 2024 | Fitness Center Remodel | Paint, add lighting, add water fountain, add 2 TVs, look at adding fans | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Fitness Equipment | Add more equipment along walkway, add storage | 1100- Specialties, Equipment & Furnishings | GC | Project | 16000 | 16000 | 0 |  | Completed
Bridgepoint | 2024 | Pool Area Remodel | Look at adding storage, other misc landscaping and needs | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Pool Furniture | All new furniture, move current tables and chairs to other areas at property | 1100- Specialties, Equipment & Furnishings | GC | Project | 35000 | 35000 | 0 |  | Completed
Bridgepoint | 2024 | Picnic/Grill Area Remodel | Grill by pool- turf under entire grill area, add gazebo, convert pergola over grill to gazebo | 1100- Specialties, Equipment & Furnishings | GC | Project | 30000 | 30000 | 0 |  | Completed
Bridgepoint | 2024 | Picnic/Grill Furniture | Add picnic tables, chairs, games | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Sports Courts | Convert old tennis court to pickleball- need to resurface and stripe, and add nets, bring surrounding soil back up to sl | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Dog Park | Water/Wash Station with concrete pad ($6k) Add gazebo or shade sail Furniture next to laundry area | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 20000 | 0 |  | Completed
Bridgepoint | 2024 | Access Control System | Replace keypad on fitness center door | 1100- Specialties, Equipment & Furnishings | GC | Project | 500 | 500 | 0 |  | Completed
Bridgepoint | 2024 | Computers | 2 new comupters for clubhouse resident use | 1100- Specialties, Equipment & Furnishings | GC | Project | 2000 | 2000 | 0 |  | Completed
Bridgepoint | 2024 | Security Camera System | No urgent need, would be nice to have for monitoring | 1100- Specialties, Equipment & Furnishings | GC | Project | 10000 | 10000 | 0 |  | Completed
Bridgepoint | 2024 | Fire Extinguishers | PCA Item- Expired certification tags were present at the fire extinguishers in common area breezeways. Servicing and re- | 1100- Specialties, Equipment & Furnishings | PMC | Project | 1000 | 7663 | -6663 |  | Completed
Bridgepoint | 2024 | Golf Cart | Need maintenance cart | 1100- Specialties, Equipment & Furnishings | GC | Project | 8000 | 8000 | 0 |  | Completed
Bridgepoint | 2024 | Sanitary sewer piping | MEP Item- Industry best practices typically include clearing sanitary waste lines every 18- to 24-months. Partner recomm | 1400 - Plumbing | GC | Project | 10000 | 10000 | 0 |  | Completed
Bridgepoint | 2024 | HVAC | Install AC pads on all units sitting on dirt, secure all unit access control panels MEP Item- Split system units - Cond | 1500- HVAC | GC | Project | 50000 | 50000 | 0 |  | Completed
Bridgepoint | 2024 | Replace AC condenser | Air conditioners at 40% conversion to 410-a, but not all replaced inside and out. Contingency for replacement of R-22 u | 1500- HVAC | GC | Project | 210000 | 210000 | 0 |  | Completed
Bridgepoint | 2024 | Electrical distribution | Inspect and repair lighting controllers on all buildings "additional wiring requirements are not included" MEP Item- Ele | 1600 - Electrical | GC | Project | 20000 | 20000 | 0 |  | Completed
Bridgepoint | 2024 | Common area light fixtures | Replace wall packs on buildings | 1600 - Electrical | GC | Project | 31000 | 31000 | 0 |  | Completed
Bridgepoint | 2024 | Replace additional lights | Replace pole light fixtures | 1600 - Electrical | GC | Project | 28000 | 28000 | 0 |  | Completed
Bridgepoint | 2024 | Contingency |  | Contingency & Fees | GC | Contingency | 90985 | 90985 | 0 |  | Reserve
Bridgepoint | 2024 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 174000 | 174000 | 0 |  | Reserve
Cityscape | 2024 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84303 | GC | Project | 15000 | 15000 | 0 |  | Completed
Cityscape | 2024 | Concrete pavement | Remove and replace 10,000 LF of failing expansion joint material | 84102 | GC | Project | 20000 | 20000 | 0 |  | Completed
Cityscape | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84239 | PMC | Project | 28634 | 44122 | -15487 |  | Completed
Cityscape | 2024 | Clubhouse / Office Remodel | Add controlled access for clubhouse for rentals | 84116 | GC | Project | 5000 | 5000 | 0 |  | Completed
Cityscape | 2024 | Fitness Center Remodel | Add lighting around perimeter soffit | 84190 | GC | Project | 3000 | 3000 | 0 |  | Completed
Cityscape | 2024 | Green Initiatives | Green Program | 83515 | GC | Project | 100000 | 100000 | 0 |  | Completed
Cityscape | 2024 | Contingency | Contingency Amount | 84510 | GC | Contingency | 17163 | 17163 | 0 |  | Reserve
Cityscape | 2024 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 9440 | 9440 | 0 |  | Reserve
Discovery Park | 2024 | Storm sewer piping | add stone around storm drains | 0200 - Site Utilities & Improvements | GC | Project | 7500 | 7500 | 0 |  | Completed
Discovery Park | 2024 | Concrete Pavement | From PCA- Replace the large area of prior-repaired concrete pavement near the southwest corner of Building 1 due to sign | 0200 - Site Utilities & Improvements | GC | Project | 43750 | 43750 | 0 |  | Completed
Discovery Park | 2024 | Concrete Pavement | From PCA- Allowance to repair all areas of random pavement cracks scattered throughout the parking areas | 0200 - Site Utilities & Improvements | GC | Project | 4500 | 4500 | 0 |  | Completed
Discovery Park | 2024 | Concrete Pavement | From PCA- Allowance to replace the deteriorated sealant in the concrete pavement joints | 0200 - Site Utilities & Improvements | GC | Project | 21700 | 21700 | 0 |  | Completed
Discovery Park | 2024 | Sidewalk Repair | From PCA- Area of heaving adjacent to the pavement curb near the southwest corner of Building 4 and deteriorated sealant | 0200 - Site Utilities & Improvements | GC | Project | 1000 | 1000 | 0 |  | Completed
Discovery Park | 2024 | Sidewalk Railing | From PCA- Install a guardrail along the east edge of the wide sidewalk leading to the maintenance garage where the adjac | 0200 - Site Utilities & Improvements | GC | Project | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Concrete Stairs | From PCA- Due to the muddy, deteriorated landscape conditions at the fire sprinkler riser room of Building 1 discussed i | 0200 - Site Utilities & Improvements | GC | Project | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Accessibility | From PCA- Install edge protection at the base of the guardrail along the west side of the pool deck for FHAA compliance | 0200 - Site Utilities & Improvements | GC | Project | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Accessibility | From PCA- Ramps are provided on the first floor of the buildings to address changes in the slab elevations. Handrails ar | 0200 - Site Utilities & Improvements | GC | Project | 5000 | 5000 | 0 |  | Completed
Discovery Park | 2024 | Landscape irrigation | inspect and repair Irrigation | 0200 - Site Utilities & Improvements | GC | Project | 22600 | 22600 | 0 |  | Completed
Discovery Park | 2024 | Resurface swimming pool | Resurface Pool | 0200 - Site Utilities & Improvements | GC | Project | 35000 | 35000 | 0 |  | Completed
Discovery Park | 2024 | Repair / replace swimming pool pumps | anti entrapment devices | 0200 - Site Utilities & Improvements | GC | Project | 6800 | 6800 | 0 |  | Completed
Discovery Park | 2024 | Carports | Look at adding, garages are sold out so there is a need | 0200 - Site Utilities & Improvements | GC | Project | 152000 | 152000 | 0 |  | Completed
Discovery Park | 2024 | Dumpster enclosures | Paint enclosure | 0200 - Site Utilities & Improvements | GC | Project | 4500 | 4500 | 0 |  | Completed
Discovery Park | 2024 | Pet yards | paint pet yard fencing | 0200 - Site Utilities & Improvements | GC | Project | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Dog Park Fence | Repair and repaint fence, replace or fix broken gate hinge and bring latches down to FHAA compliant height | 0200 - Site Utilities & Improvements | GC | Project | 9500 | 9500 | 0 |  | Completed
Discovery Park | 2024 | Soffit beam supports appear to be separating in some lo |  | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
Discovery Park | 2024 | Dryer Vents | Clean, fix any flapper valves | 0200 - Site Utilities & Improvements | GC | Project | 21225 | 21225 | 0 |  | Completed
Discovery Park | 2024 | Garages | Replace at least 6 dented garage doors (G115 is the worst) | 0200 - Site Utilities & Improvements | GC | Project | 8800 | 8800 | 0 |  | Completed
Discovery Park | 2024 | Foundation Repair | Review all exposed areas and appropriately repair any foundation cracking such as the ones noted near garage G505 on Bui | 0300 - Excavation & Foundations | GC | Project | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Roof deck | Secure Decking while doing roof tune-up | 0400 - Structure | GC | Project | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Asphalt composite shingle roofing | Roof inspection and minor repairs | 0700 - Roofing | GC | Project | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Articulating Lift Rental |  | 0700 - Roofing | GC | Project | 5000 | 5000 | 0 |  | Completed
Discovery Park | 2024 | Repair / replace cement fiber siding |  | 0800 - Exterior Wall | GC | Project | 7500 | 7500 | 0 |  | Completed
Discovery Park | 2024 | Repair / replace wood trim | minor trim replacement | 0800 - Exterior Wall | GC | Project | 8000 | 8000 | 0 |  | Completed
Discovery Park | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 0900 - FF&E in Units | GC | Project | 30069 | 30069 | 0 |  | Completed
Discovery Park | 2024 | Fire protection | Fix heads with overspray- allowance | 0900 - FF&E in Units | GC | Project | 10000 | 10000 | 0 |  | Completed
Discovery Park | 2024 | Unit deferred maintenance | Sub floor repairs | 0900 - FF&E in Units | GC | Project | 5000 | 5000 | 0 |  | Completed
Discovery Park | 2024 | Signage - Building identification | Need better signage at leasing office, new garage number signs to replace current faded ones, new window shade branded d | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Signage- Monument | Look at adding monument sign | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 20000 | 0 |  | Completed
Discovery Park | 2024 | Clubhouse / Office Remodel | Placeholder for minor items | 1100- Specialties, Equipment & Furnishings | GC | Project | 10000 | 10000 | 0 |  | Completed
Discovery Park | 2024 | Clubhouse / Office Furniture | Misc items, new pool table? | 1100- Specialties, Equipment & Furnishings | GC | Project | 18000 | 18000 | 0 |  | Completed
Discovery Park | 2024 | Indoor Basketball Area Repairs | Restripe basketball court Fix leak in roof and repair damage at ceiling Repair wall chips behind hoop Fix chipped paint | 1100- Specialties, Equipment & Furnishings | GC | Project | 8000 | 8000 | 0 |  | Completed
Discovery Park | 2024 | Indoor Basketball Area Furniture | Replace 2 long benches | 1100- Specialties, Equipment & Furnishings | GC | Project | 2000 | 2000 | 0 |  | Completed
Discovery Park | 2024 | Fitness Center Remodel | Allowance for minor repairs | 1100- Specialties, Equipment & Furnishings | GC | Project | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Fitness Equipment | Allowance for supplemental equipment and replacements for cycling room and gym | 1100- Specialties, Equipment & Furnishings | GC | Project | 30000 | 30000 | 0 |  | Completed
Discovery Park | 2024 | Pool Area Remodel | Replace bamboo screen around pool equipment room with better screen, misc repairs and pool equipment | 1100- Specialties, Equipment & Furnishings | GC | Project | 5000 | 5000 | 0 |  | Completed
Discovery Park | 2024 | Pool Furniture | New side tables, new lounge seating or at least replace cushions on existing wicker seating. 1-2 new cabanas or more cha | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 40000 | 0 |  | Completed
Discovery Park | 2024 | Business Center & Office Computers | 1 computer is cracked and needs to be replaced. | 1100- Specialties, Equipment & Furnishings | PMC | Project | 1500 | 5287 | -3787 |  | Completed
Discovery Park | 2024 | Dog Park | Water/Wash Station with concrete pad ($6k) Shade sail or pergola Look at adding additional Dog Park across road | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Access Control System | Need to add access control at 2 doors from pool to business center and to restrooms | 1100- Specialties, Equipment & Furnishings | GC | Project | 6000 | 6000 | 0 |  | Completed
Discovery Park | 2024 | Rubber Mats for Breezeway transitions for Non-Slip Surf |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 25000 | 25000 | 0 |  | Completed
Discovery Park | 2024 | Cigarette Urns | Per Shelly, look at adding smoking urns where needed to reduce cigarette butts throughout property | 1100- Specialties, Equipment & Furnishings | GC | Project | 1000 | 1000 | 0 |  | Completed
Discovery Park | 2024 | Water pressure regulator / back-flow preventer | inspect and repair PVB's | 1400 - Plumbing | GC | Project | 3500 | 3500 | 0 |  | Completed
Discovery Park | 2024 | Repair HVAC in fitness center |  | 1500- HVAC | GC | Project | 20000 | 20000 | 0 |  | Completed
Discovery Park | 2024 | Electrical distribution | Electric for car ports- Remove if we don’t add car ports | 1600 - Electrical | GC | Project | 20000 | 20000 | 0 |  | Completed
Discovery Park | 2024 | Fire and Sprinklers | Add anti freeze to hallway and patio sprinkler systems | 1600 - Electrical | GC | Project | 40000 | 40000 | 0 |  | Completed
Discovery Park | 2024 | Common area light fixtures | Lighting for carports | 1600 - Electrical | GC | Project | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Contingency |  | Contingency & Fees | GC | Contingency | 20000 | 20000 | 0 |  | Reserve
Discovery Park | 2024 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 40222 | 40222 | 0 |  | Reserve
Hampton Courts | 2024 | Repair pot holes | Repair pot holes | 7200-0064 | GC | Project | 30000 | 30000 | 0 |  | Completed
Hampton Courts | 2024 | Stripe Parking | Stripe Parking | 7200-0064 | GC | Project | 20000 | 20000 | 0 |  | Completed
Hampton Courts | 2024 | Seal Coat asphalt PCA Item- $1,725- Limited surface lin | Seal Coat asphalt PCA Item- $1,725- Limited surface linear cracking and “map” or “alligator” cracking were noted along t | 7200-0064 | GC | Project | 81000 | 81000 | 0 |  | Completed
Hampton Courts | 2024 | Repair trip hazards PCA Item- $3,000- A significant are | Repair trip hazards PCA Item- $3,000- A significant area of heaved concrete was observed in the sidewalk at the south of | 7200-0064 | GC | Project | 18500 | 18500 | 0 |  | Completed
Hampton Courts | 2024 | Initial property tree trim around buildings, landscape | Initial property tree trim around buildings, landscape cleanup, entry and tour path enhancements, etc. PCA Item- $5,000- | 7200-0045 | GC | Project | 40000 | 40000 | 0 |  | Completed
Hampton Courts | 2024 | Anti entrapment devices | Anti entrapment devices | 7200-0057 | GC | Project | 12800 | 12800 | 0 |  | Completed
Hampton Courts | 2024 | Adjust closers on pool gates | Adjust closers on pool gates | 7200-0069 | GC | Project | 6000 | 6000 | 0 |  | Completed
Hampton Courts | 2024 | Replace grill | Replace grill | 7200-0061 | GC | Project | 4000 | 4000 | 0 |  | Completed
Hampton Courts | 2024 | Repair and paint compactor enclosure | Repair and paint compactor enclosure | 7200-0081 | GC | Project | 8500 | 8500 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $6,000- Provide accessible path of travel fro | PCA Item- $6,000- Provide accessible path of travel from municipal sidewalk to leasing office entrance. | 7200-0064 | GC | Project | 7000 | 7000 | 0 |  | Completed
Hampton Courts | 2024 | replace damaged framing in gable ends | replace damaged framing in gable ends | 7200-0012 | GC | Project | 8500 | 8500 | 0 |  | Completed
Hampton Courts | 2024 | secure railings | secure railings | 7200-0016 | GC | Project | 6800 | 6800 | 0 |  | Completed
Hampton Courts | 2024 | Repair loose pickets | Repair loose pickets | 7200-0016 | GC | Project | 14000 | 14000 | 0 |  | Completed
Hampton Courts | 2024 | Repair Balconies | Repair Balconies | 7400-0015 | GC | Project | 9000 | 9000 | 0 |  | Completed
Hampton Courts | 2024 | secure railings | secure railings | 7200-0016 | GC | Project | 8600 | 8600 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $2,500- At Building A, two exterior stair con | PCA Item- $2,500- At Building A, two exterior stair conditions requiring repair were noted. At the uppermost landing of | 7200-0015 | GC | Project | 3000 | 3000 | 0 |  | Completed
Hampton Courts | 2024 | Roof tune up include chimney | Roof tune up include chimney | 7200-0002 | GC | Project | 34000 | 34000 | 0 |  | Completed
Hampton Courts | 2024 | Seal flat roof on club building - option to replace soo | Seal flat roof on club building - option to replace soon to fail skylight. Pushes cost to $30k | 7200-0002 | GC | Project | 14000 | 14000 | 0 |  | Completed
Hampton Courts | 2024 | secure and clean gutters | secure and clean gutters | 7200-0017 | GC | Project | 18000 | 18000 | 0 |  | Completed
Hampton Courts | 2024 | Seal edges of delaminated cedar | Seal edges of delaminated cedar | 7200-0012 | GC | Project | 36000 | 36000 | 0 |  | Completed
Hampton Courts | 2024 | Clubhouse needs new roof, property received bid for $40 | Clubhouse needs new roof, property received bid for $40-$50k to replace | 7200-0002 | GC | Project | 50000 | 50000 | 0 |  | Completed
Hampton Courts | 2024 | Replace rotted cedar siding | Replace rotted cedar siding | 7200-0012 | GC | Project | 27000 | 27000 | 0 |  | Completed
Hampton Courts | 2024 | Paint community - working with Keys | Paint community - working with Keys | 7200-0013 | GC | Project | 340000 | 340000 | 0 |  | Completed
Hampton Courts | 2024 | Replace rotted fascia and trim - work in conjunction w | Replace rotted fascia and trim - work in conjunction with bat removal | 7200-0012 | GC | Project | 24000 | 24000 | 0 |  | Completed
Hampton Courts | 2024 | Replace damaged storage doors | Replace damaged storage doors | 7200-0023 | GC | Project | 17000 | 17000 | 0 |  | Completed
Hampton Courts | 2024 | 99 units with missing GFCIs in the kitchen across diffe | 99 units with missing GFCIs in the kitchen across different buildings and renovation levels - Team to order stock and in | 7400-0040 | PMC | Project | 29700 | 0 | 29700 |  | Not Started
Hampton Courts | 2024 | 170 units we could add washer dryers - Team to order s | 170 units we could add washer dryers - Team to order stock and install on turn, reno, WO, PM | 7400-0041 | PMC | Project | 221000 | 0 | 221000 |  | Not Started
Hampton Courts | 2024 | Done every fall, budget for cleaning after takeover | Done every fall, budget for cleaning after takeover | 7200-0041 | GC | Project | 20700 | 20700 | 0 |  | Completed
Hampton Courts | 2024 | LowPro (Pair covers 4 burner range)- For range top micr | LowPro (Pair covers 4 burner range)- For range top microwaves (assuming current hoods are replaced with OTR microwaves) | 7400-0038 | PMC | Project | 32258 | 0 | 32258 |  | Not Started
Hampton Courts | 2024 | PCA Item- $500- At vacant Unit E105, standing water was | PCA Item- $500- At vacant Unit E105, standing water was observed on the floor - COMPLETE BEFORE TAKEOVER | 7400-0034 | GC | Project | 500 | 500 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $1,000- Remove and replace suspect microbial | PCA Item- $1,000- Remove and replace suspect microbial growth-damaged ceiling at Unit A107 bathroom - COMPLETE BEFORE TA | 7400-0032 | GC | Project | 1000 | 1000 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $2,000- Complete flooring/appliance replaceme | PCA Item- $2,000- Complete flooring/appliance replacement at Unit F102.- COMPLETE BEFORE TAKEOVER | 7400-0028 | GC | Project | 2000 | 2000 | 0 |  | Completed
Hampton Courts | 2024 | Evidence of water infiltration observed (20)- Units - C | Evidence of water infiltration observed (20)- Units - COMPLETE BEFORE TAKEOVER | 7400-0032 | GC | Project | 20000 | 20000 | 0 |  | Completed
Hampton Courts | 2024 | Allowance | Allowance | 7400-0053 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Hampton Courts | 2024 | New carpeting in corridor and on stairs, lots of drywal | New carpeting in corridor and on stairs, lots of drywall repairs | 7200-0032 | GC | Project | 60000 | 60000 | 0 |  | Completed
Hampton Courts | 2024 | New furniture - Keys | New furniture - Keys | 7200-0027 | PMC | Project | 75000 | 0 | 75000 |  | Not Started
Hampton Courts | 2024 | Paint, lighting, flooring is ok - frost the glass and p | Paint, lighting, flooring is ok - frost the glass and possibly add sound dampening panels to upper walls | 7200-0032 | GC | Project | 15000 | 15000 | 0 |  | Completed
Hampton Courts | 2024 | New equipment to supplement existing - Keys | New equipment to supplement existing - Keys | 7200-0074 | GC | Project | 40000 | 40000 | 0 |  | Completed
Hampton Courts | 2024 | Supplement or replace furniture, add games - Keys | Supplement or replace furniture, add games - Keys | 7200-0061 | PMC | Project | 60000 | 0 | 60000 |  | Not Started
Hampton Courts | 2024 | Look at adding a picnic area or enhance existing grill, | Look at adding a picnic area or enhance existing grill, add gazebo - Keys | 7200-0060 | GC | Project | 25000 | 25000 | 0 |  | Completed
Hampton Courts | 2024 | Pickleball courts in decent shape, budget for resurfaci | Pickleball courts in decent shape, budget for resurfacing and concrete repair since blue surface is loose in places with | 7200-0059 | GC | Project | 40000 | 40000 | 0 |  | Completed
Hampton Courts | 2024 | Allowance for Dog Park enhancements - adding enzyme inj | Allowance for Dog Park enhancements - adding enzyme injector | 7200-0048 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Hampton Courts | 2024 | New furniture in model unit - Keys | New furniture in model unit - Keys | 7200-0037 | PMC | Project | 18000 | 0 | 18000 |  | Not Started
Hampton Courts | 2024 | Needed, would need to find space outside or repurpose l | Needed, would need to find space outside or repurpose laundry room if possible - explore options | 7200-0055 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Hampton Courts | 2024 | 4 new computers needed | 4 new computers needed | 7200-0029 | PMC | Project | 4000 | 0 | 4000 |  | Not Started
Hampton Courts | 2024 | Have 10 cameras and good coverage, allowance for some a | Have 10 cameras and good coverage, allowance for some additional cameras |  | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Hampton Courts | 2024 | Need storage for maintenance and inventory - maintenanc | Need storage for maintenance and inventory - maintenance shop clean up first. If still not enough space, add used Conex | 7200-0066 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Hampton Courts | 2024 | PCA Item- $2,000- At the front of Building M, the adjac | PCA Item- $2,000- At the front of Building M, the adjacent asphalt parking lot and drive aisle were observed to be satur | 7200-0047 | GC | Project | 2000 | 2000 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $276,000- The maintenance supervisor reported | PCA Item- $276,000- The maintenance supervisor reported that roughly 50% of the domestic water heaters are from the orig | 7200-0007 | PMC | Project | 80000 | 0 | 80000 |  | Not Started
Hampton Courts | 2024 | PCA Item- $5,000- The clubhouse domestic water heater i | PCA Item- $5,000- The clubhouse domestic water heater is origional; to the 1986 construction. Electric, storage-type wat | 7200-0007 | GC | Project | 5000 | 5000 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $690,000- The maintenance supervisor reported | PCA Item- $690,000- The maintenance supervisor reported that roughly 50% of the heat pump condensers are from the origin | 7200-0033 | PMC | Project | 200000 | 0 | 200000 |  | Not Started
Hampton Courts | 2024 | PCA Item- $8,500- Insulation at the refrigerant lines f | PCA Item- $8,500- Insulation at the refrigerant lines for a majority of the outdoor condensing units were observed to be | 7200-0033 | GC | Project | 8500 | 8500 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $4,000- The ductwork within the clubhouse dis | PCA Item- $4,000- The ductwork within the clubhouse displayed evident signs of dust accumulation, observable upon visibl | 7200-0033 | GC | Project | 4000 | 4000 | 0 |  | Completed
Hampton Courts | 2024 | HVAC lines are under sized, need to replace. - As neede | HVAC lines are under sized, need to replace. - As needed | 7200-0033 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Hampton Courts | 2024 | inspect and repair electric for exposed electrical line | inspect and repair electric for exposed electrical lines in lighting systems . PCA Item- $3,000- Repair electrical distr | 7200-0040 | GC | Project | 21000 | 21000 | 0 |  | Completed
Hampton Courts | 2024 | Replace wall packs | Replace wall packs | 7200-0040 | GC | Project | 36000 | 36000 | 0 |  | Completed
Hampton Courts | 2024 | Replace pole lights around pool | Replace pole lights around pool | 7200-0040 | GC | Project | 12000 | 12000 | 0 |  | Completed
Hampton Courts | 2024 | Contingency Amount | Contingency Amount | 7200-0083 | GC | Contingency | 100000 | 100000 | 0 |  | Reserve
Hampton Courts | 2024 | CM Fee | CM Fee | 7200-0084 | GC | CM Fee | 104518 | 104518 | 0 |  | Reserve
Harbor Terrace | 2024 | Initial property tree trim, landscape cleanup, entry an | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 51045-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
Harbor Terrace | 2024 | All floor drains have been painted over and should have | All floor drains have been painted over and should have the covers cleaned or replaced | 51130-00 | GC | Project | 6500 | 6500 | 0 |  | Completed
Harbor Terrace | 2024 | Restripe parking garage | Restripe parking garage | 51053-00 | GC | Project | 9700 | 9700 | 0 |  | Completed
Harbor Terrace | 2024 | Equity PCR Item 7.0- ADA-compliant parking spaces are r | Equity PCR Item 7.0- ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibi | 51032-00 | GC | Project | 300 | 300 | 0 |  | Completed
Marquee | 2024 | Stripe parking areas | Restripe parking lot | 51053-00 | GC | Project | 18000 | 18000 | 0 |  | Completed
Marquee | 2024 | Landscaping | Tree trim away from buildings | 51043-00 | GC | Project | 16000 | 16000 | 0 |  | Completed
Marquee | 2024 | Repair / replace swimming pool pumps | Install anti entrapment divise on pool pumps | 51026-00 | GC | Project | 4300 | 4300 | 0 |  | Completed
Marquee | 2024 | Repair / replace swimming pool heaters | replace hot tub heater | 51026-00 | GC | Project | 25000 | 25000 | 0 |  | Completed
Marquee | 2024 | Fences & gates - swimming pool | adjust closers on pool gates amd paint pool fence | 51076-00 | GC | Project | 6000 | 6000 | 0 |  | Completed
Marquee | 2024 | Dumpster enclosures | repair and paint compacter enclosure | 51163-00 | GC | Project | 8500 | 8500 | 0 |  | Completed
Marquee | 2024 | Parking Pavement & Seal Coat | Equity PCA Item 3.2.2- Linear cracking was noted at the drive aisle on the eastern side of the subject property, adjacen | 51050-00 | GC | Project | 45000 | 45000 | 0 |  | Completed
Marquee | 2024 | ADA Signage | Equity PCA Item 7.0- A lack of signage identifying the van-accessible parking space at the leasing office was observed | 51032-00 | GC | Project | 150 | 150 | 0 |  | Completed
Marquee | 2024 | Landscape Enhancements | Add turf or better landscaping in bare areas | 51045-00 | GC | Project | 10000 | 10000 | 0 |  | Completed
Marquee | 2024 | Concrete deck / floor fill | Repair cracked areas on catwalks | 51090-00 | GC | Project | 9500 | 9500 | 0 |  | Completed
Marquee | 2024 | Repair exterior stair treads and stringers | secure railings | 51072-00 | GC | Project | 6800 | 6800 | 0 |  | Completed
Marquee | 2024 | Repair patio/balcony railings | Repair catwalk railings | 51077-00 | GC | Project | 9500 | 9500 | 0 |  | Completed
Marquee | 2024 | Gutters & downspouts | secure and clean gutters | 51071-00 | GC | Project | 19000 | 19000 | 0 |  | Completed
Marquee | 2024 | Flashing | Seal seams on parapet walls | 51062-00 | GC | Project | 14000 | 14000 | 0 |  | Completed
Marquee | 2024 | Sealants & caulking | Seal seams windows prior to paint | 51062-00 | GC | Project | 16000 | 16000 | 0 |  | Completed
Marquee | 2024 | Repair stucco | repair remaining areas of delaminated stucco and cracked stucco | 51075-00 | GC | Project | 30000 | 30000 | 0 |  | Completed
Marquee | 2024 | Interior Hallway painting | Paint interior hallways and staircases | 51080-00 | GC | Project | 89000 | 89000 | 0 |  | Completed
Marquee | 2024 | Exterior building | Paint community Using Elastomaric paint Equity PCA Item 4.3.1- Exterior paint appeared to be in fair condition. The rec | 51080-00 | GC | Project | 250000 | 250000 | 0 |  | Completed
Marquee | 2024 | Replace unit entry doors - exterior | Replace 28 back doors | 51073-00 | GC | Project | 70800 | 70800 | 0 |  | Completed
Marquee | 2024 | Interior Update Placeholder | Match renovated units with upcoming available classic units | 51150-00 | PMC | Project | 112000 | 22164 | 89836 |  | In Progress
Marquee | 2024 | Smoke & CO detectors | Per LADBS Declaration- Required complaince with Section 91.8603 LAMC Either confirm they are already installed or plan f | 51993-01 | PMC | Project | 11800 | 0 | 11800 |  | Not Started
Marquee | 2024 | Impact Glazing/Film for Sliding Glass Doors | Per LADBS Declaration- Required complaince with Section 96.302 LAMC Contingency for roughly 15-20 sliding doors in Build | 51073-00 | PMC | Project | 5000 | 4800 | 200 |  | In Progress
Marquee | 2024 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 51993-01 | PMC | Project | 11797 | 855 | 10943 |  | In Progress
Marquee | 2024 | Water Savings Project | Echelon proposal for water savings devices | 51158-00 | PMC | Project | 138000 | 21858 | 116142 |  | In Progress
Marquee | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 51180-00 | PMC | Project | 2000 | 9210 | -7210 |  | Completed
Marquee | 2024 | Clubhouse / Office Remodel | No needs, flooring ok, misc amount for repairs and paint if needed | 51169-00 | PMC | Project | 2000 | 0 | 2000 |  | Not Started
Marquee | 2024 | Clubhouse / Office Furniture | Allowance for supplemental items | 51169-00 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Marquee | 2024 | Fitness Center Remodel | No needs, flooring ok, misc amount for repairs and paint if needed | 51160-00 | PMC | Project | 2000 | 0 | 2000 |  | Not Started
Marquee | 2024 | Fitness Equipment | Replace treadmill, supplemental items | 51028-00 | PMC | Project | 8000 | 1581 | 6419 |  | In Progress
Marquee | 2024 | Pool & Spa Area Remodel | Add shade screens to each area along parking lot fence, possibly add turf in planter areas. | 51160-00 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Marquee | 2024 | Pool & Spa Area Furniture & Games | Match furniture style in main pool area, possibly move some irems from pool to spa area | 51011-00 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Marquee | 2024 | Termite treatment & Repairs | Refer to Orkin WDIR dated 9/25/24 for details | 51992-00 | PMC | Project | 25000 | 0 | 25000 |  | Not Started
Marquee | 2024 | Unit Model Update | New furniture in model unit, definitely enhance lighting in model | 51160-05 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Marquee | 2024 | Mailbox Repairs | Repair broken mailbox doors | 51168-00 | GC | Project | 1500 | 1500 | 0 |  | Completed
Marquee | 2024 | Security Camera System | Needed, especially at pedestrian gates | 51993-00 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Marquee | 2024 | Golf Cart | Maintenance Cart | 51994-00 | PMC | Project | 7500 | 0 | 7500 |  | Not Started
Marquee | 2024 | Common area water heaters / boilers | Replace two ray pak boilers and one upright 199,000 but heater | 51110-00 | PMC | Project | 65000 | 0 | 65000 |  | Not Started
Marquee | 2024 | Electrical distribution | Equity PCA Item 5.3- Stab-Lok brand breaker panels manufactured by Federal Pacific Electric (FPE) were observed in appro | 51140-00 | PMC | Project | 118000 | 8547 | 109453 |  | In Progress
Marquee | 2024 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 61607 | 61607 | 0 |  | Reserve
Marquee | 2024 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 61607 | 61607 | 0 |  | Reserve
Navigator Villas | 2024 | concrete pavement | replace broken curbs | 84221 | GC | Project | 6250 | 6250 | 0 |  | Completed
Navigator Villas | 2024 | Add Accessible Van Parking Space | The accessible parking space in front of the leasing office is not van-accessible; | 84201 | PMC | Project | 450 | 13308 | -12858 |  | Completed
Navigator Villas | 2024 | Landscape irrigation | Inspect and repair Irrigation | 84300 | PMC | Project | 22000 | 4763 | 17237 |  | In Progress
Navigator Villas | 2024 | Landscaping | Add landscaping in planters around pool | 84300 | PMC | Project | 26000 | 14820 | 11180 |  | In Progress
Navigator Villas | 2024 | Replace swimming pool deck | Presure wash pool deck (reduced to $6,000) | 84095 | GC | Project | 16000 | 16000 | 0 |  | Completed
Navigator Villas | 2024 | Repair / replace swimming pool pumps | Anti entrapment devices | 84095 | GC | Project | 12800 | 12800 | 0 |  | Completed
Navigator Villas | 2024 | Fences & gates - swimming pool | Paint pool fence | 84095 | GC | Project | 8400 | 8400 | 0 |  | Completed
Navigator Villas | 2024 | Playground equipment | Add mulch to playground | 84340 | PMC | Project | 6200 | 574 | 5626 |  | In Progress
Navigator Villas | 2024 | Carports / Garages | Repair and paint 15 Garage doors | 84219 | GC | Project | 33000 | 33000 | 0 |  | Completed
Navigator Villas | 2024 | Repair exterior stair railings | Secure railings | 84121 | GC | Project | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | Expansion Joints | Seal expansion joints | 84102 | GC | Project | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | Asphalt composite shingle roofing | Roof inspection and minor repairs | 84433 | GC | Project | 29000 | 29000 | 0 |  | Completed
Navigator Villas | 2024 | Flashing | repair flashing over clay tile | 84433 | GC | Project | 6500 | 6500 | 0 |  | Completed
Navigator Villas | 2024 | Repair / replace cement fiber siding | replace bad siding and paint to match | 84105 | GC | Project | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | Repair / replace wood trim | Minor trim replacement | 84105 | GC | Project | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | 2x2 Duplex A- Classic | See Unit Renovation Calculator for detail | 84207 | PMC | Project | 5003 | 0 | 5003 |  | Not Started
Navigator Villas | 2024 | 2x2 Duplex A- Renovated | See Unit Renovation Calculator for detail | 84207 | PMC | Project | 8489 | 0 | 8489 |  | Not Started
Navigator Villas | 2024 | 2x2 TH A- Classic | See Unit Renovation Calculator for detail | 84207 | PMC | Project | 52319 | 0 | 52319 |  | Not Started
Navigator Villas | 2024 | 2x2 TH A- Classic- Upgraded Flooring Placeholder | See Unit Renovation Calculator for detail | 84207 | PMC | Project | 43502 | 0 | 43502 |  | Not Started
Navigator Villas | 2024 | 2x2 TH A- Renovated | See Unit Renovation Calculator for detail | 84207 | PMC | Project | 176906 | 0 | 176906 |  | Not Started
Navigator Villas | 2024 | 2x2 TH B- Classic | See Unit Renovation Calculator for detail | 84207 | PMC | Project | 68015 | 0 | 68015 |  | Not Started
Navigator Villas | 2024 | 2x2 TH B- Classic- Upgraded Flooring Placeholder | See Unit Renovation Calculator for detail | 84207 | PMC | Project | 43502 | 0 | 43502 |  | Not Started
Navigator Villas | 2024 | 2x2 TH B- Renovated | See Unit Renovation Calculator for detail | 84207 | PMC | Project | 168206 | 0 | 168206 |  | Not Started
Navigator Villas | 2024 | Clean Dryer Vents | Dryer Vent Cleaning | 84106 | GC | Project | 13200 | 13200 | 0 |  | Completed
Navigator Villas | 2024 | Fire Stops | LowPro - For range top microwaves | 84239 | PMC | Project | 20570 | 48953 | -28383 |  | Completed
Navigator Villas | 2024 | Clubhouse / Office Remodel | No clubhouse, office in good shape. Misc allowance for paint, etc | 84208 | PMC | Project | 2000 | 28000 | -26000 |  | Completed
Navigator Villas | 2024 | Clubhouse / Office Furniture | Placeholder for misc items. | 84208 | PMC | Project | 2000 | 4274 | -2274 |  | Completed
Navigator Villas | 2024 | Install sink drain insulation in the fitness area bathr | There is no sink drain insulation provided in the fitness area bathroom. | 84209 | PMC | Project | 250 | 1918 | -1668 |  | Completed
Navigator Villas | 2024 | Security Camera System | Only cameras on the leasing office and gym, no expressed need for additional cameras, maybe add for package lockers | 84450 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Navigator Villas | 2024 | Replace AC condenser | AC Condenser | 84220 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Navigator Villas | 2024 | Electrical distribution | Inspect and repair electric pole lights | 84210 | GC | Project | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | Common area light fixtures | Wall Pack replacement | 84210 | GC | Project | 31000 | 31000 | 0 |  | Completed
Navigator Villas | 2024 | Contingency | Contingency Amount | 84510 | GC | Contingency | 20000 | 20000 | 0 |  | Reserve
Navigator Villas | 2024 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 44203 | 44203 | 0 |  | Reserve
Presidium Edgestone | 2024 | Sidewalks | Replace crushed granite path with concrete on front of community 600 LF 4 ft wide | 84115 | GC | Project | 41200 | 41200 | 0 |  | Completed
Presidium Edgestone | 2024 | Landscape irrigation | Adjust irrigation to not cause erosion to A/C pads | 84302 | GC | Project | 10000 | 10000 | 0 |  | Completed
Presidium Edgestone | 2024 | Fences & gates - site perimeter | Scrape and Paint perimeter fence. 3700 LF of fence PCA Item- A portion of the perimeter fencing on the south section of | 84205 | GC | Project | 29600 | 29600 | 0 |  | Completed
Presidium Edgestone | 2024 | Landscaping | Add turf and tree rings with rock to tree lines by rec area and parking lot side outside of pool to prevent erosion | 84303 | GC | Project | 37300 | 37300 | 0 |  | Completed
Presidium Edgestone | 2024 | Fences & gates - swimming pool | Repair and paint | 84205 | GC | Project | 6800 | 6800 | 0 |  | Completed
Presidium Edgestone | 2024 | Pergola court | Pressure wash and seal pavers in seating area | 84105 | GC | Project | 8700 | 8700 | 0 |  | Completed
Presidium Edgestone | 2024 | Playground equipment | Repair, scrape and paint pet park fence | 84340 | GC | Project | 6800 | 6800 | 0 |  | Completed
Presidium Edgestone | 2024 | Sidewalks | PCA Item- Potential trip hazards consisting of vertical separation were noted at the walkway southwest of the main build | 84115 | GC | Project | 2000 | 2000 | 0 |  | Completed
Presidium Edgestone | 2024 | Drainage | PCA Item- Ponding was observed along the exterior walls the parking garages M and L, south of Building 8. Regrading of t | 84517 | GC | Project | 7000 | 7000 | 0 |  | Completed
Presidium Edgestone | 2024 | ADA Parking Signage | PCA Item - ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at th | 84103 | GC | Project | 1000 | 1000 | 0 |  | Completed
Presidium Edgestone | 2024 | Repair swimming pool coping | Section of pool coping has separated from the deck, either repair with new sealant or re-set section of coping | 84361 | GC | Project | 5000 | 5000 | 0 |  | Completed
Presidium Edgestone | 2024 | Add Carports | Add 8 carports to test | 84219 | GC | Project | 30000 | 30000 | 0 |  | Completed
Presidium Edgestone | 2024 | Repair Corridor Walls | PCA Item- Cracking was observed in several areas of the corridor walls and ceilings throughout Building 1. This appears | 84120 | GC | Project | 6000 | 6000 | 0 |  | Completed
Presidium Edgestone | 2024 | Sealants & caulking and paint | Cut out and reseal lintels' on garage doors with elastomeric caulk 60 garages | 84113 | GC | Project | 6000 | 6000 | 0 |  | Completed
Presidium Edgestone | 2024 | Add Shower/Tub ADA compliant grab bars | Seller has completed half of the units, budget for 94 remaining units. All units are 1 bath | 83520 | GC | Project | 32900 | 32900 | 0 |  | Completed
Presidium Edgestone | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84211 | GC | Project | 22206 | 22206 | 0 |  | Completed
Presidium Edgestone | 2024 | Fire Lane Gates - Regulatory Compliance | PCA Item- All opticom sensors must work, or gates must remain open. On new and existing buildings, the address must be l | 84239 | GC | Project | 3000 | 3000 | 0 |  | Completed
Presidium Edgestone | 2024 | Elevator Permits | PCA Item- Current operation permits were not posted in each elevator cab. Property management should schedule re-inspect | 84905 | GC | Project | 3000 | 3000 | 0 |  | Completed
Presidium Edgestone | 2024 | Fire Riser Inspection | PCA Item- A yellow inspection tag was observed at the fire riser at Building 1 for a defective flow switch. Expired tags | 84239 | GC | Project | 3000 | 3000 | 0 |  | Completed
Presidium Edgestone | 2024 | Fire Extinguisher Inspection | PCA Item- Expired certification tags were present at the fire extinguishers Servicing and re-certification of the fire e | 84239 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Presidium Edgestone | 2024 | Fire Alarm Certification | PCA Item - A current annual fire alarm certification tag was not present at the fire alarm control panel. According to t | 84239 | PMC | Project | 2500 | 0 | 2500 |  | Not Started
Presidium Edgestone | 2024 | Green Initiatives | Green Program | 83515 | GC | Project | 100000 | 100000 | 0 |  | Completed
Presidium Edgestone | 2024 | Contingency | Contingency Amount | 84510 | GC | Contingency | 36551 | 36551 | 0 |  | Reserve
Presidium Edgestone | 2024 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 20103 | 20103 | 0 |  | Reserve
The Arbors | 2024 | Gas, Water, Sanitary Sewer Piping | Active leak on East side of community with temp line to the boilers this will have to be repaired and the gas lines will | 51132-00 | GC | Project | 200000 | 200000 | 0 |  | Completed
The Arbors | 2024 | Gas Submeter Replacements | Need to replace old submeters, 10% will be inspected each year by Orange County Weights & Measures. Summary from propert | 51200-00 | GC | Project | 96000 | 96000 | 0 |  | Completed
The Arbors | 2024 | Pavement | East side of community has deteriorated drives that need to be milled and overlayed From PCA- 3.2.1- The concrete draina | 51050-00 | GC | Project | 108000 | 108000 | 0 |  | Completed
The Arbors | 2024 | Stripe parking areas | Re-stripe From PCA- 3.2.2- The seal coat and stall striping appeared to be in fair condition. Based on the observed cond | 51053-00 | GC | Project | 14500 | 14500 | 0 |  | Completed
The Arbors | 2024 | Asphalt Coating | West side of community needs to be seal coated and crack fill From PCA- 3.2.2- Damaged pavement consisting of linear cra | 51053-00 | GC | Project | 49000 | 49000 | 0 |  | Completed
The Arbors | 2024 | Landscaping | Tree trim and landscape maintenance throughout From PCA- 3.2.4- Overgrown trees were observed to be in contact with the | 51043-00 | GC | Project | 30000 | 30000 | 0 |  | Completed
The Arbors | 2024 | Landscape irrigation | Inspect and repair | 51046-00 | GC | Project | 21000 | 21000 | 0 |  | Completed
The Arbors | 2024 | Fences & gates - site perimeter | Paint Iron fencing on perimeter of community | 51076-00 | GC | Project | 25000 | 25000 | 0 |  | Completed
The Arbors | 2024 | Resurface swimming pool | Resurface two hot tubs | 51023-00 | GC | Project | 32000 | 32000 | 0 |  | Completed
The Arbors | 2024 | Replace swimming pool coping | Deck o seal both pools | 51021-00 | GC | Project | 14500 | 14500 | 0 |  | Completed
The Arbors | 2024 | Replace swimming pool deck | Both pool decks need to be cleaned, etched and coated. Replacing decks add $60k totalAt Leasing pool- look at changing e | 51022-00 | GC | Project | 50000 | 50000 | 0 |  | Completed
The Arbors | 2024 | Repair / replace swimming pool pumps | Anti entrapment devices | 51026-00 | GC | Project | 12900 | 12900 | 0 |  | Completed
The Arbors | 2024 | Fences & gates - swimming pool | Repair gates and paint At gym pool- fix exit gate eye level hinge so it doesn't protrude | 51076-00 | GC | Project | 16000 | 16000 | 0 |  | Completed
The Arbors | 2024 | Carports / Garages | Replace rotted wood and paint parking buildings Exterior only | 51172-00 | GC | Project | 95000 | 95000 | 0 |  | Completed
The Arbors | 2024 | Dumpster enclosures | Repair and Paint | 51163-00 | GC | Project | 9000 | 9000 | 0 |  | Completed
The Arbors | 2024 | ADA Accessibility | From PCA- 7.0- Parking areas that provide self-parking for employees and visitors must provide ADA-compliant parking spa | 51169-00 | GC | Project | 2000 | 2000 | 0 |  | Completed
The Arbors | 2024 | Termite Treatment & Repairs | WDIR treatment and repairs will be required by lender within 60-90 days of closing. Reference Terminix report and quote | 51992-00 | GC | Project | 40000 | 40000 | 0 |  | Completed
The Arbors | 2024 | Repair exterior stair railings | Secure rails | 51077-00 | GC | Project | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Repair balcony framing & decking | Place Holder to have all balconies inspected and repaired | 51072-00 | GC | Project | 160000 | 160000 | 0 |  | Completed
The Arbors | 2024 | Repair patio/balcony railings | Secure rails | 51077-00 | GC | Project | 6000 | 6000 | 0 |  | Completed
The Arbors | 2024 | Expansion Joints | Re-seal expansions | 51070-00 | GC | Project | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Asphalt composite shingle roofing | Reportedly roofs were replaced on unit building 4 years ago however the ancillary buildings were not done. Allowance fo | 51061-00 | GC | Project | 35000 | 35000 | 0 |  | Completed
The Arbors | 2024 | Gutters & downspouts | Clean, re-pitch and resecure gutters | 51071-00 | GC | Project | 14000 | 14000 | 0 |  | Completed
The Arbors | 2024 | Flashing | replace damaged z bar on siding replacement | 51062-00 | GC | Project | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Sealants & caulking | caulk and seal | 51062-00 | GC | Project | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Repair / replace wood siding | Replace rotted siding | 51075-00 | GC | Project | 14000 | 14000 | 0 |  | Completed
The Arbors | 2024 | Repair stucco |  | 51075-00 | GC | Project | 16000 | 16000 | 0 |  | Completed
The Arbors | 2024 | Interior Hallway painting | Paint hallways and front doors, Stripe stair treads in breezeways to address trip hazards | 51160-00 | GC | Project | 32000 | 32000 | 0 |  | Completed
The Arbors | 2024 | Exterior building | Paint exterior From PCA- 4.3.1- The paint finish on the apartment buildings was noted to be chipping and worn. Based on | 51080-00 | GC | Project | 200000 | 200000 | 0 |  | Completed
The Arbors | 2024 | Repair / replace wood trim | Replace rotted trim and fascia | 51082-00 | GC | Project | 26000 | 26000 | 0 |  | Completed
The Arbors | 2024 | Unit Patio Concrete | From PCA- 3.2.3- Uplifting concrete patio slabs was observed at Units 136, 139, and 107. The upheaval appears to be due, | 51090-00 | GC | Project | 10500 | 10500 | 0 |  | Completed
The Arbors | 2024 | C02 Dectors | Install CO2 detectors | 51993-01 | PMC | Project | 7200 | 0 | 7200 |  | Not Started
The Arbors | 2024 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 51993-01 | PMC | Project | 7656 | 0 | 7656 |  | Not Started
The Arbors | 2024 | Signage - Entry Monument | Refresh 1 sign, replace the other, replace wall banner facing Fairhaven | 51031-00 | PMC | Project | 15000 | 29576 | -14576 |  | Completed
The Arbors | 2024 | Signage - Site | Refresh | 51032-00 | PMC | Project | 10000 | 17469 | -7469 |  | Completed
The Arbors | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 51990-00 | PMC | Project | 3000 | 10357 | -7357 |  | Completed
The Arbors | 2024 | Leasing Office Remodel | Refresh paint on accent wall to brighten space, flooring, add lighting | 51169-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | Leasing Office Furniture | Ok, small allowance | 51995-00 | PMC | Project | 2000 | 1243 | 757 |  | In Progress
The Arbors | 2024 | Computers | Allowance for new office computers and software, printer, office supplies | 51995-00 | PMC | Project | 4000 | 0 | 4000 |  | Not Started
The Arbors | 2024 | Fitness Center Remodel | Fix front door, add lighting, replace fan with something more commercial, add mini split HVAC, new larger TV, add rubber | 51160-00 | GC | Project | 20000 | 20000 | 0 |  | Completed
The Arbors | 2024 | Fitness Equipment | Refresh equipment, add stair stepper | 51028-00 | PMC | Project | 10000 | 8000 | 2000 |  | In Progress
The Arbors | 2024 | Pool Area Remodel- 2 pools | Allowance for lighting, other enhancements | 51011-00 | GC | Project | 20000 | 20000 | 0 |  | Completed
The Arbors | 2024 | Pool Furniture- 2 pools | New furniture & games | 51011-00 | GC | Project | 70000 | 70000 | 0 |  | Completed
The Arbors | 2024 | Picnic/Grill Furniture | Allowance for new grills, furniture & misc items, move concrete furniture from pool to picnic area | 51160-04 | GC | Project | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | Sports Courts | Resurface, look at pickleball, replace basketball system if that stays | 51027-00 | GC | Project | 10000 | 10000 | 0 |  | Completed
The Arbors | 2024 | Dog Park | Water/Wash Station with concrete pad | 51029-00 | GC | Project | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Property Photo Shoot | Professional photos and vdeo of remodeled exterior areas, unit interiors when applicable | 51180-00 | PMC | Project | 4000 | 5102 | -1102 |  | Completed
The Arbors | 2024 | Access Control System | Add at entry gates and fitness center | 51993-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | Package Lockers | Add package locker system | 51168-00 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
The Arbors | 2024 | Laundry rooms- one on each side | Paint refresh, replace track lighting, resurface or replace counter, look at adding equipment From PCA- 4.3.3- Worn doo | 51166-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | New storage units by leasing office pool | Add 8 new units against car port wall, behind existing storage units | 51998-00 | GC | Project | 40000 | 40000 | 0 |  | Completed
The Arbors | 2024 | Tools & Equipment | Maintenance tools, equipment, & inventory | 51998-00 | PMC | Project | 7000 | 654 | 6346 |  | In Progress
The Arbors | 2024 | Common area water heaters / boilers | 3 Boilers are reported to be original, contingency for replacement. 1 goes out frequently and they have a bid for $21k t | 51110-00 | GC | Project | 63000 | 63000 | 0 |  | Completed
The Arbors | 2024 | Sanitary sewer piping | Sewer Pipe Jetting | 51134-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | HVAC | Contingency for HVAC replacements From PCA- 5.2- While generally reported to be functional, approximately 80% of the uni | 51120-00 | GC | Project | 75000 | 75000 | 0 |  | Completed
The Arbors | 2024 | Electrical distribution | Place holder to replace Zinsco Load center in each unit ( Zinsco breakers have not been formally recalled however are co | 51140-00 | GC | Project | 380000 | 380000 | 0 |  | Completed
The Arbors | 2024 | Replace breezeway lights | Replace ceiling lights in breezeways | 51141-00 | GC | Project | 28000 | 28000 | 0 |  | Completed
The Arbors | 2024 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 70064 | 70064 | 0 |  | Reserve
The Arbors | 2024 | Construction Management Fee | CM Fees | 51190-00 | GC | CM Fee | 116966 | 116966 | 0 |  | Reserve
Village at Broadstone | 2024 | Stripe parking areas | Clean parking lot of debris and oil, crack fill 3000lf. Apply one coat of latex sealer and stripe to existing layout. In | 0200 - Site Utilities & Improvements | GC | Project | 29000 | 29000 | 0 |  | Completed
Village at Broadstone | 2024 | Compactor Ramp | Build an ADA ramp at the compactor. | 0200 - Site Utilities & Improvements | GC | Project | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Sidewalks | Remove and replace approx 375sf of concrete sidewalk. Perform approx. 40EA grinds at lifted sidewalk seams. | 0200 - Site Utilities & Improvements | GC | Project | 12000 | 12000 | 0 |  | Completed
Village at Broadstone | 2024 | Landscape Irrigation & Drainage | Repair, replace and troubleshoot exhisting irrigation system. | 0200 - Site Utilities & Improvements | GC | Project | 81000 | 81000 | 0 |  | Completed
Village at Broadstone | 2024 | Irrigation Repairs | 4 Rain bird 5000, 15 Rain bird 1806, 6 MP Rotator Nozzles, 33 Rain bird Nozzles, 2 Wireless Rain sensors, 7 zones not ru | 0200 - Site Utilities & Improvements | GC | Project | 4400 | 4400 | 0 |  | Completed
Village at Broadstone | 2024 | Tree Trim & Shrub Cutback | Trim trees & reduce shrubs where appropriate. Remove dead tree throughout all 3 phases to prevent any future damage to b | 0200 - Site Utilities & Improvements | GC | Project | 30000 | 30000 | 0 |  | Completed
Village at Broadstone | 2024 | Landscaping Enhancements | Remove, add plants. | 0200 - Site Utilities & Improvements | GC | Project | 40000 | 40000 | 0 |  | Completed
Village at Broadstone | 2024 | Fences & gates - swimming pool | Add fence between pool and grill area, repair broken pool gate latch | 0200 - Site Utilities & Improvements | GC | Project | 9500 | 9500 | 0 |  | Completed
Village at Broadstone | 2024 | Grill stations | Upgrade grill stations with new Bull Outlaw grill heads, granite countertops and gas timers. Repair and paint pergolas. | 0200 - Site Utilities & Improvements | GC | Project | 15000 | 15000 | 0 |  | Completed
Village at Broadstone | 2024 | Playground equipment | Add mulch and plastic coat damaged landings | 0200 - Site Utilities & Improvements | GC | Project | 8000 | 8000 | 0 |  | Completed
Village at Broadstone | 2024 | Roof Repairs | Remove rusted nails on pipe boots across the community. Install new rain collars, screws, and seal bottom flanges. Remov | 0700 - Roofing | GC | Project | 57000 | 57000 | 0 |  | Completed
Village at Broadstone | 2024 | Soffit/roof fascia repair | Repair where failing, building 5 & others | 0800 - Exterior Wall | GC | Project | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Bldg. Exterior Cladding | Repair damaged fiber cement siding and trim. Secure shutters. Repair damaged metal fascia, metal row lock flashing and v | 0800 - Exterior Wall | GC | Project | 14500 | 14500 | 0 |  | Completed
Village at Broadstone | 2024 | Exterior Paint | Paint one coat of SW Superpaint on the siding, trim, shutters, doors, railings and ammenities. | 0800 - Exterior Wall | GC | Project | 270000 | 270000 | 0 |  | Completed
Village at Broadstone | 2024 | Shutters | Paint or replace faded shutters | 0800 - Exterior Wall | GC | Project | 15000 | 15000 | 0 |  | Completed
Village at Broadstone | 2024 | Window screens | Contingency to remove and replace some of the 1/2 screens on the windows of the residential units and clubhouse. | 0800 - Exterior Wall | GC | Project | 20000 | 20000 | 0 |  | Completed
Village at Broadstone | 2024 | A1 | Classic | 0900 - FF&E in Units | GC | Project | 129331 | 129331 | 0 |  | Completed
Village at Broadstone | 2024 | A2 | Classic | 0900 - FF&E in Units | GC | Project | 532909 | 532909 | 0 |  | Completed
Village at Broadstone | 2024 | B1 | Classic | 0900 - FF&E in Units | GC | Project | 148907 | 148907 | 0 |  | Completed
Village at Broadstone | 2024 | B2 | Classic | 0900 - FF&E in Units | GC | Project | 420525 | 420525 | 0 |  | Completed
Village at Broadstone | 2024 | B3 | Classic | 0900 - FF&E in Units | GC | Project | 427214 | 427214 | 0 |  | Completed
Village at Broadstone | 2024 | C1 | Classic | 0900 - FF&E in Units | GC | Project | 272985 | 272985 | 0 |  | Completed
Village at Broadstone | 2024 | A1 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Project | 45402 | 45402 | 0 |  | Completed
Village at Broadstone | 2024 | A2 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Project | 184968 | 184968 | 0 |  | Completed
Village at Broadstone | 2024 | B1 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Project | 47544 | 47544 | 0 |  | Completed
Village at Broadstone | 2024 | B2 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Project | 139230 | 139230 | 0 |  | Completed
Village at Broadstone | 2024 | B3 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Project | 125874 | 125874 | 0 |  | Completed
Village at Broadstone | 2024 | C1 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Project | 78713 | 78713 | 0 |  | Completed
Village at Broadstone | 2024 | A2 | Premium Reno- SS Appliances & Flooring | 0900 - FF&E in Units | GC | Project | 11560 | 11560 | 0 |  | Completed
Village at Broadstone | 2024 | B3 | Premium Reno- SS Appliances & Flooring | 0900 - FF&E in Units | GC | Project | 13986 | 13986 | 0 |  | Completed
Village at Broadstone | 2024 | C1 | Premium Reno- SS Appliances & Flooring | 0900 - FF&E in Units | GC | Project | 7156 | 7156 | 0 |  | Completed
Village at Broadstone | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 0900 - FF&E in Units | GC | Project | 35063 | 35063 | 0 |  | Completed
Village at Broadstone | 2024 | Drier vents | Clean drier vents | 0900 - FF&E in Units | GC | Project | 22500 | 22500 | 0 |  | Completed
Village at Broadstone | 2024 | Signage - Site | Change signage for leasing hours since they are not open Sundays, add hanging clock for Sunday hours | 1100- Specialties, Equipment & Furnishings | PMC | Project | 250 | 0 | 250 |  | Not Started
Village at Broadstone | 2024 | Clubhouse / Office Remodel | New flooring, paint in the clubhouse to modernize it, using Bell Apex clubhouse as a target finish level. | 1100- Specialties, Equipment & Furnishings | GC | Project | 130000 | 130000 | 0 |  | Completed
Village at Broadstone | 2024 | Clubhouse / Office Furniture | New FF&E | 1100- Specialties, Equipment & Furnishings | GC | Project | 70000 | 70000 | 0 |  | Completed
Village at Broadstone | 2024 | Fitness Center Remodel | Add conduit for power and data cables to TVs | 1100- Specialties, Equipment & Furnishings | GC | Project | 3000 | 3000 | 0 |  | Completed
Village at Broadstone | 2024 | Fitness Equipment | Need new equipment, stairstepper, have rack, need more weights | 1100- Specialties, Equipment & Furnishings | GC | Project | 35000 | 35000 | 0 |  | Completed
Village at Broadstone | 2024 | Pool Area Remodel | Move gate/fencing in so that the grill area can be used when the pool is closed, add TV above sink under pool grill perg | 1100- Specialties, Equipment & Furnishings | GC | Project | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Pool Furniture | New furniture to replace existing strap, new lounge seating, bar stools, cornhole, other games | 1100- Specialties, Equipment & Furnishings | GC | Project | 45000 | 45000 | 0 |  | Completed
Village at Broadstone | 2024 | Picnic/Grill Area Remodel | For 2 grill areas outside of pool-Add full covered pergola over grill | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Village at Broadstone | 2024 | Picnic/Grill Furniture | Add benches by cornhole, misc furniture | 1100- Specialties, Equipment & Furnishings | GC | Project | 3000 | 3000 | 0 |  | Completed
Village at Broadstone | 2024 | Dog Park | Water/Wash Station with concrete pad Shade sail or pergola | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 15000 | 0 |  | Completed
Village at Broadstone | 2024 | Unit Model Update | New furniture in model unit | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 20000 | 0 |  | Completed
Village at Broadstone | 2024 | Correct and Close OpenViolation | PCA Item- $100- Open code violation report by building department (expired permit) should be corrected and closed. | 1100- Specialties, Equipment & Furnishings | PMC | Project | 100 | 0 | 100 |  | Not Started
Village at Broadstone | 2024 | Fire Sprinklers | PCA Item- $40,818- Replace deficient sprinkler heads, per inspection report. | 1400 - Plumbing | GC | Project | 40818 | 40818 | 0 |  | Completed
Village at Broadstone | 2024 | Provide Drain Pans for Domestic Hot Water Heaters | From MEPFLS Report- Several domestic water heaters in residential units were observed to be missing drain pans. Partner | 1400 - Plumbing | GC | Project | 5000 | 5000 | 0 |  | Completed
Village at Broadstone | 2024 | Scope and Clear Sewer Lines | From MEPFLS Report- Recent scoping and clearing of the sanitary drain lines was not reported; therefore, Partner recomme | 1400 - Plumbing | GC | Project | 5000 | 5000 | 0 |  | Completed
Village at Broadstone | 2024 | HVAC Replacements | Cost to replace two units at $5,200/unit | 1500- HVAC | GC | Project | 10400 | 10400 | 0 |  | Completed
Village at Broadstone | 2024 | Replace Refrigerant Line Insulation | From MEPFLS Report- Insulation at the refrigerant lines at the outdoor condensing units were observed to be deteriorated | 1500- HVAC | GC | Project | 7500 | 7500 | 0 |  | Completed
Village at Broadstone | 2024 | Replace all balcony ceiling lights & breezeway lights | Replace dated fixtures | 1600 - Electrical | GC | Project | 25000 | 25000 | 0 |  | Completed
Village at Broadstone | 2024 | Fire and Life Safety | Repair pull stations throughout the property. Install a riser room sign where missing, install fire extinguishers and re | 1600 - Electrical | GC | Project | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Common area light fixtures | Possibly replace remaining halogen parking lot pole lights with LED | 1600 - Electrical | GC | Project | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 186467 | 186467 | 0 |  | Reserve
Avenues of Kennesaw | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84303 | PMC | Project | 75000 | 165469 | -90469 |  | Completed
Avenues of Kennesaw | 2025 | Storm sewer piping | Clear drains around buildings | 84385 | GC | Project | 25000 | 25000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Pavement | Repair potholes on both sides of community Equity PCA Item- 3.2.2- Linear cracking, "map", or "alligator | 84204 | GC | Project | 80000 | 80000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Stripe parking areas | Stripe Parking Areas | 84201 | GC | Project | 28000 | 28000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Asphalt Coating | Crack fill cracks over 1/2 inch | 84204 | GC | Project | 50000 | 50000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Sidewalks | Remove and replace areas of trip hazards Lender PCA (Walkw | 84115 | GC | Project | 46000 | 46000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Erosion control | Fill eroded areas around buildings Equity PCA Item- 3.2.4-Significant areas of missing or lost ground cover were noted | 84517 | GC | Project | 70000 | 70000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Retaining walls | Repair fences on retaining walls Equity PCA Item- 4.1- The segmental retaining walls at the East Aparments contained loo | 84434 | GC | Project | 25000 | 25000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Resurface swimming pool | Resurface both pools, Replace missing pool tile at water line | 84095 | GC | Project | 60000 | 60000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Replace swimming pool coping | Repair or replace broken coping Lender | 84361 | GC | Project | 5000 | 5000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Replace swimming pool deck | Pressure wash pool decks, , level paver trip hazards | 84361 | GC | Project | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Swimming pool lighting | Replace pool lights | 84361 | GC | Project | 36000 | 36000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Fences & gates - swimming pool | Adjust gates and repair gate latches | 84205 | GC | Project | 18000 | 18000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Outdoor Kitchen | Pressure wash area and allowance for grill repairs or replacement with charcoal | 84203 | GC | Project | 10000 | 10000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Carports / Garages | Repair garage siding and trim Equi | 84219 | GC | Project | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Dumpster enclosures | Repair compactor areas | 84111 | GC | Project | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | ADA Compliance | Equity PCA Item- 7.0- Reconfigure leasing office restroom for ADA compliance | 83520 | GC | Project | 4500 | 4500 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Concrete deck / floor fill | Grind and seal cracks in light weight concrete landings | 84430 | GC | Project | 27000 | 27000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Roof deck | Roof Deck Repairs | 84433 | GC | Project | 12000 | 12000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair exterior stair treads and stringers | Replace 90 wood and concrete stair treads. Replace damaged railing on stair cases. Equity PCA Item- 4.2- The wood-framed | 84114 | GC | Project | 94000 | 94000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair balcony framing & decking | Repair balconies Equity PCA Item- 4.1- Rout and seal all cracks in the concrete patios. Periodically monitor for further | 84104 | GC | Project | 150000 | 150000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair patio/balcony railings | Repair balcony railings | 84121 | GC | Project | 68000 | 68000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Expansion Joints | Property Expansion Joints | 84102 | GC | Project | 32000 | 32000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Asphalt composite shingle roofing | Roof repairs Equity PCA Item- 4.4.1- Allowance for replacement of shingles and possible decking | 84433 | GC | Project | 190919 | 190919 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Gutters & downspouts | Clean, repitch, and secure gutters. Ongoing gutter cleanout. Equity PCA Item- 4.4.2- Allowance for replacement of gutte | 83439 | GC | Project | 66000 | 66000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Flashing | Repair damaged flashing | 84433 | GC | Project | 50000 | 50000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Sealants & caulking | Roof Sealants & Caulking | 84433 | GC | Project | 18000 | 18000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair/Replace roof pipe vents | Equity PCA Item- 4.4.1- Allowance for replacement of all pipe penetrations lot wide | 84433 | GC | Project | 38750 | 38750 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair / replace cement fiber siding | Replace rotted Masonite siding with Hardie on west side Equity PCA Item- 4.3.1- Replacement of deteriorated and damaged | 84206 | GC | Project | 220000 | 220000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Breezeways - Interior Coordiors | Repair soffits | 84120 | GC | Project | 32000 | 32000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Exterior building | Repaint community, west side will need special process in order to seal Masonite to prevent future delamination | 84101 | GC | Project | 733600 | 733600 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair / replace wood trim | Replace damaged trim Equity PCA Item- 4.5- Allowance to refurbish wood trim and balconies around subject property where | 84105 | GC | Project | 124000 | 124000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Shutters | Replace damaged shutters | 84206 | GC | Project | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Windows | Equity PCA Item- 4.3.2- Phased Replacement of dwelling window units from wood framed to aluminum framed - West Campus Eq | 83436 | GC | Project | 215740 | 203240 | 12500 |  | In Progress
Avenues of Kennesaw | 2025 | Interior Unit Upgrades | Interior Unit Upgrades | 84207 | GC | Project | 300585 | 0 | 300585 |  | Not Started
Avenues of Kennesaw | 2025 | Clean Dryer vents | Dryer Vent Cleaning | 84106 | GC | Project | 39300 | 39300 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Washer & Dryer in Unit | Washer & Dryer Modifications | 82480 | GC | Project | 493324 | 0 | 493324 |  | Not Started
Avenues of Kennesaw | 2025 | Fire Stops | Mix of Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods and LowPro (Pair covers 4 burner range)- For r | 84239 | PMC | Project | 61944 | 47962 | 13982 |  | In Progress
Avenues of Kennesaw | 2025 | Unit deferred maintenance | Equity PCA Item- 8.0- Address potential water intrusion, Unit 403 East. Equity PCA Item- 8.0- Address potential microbia | 82460 | GC | Project | 6500 | 6500 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Signage - Entry Monument | Reface or possibly enlarge 2 monument signs | 84290 | PMC | Project | 25000 | 25101 | -101 |  | Completed
Avenues of Kennesaw | 2025 | Clubhouse / Office Remodel | Minor refresh & repairs | 84208 | GC | Project | 20000 | 20000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Clubhouse / Office Furniture | Misc furniture items | 84208 | PMC | Project | 20000 | 106226 | -86226 |  | Completed
Avenues of Kennesaw | 2025 | Fitness Center Remodel | Paint and misc repairs | 84190 | GC | Project | 10000 | 10000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Fitness Equipment | Equipment repairs and some new equipment | 84190 | PMC | Project | 15000 | 3712 | 11288 |  | In Progress
Avenues of Kennesaw | 2025 | Pool Area Remodel | Turf areas around pool | 84361 | GC | Project | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Pool Furniture | New furniture at 2 pools | 84360 | PMC | Project | 70000 | 9000 | 61000 |  | In Progress
Avenues of Kennesaw | 2025 | Sports Courts | Resurface 3 courts, fix net and stripe for pickleball as well, add pergola, seating, etc. | 84390 | GC | Project | 175000 | 175000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Veritas After School Care | Housing Authority Program (Veritas) - Additional School Room | 84208 | PMC | Project | 10000 | 53113 | -43113 |  | Completed
Avenues of Kennesaw | 2025 | Mailboxes | Lender PCA (Mailbox Repair): Several mailboxes were noted to contain damaged or missing doors. Repair of the mailboxes i | 84260 | PMC | Project | 500 | 5894 | -5394 |  | Completed
Avenues of Kennesaw | 2025 | Entry gates | None, can look at adding but there are 4 access drives | 84275 | GC | Project | 60000 | 0 | 60000 |  | Not Started
Avenues of Kennesaw | 2025 | Security Camera System | Security Cameras | 84450 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Avenues of Kennesaw | 2025 | Water pressure regulator / back-flow preventer | Equity PCA Item- 5.1- Observed water heaters were often not provided with drain pans and lacked discharge piping from th | 84209 | GC | Project | 52500 | 52500 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Plumbing Repairs | Plumbing Fixture Leaks, Ongoing repairs due to high number of work orders. Plumbing Repairs: Ongoing repair of water lea | 84470 | PMC | Project | 23000 | 15546 | 7454 |  | In Progress
Avenues of Kennesaw | 2025 | Fire Protection Deficiencies | Equity PCA Item- 5.5.1- General fire protection deficiencies were observed. The observed general deficiencies included | 84211 | PMC | Project | 4500 | 39243 | -34743 |  | Completed
Avenues of Kennesaw | 2025 | Fire Alarm Deficiencies | Equity PCA Item- 5.5.1- The fire alarm annual inspection report was not provided. Reports often include recommendations | 84211 | PMC | Project | 9000 | 78487 | -69487 |  | Completed
Avenues of Kennesaw | 2025 | Fire Sprinkler Risers | Equity PCA Item- 5.5.1- The following risers were observed to have missing 5-year riser inspection tags: 500E, 600E, 300 | 84400 | PMC | Project | 30000 | 0 | 30000 |  | Not Started
Avenues of Kennesaw | 2025 | Fire Sprinklers | Equity PCA Item- 5.5.1- General fire sprinkler deficiencies were observed. The observed general deficiencies included da | 84400 | PMC | Project | 16030 | 600 | 15430 |  | In Progress
Avenues of Kennesaw | 2025 | Radon Remediation | Radon Mitigation | 84905 | GC | Project | 10000 | 10000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Water Intrusion Remediation | The SOW will include replacing bathroom vent fans and cleaning dirty AC coils, removing dry water staining and repaintin | 84905 | GC | Project | 200000 | 200000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Office Faucet | Office Faucet Replacement | 84209 | GC | Project | 8000 | 8000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Green Program - Echelon Water Savings | Installation of aerators on faucets and shower heads | 83515 | GC | Project | 42312 | 42312 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Condensate drain overflow sensors | Equity PCA Item- 5.2- The fan coil units were not fitted with condensate drain overflow sensors. As installed, clogged d | 83225 | GC | Project | 26200 | 26200 | 0 |  | Completed
Avenues of Kennesaw | 2025 | HVAC Preventative Maintenance | Equity PCA Item- 5.2- The fan coil units were observed with dirty coils and filters at Units 318E, 1017W, 303E. Partner | 83225 | GC | Project | 15750 | 15750 | 0 |  | Completed
Avenues of Kennesaw | 2025 | HVAC Preventative Maintenance | Equity PCA Item- 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | 83225 | GC | Project | 13100 | 13100 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Electrical distribution | inspect, repair or replace lighting controllers | 84210 | GC | Project | 33000 | 33000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Common area light fixtures | Replace wall pack lights | 84210 | GC | Project | 36000 | 36000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Electrical Repairs | Equity PCA Item- 5.3- General electrical deficiencies were observed including GFCI outlets , exit lighting, receptacle c | 84210 | GC | Project | 26000 | 26000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Emergency Lighting | Equity PCA Item- 5.3- Emergency lights were not installed at any West buildings. Installation of emergency lighting is r | 84239 | GC | Project | 10800 | 10800 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 258304 | 0 | 258304 |  | Reserve
Avenues of Kennesaw | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 271220 | 0 | 271220 |  | Reserve
Azur Aparments | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Storm sewer piping | Replace drainage on pool deck with larger channel drains and connect to proper drain | 0200 - Site Utilities & Improvements | GC | Project | 25000 | 0 | 25000 |  | Not Started
Azur Aparments | 2025 | Pavement | Large areas of asphalt paving Lender PCR Item- $6,000- Several pot holes and areas of “alligatoring”and general deterior | 0200 - Site Utilities & Improvements | GC | Project | 91000 | 63700 | 27300 |  | In Progress
Azur Aparments | 2025 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Project | 11000 | 7700 | 3300 |  | In Progress
Azur Aparments | 2025 | Asphalt Coating | Seal coat lot Equity PCA Item 3.2.2- $42,000- The seal coating appeared to be generally worn with several areas of loos | 0200 - Site Utilities & Improvements | GC | Project | 80000 | 56000 | 24000 |  | In Progress
Azur Aparments | 2025 | ADA parking & curb cuts | Replace ADA signage | 0200 - Site Utilities & Improvements | GC | Project | 6800 | 4760 | 2040 |  | In Progress
Azur Aparments | 2025 | Landscape irrigation | Inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Project | 29000 | 0 | 29000 |  | Not Started
Azur Aparments | 2025 | Erosion control |  | 0200 - Site Utilities & Improvements | GC | Project | 26000 | 0 | 26000 |  | Not Started
Azur Aparments | 2025 | Retaining walls | Replace damaged railroad tie wall | 0200 - Site Utilities & Improvements | GC | Project | 12000 | 0 | 12000 |  | Not Started
Azur Aparments | 2025 | Resurface swimming pool |  | 0200 - Site Utilities & Improvements | GC | Project | 30000 | 0 | 30000 |  | Not Started
Azur Aparments | 2025 | Replace swimming pool coping | Deck o seal | 0200 - Site Utilities & Improvements | GC | Project | 8600 | 0 | 8600 |  | Not Started
Azur Aparments | 2025 | Repair / replace swimming pool pumps | Anti entrapment devices | 0200 - Site Utilities & Improvements | GC | Project | 6800 | 0 | 6800 |  | Not Started
Azur Aparments | 2025 | Fences & gates - swimming pool | Repair and paint Equity PCA Item 3.2.7- $7,500- Partner observed some areas of damaged fencing along the northwest peri | 0200 - Site Utilities & Improvements | GC | Project | 9600 | 0 | 9600 |  | Not Started
Azur Aparments | 2025 | Dumpster enclosures | Repair dumpster enclosures | 0200 - Site Utilities & Improvements | GC | Project | 16000 | 0 | 16000 |  | Not Started
Azur Aparments | 2025 | Accessibility | Lender PCR Item- $1,350- Lack of accessible toilet room at the leasing office including lack of lever hardware, toilet g | 0200 - Site Utilities & Improvements | GC | Project | 1650 | 0 | 1650 |  | Not Started
Azur Aparments | 2025 | Fences & Gates - Site Perimeter | Lender PCR Item- $7,500- Partner observed some areas of damaged fencing along the northwest perimeter as well as a porti | 0200 - Site Utilities & Improvements | GC | Project | 7500 | 5250 | 2250 |  | In Progress
Azur Aparments | 2025 | Arbor Realty Trust Deferred Maintenance Items | Items noted from lender inspection, items due 11/11/24 & 4/9/25. Property owner only completing November items | 0200 - Site Utilities & Improvements | GC | Project | 10000 | 0 | 10000 |  | Not Started
Azur Aparments | 2025 | Concrete deck / floor fill | Entrance landings | 0400 - Structure | GC | Project | 18000 | 12600 | 5400 |  | In Progress
Azur Aparments | 2025 | Wall framing |  | 0400 - Structure | GC | Project | 1500 | 0 | 1500 |  | Not Started
Azur Aparments | 2025 | Repair exterior stair treads and stringers | Replace bad stair treads | 0400 - Structure | GC | Project | 26000 | 0 | 26000 |  | Not Started
Azur Aparments | 2025 | Repair exterior stair railings | Repair and Paint | 0400 - Structure | GC | Project | 30000 | 0 | 30000 |  | Not Started
Azur Aparments | 2025 | Repair balcony framing & decking |  | 0400 - Structure | GC | Project | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Asphalt composite shingle roofing | Minor roof repairs | 0700 - Roofing | GC | Project | 17000 | 0 | 17000 |  | Not Started
Azur Aparments | 2025 | Gutters & downspouts | Clean gutters | 0700 - Roofing | GC | Project | 17000 | 0 | 17000 |  | Not Started
Azur Aparments | 2025 | Flashing |  | 0700 - Roofing | GC | Project | 3400 | 0 | 3400 |  | Not Started
Azur Aparments | 2025 | Sealants & caulking |  | 0700 - Roofing | GC | Project | 6800 | 0 | 6800 |  | Not Started
Azur Aparments | 2025 | Repair / replace cement fiber siding | Replace damaged siding in breezeways | 0800 - Exterior Wall | GC | Project | 17000 | 0 | 17000 |  | Not Started
Azur Aparments | 2025 | Tuck-pointing | Tuck point and caulk | 0800 - Exterior Wall | GC | Project | 12000 | 0 | 12000 |  | Not Started
Azur Aparments | 2025 | Exterior building | Paint Community Lender PCR Item- $62,400- The exterior walls appeared to be in generally good to fair condition. Isolat | 0800 - Exterior Wall | GC | Project | 208000 | 145600 | 62400 |  | In Progress
Azur Aparments | 2025 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Project | 28000 | 0 | 28000 |  | Not Started
Azur Aparments | 2025 | storage room doors - exterior | Replace damaged storage room doors | 0800 - Exterior Wall | GC | Project | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Clean Drier vents |  | 0900 - FF&E in Units | GC | Project | 15600 | 0 | 15600 |  | Not Started
Azur Aparments | 2025 | Unit Exhaust Fan | Equity PCA Item 5.2- $500- Apartment 502 was noted to have a missing exhaust fan in one of its bathrooms that did not ha | 0900 - FF&E in Units | GC | Project | 500 | 0 | 500 |  | Not Started
Azur Aparments | 2025 | Turf private yards | Approximately 96 units with yards that we can turf | 0900 - FF&E in Units | GC | Project | 86400 | 0 | 86400 |  | Not Started
Azur Aparments | 2025 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 0900 - FF&E in Units | GC | Project | 10048 | 0 | 10048 |  | Not Started
Azur Aparments | 2025 | Unit deferred maintenance | There are 8 down units- all of Building #16 is down due to fire Appx. 57 units noted to have prior water stains on the d | 0900 - FF&E in Units | GC | Project | 30000 | 0 | 30000 |  | Not Started
Azur Aparments | 2025 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 1100- Specialties, Equipment & Furnishings | GC | Project | 2500 | 1750 | 750 |  | In Progress
Azur Aparments | 2025 | Clubhouse / Office Remodel | Flooring & paint ok, look at additional HVAC or insulation in roof since it gets very hot in clubhouse. Misc repairs a | 1100- Specialties, Equipment & Furnishings | GC | Project | 10000 | 7000 | 3000 |  | In Progress
Azur Aparments | 2025 | Clubhouse / Office Furniture | New furniture in clubhouse, supplement furniture in office | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 28000 | 12000 |  | In Progress
Azur Aparments | 2025 | Pool Area Remodel | Look at adding shade areas over pool and grill | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Pool Furniture & Games |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 40000 | 28000 | 12000 |  | In Progress
Azur Aparments | 2025 | Picnic/Grill Area Remodel | Add grill area with gazebo and furniture by mail area | 1100- Specialties, Equipment & Furnishings | GC | Project | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Picnic/Grill Furniture |  | 1100- Specialties, Equipment & Furnishings | GC | Project | 10000 | 7000 | 3000 |  | In Progress
Azur Aparments | 2025 | Dog Park | Look at adding more furniture, jumps, shade | 1100- Specialties, Equipment & Furnishings | GC | Project | 15000 | 10500 | 4500 |  | In Progress
Azur Aparments | 2025 | Access Control System | Office alarm and restore night drop box for keys needed | 1100- Specialties, Equipment & Furnishings | GC | Project | 10000 | 7000 | 3000 |  | In Progress
Azur Aparments | 2025 | Grills | Misc repairs | 1100- Specialties, Equipment & Furnishings | GC | Project | 2000 | 0 | 2000 |  | Not Started
Azur Aparments | 2025 | Golf Cart | Need leasing cart | 1100- Specialties, Equipment & Furnishings | GC | Project | 9000 | 0 | 9000 |  | Not Started
Azur Aparments | 2025 | Domestic water piping | Insulate main water lines going into buildings Equity PCA Item 5.1- $5,000-The domestic water piping at the central dome | 1400 - Plumbing | GC | Project | 11000 | 0 | 11000 |  | Not Started
Azur Aparments | 2025 | Separate AC condenser | Separate Condensers to achieve 12 inches between units, add equiptment pads as needed | 1500- HVAC | GC | Project | 41600 | 0 | 41600 |  | Not Started
Azur Aparments | 2025 | HVAC Condensing Refrigerant Line Insulation | Equity PCA Item 5.2- $7,500- Many of the ground mounted AC condensing units were found to have insulation missing from t | 1500- HVAC | GC | Project | 7500 | 0 | 7500 |  | Not Started
Azur Aparments | 2025 | Electrical distribution | Repair house panels issues | 1600 - Electrical | GC | Project | 8500 | 0 | 8500 |  | Not Started
Azur Aparments | 2025 | Unit Electrical Panel Repairs | Equity PCA Item 5.3- $5,200- During the inspection it was noted that many of the electrical panels within the apartments | 1600 - Electrical | GC | Project | 5200 | 0 | 5200 |  | Not Started
Azur Aparments | 2025 | Fire Extinguishers | Lender PCR Item- $1,500- The common fire extinguisher at the resident postal boxes structure had an expired tag from 201 | 1600 - Electrical | GC | Project | 7100 | 0 | 7100 |  | Not Started
Azur Aparments | 2025 | CO Detectors | Residential units were not provided with CO detectors. Residential units had wood burning fireplaces. Partner recommends | 1600 - Electrical | PMC | Project | 10400 | 0 | 10400 |  | Not Started
Azur Aparments | 2025 | Contingency |  | Contingency & Fees | GC | Contingency | 329680 | 0 | 329680 |  | Reserve
Azur Aparments | 2025 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 77884 | 0 | 77884 |  | Reserve
Cambridge Square | 2025 | Landscape Cleanup and Enhancements | Tree trim | 83307.0 | PMC | Project | 42500 | 17654 | 24846 |  | In Progress
Cambridge Square | 2025 | Asphalt Coating | Fill asphalt cracks, seal coat | 84204.0 | GC | Project | 47500 | 0 | 47500 |  | Not Started
Cambridge Square | 2025 | Resurface swimming pool | Two pools - resurface 2 pools | 84095.0 | GC | Project | 50000 | 15000 | 35000 |  | In Progress
Cambridge Square | 2025 | Pool maintenance | Deck cleaning & Equipment repair/replacement | 84361.0 | GC | Project | 50000 | 15000 | 35000 |  | In Progress
Cambridge Square | 2025 | Pavement | Replace areas of potholes | 84204.0 | GC | Project | 36000 | 0 | 36000 |  | Not Started
Cambridge Square | 2025 | Stripe parking areas | Stripe Parking Area | 84201.0 | GC | Project | 22000 | 0 | 22000 |  | Not Started
Cambridge Square | 2025 | ADA parking & curb cuts | LPCA - Add van accessible parking stall near leasing office | 83520.0 | GC | Project | 6000 | 0 | 6000 |  | Not Started
Cambridge Square | 2025 | Sidewalks | LPCA (PR-90) - Potential trip hazards consisting of vertical and horizontal separation and significantly cracked and dam | 84115.0 | GC | Project | 20000 | 20000 | 0 |  | Completed
Cambridge Square | 2025 | Landscape irrigation | Inspect and repair irrigation | 84300.0 | GC | Project | 22500 | 0 | 22500 |  | Not Started
Cambridge Square | 2025 | Fences & gates - site perimeter | Replace fences between units | 84205.0 | GC | Project | 75000 | 0 | 75000 |  | Not Started
Cambridge Square | 2025 | Dumpster enclosures | Replace exisiting dumpster enclosures with new structures throughout property | 84111.0 | GC | Project | 45000 | 0 | 45000 |  | Not Started
Cambridge Square | 2025 | Repair exterior stair treads and stringers | Scrap and paint, secure stair treads | 84114.0 | GC | Project | 8500 | 0 | 8500 |  | Not Started
Cambridge Square | 2025 | Repair exterior stair railings | Scrap and paint, secure stair railings | 84121.0 | GC | Project | 12500 | 0 | 12500 |  | Not Started
Cambridge Square | 2025 | Repair balcony framing & decking | SB 721 needed, minor repairs included. Anything more extensive will need a change order. Catwalk railing potentially too | 84104.0 | GC | Project | 30000 | 0 | 30000 |  | Not Started
Cambridge Square | 2025 | Repair patio/balcony railings | Scrap and paint, secure | 84121.0 | GC | Project | 36000 | 0 | 36000 |  | Not Started
Cambridge Square | 2025 | Expansion joints | Seal expansion joints | 84102.0 | GC | Project | 14000 | 0 | 14000 |  | Not Started
Cambridge Square | 2025 | Asphalt composite shingle roofing | Half of the roofs have been redone recently. Still need to replace 9 roofs throughout property | 84433.0 | GC | Project | 495000 | 495000 | 0 |  | Completed
Cambridge Square | 2025 | Gutters & downspouts | Secure and clean gutters | 84202.0 | GC | Project | 36000 | 36000 | 0 |  | Completed
Cambridge Square | 2025 | Flashing | Flashing around chimneys to be replaced as needed | 84433.0 | GC | Project | 35000 | 35000 | 0 |  | Completed
Cambridge Square | 2025 | Sealants & caulking | Roof Sealants and Caulking | 84433.0 | GC | Project | 25000 | 25000 | 0 |  | Completed
Cambridge Square | 2025 | Repair / replace cement fiber siding | Replace damaged horizontal siding where needed | 84206.0 | GC | Project | 88500 | 0 | 88500 |  | Not Started
Cambridge Square | 2025 | Repair / replace wood shingles | Replace any damage faux cedar shake | 84206.0 | GC | Project | 85000 | 0 | 85000 |  | Not Started
Cambridge Square | 2025 | Repair stucco | Repair Exterior Stucco - Keep existing look of property. | 84102.0 | GC | Project | 20000 | 0 | 20000 |  | Not Started
Cambridge Square | 2025 | Exterior building | Paint community LPCA - Select areas of building exteriors were observed to have dryrot damage in locations throughout th | 84101.0 | GC | Project | 250000 | 0 | 250000 |  | Not Started
Cambridge Square | 2025 | Repair / replace wood trim | Replace rotted fascia and trim | 84105.0 | GC | Project | 185000 | 0 | 185000 |  | Not Started
Cambridge Square | 2025 | Shutters | Repair/replacement of damaged shutters throughout | 84105.0 | GC | Project | 45000 | 0 | 45000 |  | Not Started
Cambridge Square | 2025 | WDO | Wood Destroying Organisms- LPCA - Select areas of building exteriors were observed to have dryrot damage in locations th | 83301.0 | PMC | Project | 2500 | 0 | 2500 |  | Not Started
Cambridge Square | 2025 | Interior Update Placeholder | Contingency for interiors | 84207.0 | PMC | Project | 225000 | 0 | 225000 |  | Not Started
Cambridge Square | 2025 | Fire Stops | Install Fire Stops | 84239.0 | PMC | Project | 21105 | 65853 | -44748 |  | Completed
Cambridge Square | 2025 | CO Detectors | Install CO Detectors | 83236.0 | PMC | Project | 12060 | 0 | 12060 |  | Not Started
Cambridge Square | 2025 | Office Clubhouse | Clubhouse upgrades - Move office to pool clubhouse room. | 84208.0 | GC | Project | 25000 | 0 | 25000 |  | Not Started
Cambridge Square | 2025 | Fitness Center Remodel | Convert other clubhouse (high ceiling) into a fitness center | 84190.0 | GC | Project | 75000 | 0 | 75000 |  | Not Started
Cambridge Square | 2025 | Mailboxes | Current boxes are damaged | 84260.0 | GC | Project | 46500 | 0 | 46500 |  | Not Started
Cambridge Square | 2025 | Security/ fire alarm systems | Install controlled access system for common areas | 84275.0 | GC | Project | 20000 | 0 | 20000 |  | Not Started
Cambridge Square | 2025 | Seismic Strapping | Seismic Strapping - LPCA - The water heaters lacked seismic bracing straps. Provision of adequate seismic bracing is rec | 84209.0 | GC | Project | 20100 | 20100 | 0 |  | Completed
Cambridge Square | 2025 | Electrical distribution | Inspect and repair lighting controllers on all buildings | 84210.0 | GC | Project | 26000 | 0 | 26000 |  | Not Started
Cambridge Square | 2025 | Common area light fixtures | Replace pole lights with LED | 84210.0 | GC | Project | 28000 | 0 | 28000 |  | Not Started
Cambridge Square | 2025 | Replace breezeway lights | Replace doorway sconces | 84210.0 | GC | Project | 32100 | 0 | 32100 |  | Not Started
Cambridge Square | 2025 | Contingency | Construction Contingency | 84510.0 | GC | Contingency | 115768 | 0 | 115768 |  | Reserve
Cambridge Square | 2025 | Construction Management Fee | CM Fee | 84505.0 | GC | CM Fee | 121557 | 0 | 121557 |  | Reserve
Candlewood | 2025 | Landscape Cleanup and Enhancements | Item No. 1: Trim trees along the perimeter throughout the site to prevent the accumulation of debris and tree leaves ove | 51043-00 | PMC | Project | 50000 | 10850 | 39150 |  | In Progress
Candlewood | 2025 | Asphalt Coating | Fill, seal and coat of parking area at back of property. Mix of asphalt and concrete repairs needed (approx 80% asphalt) | 51053-00 | GC | Project | 173000 | 0 | 173000 |  | Not Started
Candlewood | 2025 | Asphalt Pavement | 3.1.6 - Isolated asphalt cracking was observed in the rear drive aisles and areas near the entrance gates. Repair is rec | 51050-00 | GC | Project | 2000 | 0 | 2000 |  | Not Started
Candlewood | 2025 | Stripe parking areas | Restripe Parking Area including carports. | 51053-00 | GC | Project | 19000 | 0 | 19000 |  | Not Started
Candlewood | 2025 | Fences & gates - site perimeter | Item No. 4: Allowance for periodic fencing repairs, including property perimeter wood slat fencing and CMU fencing along | 51076-00 | GC | Project | 5000 | 5000 | 0 |  | Completed
Candlewood | 2025 | Resurface swimming pool | Item No. 6: Allowance to resurface both pools and one spa, including repairing any cracks around the pool decks and repl | 51023-00 | GC | Project | 50000 | 50000 | 0 |  | Completed
Candlewood | 2025 | Carports / Garages | Significant wood rotting at stand alone carports. Need to replace all rotted wood and fix all damaged stucco on all 3 st | 51172-00 | GC | Project | 340000 | 0 | 340000 |  | Not Started
Candlewood | 2025 | Storm Sewer Piping | 50% of storm water drains on balconies need to be repaired/replaced due to paint/damage. | 51134-00 | GC | Project | 25988 | 25988 | 0 |  | Completed
Candlewood | 2025 | Roof framing | Replace/repair any wood rotting on carport roof decking on all 3 stand alone carports. | 51062-00 | GC | Project | 30000 | 0 | 30000 |  | Not Started
Candlewood | 2025 | Roof deck | Roof Deck Repairs | 51062-00 | GC | Project | 7500 | 7500 | 0 |  | Completed
Candlewood | 2025 | Repair balcony framing & decking | 3.2.7 - The balcony deck surface at unit A303 was buckled and standing water observed. The deck surface should be repair | 51072-00 | GC | Project | 2250 | 2250 | 0 |  | Completed
Candlewood | 2025 | Roof Drainage | 3.2.9 - Areas of roof ponding were noted on all roofs. Although ponding may decrease the useful life of the roof, deckin | 51062-00 | GC | Project | 2250 | 2250 | 0 |  | Completed
Candlewood | 2025 | Gutters & downspouts | Replace gutters at the 3 stand alone carports | 51071-00 | GC | Project | 22500 | 0 | 22500 |  | Not Started
Candlewood | 2025 | Roof Maintenance | Item No. 15: Allowance for annual roof maintenance on all roof areas including inspection and repair of flashing, sealan | 51062-00 | GC | Project | 5000 | 0 | 5000 |  | Not Started
Candlewood | 2025 | Exterior building repairs | Due to extensive repairs at the 3 stand alone carports need to repaint entire structures to match exisiting color scheme | 51080-00 | GC | Project | 135000 | 0 | 135000 |  | Not Started
Candlewood | 2025 | Exterior Paint | Item No. 11: Budget for pressure washing, preparation, caulking, stucco wall repairs, and painting of building exteriors | 51080-00 | GC | Project | 283500 | 283500 | 0 |  | Completed
Candlewood | 2025 | Balconies | Item No. 13: Engage a specialty consultant to survey 100% of apartment balconies associated with observed deterioration | 51993-01 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Candlewood | 2025 | Unit deferred maintenance | Item No. 3: Repair cracked concrete at Unit A119 patio. | 52111-00 | GC | Project | 2500 | 2500 | 0 |  | Completed
Candlewood | 2025 | Unit deferred maintenance (cont.) - 1 | Item No. 17: Allowance for repairs in bathrooms showing evidence of minor ceiling damage. Seen in Units C311 with tape i | 52111-00 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Candlewood | 2025 | Unit deferred maintenance (cont.) -2 | Item No. 18: Allowance for remediation of organic growth in isolated areas, especially in bathrooms where exhaust fans a | 52111-00 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Candlewood | 2025 | Radon Mitigation | 1.1.5 - Elevated levels of radon were detected in Building 9830 - Unit 123 and Building 9850 - Unit 118. The sponsor has | 51180-00 | PMC | Project | 20000 | 28975 | -8975 |  | Completed
Candlewood | 2025 | Pool Area Remodel | Building A: replace umbrellas and furniture Building B: repurpose middle space and replace plants. | 51160-00 | PMC | Project | 75000 | 0 | 75000 |  | Not Started
Candlewood | 2025 | Elevator Tests | Item No. 28: Perform the annual elevator tests and post the most recent certificates. Cab certificates expired 6/29/2024 | 51993-01 | PMC | Project | 4800 | 28842 | -24042 |  | Completed
Candlewood | 2025 | Electrical Load Tests | Item No. 29: Perform the required 5-year load test. Posted placard expired 6/11/2018. | 51993-01 | PMC | Project | 7200 | 0 | 7200 |  | Not Started
Candlewood | 2025 | Electrical distribution systems | Item No. 21: Allowance to provide periodic maintenance of the electrical distribution systems including infrared scans, | 51140-00 | GC | Project | 6000 | 0 | 6000 |  | Not Started
Candlewood | 2025 | Meter Banks - Rust and Corrosion | Item No. 22: Remove rust and corrosion from the multi-meter assemblies and paint with a matching rust inhibitive paint. | 51140-00 | GC | Project | 4500 | 32000 | -27500 |  | Completed
Candlewood | 2025 | Electrical - Load Centers | Item No. 23: Ensure that all apartment load centers have the proper index identifying circuit number and devices served. | 51140-00 | GC | Project | 9450 | 0 | 9450 |  | Not Started
Candlewood | 2025 | Common Area Light Fixtures | Change all patio/balcony lights to LED flush mounted lights | 51141-00 | GC | Project | 28350 | 28350 | 0 |  | Completed
Candlewood | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 132579 | 0 | 132579 |  | Reserve
Candlewood | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 72918 | 0 | 72918 |  | Reserve
Canyon Villa | 2025 | Asphalt Coating | R&R 1500 SF of potholes in concrete pavement LPCA - Cracking in the concrete driving lanes and parking areas was observe | 83000-2000 | GC | Project | 45000 | 5802 | 39198 |  | In Progress
Canyon Villa | 2025 | Stripe parking areas | Stripe parking lot LPCA - Pavement markings and striping appeared to be in fair condition. Reapplication of pavement mar | 83000-2000 | GC | Project | 22000 | 2837 | 19163 |  | In Progress
Canyon Villa | 2025 | Sidewalks | Repair Trip Hazards LPCA - Cracking in the concrete walkways was observed adjacent to Units 121, 140, 167, and 288. Repa | 83000-2800 | GC | Project | 15000 | 1934 | 13066 |  | In Progress
Canyon Villa | 2025 | Fences & gates - site perimeter | Repair Iron fence and paint | 83000-3900 | GC | Project | 25000 | 3224 | 21776 |  | In Progress
Canyon Villa | 2025 | Fences & gates - swimming pool | Repair and paint | 83000-5300 | GC | Project | 12000 | 1547 | 10453 |  | In Progress
Canyon Villa | 2025 | Carports / Garages | Repair carports | 83000-2600 | GC | Project | 15000 | 1934 | 13066 |  | In Progress
Canyon Villa | 2025 | Termite treatment | Includes inspection/treatment of Drywood, Subterranean and Dampwood termites) LPCA - According to provided information, | 80000-6800 | GC | Project | 54900 | 7079 | 47821 |  | In Progress
Canyon Villa | 2025 | Concrete deck / floor fill | Seal cracks in landing | 83000-2800 | GC | Project | 32000 | 4126 | 27874 |  | In Progress
Canyon Villa | 2025 | Repair exterior stair treads and stringers | Repair stair tread and stringers | 83000-7100 | GC | Project | 32000 | 4126 | 27874 |  | In Progress
Canyon Villa | 2025 | Repair exterior stair railings | repair and secure stair railings | 83000-7100 | GC | Project | 16000 | 2063 | 13937 |  | In Progress
Canyon Villa | 2025 | Repair balcony framing & decking | Repair damaged patio framing | 83000-2400 | GC | Project | 38000 | 4900 | 33100 |  | In Progress
Canyon Villa | 2025 | Repair patio/balcony railings | Secure all balcony railings LPCA - Paint along the balcony railing was observed to be chipping and peeling. Additionally | 83000-2400 | GC | Project | 16000 | 2063 | 13937 |  | In Progress
Canyon Villa | 2025 | Retaining Wall repairs | ESCA - Repair chips and broken sections of concrete on top of the concrete retaining wall. Repair to consist of placing | 83000-7500 | GC | Project | 4000 | 516 | 3484 |  | In Progress
Canyon Villa | 2025 | Retaining Wall repairs | ESCA - Implement a protocol for regular maintenance and cleaning of the drainage system including removal of plants | 83000-7500 | GC | Project | 400 | 52 | 348 |  | In Progress
Canyon Villa | 2025 | SB721 Repairs | Various SB721 repairs | 83000-7600 | GC | Project | 100000 | 12894 | 87106 |  | In Progress
Canyon Villa | 2025 | Roofing | Tune up clay tile and repair flashing LPCA - Organic materials were observed on the clay/concrete mission tiles. Cleanin | 83000-6100 | GC | Project | 25000 | 3224 | 21776 |  | In Progress
Canyon Villa | 2025 | Modified bitumen membrane roof Repairs | Roof repairs on 35 roofs | 83000-6100 | GC | Project | 35000 | 4513 | 30487 |  | In Progress
Canyon Villa | 2025 | Flashing | Replace damaged drip edge on balconies. | 83000-6100 | GC | Project | 16000 | 2063 | 13937 |  | In Progress
Canyon Villa | 2025 | Roof Cleanup and treatment | Roof Cleaning & Moss Treatment | 83000-6100 | GC | Project | 72000 | 9284 | 62716 |  | In Progress
Canyon Villa | 2025 | Gutters & downspouts | Clean and secure gutters and down spouts | 800 | GC | Project | 32000 | 4126 | 27874 |  | In Progress
Canyon Villa | 2025 | Sealants & caulking | Seal & Caulk Roofing Areas | 83000-6100 | GC | Project | 25000 | 3224 | 21776 |  | In Progress
Canyon Villa | 2025 | Repair stucco | Repairs to damaged stucco | 83000-3700 | GC | Project | 14000 | 1805 | 12195 |  | In Progress
Canyon Villa | 2025 | Exterior building Paint | Paint Community EPCA - Perform maintenance needs on the exterior elevated elements as recommended in the EEE Report prep | 83000-3400 | GC | Project | 354000 | 45646 | 308354 |  | In Progress
Canyon Villa | 2025 | Repair / replace wood trim | Replace all rotted fascia throughout property | 83000-3700 | GC | Project | 25000 | 3224 | 21776 |  | In Progress
Canyon Villa | 2025 | Fire Protection | Fire Stops | 80000-6400 | PMC | Project | 17934 | 509 | 17425 |  | In Progress
Canyon Villa | 2025 | Signage - Entry Monument | EPCA - Provide signage directing individuals from the accessible parking spaces to the leasing office entrance doors. | 83000-4300 | PMC | Project | 300 | 0 | 300 |  | Not Started
Canyon Villa | 2025 | Security/ fire alarm systems | LPCA (PR-90) - An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and rec | 80000-1700 | GC | Project | 20000 | 2579 | 17421 |  | In Progress
Canyon Villa | 2025 | Fire/Life Safety System - Smoke/CO alarm | EPCA - Budget to replace the existing combination smoke/CO alarms based on age and useful life. The NFPA requires that s | 80000-1700 | PMC | Project | 20720 | 0 | 20720 |  | Not Started
Canyon Villa | 2025 | Back-flow preventer | EPCA - The three irrigation backflow preventer assemblies were last inspected in February 2024 and are now past due for | 80000-5100 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Canyon Villa | 2025 | Galvanized Pipe Replacement | EPCA - Allowance for periodic domestic and sanitary piping repairs or replacements based on age and EUL (year 1 upfront, | 80000-5200 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Canyon Villa | 2025 | Electrical distribution | Repair electric to pole lights and photo cells | 80000-4800 | GC | Project | 20000 | 2579 | 17421 |  | In Progress
Canyon Villa | 2025 | Common area light fixtures | replace exterior building lights and post lights | 83000-3200 | GC | Project | 32000 | 4126 | 27874 |  | In Progress
Canyon Villa | 2025 | Replace transformer | EPCA - Contact the local utility to replace one utility transformer exhibiting significant corrosion. The unit is neares | 80000-4800 | GC | Project | 50000 | 6447 | 43553 |  | In Progress
Canyon Villa | 2025 | Install GFCI protection | EPCA - Install GFCI protection on the counter-height kitchen power outlets. Only 1 protected outlet was observed in each | 80000-4800 | PMC | Project | 36600 | 0 | 36600 |  | Not Started
Canyon Villa | 2025 | Preventative Maintenance - Breaker Panels | EPCA - Perform preventative maintenance on the electrical systems throughout the site, including opening breaker panels, | 80000-4800 | PMC | Project | 18300 | 0 | 18300 |  | Not Started
Canyon Villa | 2025 | Contingency | Contingency Amount | 80000-7700 | GC | Contingency | 33781 | 4356 | 29425 |  | Reserve
Canyon Villa | 2025 | Construction Management Fee | CM Fees | 80000-7200 | GC | CM Fee | 64822 | 8358 | 56463 |  | Reserve
Chaparral | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 51043-00 | PMC | Project | 20000 | 7420 | 12580 |  | In Progress
Chaparral | 2025 | Asphalt pavement | Mill and overlay asphalt throughout entire property Includes Equity PCA Item 3.2.2- Asphalt Pavment; Mill and overlay ap | 51050-00 | GC | Project | 740000 | 740000 | 0 |  | Completed
Chaparral | 2025 | Stripe parking areas | Stripe throughout property | 51053-00 | GC | Project | 35000 | 35000 | 0 |  | Completed
Chaparral | 2025 | Asphalt Coating | Double seal coat entire pavement throughout property | 51053-00 | GC | Project | 525000 | 525000 | 0 |  | Completed
Chaparral | 2025 | ADA parking & curb cuts | Restripe all handicap parking spots | 51091-00 | GC | Project | 25000 | 25000 | 0 |  | Completed
Chaparral | 2025 | Sidewalks | Replace cracked sidewalks throughout property | 51091-00 | GC | Project | 4500 | 4500 | 0 |  | Completed
Chaparral | 2025 | Resurface swimming pool | Resurface both pools, not including spas (completed recently) | 51023-00 | GC | Project | 67500 | 67500 | 0 |  | Completed
Chaparral | 2025 | Replace swimming pool coping | Deck-o-seal coping around both pools | 51021-00 | GC | Project | 6000 | 6000 | 0 |  | Completed
Chaparral | 2025 | Fences & gates - swimming pool | Scrap, prime and paint both pool fences. Add metal fence topper to extend height on gates and improve gate security. Pro | 51076-00 | GC | Project | 37600 | 37600 | 0 |  | Completed
Chaparral | 2025 | Sport Court | Resurface and stripe for tennis & pickleball. Fencing and lighting repairs. Includes Equity PCA Item 3.2.9- Tennis Court | 51027-00 | GC | Project | 55000 | 55000 | 0 |  | Completed
Chaparral | 2025 | Retaining walls | Equity PCA Item 3.2.5- Install weepholes on southern perimeter concrete masonry retaining walls | 51085-00 | GC | Project | 2400 | 2400 | 0 |  | Completed
Chaparral | 2025 | West Poolhouse | Equity PCA Item 3.2.9- Eliminate step between pool surround and poolhouse interior to provide wheelchair accessible rout | 51021-00 | GC | Project | 1250 | 1250 | 0 |  | Completed
Chaparral | 2025 | Pool Equipment | Includes Equity PCA Item 3.2.9- Repair active leaks observed at East and West pool heater PVC distribution piping | 51026-00 | GC | Project | 300 | 300 | 0 |  | Completed
Chaparral | 2025 | Fences & gates - swimming pool | Reinforce or increase size of pool gate gate posts at both pools | 51076-00 | GC | Project | 3000 | 3000 | 0 |  | Completed
Chaparral | 2025 | Playground equipment | Playground Addition | 51020-00 | GC | Project | 40000 | 0 | 40000 |  | Not Started
Chaparral | 2025 | Picnic areas | Tables & Seating | 51160-04 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Chaparral | 2025 | ADA Accessibility | Equity PCA Item- 7.1- Provide compliant scald-protection underneath leasing office men's restroom sink | 51158-00 | GC | Project | 200 | 200 | 0 |  | Completed
Chaparral | 2025 | Interior Update Placeholder | Placeholder Expense | 51150-00 | PMC | Project | 296000 | 1706 | 294294 |  | In Progress
Chaparral | 2025 | Signage - Building identification | Unit number signage needed at doors | 51033-00 | PMC | Project | 22200 | 0 | 22200 |  | Not Started
Chaparral | 2025 | Fitness Center Remodel (Defer Costs) | Paint & Reupholster ($5,000) | 51160-00 | GC | Project | 5000 | 0 | 5000 |  | Not Started
Chaparral | 2025 | Picnic/Grill Area Remodel | Remove and install new stand alone grils throughout property | 51160-04 | GC | Project | 8500 | 8500 | 0 |  | Completed
Chaparral | 2025 | Package Lockers (Defer Costs) | Accept small packages at office, otherwise deliver to door. Look at adding package lockers in enclosed room by 2nd pool. | 51168-00 | GC | Project | 29600 | 0 | 29600 |  | Not Started
Chaparral | 2025 | Security Camera System | Have 23 cameras, need 2-4 more cameras to cover side views | 51993-00 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Chaparral | 2025 | Golf Cart | Have leasing cart but could use new one | 51994-00 | PMC | Project | 8000 | 16562 | -8562 |  | Completed
Chaparral | 2025 | Domestic Water Service Main | Equity PCA Item- 5.1- The east domestic water service backflow prevention device was observed with an active drip leak. | 51158-00 | GC | Project | 2000 | 2000 | 0 |  | Completed
Chaparral | 2025 | Domestic Water Hose Bibs | Equity PCA Item- 5.1- Hose bibs were observed with active drip leaks on the exterior risers of apartment buildings E and | 51158-00 | GC | Project | 500 | 500 | 0 |  | Completed
Chaparral | 2025 | Water Heater T&P Valve Discharge | Equity PCA Item- 5.1- The water heater at unit A9 was observed lacking piping from the T&P valve to the building exterio | 51158-00 | GC | Project | 200 | 200 | 0 |  | Completed
Chaparral | 2025 | HVAC inspection and maintenance | Add HVAC pads to 3 units at the leasing office. Currently sitting on ground with debris around. | 51120-00 | GC | Project | 750 | 750 | 0 |  | Completed
Chaparral | 2025 | HVAC Exterior Condensing Unit Refrigerant Line Insulati | Equity PCA Item- 5.1- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | 51122-00 | GC | Project | 3700 | 3700 | 0 |  | Completed
Chaparral | 2025 | Natural Gas Seismic Shutoff Devices | Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices to prevent dang | 51158-00 | GC | Project | 148000 | 148000 | 0 |  | Completed
Chaparral | 2025 | Electrical distribution | Electrical Panels | 51140-00 | GC | Project | 27000 | 27000 | 0 |  | Completed
Chaparral | 2025 | Common area light fixtures | Replace all pole lights with LED and change tennis court lights with LED | 51141-00 | GC | Project | 55750 | 55750 | 0 |  | Completed
Chaparral | 2025 | Replace breezeway lights | Replace all breezeway lights in stairwells with LED | 51141-00 | GC | Project | 16500 | 16500 | 0 |  | Completed
Chaparral | 2025 | Fire Alarm Panels | Equity PCA Item- 5.5.2- Fire alarm control panels (FACP) at Buildings L and N were observed to with active trouble alarm | 51993-00 | PMC | Project | 40000 | 0 | 40000 |  | Not Started
Chaparral | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 87488 | 0 | 87488 |  | Reserve
Chaparral | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 116447 | 0 | 116447 |  | Reserve
Crestmark | 2025 | Pavement | Repair potholes | 84201 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
Crestmark | 2025 | Asphalt Coating | Seal Coat and Crack Fill | 84204 | PMC | Project | 144000 | 6391 | 137609 |  | In Progress
Crestmark | 2025 | Resurface swimming pool | Resurface both pools | 84095 | GC | Project | 79000 | 79000 | 0 |  | Completed
Crestmark | 2025 | Replace swimming pool deck | Level pavers and presure wash | 84361 | GC | Project | 31000 | 31000 | 0 |  | Completed
Crestmark | 2025 | Fences & gates - swimming pool | Repair fence and gates | 84361 | GC | Project | 18000 | 18000 | 0 |  | Completed
Crestmark | 2025 | Carports / Garages | Repairs to garage door - The garage door at 14C was observed damaged and should be repaired or replaced at this time. | 84219 | PMC | Project | 26000 | 0 | 26000 |  | Not Started
Crestmark | 2025 | Stripe parking areas | Restripe of parking lot | 84201 | PMC | Project | 28000 | 0 | 28000 |  | Not Started
Crestmark | 2025 | Sidewalks | PNA - Sidewalk Cracks LPCA - Sidewalks were observed to be in good to fair condition with cracks noted in isolated area | 84115 | PMC | Project | 5000 | 1650 | 3350 |  | In Progress
Crestmark | 2025 | Landscape irrigation | A leak from the irrigation system was observed at the site stairs between building 5 and the leasing office/clubhouse bu | 84300 | PMC | Project | 1500 | 877 | 623 |  | In Progress
Crestmark | 2025 | Fences & gates - compactor | The gates on the trash compactor enclosures are either damaged or missing. Repairs are recommended at this time. | 84111 | PMC | Project | 5000 | 1302 | 3698 |  | In Progress
Crestmark | 2025 | Fences & gates - site perimeter | The motor for automated gates at Crestmark Drive were reported to be inoperable. Repairs are recommended at this time. | 84205 | PMC | Project | 7000 | 1823 | 5177 |  | In Progress
Crestmark | 2025 | Landscaping | Curb Appeal | 84303 | PMC | Project | 75000 | 88873 | -13873 |  | Completed
Crestmark | 2025 | Pressure wash Breezeways | Pressure Washing - Breezeways | 84206 | GC | Project | 10000 | 10000 | 0 |  | Completed
Crestmark | 2025 | Pool Area | Pool bathroom upgrades - 1st Call to verify scope | 84361 | PMC | Project | 25000 | 39730 | -14730 |  | Completed
Crestmark | 2025 | Playground | Replace/repair playground equipment next to blacktop courts | 84195 | PMC | Project | 30000 | 2300 | 27700 |  | In Progress
Crestmark | 2025 | Concrete deck / floor fill | Rout and seal landings | 84102 | GC | Project | 16000 | 16000 | 0 |  | Completed
Crestmark | 2025 | Repair exterior stair railings | Secure railings | 84121 | GC | Project | 7000 | 7000 | 0 |  | Completed
Crestmark | 2025 | Repair balcony framing & decking | Repair 3 landing with structural issues | 84104 | GC | Project | 30000 | 15000 | 15000 |  | In Progress
Crestmark | 2025 | Repair patio/balcony railings | Secure railings | 84121 | GC | Project | 7000 | 7000 | 0 |  | Completed
Crestmark | 2025 | Asphalt composite shingle roofing | Standard roof tune up on ridge, vault and pipe jacks | 84433 | GC | Project | 32000 | 9600 | 22400 |  | In Progress
Crestmark | 2025 | Gutters & downspouts | Clean and repitch gutters throughout property | 84202 | GC | Project | 18000 | 5400 | 12600 |  | In Progress
Crestmark | 2025 | Siding- Water Intrusion | Address water intrusion near bay windows - 32 units | 84113 | GC | Project | 160000 | 80000 | 80000 |  | In Progress
Crestmark | 2025 | Flashing/Siding | A section of metal flashing is missing on the west side of the clock tower. Repairs are recommended. | 84105 | PMC | Project | 700 | 0 | 700 |  | Not Started
Crestmark | 2025 | Repair / replace vinyl siding | Repair Vinyl siding / trim / flashing | 84105 | PMC | Project | 85000 | 0 | 85000 |  | Not Started
Crestmark | 2025 | Paint/finish | Repaint full site | 84101 | PMC | Project | 334000 | 0 | 334000 |  | Not Started
Crestmark | 2025 | Repair / replace wood trim | Replace rotten wood throughout | 84105 | PMC | Project | 83500 | 0 | 83500 |  | Not Started
Crestmark | 2025 | Install CO Detectors | CO detectors were not observed in the units. The fireplaces are reportedly gas-fired units and require a CO detector. In | 83236 | PMC | Project | 20040 | 35518 | -15478 |  | Completed
Crestmark | 2025 | Clean Drier vents | clean dryer vents and replace damaged covers | 84106 | GC | Project | 16700 | 16700 | 0 |  | Completed
Crestmark | 2025 | Install GCI Outlets | Non-GFCI outlets were observed in the pool restrooms and some secondary bathrooms of the apartment units, including 8-81 | 83330 | PMC | Project | 10020 | 0 | 10020 |  | Not Started
Crestmark | 2025 | Fire Stops | Fire stops | 84239 | PMC | Project | 36740 | 15411 | 21329 |  | In Progress
Crestmark | 2025 | Unit deferred maintenance | Repair mechanical closet subfloors | 84304 | GC | Project | 20000 | 6000 | 14000 |  | In Progress
Crestmark | 2025 | Signage - Entry Monument | Noted during concept walk | 84290 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Crestmark | 2025 | Signage - Site | Added based on Kevin DD email feedback | 84103 | PMC | Project | 5000 | 2062 | 2938 |  | In Progress
Crestmark | 2025 | Clubhouse | Update color scheme and game room | 84116 | PMC | Project | 30000 | 3425 | 26575 |  | In Progress
Crestmark | 2025 | Fitness Center: New Equipment | Supplement existing equipment & redo bathrooms | 84190 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Crestmark | 2025 | Pool Area Furniture | Split between the two pools | 84360 | PMC | Project | 60000 | 0 | 60000 |  | Not Started
Crestmark | 2025 | Picnic/Grill Area Remodel | Pool 1: $25K & Pool 2: $15K | 84203 | PMC | Project | 40000 | 0 | 40000 |  | Not Started
Crestmark | 2025 | Sports Courts | Convert tennis court to pickle ball court | 84390 | GC | Project | 75000 | 22500 | 52500 |  | In Progress
Crestmark | 2025 | Mailboxes | New Mailboxes | 84005 | PMC | Project | 65000 | 0 | 65000 |  | Not Started
Crestmark | 2025 | Golf Cart | Maintenace carts; property has 2 maintenance carts & 1 6-seat leasing | 83375 | PMC | Project | 30000 | 12840 | 17160 |  | In Progress
Crestmark | 2025 | Replace AC condenser | Add insulation to Condensing unit lines | 84217 | GC | Project | 15000 | 15000 | 0 |  | Completed
Crestmark | 2025 | Replace breezeway lights | Inspect and replace emergency lighting | 84210 | GC | Project | 19000 | 19000 | 0 |  | Completed
Crestmark | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 87760 | 0 | 87760 |  | Reserve
Crestmark | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 92148 | 0 | 92148 |  | Reserve
Cypress Bend | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84303 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Cypress Bend | 2025 | Pavement | PNA - Repair Potholes PCA 3.2.2 - Areas of linear cracking and isolated spalling around linear cracks was observed at t | 84204 | GC | Project | 21000 | 21000 | 0 |  | Completed
Cypress Bend | 2025 | Sidewalks | PNA - Remove and replace areas of trip hazards. PCA 3.2.3 -Areas of linear cracking was observed in the concrete walkwa | 84115 | GC | Project | 14000 | 14000 | 0 |  | Completed
Cypress Bend | 2025 | Erosion control | PNA - Fill in erosion areas around buildings. | 84517 | GC | Project | 29000 | 29000 | 0 |  | Completed
Cypress Bend | 2025 | Fences & gates - site perimeter | PNA - Repair perimater fencing | 84205 | GC | Project | 43000 | 43000 | 0 |  | Completed
Cypress Bend | 2025 | Dumpster enclosures | PNA - Repair dumpster enclosures PCA 3.2.7 - Areas of damaged wood fencing was observed east adjacent to Building 12, n | 84111 | GC | Project | 16000 | 16000 | 0 |  | Completed
Cypress Bend | 2025 | Stripe parking areas | Stripe Parking | 84201 | GC | Project | 15000 | 4500 | 10500 |  | In Progress
Cypress Bend | 2025 | ADA parking & curb cuts | PCA 7.1 - Installation of an access aisle adjacent to the accessible parking stall north adjacent to Building 10 | 84221 | GC | Project | 250 | 250 | 0 |  | Completed
Cypress Bend | 2025 | Concrete deck / floor fill | Grind and seal cracks in light weight concrete landings | 84110 | GC | Project | 15000 | 15000 | 0 |  | Completed
Cypress Bend | 2025 | Repair exterior stair railings | PNA - Replace damaged railing on staircases. PCA 4.5 - Rust and corrosion was observed on the metal stringers, handrai | 84121 | GC | Project | 39000 | 39000 | 0 |  | Completed
Cypress Bend | 2025 | Asphalt composite shingle roofing | PNA - Roof tune up. PCA 4.4.1 - Unit 606 was observed to have water staining on the ceiling indicative of a roof leak. | 84433 | GC | Project | 13000 | 13000 | 0 |  | Completed
Cypress Bend | 2025 | Gutters & downspouts | PNA - Clean, repitch, and secure gutters. PCA 4.4.2 - Building 1 was observed to have a missing gutter system on the so | 84202 | GC | Project | 7500 | 7500 | 0 |  | Completed
Cypress Bend | 2025 | Flashing | Repair damaged flashing | 84433 | GC | Project | 5000 | 5000 | 0 |  | Completed
Cypress Bend | 2025 | Sealants & caulking | Roof Sealants | 84433 | GC | Project | 6000 | 6000 | 0 |  | Completed
Cypress Bend | 2025 | Repair / replace cement fiber siding | PNA - Siding repairs. PCA 4.3.1 - Damaged fiber cement lap board siding was observed on the east elevation of Building | 84206 | GC | Project | 7500 | 7500 | 0 |  | Completed
Cypress Bend | 2025 | Breezeways | PNA - Repair soffits | 84120 | GC | Project | 6000 | 6000 | 0 |  | Completed
Cypress Bend | 2025 | Exterior building | PNA - Exterior painting. PCA 4.3.1- Exterior cleaning, painting, sealing | 84101 | GC | Project | 195000 | 167100 | 27900 |  | In Progress
Cypress Bend | 2025 | Repair / replace wood trim | PNA - Replace damaged trim | 84105 | GC | Project | 8000 | 8000 | 0 |  | Completed
Cypress Bend | 2025 | Drier vents | PNA - Clean all dryer vents. PCA 5.2 Some of the dryer vents appeared to be damaged and full of debris. Cracked or vents | 84106 | GC | Project | 14400 | 14400 | 0 |  | Completed
Cypress Bend | 2025 | Garabage Disposals | Interior Replacements | 82206 | PMC | Project | 7500 | 0 | 7500 |  | Not Started
Cypress Bend | 2025 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84239 | PMC | Project | 22440 | 0 | 22440 |  | Not Started
Cypress Bend | 2025 | Unit deferred maintenance | Major Repairs Floors 18 Bedrooms 13 Living Rooms 3 Kitchens 2 Kitchen Countertop Resurface 2 Interior Door Replacement E | 84304 | PMC | Project | 21000 | 0 | 21000 |  | Not Started
Cypress Bend | 2025 | Signage | Budget for wall signage, current is dated. | 84103 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Cypress Bend | 2025 | Signage - Site | PCA 7.1 - Installation of ADA vertical identification parking signage | 84103 | PMC | Project | 450 | 0 | 450 |  | Not Started
Cypress Bend | 2025 | Clubhouse / Office Remodel | PCA 7.1 - Installation of grab bars adjacent to the commode in the leasing office | 84208 | PMC | Project | 500 | 0 | 500 |  | Not Started
Cypress Bend | 2025 | Clubhouse / Office Furniture | No clubhouse, allowance for office furniture | 84306 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Cypress Bend | 2025 | Computers | Budget for 2 replacement | 82140 | PMC | Project | 4000 | 9877 | -5877 |  | Completed
Cypress Bend | 2025 | Playground | PCA 3.2.9 - Partner observed that the ground cover beneath the play equipment consisted of grass. According to the Consu | 84195 | PMC | Project | 11250 | 12048 | -798 |  | Completed
Cypress Bend | 2025 | Unit Model Update | New furniture in model unit | 84280 | PMC | Project | 18000 | 0 | 18000 |  | Not Started
Cypress Bend | 2025 | Tools & Equipment | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools | 83440 | PMC | Project | 10000 | 866 | 9134 |  | In Progress
Cypress Bend | 2025 | Golf Cart | Don't have any carts, nowhere to park them. Could budget for one | 83375 | PMC | Project | 8000 | 0 | 8000 |  | Not Started
Cypress Bend | 2025 | AC condenser | PNA - Reposistion A/C condensers to achive 12" between units | 84220 | GC | Project | 20000 | 20000 | 0 |  | Completed
Cypress Bend | 2025 | HVAC Preventative Maintenance | PCA - 5.2 Supply and return air vents were observed with buildup of debris and need cleaning in buildings 10 and 12 due | 84217 | GC | Project | 15600 | 0 | 15600 |  | Not Started
Cypress Bend | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 77339 | 0 | 77339 |  | Reserve
Cypress Bend | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 42724 | 0 | 42724 |  | Reserve
Cypress Bend Village | 2025 | Storm sewer piping | PNA - Add drainage behing 4 building and connect to downspouts | 84385 | GC | Project | 75000 | 75000 | 0 |  | Completed
Cypress Bend Village | 2025 | Pavement | PNA - Repair Potholes PCA 3.2.2 - Linear cracking was observed in the drive aisles and parking spaces at the entrance d | 84204 | GC | Project | 20000 | 20000 | 0 |  | Completed
Cypress Bend Village | 2025 | Stripe parking areas | Stripe Parking | 84204 | GC | Project | 24000 | 24000 | 0 |  | Completed
Cypress Bend Village | 2025 | ADA parking & curb cuts | PNA - Add rail around ADA Ramp to units PCA - Installation of vertical identification signage at parking space | 84204 | GC | Project | 14000 | 14000 | 0 |  | Completed
Cypress Bend Village | 2025 | Sidewalks | PNA - remove and replace areas of trip hazards PCA 3.2.3 - Potential tripping hazards due to heaved concrete sections w | 84221 | GC | Project | 14400 | 14400 | 0 |  | Completed
Cypress Bend Village | 2025 | Erosion control / Tree trimming | PNA - Fill eroded areas around buildings; PCA - 3.2.4- Areas of soil erosion were observed on the northeast corner ad e | 83517 | GC | Project | 24000 | 24000 | 0 |  | Completed
Cypress Bend Village | 2025 | Resurface swimming pool | Swimming Pool | 84095 | GC | Project | 42000 | 18600 | 23400 |  | In Progress
Cypress Bend Village | 2025 | Replace swimming pool coping | PNA - Replace deck-o-seal | 84361 | GC | Project | 6500 | 6500 | 0 |  | Completed
Cypress Bend Village | 2025 | Replace swimming pool deck | PNA - Pressure wash pool decks | 84361 | GC | Project | 12000 | 12000 | 0 |  | Completed
Cypress Bend Village | 2025 | Fences & gates - swimming pool | PNA - Adjust gates and repair gate latches | 84361 | GC | Project | 6500 | 6500 | 0 |  | Completed
Cypress Bend Village | 2025 | Dumpster enclosures | PNA - Repair compactor areas | 84111 | GC | Project | 16000 | 16000 | 0 |  | Completed
Cypress Bend Village | 2025 | Fences & gates - site perimeter | PCA 3.2.7 - Isolated areas of damaged fencing was observed north adjacent to Building 12, south adjacent to Building 4, | 84205 | GC | Project | 980 | 980 | 0 |  | Completed
Cypress Bend Village | 2025 | Concrete deck / floor fill | PNA - Grind and seal cracks in light weight concrete landings | 84206 | GC | Project | 12000 | 12000 | 0 |  | Completed
Cypress Bend Village | 2025 | Repair exterior stair treads, stringers, and railings | PNA - Replace damaged railing on stair cases PCA 4.5 - Areas of rust and corrosion was observed on the steel stingers an | 84114 | GC | Project | 35000 | 35000 | 0 |  | Completed
Cypress Bend Village | 2025 | Repair patio/balcony railings | PNA - Repair balcony railings | 84121 | GC | Project | 18000 | 18000 | 0 |  | Completed
Cypress Bend Village | 2025 | Expansion Joints | Building Expansion Joints | 84102 | GC | Project | 8000 | 8000 | 0 |  | Completed
Cypress Bend Village | 2025 | Asphalt composite shingle roofing | PNA - Roof tune up | 84433 | GC | Project | 18000 | 18000 | 0 |  | Completed
Cypress Bend Village | 2025 | Gutters & downspouts | PNA - Clean, repitch, and secure gutters | 84202 | GC | Project | 9500 | 9500 | 0 |  | Completed
Cypress Bend Village | 2025 | Flashing | PNA - Repair damaged flashing | 84433 | GC | Project | 6000 | 6000 | 0 |  | Completed
Cypress Bend Village | 2025 | Sealants & caulking | Roof Sealants | 84433 | GC | Project | 6000 | 6000 | 0 |  | Completed
Cypress Bend Village | 2025 | Breezeways | Repair soffits | 84120 | GC | Project | 6000 | 6000 | 0 |  | Completed
Cypress Bend Village | 2025 | Exterior building | PNA - Repaint community PCA 4.3.1 - Areas of damaged siding were observed on the east and south elevations of Building | 84101 | GC | Project | 198000 | 185750 | 12250 |  | In Progress
Cypress Bend Village | 2025 | Repair / replace wood trim | Replace damaged trim | 84105 | GC | Project | 8000 | 8000 | 0 |  | Completed
Cypress Bend Village | 2025 | Drier vents | PNA - Clean drier vents and repair as needed. PCA 5.2 - Some of the dryer vents appeared to be damaged and full of debri | 84106 | GC | Project | 16660 | 24500 | -7840 |  | Completed
Cypress Bend Village | 2025 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84239 | PMC | Project | 23375 | 0 | 23375 |  | Not Started
Cypress Bend Village | 2025 | Unit Deferred Maintenance | 2 Units have mold: (1-601, 1-610) 97% of water heaters > 10 years old Major Repairs Flooring repair: 17 Bedrooms 18 Livi | 84304 | PMC | Project | 26000 | 0 | 26000 |  | Not Started
Cypress Bend Village | 2025 | Clubhouse / Office Remodel | No clubhouse, allowance for office | 84208 | PMC | Project | 7500 | 3871 | 3629 |  | In Progress
Cypress Bend Village | 2025 | Computers | Budget for 3 replacement | 83265 | PMC | Project | 6000 | 75832 | -69832 |  | Completed
Cypress Bend Village | 2025 | Fitness Equipment | Add equipment | 84190 | PMC | Project | 25000 | 0 | 25000 |  | Not Started
Cypress Bend Village | 2025 | Pool Area Remodel | Add gazebo, turf next to clubhouse | 84361 | GC | Project | 30000 | 30000 | 0 |  | Completed
Cypress Bend Village | 2025 | Pool Furniture | New furniture | 84360 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Cypress Bend Village | 2025 | Dog Park | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola | 84130 | GC | Project | 15000 | 15000 | 0 |  | Completed
Cypress Bend Village | 2025 | Model Unit Update | New furniture in model unit | 84280 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Cypress Bend Village | 2025 | Security Camera System | Manager says system is ok, maybe add license plate reader and a few cameras | 84450 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Cypress Bend Village | 2025 | Restoration & Remediation | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools | 84905 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Cypress Bend Village | 2025 | Golf Cart | Budget for maintenance cart. Don't have leasing cart, budget for one in case it is needed | 83375 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Cypress Bend Village | 2025 | Replace forced air unit | PCA 5.2 - Split-system furnace/fan coil, Replace | 84220 | GC | Project | 78000 | 23400 | 54600 |  | In Progress
Cypress Bend Village | 2025 | Replace AC condenser | PCA 5.2 -Many of the condensing units were installed in an improper manner. Limited units were observed set on pads that | 84218 | GC | Project | 20000 | 20000 | 0 |  | Completed
Cypress Bend Village | 2025 | Contingency | Contingency | 84510 | GC | Contingency | 103516 | 0 | 103516 |  | Reserve
Cypress Bend Village | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 57309 | 0 | 57309 |  | Reserve
David Ave | 2025 | Asphalt Coating | Seal asphalt Includes Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in fair con | 51053-00 | GC | Project | 61000 | 61000 | 0 |  | Completed
David Ave | 2025 | Resurface swimming pool | Resurface two pools | 51023-00 | GC | Project | 92000 | 27600 | 64400 |  | In Progress
David Ave | 2025 | Repair / replace swimming pool pumps | Anti entrapment devices | 51026-00 | GC | Project | 12600 | 3780 | 8820 |  | In Progress
David Ave | 2025 | Fences & gates - swimming pool | Adjust closers on pool gates | 51076-00 | GC | Project | 12800 | 12800 | 0 |  | Completed
David Ave | 2025 | Carports / Garages | Repair and paint carport supports | 51172-00 | GC | Project | 12000 | 12000 | 0 |  | Completed
David Ave | 2025 | Termite Remediation | Drywood termites treatment | 51992-00 | PMC | Project | 6000 | 6000 | 0 |  | Completed
David Ave | 2025 | Install metal hardware connections at post-to-beam and | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces. | 51092-00 | GC | Project | 22500 | 22500 | 0 |  | Completed
David Ave | 2025 | Rout and seal cracks in concrete slab-on-grade. | PCA 4.1 Rout and seal cracks in concrete slab-on-grade. | 51090-00 | GC | Project | 3000 | 3000 | 0 |  | Completed
David Ave | 2025 | 3040 David – Engineered repair design to remediate dama | PCA 4.2. -3040 David – Engineered repair design to remediate damaged beam at TUP. | 51070-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
David Ave | 2025 | Remediation of exposed wood beams exhibiting deteriorat | PCA 4.2 - Remediation of exposed wood beams exhibiting deterioration at TUP regions. | 51070-00 | GC | Project | 10000 | 10000 | 0 |  | Completed
David Ave | 2025 | Replace edge beams in-kind at TUP areas, where needed. | PCA 4.2. Replace edge beams in-kind at TUP areas, where needed. | 51070-00 | GC | Project | 8000 | 8000 | 0 |  | Completed
David Ave | 2025 | Repair or replace damaged concrete treads at stairs. | PCA 4.2.- Repair or replace damaged concrete treads at stairs. | 51090-00 | GC | Project | 5000 | 5000 | 0 |  | Completed
David Ave | 2025 | Clean and repaint steel stair frame with surface corros | PCA 4.2. -Clean and repaint steel stair frame with surface corrosion. | 51077-00 | GC | Project | 3000 | 3000 | 0 |  | Completed
David Ave | 2025 | Replace missing vent tops. | PCA4.4.1 - Replace missing vent tops. | 51062-00 | GC | Project | 1000 | 1000 | 0 |  | Completed
David Ave | 2025 | Repair exterior stair railings | Secure railings on all catwalks | 51077-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
David Ave | 2025 | Repair balcony framing & decking | Repairs for 2 walkways and stairwells per SB721 report from Medro, contingency for additional repairs PCA 4.5- As no doc | 51072-00 | GC | Project | 55000 | 49862 | 5138 |  | In Progress
David Ave | 2025 | Increase rail height | Raise catwalk rail height to 42" per SB 721 report | 51077-00 | GC | Project | 100000 | 30000 | 70000 |  | In Progress
David Ave | 2025 | Gutters & downspouts Replace missing or crushed downspo | Secure and clean gutters PCA 4.4.1. -Replace missing or crushed downspouts. | 51071-00 | GC | Project | 8000 | 8000 | 0 |  | Completed
David Ave | 2025 | Sealants & caulking | Prep and seal exterior | 51062-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
David Ave | 2025 | Repair / replace wood shingles | Replace window walls with Hardie Horizontal | 51075-00 | GC | Project | 30000 | 30000 | 0 |  | Completed
David Ave | 2025 | Exterior building Paint | Paint community | 51080-00 | GC | Project | 98000 | 98000 | 0 |  | Completed
David Ave | 2025 | Repair / replace wood trim Repair or replace damaged wo | Replace rotted fascia and trim PCA 4.2. - Repair or replace damaged wood trim and stucco at elevated walkways and soffi | 51082-00 | GC | Project | 36000 | 36000 | 0 |  | Completed
David Ave | 2025 | Common area FF&E, Replace | FF& E - Common Areas | 51160-06 | GC | Project | 2000 | 0 | 2000 |  | Not Started
David Ave | 2025 | Leasing Office Restroom Accessibility | Equity PCA Item- 7.1- The leasing office restroom is provided with a full vanity at the lavatory. Replacement of the va | 51169-00 | GC | Project | 1550 | 0 | 1550 |  | Not Started
David Ave | 2025 | Pool Area Remodel | Allowance | 51160-00 | PMC | Project | 5000 | 2400 | 2600 |  | In Progress
David Ave | 2025 | Pool Furniture | No furniture, need to add for 2 pools | 51011-00 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
David Ave | 2025 | Picnic/Grill Area Remodel | Allowance for grill/outdoor kitchen upgrades | 51160-04 | PMC | Project | 6000 | 0 | 6000 |  | Not Started
David Ave | 2025 | Picnic/Grill Furniture | Allowance for furniture | 51160-04 | PMC | Project | 2000 | 0 | 2000 |  | Not Started
David Ave | 2025 | Back-flow preventer | Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. Municipalities typically r | 51130-00 | PMC | Project | 3000 | 2184 | 816 |  | In Progress
David Ave | 2025 | Galvanized Pipe Replacement | Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone to developing pinhol | 51130-00 | GC | Project | 30000 | 0 | 30000 |  | Not Started
David Ave | 2025 | Stormwater Pipe Repair | Number based on actual bid; $285 per cleanout, est. 10 cleanouts. $402 per storm drain, 4 cleanouts. $129 per flow test, | 51130-00 | GC | Project | 6746 | 0 | 6746 |  | Not Started
David Ave | 2025 | Sanitary Sewer Piping | Equity PCA Item- 5.1- The sanitary waste system was original to construction. Typically, sections were replaced as neede | 51134-00 | PMC | Project | 4000 | 7211 | -3211 |  | Completed
David Ave | 2025 | Natural Gas Seismic Shutoff | Will confirm with Gas utility company if needed Equity PCA Item- 5.1- The natural gas services were not equipped with au | 51130-00 | GC | Project | 6000 | 6000 | 0 |  | Completed
David Ave | 2025 | Green Program - Energy Retrofit | Echelon upfront costs | 51990-00 | PMC | Project | 35760 | 2436 | 33324 |  | In Progress
David Ave | 2025 | Fire Department Violations - Engage expeditor to clear | Lender PCA Item- There are outstanding fire department violations. CBRE recommends engaging an expeditor to clear all ou | 51993-01 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
David Ave | 2025 | Electrical Panel Disconnects & Meter Banks | Phased replacement of 2 main meter banks Equity PCA Item- 5.3- The main disconnects and meter banks were manufactured by | 51140-00 | GC | Project | 120000 | 36000 | 84000 |  | In Progress
David Ave | 2025 | Replace Electrical Meter Panel at Building 3 | Equity PCA Item- 5.3- A metal panel was missing on the wiring trough at the meter enclosure at Building 3. The missing p | 51140-00 | PMC | Project | 500 | 156 | 344 |  | In Progress
David Ave | 2025 | Electrical service and distribution, Ongoing Repalcemen | Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B (Recomme | 51140-00 | GC | Project | 5000 | 1500 | 3500 |  | In Progress
David Ave | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 45096 | 0 | 45096 |  | Reserve
David Ave | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 47350 | 0 | 47350 |  | Reserve
Elliot Baymeadows | 2025 | Landscape Cleanup and Enhancements | Tree trim, foliage cut back throughout | 84303 | GC | Project | 100000 | 90000 | 10000 |  | In Progress
Elliot Baymeadows | 2025 | Stripe parking areas PCA 7.0 - install proper access ai | Parking Lot Striping | 84201 | GC | Project | 22000 | 22000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Parking equipment | Need more info from Mark | 84219 | GC | Project | 32000 | 0 | 32000 |  | Not Started
Elliot Baymeadows | 2025 | Parking pavement PCA 3.2.2 - Repair pothole formation | Linear cracking, "map" or "alligator" cracking, and pothole formation were noted throughout the drive aisles adjacent to | 84204 | GC | Project | 26500 | 32500 | -6000 |  | Completed
Elliot Baymeadows | 2025 | Sidewalks | Sidewalk Repairs | 84115 | GC | Project | 28000 | 21000 | 7000 |  | In Progress
Elliot Baymeadows | 2025 | Landscape irrigation PCA 3.2.11 - Evaluate system, repa | Irrigation in fair to poor condition. Electrical wiring in the control panel appeared to be cut and maintenance personne | 84302 | PMC | Project | 32000 | 22824 | 9176 |  | In Progress
Elliot Baymeadows | 2025 | Erosion control | Site Erosion Control | 84517 | GC | Project | 22000 | 0 | 22000 |  | Not Started
Elliot Baymeadows | 2025 | Fences & gates - site perimeter PCR - Repair inoperable | The motor for the automated gates were reported and observed to be inoperable. Repairs are recommended at this time. | 84205 | PMC | Project | 2500 | 1600 | 900 |  | In Progress
Elliot Baymeadows | 2025 | Resurface swimming pool | Two pools - Resurface | 84095 | GC | Project | 70000 | 0 | 70000 |  | Not Started
Elliot Baymeadows | 2025 | Maintenance Shop PCR - Overhead door repair (Maintenanc | Minor damage was observed on the overhead door trim at the maintenance shop. Repairs are recommended | 83270 | PMC | Project | 350 | 0 | 350 |  | Not Started
Elliot Baymeadows | 2025 | Sports Courts PCA 3.2.9 - Repair tennis and sports cour | Placeholder for repurposing of sports court area. Could include turf installation for soccer Tennis/sports court were ob | 84390 | GC | Project | 75000 | 75000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Termite Repairs PCR - Termite Damage Repairs | Evidence of termite damage was observed on the door frame of the poop pump room, near the fitness center building. All d | 83301 | PMC | Project | 700 | 21 | 679 |  | In Progress
Elliot Baymeadows | 2025 | Termite treatment PCR - Termite damage repairs | Subsequent to the site visit, a WDO inspection wasconducted by Busy Bee Termite, and their findings indicate visible sig | 83301 | PMC | Project | 7500 | 223 | 7277 |  | In Progress
Elliot Baymeadows | 2025 | WDO Repairs PCR - WDO Repairs - WDO report | Subsequent to the site visit, a WDO inspection was conducted by Busy Bee Termite, and their findings indicate evidence o | 83301 | PMC | Project | 12000 | 356 | 11644 |  | In Progress
Elliot Baymeadows | 2025 | Repair exterior stair treads and stringers | Repair failing wood stair cases | 84114 | GC | Project | 43000 | 80000 | -37000 |  | Completed
Elliot Baymeadows | 2025 | Asphalt composite shingle roofing | Roof tune up | 84433 | GC | Project | 160000 | 160000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Flashing | Roof Flashing | 84433 | GC | Project | 40000 | 40000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Sealants & caulking and paint | Roof Sealants & Caulking | 84433 | GC | Project | 20000 | 16000 | 4000 |  | In Progress
Elliot Baymeadows | 2025 | Repair / replace wood siding | Replace failing siding | 84102 | GC | Project | 38000 | 30400 | 7600 |  | In Progress
Elliot Baymeadows | 2025 | Exterior Building Painting | Heavy pressure wash and prep for mildew and paint community | 84101 | GC | Project | 675000 | 405000 | 270000 |  | In Progress
Elliot Baymeadows | 2025 | Repair / replace wood trim | Wood Trim Repairs | 84113 | GC | Project | 28000 | 22400 | 5600 |  | In Progress
Elliot Baymeadows | 2025 | Chimney Cap Covers | Fabricate and replace rusted out and failing chimney covers | 84102 | GC | Project | 43000 | 43000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Unit Interior Replacements (Partials) | Partial Units | 84207 | GC | Project | 414000 | 0 | 414000 |  | Not Started
Elliot Baymeadows | 2025 | Unit Interior Replacements (Classics) | Classic Units | 84207 | GC | Project | 466000 | 0 | 466000 |  | Not Started
Elliot Baymeadows | 2025 | Dryer Vents | Clean dryer vents | 84106 | GC | Project | 26400 | 26400 | 0 |  | Completed
Elliot Baymeadows | 2025 | Fire Stops | Fire Stops | 84239 | PMC | Project | 29920 | 59840 | -29920 |  | Completed
Elliot Baymeadows | 2025 | Fitness Center Remodel | New equipment, refurbishment of existing equipment | 84195 | PMC | Project | 40000 | 49616 | -9616 |  | Completed
Elliot Baymeadows | 2025 | Package lockers | Add Lockers | 84230 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Elliot Baymeadows | 2025 | Pool Area Remodel | Allocation for two pools | 84361 | PMC | Project | 50000 | 19703 | 30297 |  | In Progress
Elliot Baymeadows | 2025 | Pool Furniture | Allocation for two pools | 84360 | PMC | Project | 35000 | 537 | 34463 |  | In Progress
Elliot Baymeadows | 2025 | Unit Model Update | New furniture in model unit | 84280 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Elliot Baymeadows | 2025 | Sanitary Sewer Piping PCA 5.1 - Sewer scoping | Due to the age of the site, Partner recommends a sewer scoping of all waste lines. This scoping can tell if there are br | 84385 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Elliot Baymeadows | 2025 | Domestic Hot Water Heater Replacement | Contingent hot water heater replacement | 84476 | PMC | Project | 7040 | 4600 | 2440 |  | In Progress
Elliot Baymeadows | 2025 | PCR - Water heater repairs | Minor damage was observed at the water heater pan in units 609 and 1709. A cover plate for the control panel is also mis | 84218 | PMC | Project | 700 | 0 | 700 |  | Not Started
Elliot Baymeadows | 2025 | Replace forced air unit | Level and replace AC pads | 84218 | GC | Project | 35200 | 0 | 35200 |  | Not Started
Elliot Baymeadows | 2025 | Replace AC condenser | Contingent HVAC replacement - projections taken from EPCA | 84220 | GC | Project | 69490 | 0 | 69490 |  | Not Started
Elliot Baymeadows | 2025 | Common area light fixtures | Pole lights, buildings lights, and amenities courts | 84210 | GC | Project | 72000 | 72000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Replace breezeway lights | Entry lights | 84210 | GC | Project | 32100 | 32100 | 0 |  | Completed
Elliot Baymeadows | 2025 | Electrical Panel Disconnects & Meter Banks PCA 5.3 - IR | Electrical systems are approaching 40-years-old and are exposed to the weather. IR scans can identify loose connections, | 84330 | GC | Project | 14000 | 12600 | 1400 |  | In Progress
Elliot Baymeadows | 2025 | Electrical service and distribution, Ongoing Repalcemen | CBRE recommends verifying that the non-GFCI outlets in the secondary bathrooms are on the same circuit as the GFCI outle | 84210 | GC | Project | 23000 | 0 | 23000 |  | Not Started
Elliot Baymeadows | 2025 | Smoke detectors PCA 5.5.2 - Replace all smoke detectors | In dwelling units observed, smoke detectors were only mounted in the hallways or living room areas, not in the sleeping | 83236 | PMC | Project | 17600 | 5535 | 12065 |  | In Progress
Elliot Baymeadows | 2025 | CO Detectors PCR (PR-90) - Provide CO detectors PCA 5.5 | Carbon Monoxide detectors were not observed as required. A recommendation has been included to install CO detectors in a | 83236 | PMC | Project | 8800 | 2767 | 6033 |  | In Progress
Elliot Baymeadows | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 143440 | 0 | 143440 |  | Reserve
Foster Creek | 2025 | Landscape Cleanup and Enhancements Equity PCA 3.2.2 | Install Landscaping and Mulch - North of Building 15042 | 84303 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Foster Creek | 2025 | ADA parking & curb cuts Lender PCA 5.4 Equity PCA 4.1 | The subject property does not provide van-accessible parking spaces at the Leasing Office. Installation of one van-acces | 83520 | GC | Project | 1600 | 1600 | 0 |  | Completed
Foster Creek | 2025 | Sidewalks Lender PCA 3.1.7 Equity PCA 3.2.4 | Remove and replace areas of trip hazards. Cracked concrete was observed adjacent to the entrance to Building C. Repair | 84115 | GC | Project | 30000 | 30000 | 0 |  | Completed
Foster Creek | 2025 | Asphalt Pavement Lender PCA 3.1.6 Equity PCA 3.2.4 | Lender PCA 3.1.6 Damaged asphalt pavement consisting of linear cracking, alligator cracking, potholes, and surface ravel | 84204 | GC | Project | 24250 | 24250 | 0 |  | Completed
Foster Creek | 2025 | Storm Water Management Equity PCA 3.2.1 | Erosion Repairs | 84517 | GC | Project | 15000 | 15000 | 0 |  | Completed
Foster Creek | 2025 | Dumpster enclosures Equity PCA 3.2.2 | Repair dumpster inclosures. Replaced Damaged Dumpster Gates | 84111 | GC | Project | 16000 | 4800 | 11200 |  | In Progress
Foster Creek | 2025 | Security Camreas System | Add additional security camreas systems to the property | 84450 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Foster Creek | 2025 | Key Pad and Auto Locking Door | Add to gym door | 84275 | PMC | Project | 7500 | 0 | 7500 |  | Not Started
Foster Creek | 2025 | Repair patio/balcony railings Equty PCA 3.3.5 | Repair balconies railings Balcony Repairs | 84121 | GC | Project | 40000 | 12000 | 28000 |  | In Progress
Foster Creek | 2025 | Concrete deck / floor fill | np1 sealant to cracks in landing | 84430 | GC | Project | 19000 | 19000 | 0 |  | Completed
Foster Creek | 2025 | Repair exterior stair railings | Repair wooden railings on stairs | 84121 | GC | Project | 35000 | 10500 | 24500 |  | In Progress
Foster Creek | 2025 | Asphalt composite shingle roofing | Roof Tune Up | 84433 | GC | Project | 12000 | 12000 | 0 |  | Completed
Foster Creek | 2025 | Modified bitumen membrane roof Repairs | Repairs to flat roofs. Equity PCA did not mention roof as an immediate need, but did mention as a replacement in YR 1 | 84433 | GC | Project | 30000 | 30000 | 0 |  | Completed
Foster Creek | 2025 | Gutters & downspouts | Clear scuppers and roof drains | 83439 | GC | Project | 19000 | 19000 | 0 |  | Completed
Foster Creek | 2025 | Flashing | Repair damaged flashing | 84433 | GC | Project | 8500 | 2550 | 5950 |  | In Progress
Foster Creek | 2025 | Sealants & caulking and paint | Roof Sealants & Caulking | 84433 | GC | Project | 8500 | 2550 | 5950 |  | In Progress
Foster Creek | 2025 | Repair / replace wood siding Lender PCA 3.2.4 Equity PC | Replace damaged T 1-11 siding on mansards Damaged T1-11 siding was present at Building G (Phase II). Repair is recommen | 84102 | GC | Project | 34000 | 10200 | 23800 |  | In Progress
Foster Creek | 2025 | Repair / replace vinyl siding Lender PCA 3.2.4 | Isolated areas of warped vinyl lap siding were observed at the leasing office and Buildings B and C of Phase I. Repairs | 84102 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Foster Creek | 2025 | Breezeway soffit repairs | Repair soffits - Could be changed to $120k | 84113 | GC | Project | 160000 | 48000 | 112000 |  | In Progress
Foster Creek | 2025 | Exterior building Paint | Repaint Community | 84101 | GC | Project | 320000 | 96000 | 224000 |  | In Progress
Foster Creek | 2025 | Repair / replace wood trim Equity PCA 3.3.3 | Replace damaged trim | 84113 | GC | Project | 16000 | 4800 | 11200 |  | In Progress
Foster Creek | 2025 | Moisture and Microbial Growth Equity PCA 4.6 | Proactive rewire bathroom fan to light switch. Mold & Moisture Removal | 84905 | GC | Project | 15215 | 15215 | 0 |  | Completed
Foster Creek | 2025 | Clean Dryer vents | Clean dryer vents. Get a unit count of units with W/D | 84106 | PMC | Project | 2250 | 0 | 2250 |  | Not Started
Foster Creek | 2025 | Fire Stops | Install Fire Stops | 84211 | PMC | Project | 15215 | 105065 | -89850 |  | Completed
Foster Creek | 2025 | Down Unit Renovation (C-309) Lender PCA 3.4.2 | Unit C-309 was observed in poor condition and is considered ‘down’. A notice affixed to the door by the King County Sher | 82460 | PMC | Project | 10800 | 0 | 10800 |  | Not Started
Foster Creek | 2025 | Damaged Unit Repair (C-209) Lender PCA 3.4.2 Equity PC | Additionally, Unit C-209 was observed in fair condition. The unit has water damage to finishes from the unit above (C-30 | 82460 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Foster Creek | 2025 | General Electrical Services Equity PCA 3.4.4 | Replace wall packs | 84210 | GC | Project | 32000 | 32000 | 0 |  | Completed
Foster Creek | 2025 | Improperly supported meter bank Equity PCA 3.4.4 | Meter bank supports | 84330 | GC | Project | 1000 | 1000 | 0 |  | Completed
Foster Creek | 2025 | GFCI Receptacles Equity PCA 3.4.4 | Missing GFCI receptacles | 84330 | PMC | Project | 13500 | 0 | 13500 |  | Not Started
Foster Creek | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 48067 | 0 | 48067 |  | Reserve
Foster Creek | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 50470 | 0 | 50470 |  | Reserve
Foster Creek | 2025 | Signage | Building Signage | 83103 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Foster Creek | 2025 | Dog Park & Grilling Area | Dog Park & Grilling Area | 84130 | PMC | Project | 35000 | 0 | 35000 |  | Not Started
Foster Creek | 2025 | 83209 - Plumbing | Plumbing Work Orders | 83209 | PMC | Project | 3500 | 29571 | -26071 |  | Completed
Foster Creek | 2025 | 83209 - Plumbing | Water Leaks Behind Sheetrock | 83209 | PMC | Project | 1667 | 14084 | -12417 |  | Completed
Foster Creek | 2025 | 83210 - Electrical | Outlets and switches replacement program | 83210 | PMC | Project | 102000 | 81929 | 20071 |  | In Progress
Foxdale Village | 2025 | Storm sewer piping | Clean storm drains | 51130-00 | GC | Project | 22000 | 0 | 22000 |  | Not Started
Foxdale Village | 2025 | Stripe parking areas | Restripe parking lot | 51053-00 | GC | Project | 21000 | 0 | 21000 |  | Not Started
Foxdale Village | 2025 | Asphalt Coating | Fill asphalt cracks and seal coat parking lot Equity PCA Item 3.2.2- $110,500- Damaged pavement consisting of linear cra | 51050-00 | GC | Project | 182000 | 182000 | 0 |  | Completed
Foxdale Village | 2025 | Add Parking Spaces | Parking is an issue at the property, explore adding lot area or gaining spaced via restriping | 51050-00 | GC | Project | 100000 | 0 | 100000 |  | Not Started
Foxdale Village | 2025 | Sidewalks | Replace trip hazards Lender PCR Item- $3,000- Sidewalks were observed to have uneven edges, resulting in trip hazards. T | 51091-00 | GC | Project | 36000 | 36000 | 0 |  | Completed
Foxdale Village | 2025 | Landscape irrigation | Inspect and repair irrigation | 51046-00 | GC | Project | 32000 | 32000 | 0 |  | Completed
Foxdale Village | 2025 | Landscaping | Tree trim Equity PCA Item 3.2.4- $5,000- Overgrown tress were observed throughout the subject property. Many of the ove | 51043-00 | GC | Project | 42000 | 42000 | 0 |  | Completed
Foxdale Village | 2025 | Replace camera / security equipment | Replace camera and security equipment | 51993-00 | PMC | Project | 51000 | 0 | 51000 |  | Not Started
Foxdale Village | 2025 | Playground | Fall zone on 4 playgrounds, misc equipment repairs and replacements | 51029-00 | GC | Project | 30000 | 0 | 30000 |  | Not Started
Foxdale Village | 2025 | Concrete deck / floor fill | 25 Balcony or landing replacements | 51072-00 | GC | Project | 90000 | 90000 | 0 |  | Completed
Foxdale Village | 2025 | Wall framing | Replace damaged framing in gable ends | 51070-00 | GC | Project | 50000 | 50000 | 0 |  | Completed
Foxdale Village | 2025 | Repair exterior stair treads and stringers | Secure railings | 51072-00 | GC | Project | 24000 | 24000 | 0 |  | Completed
Foxdale Village | 2025 | Repair balcony framing & decking | Balcony Decking | 51072-00 | GC | Project | 24000 | 24000 | 0 |  | Completed
Foxdale Village | 2025 | Landscaping -Leasing office | PCA 4.1 -Leasing Office – Allowance for landscaping remediation at ledge extension | 51045-00 | GC | Project | 5000 | 0 | 5000 |  | Not Started
Foxdale Village | 2025 | Repair cracks in leasing office | PCA -4.1 - Leasing Office – Allowance for spalling and crack repairs at concrete slab ledge extension, and potential sec | 51090-00 | GC | Project | 5000 | 0 | 5000 |  | Not Started
Foxdale Village | 2025 | Replace damaged wood | PCA 4.2 -Allowance for replacement of damaged wood framing during exterior cladding replacement. | 51070-00 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Foxdale Village | 2025 | Repair masonary fence | PCA 4.2 - Remediation and/or sectional replacement of masonry perimeter fence. | 51076-00 | GC | Project | 20000 | 0 | 20000 |  | Not Started
Foxdale Village | 2025 | Repair concrete stairs | PCA 4.2 - Repair or replace damaged concrete treads at stairs. | 51090-00 | GC | Project | 20000 | 0 | 20000 |  | Not Started
Foxdale Village | 2025 | Inspect stair landing | PCA 4.2- Evaluate stair landing framing with borescope and replace any damaged framing, soffit material and rim joist as | 51070-00 | GC | Project | 5000 | 0 | 5000 |  | Not Started
Foxdale Village | 2025 | Repair exposed wood beams | PCA 4.2 -Remediate wood deterioration of exterior exposed wood beams and vertical braces | 51070-00 | GC | Project | 15000 | 0 | 15000 |  | Not Started
Foxdale Village | 2025 | Replace skylight lens | PCA 4.4.1 -Replace deteriorated or capped skylight lens | 51074-00 | GC | Project | 3000 | 0 | 3000 |  | Not Started
Foxdale Village | 2025 | Replace deteriorated roof-lines | PCA 4.4.1 - Replace deteriorated wood siding at roof-lines | 51075-00 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Foxdale Village | 2025 | Replace roof hatch | PCA 4.4.1 - Replace roof hatch and install safety railing | 51062-00 | GC | Project | 7000 | 0 | 7000 |  | Not Started
Foxdale Village | 2025 | Replace missing vent tops | PCA 4.4.1 - Replace missing vent tops | 51062-00 | GC | Project | 2000 | 0 | 2000 |  | Not Started
Foxdale Village | 2025 | Replace equipment screen | PCA 4.4.1 - Replace equipment screen | 51070-00 | GC | Project | 36000 | 0 | 36000 |  | Not Started
Foxdale Village | 2025 | Repair patio/balcony railings | Patio fence repairs | 51077-00 | GC | Project | 48000 | 48000 | 0 |  | Completed
Foxdale Village | 2025 | Expansion Joints | Replace stucco expansion joints | 51075-00 | GC | Project | 48000 | 48000 | 0 |  | Completed
Foxdale Village | 2025 | Roofing | 19 roofs appear to be TPO- replace one roof and repair 19 roofs yr2 A, C, D, E, F, G, H, I, J, K, M, N, P, R, T, V, X, | 51061-00 | GC | Project | 97500 | 88000 | 9500 |  | In Progress
Foxdale Village | 2025 | Roofing Maintenance | PCA 4.4.1 All roof sections: Annual maintenance | 51062-00 | GC | Project | 25243 | 0 | 25243 |  | Not Started
Foxdale Village | 2025 | Gutters & downspouts | Clean and repair gutters | 51071-00 | GC | Project | 29274 | 29274 | 0 |  | Completed
Foxdale Village | 2025 | Flashing | Replace damaged flashing | 51062-00 | GC | Project | 24000 | 24000 | 0 |  | Completed
Foxdale Village | 2025 | Sealants & caulking | Seal transition to stucco from siding | 51062-00 | GC | Project | 24000 | 24000 | 0 |  | Completed
Foxdale Village | 2025 | Repair / replace wood shingles | Replace T-111 siding with Hardie. Equity PCA Item 4.3.1- $19,800- Damaged and deteriorated T1-11 siding was present at n | 51075-00 | GC | Project | 1033200 | 1033200 | 0 |  | Completed
Foxdale Village | 2025 | Repair stucco | Repair damaged stucco | 51075-00 | GC | Project | 75000 | 75000 | 0 |  | Completed
Foxdale Village | 2025 | Exterior building paint | Paint community Equity PCA Item 3.2.7- $15,000- The paint finish on the wood fencing throughout the site was observed t | 51080-00 | GC | Project | 401800 | 401800 | 0 |  | Completed
Foxdale Village | 2025 | Repair / replace wood trim | Replace trim and damaged fascia | 51082-00 | GC | Project | 179500 | 179500 | 0 |  | Completed
Foxdale Village | 2025 | Green Program - Echelon Energy Retrofit | Energy Retrofit | 51160-00 | GC | Project | 116000 | 0 | 116000 |  | Not Started
Foxdale Village | 2025 | Deferred Maintenance - Remove Mold | Lender PCR Item- $6,000- Mold was observed in the bathrooms of many units. The units include the following: Unit 1350-52 | 52111-00 | PMC | Project | 6000 | 25702 | -19702 |  | Completed
Foxdale Village | 2025 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 51993-00 | PMC | Project | 14129 | 60523 | -46394 |  | Completed
Foxdale Village | 2025 | Unit deferred maintenance | Flooring replacement needed: kitchen (26), living room (13), bedroom (31), and bathroom (7) Equity PCA Item 6.5.2- $341, | 51157-00 | PMC | Project | 85400 | 42108 | 43292 |  | In Progress
Foxdale Village | 2025 | Down Units | Lender PCR Item- $5,500- At the time of the site visit, one (1) down unit (Unit 1350-513) was observed due to fire damag | 52111-00 | GC | Project | 5500 | 0 | 5500 |  | Not Started
Foxdale Village | 2025 | Clubhouse / Office Remodel | Paint, Repair, and replace carpet in office, explore repurposing community center for fitness center or other use | 51169-00 | GC | Project | 150000 | 0 | 150000 |  | Not Started
Foxdale Village | 2025 | Clubhouse / Office Furniture | Clubhouse Furniture | 51160-06 | GC | Project | 30000 | 0 | 30000 |  | Not Started
Foxdale Village | 2025 | Electrical distribution | Inspect and repair lighting controllers on all buildings Contingency for electrical panel upgrades/replacements starting | 51140-00 | GC | Project | 27500 | 25000 | 2500 |  | In Progress
Foxdale Village | 2025 | Electrical distribution | Electrical service and distribution equipment, Phased replacement | 51140-00 | GC | Project | 57400 | 0 | 57400 |  | Not Started
Foxdale Village | 2025 | Fire Alarm System | Lender PCR Item- $2,000- Repair the main fire alarm system which indicates "trouble" and perform the expired annual insp | 51993-00 | PMC | Project | 1000 | 4284 | -3284 |  | Completed
Foxdale Village | 2025 | Infrared Scan of Electrical Equipment | Equity PCA Item 5.3- $6,000- An infrared (IR) scan tag was observed at an electrical service entrance, the date on the t | 51993-01 | GC | Project | 6000 | 0 | 6000 |  | Not Started
Foxdale Village | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 351235 | 0 | 351235 |  | Reserve
Foxdale Village | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 183884 | 0 | 183884 |  | Reserve
Latitude at the Commons | 2025 | Landscape Cleanup and Enhancements | Concept Walk - Tree trimming | 84303 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Latitude at the Commons | 2025 | Asphalt Coating | Seal Coat parking lot | 84204 | GC | Project | 89000 | 26700 | 62300 |  | In Progress
Latitude at the Commons | 2025 | Stripe parking areas | Stripe Parking Lots | 84201 | GC | Project | 12000 | 3600 | 8400 |  | In Progress
Latitude at the Commons | 2025 | Sidewalks | Sidewalk Repairs H - Sunken and uplifted sidewalks at the front of buildings | 84115 | GC | Project | 5200 | 1560 | 3640 |  | In Progress
Latitude at the Commons | 2025 | ADA parking & curb cuts | Need ADA signage and poles LPCA - ADA compliant parking spaces are required to have a sign with the International Symbo | 83520 | PMC | Project | 9000 | 0 | 9000 |  | Not Started
Latitude at the Commons | 2025 | Pavement | Crack fill large crack running in the center of the drive aisle LPCA - Localized cracking was observed in the center of | 84204 | GC | Project | 12000 | 3600 | 8400 |  | In Progress
Latitude at the Commons | 2025 | Flatwork Repairs | LPCA (PR-90) - Two vertical-separation trip hazards were observed. One was at the north entrance to the breezeway of Bui | 84115 | PMC | Project | 1000 | 503 | 497 |  | In Progress
Latitude at the Commons | 2025 | Erosion control | Concept Walk - Required in two separate locations per management. They are currently digging a trench to release, howeve | 84517 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Latitude at the Commons | 2025 | Resurface swimming pool | Resurface Pool | 84095 | GC | Project | 45000 | 13500 | 31500 |  | In Progress
Latitude at the Commons | 2025 | Swimming pool furniture | Concept Walk - Pool umbrellas | 84360 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Latitude at the Commons | 2025 | Dumpster enclosures | Paint Enclosures | 84111 | GC | Project | 7500 | 2250 | 5250 |  | In Progress
Latitude at the Commons | 2025 | Repair exterior stair treads and stringers | Stairs, Treads, and stringers are bare wood they are in good shape - need sealant | 84114 | GC | Project | 72000 | 21600 | 50400 |  | In Progress
Latitude at the Commons | 2025 | Repair balcony framing & decking | Landings and balconies are bare wood - need sealant | 84104 | GC | Project | 60000 | 18000 | 42000 |  | In Progress
Latitude at the Commons | 2025 | Gutters & downspouts | Clean and repitch gutters throughout property H - The roof and gutters at Garage G is damaged. | 83439 | GC | Project | 18000 | 5400 | 12600 |  | In Progress
Latitude at the Commons | 2025 | Sealants & caulking | Seal all seams on face nailed siding | 84102 | GC | Project | 18000 | 5400 | 12600 |  | In Progress
Latitude at the Commons | 2025 | Repair / replace cement fiber siding | Remove and replace buckling siding on 5 gable ends of buildings | 84206 | GC | Project | 46000 | 13800 | 32200 |  | In Progress
Latitude at the Commons | 2025 | Breezeway Missing/Exposed Nails | H - Breezeway at building missing/exposed nails on the stairway for building 2184 and 2210 | 84120 | GC | Project | 1000 | 300 | 700 |  | In Progress
Latitude at the Commons | 2025 | Exterior building | Corner to corner point of repaired areas. | 84101 | GC | Project | 54000 | 16200 | 37800 |  | In Progress
Latitude at the Commons | 2025 | Repair / replace wood trim | Replace rotted wood | 84105 | GC | Project | 12000 | 3600 | 8400 |  | In Progress
Latitude at the Commons | 2025 | Flooring Repairs | H - Repair carpets with trip hazards in units 115, 118, 121, 123, 127, 128, 133, 212, 234, 432, 613, 625, 827, 914, 922, | 83304.0 | PMC | Project | 20736 | 0 | 20736 |  | Not Started
Latitude at the Commons | 2025 | Replace old smoke detectors | H - Majority of units. These devices have an EUL of 7-10. The majority of smoke detectors were of original installation. | 83236 | PMC | Project | 32400 | 0 | 32400 |  | Not Started
Latitude at the Commons | 2025 | Replace Smoke Detectors in observed units | H - Smoke detectors missing in units: 212, 234, 726, 1021, 1114 | 83236 | PMC | Project | 375 | 0 | 375 |  | Not Started
Latitude at the Commons | 2025 | Clean Dryer vents | Dryer Vent Cleaning | 84106 | GC | Project | 21600 | 6480 | 15120 |  | In Progress
Latitude at the Commons | 2025 | Window Repairs | H - Windows in units 137, 213, and 417 are in need of repair. | 84304.0 | PMC | Project | 2097 | 646 | 1451 |  | In Progress
Latitude at the Commons | 2025 | Missing Kitchen cabinet drawer front | H - Unit 117 has missing drawer front in kitchen | 83212 | PMC | Project | 200 | 0 | 200 |  | Not Started
Latitude at the Commons | 2025 | Patio screening on remaining units | Concept Walk - Add patio screen doors | 84215 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Latitude at the Commons | 2025 | Fire Stops | Install fire stops in every unit | 84211 | PMC | Project | 28224 | 82476 | -54252 |  | Completed
Latitude at the Commons | 2025 | Golf Cart | Concept Walk - not included in personal property list. Currently have 4 carts on site | 83375 | PMC | Project | 40000 | 0 | 40000 |  | Not Started
Latitude at the Commons | 2025 | Domestic Hot Water Heater | H - Rust damage on the DHW heater for units 522, 925, and 1217 | 84476 | GC | Project | 4485 | 1346 | 3140 |  | In Progress
Latitude at the Commons | 2025 | Electrical Distribution | Repair timers or photo cells | 84210 | GC | Project | 9000 | 2700 | 6300 |  | In Progress
Latitude at the Commons | 2025 | Exit Sign | H - Exit sign is damaged at 2210 and 2175 buildings | 84239 | GC | Project | 376 | 113 | 263 |  | In Progress
Latitude at the Commons | 2025 | Add lighting | Concept Walk - exterior lighting is lacking, should supplement the existing lighting to ensure it's well lit at night | 84210 | GC | Project | 20000 | 6000 | 14000 |  | In Progress
Latitude at the Commons | 2025 | LED Upgrade - Exterior Common Area Lighting | Hillmann Green Energy Audit - EEM No. 7 | 84210 | PMC | Project | 4546 | 2222 | 2324 |  | In Progress
Latitude at the Commons | 2025 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 271880 | 0 | 271880 |  | Reserve
Latitude at the Commons | 2025 | Construction Management Fee | CM Fees | 84505.0 | GC | CM Fee | 50381 | 0 | 50381 |  | Reserve
Oak Park Monrovia | 2025 | Landscape Cleanup and Enhancements | DPCA 3.1.4 / EPCA 3.2.4 - Landscape areas were observed to be eroded with exposed irrigation lines at significant areas | 51045-00 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Oak Park Monrovia | 2025 | Erosion control | Fill areas of erosion around buildings and flower beds throughout property. Specifically areas that have exposed PVC irr | 51086-00 | GC | Project | 17500 | 5250 | 12250 |  | In Progress
Oak Park Monrovia | 2025 | Landscaping | Tree trim - building clearance throughout property | 51043-00 | PMC | Project | 28500 | 0 | 28500 |  | Not Started
Oak Park Monrovia | 2025 | Carports / Garages | Repair damaged coating in parking structure at spots 65, 66 and 68. Also, extend routed and repair expansion joint at ra | 51172-00 | GC | Project | 5250 | 1575 | 3675 |  | In Progress
Oak Park Monrovia | 2025 | Mold Remediation | Mold Remediation | 51180-00 | PMC | Project | 6000 | 0 | 6000 |  | Not Started
Oak Park Monrovia | 2025 | Termite Remediation | Termite Remediation - tent and local treatment (per Ecola remediation proposal) | 51992-00 | PMC | Project | 57400 | 0 | 57400 |  | Not Started
Oak Park Monrovia | 2025 | Roof framing | Inspect all mansard roofs and repair any damage to coping/façade of building to ensure areas are secure to prevent leaki | 51070-00 | GC | Project | 47500 | 14250 | 33250 |  | In Progress
Oak Park Monrovia | 2025 | Repair patio/balcony railings | Repair/replace areas of rotted/failing wood railings on balconies. | 51077-00 | GC | Project | 75000 | 22500 | 52500 |  | In Progress
Oak Park Monrovia | 2025 | Repair balcony framing & decking | DPCA 3.2.7 / EPCA 4.5 Select balconies at the buildings were observed to have deteriorated wood members at the balcony d | 51072-00 | GC | Project | 140000 | 42000 | 98000 |  | In Progress
Oak Park Monrovia | 2025 | Asphalt composite shingle roofing | Repair and add proper flashing to the roofing of the ganged mains and meter bank closets. | 51060-00 | GC | Project | 21500 | 6450 | 15050 |  | In Progress
Oak Park Monrovia | 2025 | Repair stucco | Repairs throughout property, also repair cement plaster at northeaster corner of western wing of parking garage. | 51075-00 | GC | Project | 40000 | 12000 | 28000 |  | In Progress
Oak Park Monrovia | 2025 | Interior Hallway painting | Repair drywall and paint all interior hallways & Common Areas | 51160-00 | GC | Project | 94000 | 28200 | 65800 |  | In Progress
Oak Park Monrovia | 2025 | Exterior building | Paint Exterior of Property (incl. Parking Garages) | 51080-00 | GC | Project | 234000 | 70200 | 163800 |  | In Progress
Oak Park Monrovia | 2025 | Signage - Building identification | Adding signage to locate the leasing office - specifically on the North Building to guide tenants to the South Building | 51030-00 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Oak Park Monrovia | 2025 | Common Area Greenspace Enhancements | Placeholder for greenspace improvements (e.g. dog park, bocce ball, etc.) | 51160-00 | PMC | Project | 24000 | 5162 | 18838 |  | In Progress
Oak Park Monrovia | 2025 | Smoke and Fire Detection System, central panel | PCA 3.3.10: Current inspection tags were not observed on the main control panel, building panels or elevator panels. Ins | 51140-00 | PMC | Project | 1500 | 403 | 1097 |  | In Progress
Oak Park Monrovia | 2025 | Water pressure regulator / back-flow preventer | Install backflow prevention device at north building. Currently leaking. | 51130-00 | GC | Project | 2000 | 600 | 1400 |  | In Progress
Oak Park Monrovia | 2025 | Stormwater sump pump system, replace | PCA 3.3.4. It was observed that the South Building parking garage had failed, and control panel could not be energized a | 51130-00 | GC | Project | 8800 | 2640 | 6160 |  | In Progress
Oak Park Monrovia | 2025 | Hydro-jetting & Camera inspection | PCA 5.1 -It appears that no hydro-jetting and camera inspection has been performed at the property. Industry best practi | 51134-00 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Oak Park Monrovia | 2025 | Seismic shut off valve - install | DPCA 3.3.6 / EPCA 5.3 -The observed natural gas services lacked seismic shutoff valves to prevent dangerous gas leaks in | 51990-00 | GC | Project | 39000 | 11700 | 27300 |  | In Progress
Oak Park Monrovia | 2025 | MAUs - Ventilation System | DPCA 3.3.1 / EPCA 5.2 The MAUs at each building were in poor overall condition. The unit at the North Building unit was | 51120-00 | GC | Project | 32000 | 9600 | 22400 |  | In Progress
Oak Park Monrovia | 2025 | Electrical Distribution Center and Unit Electrical Pane | PCA 3.3.3 Exterior electrical service and distribution equipment was generally from the original construction and approx | 51140-00 | GC | Project | 360000 | 108000 | 252000 |  | In Progress
Oak Park Monrovia | 2025 | Common area light fixtures | Replace all patio lighting with new LED lighting. | 51141-00 | GC | Project | 23500 | 7050 | 16450 |  | In Progress
Oak Park Monrovia | 2025 | Replace garage lighting | Replace existing garage lighting with LED. | 51141-00 | GC | Project | 15000 | 4500 | 10500 |  | In Progress
Oak Park Monrovia | 2025 | Contingency | Construction Contingency | 51175-00 | GC | Contingency | 90693 | 0 | 90693 |  | Reserve
Oak Park Monrovia | 2025 | Construction Management Fee | CM Fees | 51190-00 | GC | CM Fee | 69407 | 0 | 69407 |  | Reserve
Orchard Glen | 2025 | Landscape Cleanup and Enhancements | EPCA 4.4.1 - Cut back trees in contact with roofs. Initial tree trim, landscape cleanup, entry and tour path enhancement | 51045-00 | GC | Project | 100000 | 0 | 100000 |  | Not Started
Orchard Glen | 2025 | Asphalt Coating | EPCA 3.2.2 - The asphalt seal coat and pavement markings and striping appeared to be in fair to poor condition. The seal | 51053-00 | GC | Project | 121000 | 36300 | 84700 |  | In Progress
Orchard Glen | 2025 | Accessibility | EPCA 7.1 - The leasing office restroom lacked scald protection at the exposed lavatory piping. Installation is recommend | 51091-00 | GC | Project | 400 | 400 | 0 |  | Completed
Orchard Glen | 2025 | Repair / replace swimming pool pumps | Pool Pumps | 51026-00 | GC | Project | 6800 | 4080 | 2720 |  | In Progress
Orchard Glen | 2025 | Fences & gates - patios | EPCA 3.2.3 - The ground floor patio fence (wood guardrail) located between Units 85 and 87 was noted to be leaning outwa | 51076-00 | GC | Project | 1000 | 1000 | 0 |  | Completed
Orchard Glen | 2025 | Carports / Garages | Repair carports and paint post and pearling EPCA 4.4.1 - Repair of impact damage to metal carport canopies. EPCA 3.2.9 - | 51172-00 | GC | Project | 28000 | 16800 | 11200 |  | In Progress
Orchard Glen | 2025 | Stripe parking areas | Striping of Parking Lots | 51053-00 | GC | Project | 23000 | 6900 | 16100 |  | In Progress
Orchard Glen | 2025 | Repair ADA deficiencies | LPCA - No ADA access aisles were observed in three ADA parking spaces. No insulation under the common area restroom sink | 51091-00 | GC | Project | 1500 | 450 | 1050 |  | In Progress
Orchard Glen | 2025 | Sidewalks | LPCA - limited sidewalk cracks were observed by the west playground equipment LPCA (PR-90) - a limited concrete sidewalk | 51091-00 | GC | Project | 32000 | 32000 | 0 |  | Completed
Orchard Glen | 2025 | Fences & gates - site perimeter | EPCA 3.2.7 - Damage/deterioration of the metal security perimeter fencing and the welded steel pool fencing was noted in | 51076-00 | GC | Project | 5000 | 5000 | 0 |  | Completed
Orchard Glen | 2025 | Retaining walls | The retaining walls appeared to be in fair condition. The walls appeared to exhibit lateral movement (leaning) and separ | 51085-00 | GC | Project | 62900 | 62900 | 0 |  | Completed
Orchard Glen | 2025 | Resurface swimming pool | Pool Resurfacing | 51023-00 | GC | Project | 51000 | 30600 | 20400 |  | In Progress
Orchard Glen | 2025 | Fences & gates - swimming pool | Swimming Pool Gate Repairs | 51076-00 | GC | Project | 38000 | 38000 | 0 |  | Completed
Orchard Glen | 2025 | Replacement of metal standoff post bases | EPCA 4.2 - The metal standoff bases at the wood walkway and stair posts near Unit 169 were exhibiting corrosion and pote | 51070-00 | GC | Project | 1000 | 1000 | 0 |  | Completed
Orchard Glen | 2025 | Replacement of damaged concrete treads at stairs | EPCA 4.2 - The concrete stair treads were noted with cracks (varying degrees) and spalling areas with exposed steel rein | 51090-00 | GC | Project | 16000 | 16000 | 0 |  | Completed
Orchard Glen | 2025 | WDO Treatment/Repairs | LPCA - Subsequent to thesite visit,managementprovided a WDOinspection reportconducted on 4/29/25 by TerminixInternationa | 51992-00 | PMC | Project | 160000 | 37109 | 122891 |  | In Progress
Orchard Glen | 2025 | WDO Inspection | LPCA - Subsequent to the site visit, management provided a WDO inspection report conducted on 4/29/25 by Terminix Intern | 51992-00 | PMC | Project | 2000 | 464 | 1536 |  | In Progress
Orchard Glen | 2025 | Concrete deck / floor fill | repair and paint balconies | 51072-00 | GC | Project | 40000 | 40000 | 0 |  | Completed
Orchard Glen | 2025 | Wall framing | replace damaged framing in chimney | 51070-00 | GC | Project | 48000 | 48000 | 0 |  | Completed
Orchard Glen | 2025 | Balcony framing & decking | Repair balcony framing & decking | 51072-00 | GC | Project | 16000 | 16000 | 0 |  | Completed
Orchard Glen | 2025 | Balconies/handrails/guardrails | Patio fence repairs and paint EPCA 4.2 - Elevated balconies and walkways are provided with wood guardrails, where posts | 51077-00 | GC | Project | 18000 | 72000 | -54000 |  | Completed
Orchard Glen | 2025 | Expansion joints | Repair exterior expansion joints | 51070-00 | GC | Project | 24000 | 24000 | 0 |  | Completed
Orchard Glen | 2025 | Asphalt composite shingle roofing | EPCA 4.4.1 - Replacement of half of the shingled roofs within the next year. EPCA 4.4.1 - Replacement of half of the shi | 51061-00 | GC | Project | 80000 | 24000 | 56000 |  | In Progress
Orchard Glen | 2025 | Repairs to roof systems | EPCA 4.4.1 - Immediate repairs to roof system to maintain water-tightness leading up to replacement. Immediate Repairs t | 51062-00 | GC | Project | 45000 | 13500 | 31500 |  | In Progress
Orchard Glen | 2025 | Gutters & downspouts | Gutters & Downspout Repairs | 51071-00 | GC | Project | 244800 | 244800 | 0 |  | Completed
Orchard Glen | 2025 | Sealants & caulking | Sealants and Caulking for Roof | 51062-00 | GC | Project | 24000 | 24000 | 0 |  | Completed
Orchard Glen | 2025 | Flashing | Flashing Repairs | 51062-00 | GC | Project | 38000 | 38000 | 0 |  | Completed
Orchard Glen | 2025 | Repair / replace wall shake shingles | Post cost is inclusive of dry rot repair Replace shake siding, T111 and window wall siding and repair textured siding | 51075-00 | GC | Project | 921600 | 921600 | 0 |  | Completed
Orchard Glen | 2025 | Exterior building paint | Exterior Painting | 51080-00 | GC | Project | 433550 | 390195 | 43355 |  | In Progress
Orchard Glen | 2025 | Repair / replace wood trim | EPCA 4.4.1 - Contingency for replacement of damaged wood decking and fascia during the first phase of roof replacements; | 51082-00 | GC | Project | 151200 | 151200 | 0 |  | Completed
Orchard Glen | 2025 | Remove Microbial Growth | LPCA (PR-90) - CBRE observed microbial growth. Specifically, these conditions were observed at the bathtub of Unit 3873- | 52111-00 | PMC | Project | 1100 | 30373 | -29273 |  | Completed
Orchard Glen | 2025 | Down Units | EPCA 6.5.2 - At the time of the site assessment, one residential unit (Unit 142) was identified to be in an un-rentable/ | 52111-00 | PMC | Project | 20000 | 35021 | -15021 |  | Completed
Orchard Glen | 2025 | Damaged Ceiling | LPCA (PR-90) - During an additional inspection conducted by the Lender, ceiling damage and possible water intrusion were | 52111-00 | PMC | Project | 700 | 1695 | -995 |  | Completed
Orchard Glen | 2025 | Roach Treatment | LPCA (PR-90) - During an additional inspection conducted by the Lender, evidence of roaches was observed in Unit 1-10. C | 51992-00 | PMC | Project | 350 | 81 | 269 |  | In Progress
Orchard Glen | 2025 | Back-flow preventer | EPCA 5.1 - The two 6" reduced pressure backflow prevention devices appear to be original and should be replaced. Annual | 51130-00 | PMC | Project | 16000 | 142413 | -126413 |  | Completed
Orchard Glen | 2025 | Split HVAC System (Move to HVAC) | EPCA 5.2 - The split heat pump system serving the clubhouse is more than 20 years old. Based on age and EUL, replacement | 51120-00 | PMC | Project | 24000 | 3786 | 20214 |  | In Progress
Orchard Glen | 2025 | Stormwater Pipe Repair | Clean storm drains | 51131-00 | GC | Project | 25000 | 25000 | 0 |  | Completed
Orchard Glen | 2025 | Natural Gas Seismic Shutoff | EPCA 5.3 - Seismic shut-off valves were not installed on the natural gas services. The property is located in a seismic | 51130-00 | GC | Project | 21000 | 21000 | 0 |  | Completed
Orchard Glen | 2025 | Green Up Program | Domestic Hot Water - Gas Tank Heater - Large, (0.95 TE), Qty 12, Apartments | 51990-00 | PMC | Project | 187200 | 12212 | 174988 |  | In Progress
Orchard Glen | 2025 | Green Up Program | Water Fixture - Kitchen Aerators, (1.2 gpm 100% Aerator Replacement), Qty 288, Apartments | 51990-00 | PMC | Project | 2880 | 0 | 2880 |  | Not Started
Orchard Glen | 2025 | Green Up Program | Water Fixture - Bathroom Aerators, (0.5 gpm 100% Aerator Replacement), Qty 320, Apartments | 51990-00 | PMC | Project | 3200 | 0 | 3200 |  | Not Started
Orchard Glen | 2025 | Green Up Program | Water Fixture - WaterSense Certified Showerheads, (1.25 gpm), Qty 294, 92% of Total Showerheads | 51990-00 | PMC | Project | 19110 | 0 | 19110 |  | Not Started
Orchard Glen | 2025 | Green Up Program | Water Fixture - WaterSense Certified Toilets, (0.8 gpf), Qty 240, 75% of Total Toilets | 51990-00 | PMC | Project | 108960 | 0 | 108960 |  | Not Started
Orchard Glen | 2025 | Electrical service and distribution, Ongoing Repalcemen | inspect and repair lighting controllers on all buildings | 51140-00 | GC | Project | 16000 | 16000 | 0 |  | Completed
Orchard Glen | 2025 | Contingency | Contingency Amount | 51180-00 | GC | Contingency | 166381 | 0 | 166381 |  | Reserve
Orchard Glen | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 174700 | 0 | 174700 |  | Reserve
Paddock Club | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84303 | PMC | Project | 20000 | 37500 | -17500 |  | Completed
Paddock Club | 2025 | Stripe parking areas | Stripe Parking Lots | 84201 | GC | Project | 24000 | 24000 | 0 |  | Completed
Paddock Club | 2025 | Asphalt Coating | Crack fill and double seal coat asphalt throughout property. Lender PCA Item- Damaged pavement consisting of linear crac | 84204 | GC | Project | 425000 | 425000 | 0 |  | Completed
Paddock Club | 2025 | ADA parking & curb cuts | Lender PCA Item- Inadequate number of accessible parking and van accessible parking spaces at the leasing office. Instal | 84221 | GC | Project | 15000 | 15000 | 0 |  | Completed
Paddock Club | 2025 | Sidewalks | Repair cracked/broken sidewalks throughout property. | 84115 | GC | Project | 40000 | 40000 | 0 |  | Completed
Paddock Club | 2025 | Fences & gates - site perimeter | Repair deck walkways/fencing throughout property. Some areas have broken stairs and missing areas of pickets. Railing r | 84205 | GC | Project | 50000 | 50000 | 0 |  | Completed
Paddock Club | 2025 | Retaining walls | Repair retaining walls where railroad ties are rotted out. Lender PCA Item- Damage was observed at a section of retaini | 84434 | GC | Project | 12500 | 48000 | -35500 |  | Completed
Paddock Club | 2025 | Landscaping | Tree trim around property, especially around the lake. Clean up of brush foliage around lakes, as well. 1st call biddin | 84303 | GC | Project | 125000 | 125000 | 0 |  | Completed
Paddock Club | 2025 | Resurface swimming pool | Resurface main pool at clubhouse. | 84095 | GC | Project | 42750 | 42750 | 0 |  | Completed
Paddock Club | 2025 | Replace swimming pool coping | Deck-O-Seal coping around pool. | 84361 | GC | Project | 5000 | 5000 | 0 |  | Completed
Paddock Club | 2025 | Repair swimming pool deck | Clean pool deck, fill cracks and seal. Also, clean and resurface concreted steps going down to pool from clubhouse. | 84361 | GC | Project | 22500 | 22500 | 0 |  | Completed
Paddock Club | 2025 | Pergola Court | Replace any damaged/rotted decking around the clubhouse and pool area. | 84105 | GC | Project | 26500 | 26500 | 0 |  | Completed
Paddock Club | 2025 | ADA Signage | Add ADA signage at clubhouse for wheelchair lift. | 84103 | GC | Project | 850 | 850 | 0 |  | Completed
Paddock Club | 2025 | Drainage | Add drainage in areas where water accumulates at base of retaining walls at building 17 | 84517 | GC | Project | 6000 | 6000 | 0 |  | Completed
Paddock Club | 2025 | Asphalt composite shingle roofing | Moderate Roof Tune up on every building. This would include securing shingles, flashing, etc. Repairs of moderate water | 84433 | GC | Project | 75000 | 75000 | 0 |  | Completed
Paddock Club | 2025 | Repair / replace cement fiber siding | Repair/replace areas of failed hardie board and paint to match throughout property | 84206 | GC | Project | 68500 | 68500 | 0 |  | Completed
Paddock Club | 2025 | Repair / replace vinyl siding | Repair areas of damaged vinyl siding and clean vinyl covered in mold and grime throughout property. Also, secure vinyl s | 84206 | GC | Project | 68500 | 68500 | 0 |  | Completed
Paddock Club | 2025 | Repair / replace wood trim | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. Include ALL buildings throughout property. | 84105 | GC | Project | 95000 | 95000 | 0 |  | Completed
Paddock Club | 2025 | Clean Drier vents | Clean dryer vents throughout property. | 84106 | GC | Project | 25200 | 25200 | 0 |  | Completed
Paddock Club | 2025 | Water Damage in Units | Lender PCA Item- Partner recommends repair of any damaged finishes subsequent to the plumbing repairs in Units 1 and 146 | 83465 | PMC | Project | 3000 | 24082 | -21082 |  | Completed
Paddock Club | 2025 | Co 2 detectors | Install Co2 detectors in each unit. Lender PCR Item- Due to the presence of gas-fire water heaters at each unit, carbon | 82131 | PMC | Project | 23520 | 0 | 23520 |  | Not Started
Paddock Club | 2025 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 84239 | PMC | Project | 16269 | 0 | 16269 |  | Not Started
Paddock Club | 2025 | Hard turn/ renovation units | Lender PCA Item- Partner recommends completing the hard turn/ renovation in Units 130 and 281, which includes repair of | 84431 | PMC | Project | 10000 | 17250 | -7250 |  | Completed
Paddock Club | 2025 | Clubhouse / Office Remodel | Placeholder budget, paint the blue framed wall areas - possibly use 1st call to renovate kitchen if budget permits | 84208 | GC | Project | 20000 | 0 | 20000 |  | Not Started
Paddock Club | 2025 | Clubhouse / Office Furniture | Clubhouse Furniture | 84306 | PMC | Project | 50000 | 66212 | -16212 |  | Completed
Paddock Club | 2025 | Fitness Center Remodel | Flooring and walls ok, misc allowance - update lighting in boxing closet to match main gym and add Tonal or equivalent w | 84190 | PMC | Project | 5000 | 5465 | -465 |  | Completed
Paddock Club | 2025 | Fitness Equipment | Replace broken items, add equipment- functional trainer, stair stepper | 84190 | PMC | Project | 18000 | 19675 | -1675 |  | Completed
Paddock Club | 2025 | Pool Area Remodel | Placeholder budget | 84361 | PMC | Project | 10000 | 5620 | 4380 |  | In Progress
Paddock Club | 2025 | Pool Furniture | New furniture and games needed | 84360 | PMC | Project | 50000 | 57216 | -7216 |  | Completed
Paddock Club | 2025 | Picnic/Grill Area Remodel | Placeholder budget | 84203 | PMC | Project | 5000 | 18550 | -13550 |  | Completed
Paddock Club | 2025 | Picnic/Grill Furniture | Placeholder budget | 84340 | PMC | Project | 5000 | 7950 | -2950 |  | Completed
Paddock Club | 2025 | Access Control System | Add at maintenance shop. Fix system so that it can track which residents enter and leave, the manager said the system ca | 84275 | PMC | Project | 8000 | 0 | 8000 |  | Not Started
Paddock Club | 2025 | Mailboxes | Misc repairs - add concrete pad and USPS parcel boxes. | 84260 | GC | Project | 2000 | 7000 | -5000 |  | Completed
Paddock Club | 2025 | Package Lockers | Look at adding to laundry room. Budget 1 locker per 4-5 units @$400/locker | 84305 | PMC | Project | 33600 | 13600 | 20000 |  | In Progress
Paddock Club | 2025 | Laundry Room Renovation | Replace fluorescent lights, clean fans and paint ceiling where needed, add TV - TAM to negotiate laundry contract to inc | 84240 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Paddock Club | 2025 | Laundry Room Furniture | Add seating | 84240 | PMC | Project | 4000 | 0 | 4000 |  | Not Started
Paddock Club | 2025 | Office Computers | Have 2 new ones, budget for 1 new | 83265 | PMC | Project | 2000 | 13592 | -11592 |  | Completed
Paddock Club | 2025 | Plumbing Repairs | Lender PCR Item- Evidence of leaks and faulty piping was observed. According to the site escort, the piping leaks are re | 84209 | PMC | Project | 4800 | 76513 | -71713 |  | Completed
Paddock Club | 2025 | HVAC inspection and maintenance | Clean foliage around condensors and raise AC units with HVAC pads where needed. | 84217 | GC | Project | 33600 | 33600 | 0 |  | Completed
Paddock Club | 2025 | Electrical distribution | Electrical Distribution | 84210 | GC | Project | 26000 | 26000 | 0 |  | Completed
Paddock Club | 2025 | Common area light fixtures | Replace wallpacks on all buildings | 84112 | GC | Project | 28000 | 28000 | 0 |  | Completed
Paddock Club | 2025 | Replace breezeway lights | Install LED pole lights on pre-existing posts throughout the propety | 84112 | GC | Project | 50000 | 50000 | 0 |  | Completed
Paddock Club | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 282911 | 0 | 282911 |  | Reserve
Paddock Club | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 92400 | 0 | 92400 |  | Reserve
Rancho Cordova | 2025 | Asphalt Coating | Slurry Coat & Seal | 51050-00 | GC | Project | 64000 | 64000 | 0 |  | Completed
Rancho Cordova | 2025 | Stripe parking areas | PNA - Stripe parking areas | 51053-00 | GC | Project | 12000 | 12000 | 0 |  | Completed
Rancho Cordova | 2025 | ADA parking & curb cuts | Lender PCA - There is a van accessible parking space near the leasing office that is missing a pole-mounted sign. | 51091-00 | PMC | Project | 350 | 101 | 249 |  | In Progress
Rancho Cordova | 2025 | Sidewalks | PNA - Repair failing sidewalks | 51091-00 | GC | Project | 10000 | 10000 | 0 |  | Completed
Rancho Cordova | 2025 | Asphalt pavement | PNA - Remove and replace failing asphalt EPCA - All | 51050-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
Rancho Cordova | 2025 | Fences & gates - site perimeter | PNA - Rough iron repairs | 51076-00 | GC | Project | 8500 | 8500 | 0 |  | Completed
Rancho Cordova | 2025 | Patio and Fencing | EPCA - Repair areas of leaning wood patio enclosures as needed. Clean and restrain the fence with visible signs of deter | 51076-00 | GC | Project | 30000 | 30000 | 0 |  | Completed
Rancho Cordova | 2025 | Landscaping | PNA - Tree trim and branch removal | 51045-00 | PMC | Project | 32000 | 0 | 32000 |  | Not Started
Rancho Cordova | 2025 | Playground equipment | PNA - Fall Zone Material | 51029-00 | GC | Project | 9800 | 9800 | 0 |  | Completed
Rancho Cordova | 2025 | Storm sewer piping | PNA - Clean out storm sewer catch basin | 51130-00 | GC | Project | 8000 | 8000 | 0 |  | Completed
Rancho Cordova | 2025 | Exterior Wall framing | Building Framing repairs | 51070-00 | GC | Project | 12000 | 12000 | 0 |  | Completed
Rancho Cordova | 2025 | Expansion joints | Foundation Expansion Joint Repairs | 51090-00 | GC | Project | 8500 | 8500 | 0 |  | Completed
Rancho Cordova | 2025 | Asphalt composite shingle roofing | PNA - Shingle roof tune up, loose and hanging shingles were observed | 51062-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
Rancho Cordova | 2025 | Modified bitumen membrane Roof Repairs | PNA - Clean flat roofs and repair minor areas of potential water intrusion | 51062-00 | GC | Project | 26000 | 26000 | 0 |  | Completed
Rancho Cordova | 2025 | Gutters & downspouts | PNA - Cleanout gutters and scuppers | 51071-00 | GC | Project | 8500 | 8500 | 0 |  | Completed
Rancho Cordova | 2025 | Sealants & caulking | Roofing Sealants & Caulking Repairs | 51062-00 | GC | Project | 4500 | 4500 | 0 |  | Completed
Rancho Cordova | 2025 | Repair / replace wood siding | PNA - Replace rotted T1-11 | 51075-00 | GC | Project | 15000 | 15000 | 0 |  | Completed
Rancho Cordova | 2025 | Repair stucco | PNA - Repair stucco, mansard/hip wall | 51075-00 | GC | Project | 14000 | 14000 | 0 |  | Completed
Rancho Cordova | 2025 | Exterior building | PNA - Repaint community | 51080-00 | GC | Project | 188000 | 188000 | 0 |  | Completed
Rancho Cordova | 2025 | Repair / replace wood trim | PNA - Repair/replace rotted trim | 51082-00 | GC | Project | 8500 | 8500 | 0 |  | Completed
Rancho Cordova | 2025 | Repair/Replace Soffit | EPCA - Allowance to repair and replace all dry-rotted wood siding and soffits of the two-story residential buildings | 51075-00 | GC | Project | 6500 | 6500 | 0 |  | Completed
Rancho Cordova | 2025 | Smoke Alarm | EPCA - Budget to replace the existing smoke alarms based on age and useful life. The NFPA requires that smoke alarms not | 51993-00 | PMC | Project | 10920 | 0 | 10920 |  | Not Started
Rancho Cordova | 2025 | Fire Stops | Install Fire Stops | 51993-00 | PMC | Project | 8075 | 6119 | 1956 |  | In Progress
Rancho Cordova | 2025 | Unit deferred maintenance | EPCA - Remediate select bathrooms with signs of organic growth observed in Units 16, 25, 35, 45, 61 & 70 LPCA - Unit 70 | 52111-00 | PMC | Project | 12500 | 11546 | 954 |  | In Progress
Rancho Cordova | 2025 | Common area light fixtures | PNA - Building wall packs LPCA - Budget for installation of building wall packs throughout the site. | 51141-00 | GC | Project | 18500 | 18500 | 0 |  | Completed
Rancho Cordova | 2025 | Replace Pole light fixtures | PNA - Pole lights throughout the parking lot LPCA - Replacement of pole lights throughout the parking area. | 51141-00 | GC | Project | 28500 | 28500 | 0 |  | Completed
Rancho Cordova | 2025 | Replace electric panels | EPCA - Budget for phased replacement of the apartment Zinsco electrical distribution panels based on age and a recall du | 51140-00 | GC | Project | 47500 | 47500 | 0 |  | Completed
Rancho Cordova | 2025 | Contingency | Contingency | 51180-00 | GC | Contingency | 31107 | 0 | 31107 |  | Reserve
Rancho Cordova | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 32663 | 0 | 32663 |  | Reserve
Regency & Lexington | 2025 | Initial Lanscape Cleanup | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 51045-00 | PMC | Project | 10000 | 602 | 9398 |  | In Progress
Regency & Lexington | 2025 | Storm sewer piping | Storm water drainage repairs in courtyards | 51130-00 | GC | Project | 16714 | 0 | 16714 |  | Not Started
Regency & Lexington | 2025 | Asphalt Coating | Fill asphalt cracks Regency Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in go | 51053-00 | GC | Project | 91929 | 42900 | 49029 |  | In Progress
Regency & Lexington | 2025 | ADA parking & curb cuts | Repair trip hazards | 51091-00 | GC | Project | 24429 | 38000 | -13571 |  | Completed
Regency & Lexington | 2025 | Landscape irrigation | Inspect and repair Irrigation | 51046-00 | GC | Project | 20571 | 32000 | -11429 |  | Completed
Regency & Lexington | 2025 | Landscaping | Tree trim | 51043-00 | PMC | Project | 13000 | 300 | 12700 |  | In Progress
Regency & Lexington | 2025 | Resurface swimming pool | Resurface two pools | 51023-00 | GC | Project | 44500 | 71200 | -26700 |  | Completed
Regency & Lexington | 2025 | Repair / replace swimming pool pumps | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool d | 51026-00 | GC | Project | 7000 | 11200 | -4200 |  | Completed
Regency & Lexington | 2025 | Fences & gates - swimming pool | Adjust closers on pool gates | 51076-00 | GC | Project | 7000 | 14000 | -7000 |  | Completed
Regency & Lexington | 2025 | Parking Lot Cleaning | Power wash garage/parking walls and asphalt | 51050-00 | GC | Project | 10000 | 20000 | -10000 |  | Completed
Regency & Lexington | 2025 | Landscape irrigation | Irrigation repairs & upgrades | 51046-00 | PMC | Project | 7500 | 2007 | 5493 |  | In Progress
Regency & Lexington | 2025 | Termite Remediation | Regency - Drywood termite local treatments | 51992-00 | PMC | Project | 19000 | 18010 | 990 |  | In Progress
Regency & Lexington | 2025 | Termite Remediation | Regency - Subterranean termite treatment and baiting | 51992-00 | PMC | Project | 15400 | 14598 | 802 |  | In Progress
Regency & Lexington | 2025 | Wall framing | Replace damaged framing in gable ends | 51070-00 | GC | Project | 4500 | 9000 | -4500 |  | Completed
Regency & Lexington | 2025 | Replace hardware | PCA 4.2 - Building C, Unit 37 – Immediately replace the existing bolts with adequately sized bolts and washers. | 51156-00 | GC | Project | 500 | 500 | 0 |  | Completed
Regency & Lexington | 2025 | Install metal hardware | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces | 51092-00 | GC | Project | 67500 | 107500 | -40000 |  | Completed
Regency & Lexington | 2025 | Shore Maintenance Shed | PCA 4.2- Maintenance Shed - Immediately temporarily shore the unsupported double top plate. Engage licensed engineer to | 51998-00 | GC | Project | 6000 | 0 | 6000 |  | Not Started
Regency & Lexington | 2025 | Replace sheathing | PCA 4.2 - Replace deteriorated sheathing and joists at roof eaves, as required. | 51070-00 | GC | Project | 7500 | 7500 | 0 |  | Completed
Regency & Lexington | 2025 | Allowance for sectional replacement of damaged sheathin | PCA 4.2 - Allowance for sectional replacement of damaged sheathing and joists at carports. | 51172-00 | GC | Project | 5000 | 2500 | 2500 |  | In Progress
Regency & Lexington | 2025 | Repair exterior stair railings | Secure railings | 51077-00 | GC | Project | 12000 | 24000 | -12000 |  | Completed
Regency & Lexington | 2025 | Repair balcony framing & decking | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail PCA 4.2 - Repair wate | 51072-00 | GC | Project | 189643 | 236000 | -46357 |  | Completed
Regency & Lexington | 2025 | Expansion Joints | Expansion Joints | 51075-00 | GC | Project | 6000 | 12000 | -6000 |  | Completed
Regency & Lexington | 2025 | Asphalt composite shingle roofing Repair loose gravel s | Roof tune-up to include gravel. Reseal and secure gravel stop and drip edge. PCA 4.4.1 - Repair loose gravel stop and op | 51062-00 | GC | Project | 27000 | 125000 | -98000 |  | Completed
Regency & Lexington | 2025 | Gutters & downspouts Reconnect loose downspout. | Secure and clean gutters PCA 4.4.1 - Reconnect loose downspout. | 51071-00 | GC | Project | 12000 | 24000 | -12000 |  | Completed
Regency & Lexington | 2025 | Flashing | Repair flashing between stucco and t-111 | 51062-00 | GC | Project | 10000 | 20000 | -10000 |  | Completed
Regency & Lexington | 2025 | Sealants & caulking | Seal joints in t-111 | 51062-00 | GC | Project | 18000 | 36000 | -18000 |  | Completed
Regency & Lexington | 2025 | Repair / replace wood siding | Replace rotted t-111 siding | 51075-00 | GC | Project | 24000 | 48000 | -24000 |  | Completed
Regency & Lexington | 2025 | Exterior building | Paint community | 51080-00 | GC | Project | 239143 | 297600 | -58457 |  | Completed
Regency & Lexington | 2025 | Repair / replace wood trim | Replace rotted fascia and trim | 51082-00 | GC | Project | 36000 | 57600 | -21600 |  | Completed
Regency & Lexington | 2025 | Repair stucco | Some walls next to windows need patching and paint | 51075-00 | GC | Project | 3000 | 6000 | -3000 |  | Completed
Regency & Lexington | 2025 | Clubhouse / Office Remodel | No clubhouse, allowance for office | 51169-00 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Regency & Lexington | 2025 | Clubhouse / Office Furniture | Need seating for reception area in leasing office. | 51160-06 | PMC | Project | 4000 | 0 | 4000 |  | Not Started
Regency & Lexington | 2025 | Pool Area Remodel | Expand pool fenced area to make space for furniture | 51160-00 | GC | Project | 15000 | 0 | 15000 |  | Not Started
Regency & Lexington | 2025 | Pool Furniture | No furniture currently, need chaises and other furniture for main pool. Tables/chairs and armcharis only for 2nd pool d | 51011-00 | PMC | Project | 25000 | 0 | 25000 |  | Not Started
Regency & Lexington | 2025 | Picnic/Grill Area Remodel | Small grill area by pool, look at adding outdoor counter | 51160-04 | PMC | Project | 8000 | 0 | 8000 |  | Not Started
Regency & Lexington | 2025 | Picnic/Grill Furniture | Picnic tables or tables/chairs needed | 51160-04 | PMC | Project | 3000 | 0 | 3000 |  | Not Started
Regency & Lexington | 2025 | Playground equipment | Add seating and/or picnic tables year 1, budget for equipment replacement in year 4. | 51029-00 | GC | Project | 6000 | 10000 | -4000 |  | Completed
Regency & Lexington | 2025 | Need key trak for office | Key Track | 51990-02 | PMC | Project | 3500 | 0 | 3500 |  | Not Started
Regency & Lexington | 2025 | Security Camera System | Don't have anything, budget for a new system | 51993-00 | PMC | Project | 25000 | 0 | 25000 |  | Not Started
Regency & Lexington | 2025 | Back-flow preventer | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. | 51130-00 | PMC | Project | 2250 | 1856 | 394 |  | In Progress
Regency & Lexington | 2025 | Galvanized Pipe Replacement | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. | 51130-00 | GC | Project | 30000 | 0 | 30000 |  | Not Started
Regency & Lexington | 2025 | Sanitary Sewer Piping | Number based on actual bid; $285 per cleanout, est. 12 cleanouts. $402 per storm drain, 11 cleanouts. Regency & Lexingto | 51134-00 | PMC | Project | 7842 | 26166 | -18324 |  | Completed
Regency & Lexington | 2025 | Pipe Repair at Building 1 Boiler | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could p | 51130-00 | GC | Project | 750 | 3750 | -3000 |  | Completed
Regency & Lexington | 2025 | Natural Gas Seismic Shutoff | Will confirm with Gas utiliity company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equippe | 51130-00 | GC | Project | 12000 | 6000 | 6000 |  | In Progress
Regency & Lexington | 2025 | Energy Retrofit | Echelon upfront costs | 51160-00 | PMC | Project | 38441 | 0 | 38441 |  | Not Started
Regency & Lexington | 2025 | HVAC Replacement | Large Rheem HVAC unit outside office looks very old and may need to be replaced | 51120-00 | GC | Project | 4500 | 0 | 4500 |  | Not Started
Regency & Lexington | 2025 | Electrical distribution | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Inf | 51140-00 | GC | Project | 28143 | 13800 | 14343 |  | In Progress
Regency & Lexington | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 127553 | 0 | 127553 |  | Reserve
Regency & Lexington | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 70154 | 0 | 70154 |  | Reserve
Regency & Lexington | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 51045-00 | PMC | Project | 10000 | 602 | 9398 |  | In Progress
Regency & Lexington | 2025 | Storm sewer piping | Storm water drainage repairs in courtyards | 51130-00 | GC | Project | 9286 | 0 | 9286 |  | Not Started
Regency & Lexington | 2025 | Asphalt Coating | Filll asphalt cracks | 51053-00 | GC | Project | 51071 | 0 | 51071 |  | Not Started
Regency & Lexington | 2025 | ADA parking & curb cuts | Repair trip hazards | 51091-00 | GC | Project | 13571 | 0 | 13571 |  | Not Started
Regency & Lexington | 2025 | Landscape irrigation | Inspect and repair Irrigation | 51046-00 | GC | Project | 11429 | 0 | 11429 |  | Not Started
Regency & Lexington | 2025 | Landscaping | Tree trim | 51043-00 | PMC | Project | 13000 | 300 | 12700 |  | In Progress
Regency & Lexington | 2025 | Resurface swimming pool | Resurface two pools | 51023-00 | GC | Project | 44500 | 0 | 44500 |  | Not Started
Regency & Lexington | 2025 | Repair / replace swimming pool pumps | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool d | 51026-00 | GC | Project | 7000 | 0 | 7000 |  | Not Started
Regency & Lexington | 2025 | Fences & gates - swimming pool | Adjust closers on pool gates | 51076-00 | GC | Project | 7000 | 0 | 7000 |  | Not Started
Regency & Lexington | 2025 | Parking Lot Cleaning | Power wash garage/parking walls and asphalt | 51050-00 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Regency & Lexington | 2025 | Termite Remediation | Lexington - Drywood termite local treatments | 51992-00 | PMC | Project | 22000 | 20854 | 1146 |  | In Progress
Regency & Lexington | 2025 | Termite Remediation | Lexington - Subterranean termite treatment and baiting | 51992-00 | PMC | Project | 10800 | 10237 | 563 |  | In Progress
Regency & Lexington | 2025 | Wall framing | Replace damaged framing in gable ends | 51070-00 | GC | Project | 4500 | 0 | 4500 |  | Not Started
Regency & Lexington | 2025 | Allowance to epoxy inject concrete topping slabs and ap | PCA 4.2- Allowance to epoxy inject concrete topping slabs and apply elastomeric coating at elevated walkways. | 51072-00 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Regency & Lexington | 2025 | Install metal hardware | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces | 51092-00 | GC | Project | 40000 | 0 | 40000 |  | Not Started
Regency & Lexington | 2025 | Repair checked wood beams by epoxy injection. | PCA 4.2- Repair checked wood beams by epoxy injection. | 51070-00 | GC | Project | 500 | 500 | 0 |  | Completed
Regency & Lexington | 2025 | Fill pitch pockets and flash parking lot light bases. | PCA 4.4.1 - Fill pitch pockets and flash parking lot light bases. | 51141-00 | GC | Project | 2000 | 2000 | 0 |  | Completed
Regency & Lexington | 2025 | Allowance to replace deteriorated wood trim, fascia, ri | PCA 4.2-Allowance to replace deteriorated wood trim, fascia, rim joists and sheathing at elevated walkways and landings. | 51082-00 | GC | Project | 30000 | 24000 | 6000 |  | In Progress
Regency & Lexington | 2025 | Building G Balcony – sectional replacement of deteriora | PCA 4.2 -Building G Balcony – sectional replacement of deteriorated framing. | 51072-00 | GC | Project | 4500 | 3600 | 900 |  | In Progress
Regency & Lexington | 2025 | Allowance for exterior cladding replacement and replace | PCA 4.2 -Allowance for exterior cladding replacement and replacement of any damaged wood framing. | 51075-00 | GC | Project | 10000 | 8000 | 2000 |  | In Progress
Regency & Lexington | 2025 | Repair exterior stair railings | Secure railings | 51077-00 | GC | Project | 12000 | 0 | 12000 |  | Not Started
Regency & Lexington | 2025 | Repair balcony framing & decking | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail | 51072-00 | GC | Project | 105357 | 0 | 105357 |  | Not Started
Regency & Lexington | 2025 | Expansion Joints | Expansion Joints | 51075-00 | GC | Project | 6000 | 0 | 6000 |  | Not Started
Regency & Lexington | 2025 | Asphalt composite shingle roofing Repair loose gravel s | Roll roofing on roofs inspect and repair PCA 4.4.1 - Repair loose gravel stop and open perimeter flashing and membrane | 51062-00 | GC | Project | 20000 | 0 | 20000 |  | Not Started
Regency & Lexington | 2025 | Gutters & downspouts | Secure and clean gutters | 51071-00 | GC | Project | 12000 | 0 | 12000 |  | Not Started
Regency & Lexington | 2025 | Flashing | Repair flashing between stucco and t-111 | 51062-00 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Regency & Lexington | 2025 | Sealants & caulking | Seal joints in t-111 | 51062-00 | GC | Project | 18000 | 0 | 18000 |  | Not Started
Regency & Lexington | 2025 | Repair / replace wood siding | Replace rotted t-111 siding | 51075-00 | GC | Project | 24000 | 0 | 24000 |  | Not Started
Regency & Lexington | 2025 | Exterior building Paint | Paint community | 51080-00 | GC | Project | 132857 | 0 | 132857 |  | Not Started
Regency & Lexington | 2025 | Repair / replace wood trim Repair exposed lumber and el | Replace rotted fascia and trim PCA 4.4.1 - Repair exposed lumber and elevation changes. | 51082-00 | GC | Project | 36000 | 0 | 36000 |  | Not Started
Regency & Lexington | 2025 | Repair stucco | Some walls next to windows need patching and paint | 51075-00 | GC | Project | 3000 | 0 | 3000 |  | Not Started
Regency & Lexington | 2025 | Security Camera System | Don't have anything, budget for a new system | 51993-00 | PMC | Project | 25000 | 0 | 25000 |  | Not Started
Regency & Lexington | 2025 | Back-flow preventer | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. | 51130-00 | PMC | Project | 3000 | 2474 | 526 |  | In Progress
Regency & Lexington | 2025 | Galvanized Pipe Replacement | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone | 51130-00 | GC | Project | 40000 | 0 | 40000 |  | Not Started
Regency & Lexington | 2025 | Sanitary Sewer Piping | Number based on actual bid; $285 per cleanout, 8 cleanouts. $402 per storm drain, 6 cleanouts. Regency & Lexington Equit | 51134-00 | PMC | Project | 4692 | 15655 | -10963 |  | Completed
Regency & Lexington | 2025 | Pipe Repair at Building 1 Boiler | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could p | 51130-00 | GC | Project | 3000 | 0 | 3000 |  | Not Started
Regency & Lexington | 2025 | Natural Gas Seismic Shutoff | Will confirm with Gas utility company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equipped | 51130-00 | GC | Project | 8000 | 0 | 8000 |  | Not Started
Regency & Lexington | 2025 | Energy Retrofit | Echelon upfront costs | 51160-00 | PMC | Project | 27121 | 0 | 27121 |  | Not Started
Regency & Lexington | 2025 | HVAC Replacement | Large Rheem HVAC unit outside office looks very old and may need to be replaced | 51120-00 | GC | Project | 4500 | 0 | 4500 |  | Not Started
Regency & Lexington | 2025 | Electrical distribution | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Infr | 51140-00 | GC | Project | 17857 | 0 | 17857 |  | Not Started
Regency & Lexington | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 87858 | 0 | 87858 |  | Reserve
Regency & Lexington | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 48322 | 0 | 48322 |  | Reserve
Renaissance | 2025 | Landscape Cleanup and Enhancements | PNA: Building clearance tree trim and cleanup. | 83000-8300 | PMC | Project | 84500 | 0 | 84500 |  | Not Started
Renaissance | 2025 | Asphalt Coating | PNA - Fill all alligator cracks, potholes and then seal coat throughout property. Also, speed bump repairs throughout pr | 83000-2200 | GC | Project | 271120 | 0 | 271120 |  | Not Started
Renaissance | 2025 | Concrete pavement | PNA: Repair damaged/ cracked swales throughtout property Lender PCA: At the time of the assessment, several concrete tri | 83000-2800 | PMC | Project | 36500 | 6500 | 30000 |  | In Progress
Renaissance | 2025 | Stripe parking areas | PNA: Stripe parking lot throughout property. | 83000-2200 | GC | Project | 30000 | 0 | 30000 |  | Not Started
Renaissance | 2025 | ADA parking & curb cuts | PNA: Repair of any damaged curbs. | 83000-2800 | GC | Project | 10660 | 0 | 10660 |  | Not Started
Renaissance | 2025 | Sidewalks | Sidewalk Repairs | 83000-7100 | GC | Project | 33350 | 0 | 33350 |  | Not Started
Renaissance | 2025 | Landscape irrigation | PNA: Inspect and repair irrigation Lender PCA: At the time of the assessment, standing water was observed in various ar | 83000-6900 | PMC | Project | 31200 | 0 | 31200 |  | Not Started
Renaissance | 2025 | Replace swimming pool deck | PNA: Repairs to pool deck cracks and resurface. Bring depth markers, tile, and coping up to code | 83000-5100 | GC | Project | 100000 | 0 | 100000 |  | Not Started
Renaissance | 2025 | Playground equipment | PNA: Current playground extremely faded, if wanting replacement will need to add more funds. Number given is for adding | 83000-1700 | GC | Project | 12600 | 0 | 12600 |  | Not Started
Renaissance | 2025 | Carport and garage | PNA: Repair any damaged carports throughtout property. Replace 31 garage doors throughout property - significant damage. | 83000-2600 | GC | Project | 92400 | 2595 | 89805 |  | In Progress
Renaissance | 2025 | Dumpster enclosures | PNA: Damage cinderblocks at dumpster enclosures to be repaired. Lender PCA: Two of the refuse enclosures were observed w | 83000-3700 | PMC | Project | 18500 | 0 | 18500 |  | Not Started
Renaissance | 2025 | Parking Lot Concersion | Potential to convert unused parking lot, will evaluate further into hold | 83000-2200 | GC | Project | 30000 | 0 | 30000 |  | Not Started
Renaissance | 2025 | Sports Court | PNA: Complete resurface of sports court and new lines for basketball court. | 83000-6700 | PMC | Project | 98250 | 2510 | 95740 |  | In Progress
Renaissance | 2025 | Repair or replace damaged concrete treads at stairs. | Lender PCA: At the time of the assessment, a damaged concrete thread was observed at the stairs to the upper floor apart | 83000-7000 | PMC | Project | 500 | 0 | 500 |  | Not Started
Renaissance | 2025 | Repair exterior stair treads and stringers | PNA: Secure Stair Treads & Stringers | 83000-7100 | GC | Project | 12200 | 0 | 12200 |  | Not Started
Renaissance | 2025 | Repair exterior stair railings | PNA: Secure railings and paint all metal stair railings. Currently significantly chipped. | 83000-7100 | GC | Project | 37800 | 0 | 37800 |  | Not Started
Renaissance | 2025 | Moss Treatment | Moss treatment and pine needle cleaning | 83000-6100 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Renaissance | 2025 | Tile roofing | PNA: Clay tile roofing - inspect and minor repairs | 83000-6100 | GC | Project | 39860 | 0 | 39860 |  | Not Started
Renaissance | 2025 | Gutters & downspouts | PNA: Secure and clean downspouts. Confirm this includes gutters and repinning | 83000-6100 | GC | Project | 36200 | 0 | 36200 |  | Not Started
Renaissance | 2025 | Repair / replace cement fiber siding | PNA: Maintenance shed needs to new siding replacment and paint. | 83000-6500 | GC | Project | 18500 | 0 | 18500 |  | Not Started
Renaissance | 2025 | Exterior building painting | Including estimate from WDIR , to be in Yr 2 (Q4 of'27) | 83000-3400 | PMC | Project | 556000 | 0 | 556000 |  | Not Started
Renaissance | 2025 | Exterior repair for WDIR | Remediation of active termites | 80000-6800 | PMC | Project | 250000 | 0 | 250000 |  | Not Started
Renaissance | 2025 | Fire Stops | PNA: Fire stops | 80000-6400 | PMC | Project | 27244 | 9697 | 17547 |  | In Progress
Renaissance | 2025 | Security/ fire alarm systems | Lender PCA: At the time of the assessment, unit 143 was observed to have missing smoke detectors in the hallways and bed | 80000-1700 | PMC | Project | 100 | 0 | 100 |  | Not Started
Renaissance | 2025 | Common area light fixtures | PNA: Replace all pole lights, wall packs throughout property. | 83000-3200 | GC | Project | 44600 | 0 | 44600 |  | Not Started
Renaissance | 2025 | Replace breezeway lights | PNA: Replace all breezeway sconces to LED throughout property. | 83000-3200 | GC | Project | 27800 | 0 | 27800 |  | Not Started
Renaissance | 2025 | Contingency | Contingency Amount | 80000-7200 | GC | Contingency | 95494 | 0 | 95494 |  | Reserve
Renaissance | 2025 | Construction Management Fee | CM Fee | 80000-7200 | GC | CM Fee | 100269 | 0 | 100269 |  | Reserve
Rosemont | 2025 | Landscape Cleanup and Enhancements | Initial property landscape entry and tour path enhancements, etc | 84303 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Rosemont | 2025 | Storm sewer piping | Address 7 areas of water intrusion throughout property |  | GC | Project | 36000 | 36000 | 0 |  | Completed
Rosemont | 2025 | Asphalt Repairs | Mill, cement stabilize and overlay all drive aisles throughout property. Includes Equity PCR Item 3.3.2- Mill and overla | 84204 | GC | Project | 750000 | 750000 | 0 |  | Completed
Rosemont | 2025 | Stripe parking areas | Layout and stripe throughout property | 84201 | GC | Project | 30000 | 30000 | 0 |  | Completed
Rosemont | 2025 | ADA parking & curb cuts | ADA Parking & Curb Cuts | 84221 | GC | Project | 10000 | 10000 | 0 |  | Completed
Rosemont | 2025 | Sidewalks | Secure, scrape, sand & paint deck walkway from office area to sports complex. | 84115 | GC | Project | 9500 | 9500 | 0 |  | Completed
Rosemont | 2025 | Grind Sidewalk Trip Hazard | Lender PCR Item- Limited trip hazards were observed by Buildings 3825-A, 3777, and the Fitness Center Building. | 84115 | GC | Project | 2100 | 0 | 2100 |  | Not Started
Rosemont | 2025 | Fences & gates - site perimeter | Repair any damaged wooden fencing around property | 84205 | GC | Project | 40000 | 40000 | 0 |  | Completed
Rosemont | 2025 | Retaining walls | Replace missing or rotted timbers within existing retaining walls, replace some walls. Includes Lender PCR Item- Wood ti | 84434 | GC | Project | 80000 | 0 | 80000 |  | Not Started
Rosemont | 2025 | Landscaping | Tree trim clearance of all buildings. Includes Equity PCR Item 3.2.4- Many trees were overhanging buildings and depositi | 84303 | GC | Project | 60000 | 60000 | 0 |  | Completed
Rosemont | 2025 | Dumpster enclosures | Replace fencing around dumpster/compactor enclosures | 84111 | GC | Project | 18000 | 18000 | 0 |  | Completed
Rosemont | 2025 | Irrigation | Equity PCR Item 3.2.4- Although operation of the sprinkler system was not directly tested, property management reported | 84302 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Rosemont | 2025 | Re-apply Coating on Walkways & Breezeways | Budget for initial repairs and contingency for ongoing replacements | 84120 | GC | Project | 50000 | 50000 | 0 |  | Completed
Rosemont | 2025 | Repair exterior stair treads and stringers | Grind any rusted toe kick plates and red oxide prior to repaint. Replace damaged metal toe plates, as needed. Secure, a | 84114 | GC | Project | 100000 | 100000 | 0 |  | Completed
Rosemont | 2025 | Repair exterior stair railings | Secure and paint | 84121 | GC | Project | 110000 | 110000 | 0 |  | Completed
Rosemont | 2025 | Repair patio/balcony railings | Replace all bottom level patio fencing on each building | 84121 | GC | Project | 55000 | 55000 | 0 |  | Completed
Rosemont | 2025 | Asphalt composite shingle roofing | Roofs were replaced in 2019- Initial and ongoing repairs, and contingency for phased replacements in yrs 9-10 | 84433 | GC | Project | 50000 | 50000 | 0 |  | Completed
Rosemont | 2025 | Flashing | Roof Flashing | 84433 | GC | Project | 79200 | 79200 | 0 |  | Completed
Rosemont | 2025 | Underlayment | Roof Underlayment | 84433 | GC | Project | 88000 | 88000 | 0 |  | Completed
Rosemont | 2025 | Gutters & downspouts | Equity PCR Item 4.4.2- Gutters and downspouts should be installed at the roof eaves where not currently installed to hel | 84202 | GC | Project | 130000 | 130000 | 0 |  | Completed
Rosemont | 2025 | Repair / replace vinyl siding | Repair/replace damaged vinyl siding throughout property Includes Lender PCR Item- Dry rot was observed by the siding at | 84206 | GC | Project | 52000 | 52000 | 0 |  | Completed
Rosemont | 2025 | Exterior building | Paint all metal throughout property | 84101 | GC | Project | 90000 | 90000 | 0 |  | Completed
Rosemont | 2025 | Window Replacement and Repairs, including frames | Contingency for replacements and repairs | 84206 | GC | Project | 25000 | 25000 | 0 |  | Completed
Rosemont | 2025 | Metal Entry Door Replacement and Repairs | Contingency for replacements and repairs | 84215 | GC | Project | 50000 | 50000 | 0 |  | Completed
Rosemont | 2025 | Sliding Balcony Door Replacement and Repairs | Contingency for replacements and repairs | 84215 | GC | Project | 25000 | 25000 | 0 |  | Completed
Rosemont | 2025 | Co 2 detectors | Install Co2 detectors in every unit | 82131 | PMC | Project | 22000 | 0 | 22000 |  | Not Started
Rosemont | 2025 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84239 | PMC | Project | 52009 | 0 | 52009 |  | Not Started
Rosemont | 2025 | Signage - Building identification | Misc replacement signage | 84103 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Designer Fees | TBD scope | 84310 | PMC | Project | 2500 | 0 | 2500 |  | Not Started
Rosemont | 2025 | Clubhouse / Office Remodel | Not needed, misc allowance | 84208 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Clubhouse / Office Furniture | Not needed, misc allowance | 84306 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Fitness Center Remodel | Need to replace lights, repair damaged walls, paint, repair flooring that is lifting, repair men's bathroom items | 84190 | GC | Project | 25000 | 0 | 25000 |  | Not Started
Rosemont | 2025 | Fitness Equipment | Stair Stepper, other misc items | 84190 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Rosemont | 2025 | Leasing Pool Area Remodel | Replace wood/cable fence section in raised area with metal rail to match other fencing, other misc repairs | 84361 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Rosemont | 2025 | Leasing Pool Furniture | Supplement current furniture, add freestanding umbrellas, cornhole & ping pong, 2 cabanas, move some furniture to second | 84360 | PMC | Project | 45000 | 0 | 45000 |  | Not Started
Rosemont | 2025 | Secondary Pool Area Remodel | Need to fix cosmetic issues or possibly resurface | 84361 | GC | Project | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Secondary Pool Furniture | Misc items & move items from main pool | 84360 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Playground Remodel | Replace swing sets, border and mulch as well as replacing grills with new stand alone ones at secondary park area | 84195 | GC | Project | 13000 | 0 | 13000 |  | Not Started
Rosemont | 2025 | Playground Furniture | Picnic tables and misc items | 84340 | GC | Project | 8000 | 0 | 8000 |  | Not Started
Rosemont | 2025 | Picnic/Grill Area Remodel | Add 1-2 outdoor grill/kitchen areas at the property with gazebo | 84203 | GC | Project | 60000 | 0 | 60000 |  | Not Started
Rosemont | 2025 | Picnic/Grill Furniture | Furniture for new grill areas | 84340 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Rosemont | 2025 | Sports Court | Resurface, add 2 Pickleball nets. Keep running track, stripe for Pickleball courts Includes Equity PCR Item 3.2.9- The | 84390 | GC | Project | 35000 | 0 | 35000 |  | Not Started
Rosemont | 2025 | Sports Court- Soccer | Replace shade sails | 84390 | GC | Project | 8000 | 0 | 8000 |  | Not Started
Rosemont | 2025 | Unit Model Update | Change out carpet, misc supplemental furniture, remove screen door since it is broken and obscures visibility in the mod | 84280 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Rosemont | 2025 | Access Control System | Need to add access control for package lockers in fitness center | 84275 | PMC | Project | 3000 | 0 | 3000 |  | Not Started
Rosemont | 2025 | Mailboxes | Misc repairs | 84260 | PMC | Project | 2000 | 0 | 2000 |  | Not Started
Rosemont | 2025 | New access gate at back entrance | Look at adding gate ro restrict access to dumpster area and prevent dumping | 84275 | GC | Project | 50000 | 0 | 50000 |  | Not Started
Rosemont | 2025 | Security Camera System | Add cameras by mailboxes | 84450 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Carports | Look at adding carports for additional income | 84219 | GC | Project | 50000 | 0 | 50000 |  | Not Started
Rosemont | 2025 | Golf Cart | Need 1-2 leasing carts, have 2 maintenance carts | 83375 | PMC | Project | 16000 | 0 | 16000 |  | Not Started
Rosemont | 2025 | Unit water heaters | Equity PCR Item- 5.1- Observed water heaters were not provided with drain pans. Additionally, most water heaters observe | 84476 | GC | Project | 211000 | 0 | 211000 |  | Not Started
Rosemont | 2025 | Sanitary sewer Repairs | Contingency to remove roots and blockages at several locations, per the sewer scoping. See final report in diligence fo | 84385 | GC | Project | 50000 | 0 | 50000 |  | Not Started
Rosemont | 2025 | Install P trap on HVAC condensate piping | Equity PCR Item 5.3- The interior fan coil units (FCUs) observed at the residential units lacked p-traps at the condens | 84217 | GC | Project | 16880 | 16880 | 0 |  | Completed
Rosemont | 2025 | Insulate HVAC lines | Equity PCR Item 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | 84217 | GC | Project | 5375 | 0 | 5375 |  | Not Started
Rosemont | 2025 | HVAC inspection and maintenance | Clean debris/foliage from around condensors as well as leveling with condensor pads. Includes Equity PCR Item 5.2- Many | 84217 | PMC | Project | 8500 | 0 | 8500 |  | Not Started
Rosemont | 2025 | Inspect Fire Extinguishers | Lender PCR Item- Fire extinguishers are expired. | 84239 | PMC | Project | 2000 | 0 | 2000 |  | Not Started
Rosemont | 2025 | Fire Suppression System Inspection | Equity PCR Item 5.5.1- Annual Fire suppression system inspection for Building 3971-3975 | 84211 | PMC | Project | 1000 | 0 | 1000 |  | Not Started
Rosemont | 2025 | Fire Alarm System Inspection | Equity PCR Item 5.5.2- Annual fire alarm system inspection for Building 3971-3975. | 84211 | PMC | Project | 1000 | 0 | 1000 |  | Not Started
Rosemont | 2025 | Smoke Detectors | Equity PCR Item 5.5.2- Smoke detectors not observed in bedrooms, Install | 82131 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Rosemont | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 137853 | 0 | 137853 |  | Reserve
Rosemont | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 144746 | 0 | 144746 |  | Reserve
Swiss Gables | 2025 | Landscape Cleanup and Enhancements | Isolated locations of tree overgrowth at building elevations were observed. Tree trimming is recommended | 84303 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Swiss Gables | 2025 | Asphalt Coating | Crack fill alligatored asphalt Damaged pavement consisting of linear cracking and alligator cracking was observed east o | 84204 | GC | Project | 65000 | 19500 | 45500 |  | In Progress
Swiss Gables | 2025 | Stripe parking areas | Stripe parking lot and garages | 84204 | GC | Project | 36000 | 10800 | 25200 |  | In Progress
Swiss Gables | 2025 | Curbing Repairs | Damaged curbing was present southeast of Building C and at the east entrance to Building E. Repairs are recommended. | 84115 | GC | Project | 1500 | 2000 | -500 |  | Completed
Swiss Gables | 2025 | Sidewalks | Repair trip Hazards Damaged concrete sidewalk was present at the walkway south of Building G. Repairs are recommended. R | 84115 | GC | Project | 18000 | 10800 | 7200 |  | In Progress
Swiss Gables | 2025 | Fences & gates - site perimeter | Repair and paint fence | 84205 | GC | Project | 21000 | 10500 | 10500 |  | In Progress
Swiss Gables | 2025 | Install ADA Van-Accessible Space | The accessible parking spaces did not appear to be generally correctly configured. The installation of one van-accessibl | 83520 | PMC | Project | 400 | 3088 | -2688 |  | Completed
Swiss Gables | 2025 | Install ADA-Compliant Curb Cut Ramps | ADA-compliant curb cut ramps are not present on accessible route at the subject property. Inclusion of ADA-compliant cur | 83520 | PMC | Project | 1200 | 9265 | -8065 |  | Completed
Swiss Gables | 2025 | Install ADA-Compliant Handrailing at Ramp | The ramps within the accessible route do not appear to have ADA-compliant handrails. Reconfiguration of the handrails is | 83520 | PMC | Project | 1200 | 9265 | -8065 |  | Completed
Swiss Gables | 2025 | Install ADA-Compliant Door Hardware | The door at the designated accessible entrance does not appear to have ADA compliant hardware. Installation of ADA compl | 83520 | PMC | Project | 450 | 3474 | -3024 |  | Completed
Swiss Gables | 2025 | Playground equipment | Enhance playground equipment | 84340 | PMC | Project | 30000 | 0 | 30000 |  | Not Started
Swiss Gables | 2025 | Dumpster enclosures | Replace fencing on all dumpster enclosures Custom Pickets | 84111 | GC | Project | 15000 | 12000 | 3000 |  | In Progress
Swiss Gables | 2025 | Carports / Garages | Repair damaged sheet rock and paint 1st floor parking garages | 84219 | GC | Project | 66000 | 52800 | 13200 |  | In Progress
Swiss Gables | 2025 | Concrete deck / floor fill | Seal cracks in landings and cat walks | 84120 | GC | Project | 70000 | 56000 | 14000 |  | In Progress
Swiss Gables | 2025 | Repair exterior stair railings | Repair and secure stair railings | 84121 | GC | Project | 12000 | 9600 | 2400 |  | In Progress
Swiss Gables | 2025 | Repair balcony framing & decking | Repair damaged patio and Catwalk framing Balcony repair allowance Deteriorating wood was present at the underside of the | 84104 | GC | Project | 109000 | 81750 | 27250 |  | In Progress
Swiss Gables | 2025 | Repair patio/balcony railings | Secure all balcony and catwalk railings (custom pickets) | 84121 | GC | Project | 35000 | 28000 | 7000 |  | In Progress
Swiss Gables | 2025 | Asphalt composite shingle roofing | Roof tune up on 7 buildings | 84433 | GC | Project | 21000 | 21000 | 0 |  | Completed
Swiss Gables | 2025 | Gutters & downspouts | Clean and secure gutters and down spouts | 83439 | GC | Project | 14000 | 14000 | 0 |  | Completed
Swiss Gables | 2025 | Flashing | Replace damaged drip edge on cat walks | 84433 | GC | Project | 21000 | 16800 | 4200 |  | In Progress
Swiss Gables | 2025 | Sealants & caulking | Sealants & caulking | 84433 | GC | Project | 14000 | 14000 | 0 |  | Completed
Swiss Gables | 2025 | Repair / replace wood siding | Replace rotted T-111 siding Damaged soffits were observed along the elevated walkway at Building A, isolated areas at th | 84206 | GC | Project | 35000 | 28000 | 7000 |  | In Progress
Swiss Gables | 2025 | Exterior building Painting | Paint community including peal stop on all delaminated cedar Paint chipping was observed at the columns and posts of the | 84101 | GC | Project | 189000 | 151200 | 37800 |  | In Progress
Swiss Gables | 2025 | Repair / replace wood trim | Replace all rotted trim throughout property All Facia is Custom Scalloped Facia | 84105 | GC | Project | 45000 | 36000 | 9000 |  | In Progress
Swiss Gables | 2025 | Install CO Detectors | Carbon monoxide detectors are not provided in dwelling units, and wood burning fireplaces were provided in the third flo | 83236 | PMC | Project | 770 | 0 | 770 |  | Not Started
Swiss Gables | 2025 | Fire protection | Fire protection - Fire Stops | 84211 | PMC | Project | 10584 | 0 | 10584 |  | Not Started
Swiss Gables | 2025 | Signage - Entry Monument | Site Rebrand - New Monument Sign | 84290 | PMC | Project | 25000 | 0 | 25000 |  | Not Started
Swiss Gables | 2025 | Signage - Building identification | Site Rebrand - New Building Signage/New Door Numbers | 84103 | PMC | Project | 30000 | 0 | 30000 |  | Not Started
Swiss Gables | 2025 | Seal Penetrations in Fire Walls and Smoke Barriers | Penetrations in the fire and smoke barriers are in poor condition. Penetrations in the fire rated walls were observed as | 84211 | GC | Project | 70000 | 21000 | 49000 |  | In Progress
Swiss Gables | 2025 | General Fire Alarm Deficiencies | General fire alarm deficiencies were observed. The general deficiency noted is: expired smoke detectors throughout the b | 84211 | PMC | Project | 16100 | 8112 | 7988 |  | In Progress
Swiss Gables | 2025 | Sanitary Sewer Piping | Cleanout replacement; Hydrojet as needed | 84385 | PMC | Project | 24150 | 3967 | 20183 |  | In Progress
Swiss Gables | 2025 | Install Seismic Strapping | The water heater at the employee restroom in Building C lacked seismic bracing straps. Provision of adequate seismic bra | 84476 | PMC | Project | 250 | 0 | 250 |  | Not Started
Swiss Gables | 2025 | Electrical Distribution | Repair electric to pole lights and photo cells General electrical deficiencies were observed. The general deficiencies n | 84210 | GC | Project | 24400 | 19520 | 4880 |  | In Progress
Swiss Gables | 2025 | Common Area Light Fixtures | Replace parking garage and parking lot lights to LED | 84210 | GC | Project | 32000 | 25600 | 6400 |  | In Progress
Swiss Gables | 2025 | Organize Electrical Wiring | The surface raceway in Building-C, unit C303, requires repair to ensure the proper protection and organization of electr | 84210 | GC | Project | 5000 | 4000 | 1000 |  | In Progress
Swiss Gables | 2025 | Electrical Buzzing Sound | An electrical buzzing sound coming from the underground vault adjacent to the main roadside transformer indicates a pote | 84210 | GC | Project | 1000 | 0 | 1000 |  | Not Started
Swiss Gables | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 53250 | 0 | 53250 |  | Reserve
The Ardent | 2025 | Asphalt Coating | Crack fill, seal, and coat Damaged pavement consisting of pothole formation and alligator cracking was observed primaril | 84204 | GC | Project | 260000 | 78000 | 182000 |  | In Progress
The Ardent | 2025 | Seal & Stripe parking areas | Stripe Parking Lot | 84204 | GC | Project | 32000 | 9600 | 22400 |  | In Progress
The Ardent | 2025 | Curb cuts | Damaged concrete curbs were observed consisting of displacement and linear cracking were observed at the parking area pe | 83520 | GC | Project | 20000 | 6000 | 14000 |  | In Progress
The Ardent | 2025 | Sidewalks | Repair trip hazards Potential trip hazards consisting of damaged concrete and vertical and horizontal separation were pr | 84115 | GC | Project | 32000 | 9600 | 22400 |  | In Progress
The Ardent | 2025 | Landscaping | Trees were observed impeding on the building envelope at apartment buildings and also at the roofs of the carports. It i | 84303 | GC | Project | 80000 | 0 | 80000 |  | Not Started
The Ardent | 2025 | Resurface swimming pool | Resurface Swimming Pool | 84095 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
The Ardent | 2025 | Replace swimming pool coping | Replace Pool Coping | 84361 | GC | Project | 17500 | 5250 | 12250 |  | In Progress
The Ardent | 2025 | Swimming Pool 1 (Phase I: Leasing Office) | Repair cracked conrete & Update Pool Furniture | 84361 | GC | Project | 35000 | 10500 | 24500 |  | In Progress
The Ardent | 2025 | Swimming Pool 2 (Phase I: Tennis Court) | Repair cracked conrete & Update Pool Furniture (Removed) | 84361 | GC | Project | 35000 | 0 | 35000 |  | Not Started
The Ardent | 2025 | Swimming Pool 3 (Phase II) | Repair gate and paint fence Mark had $7.6K. Repair cracked concrete & Update Pool Furniture | 84361 | GC | Project | 35000 | 10500 | 24500 |  | In Progress
The Ardent | 2025 | Storm Sewer Piping | Clean Yard Basin | 84432 | GC | Project | 14000 | 4200 | 9800 |  | In Progress
The Ardent | 2025 | Playground equipment | Replace fall zone mulch | 84340 | GC | Project | 5400 | 1620 | 3780 |  | In Progress
The Ardent | 2025 | Carports | Replace rotted facia on carports Isolated posts show significant deterioration and should be replaced immediately. Recom | 84219 | GC | Project | 52000 | 15600 | 36400 |  | In Progress
The Ardent | 2025 | Dumpster enclosures | Replace fencing on all dumpster enclosures | 84111 | GC | Project | 27000 | 8100 | 18900 |  | In Progress
The Ardent | 2025 | Sport Court Renovation: Tennis | Repair chain link fence around tennis court. Turn into pickleball | 84390 | GC | Project | 50000 | 15000 | 35000 |  | In Progress
The Ardent | 2025 | Sport Court Renovation: Basketball | Restripe & Add New Hoop | 84390 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
The Ardent | 2025 | Pavement | R&R 6000 SF of Potholes and the worst alligatored pavement | 84204 | GC | Project | 60000 | 18000 | 42000 |  | In Progress
The Ardent | 2025 | Foundation - Seal pier and beam area | Replace damaged foundation vents | 84430 | GC | Project | 12000 | 3600 | 8400 |  | In Progress
The Ardent | 2025 | Concrete deck / floor fill | Seal cracks in landings | 84430 | GC | Project | 28000 | 8400 | 19600 |  | In Progress
The Ardent | 2025 | Stairs - Repair or replace damaged concrete treads at s | Replace sill plate supporting stair landing post outside of Unit 24 at Building 03C - Still plate has signficant rot | 84110 | GC | Project | 2000 | 600 | 1400 |  | In Progress
The Ardent | 2025 | Fire - Draft Stops | Allowance to seal small penetrations in attic draft stops - Small openings were observed within the demising draft stop | 84211 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
The Ardent | 2025 | Repair exterior stair treads and stringers | Repair stair tread and stringers | 84114 | GC | Project | 37000 | 11100 | 25900 |  | In Progress
The Ardent | 2025 | Repair exterior stair railings | Repair and secure stair railings | 84121 | GC | Project | 12000 | 3600 | 8400 |  | In Progress
The Ardent | 2025 | Repair balcony framing & decking | Repair damaged patio framing | 84104 | GC | Project | 45000 | 13500 | 31500 |  | In Progress
The Ardent | 2025 | Repair patio/balcony railings | Secure all balcony railings | 84121 | GC | Project | 16000 | 4800 | 11200 |  | In Progress
The Ardent | 2025 | Exterior Doors - replacement doors at patio and balcony | Patio & Balcony Storage Doors | 83426 | GC | Project | 12000 | 3600 | 8400 |  | In Progress
The Ardent | 2025 | Building Repairs & Exterior Walls | The exterior walls were observed with vegetative staining, peeling paint, and areas of damaged siding at the exterior wa | 84102 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
The Ardent | 2025 | Asphalt composite shingle roofing | Roof tune up on 37 buildings Isolated areas of damaged and lifted asphalt shingles were observed at Buildings B and S. | 84433 | GC | Project | 57000 | 17100 | 39900 |  | In Progress
The Ardent | 2025 | Gutters & downspouts | Clean and secure gutters and down spouts | 83439 | GC | Project | 37000 | 11100 | 25900 |  | In Progress
The Ardent | 2025 | Roofing - Flashing | Replace damaged drip edge on balconies | 84433 | GC | Project | 67400 | 20220 | 47180 |  | In Progress
The Ardent | 2025 | Roofing - Sealants & caulking | Roof Sealant & Caulking | 84433 | GC | Project | 49000 | 14700 | 34300 |  | In Progress
The Ardent | 2025 | Repair / replace wood siding | Replace rotted siding and scrape and paint Cedar siding Recommended to evaluate wall cavity conditions and prioritize bu | 84102 | GC | Project | 110000 | 33000 | 77000 |  | In Progress
The Ardent | 2025 | Masonry Repairs | Repair Exterior Masonry Walls | 84102 | GC | Project | 23500 | 7050 | 16450 |  | In Progress
The Ardent | 2025 | Dryer Vents | Dryer Vent Cleaning | 84106 | PMC | Project | 42750 | 16706 | 26044 |  | In Progress
The Ardent | 2025 | Breezeway soffit repairs | Add soffit vents at Phase 3 breezeways to improve attic ventilation and enhance moisture control; addresses incomplete v | 84113 | GC | Project | 10000 | 0 | 10000 |  | Not Started
The Ardent | 2025 | Exterior Painting | Paint community including peal stop on all delaminated cedar | 84101 | GC | Project | 916200 | 274860 | 641340 |  | In Progress
The Ardent | 2025 | Repair / replace wood trim | Replace all rotted trim throughout property | 84113 | GC | Project | 158000 | 47400 | 110600 |  | In Progress
The Ardent | 2025 | Water Heater Strapping | This item is for compliance with Section 507.2 of the Washington Plumbing Code. This item can be carried out as part of | 84209 | PMC | Project | 300 | 0 | 300 |  | Not Started
The Ardent | 2025 | Seismic Shutoff Valve | There is a natural gas line provided to Fitness Center B, and it is not provided with a seismic shutoff valve. Provide a | 84217 | PMC | Project | 1000 | 0 | 1000 |  | Not Started
The Ardent | 2025 | Fire Protection | Includes adding fire stops in all units | 84211 | PMC | Project | 42750 | 19836 | 22914 |  | In Progress
The Ardent | 2025 | Fitness Center Remodel (Gym 1 Phase II) | Turn yoga studio into pool lounge with Bay door | 84190 | GC | Project | 50000 | 15000 | 35000 |  | In Progress
The Ardent | 2025 | Fitness Center Remodel (Gym 2 Phase III) | Convert into golf simulator | 84190 | GC | Project | 25000 | 0 | 25000 |  | Not Started
The Ardent | 2025 | Dog Park | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola | 84130 | GC | Project | 16000 | 0 | 16000 |  | Not Started
The Ardent | 2025 | Electrical Distribution | Repair electric to pole lights and photo cells | 84210 | GC | Project | 32000 | 9600 | 22400 |  | In Progress
The Ardent | 2025 | Lighting - Common area light fixtures | Replace walkway pole lights - change to wall pack lights? ($5k) | 84210 | GC | Project | 48000 | 14400 | 33600 |  | In Progress
The Ardent | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 133740 | 0 | 133740 |  | Reserve
The Ardent | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 140427 | 0 | 140427 |  | Reserve
The Ardent | 2025 | 82260 - Exterior Lighting | Increase lighting across the property - Defer | 82260 | GC | Project | 25000 | 0 | 25000 |  | Not Started
The Fairways | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84300 | PMC | Project | 20000 | 27840 | -7840 |  | Completed
The Fairways | 2025 | Sanitary sewer piping | Add rocks around storm drains around property. Clean the area around the drain. | 84209 | GC | Project | 12000 | 12000 | 0 |  | Completed
The Fairways | 2025 | Storm sewer piping | Improve current french drain towards the back right of the property. | 84385 | GC | Project | 8500 | 8500 | 0 |  | Completed
The Fairways | 2025 | concrete pavement | Fill cracks and seal area next to dog park and sports court. | 84221 | GC | Project | 17500 | 17500 | 0 |  | Completed
The Fairways | 2025 | Asphalt Coating | Crack fill and double seal coat asphalt throughout property. Includes Lender PCR Item- Damaged pavement consisting of l | 84204 | GC | Project | 298500 | 298500 | 0 |  | Completed
The Fairways | 2025 | ADA parking & curb cuts | Include where needed in concrete/asphalt work | 84201 | GC | Project | 10000 | 10000 | 0 |  | Completed
The Fairways | 2025 | Sidewalks | Repair cracked/broken sidewalks throughout property. | 84221 | GC | Project | 22000 | 22000 | 0 |  | Completed
The Fairways | 2025 | Landscaping | Tree trim and clean up throughout property. 1st Call getting bid in conjunction with Paddocks to improve cost | 84300 | GC | Project | 92800 | 92800 | 0 |  | Completed
The Fairways | 2025 | Resurface swimming pool | Resurface pool | 84095 | GC | Project | 40000 | 32200 | 7800 |  | In Progress
The Fairways | 2025 | Replace swimming pool coping | Deck-O-Seal coping around pool. And relocate pots off the new deck to avoid further damage | 84361 | GC | Project | 4500 | 4500 | 0 |  | Completed
The Fairways | 2025 | Repair swimming pool deck | Clean pool deck, crack fill and seal. Repair the deck attached to pool deck and repaint/stain. Reinforce and lvel suppor | 84361 | GC | Project | 35000 | 35000 | 0 |  | Completed
The Fairways | 2025 | Dog Park | Replace chainlink fencing around dog park and replace with aluminum fencing. Add enzyme injector to irrigation valve | 84130 | GC | Project | 26000 | 7800 | 18200 |  | In Progress
The Fairways | 2025 | Dumpster enclosures | Repair any damage on dumpster enclosure. | 84111 | GC | Project | 2150 | 2150 | 0 |  | Completed
The Fairways | 2025 | Retaining walls | Retaining wall needs repair by sport court - replace with stone wall | 84434 | GC | Project | 2000 | 2000 | 0 |  | Completed
The Fairways | 2025 | Repair exterior stair treads and stringers | Secure. | 84114 | GC | Project | 7500 | 7500 | 0 |  | Completed
The Fairways | 2025 | Repair exterior stair railings | Secure. | 84121 | GC | Project | 7500 | 7500 | 0 |  | Completed
The Fairways | 2025 | Repair balcony framing & decking | Half the properties balconies are showing signs of weathering due to moisture/rot. Replace any rotted wood and scrap, sa | 84101 | GC | Project | 95000 | 95000 | 0 |  | Completed
The Fairways | 2025 | Asphalt composite shingle roofing | Replace flashing around all chimneys throughout property as well as a minor roof tune up to each building. Any significa | 84433 | GC | Project | 50000 | 50000 | 0 |  | Completed
The Fairways | 2025 | Repair / replace cement fiber siding | Repair/replace areas of failed hardie board and paint to match throughout property | 84206 | GC | Project | 41500 | 41500 | 0 |  | Completed
The Fairways | 2025 | Repair / replace wood trim | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. | 84113 | GC | Project | 38500 | 38500 | 0 |  | Completed
The Fairways | 2025 | Drier vents | Clean dryer vents throughout property. | 84106 | GC | Project | 18000 | 18000 | 0 |  | Completed
The Fairways | 2025 | CO detectors | Install CO detectors in each unit. Lender PCA Item- Due to the presence of gas-fire water heaters at each unit, carbon m | 82131 | PMC | Project | 16800 | 0 | 16800 |  | Not Started
The Fairways | 2025 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods TV to verify with Dan H on ordering | 84239 | PMC | Project | 11723 | 0 | 11723 |  | Not Started
The Fairways | 2025 | Clubhouse / Office Remodel | Paint cabinets in kitchen with hardware, add backsplash, replace appliances, replace "snack shack" window to be function | 84208 | GC | Project | 15000 | 15000 | 0 |  | Completed
The Fairways | 2025 | Clubhouse / Office Furniture | Looks good, misc supplemental items - Add a TV. TAM to order and install. Move the leasing desktop to back work area, pu | 82140 | PMC | Project | 10000 | 10439 | -439 |  | Completed
The Fairways | 2025 | Pool Area Remodel | Games and placeholder budget - TV contacting Key Designs | 84361 | PMC | Project | 15000 | 65776 | -50776 |  | Completed
The Fairways | 2025 | Pool Furniture | Maybe budget for full replacement. Tables and chairs look ok, 24 chaises are ok but a cheaper style. Budget for new, a f | 84360 | PMC | Project | 50000 | 75016 | -25016 |  | Completed
The Fairways | 2025 | Picnic/Grill Area Remodel | Look at adding grills and outdoor kitchen, gazebo, landscaping or turf in planters, replace/fix lights | 84203 | GC | Project | 30000 | 27000 | 3000 |  | In Progress
The Fairways | 2025 | Picnic/Grill Furniture | Tables ok, possibly add games | 84195 | PMC | Project | 10000 | 24300 | -14300 |  | Completed
The Fairways | 2025 | Sports Courts | Resurface and add 2 pickleball courts along with tennis | 84390 | GC | Project | 25000 | 25000 | 0 |  | Completed
The Fairways | 2025 | Dog Park | Looks good, misc budget - add enzyme injector | 84130 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
The Fairways | 2025 | Access Control System | Need for pool area and bathroom doors - just updating to keypad. Review for future FOB system for afterhours access on a | 84275 | PMC | Project | 6000 | 0 | 6000 |  | Not Started
The Fairways | 2025 | Storage Shed | Look at adding storage shed for appliances next to maintenance - enclose area to left of maintenance shop | 84206 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
The Fairways | 2025 | HVAC inspection and maintenance | Clean foliage around condensors throughout property. Raise units with HVAC pad as needed. | 84218 | GC | Project | 24000 | 24000 | 0 |  | Completed
The Fairways | 2025 | Electrical distribution | Electrical Distribution | 84210 | GC | Project | 22000 | 22000 | 0 |  | Completed
The Fairways | 2025 | Replace breezeway lights | Breezeway Lighting | 84210 | GC | Project | 37500 | 37500 | 0 |  | Completed
The Fairways | 2025 | Pool area lighting | Lights are all 110 and need to be rewired | 84361 | GC | Project | 5000 | 5000 | 0 |  | Completed
The Fairways | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 178027 | 0 | 178027 |  | Reserve
The Fairways | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 66000 | 0 | 66000 |  | Reserve
The Lakes | 2025 | Landscape Cleanup and Enhancements | Lakes - Landscape Enhancements Revive - Landscape Enhancements | 84303 | PMC | Project | 40000 | 0 | 40000 |  | Not Started
The Lakes | 2025 | Asphalt Coating | Lakes - Crack fill, seal and coating Revive - Crack fill, seal and coating | 84204 | GC | Project | 455000 | 136500 | 318500 |  | In Progress
The Lakes | 2025 | Fencing | Take down the chain-link fence separating properties. Add two paths for golf cart to travel between. Add walking path - | 84205 | GC | Project | 50000 | 15000 | 35000 |  | In Progress
The Lakes | 2025 | Stripe Parking Areas | Lakes - Stripe Parking Lot Revive - Stripe Parking Lot | 84201 | GC | Project | 28000 | 8400 | 19600 |  | In Progress
The Lakes | 2025 | ADA Parking & Curb Cuts | Lakes - Concrete Modifications Revive - Concrete Modifications | 83520 | GC | Project | 26000 | 7800 | 18200 |  | In Progress
The Lakes | 2025 | Sidewalks Trip Hazard | Lakes - Repair trip hazards Revive - Repair trip hazards. A limited sidewalk crack was also observed by Building 2335. | 84115 | GC | Project | 29000 | 8700 | 20300 |  | In Progress
The Lakes | 2025 | Storm Sewer Piping | Lakes - Clean Yard Basins of Debris Revive - Clean Yard Basins of Debris | 84432 | GC | Project | 23000 | 6900 | 16100 |  | In Progress
The Lakes | 2025 | Fences & Gates - Site Perimeter | Revive - Add ~200ft wall between Revive and comp with razor wire | 84205 | GC | Project | 15000 | 4500 | 10500 |  | In Progress
The Lakes | 2025 | Pavement | Lakes - R&R 2000 Sf of Potholes Revive - R&R 1500 sq ft pavement | 84204 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
The Lakes | 2025 | Landscaping | Lakes - Tree trim and raise canopy | 84303 | GC | Project | 64000 | 19200 | 44800 |  | In Progress
The Lakes | 2025 | ADA Modifications | Revive - Common area restroom sink is not insulated at clubhouse. LRR- ADA sink insulation | 83520 | PMC | Project | 350 | 0 | 350 |  | Not Started
The Lakes | 2025 | Fences & Gates - Swimming Pool | Lakes - Repair gate and paint fence Revive - Repair gate and paint fence | 84205 | GC | Project | 16200 | 4860 | 11340 |  | In Progress
The Lakes | 2025 | Pool Area | Lakes - Enhance pool area with turf and a fireplace | 84361 | GC | Project | 20000 | 6000 | 14000 |  | In Progress
The Lakes | 2025 | Dumpster Enclosures | Lakes - Replace fencing on all dumpster enclosures Revive - Replace fencing on all dumpster enclosures | 84111 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
The Lakes | 2025 | Concrete Deck / Floor Fill | Lakes - Seal cracks in landings Revive - Seal cracks in landings | 84430 | GC | Project | 41000 | 12300 | 28700 |  | In Progress
The Lakes | 2025 | Roof Deck | Revive - Roof Deck Repairs | 84433 | GC | Project | 13000 | 13000 | 0 |  | Completed
The Lakes | 2025 | Repair Exterior Stair Treads and Stringers | Lakes - Repair stair tread and stringers Revive - Repair stair tread and stringers | 84114 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
The Lakes | 2025 | Repair Exterior Stair Railings | Lakes - Repair and secure stair railings Revive - Repair and secure stair railings | 84121 | GC | Project | 24000 | 7200 | 16800 |  | In Progress
The Lakes | 2025 | Repair Balcony Framing & Decking | Lakes - Repair damaged patio framing Revive - Repair damaged patio framing | 84104 | GC | Project | 22000 | 6600 | 15400 |  | In Progress
The Lakes | 2025 | Repair Patio/Balcony Railings | Lakes - Secure all balcony railings Revive - Secure all balcony railings | 84121 | GC | Project | 22000 | 6600 | 15400 |  | In Progress
The Lakes | 2025 | Asphalt Composite Shingle Roofing | Lakes - Roof tune up on buildings 9 Revive - Replace Roofs | 84433 | GC | Project | 428000 | 428000 | 0 |  | Completed
The Lakes | 2025 | Gutters & Downspouts | Lakes - Clean and secure gutters and down spouts Revive - Clean and secure gutters and down spouts | 84202.0 | GC | Project | 22000 | 22000 | 0 |  | Completed
The Lakes | 2025 | Flashing | Lakes - Replace damaged drip edge on balconies. Revive - Replace damaged drip edge on balconies. LRR - Damaged balconi | 84433 | GC | Project | 22800 | 6840 | 15960 |  | In Progress
The Lakes | 2025 | Sealants & Caulking | Lakes - Roof Sealants & Caulking Revive - Roof Sealants & Caulking | 84102 | GC | Project | 22000 | 22000 | 0 |  | Completed
The Lakes | 2025 | Repair / Replace Wood Siding | Lakes - Replace rotted siding and scrape and paint Cedar siding Revive - Replace rotted siding and scrape and paint Ceda | 84102 | GC | Project | 40000 | 12000 | 28000 |  | In Progress
The Lakes | 2025 | Exterior Building Paint | Lakes - Paint community Revive - Paint community | 84101 | GC | Project | 348000 | 104400 | 243600 |  | In Progress
The Lakes | 2025 | Repair / Replace Wood Trim | Lakes - Replace all rotted trim throughout property Revive - Replace all rotted trim throughout property | 84113 | GC | Project | 40000 | 12000 | 28000 |  | In Progress
The Lakes | 2025 | Repair Microbial Growth | LRR - Limited areas of microbial growth was observed in the bedroom corner and closet wall of Unit 2347-1. Affected non- | 82460 | PMC | Project | 900 | 0 | 900 |  | Not Started
The Lakes | 2025 | Fire Stops | Add Fire Stops | 84211 | PMC | Project | 24696 | 18931 | 5765 |  | In Progress
The Lakes | 2025 | Leasing Golf Cart | Get Leasing Golf Cart | 83375 | PMC | Project | 15000 | 32400 | -17400 |  | Completed
The Lakes | 2025 | Fitness Center Remodel | Revive - Convert Leasing office into a Gym | 84190 | GC | Project | 100000 | 30000 | 70000 |  | In Progress
The Lakes | 2025 | Cyber Café upgrade at Lakes | Lakes - Open up the side wall and expand the leasing area | 84208 | GC | Project | 30000 | 9000 | 21000 |  | In Progress
The Lakes | 2025 | Security Camera System | Install new Security Cameras | 84450 | PMC | Project | 35000 | 0 | 35000 |  | Not Started
The Lakes | 2025 | Sanitary Sewer Piping | Lakes - Building C - Minor tree root intrusion. Recommended remediation: Dig approximately 4 feet and replace the affect | 84385 | PMC | Project | 6600 | 0 | 6600 |  | Not Started
The Lakes | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 104927 | 0 | 104927 |  | Reserve
The Lakes | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 119624 | 0 | 119624 |  | Reserve
The Vibe | 2025 | Landscape Cleanup and Enhancements | HPCA - Tree trimming/removal overhanging structures | 84300 | PMC | Project | 7500 | 4077 | 3423 |  | In Progress
The Vibe | 2025 | Asphalt Coating | PNA - contingent amount to work on parking lot as needed. LPCA - Linear/alligator cracking and pothole formation was obs | 84204 | GC | Project | 68000 | 40800 | 27200 |  | In Progress
The Vibe | 2025 | Stripe parking areas | PNA - stripe parking lot | 84090 | GC | Project | 32000 | 9600 | 22400 |  | In Progress
The Vibe | 2025 | Parking equipment | HPCA - Add ADA van stall at Carport | 84085 | GC | Project | 500 | 150 | 350 |  | In Progress
The Vibe | 2025 | ADA parking & curb cuts | Concrete Modifications | 84090 | GC | Project | 2250 | 675 | 1575 |  | In Progress
The Vibe | 2025 | Sidewalks | PNA - Repair trip hazards HPCA - Concrete Walks/Steps - Trip Hazards/ADA | 84080 | GC | Project | 18000 | 5400 | 12600 |  | In Progress
The Vibe | 2025 | Storm sewer piping | PNA - Clean yard basins of debree | 84470 | GC | Project | 12000 | 9600 | 2400 |  | In Progress
The Vibe | 2025 | Fences & gates - site perimeter | PNA - Pool fence is vinyl and post holding up the fence are rotting. Repair posts and repair fence | 84205 | GC | Project | 24000 | 19200 | 4800 |  | In Progress
The Vibe | 2025 | Move topsoil/mulch away from bldg. siding | HPCA - Backfill exposed/undercut concrete steps and foundations | 84080 | GC | Project | 7500 | 6000 | 1500 |  | In Progress
The Vibe | 2025 | Resurface swimming pool | PNA - contingent amount to work on pool resurface | 84095 | GC | Project | 70000 | 21000 | 49000 |  | In Progress
The Vibe | 2025 | Pool Lift | HPCA - Add ADA lift to 1 pool | 84095 | GC | Project | 9500 | 2850 | 6650 |  | In Progress
The Vibe | 2025 | Pool Pumps | HPCA - Install variable speed pool pumps with VFD control | 84095 | GC | Project | 8659 | 2598 | 6061 |  | In Progress
The Vibe | 2025 | Replace swimming pool deck | PNA - address existing cracking on pool decks and cosmetic enhacement | 84095 | GC | Project | 40000 | 12000 | 28000 |  | In Progress
The Vibe | 2025 | Playground area | HPCA - Add ADA path of travel to playground | 84122 | GC | Project | 3500 | 1050 | 2450 |  | In Progress
The Vibe | 2025 | Dumpster enclosures | PNA - Replace fencing on all dumpster enclosures | 84125 | GC | Project | 12000 | 12000 | 0 |  | Completed
The Vibe | 2025 | Carports / Garages | PNA - Replace rotted facia on carports | 84085 | GC | Project | 17000 | 17000 | 0 |  | Completed
The Vibe | 2025 | Drainage correction | HPCA - Drainage corrections at carports | 84432 | GC | Project | 5000 | 5000 | 0 |  | Completed
The Vibe | 2025 | Concrete deck / floor fill | PNA - seal cracks in landings | 84102 | GC | Project | 26000 | 18200 | 7800 |  | In Progress
The Vibe | 2025 | Unit Deck Resurfacing | HPCA - Bldg. M Unit 302 Deck resurfacing. Exposed painted plywood at unit deck surface | 84105 | GC | Project | 1200 | 360 | 840 |  | In Progress
The Vibe | 2025 | Repair exterior stair treads and stringers | PNA - repair stair tread and stringers | 84114 | GC | Project | 16000 | 16000 | 0 |  | Completed
The Vibe | 2025 | Repair exterior stair railings | PNA - repair and secure stair railings | 84205 | GC | Project | 12000 | 12000 | 0 |  | Completed
The Vibe | 2025 | Repair balcony framing & decking | PNA - repair damaged patio framing | 84104 | GC | Project | 18000 | 18000 | 0 |  | Completed
The Vibe | 2025 | Repair patio/balcony railings | PNA - secure all balcony railings | 84205 | GC | Project | 16000 | 16000 | 0 |  | Completed
The Vibe | 2025 | Asphalt composite shingle roofing | PNA - Roof tune up on 37 buildings | 84050 | GC | Project | 40000 | 40000 | 0 |  | Completed
The Vibe | 2025 | Gutters & downspouts | PNA - Clean and secure gutters and down spouts HPCA - Repair selective areas of damaged gutter; reconnect Downspouts to | 84050 | GC | Project | 32000 | 32000 | 0 |  | Completed
The Vibe | 2025 | Flashing | PNA - Replace damaged drip edge on balconies | 84050 | GC | Project | 12000 | 12000 | 0 |  | Completed
The Vibe | 2025 | Sealants & caulking | Roof Sealant & Caulking | 84050 | GC | Project | 26000 | 26000 | 0 |  | Completed
The Vibe | 2025 | Repair / replace wood siding | PNA - Replace rotted siding and scrape and paint Cedar siding | 84105 | GC | Project | 18000 | 18000 | 0 |  | Completed
The Vibe | 2025 | Repair stucco | Exterior Stucco Repair | 84105 | GC | Project | 5000 | 5000 | 0 |  | Completed
The Vibe | 2025 | Exterior building | PNA - Paint community including peal stop on all delaminated cedar LPCA - Faded paint finishes were observed at several | 84101 | GC | Project | 592200 | 532980 | 59220 |  | In Progress
The Vibe | 2025 | Repair / replace wood trim | PNA - Replace all rotted trim throughout property | 84105 | GC | Project | 35000 | 35000 | 0 |  | Completed
The Vibe | 2025 | Fire Protection | Fire Stops | 84239 | PMC | Project | 24675 | 2798 | 21877 |  | In Progress
The Vibe | 2025 | Unit Water Leak Repairs | HPCA - Unit P104 Bathroom Water Leak Repairs | 84470 | PMC | Project | 3000 | 0 | 3000 |  | Not Started
The Vibe | 2025 | Bathroom cleaning/klitz/painting with organic growth | HPCA - Excessive damage repair and repainting | 84304 | PMC | Project | 12000 | 0 | 12000 |  | Not Started
The Vibe | 2025 | Security Camera System | Adding 9 security cameras (inc. installation, labor, etc.) | 84450 | PMC | Project | 37000 | 0 | 37000 |  | Not Started
The Vibe | 2025 | Water Distribution and Domestic Hot Water | Discuss with maintenace manager | 84470 | PMC | Project | 2250 | 0 | 2250 |  | Not Started
The Vibe | 2025 | Inspect defective heaters | HPCA - Review Cadet Heaters and replace any Models installed between 1982 through 1999 Modles: FW, FX, LX, TK, ZA, Z, RA | 84218 | GC | Project | 5250 | 5250 | 0 |  | Completed
The Vibe | 2025 | Inspect defective ITE electrical panels | HPCA - Given the Bldg.'s were constructed between 1985 and 1986 there is the potential some of the Unit ITE Electrical P | 84210 | GC | Project | 5250 | 5250 | 0 |  | Completed
The Vibe | 2025 | Replace recalled heaters | HPCA - Replace 16 Recalled Heaters (Estimated Potential Recalled Heaters) | 842220 | GC | Project | 3200 | 960 | 2240 |  | In Progress
The Vibe | 2025 | Replace electrical panels | HPCA - Replace 8 Electrical Panels (Estimated Potential Recalled Heaters) | 84210 | GC | Project | 36000 | 10800 | 25200 |  | In Progress
The Vibe | 2025 | Electrical distribution | PNA - Repair electric to pole lights and photo cells | 84210 | GC | Project | 12000 | 12000 | 0 |  | Completed
The Vibe | 2025 | Common area light fixtures | PNA - Replace pole lights around pool | 84210 | GC | Project | 7500 | 7500 | 0 |  | Completed
The Vibe | 2025 | Outlets & Dryer Vents | Contingent as needed | 84210 | PMC | Project | 2000 | 5003 | -3003 |  | Completed
The Vibe | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 229733 | 0 | 229733 |  | Reserve
The Vibe | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 78333 | 0 | 78333 |  | Reserve
Valera Riverside | 2025 | Repair / replace swimming pool pumps | seal small cracks on pool deck | 84361.0 | GC | Project | 6500 | 0 | 6500 |  | Not Started
Valera Riverside | 2025 | Retaining walls | Paint mural on retaining wall outside pool | 84434.0 | PMC | Project | 25000 | 0 | 25000 |  | Not Started
Valera Riverside | 2025 | Pergola | repair and stain bar and deck | 84195.0 | GC | Project | 9500 | 0 | 9500 |  | Not Started
Valera Riverside | 2025 | Outdoor Kitchen | replace broken gas valve | 84203.0 | GC | Project | 3000 | 0 | 3000 |  | Not Started
Valera Riverside | 2025 | Fire Stops | Fire stops | 84239.0 | PMC | Project | 25480 | 3345 | 22135 |  | In Progress
Valera Riverside | 2025 | Signage - Building identification | *Per Kevin for Signage Change/Rebrand | 84103.0 | PMC | Project | 50000 | 3833 | 46167 |  | In Progress
Valera Riverside | 2025 | Fitness Center Remodel | additional equipment | 84190.0 | PMC | Project | 20000 | 1814 | 18186 |  | In Progress
Valera Riverside | 2025 | Security/ fire alarm systems | Yellow, Non-Compliance tags were observed affixed to the sprinkler risers, dated May 2025. | 84211.0 | PMC | Project | 5000 | 8924 | -3924 |  | Completed
Valera Riverside | 2025 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 7224 | 0 | 7224 |  | Reserve
Valera Riverside | 2025 | Construction Management Fee | CM Fees | 84505.0 | GC | CM Fee | 7585 | 0 | 7585 |  | Reserve
Windward | 2025 | Landscape Cleanup and Enhancements | Tree trimming (Added in after PNA/Site Visit) | 84303 | PMC | Project | 50000 | 19200 | 30800 |  | In Progress
Windward | 2025 | Asphalt Coating | PNA: Seal Coat and Crack Fill (Decreased by $127380 and moved BTL in Yr 5) | 84204 | GC | Project | 144000 | 43200 | 100800 |  | In Progress
Windward | 2025 | Stripe parking areas | Stripe Parking Lot Decreased $34,115 and moved BTL in Yr 9 | 84201 | GC | Project | 28000 | 8400 | 19600 |  | In Progress
Windward | 2025 | Pavement Repairs | PNA: Repair potholes Lender PCA/Equity PCA: Damaged pavement consisting of linear cracking and alligator cracking, was o | 84204 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
Windward | 2025 | ADA parking & curb cuts | Equity PCA: No van-accessible parking space was present at the leasing office. Installation of one van-accessible space | 83520 | PMC | Project | 1000 | 0 | 1000 |  | Not Started
Windward | 2025 | Exterior Stairs - Repair exterior stair railings | Post: Adding in painting of exterior railings | 84121 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Windward | 2025 | Asphalt composite shingle roofing | PNA: Standard roof tune up on ridge, vallt and pipe jacks; Equity PCA: Roof replacement - asphalt shingles (Yr 10) (Decr | 84433 | GC | Project | 22000 | 6600 | 15400 |  | In Progress
Windward | 2025 | Gutters & downspouts | PNA: Clean and repitch gutters throughout property | 84202.0 | GC | Project | 16000 | 4800 | 11200 |  | In Progress
Windward | 2025 | Exterior building | Capitalized year 5 work: exterior painting, repairing stucco, replacing wood trim, replacing siding (Decreased by $38,01 | 84206 | PMC | Project | 359000 | 371 | 358629 |  | In Progress
Windward | 2025 | Appliances Package | Cost Reallocation from BTL Yr1: Adjusted amount to reflect appliance actuals on Cortland's past BTL | 84431.0 | PMC | Project | 29680 | 0 | 29680 |  | Not Started
Windward | 2025 | Flooring | Cost Reallocation from BTL Yr1: Adjusted amount to reflect replacing one unit's floors per month ($3k per turn) | 84431.0 | PMC | Project | 36000 | 0 | 36000 |  | Not Started
Windward | 2025 | Clean Dryer vents | Clean vents and replace missing covers (Added in after PNA/Site Visit) | 84106 | GC | Project | 16170 | 4851 | 11319 |  | In Progress
Windward | 2025 | Water Heaters | Cost Reallocation from BTL Yr1: Adjusted amount to reflect water heater actuals on Cortland's past BTL | 84476.0 | PMC | Project | 16000 | 0 | 16000 |  | Not Started
Windward | 2025 | HVAC inspection and maintenance | Cost Reallocation from BTL Yr1: Adjusted amount to reflect HVAC actuals on Cortland's past BTL | 84218.0 | PMC | Project | 16000 | 9522 | 6478 |  | In Progress
Windward | 2025 | Doors | Cost Reallocation from BTL Yr1: replace sliding doors at turnover (40% in Yr 1, 30% in Yr 2, 20% in Yr 3, and 10% in Yr | 84304.0 | PMC | Project | 180000 | 1022 | 178978 |  | In Progress
Windward | 2025 | Fire Stops | PNA: Fire stops | 84211 | PMC | Project | 28812 | 24990 | 3822 |  | In Progress
Windward | 2025 | Carbon Monoxide/Smoke Detectors | Lender PCA: Two smoke-only detectors were observed in Units 16014 and 2004. This appeared to be a rare exception, and th | 83236 | PMC | Project | 450 | 0 | 450 |  | Not Started
Windward | 2025 | Signage - Site | Post: Adding in signage to account for switching from Cortland signage | 84103 | PMC | Project | 50000 | 1032 | 48968 |  | In Progress
Windward | 2025 | Security Camera System | Vistria: address adding security cameras to mailbox area | 84450 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Windward | 2025 | Golf Cart | Post: Adding in new leasing golf cart | 83375 | PMC | Project | 15000 | 5814 | 9186 |  | In Progress
Windward | 2025 | Replace AC condenser | PNA: Add insulation to Condensing unit lines | 84218.0 | GC | Project | 26000 | 7800 | 18200 |  | In Progress
Windward | 2025 | Electrical Panel Disconnects & Meter Banks | Vistria: raise electrical panel replacements up front @ $2,300 a unit | 84330 | GC | Project | 676200 | 202860 | 473340 |  | In Progress
Windward | 2025 | Common area light fixtures | Vistria: address adding exterior lighting around mailbox area (includes other lighting enhancements) | 84210 | GC | Project | 35000 | 10500 | 24500 |  | In Progress
Windward | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 89516 | 0 | 89516 |  | Reserve
Windward | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 93991 | 0 | 93991 |  | Reserve
Almaden 1930 | 2026 | Landscape Cleanup and Enhancements | Post: General curb appeal enhancement | 51045-00 | GC | Project | 35000 | 96250 | -61250 |  | Completed
Almaden 1930 | 2026 | Asphalt Coating | PNA: Repair asphalt, seal coat, and stripe. Lender PCA: The asphalt pavement has localized alligator cracking, and gener | 51051-00 | GC | Project | 32970 | 700 | 32270 |  | In Progress
Almaden 1930 | 2026 | Repair / replace swimming pool pumps | PNA: Anti entrapment devices | 51025-00 | GC | Project | 7140 | 63158 | -56018 |  | Completed
Almaden 1930 | 2026 | Fences & gates - swimming pool | PNA: Repair and paint pool fence | 51025-00 | GC | Project | 22050 | 0 | 22050 |  | Not Started
Almaden 1930 | 2026 | Carports / Garages | PNA: Repair car ports and paint posts and pearling | 51172-00 | GC | Project | 13650 | 0 | 13650 |  | Not Started
Almaden 1930 | 2026 | ADA parking & curb cuts | Lender PCA: One van accessible space should be added at the leasing office. The restroom at the leasing office has acces | 51091-00 | GC | Project | 2000 | 0 | 2000 |  | Not Started
Almaden 1930 | 2026 | Sidewalks | Lender PCA: A cracked walkway was observed. Immediate repairs are recommended to repair the walkway. | 51091-00 | GC | Project | 500 | 0 | 500 |  | Not Started
Almaden 1930 | 2026 | Landscape irrigation | PNA: Inspect and repair irrigation | 51045-00 | GC | Project | 29400 | 0 | 29400 |  | Not Started
Almaden 1930 | 2026 | Fences & gates - site perimeter | PNA: Overlay wood fence on back of community. Lender PCA: Some of the chain link has been bowed slightly where cars have | 51077-00 | GC | Project | 19950 | 0 | 19950 |  | Not Started
Almaden 1930 | 2026 | Retaining walls | PNA: Rebuild one section of retaining wall | 51085-00 | GC | Project | 16800 | 0 | 16800 |  | Not Started
Almaden 1930 | 2026 | Landscaping | PNA: Remove dead tree branches and trim trees. EPCA: Trees were observed impeding on the building rooftops and facades o | 51043-00 | GC | Project | 91350 | 0 | 91350 |  | Not Started
Almaden 1930 | 2026 | Resurface swimming pool | PNA: Repair to pool shell and resurface pool | 51025-00 | GC | Project | 68250 | 0 | 68250 |  | Not Started
Almaden 1930 | 2026 | Replace swimming pool coping | PNA: Replace decko seal | 51025-00 | GC | Project | 9975 | 0 | 9975 |  | Not Started
Almaden 1930 | 2026 | Replace swimming pool deck | PNA: Pressure wash and seal brick pool deck | 51025-00 | GC | Project | 18900 | 0 | 18900 |  | Not Started
Almaden 1930 | 2026 | Storm sewer piping | PNA: Clean storm drains. EPCA: Debris was observed clogging storm drains. Clearing the debris is recommended | 51130-00 | GC | Project | 18900 | 0 | 18900 |  | Not Started
Almaden 1930 | 2026 | Termite Remediation | EPCA: Partner engaged Terminix for a termite and fungus/dryrot inspection at the subject property. Based on their findin | 51992-00 | GC | Project | 35000 | 17500 | 17500 |  | In Progress
Almaden 1930 | 2026 | Water distribution piping | PNA: Install sewer covers | 51134-00 | GC | Project | 10500 | 14700 | -4200 |  | Completed
Almaden 1930 | 2026 | Concrete deck / floor fill | PNA: Rebuild 20% of balconies | 51072-00 | GC | Project | 124488 | 0 | 124488 |  | Not Started
Almaden 1930 | 2026 | Wall framing | PNA: Replace damaged framing in gable ends | 51070-00 | GC | Project | 14700 | 0 | 14700 |  | Not Started
Almaden 1930 | 2026 | Balcony inspection | Lender PCA: Based on exterior appurtenances, this Property is subject to the State of California Law. According to a rec | 51072-00 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Almaden 1930 | 2026 | Repair exterior stair treads and stringers | PNA: Repair stair treads and stringers | 51093-00 | GC | Project | 9975 | 0 | 9975 |  | Not Started
Almaden 1930 | 2026 | Repair exterior stair railings | PNA: Secure railings | 51077-00 | GC | Project | 10500 | 0 | 10500 |  | Not Started
Almaden 1930 | 2026 | Repair balcony framing & decking | PNA: Add joist hangers to balcony joists | 51072-00 | GC | Project | 30450 | 5000 | 25450 |  | In Progress
Almaden 1930 | 2026 | Repair balcony railings | PNA: Secure railings | 51077-00 | GC | Project | 9975 | 0 | 9975 |  | Not Started
Almaden 1930 | 2026 | Asphalt composite shingle roofing | PNA: Roof tune up and Roof replacements (Yr. 8): | 51061-00 | GC | Project | 40950 | 29675 | 11275 |  | In Progress
Almaden 1930 | 2026 | Gutters & downspouts | PNA: Secure and clean gutters. Lender PCA: Ac cracked concrete gutter was observed at the driveway entrance to the prope | 51071-00 | GC | Project | 10551 | 0 | 10551 |  | Not Started
Almaden 1930 | 2026 | Sealants & caulking | PNA: Seal between T-111 siding | 51062-00 | GC | Project | 37800 | 0 | 37800 |  | Not Started
Almaden 1930 | 2026 | Flashing | PNA: Add z flash to replacement siding | 51062-00 | GC | Project | 29400 | 0 | 29400 |  | Not Started
Almaden 1930 | 2026 | Repair / replace wood siding | PNA: Replace rotted siding. EPCA: Partner observed deteriorated siding located below and near dryer vents at the communa | 51070-00 | GC | Project | 69250 | 0 | 69250 |  | Not Started
Almaden 1930 | 2026 | Repair / replace wood trim | PNA: Replace rotted fascia and trim | 51070-00 | GC | Project | 58800 | 0 | 58800 |  | Not Started
Almaden 1930 | 2026 | Paint community | PNA: Paint community - LRR | 51080-00 | GC | Project | 239400 | 0 | 239400 |  | Not Started
Almaden 1930 | 2026 | Designer Fees | Post: Leasing office refresh | 51200-00 | GC | Project | 32500 | 16250 | 16250 |  | In Progress
Almaden 1930 | 2026 | Pool Furniture | Post: Pool furniture replacement | 51011-00 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Almaden 1930 | 2026 | Smoke/fire detection | Lender PCA: Smoke detectors were generally present where required, however several units were observed where the tenant | 51990-00 | GC | Project | 1000 | 1000 | 0 |  | Completed
Almaden 1930 | 2026 | Sanitary Sewer Piping | Jet main drain lines per scope | 51131-00 | GC | Project | 28896 | 11000 | 17896 |  | In Progress
Almaden 1930 | 2026 | Electrical Panel Disconnects & Meter Banks | Lender PCA: At unit electric panels, some panels did not have the breakers labeled. Immediate repairs are recommended fo | 51140-00 | PMC | Project | 150000 | 0 | 150000 |  | Not Started
Almaden 1930 | 2026 | Electrical IR Inspection | EPCA: Based on the age of the property and some of the electrical equipment, an IR survey is recommended. | 51140-00 | GC | Project | 6130 | 0 | 6130 |  | Not Started
Almaden 1930 | 2026 | Electrical distribution | PNA: Inspect and repair lighting controllers on all buildings | 51140-00 | GC | Project | 18900 | 0 | 18900 |  | Not Started
Almaden 1930 | 2026 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 87089 | 0 | 87089 |  | Reserve
Almaden 1930 | 2026 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 73654 | 0 | 73654 |  | Reserve
Ardmore Springs | 2026 | Asphalt Coating | PNA: Repair potholes. Lender PCA: One area with a failed asphalt patch was noted in front of Building 11. Priority repai | 84204.0 | GC | Project | 30000 | 9000 | 21000 |  | In Progress
Ardmore Springs | 2026 | ADA parking & curb cuts | Lender PCA: One ADA parking space at the leasing office has a post for an ADA sign, but the face is blank and missing th | 84221.0 | PMC | Project | 150 | 0 | 150 |  | Not Started
Ardmore Springs | 2026 | Sidewalks | PNA: Repair trip hazards | 84221.0 | GC | Project | 8500 | 2550 | 5950 |  | In Progress
Ardmore Springs | 2026 | Landscape irrigation | Lender PCA: A broken irrigation line was observed at Building 6. Priorty repairs are recommended to repair the broken ir | 84302.0 | PMC | Project | 500 | 0 | 500 |  | Not Started
Ardmore Springs | 2026 | Erosion control | PNA: Add rocks at downspout in eroded areas | 83517.0 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Ardmore Springs | 2026 | Fences & gates - site perimeter | Lender PCA: The site fencing near the pet wash station near the operable gate is damaged. Priority repairs are recommend | 84205.0 | PMC | Project | 2000 | 0 | 2000 |  | Not Started
Ardmore Springs | 2026 | Building entrance | Post: Signage replacements for rebranding | 84103.0 | PMC | Project | 75000 | 0 | 75000 |  | Not Started
Ardmore Springs | 2026 | Mold and water remediation | Lender PCA: Approximately 12 sf of suspect mold was observed at the fire sprinkler room of Building 8, possibly from tes | 83160.0 | PMC | Project | 2500 | 0 | 2500 |  | Not Started
Ardmore Springs | 2026 | Repair exterior stair railings | PNA: Secure stair rails | 84121.0 | GC | Project | 8500 | 2550 | 5950 |  | In Progress
Ardmore Springs | 2026 | Repair balcony framing & decking | PNA: Repair vinyl on balcony band board ($10,000) and secure all patio railings ($6,500) | 84104.0 | GC | Project | 16500 | 4950 | 11550 |  | In Progress
Ardmore Springs | 2026 | Expansion joints | Expansion Joints | 84206.0 | GC | Project | 8000 | 2400 | 5600 |  | In Progress
Ardmore Springs | 2026 | Asphalt composite shingle roofing | PNA: Roof inspection and tune up | 84433.0 | GC | Project | 22000 | 6600 | 15400 |  | In Progress
Ardmore Springs | 2026 | Gutters & downspouts | PNA: Replace damaged gutter and downspouts, clean, re-pitch remaining | 84202.0 | GC | Project | 11000 | 3300 | 7700 |  | In Progress
Ardmore Springs | 2026 | Sealants & caulking | Roof Sealants and Caulking | 84433.0 | GC | Project | 8500 | 2550 | 5950 |  | In Progress
Ardmore Springs | 2026 | Flashing | PNA: Replace damaged flashing on breezeway roofs | 84433.0 | GC | Project | 12000 | 3600 | 8400 |  | In Progress
Ardmore Springs | 2026 | Repair / replace cement fiber siding | PNA: Replace damaged siding and paint | 84206.0 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Ardmore Springs | 2026 | Repair / replace wood shingles | PNA: Replace rotted trim and paint to match | 84113.0 | GC | Project | 5000 | 1500 | 3500 |  | In Progress
Ardmore Springs | 2026 | Dryer Vents | Lender PCA: Three locations total, at Building 5 and 10, exhibit missing laundry vent covers which allows for moisture a | 83106.0 | PMC | Project | 225 | 0 | 225 |  | Not Started
Ardmore Springs | 2026 | Tuck-pointing | Lender PCA: One stairstep cracked area was observed in the central part of an entrance arch of brick masonry facade at b | 83212.0 | GC | Project | 1000 | 300 | 700 |  | In Progress
Ardmore Springs | 2026 | Breezeway soffit repairs | PNA: Repair breezeway soffit | 84120.0 | GC | Project | 9500 | 2850 | 6650 |  | In Progress
Ardmore Springs | 2026 | Exterior building | PNA: Paint community, iron will require special treatment | 84101.0 | GC | Project | 300000 | 90000 | 210000 |  | In Progress
Ardmore Springs | 2026 | Masonry Repairs | PNA: Pressure wash vinyl on posts and balcony head | 84102.0 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Ardmore Springs | 2026 | Appliances Package | Post: Washer/Dryer installs | 82200.0 | PMC | Project | 272400 | 80321 | 192079 |  | In Progress
Ardmore Springs | 2026 | Radon remediation | Per ESA: Radon remediation in 9 areas, ($3,500-$4,500 per location) EBI recommends completing pilot testing, building ch | 84250.0 | GC | Project | 47750 | 14325 | 33425 |  | In Progress
Ardmore Springs | 2026 | Leasing office floor/wall finishes, Replace Furniture | Post: Remodel leasing office (Paint - 1st Call & Furniture - PMC) | 84116.0 | GC | Project | 119850 | 0 | 119850 |  | Not Started
Ardmore Springs | 2026 | Leasing office | Lender PCA: The sinks at the leasing office bathroom do not appear to havescald/abrasion protection at the sink piping a | 84116.0 | GC | Project | 150 | 35955 | -35805 |  | Completed
Ardmore Springs | 2026 | Fitness Center Remodel | PNA: Repair sheetrock and paint fitness center and package room | 84190.0 | GC | Project | 20000 | 6000 | 14000 |  | In Progress
Ardmore Springs | 2026 | Gym Equipment | Post: Replace gym equipment | 84190.0 | PMC | Project | 50000 | 8571 | 41429 |  | In Progress
Ardmore Springs | 2026 | Unit Model Update | Post: Set up model unit | 84280.0 | PMC | Project | 30000 | 0 | 30000 |  | Not Started
Ardmore Springs | 2026 | Fire stops | PNA: Fire stops | 84239.0 | PMC | Project | 24696 | 41880 | -17184 |  | Completed
Ardmore Springs | 2026 | Stormwater Pipe Repair | PNA: Clean storm sewer basins | 84432.0 | GC | Project | 4000 | 1200 | 2800 |  | In Progress
Ardmore Springs | 2026 | Replace defective outlet | Lender PCA: One GFCI outlet at unit 4206 in the kitchen does not reset, and priorty repairs are recommended to replace t | 84210.0 | PMC | Project | 30 | 0 | 30 |  | Not Started
Ardmore Springs | 2026 | Replace electric baseboard heater | Lender PCA: One electric baseboard heater located within the sprinkler system closet in building 8 was noted to have dis | 83217.0 | PMC | Project | 500 | 1249 | -749 |  | Completed
Ardmore Springs | 2026 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 56013 | 0 | 56013 |  | Reserve
Ardmore Springs | 2026 | Construction Management Fee | CM Fee | 84505.0 | GC | CM Fee | 58813 | 0 | 58813 |  | Reserve
Bentley Parke | 2026 | Storm sewer piping and drains | PNA - Clear drains on pool deck |  | GC | Project | 5000 | 1500 | 3500 |  | In Progress
Bentley Parke | 2026 | Sidewalks and curbs | PNA - Grind trip hazards |  | GC | Project | 13000 | 3900 | 9100 |  | In Progress
Bentley Parke | 2026 | Carports / Garages | PNA - Repair carports |  | GC | Project | 22000 | 6600 | 15400 |  | In Progress
Bentley Parke | 2026 | Dumpster enclosures | PNA - Repair dumpster enclosures |  | GC | Project | 16000 | 4800 | 11200 |  | In Progress
Bentley Parke | 2026 | WDIR | WDIR Treatment per Inspection |  | PMC | Project | 15900 | 0 | 15900 |  | Not Started
Bentley Parke | 2026 | Concrete deck / floor fill | PNA - Repair landings |  | GC | Project | 15000 | 4500 | 10500 |  | In Progress
Bentley Parke | 2026 | Exterior building | PNA - Paint community 100% paintable 3.2.4. Painting, Exterior. The paint finish on the apartment buildings was observe |  | GC | Project | 382800 | 114840 | 267960 |  | In Progress
Bentley Parke | 2026 | Repair exterior stair treads and stringers | PNA - Replace 40 broken stair treads |  | GC | Project | 18900 | 5670 | 13230 |  | In Progress
Bentley Parke | 2026 | Expansion joints | PNA - Seal expansion joints |  | GC | Project | 16000 | 4800 | 11200 |  | In Progress
Bentley Parke | 2026 | Asphalt composite shingle roofing | PNA - Roof tune up 3.2.8 - Asphalt Shingle (3-tab). The inboard parapet asphalt shingle installation date was not provid |  | GC | Project | 10260 | 3078 | 7182 |  | In Progress
Bentley Parke | 2026 | Modified bitumen membrane roof repairs | PNA - Repairs to flat roofing and repairs with modified bit 3.2.8. - Built-up roof / Modified Bitumen |  | GC | Project | 75000 | 22800 | 52200 |  | In Progress
Bentley Parke | 2026 | Gutters & downspouts | PNA - Clean and repatch gutters throughout property |  | GC | Project | 21000 | 6300 | 14700 |  | In Progress
Bentley Parke | 2026 | Flashing | PNA - Repair parapet wall flashing |  | GC | Project | 15600 | 4680 | 10920 |  | In Progress
Bentley Parke | 2026 | Sealants & caulking | PNA - Seal windows as part of paint |  | GC | Project | 20000 | 6000 | 14000 |  | In Progress
Bentley Parke | 2026 | Repair stucco | PNA - Repairs to stucco |  | GC | Project | 26000 | 7800 | 18200 |  | In Progress
Bentley Parke | 2026 | Domestic Hot Water Heater, Replace | 3.3.5 - Water Heater Sesimic Strapping. The water heaters lacked one or both seismic bracing straps at observed units 10 |  | PMC | Project | 3000 | 0 | 3000 |  | Not Started
Bentley Parke | 2026 | Electrical distribution | PNA - Replace lighting controlers |  | GC | Project | 16000 | 4800 | 11200 |  | In Progress
Bentley Parke | 2026 | Replace breezeway lights | PNA - R&R ceiling lights in breezeways with LED |  | GC | Project | 38600 | 11580 | 27020 |  | In Progress
Bentley Parke | 2026 | Interior Upgrades | Raising Y1 of Unit Interior Upgrades upfront |  | PMC | Project | 260680 | 38010 | 222670 |  | In Progress
Bentley Parke | 2026 | Drier vents | PNA - Remove vent covers, clean vent piping, and install new dryer vent covers |  | GC | Project | 38280 | 11484 | 26796 |  | In Progress
Bentley Parke | 2026 | Fire Stops | PNA - Fire stops |  | PMC | Project | 22736 | 1916 | 20820 |  | In Progress
Bentley Parke | 2026 | ADA - Leasing Office Restrooms | 5.4 - The plumbing under the lavatories within the publicly-accessible toilet rooms did not appear to be configured to p |  | PMC | Project | 300 | 25 | 275 |  | In Progress
Bentley Parke | 2026 | Unit Deferred Maintenance | Down Unit Refurbishment (Unit 1405) - Damaged bedroom ceiling ($8,000) Roof Leak Repair (Unit 1405) - Repair Roof above |  | GC | Project | 9000 | 2400 | 6600 |  | In Progress
Bentley Parke | 2026 | CA SB-721 Elevated Exterior Elements Inspection | 3.2.7 - According to a recent State of California Law (SB 721), subject properties that contain “exterior elevated eleme |  | GC | Project | 6500 | 1950 | 4550 |  | In Progress
Bentley Parke | 2026 | Clubhouse / Office remodel | Concept Walk - Convert staff room to a business center/cybercafe |  | PMC | Project | 25000 | 3750 | 21250 |  | In Progress
Bentley Parke | 2026 | Security/ fire alarm systems | Concept Walk - Add security cameras |  | PMC | Project | 35000 | 0 | 35000 |  | Not Started
Bentley Parke | 2026 | Swimming pool deck | PNA - Presure wash pool deck |  | GC | Project | 12000 | 3600 | 8400 |  | In Progress
Bentley Parke | 2026 | Swimming Pool Shower | Concept Walk - Re-tile shower |  | GC | Project | 5000 | 1500 | 3500 |  | In Progress
Bentley Parke | 2026 | Swimming pool fencing / gates | PNA - Repair pool fence |  | GC | Project | 5600 | 1680 | 3920 |  | In Progress
Bentley Parke | 2026 | BBQ Grill Area | Concept Walk - Add BBQ/Grill Area outside swimming pool fence |  | GC | Project | 25000 | 7500 | 17500 |  | In Progress
Bentley Parke | 2026 | Contingency | Contingency Amount |  | GC | Contingency | 58758 | 0 | 58758 |  | Reserve
Bentley Parke | 2026 | Construction Management Fee | CM Fee |  | GC | CM Fee | 61696 | 0 | 61696 |  | Reserve
Cherry Creek | 2026 | Storm sewer piping and drains | PNA: clean storm drains | 51130-00 | GC | Project | 20000 | 0 | 20000 |  | Not Started
Cherry Creek | 2026 | Asphalt seal coating | Lender PCA: Damaged pavement consisting of linear cracking was present at the drive aisles typical of the conditions not | 51053-00 | GC | Project | 81000 | 0 | 81000 |  | Not Started
Cherry Creek | 2026 | Stripe parking areas | Stripe Parking Lots | 51053-00 | GC | Project | 28000 | 0 | 28000 |  | Not Started
Cherry Creek | 2026 | Sidewalks and curbs | Lender PCA: A potential trip hazard consisting of vertical and horizontal separation was observed to the northeast of bu | 51091-00 | PMC | Project | 500 | 0 | 500 |  | Not Started
Cherry Creek | 2026 | Sidewalks and curbs | PNA: Trip Hazards | 51091-00 | GC | Project | 14000 | 0 | 14000 |  | Not Started
Cherry Creek | 2026 | Landscape Cleanup & Enhancements | Lender PCA: Trees were observed impeding on the building rooftop and facade between units 54 and 64. No portion of any t | 51045-00 | PMC | Project | 12000 | 0 | 12000 |  | Not Started
Cherry Creek | 2026 | Carports / Garages | PNA: Carport repairs and paint post and pearling | 51172-00 | GC | Project | 36000 | 0 | 36000 |  | Not Started
Cherry Creek | 2026 | Dumpster enclosures | Lender PCA: The threshold height at the accessible leasing office entrance does not appear to be ADA-compliant. Installa | 51163-00 | PMC | Project | 125 | 0 | 125 |  | Not Started
Cherry Creek | 2026 | Termite Remediation | Lender PCA: Termite remediation - Evidence of drywood termites for areas 2A, 2C, 2E, 2F, 2H, and 2I on the termite map. | 51992-00 | PMC | Project | 23250 | 1000 | 22250 |  | In Progress
Cherry Creek | 2026 | Termite damage repairs | Lender PCA: Termite Damage - Repair and replace damaged materials noted on the termite report. Lender PCA: Termite Damag | 51070-00 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Cherry Creek | 2026 | Repair exterior stair railings | PNA: secure and paint railings | 51077-00 | GC | Project | 26000 | 0 | 26000 |  | Not Started
Cherry Creek | 2026 | Repair patio/balcony railings/fences | Lender PCA: Deteriorated and damaged wood framing and trim were noted at balconies and upper landings including at build | 51077-00 | GC | Project | 20000 | 0 | 20000 |  | Not Started
Cherry Creek | 2026 | Repair Catwalks | PNA: secure catwalk railings | 51072-00 | GC | Project | 28000 | 0 | 28000 |  | Not Started
Cherry Creek | 2026 | Expansion Joints | PNA: Stucco expansion joints | 51090-00 | GC | Project | 6000 | 0 | 6000 |  | Not Started
Cherry Creek | 2026 | Gutters & downspouts | Lender PCA: Leaf accumulation was noted in gutters across the site. Removal of the leaf debris is recommended. PNA: sec | 51071-00 | GC | Project | 19000 | 0 | 19000 |  | Not Started
Cherry Creek | 2026 | Sealants & caulking | PNA: seal and prep stucco | 51062-00 | GC | Project | 36000 | 0 | 36000 |  | Not Started
Cherry Creek | 2026 | Repair Roof Gambles | Lender PCA: Deteriorated and damaged roof gables were observed at buildings 6 and 7. Repair of the noted issues is recom | 84433.0 | GC | Project | 3000 | 0 | 3000 |  | Not Started
Cherry Creek | 2026 | Repair / replace wood shingles | PNA: Replace rotted fascia and trim | 51075-00 | GC | Project | 46000 | 0 | 46000 |  | Not Started
Cherry Creek | 2026 | Wall framing | PNA: damaged framing on stair supports | 51159-00 | GC | Project | 35000 | 0 | 35000 |  | Not Started
Cherry Creek | 2026 | Stucco repairs | PNA: Stucco repairs | 51075-00 | GC | Project | 40000 | 0 | 40000 |  | Not Started
Cherry Creek | 2026 | Exterior paint | Lender PCA: Peeling paint was observed on the exterior stairway wall of building 7. Reapplication of exterior paint is r | 51080-00 | GC | Project | 230000 | 0 | 230000 |  | Not Started
Cherry Creek | 2026 | Unit water heaters | PNA: replace two hot water heaters | 50050-00 | GC | Project | 42000 | 0 | 42000 |  | Not Started
Cherry Creek | 2026 | Electrical distribution - exterior | PNA: Place Holder for electric meter and load center replacement | 51140-00 | GC | Project | 80000 | 0 | 80000 |  | Not Started
Cherry Creek | 2026 | Pole lighting | Retrofit porch lights to LED - Concept Walk | 51141-00 | GC | Project | 12000 | 0 | 12000 |  | Not Started
Cherry Creek | 2026 | Breezeway and patio lights | Concept Walk: there are 13 breezeways (budgeting $750/unit) | 51141-00 | GC | Project | 9750 | 0 | 9750 |  | Not Started
Cherry Creek | 2026 | Fire monitoring system | Fire Stops: Expire 2031 but some maybe old - approx. 50% - Concept Walk | 51177-00 | PMC | Project | 3000 | 0 | 3000 |  | Not Started
Cherry Creek | 2026 | Security alarm systems | Lender PCA: An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recert | 51993-00 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Cherry Creek | 2026 | Elevators | Lender PCA: Current operation permits were not posted in each elevator cab. Property management should schedule reinspec | 51164-00 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Cherry Creek | 2026 | Swimming pool resurface | PNA: resurface pool | 51023-00 | GC | Project | 52000 | 0 | 52000 |  | Not Started
Cherry Creek | 2026 | Swimming pool deck | PNA: deck o seal on pool | 51022-00 | GC | Project | 14000 | 0 | 14000 |  | Not Started
Cherry Creek | 2026 | Swimming pool pumps repair / replace | PNA: anti entrapment devices | 51026-00 | GC | Project | 6800 | 0 | 6800 |  | Not Started
Cherry Creek | 2026 | Swimming pool fencing / gates | PNA: Repair fence and Paint | 51076-00 | GC | Project | 22000 | 0 | 22000 |  | Not Started
Cherry Creek | 2026 | Pool furniture | Pool Furniture Straps, BBQ Grill Upgrade - Concept Walk | 51011-00 | PMC | Project | 30000 | 0 | 30000 |  | Not Started
Cherry Creek | 2026 | Contingency | Contingency Amount | 51990-00 | GC | Contingency | 49171 | 0 | 49171 |  | Reserve
Cherry Creek | 2026 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 51630 | 0 | 51630 |  | Reserve
Clipper Cove | 2026 | Storm sewer piping and drains | PNA - Clean storm drains throughout property |  | GC | Project | 24000 | 7200 | 16800 |  | In Progress
Clipper Cove | 2026 | Parking lot repairs | PNA - Seal coat entire parking lot - add crack fill as needed |  | GC | Project | 430000 | 129000 | 301000 |  | In Progress
Clipper Cove | 2026 | Asphalt seal coating | PNA - Repair broken or failing asphalt LPCA - Asphalt pavement |  | GC | Project | 68000 | 20400 | 47600 |  | In Progress
Clipper Cove | 2026 | Stripe parking areas | PNA - Stripe parking areas |  | GC | Project | 24000 | 7200 | 16800 |  | In Progress
Clipper Cove | 2026 | ADA parking & ramps | PNA - Repairs to failing ADA ramps LPCA - ADA van-accessible parking |  | GC | Project | 18000 | 5400 | 12600 |  | In Progress
Clipper Cove | 2026 | Sidewalks and curbs | PNA - Replace failing areas of sidewalk LPCA - Trip hazards at concrete walkway |  | GC | Project | 42000 | 12600 | 29400 |  | In Progress
Clipper Cove | 2026 | Detention pond fountain | Concept Walk - Installation of 6 lake fountains |  | GC | Project | 35000 | 0 | 35000 |  | Not Started
Clipper Cove | 2026 | Erosion control and drainage | PNA - Erosion control around all buildings |  | GC | Project | 82500 | 24750 | 57750 |  | In Progress
Clipper Cove | 2026 | Landscape irrigation | Concept Walk - Irrigation LPCA - Irrigation |  | GC | Project | 40000 | 300 | 39700 |  | In Progress
Clipper Cove | 2026 | Landscape Cleanup & Enhancements | Concept Walk - Office landscape enhancements |  | GC | Project | 50000 | 8572 | 41428 |  | In Progress
Clipper Cove | 2026 | Tree Trimming | PNA - Tree trim, get overgrowth off buildings |  | GC | Project | 48000 | 14400 | 33600 |  | In Progress
Clipper Cove | 2026 | Dumpster enclosures | PNA - Repair dumpster enclosures |  | GC | Project | 42000 | 12600 | 29400 |  | In Progress
Clipper Cove | 2026 | Termite damage repairs | LPCA - WDO Repairs |  | GC | Project | 19500 | 5850 | 13650 |  | In Progress
Clipper Cove | 2026 | Repair balcony framing & decking | PNA - Repair failing lightweight concrete on catwalk |  | GC | Project | 49000 | 14700 | 34300 |  | In Progress
Clipper Cove | 2026 | Repair exterior stair treads and stringers | PNA - Replace twenty failing exterior stair cases LPCA - Exterior stairs, balconies, and breezeways (near units 104 and |  | GC | Project | 360000 | 108000 | 252000 |  | In Progress
Clipper Cove | 2026 | Repair exterior stair railings | PNA - Repair failing stair and catwalk railings |  | GC | Project | 86000 | 25800 | 60200 |  | In Progress
Clipper Cove | 2026 | Expansion Joints | PNA - Expansion joints |  | GC | Project | 25000 | 7500 | 17500 |  | In Progress
Clipper Cove | 2026 | Modified bitumen membrane repairs / replacement | PNA - Replace the modified bit roofing on racquetball structures |  | GC | Project | 16500 | 4950 | 11550 |  | In Progress
Clipper Cove | 2026 | Gutters & downspouts | PNA - Repair, clean, reattach replace gutters throughout the property |  | GC | Project | 62500 | 18750 | 43750 |  | In Progress
Clipper Cove | 2026 | Sealants & caulking | PNA - Sealants & caulking |  | GC | Project | 24000 | 7200 | 16800 |  | In Progress
Clipper Cove | 2026 | Repair / replace siding | PNA - Pressure wash to remove mildew. Repair/replace damaged or broken vinyl siding matching the existing color |  | GC | Project | 92000 | 27600 | 64400 |  | In Progress
Clipper Cove | 2026 | Wall framing | PNA - Repair structural framing in areas that indicate failures |  | GC | Project | 210000 | 63000 | 147000 |  | In Progress
Clipper Cove | 2026 | Stucco repairs | PNA - Failing and damaged stucco was observed throughout the property |  | GC | Project | 82000 | 24600 | 57400 |  | In Progress
Clipper Cove | 2026 | Exterior paint | PNA - Paint stucco, trim and wood rails |  | GC | Project | 428000 | 128400 | 299600 |  | In Progress
Clipper Cove | 2026 | Repair / replace wood trim | PNA - Rotted window trim and facia was observed, repairs would include paint to match |  | GC | Project | 52000 | 15600 | 36400 |  | In Progress
Clipper Cove | 2026 | HVAC pipe insulation | PNA - Install linset insulation |  | GC | Project | 24000 | 7200 | 16800 |  | In Progress
Clipper Cove | 2026 | Electrical distribution - exterior | PNA - Electrical distribution LPCA - Electrical (open electrical boxes were observed near irrigation piping) |  | GC | Project | 12000 | 3600 | 8400 |  | In Progress
Clipper Cove | 2026 | Pole lighting | PNA - Replace with LED fixture |  | GC | Project | 39000 | 11700 | 27300 |  | In Progress
Clipper Cove | 2026 | Lighing controller system | PNA - Common area light fixtures (building light LED retrofit) |  | GC | Project | 46000 | 13800 | 32200 |  | In Progress
Clipper Cove | 2026 | Interior Upgrades | Concept Walk - Renovate classic units |  | PMC | Project | 1000000 | 133969 | 866031 |  | In Progress
Clipper Cove | 2026 | Drier vents | PNA - Drier vents |  | PMC | Project | 28800 | 0 | 28800 |  | Not Started
Clipper Cove | 2026 | Stovetop fire suppression | PNA - Fire protection |  | PMC | Project | 37632 | 0 | 37632 |  | Not Started
Clipper Cove | 2026 | Interior microbial growth treatment | LPCA - Localized water staining was observed at the ceiling of Unit 103.The unit appears to currently be used for miscel |  | PMC | Project | 1000 | 0 | 1000 |  | Not Started
Clipper Cove | 2026 | Patio Fence Enclosure | Concept Walk - Screened in porches for all unit stacks |  | GC | Project | 270000 | 81000 | 189000 |  | In Progress
Clipper Cove | 2026 | Clubhouse / Office remodel | Concept Walk - Clubhouse repaint, kitchen remodel, & flooring |  | GC | Project | 95000 | 28500 | 66500 |  | In Progress
Clipper Cove | 2026 | Clubhouse / Office redecorate (FFE) | Concept Walk - Leasing office / clubhouse redec and furniture |  | PMC | Project | 105000 | 14962 | 90038 |  | In Progress
Clipper Cove | 2026 | Model Unit | Concept Walk - Update model to include appliances, cabinetry, flooring, & fixtures |  | PMC | Project | 35000 | 0 | 35000 |  | Not Started
Clipper Cove | 2026 | Golf Cart | Concept Walk - 3 golf carts |  | PMC | Project | 45000 | 0 | 45000 |  | Not Started
Clipper Cove | 2026 | Swimming pool resurface | PNA - Resurface the pool and hot tub at the leasing office |  | GC | Project | 38000 | 11400 | 26600 |  | In Progress
Clipper Cove | 2026 | Swimming pool coping and tile | PNA - Replace swimming pool coping |  | GC | Project | 12000 | 3600 | 8400 |  | In Progress
Clipper Cove | 2026 | Swimming pool deck | PNA - Powerwash decking on both pools |  | GC | Project | 18000 | 5400 | 12600 |  | In Progress
Clipper Cove | 2026 | Swimming pool pumps repair / replace | PNA - Repair the hot tub that is currently not working Concept Walk - Fill in hot tub and make seating area |  | GC | Project | 50000 | 15000 | 35000 |  | In Progress
Clipper Cove | 2026 | Pool furniture | Concept Walk - 1st pool furniture + 2nd pool furniture |  | PMC | Project | 75000 | 0 | 75000 |  | Not Started
Clipper Cove | 2026 | Tennis / sports court | Concept Walk - Tennis court repurpose ($100k) + repurpose racquetball court to maintenance/storage ($50k) LPCA - Tennis |  | GC | Project | 134854 | 40456 | 94398 |  | In Progress
Clipper Cove | 2026 | Playground area and equipment | PNA - install fall zone borders and add fall zone material |  | GC | Project | 28000 | 8400 | 19600 |  | In Progress
Clipper Cove | 2026 | Pool Area Upgrades | Concept Walk - Turf installation, landscape cleanup, lighting replacement, palm tree cleanup, etc. |  | GC | Project | 250000 | 75000 | 175000 |  | In Progress
Clipper Cove | 2026 | Contingency | Contingency Amount |  | GC | Contingency | 237714 | 0 | 237714 |  | Reserve
Clipper Cove | 2026 | Construction Management Fee | CM Fee |  | GC | CM Fee | 249600 | 0 | 249600 |  | Reserve
Cypress Ridge | 2026 | Parking Lots | PNA - repair potholes |  | GC | Project | 22000 | 6600 | 15400 |  | In Progress
Cypress Ridge | 2026 | Asphalt Milling/Paving/SealCoat | PNA - Crack fill TCAC - Asphalt seal coat and striping |  | GC | Project | 27000 | 8100 | 18900 |  | In Progress
Cypress Ridge | 2026 | Stripe parking areas | PNA - Stripe parking lot |  | GC | Project | 28000 | 8400 | 19600 |  | In Progress
Cypress Ridge | 2026 | ADA parking & ramps | PNA - Repair concrete on ramp |  | GC | Project | 14000 | 4200 | 9800 |  | In Progress
Cypress Ridge | 2026 | Sidewalks and curbs | PNA - Grind trip hazards |  | GC | Project | 16000 | 4800 | 11200 |  | In Progress
Cypress Ridge | 2026 | Site perimeter fencing | LPCA - Minor fence board damage was noted at a single location near Unit 2154. Repair of the noted issue is recommended. |  | PMC | Project | 750 | 0 | 750 |  | Not Started
Cypress Ridge | 2026 | Landscape Cleanup & Enhancements | Concept Walk - landscape cleanup and ground cover |  | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Cypress Ridge | 2026 | Dumpster enclosures | PNA - Repair enclosures |  | GC | Project | 18000 | 5400 | 12600 |  | In Progress
Cypress Ridge | 2026 | Termite Remediation | LPCA - Partner was provided with a WDO report by Redwood Empire Termite and Pest Control, dated January 25, 2026. The re |  | PMC | Project | 920 | 0 | 920 |  | Not Started
Cypress Ridge | 2026 | Termite damage repairs | LPCA - The WDO report also stated fungus/dryrot was observed. Partner recomments repairs. |  | GC | Project | 5000 | 1500 | 3500 |  | In Progress
Cypress Ridge | 2026 | Repair exterior stair treads and stringers | LPCA - Subsequent to site inspection activities, Partner was notified that installation of EV charging station caused cr |  | GC | Project | 5000 | 1500 | 3500 |  | In Progress
Cypress Ridge | 2026 | Expansion Joints | PNA - Expansion joints |  | GC | Project | 20000 | 6000 | 14000 |  | In Progress
Cypress Ridge | 2026 | Asphalt composite shingle roofing | PNA - Tune up roofs (building replacements as needed) TCAC - Asphalt shingle |  | GC | Project | 50000 | 15000 | 35000 |  | In Progress
Cypress Ridge | 2026 | Gutters & downspouts | PNA - Repair downspouts and gutters |  | GC | Project | 25000 | 7500 | 17500 |  | In Progress
Cypress Ridge | 2026 | Flashing | PNA - Flashing |  | GC | Project | 12000 | 3600 | 8400 |  | In Progress
Cypress Ridge | 2026 | Sealants & caulking | PNA - Seal roof cracks LPCA (PR-90) - Evidence of discoloration was noted in the upper bedroom or bathroom ceilings at U |  | GC | Project | 20000 | 6000 | 14000 |  | In Progress
Cypress Ridge | 2026 | Roof treatment / cleaning | LPCA - Organic growth including moss was noted on main and secondary asphalt-shingle roofs. Over time the organic materi |  | GC | Project | 18900 | 5670 | 13230 |  | In Progress
Cypress Ridge | 2026 | Stucco repairs | PNA - Patch cracked stucco LPCA - Horizontal cracking was noted at multiple facades including Units 2129, 2159, 2209, an |  | GC | Project | 40000 | 12000 | 28000 |  | In Progress
Cypress Ridge | 2026 | Exterior paint | PNA - Paint community |  | GC | Project | 227400 | 68220 | 159180 |  | In Progress
Cypress Ridge | 2026 | Repair / replace wood trim | PNA - Repair / replace wood trim |  | GC | Project | 25000 | 7500 | 17500 |  | In Progress
Cypress Ridge | 2026 | Electrical distribution - exterior | PNA - Repair lighting controllers |  | GC | Project | 18000 | 5400 | 12600 |  | In Progress
Cypress Ridge | 2026 | Partial Renovation | Seller to address: LPCA - Units 65 and 103 are considered down units due to evictions that are currently in progress. Ma |  | PMC | Project | 17000 | 0 | 17000 |  | Not Started
Cypress Ridge | 2026 | Drier vents | PNA - Drier vents |  | PMC | Project | 11590 | 0 | 11590 |  | Not Started
Cypress Ridge | 2026 | Stovetop fire suppression | PNA - Fire stops |  | PMC | Project | 11956 | 0 | 11956 |  | Not Started
Cypress Ridge | 2026 | Interior microbial growth treatment | Seller to address: LPCA (PR-90) - Water damage was observed at ceiling areas in the bathroom and bedroom of Unit 2 and t |  | PMC | Project | 3000 | 0 | 3000 |  | Not Started
Cypress Ridge | 2026 | Signage - entry | Concept Walk - replace main ID and add directional signage |  | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Cypress Ridge | 2026 | Fire system - Code Violations | LPCA (PR-90) - There are open There are open fire code violations for expired fire extinguishers at 1815 Meda Ave. At th |  | PMC | Project | 500 | 0 | 500 |  | Not Started
Cypress Ridge | 2026 | Video systems | Concept Walk - replace inoperable cameras and add in dead zones |  | PMC | Project | 15000 | 47799 | -32799 |  | Completed
Cypress Ridge | 2026 | Outdoor kitchen, fire pits, and seating area | Concept Walk - outdoor grills and seating area |  | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Cypress Ridge | 2026 | Playground area and equipment | Concept Walk - playground and fall zone |  | GC | Project | 45000 | 13500 | 31500 |  | In Progress
Cypress Ridge | 2026 | Contingency | Contingency Amount |  | GC | Contingency | 38601 | 0 | 38601 |  | Reserve
Cypress Ridge | 2026 | Construction Management Fee | CM Fees |  | GC | CM Fee | 40531 | 0 | 40531 |  | Reserve
Oslo | 2026 | Dryer Vent Cleaning | Dryer Vent Cleaning - Contingency | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Oslo | 2026 | Gutter Cleaning | Gutter Cleaning - Contingency | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Oslo | 2026 | Plumbing | Plumbing Repairs - Contingency | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Oslo | 2026 | Windows/Doors | Window/Door Repairs - Contingency | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Oslo | 2026 | Capital Plan |  |  | Unmarked | Project | 95000 | 119427 | -24427 |  | Completed
Oslo | 2026 | Contingency Amount | Contingency | Contingency & Fees | GC | Contingency | 4750 | 0 | 4750 |  | Reserve
Oslo | 2026 | Construction Management Fees | CM Fees | Contingency & Fees | GC | CM Fee | 4988 | 0 | 4988 |  | Reserve
San Regis | 2026 | Storm sewer piping and drains | PNA - clear parking lot drains |  | GC | Project | 30000 | 0 | 30000 |  | Not Started
San Regis | 2026 | Parking lot repairs | PNA - repair potholes |  | GC | Project | 28000 | 0 | 28000 |  | Not Started
San Regis | 2026 | Asphalt seal coating | PNA - crack fill |  | GC | Project | 19000 | 0 | 19000 |  | Not Started
San Regis | 2026 | Stripe parking areas | PNA - stripe parking lot |  | GC | Project | 27000 | 0 | 27000 |  | Not Started
San Regis | 2026 | ADA parking & ramps | PNA - repair concrete on ramp |  | GC | Project | 14000 | 0 | 14000 |  | Not Started
San Regis | 2026 | Sidewalks and curbs | PNA - grind trip hazards |  | GC | Project | 14000 | 0 | 14000 |  | Not Started
San Regis | 2026 | Landscape Cleanup & Enhancements | Concept Walk - tree trim + landscape cleanup |  | GC | Project | 30000 | 0 | 30000 |  | Not Started
San Regis | 2026 | Dumpster enclosures | PNA - Prevent damage to hallway to parking lot |  | GC | Project | 18000 | 0 | 18000 |  | Not Started
San Regis | 2026 | Termite Remediation | WDIR - findings from WDIR (placeholder) |  | GC | Project | 31500 | 0 | 31500 |  | Not Started
San Regis | 2026 | Repair balcony framing & decking | PNA - repair and recoat exposed walkways |  | GC | Project | 39500 | 0 | 39500 |  | Not Started
San Regis | 2026 | Expansion Joints | PNA - seal joint |  | GC | Project | 8500 | 0 | 8500 |  | Not Started
San Regis | 2026 | Modified bitumen membrane repairs / replacement | PNA - was not able to get on roofs but based on age suspect damage on all roofs and replace roof on office building |  | GC | Project | 95000 | 0 | 95000 |  | Not Started
San Regis | 2026 | Gutters & downspouts | PNA - replace crushed down spouts |  | GC | Project | 21000 | 0 | 21000 |  | Not Started
San Regis | 2026 | Flashing | PNA - flashing |  | GC | Project | 19800 | 0 | 19800 |  | Not Started
San Regis | 2026 | Sealants & caulking | PNA - sealants & caulking |  | GC | Project | 20000 | 0 | 20000 |  | Not Started
San Regis | 2026 | Stucco repairs | PNA - patch stucco and paint to match |  | GC | Project | 30000 | 0 | 30000 |  | Not Started
San Regis | 2026 | Interior Hallway flooring / painting | PNA - paint hallways/breezeways |  | GC | Project | 156000 | 0 | 156000 |  | Not Started
San Regis | 2026 | Exterior paint | PNA - exterior building |  | GC | Project | 646000 | 0 | 646000 |  | Not Started
San Regis | 2026 | Domestic water piping | PNA - insulate hot water lines on office roofs |  | GC | Project | 10000 | 0 | 10000 |  | Not Started
San Regis | 2026 | Common area water heaters / boilers | PNA - insulate boiler lines on office roof |  | GC | Project | 10000 | 0 | 10000 |  | Not Started
San Regis | 2026 | Electrical distribution - exterior | PNA - provide and install can light adapters to catwalk lighting and inspect and replace lighting controllers |  | GC | Project | 19500 | 0 | 19500 |  | Not Started
San Regis | 2026 | Breezeway and patio lights | PNA - replace breezeway and catwalk lighting to LED |  | GC | Project | 59800 | 0 | 59800 |  | Not Started
San Regis | 2026 | Interior Upgrades | 2746679.999999999 |  | PMC | Project | 425380 | 0 | 425380 |  | Not Started
San Regis | 2026 | ADA Accessibility | ADA Upgrades (responsible for 25 of 43 total required) |  | PMC | Project | 2321300 | 0 | 2321300 |  | Not Started
San Regis | 2026 | Stovetop fire suppression | PNA - fire stops |  | PMC | Project | 38220 | 0 | 38220 |  | Not Started
San Regis | 2026 | ADA Relocation Costs | ADA Relocation Costs |  | PMC | Project | 125000 | 0 | 125000 |  | Not Started
San Regis | 2026 | Clubhouse / Office remodel | Concept Walk - fix water leaks and prevent any continued deterioration in leasing office (2nd and 3rd floor) |  | GC | Project | 100000 | 0 | 100000 |  | Not Started
San Regis | 2026 | Fire suppression system | LPCA - The annual inspection and 5-year inspection tags were not current. Partner recommends obtaining current inspectio |  | PMC | Project | 1500 | 0 | 1500 |  | Not Started
San Regis | 2026 | Elevators | LPCA - Current operation permits were not posted in each elevator cab. Partner recommends obtaining current inspection t |  | PMC | Project | 1500 | 0 | 1500 |  | Not Started
San Regis | 2026 | Swimming pool resurface | PNA - resurface pool and hot tub |  | GC | Project | 58000 | 0 | 58000 |  | Not Started
San Regis | 2026 | Swimming pool deck | PNA - repair cracks and seal |  | GC | Project | 38000 | 0 | 38000 |  | Not Started
San Regis | 2026 | Swimming pool fencing / gates | PNA - fences & gates - swimming pool |  | GC | Project | 14000 | 0 | 14000 |  | Not Started
San Regis | 2026 | Pool furniture | Concept Walk - pool furniture |  | PMC | Project | 30000 | 0 | 30000 |  | Not Started
San Regis | 2026 | Tennis / sports court | Concept Walk - sports court furniture |  | PMC | Project | 50000 | 0 | 50000 |  | Not Started
San Regis | 2026 | Contingency | Contingency Amount |  | GC | Contingency | 227475 | 0 | 227475 |  | Reserve
San Regis | 2026 | Construction Management Fee | CM Fee |  | GC | CM Fee | 238849 | 0 | 238849 |  | Reserve
Tribute Verdae | 2026 | Asphalt Coating | Asphalt seal coat & striping | 84204.0 | GC | Project | 46000 | 13800 | 32200 |  | In Progress
Tribute Verdae | 2026 | Stripe parking areas | Restripe parking | 84201.0 | GC | Project | 14000 | 4200 | 9800 |  | In Progress
Tribute Verdae | 2026 | Accessibility Exterior accessible route | Please refer to the accessibility report | 84221.0 | GC | Project | 132850 | 39855 | 92995 |  | In Progress
Tribute Verdae | 2026 | Accessibility Parking and route from parking | Please refer to the accessibility report | 84201.0 | GC | Project | 32000 | 9600 | 22400 |  | In Progress
Tribute Verdae | 2026 | Accessibility Exterior door approaches | Please refer to the accessibility report | 84221.0 | GC | Project | 5250 | 1575 | 3675 |  | In Progress
Tribute Verdae | 2026 | Accessibility Interior access & access to amenities | Please refer to the accessibility report | 84221.0 | GC | Project | 750 | 225 | 525 |  | In Progress
Tribute Verdae | 2026 | Accessibility Public toilets /common area toilets | Please refer to the accessibility report | 84116.0 | GC | Project | 6700 | 2010 | 4690 |  | In Progress
Tribute Verdae | 2026 | Accessibility Access to other items | Please refer to the accessibility report | 84116.0 | GC | Project | 3650 | 1095 | 2555 |  | In Progress
Tribute Verdae | 2026 | Landscape irrigation | Inspect and repair irrigation prior to installing turf | 84300.0 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Tribute Verdae | 2026 | Erosion control | The grade around a few of the apartment buildings exhibited substantial runoff erosion and/or water ponding adjacent to | 84435.0 | GC | Project | 15000 | 4500 | 10500 |  | In Progress
Tribute Verdae | 2026 | Erosion control | Additional soil and regional turf to barren areas Barren turf was observed at isolated areas throughout, typical to sid | 84435.0 | PMC | Project | 100000 | 9153 | 90847 |  | In Progress
Tribute Verdae | 2026 | Retaining walls | Add additional retaining wall between building 8 and 9 | 84434.0 | GC | Project | 75000 | 22500 | 52500 |  | In Progress
Tribute Verdae | 2026 | Swimming pool deck | Pressure wash deck | 84361.0 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Tribute Verdae | 2026 | Swimming pool fencing / gates | Repair gate closers | 84361.0 | GC | Project | 4000 | 1200 | 2800 |  | In Progress
Tribute Verdae | 2026 | Storm sewer piping and drains | Add storm drains between bulding 8 and 9 | 84385.0 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Tribute Verdae | 2026 | Playground equipment | New Playground (Find Placement) | 84195.0 | GC | Project | 65000 | 19500 | 45500 |  | In Progress
Tribute Verdae | 2026 | Radon Long-Term Testing and Remediation | Post-Closing Radon Long-Term Testing and Remediation for 21 units | 84250.0 | PMC | Project | 150000 | 0 | 150000 |  | Not Started
Tribute Verdae | 2026 | Sustainability Improvements | Reserve for post-closing sustainability due diligence review and imrovements | 84905.0 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Tribute Verdae | 2026 | Jack & underpin foundations | Inspect all building cut post tension cables and seal | 84435.0 | GC | Project | 3000 | 900 | 2100 |  | In Progress
Tribute Verdae | 2026 | Concrete deck / floor fill | Inspect route and seal concrete cracks The concrete patio in the northwest corner contained exposed and improperly term | 84430.0 | GC | Project | 28000 | 8400 | 19600 |  | In Progress
Tribute Verdae | 2026 | Repair balcony framing & decking | Inspect & repair wood decking on breezeways. Some of the wood-framed upper floor balconies & breezeway landings were obs | 84104.0 | GC | Project | 50000 | 15000 | 35000 |  | In Progress
Tribute Verdae | 2026 | Pressure Wash | Pressure wash 1st floor of brick to remove clay spoils | 84206.0 | GC | Project | 28000 | 8400 | 19600 |  | In Progress
Tribute Verdae | 2026 | Repair brick pier damage | The brick pier adjacent to garage 2202 was observed with damage, likely resulting from mechanical impact. The observed d | 84102.0 | GC | Project | 2500 | 750 | 1750 |  | In Progress
Tribute Verdae | 2026 | Repair balcony support posts | The bases at some balcony support posts are overhanging the concrete patio slab edge and not fully bearing on the concre | 84104.0 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
Tribute Verdae | 2026 | Gutters & downspouts | Inspect and repair downspouts, splash blocks | 84202.0 | GC | Project | 45000 | 13500 | 31500 |  | In Progress
Tribute Verdae | 2026 | Dog Park | Purchasing new astroturf, benches, and shade | 84130.0 | GC | Project | 75000 | 22500 | 52500 |  | In Progress
Tribute Verdae | 2026 | Sanitary Sewer Piping | At sewer scope cleanouts numbers 9 and 2 joint separations were observed. It is recommended to replace or repair the joi | 84385.0 | PMC | Project | 29500 | 4481 | 25019 |  | In Progress
Tribute Verdae | 2026 | Refrigerant linesets insulation | Partner observed that the insulation on the exterior portion of the refrigerant linesets between the condensing units an | 84217.0 | GC | Project | 6500 | 1950 | 4550 |  | In Progress
Tribute Verdae | 2026 | Construction Management Fee | CM Fee | 84505.0 | GC | CM Fee | 51635 | 0 | 51635 |  | Reserve
Walnut Square | 2026 | Landscape Cleanup and Enhancements | Tree trim and landscape cleanup | 84303.0 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Walnut Square | 2026 | Water Distribution Piping | Two different water leaks from meter boxes Allowance to repair city water main leaks at the property based on observed c | 84470.0 | GC | Project | 12000 | 0 | 12000 |  | Not Started
Walnut Square | 2026 | Pavement | Remove and replace pothole areas on site | 84204.0 | GC | Project | 28000 | 0 | 28000 |  | Not Started
Walnut Square | 2026 | ADA parking & curb cuts | Remove and replace damaged curbs on community | 84221.0 | GC | Project | 30000 | 0 | 30000 |  | Not Started
Walnut Square | 2026 | Sidewalks | Grind trip hazards | 84221.0 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Walnut Square | 2026 | Fences & gates - site perimeter | Rebuild 2500 lf of wood fence, repair 2000 lf of iron fence and paint both | 84205.0 | GC | Project | 192000 | 0 | 192000 |  | Not Started
Walnut Square | 2026 | Fences & gates - swimming pool | Repair and paint | 84205.0 | GC | Project | 5600 | 0 | 5600 |  | Not Started
Walnut Square | 2026 | Playground area | Turf around playground areas | 84195.0 | GC | Project | 45000 | 0 | 45000 |  | Not Started
Walnut Square | 2026 | Dumpster enclosures | Repair and paint | 84111.0 | GC | Project | 14000 | 0 | 14000 |  | Not Started
Walnut Square | 2026 | Repair exterior stair treads and stringers | Resurface stairs to office | 84114.0 | GC | Project | 10000 | 0 | 10000 |  | Not Started
Walnut Square | 2026 | Repair patio/balcony railings | Secure balcony railings | 84121.0 | GC | Project | 8500 | 0 | 8500 |  | Not Started
Walnut Square | 2026 | Expansion joints | Exterior Expansion Joints | 84206.0 | GC | Project | 17000 | 0 | 17000 |  | Not Started
Walnut Square | 2026 | Gutters & downspouts | Clean and repitch gutters and repair down spouts throughout property | 84202.0 | GC | Project | 28000 | 8400 | 19600 |  | In Progress
Walnut Square | 2026 | Flashing | Roof Flashing | 84433.0 | GC | Project | 8500 | 2550 | 5950 |  | In Progress
Walnut Square | 2026 | Sealants & caulking | Roof Sealants & caulking | 84433.0 | GC | Project | 8500 | 2550 | 5950 |  | In Progress
Walnut Square | 2026 | Repair / replace cement fiber siding | Repair or replace damaged siding siding | 84105.0 | GC | Project | 19000 | 5700 | 13300 |  | In Progress
Walnut Square | 2026 | Exterior building Painting | Paint community | 84101.0 | GC | Project | 232000 | 69600 | 162400 |  | In Progress
Walnut Square | 2026 | Repair / replace wood trim | Repair / replace wood trim | 84105.0 | GC | Project | 16000 | 4800 | 11200 |  | In Progress
Walnut Square | 2026 | Drier vents | Drier vents | 84106.0 | GC | Project | 15675 | 0 | 15675 |  | Not Started
Walnut Square | 2026 | Leasing office floor/wall finishes, Replace | Reflooring / repaint in office | 84208 | GC | Project | 50000 | 0 | 50000 |  | Not Started
Walnut Square | 2026 | Leasing office FF&E, Replace | Leasing office FF&E, Replace | 84306 | GC | Project | 50000 | 4702 | 45298 |  | In Progress
Walnut Square | 2026 | Electrical distribution | Replace lightning controllers | 84210 | GC | Project | 6000 | 7200 | -1200 |  | Completed
Walnut Square | 2026 | Common area light fixtures | Replace 6 missing pole lights Allowance to repair/replace emergency light fixtures in common areas based on expired tags | 84112 | GC | Project | 8000 | 1800 | 6200 |  | In Progress
Walnut Square | 2026 | Replace breezeway lights | Replace front door lights with mini LED wallpacks | 84112 | GC | Project | 24000 | 2400 | 21600 |  | In Progress
Walnut Square | 2026 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 44389 | 0 | 44389 |  | Reserve
Walnut Square | 2026 | Construction Management Fee | CM Fee | 84505.0 | GC | CM Fee | 46608 | 0 | 46608 |  | Reserve
Waterford | 2026 | Parking lot repairs | PNA: repair potholes. Concept Walk - Replace speed bumps as needed | 84201 | GC | Project | 38000 | 12000 | 26000 |  | In Progress
Waterford | 2026 | Asphalt seal coating | PNA: Crack Fill | 84221 | GC | Project | 29000 | 8700 | 20300 |  | In Progress
Waterford | 2026 | Curbing Repairs | PNA: Curbing Repairs | MISSING | GC | Project | 24000 | 7200 | 16800 |  | In Progress
Waterford | 2026 | Sidewalks and curbs | PNA: grind trip hazards | 84221 | GC | Project | 14000 | 4200 | 9800 |  | In Progress
Waterford | 2026 | Site perimeter fencing | Concept Walk - Stain streetside perimeter fencing. Pressure wash interior perimeter fencing to remove moss buildup. | 84205 | GC | Project | 16480 | 4944 | 11536 |  | In Progress
Waterford | 2026 | Landscape Cleanup and Enhancements | Concept Walk - Tree trim and general curb appeal enhancement; Streetside cleanup around sign | 84303 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Waterford | 2026 | Carports / Garages | PNA: Repair carports | 84219 | GC | Project | 22000 | 6600 | 15400 |  | In Progress
Waterford | 2026 | Dumpster enclosures | PNA - Repair dumpster enclosures. | 84111 | GC | Project | 18000 | 5400 | 12600 |  | In Progress
Waterford | 2026 | Concrete deck / floor fill | PNA: Repair catwalks and install new outdoor carpet | 84221 | GC | Project | 81000 | 24300 | 56700 |  | In Progress
Waterford | 2026 | Repair exterior stair treads and stringers | PNA: inspect and secure railings on cat walks | 84114 | GC | Project | 20000 | 6000 | 14000 |  | In Progress
Waterford | 2026 | Asphalt composite shingle roofing | PNA: roof tune up | 84433 | GC | Project | 29000 | 8700 | 20300 |  | In Progress
Waterford | 2026 | Roof treatment / cleaning | PNA: Flashing | 84433 | GC | Project | 9800 | 2940 | 6860 |  | In Progress
Waterford | 2026 | Gutters & downspouts | PNA: Clean and repatch gutters throughout property | 84202 | GC | Project | 21000 | 6300 | 14700 |  | In Progress
Waterford | 2026 | Sealants & caulking | PNA: At band boards | 84433 | GC | Project | 20000 | 6000 | 14000 |  | In Progress
Waterford | 2026 | Repair / replace siding | PNA: Replace damaged Masonite and paint to match | 84206 | GC | Project | 30000 | 9000 | 21000 |  | In Progress
Waterford | 2026 | Breezeway soffit repairs | PNA: R&R ceiling lights in breezeways with LED | 84206 | GC | Project | 33200 | 9960 | 23240 |  | In Progress
Waterford | 2026 | Repair / replace wood trim | PNA: R&R rotted wood trim and paint to match | 84206 | GC | Project | 10000 | 3000 | 7000 |  | In Progress
Waterford | 2026 | Patio yard enclosures | Concept Walk - Installation of patior fencing where applicable | 84120 | GC | Project | 3600 | 0 | 3600 |  | Not Started
Waterford | 2026 | Electrical Panel Disconnects & Meter Banks | Electrical Panel Replacements | 84330 | GC | Project | 200000 | 0 | 200000 |  | Not Started
Waterford | 2026 | Breezeway Lighting | PNA - Wiring for pole lights | 84112 | GC | Project | 30000 | 9000 | 21000 |  | In Progress
Waterford | 2026 | Common Area Lighting | PNA: replace both pole light on existing post, straiten posts and add a concrete curb, replace wall packs with LED | 84112 | GC | Project | 73000 | 21900 | 51100 |  | In Progress
Waterford | 2026 | Breezeway Lighting | R&R ceiling lights in breezeway with LED | 84112 | GC | Project | 33200 | 9960 | 23240 |  | In Progress
Waterford | 2026 | Drier vents | PNA: Remove vent covers, clean vent piping, and install new dryer vent covers | 84106.0 | GC | Project | 33000 | 9900 | 23100 |  | In Progress
Waterford | 2026 | Fire Stops | Fire Stops | 84239 | PMC | Project | 19600 | 0 | 19600 |  | Not Started
Waterford | 2026 | Clubhouse / Office redecorate (FFE) | Concept Walk - Update clubhouse furniture and fixtures | 84208 | PMC | Project | 75000 | 0 | 75000 |  | Not Started
Waterford | 2026 | Security/ fire alarm systems | Lender PCA: Valid inspection certificates were affixed to the fire sprinklers dated September 2025. While the systems we | 84211 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Waterford | 2026 | Swimming pool resurface | PNA: Outdoor pool covered assume needing resurface hot tub needs resurface Indoor pool has been painted All Four nee | 84095 | GC | Project | 135000 | 40500 | 94500 |  | In Progress
Waterford | 2026 | Swimming pool coping and tile | Lender PCA: The pool and spa were down at the time of the site visit. Management reported the pool/spa area was closed d | 84095 | GC | Project | 5000 | 0 | 5000 |  | Not Started
Waterford | 2026 | Swimming pool deck | PNA: Repair cracks | 84095 | GC | Project | 32000 | 9600 | 22400 |  | In Progress
Waterford | 2026 | Swimming pool fencing / gates | PNA - Repair pool fence and gate. | 84205 | GC | Project | 14000 | 4200 | 9800 |  | In Progress
Waterford | 2026 | Pool furniture | Concept Walk - Add pool furniture | 84360 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Waterford | 2026 | Pergola / shade covers | PNA: Repair, paint, and pressure was outdoor kitchen area | 84113.0 | GC | Project | 26000 | 7800 | 18200 |  | In Progress
Waterford | 2026 | Tennis / sports court | Concept Walk - Resurface basketball court / replace goals | 84390 | GC | Project | 25200 | 7560 | 17640 |  | In Progress
Waterford | 2026 | Outdoor kitchen, fire pits, and seating area | PNA: Replace grill with Charcoal Grill to fit in island (8K). Concept Walk: placeholder for outdoor kitchen and shade st | 84203.0 | GC | Project | 28000 | 8400 | 19600 |  | In Progress
Waterford | 2026 | Playground area and equipment | Concept Walk - Install new playground | 84340 | GC | Project | 40000 | 12000 | 28000 |  | In Progress
Waterford | 2026 | Pet park / pet washing station | Concept Walk: placeholder for adding gravel/turf | 84130 | GC | Project | 25000 | 7500 | 17500 |  | In Progress
Waterford | 2026 | Fitness Center Remodel | Concept Walk: placeholder for fitness room/flooring paint in the lobby | 84190 | GC | Project | 15000 | 0 | 15000 |  | Not Started
Waterford | 2026 | Model Unit | Concept Walk - Update model | 84280.0 | PMC | Project | 25000 | 0 | 25000 |  | Not Started
Waterford | 2026 | Golf Carts | Concept Walk: need to purchase two new golf carts | 83375.0 | PMC | Project | 12500 | 0 | 12500 |  | Not Started
Waterford | 2026 | Shed (Storage Space) | Concept Walk: The current shop is only 8x8 and lacks adequate storage space. | 84102.0 | PMC | Project | 7500 | 0 | 7500 |  | Not Started
Waterford | 2026 | Contingency | Contingency Amount | 84510 | GC | Contingency | 66979 | 0 | 66979 |  | Reserve
Waterford | 2026 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 70328 | 0 | 70328 |  | Reserve
Willow Lakes | 2026 | Landscape Enhancements | Tree trim, Increasing by 50K for curb appeal based on concept walk LPCA - Tree branches were observed in contact at Bui | 84303.0 | PMC | Project | 95000 | 0 | 95000 |  | Not Started
Willow Lakes | 2026 | Pool Area Repairs & Equipment | Repair pool gates | 84361.0 | GC | Project | 19000 | 9500 | 9500 |  | In Progress
Willow Lakes | 2026 | Covered Parking & Misc. Parking Items | LPCA - Impact damage was observed at the garage door at the G-30 garage. Repairs are recommended. | 84219.0 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Willow Lakes | 2026 | Asphalt Milling/Paving/Sealcoat | Stripe Parking Areas | 84204.0 | GC | Project | 22000 | 22000 | 0 |  | Completed
Willow Lakes | 2026 | Concrete Curb/Sidewalk | Repair 2000 sq ft of concrete | 84221.0 | GC | Project | 70000 | 96000 | -26000 |  | Completed
Willow Lakes | 2026 | ADA Compliance Expense | ADA landings on apartment entrances are cracking up and failing | 83520.0 | GC | Project | 36000 | 36000 | 0 |  | Completed
Willow Lakes | 2026 | Sidewalks | repair trip hazards | 84115.0 | GC | Project | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Pool Area Repairs & Equipment | LPCA - Excessive algae growth due to an inoperable aeration pump was observed at the south portion of the pond. | 84361.0 | GC | Project | 2500 | 16000 | -13500 |  | Completed
Willow Lakes | 2026 | Erosion control | Landscaping Erosion Control | 84517.0 | GC | Project | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Fences & gates - site perimeter | repair iron and wood fence and paint | 84205.0 | GC | Project | 56000 | 66000 | -10000 |  | Completed
Willow Lakes | 2026 | Pool Area Repairs & Equipment | deck o seal | 84361.0 | GC | Project | 9500 | 0 | 9500 |  | Not Started
Willow Lakes | 2026 | Pool Area Repairs & Equipment | seal small cracks on pool deck and clean | 84361.0 | GC | Project | 16000 | 0 | 16000 |  | Not Started
Willow Lakes | 2026 | Fences & gates | Pedestrian and Front Gate Improvements | 84205.0 | GC | Project | 10000 | 19000 | -9000 |  | Completed
Willow Lakes | 2026 | Exterior Kitchen | replace grills | 84203.0 | GC | Project | 9500 | 9500 | 0 |  | Completed
Willow Lakes | 2026 | Dumpster enclosures | Build an enclosed area around roll off trash set up | 84111.0 | GC | Project | 25000 | 25000 | 0 |  | Completed
Willow Lakes | 2026 | Common Corridors Rehab | Grind and seal cracks in breezeways An isolated area of sectional cracking was noted on the main entrance drive and area | 84120.0 | GC | Project | 26000 | 0 | 26000 |  | Not Started
Willow Lakes | 2026 | Exterior Stairs | Repair exterior stair treads and stringers - Replace 90 stair treads | 84114.0 | GC | Project | 12500 | 12500 | 0 |  | Completed
Willow Lakes | 2026 | Handrail / Railings | Repair Exterior Railings | 84121.0 | GC | Project | 8500 | 8500 | 0 |  | Completed
Willow Lakes | 2026 | Balconies | Repair Balcony Decks | 84104.0 | GC | Project | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Roof Replacements/Repairs | Roof tune up - Asphalt composite shingle roofing | 84433.0 | GC | Project | 26000 | 26000 | 0 |  | Completed
Willow Lakes | 2026 | Roof/Gutters | Clean gutters and downspouts | 84202.0 | GC | Project | 21000 | 21000 | 0 |  | Completed
Willow Lakes | 2026 | Building - Exterior | replace siding that was caulked and painted over | 84206.0 | GC | Project | 26000 | 26000 | 0 |  | Completed
Willow Lakes | 2026 | Building Repairs | Masonry Repairs - Repair areas of damaged stone | 84102.0 | GC | Project | 20000 | 20000 | 0 |  | Completed
Willow Lakes | 2026 | Dryer Vents | Annual Dryer Vent Cleaning | 84106.0 | GC | Project | 20460 | 20460 | 0 |  | Completed
Willow Lakes | 2026 | Exterior Paint, Carpentry, & Misc. Repairs | Repair / replace wood trim - replace rotted wood | 84113.0 | GC | Project | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Equipment, baracades and staging | Equipment & Staging (Details of Scope?) | 84305.0 | GC | Project | 10000 | 10000 | 0 |  | Completed
Willow Lakes | 2026 | Fire Life Safety Work | Fire stops | 84239.0 | PMC | Project | 36456 | 0 | 36456 |  | Not Started
Willow Lakes | 2026 | Smoke Alarms | Completed by Seller - Move to Contingency? | 83236.0 | PMC | Project | 18600 | 0 | 18600 |  | Not Started
Willow Lakes | 2026 | Monument Sign | Enhance Signage (cordinate w/ church - add signage on their property) | 84290.0 | PMC | Project | 20000 | 0 | 20000 |  | Not Started
Willow Lakes | 2026 | Club House/Leasing Center Addition/Alteration | Leasing office floor/wall finishes - Light leasing office upgrade | 84116.0 | PMC | Project | 10000 | 0 | 10000 |  | Not Started
Willow Lakes | 2026 | Fitness Center | Moderate upgrades to the fitness center | 84190.0 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Willow Lakes | 2026 | Pool Area Remodel | Refresh area with color and furniture. Split between the two pools | 84360.0 | PMC | Project | 60000 | 49907 | 10093 |  | In Progress
Willow Lakes | 2026 | Dog Run | Add lighting, dog amenities, and repairs to fencing | 84130.0 | GC | Project | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Golf Cart | Add leasing cart | 83375.0 | PMC | Project | 15000 | 0 | 15000 |  | Not Started
Willow Lakes | 2026 | Stormwater Piping | Clean out basin | 84432.0 | GC | Project | 14000 | 14000 | 0 |  | Completed
Willow Lakes | 2026 | Replace AC condenser | align condensers and insulate suction lines | 84218.0 | GC | Project | 38000 | 38000 | 0 |  | Completed
Willow Lakes | 2026 | Electrical/Lighting | Electrical distribution - repair lighting controlers | 84210.0 | GC | Project | 21000 | 21000 | 0 |  | Completed
Willow Lakes | 2026 | Exterior Lighting | Common area light fixtures - wall packs and pole light throughout | 84112.0 | GC | Project | 39000 | 39000 | 0 |  | Completed
Willow Lakes | 2026 | Exterior Lighting | Replace breezeway lights - wall sconce, ceiling and garage lights | 84112.0 | GC | Project | 59500 | 59500 | 0 |  | Completed
Willow Lakes | 2026 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 51163 | 0 | 51163 |  | Reserve
Willow Lakes | 2026 | Other CM Fees | Construction Management Fee Amount | 84505.0 | GC | CM Fee | 54509 | 0 | 54509 |  | Reserve
Colonnade |  | Interior Hallway painting | Interior hallway repaint | 51160-00 | GC | Project | 158900 | 158900 | 0 |  | Completed
Colonnade |  | Controlled access gates | Add controlled access to main entry, fitness center, pool, & any other main entry point | 51993-00 | GC | Project | 100000 | 100000 | 0 |  | Completed
Colonnade |  | Trellis Repairs | Deteriorated beam framing at the wood beam framed trellis structure was noted. Repair is recommended. | 51070-00 | PMC | Project | 2500 | 0 | 2500 |  | Not Started
Colonnade |  | Equipment, Baracades, & Staging | Baracades & Staging | 51180-00 | GC | Project | 45000 | 45000 | 0 |  | Completed
Colonnade |  | Repair exterior stair railings | Paint interior stairwells and iron | 51077-00 | GC | Project | 38000 | 38000 | 0 |  | Completed
Colonnade |  | Façade repairs | Stucco deterioration was noted on the northern upper facade locations and organic build-up was noted. Repairs are recomm | 51075-00 | GC | Project | 5000 | 5000 | 0 |  | Completed
Colonnade |  | Full Property Repaint | Full property repaint | 51080-00 | GC | Project | 663000 | 663000 | 0 |  | Completed
Colonnade |  | Gutters & downspouts | Clean scuppers and roof drains | 51071-00 | GC | Project | 24000 | 24000 | 0 |  | Completed
Colonnade |  | Sealants & caulking | Roof Sealants & Caulking | 51062-00 | GC | Project | 25300 | 25300 | 0 |  | Completed
Colonnade |  | Elevator Cabs | Full repairs of 3 elevator interiors. Wood panels, flooring, stainless doors | 51160-00 | GC | Project | 30000 | 30000 | 0 |  | Completed
Colonnade |  | Fire Stops | Add fire stops to 50% of units missing | 51993-01 | PMC | Project | 10829 | 0 | 10829 |  | Not Started
Colonnade |  | Fitness center renovation | Full redeck of flooring and full repaint | 51160-00 | GC | Project | 25000 | 25000 | 0 |  | Completed
Colonnade |  | Stab-Lok Panels | Stab-Lok brand breaker panels manufactured by Federal Pacific Electric (FPE) were observed in the units. These panels ha | 51142-00 | GC | Project | 123200 | 123200 | 0 |  | Completed
Colonnade |  | Security/ fire alarm systems | An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recertification of | 51993-00 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Colonnade |  | Fire Sprinkler Certificaiton | The systems display lapsed certification. Recertification is required | 51993-01 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Colonnade |  | Fire extinguisher certification | The extinguishers displayed lapsed certification. Recertification is required. | 51993-01 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Colonnade |  | Elevator Inspection | A current cab certification permit was not provided and load test information was not displayed. Property management sho | 51993-01 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Colonnade |  | Fountain Repairs | The water feature is reportedly leaking into the garage area and are not presently in use. Repair is recommended. | 51160-00 | PMC | Project | 5000 | 0 | 5000 |  | Not Started
Colonnade |  | Startup Marketing | Rebrand of property signage | 51990-00 | PMC | Project | 35000 | 0 | 35000 |  | Not Started
Colonnade |  | Pest Control | Rat droppings were observed at the emergency generator room. Engaging a pest contractor and treatment for pest control o | 51992-00 | PMC | Project | 1500 | 0 | 1500 |  | Not Started
Colonnade |  | Swimming pool coping and tile | Resurface pool ( pool is on 4th floor and will required extreme labor cost ) | 51021-00 | GC | Project | 50000 | 50000 | 0 |  | Completed
Colonnade |  | Swimming pool deck | Seal small cracks on pool deck and clean | 51022-00 | GC | Project | 16000 | 16000 | 0 |  | Completed
Colonnade |  | Pool furniture | Furniture Upgrades | 51011-00 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Colonnade |  | Pergola / shade covers | Repair and recoat pergola | 51070-00 | GC | Project | 26000 | 26000 | 0 |  | Completed
Colonnade |  | Outdoor kitchen, fire pits, and seating area | Kitchen and outdoor cooking area upgrades | 51160-04 | PMC | Project | 50000 | 0 | 50000 |  | Not Started
Colonnade |  | Steam Sauna & Bathroom | FF&E facelift and upgrade | 51160-00 | PMC | Project | 12000 | 0 | 12000 |  | Not Started
Colonnade |  | Fitness equipment | 7 pieces of new equipments | 51028-00 | PMC | Project | 75000 | 0 | 75000 |  | Not Started
Colonnade |  | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 78861 | 78861 | 0 |  | Reserve
Colonnade |  | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 82805 | 82805 | 0 |  | Reserve
The Retreat |  | Parking equipment | add 15 speed bumps | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
The Retreat |  | Sidewalks | repair cracked concrete | 0200 - Site Utilities & Improvements | GC | Project | 20000 | 20000 | 0 |  | Completed
The Retreat |  | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Project | 26000 | 26000 | 0 |  | Completed
The Retreat |  | Patio fencing | 20 Extended Dog yards @ $5k- Value add | 0200 - Site Utilities & Improvements | GC | Project | 100000 | 100000 | 0 |  | Completed
The Retreat |  | Landscaping | New palms, bare land, dead bushes, etc.. | 0200 - Site Utilities & Improvements | GC | Project | 25000 | 25000 | 0 |  | Completed
The Retreat |  | Fences & gates - swimming pool | Replace entire dog park fence | 0200 - Site Utilities & Improvements | GC | Project | 35000 | 35000 | 0 |  | Completed
The Retreat |  | Pickleball court | Install pickleball court behind clubhouse | 0200 - Site Utilities & Improvements | GC | Project | 40000 | 40000 | 0 |  | Completed
The Retreat |  | Playground equipment | New Playground | 0200 - Site Utilities & Improvements | GC | Project | 30000 | 30000 | 0 |  | Completed
The Retreat |  | Dumpster enclosures | Repair Dumpsters and paint | 0200 - Site Utilities & Improvements | GC | Project | 6000 | 6000 | 0 |  | Completed
The Retreat |  | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | 0700 - Roofing | GC | Project | 16500 | 16500 | 0 |  | Completed
The Retreat |  | Dryer Vents | Clean all dryer vents | 0800 - Exterior Wall | GC | Project | 11340 | 11340 | 0 |  | Completed
The Retreat |  | Appliances Package |  | 0900 - FF&E in Units | PMC | Project | 486000 | 0 | 486000 |  | Not Started
The Retreat |  | Ceramic tile | 324 Backsplash @ $700 | 0900 - FF&E in Units | PMC | Project | 226800 | 0 | 226800 |  | Not Started
The Retreat |  | Range Queen |  | 0900 - FF&E in Units | PMC | Project | 29160 | 0 | 29160 |  | Not Started
The Retreat |  | Unit Model Update | New furniture in model unit | 0900 - FF&E in Units | PMC | Project | 13000 | 0 | 13000 |  | Not Started
The Retreat |  | Signage - site |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 25000 | 3739 | 21261 |  | In Progress
The Retreat |  | Clubhouse / Office Remodel | Wall and glass door between game/movie rooms | 1100- Specialties, Equipment & Furnishings | GC | Project | 6500 | 6500 | 0 |  | Completed
The Retreat |  | Video Systems | Movie Room refresh | 1100- Specialties, Equipment & Furnishings | PMC | Project | 15000 | 0 | 15000 |  | Not Started
The Retreat |  | Clubhouse / Office Redecorate (FFE) | Clubhouse furniture- quote #PS6143285 from Charter Furniture | 1100- Specialties, Equipment & Furnishings | PMC | Project | 92000 | 46776 | 45224 |  | In Progress
The Retreat |  | Tech Package per unit | 162 units x $700 | 1100- Specialties, Equipment & Furnishings | PMC | Project | 113400 | 0 | 113400 |  | Not Started
The Retreat |  | Audio systems | Audio systems - Game Room | 1100- Specialties, Equipment & Furnishings | PMC | Project | 10000 | 0 | 10000 |  | Not Started
The Retreat |  | Pool furniture | Update pool furniture to include cabanas | 1100- Specialties, Equipment & Furnishings | PMC | Project | 40000 | 37994 | 2006 |  | In Progress
The Retreat |  | Golf Cart |  | 1100- Specialties, Equipment & Furnishings | PMC | Project | 14000 | 24807 | -10807 |  | Completed
The Retreat |  | Replace Fire Alarm Panel |  | 1600 - Electrical | GC | Project | 1500 | 1500 | 0 |  | Completed

## Summary
Post Capital Plans — Alternative Approach (All Properties)
GC by cohort: 2024 & earlier assumed 100% @ budget; 2025 from pay app (else GL); 2026 pay app only. PMC/Unmarked from GL (cohort window). '% Projects' EXCLUDES Contingency & CM Fee. 'Net vs Total Budget' = Total Budget − Project Spent: positive = contingency/CM reserve covers any base overage; red/negative = genuinely over total budget. '10 yr Budget' = capital plan ex-BTL (blank where current-yr-only or pending review).
Data as of: Banner report 7/31/26 · PMC GLs 6/30/26 (2026 GL refreshed 7/30/26) · pay apps 7/2/26
Property | Acquired | Method | Project Budget | Project Spent | % Projects | Contingency | CM Fee | Total Budget | Net vs Total Budget | Capital Plan | GC Contract | Recent Pay App | GL Detail | Banner Report | First Call A/R | Scope Split GC/PMC/Unmarked | 10 yr Budget (ex-BTL) | 10-yr basis
Emerald Pointe | 2015 | GC @ budget | 2644954 | 1321427 |  | 64432 | 0 | 2709387 |  | ✓ |  | ✓ app 003 |  | ✓ |  | 19 GC / 4 PMC / 1 unmarked |  | current-yr only
Crescent Village 1 & 2 | 2017 | GC @ budget | 648850 | 648850 |  | 0 | 0 | 648850 |  | ✓ | ✓ | ✓ app 003 |  | ✓ | ✓ | 19 GC / 1 PMC |  | current-yr only
Viewcrest Village | 2021 | GC @ budget | 1098375 | 1036958 |  | 0 | 0 | 1098375 |  | ✓ |  | ✓ app 2 |  | ✓ |  | 9 GC / 10 PMC |  | current-yr only
Encore Crossing | 2022 | GC @ budget | 2244350 | 1283909 |  | 0 | 0 | 2244350 |  | ✓ |  | ✓ app 004 | Entrata GL | ✓ |  | 39 GC / 9 PMC |  | current-yr only
Island Villas | 2022 | GC @ budget | 2101360 | 1838026 |  | 0 | 0 | 2101360 |  | ✓ |  | ✓ app 004 | Entrata GL | ✓ | ✓ | 35 GC / 8 PMC |  | current-yr only
Amalfi at Tuscan Lakes | 2023 | GC @ budget | 3314095 | 3231255 |  | 279443 | 0 | 3593538 |  | ✓ |  | ✓ app 005 | Entrata GL | ✓ | ✓ | 48 GC / 0 PMC / 11 unmarked |  | current-yr only
Avila | 2023 | GC @ budget | 1578975 | 1578975 |  | 0 | 0 | 1578975 |  | ✓ |  | ✓ app 005 | Entrata GL | ✓ |  | 42 GC / 0 PMC |  | current-yr only
Collin Creek | 2023 | GC @ budget | 2763458 | 2168870 |  | 1004542 | 0 | 3768000 |  | ✓ |  | ✓ app 004 | Entrata GL | ✓ |  | 46 GC / 11 PMC / 2 unmarked |  | current-yr only
Las Colinas Heights | 2023 | GC @ budget | 5539442 | 3979908 |  | 162465 | 0 | 5701907 |  | ✓ |  | ✓ app 006 | Entrata GL | ✓ |  | 56 GC / 13 PMC / 1 unmarked |  | current-yr only
Oak Forest | 2023 | GC @ budget | 2613720 | 2198268 |  | 4346280 | 0 | 6960000 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ |  | 40 GC / 8 PMC / 4 unmarked |  | current-yr only
Oak Park | 2023 | GC @ budget | 7843534 | 6119761 |  | 572778 | 534592 | 8950904 |  | ✓ |  |  | Entrata GL | ✓ |  | 0 GC / 0 PMC / 70 unmarked |  | current-yr only
Sorrento at Tuscan Lakes | 2023 | GC @ budget | 2479733 | 2438420 |  | 77226 | 127848 | 2684807 |  | ✓ |  | ✓ app 005 | Entrata GL | ✓ |  | 44 GC / 0 PMC / 12 unmarked |  | current-yr only
The Grand at Hill Street | 2023 | GC @ budget | 454050 | 506463 |  | 0 | 0 | 454050 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ |  | 14 GC / 3 PMC |  | current-yr only
The Hightone (Allora Denton) | 2023 | GC @ budget | 509500 | 610504 |  | 0 | 0 | 509500 |  | ✓ |  | ✓ app 002 | Entrata GL | ✓ | ✓ | 11 GC / 3 PMC |  | current-yr only
Allora Bella Terra | 2024 | GC @ budget | 1420738 | 1420738 |  | 802262 | 111150 | 2334150 |  | ✓ |  | ✓ app 004 | Entrata GL | ✓ | ✓ | 47 GC / 0 PMC |  | current-yr only
Avonmora | 2024 | GC @ budget | 3700650 | 2514650 |  | 20000 | 0 | 3720650 |  | ✓ |  | ✓ app 003 |  | ✓ | ✓ | 32 GC / 4 PMC |  | current-yr only
Bridgepoint | 2024 | GC @ budget | 3389015 | 3395678 |  | 90985 | 174000 | 3654000 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ | ✓ | 71 GC / 1 PMC |  | current-yr only
Cityscape | 2024 | GC @ budget | 171634 | 187122 |  | 17163 | 9440 | 198238 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ | ✓ | 7 GC / 1 PMC |  | current-yr only
Discovery Park | 2024 | GC @ budget | 784444 | 788231 |  | 20000 | 40222 | 844666 |  | ✓ |  | ✓ app 002 | Entrata GL | ✓ | ✓ | 49 GC / 1 PMC |  | current-yr only
Hampton Courts | 2024 | GC @ budget | 1990358 | 1150400 |  | 100000 | 104518 | 2194875 |  | ✓ | ✓ | ✓ app 003 |  | ✓ | ✓ | 44 GC / 15 PMC |  | current-yr only
Harbor Terrace | 2024 | GC @ budget | 31500 | 31500 |  | 0 | 0 | 31500 |  | ✓ | ✓ | ✓ app 002 | Aperto GL | ✓ | ✓ | 4 GC / 0 PMC |  | current-yr only
Marquee | 2024 | GC @ budget | 1232147 | 718065 |  | 61607 | 61607 | 1355362 |  | ✓ | ✓ | ✓ app 003 | Aperto GL | ✓ | ✓ | 22 GC / 18 PMC |  | current-yr only
Navigator Villas | 2024 | GC @ budget | 864061 | 310259 |  | 20000 | 44203 | 928264 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ |  | 16 GC / 18 PMC |  | current-yr only
Presidium Edgestone | 2024 | GC @ budget | 365506 | 361506 |  | 36551 | 20103 | 422160 |  | ✓ |  | ✓ app 003 | CapEX GL | ✓ |  | 22 GC / 2 PMC |  | current-yr only
The Arbors | 2024 | GC @ budget | 2269256 | 2221801 |  | 70064 | 116966 | 2456286 |  | ✓ | ✓ | ✓ app 004 | Aperto GL | ✓ |  | 48 GC / 11 PMC |  | current-yr only
Village at Broadstone | 2024 | GC @ budget | 3729334 | 3728984 |  | 0 | 186467 | 3915800 |  | ✓ | ✓ | ✓ app 001 |  | ✓ |  | 52 GC / 2 PMC |  | current-yr only
Avenues of Kennesaw | 2025 | GC pay app | 4667854 | 3941824 |  | 258304 | 271220 | 5197378 |  | ✓ | ✓ | ✓ app 006 | Entrata GL | ✓ | ✓ | 56 GC / 14 PMC | 13111078 | grand-total
Azur Aparments | 2025 | GC pay app | 1227998 | 384860 |  | 329680 | 77884 | 1635562 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 55 GC / 1 PMC | 1635562 | grand-total
Cambridge Square | 2025 | GC pay app | 2315365 | 744607 |  | 115768 | 121557 | 2552690 |  | ✓ |  | ✓ app 001 | Entrata GL | ✓ |  | 35 GC / 5 PMC | 2552690 | grand-total
Candlewood | 2025 | GC pay app | 1325788 | 508005 |  | 132579 | 72918 | 1531285 |  | ✓ |  | ✓ app 002 | Aperto GL | ✓ |  | 22 GC / 8 PMC | 2098887 | grand-total
Canyon Villa | 2025 | GC GL fallback | 1262654 | 148445 |  | 33781 | 64822 | 1361257 |  | ✓ |  | Project not started |  | ✓ | ✓ | 30 GC / 7 PMC |  | REVIEW
Chaparral | 2025 | GC pay app | 2241450 | 1791338 |  | 87488 | 116447 | 2445384 |  | ✓ | ✓ | ✓ app 003 | Aperto GL | ✓ | ✓ | 30 GC / 6 PMC | 2445384 | grand-total
Crestmark | 2025 | GC pay app | 1755200 | 576902 |  | 87760 | 92148 | 1935108 |  | ✓ | ✓ | ✓ app 002 | Entrata GL | ✓ | ✓ | 19 GC / 25 PMC | 2043054 | grand-total
Cypress Bend | 2025 | GC pay app | 623390 | 459041 |  | 77339 | 42724 | 743453 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 22 GC / 13 PMC | 1404648 | grand-total
Cypress Bend Village | 2025 | GC pay app | 932415 | 736833 |  | 103516 | 57309 | 1093241 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ | ✓ | 30 GC / 10 PMC | 2546102 | grand-total
David Ave | 2025 | GC pay app | 864956 | 530429 |  | 45096 | 47350 | 957402 |  | ✓ | ✓ | ✓ app 002 | Aperto GL | ✓ | ✓ | 30 GC / 10 PMC | 1989091 | grand-total
Elliot Baymeadows | 2025 | GC pay app | 2868800 | 1351023 |  | 0 | 143440 | 3012240 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 27 GC / 16 PMC | 7058480 | line-item sum
Foster Creek | 2025 | GC pay app | 1118497 | 624115 |  | 48067 | 50470 | 1217034 |  | ✓ | ✓ | ✓ app 2 | Entrata GL | ✓ | ✓ | 23 GC / 13 PMC | 1880944 | line-item sum
Foxdale Village | 2025 | GC pay app | 3326446 | 2588390 |  | 351235 | 183884 | 3861564 |  | ✓ | ✓ | ✓ app 004 | Aperto GL | ✓ | ✓ | 44 GC / 5 PMC | 9345445 | grand-total
Latitude at the Commons | 2025 | GC pay app | 735739 | 240995 |  | 271880 | 50381 | 1058000 |  | ✓ |  | ✓ app 001 | Entrata GL | ✓ |  | 22 GC / 13 PMC | 2072383 | grand-total
Oak Park Monrovia | 2025 | GC pay app | 1297450 | 352080 |  | 90693 | 69407 | 1457550 |  | ✓ | ✓ | ✓ app 001 |  | ✓ | ✓ | 18 GC / 8 PMC | 2670267 | grand-total
Orchard Glen | 2025 | GC pay app | 3179250 | 2583879 |  | 166381 | 174700 | 3520331 |  | ✓ | ✓ | ✓ app 003 | Aperto GL | ✓ | ✓ | 33 GC / 13 PMC | 5096557 | grand-total
Paddock Club | 2025 | GC pay app | 1565089 | 1670625 |  | 282911 | 92400 | 1940400 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ |  | 26 GC / 18 PMC | 1940400 | grand-total
Rancho Cordova | 2025 | GC pay app | 622145 | 576066 |  | 31107 | 32663 | 685915 |  | ✓ | ✓ | ✓ app 002 | Aperto GL | ✓ | ✓ | 24 GC / 5 PMC | 1731465 | line-item sum
Regency & Lexington | 2025 | GC pay app | 1996796 | 1430810 |  | 215411 | 118476 | 2330684 |  | ✓ | ✓ | ✓ app 003 | Aperto GL | ✓ | ✓ | 68 GC / 23 PMC |  | NO-ANCHOR
Renaissance | 2025 | GC GL fallback | 1909884 | 21302 |  | 95494 | 100269 | 2105647 |  | ✓ |  | Project not started | CapEX GL | ✓ |  | 18 GC / 10 PMC | 2276997 | grand-total
Rosemont | 2025 | GC pay app | 2757064 | 1874580 |  | 137853 | 144746 | 3039663 |  | ✓ | ✓ | ✓ app 007 |  |  |  | 40 GC / 21 PMC | 5862468 | grand-total
Swiss Gables | 2025 | GC pay app | 1065004 | 682042 |  | 0 | 53250 | 1118254 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 24 GC / 13 PMC | 1297804 | Adam 7/21 stated total · line detail Δ26,996
The Ardent | 2025 | GC pay app | 2699800 | 763142 |  | 133740 | 140427 | 2973967 |  | ✓ |  | ✓ app 001 | Entrata GL | ✓ |  | 44 GC / 4 PMC | 11923686 | grand-total
The Fairways | 2025 | GC pay app | 1141973 | 1164821 |  | 178027 | 66000 | 1386000 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 30 GC / 9 PMC | 1386000 | grand-total
The Lakes | 2025 | GC pay app | 2098546 | 983631 |  | 104927 | 119624 | 2323097 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ |  | 29 GC / 7 PMC | 2504539 | Capital Plan Total · Δ141,630 in plan total col
The Vibe | 2025 | GC pay app | 1336934 | 1000100 |  | 229733 | 78333 | 1645000 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 38 GC / 7 PMC | 2055985 | grand-total
Valera Riverside | 2025 | GC GL fallback | 144480 | 17916 |  | 7224 | 7585 | 159289 |  | ✓ |  | Project not started | Entrata GL | ✓ |  | 5 GC / 5 PMC | 866789 | grand-total
Windward | 2025 | GC pay app | 1790312 | 361463 |  | 89516 | 93991 | 1973819 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ |  | 12 GC / 13 PMC | 2190078 | grand-total
Almaden 1930 | 2026 | GC pay app | 1386000 | 255233 |  | 87089 | 73654 | 1546744 |  | ✓ |  | ✓ app 001 | Aperto GL | ✓ |  | 38 GC / 2 PMC | 1541214 | Yr-1 as 10-yr (Adam 7/21)
Ardmore Springs | 2026 | GC pay app | 1120251 | 330651 |  | 56013 | 58813 | 1235077 |  | ✓ |  | ✓ app 001 | Entrata GL | ✓ |  | 23 GC / 12 PMC | 1235077 | Yr-1 as 10-yr (Adam 7/21)
Bentley Parke | 2026 | GC pay app | 1175156 | 287463 |  | 58758 | 61696 | 1295609 |  | ✓ |  | ✓ app 001 | Aperto GL | ✓ |  | 25 GC / 7 PMC | 1411529 | Capital Plan Total
Cherry Creek | 2026 | GC none ($0) | 983425 | 1000 |  | 49171 | 51630 | 1084226 |  | ✓ |  | Project not started | Aperto GL | ✓ |  | 26 GC / 9 PMC | 1084226 | Capital Plan Total
Clipper Cove | 2026 | GC pay app | 4754286 | 1148359 |  | 237714 | 249600 | 5241600 |  | ✓ |  | ✓ app 001 | Entrata GL | ✓ |  | 40 GC / 8 PMC | 5241600 | Capital Plan Total
Cypress Ridge | 2026 | GC pay app | 772016 | 241689 |  | 38601 | 40531 | 851148 |  | ✓ |  | ✓ app 003 | CapEX GL | ✓ |  | 22 GC / 10 PMC | 851148 | Capital Plan Total
Oslo | 2026 | GC none ($0) | 115000 | 119427 |  | 4750 | 4988 | 124738 |  | ✓ |  | Project not started | Entrata GL | ✓ |  | 2 GC / 4 PMC / 1 unmarked | 740194 | grand-total
San Regis | 2026 | GC none ($0) | 4549500 | 0 |  | 227475 | 238849 | 5015824 |  | ✓ |  | Project not started | Aperto GL | ✓ |  | 28 GC / 8 PMC | 5015824 | Capital Plan Total
Tribute Verdae | 2026 | GC pay app | 1032700 | 218594 |  | 0 | 51635 | 1084335 |  | ✓ |  | ✓ app 001 | Entrata GL | ✓ |  | 24 GC / 5 PMC | 1234700 | grand-total
Walnut Square | 2026 | GC pay app | 887775 | 109702 |  | 44389 | 46608 | 978772 |  | ✓ |  | ✓ app 001 | CapEX GL | ✓ |  | 25 GC / 1 PMC | 978772 | grand-total
Waterford | 2026 | GC pay app | 1339580 | 273564 |  | 66979 | 70328 | 1476887 |  | ✓ |  | ✓ app 001 | Entrata GL | ✓ |  | 34 GC / 8 PMC | 1476887 | Capital Plan Total
Willow Lakes | 2026 | GC pay app | 1039016 | 814867 |  | 51163 | 54509 | 1144688 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ |  | 32 GC / 9 PMC | 1994151 | line-item sum
Colonnade |  | GC @ budget | 1577229 | 1329400 |  | 78861 | 82805 | 1738895 |  | ✓ |  | Project not started |  |  |  | 16 GC / 13 PMC |  | current-yr only
The Retreat |  | GC @ budget | 1402200 | 451156 |  | 0 | 0 | 1402200 |  | ✓ |  | ✓ app 003 | Entrata GL |  |  | 13 GC / 11 PMC |  | current-yr only
TOTAL |  |  | 126788452 | 79480897 |  | 12452273 | 5301186 | 144541911

## Emerald Pointe
Emerald Pointe — 10-Year Capital Plan
Acquired 2015. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
130 | Capital Plan | Capital Plan |  | Unmarked | Project | 1288650 | 3033 | [15 empty] | GL (unmarked scope) · Yr-1 only (not in 10-yr plan)
84 | 51140-00 | Electrical Replacement | Replace Zinsco Electrical Subpanels ($525,000) Zinsco breakers were observed in the electrical subpanels inside all the | GC | Project | 587000 | 587000 | [15 empty] | GC assumed 100% @ budget
117 | 51992-00 | Termite/Pest Control | Termite Remediation ($249,500) WDI infestation noted at rafter tail, water heater closet door jam, and water heater clos | GC | Project | 249500 | 249500 | [15 empty] | GC assumed 100% @ budget
87 | 51143-00 | Wiring | Repair Aluminum Wiring - Allowance ($225,000) Aluminum wiring was observed in the residential units. To mitigate aluminu | GC | Project | 225000 | 225000 | [15 empty] | GC assumed 100% @ budget
58 | 51084-00 | Railings & Fences | Replace Landing Railings ($60,000) | GC | Project | 60000 | 60000 | [15 empty] | GC assumed 100% @ budget
21 | 51023-00 | Pool Resurfacing | Resurface Pool Decks ($42,500) | GC | Project | 42500 | 42500 | [15 empty] | GC assumed 100% @ budget
32 | 51043-00 | Tree Trimming/Pruning & Removal | Tree Trimming ($25,000) | PMC | Project | 25000 | 59 | [15 empty] | GL PMC
34 | 51046-00 | Irrigation System | Irrigation Repairs ($25,000) | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
42 | 51062-00 | Roof Repairs | Roof Repairs ($15,000) | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
52 | 51076-00 | Fence Repair/Replacement | Remove Pergolas ($15,000) | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
57 | 51083-00 | Decks/Balconies/Patio Repairs | Repair Deteriorating Wood on Patios ($15,000) | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
43 | 51063-00 | Roof Cleaning | Roof Inspection & Cleaning ($10,000) | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
33 | 51045-00 | Landscape Upgrades | Repair/Improve Landscape ($7,500) Many of the landscaping sprinkler systems are broken in multiple areas of theProperty. | PMC | Project | 7500 | 18 | [15 empty] | GL PMC
15 | 51010-00 | Pool Furniture Replacement | New Pool Furniture ($5,000) | PMC | Project | 5000 | 12 | [15 empty] | GL PMC
62 | 51091-00 | Sidewalk/Curb Repair/Replacement | Repair Sidewalk Tripping Hazards ($2,500) | GC | Project | 2500 | 2500 | [15 empty] | GC assumed 100% @ budget
92 | 51159-00 | Carpentry/Sheetrock | Repair Damaged Breezeway Ceiling ($1,000) A limited damaged of exterior breezeway ceiling finishes located by Building 2 | GC | Project | 1000 | 1000 | [15 empty] | GC assumed 100% @ budget
56 | 51082-00 | Trim/Doors | Repair Damaged Door ($750) The maintenance room door located near the north pool was observed to bedamaged. Repairing th | GC | Project | 750 | 750 | [15 empty] | GC assumed 100% @ budget
19 | 51021-00 | Pool Deck Repair | Seal Cracks Pool Deck ($700) Cracks were observed on the clubhouse pool deck. It appeared that there were attempts of re | GC | Project | 700 | 700 | [15 empty] | GC assumed 100% @ budget
63 | 51091-00 | Sidewalk/Curb Repair/Replacement | Repair Sidewalk Cracks ($700) A couple of the Subject's concrete sidewalk sections exhibit cracks. These conditions were | GC | Project | 700 | 700 | [15 empty] | GC assumed 100% @ budget
25 | 51027-00 | Court Resurfacing | Repair Basketball Court Cracks ($500) Asphalt pavement cracks was observed throughout the basketball court. Resealing cr | GC | Project | 500 | 500 | [15 empty] | GC assumed 100% @ budget
61 | 51090-00 | Concrete/Foundation | Repair Concrete Pavement Cracks ($500) Concrete cracks were observed at the concrete pavement located adjacent to the ba | GC | Project | 500 | 500 | [15 empty] | GC assumed 100% @ budget
69 | 51110-00 | Boiler Replacement | Repair Water Heater Leaks - Building 3 ($500) The water heater was leaking in Building 3 at the time of the assessment. | PMC | Project | 500 | 1 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2577300
|  |  | CM Fee |  |  | 67654 | 67654
|  |  | Contingency |  |  | 64432 | 64432
|  |  | Capital Plan Total (ex-BTL) |  |  | 2709387
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Crescent Village 1 & 2
Crescent Village 1 & 2 — 10-Year Capital Plan
Acquired 2017. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
15 | 84204 | Asphalt & Pavement | Mill cement stabilize and repave asphalt part of drive esles and repair concrete potholes on phase two Repair concrete | GC | Project | 400000 | 400000 | [15 empty] | GC assumed 100% @ budget
19 | 84205 | Fences & gates - site perimeter | Replace perimater fence on three sides of community Repair perimeter fencing - Collapsed fence panels were observed alon | GC | Project | 95000 | 95000 | [15 empty] | GC assumed 100% @ budget
53 | 84210 | Common area light fixtures | repair /replace leaning or broken poles and pole lights throughout the community | GC | Project | 32000 | 32000 | [15 empty] | GC assumed 100% @ budget
20 | 84303 | Tree Trimming - Landscaping | Tree trim | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
16 | 84201 | Stripe parking areas | Stripe Parking | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
17 | 84115 | Sidewalks | Repair trip Hazards | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
26 | 84111 | Dumpster enclosures | repair and paint | GC | Project | 9800 | 9800 | [15 empty] | GC assumed 100% @ budget
36 | 84202 | Gutters & downspouts | Replace damaged gutter and downspouts, Clean, re-pitch remaining | GC | Project | 9800 | 9800 | [15 empty] | GC assumed 100% @ budget
50 | 84220 | Replace AC condenser | Install installation and separate condensing units | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
24 | 84095 | Fences & gates - swimming pool | Rerair and paint pool fence | GC | Project | 8500 | 8500 | [15 empty] | GC assumed 100% @ budget
33 | 84206 | Expansion Joints | Building Expansion Joints | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
25 | 84105 | Pergola court | Repair and paint purgola in culdasac | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
32 | 84121 | Repair patio/balcony railings | secure all patio railings Repair exterior railings on east side of the property - Peeling and flaking paint was specifi | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
52 | 84210 | Electrical distribution | repair lighting control system | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
38 | 84433 | Roof - Sealants & caulking | Roof Sealants | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
37 | 84433 | Roof Flashing | replace damaged flashing | GC | Project | 4000 | 4000 | [15 empty] | GC assumed 100% @ budget
14 | 84432 | Storm sewer piping | Clean storm sewer basins | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
28 | 84221 | Repair ADA accessway and wheel stop | Repair ADA accessway and wheel stop - the accessway from the ADA parking lot, between Crescent Village 1 and 2 on the no | GC | Project | 1800 | 1800 | [15 empty] | GC assumed 100% @ budget
18 | 84517 | Erosion control | Add soil to eroded areas Repair erosion at drainage channel - Minor erosion was observed in the drainage channel at the | GC | Project | 1200 | 1200 | [15 empty] | GC assumed 100% @ budget
27 | 84221 | Concrete Repairs - Repair washed out wal | Repair wash out walkway at unit 2301 - The front entry concrete walkway to unit 2301 was noted as damaged from flooding | PMC | Project | 750 | 750 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 648850
|  |  | Capital Plan Total (ex-BTL) |  |  | 648850
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Viewcrest Village
Viewcrest Village — 10-Year Capital Plan
Acquired 2021. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
31 | 84101 | Exterior painting | Community Paint | GC | Project | 375000 | 375000 | [15 empty] | GC assumed 100% @ budget
25 | 84433 | Roof Replacement | Replace 12 roofs | GC | Project | 372000 | 372000 | [15 empty] | GC assumed 100% @ budget
37 | 84330 | Electrical Panels - Replace FPE Stab-Lok | It was reported that approximately 20% of the units still have FPE stab-lok panels. | GC | Project | 126000 | 126000 | [15 empty] | GC assumed 100% @ budget
38 | 84210 | Electrical Meters - Electrical audit and | Audit meters for proper housing, mounting and grounding and repair/replace as needed | GC | Project | 51000 | 51000 | [15 empty] | GC assumed 100% @ budget
17 | 84116 | Leasing office | Spot reno (new FF&E) | PMC | Project | 35000 | 8746 | [15 empty] | GL PMC
23 | 84210 | Meter Boxes - Repair/replace meter/cable | Replace on all buildings | PMC | Project | 25000 | 6247 | [15 empty] | GL PMC
26 | 84202 | Gutters & downspouts | Repair and replace damaged or missing gutters | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
30 | 84206 | Repair / replace vinyl siding | Replace failing siding as needed | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
32 | 84105 | Repair / replace wood trim | Replace bad areas of Fascia | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
27 | 84433 | Flashing | Replace flashing on 12 remaining roofs | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
28 | 84433 | Roof Repairs - Repair/replace sofits | Repair/replace missing or poorly maintained sofits to improve airflow | GC | Project | 12500 | 12500 | [15 empty] | GC assumed 100% @ budget
40 | 82480 | Appliances - Repair Washer/Dryer Hookups | Approximately 10-15 units have improperly installed hookups. | PMC | Project | 9375 | 2343 | [15 empty] | GL PMC
34 | 84217 | HVAC Repair - Heating System | Cadet wall heaters were observed in 3-BR units. | PMC | Project | 3188 | 796 | [15 empty] | GL PMC
14 | 84221 | Grind Sidewalk Trip Hazard | Trip hazards were specifically observed by Buildings 3342, 3423, 3412, 3413, 3430, 1542, 3427. | PMC | Project | 3062 | 765 | [15 empty] | GL PMC
41 | 83160 | Interior Other - Bathroom tub mold | Mold at the bottom of the tub surround was observed at Unit 3412, 1512, 1538B, 1579, 4 out of 30 units that were inspect | PMC | Project | 2500 | 625 | [15 empty] | GL PMC
42 | 83170 | Pest Control - Interior pest control | Two vacant units, 3419B and 1512B have been found to have fleas throughout. Pest control treatment has been scheduled fo | PMC | Project | 2000 | 500 | [15 empty] | GL PMC
15 | 84221 | Sidewalk - Seal Concrete Cracks | Limited areas of concrete sidewalk were observed with cracks. These area were specifically were observed by Units 3472C | PMC | Project | 750 | 187 | [15 empty] | GL PMC
16 | 84221 | Concrete Crack - Building 8 | Sidewalk exhibiting crack in concrete | PMC | Project | 625 | 156 | [15 empty] | GL PMC
36 | 84211 | Fire System Work - Clear Fire Department | The fire inspection report dated March 27, 2023, cited violations, including extension cords hanging from the ceiling an | PMC | Project | 375 | 94 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1098375
|  |  | Capital Plan Total (ex-BTL) |  |  | 1098375
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Encore Crossing
Encore Crossing — 10-Year Capital Plan
Acquired 2022. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
90 | 0900 - FF&E in Units | Interior Update Placeholder |  | PMC | Project | 960000 | 332 | [15 empty] | GL PMC
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Per Mark, placeholder for office redecoration x 2 (Includes adding sliding glass doors out to pool and opening up wall t | GC | Project | 125000 | 125000 | [15 empty] | GC assumed 100% @ budget
24 | 0200 - Site Utilities & Improvements | Landscaping | remove dead shrubs and change entrance island shrubs. DD $60k placeholder for landscape enhancement | GC | Project | 110000 | 110000 | [15 empty] | GC assumed 100% @ budget
22 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | $40k = Repair wood fence and paint, $40k = Repair (3) entrance gates. $15k iron fence repairs Phase 1 | GC | Project | 95000 | 95000 | [15 empty] | GC assumed 100% @ budget
121 | 1100- Specialties, Equipment & Furnishings | Video systems | Installation of new system (placeholder) | PMC | Project | 75000 | 0 | [15 empty] | GL PMC
123 | 1100- Specialties, Equipment & Furnishings | Pool furniture | New pool furniture (2 pools) | PMC | Project | 60000 | 206 | [15 empty] | GL PMC
116 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | Office redecoration placeholder | PMC | Project | 50000 | 131158 | [15 empty] | GL PMC
32 | 0200 - Site Utilities & Improvements | Pool Area Enhancement | Value-add enhancement to pool area, to inlcude turf installation, outdoor kitchen, fire pit area | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
122 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | New fitness equipment | PMC | Project | 50000 | 67319 | [15 empty] | GL PMC
39 | 0200 - Site Utilities & Improvements | Carports / Garages | Replace 10 garage doors | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
38 | 0200 - Site Utilities & Improvements | Building entrance | Entrance upgrade | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
108 | 0900 - FF&E in Units | Range Queen |  | PMC | Project | 32040 | 0 | [15 empty] | GL PMC
145 | 1600 - Electrical | Replace breezeway lights | Replace breezeway fixtures with led | GC | Project | 28600 | 28600 | [15 empty] | GC assumed 100% @ budget
25 | 0200 - Site Utilities & Improvements | Resurface swimming pool | Resurface Phase I | GC | Project | 28000 | 28000 | [15 empty] | GC assumed 100% @ budget
82 | 0800 - Exterior Wall | Repair / replace wood trim | Added $8000 for paint to match | GC | Project | 26900 | 26900 | [15 empty] | GC assumed 100% @ budget
16 | 0200 - Site Utilities & Improvements | Parking equipment | add 10 speed bumps | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
20 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
72 | 0800 - Exterior Wall | Repair / replace wood siding | Added $8000 for paint to match | GC | Project | 25200 | 25200 | [15 empty] | GC assumed 100% @ budget
12 | 0200 - Site Utilities & Improvements | Storm sewer piping |  | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
113 | 1100- Specialties, Equipment & Furnishings | Signage - site | Front monument sign & lighting | PMC | Project | 25000 | 29319 | [15 empty] | GL PMC
120 | 1100- Specialties, Equipment & Furnishings | Audio systems | Audio system for 2 pool areas | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
144 | 1600 - Electrical | Common area light fixtures | replace garage light fixtures | GC | Project | 22000 | 22000 | [15 empty] | GC assumed 100% @ budget
14 | 0200 - Site Utilities & Improvements | Concrete pavement | Repair | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Sidewalks | repair cracked concrete | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
61 | 0700 - Roofing | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Signage - building identification | New signage throughout, includes logo design and all new collateral | PMC | Project | 20000 | 23455 | [15 empty] | GL PMC
27 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | Pressure wash and coat pool deck in phase two | GC | Project | 18900 | 18900 | [15 empty] | GC assumed 100% @ budget
55 | 0400 - Structure | Repair balcony framing & decking |  | GC | Project | 18500 | 18500 | [15 empty] | GC assumed 100% @ budget
30 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | repair dog park and Pool fences and paint | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
124 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | Install new gym floor phase 2 and paint | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
76 | 0800 - Exterior Wall | Dryer Vents | Clean 256 dryer vents ($35 per) and replace (100) dryer vents | GC | Project | 13960 | 13960 | [15 empty] | GC assumed 100% @ budget
40 | 0200 - Site Utilities & Improvements | Carports / Garages | Repair/replace 15 garage door openers/ placeholder for purchase of openers | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
83 | 0800 - Exterior Wall | Shutters | Replace missing shutters and paint to match | GC | Project | 10200 | 10200 | [15 empty] | GC assumed 100% @ budget
125 | 1100- Specialties, Equipment & Furnishings | Golf Cart | Repair (2) golf carts- changed to 3 new golf carts | PMC | Project | 10000 | 69808 | [15 empty] | GL PMC
41 | 0200 - Site Utilities & Improvements | Dog Park | Placeholder for upgrade of equipment in dog park | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
66 | 0700 - Roofing | Gutters & downspouts | clean and repin | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
26 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | replace deck-o-seal in both pools | GC | Project | 9200 | 9200 | [15 empty] | GC assumed 100% @ budget
49 | 0400 - Structure | Wall framing |  | GC | Project | 8200 | 8200 | [15 empty] | GC assumed 100% @ budget
15 | 0200 - Site Utilities & Improvements | Stripe parking areas |  | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
37 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair Dumpsters and paint | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
54 | 0400 - Structure | Repair exterior stair railings |  | GC | Project | 7000 | 7000 | [15 empty] | GC assumed 100% @ budget
56 | 0400 - Structure | Repair patio/balcony railings |  | GC | Project | 7000 | 7000 | [15 empty] | GC assumed 100% @ budget
141 | 1600 - Electrical | Electrical distribution |  | GC | Project | 6600 | 6600 | [15 empty] | GC assumed 100% @ budget
67 | 0700 - Roofing | Flashing |  | GC | Project | 5600 | 5600 | [15 empty] | GC assumed 100% @ budget
68 | 0700 - Roofing | Sealants & caulking and paint |  | GC | Project | 5600 | 5600 | [15 empty] | GC assumed 100% @ budget
28 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | Phase 2 pool fountain repair | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | Parking Lot | Install 27 car stops in front of iron fencing Phase 1 | GC | Project | 4050 | 4050 | [15 empty] | GC assumed 100% @ budget
77 | 0800 - Exterior Wall | Tuck-pointing |  | GC | Project | 3800 | 3800 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2244350
|  |  | Capital Plan Total (ex-BTL) |  |  | 2244350
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 46880
BTL (dropped per Adam): $0

## Island Villas
Island Villas — 10-Year Capital Plan
Acquired 2022. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
88 | 0900 - FF&E in Units | Interior Update Placeholder |  | PMC | Project | 749760 | 592172 | [15 empty] | GL PMC
21 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Replace wood fence and paint | GC | Project | 154000 | 154000 | [15 empty] | GC assumed 100% @ budget
23 | 0200 - Site Utilities & Improvements | Landscaping | remove dead shrubs and change entrance island shrubs, landscaping around pool and planters for 2nd pool. Installation of | GC | Project | 100000 | 100000 | [15 empty] | GC assumed 100% @ budget
27 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | Replace pool deck w/ stamp stain concrete (main pool) and repairs to 2nd pool deck | GC | Project | 80000 | 80000 | [15 empty] | GC assumed 100% @ budget
66 | 0700 - Roofing | Sealants & caulking and paint | Seal all face nails in siding | GC | Project | 67200 | 67200 | [15 empty] | GC assumed 100% @ budget
22 | 0200 - Site Utilities & Improvements | Retaining walls | build retaining wall at site exit | GC | Project | 60000 | 60000 | [15 empty] | GC assumed 100% @ budget
61 | 0700 - Roofing | Cleaning Blue Algae | Treating/cleaning blue algae on roofs ($4k per building) | GC | Project | 60000 | 60000 | [15 empty] | GC assumed 100% @ budget
117 | 1100- Specialties, Equipment & Furnishings | Security/ fire alarm systems | Placeholder for installation of cameras | PMC | Project | 60000 | 30339 | [15 empty] | GL PMC
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Re-paint / new flooring for office | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
20 | 0200 - Site Utilities & Improvements | Erosion control | replace dirt missing due to erosion | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
31 | 0200 - Site Utilities & Improvements | Pool Area | Install (2) pool cabanas, turf in outdoor kitchen area | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
24 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface pool by office | GC | Project | 41000 | 41000 | [15 empty] | GC assumed 100% @ budget
143 | 1600 - Electrical | Common area light fixtures | replace garage light fixtures and wall packs | GC | Project | 36000 | 36000 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) |  | PMC | Project | 35000 | 53745 | [15 empty] | GL PMC
106 | 0900 - FF&E in Units | Range Queen |  | PMC | Project | 30240 | 0 | [15 empty] | GL PMC
122 | 1100- Specialties, Equipment & Furnishings | Pool furniture | Include additional tables/sitting areas | PMC | Project | 30000 | 4650 | [15 empty] | GL PMC
120 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | New gym equipment | PMC | Project | 30000 | 19034 | [15 empty] | GL PMC
16 | 0200 - Site Utilities & Improvements | Parking equipment | add 10 speed bumps | GC | Project | 28000 | 28000 | [15 empty] | GC assumed 100% @ budget
38 | 0200 - Site Utilities & Improvements | Carports / Garages | Replace 6 garage doors and paint garages | GC | Project | 28000 | 28000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
110 | 1100- Specialties, Equipment & Furnishings | Signage - entry | New Monument Sign at corner | PMC | Project | 25000 | 7329 | [15 empty] | GL PMC
123 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | Remove wall to enlarge gym area & install flooring/paint | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
70 | 0800 - Exterior Wall | Repair / replace wood siding | Added $8000 for paint to match | GC | Project | 24000 | 24000 | [15 empty] | GC assumed 100% @ budget
124 |  | Golf cart |  | AMN |  | 23000 | 0
80 | 0800 - Exterior Wall | Repair / replace wood trim | Added $7500 for paint to match | GC | Project | 22500 | 22500 | [15 empty] | GC assumed 100% @ budget
18 | 0200 - Site Utilities & Improvements | Sidewalks | repair cracked concrete | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
59 | 0700 - Roofing | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
53 | 0400 - Structure | Repair balcony framing & decking | Fill cracks in decking | GC | Project | 18500 | 18500 | [15 empty] | GC assumed 100% @ budget
14 | 0200 - Site Utilities & Improvements | Concrete pavement | Repair | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
29 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | repair dog park and Pool fences and paint | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
12 | 0200 - Site Utilities & Improvements | Storm sewer piping |  | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
140 | 1600 - Electrical | Electrical distribution | repair outside GFCI'S | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
118 | 1100- Specialties, Equipment & Furnishings | Audio systems | Speaker system for main pool area | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
111 | 1100- Specialties, Equipment & Furnishings | Signage - site | Bldg ID signs, common area signage | PMC | Project | 15000 | 4397 | [15 empty] | GL PMC
15 | 0200 - Site Utilities & Improvements | Stripe parking areas | Includes $5k for painting curbs at closing | GC | Project | 13000 | 13000 | [15 empty] | GC assumed 100% @ budget
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair Dumpsters and paint | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
64 | 0700 - Roofing | Gutters & downspouts | replace missing elbows and splash blocks | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
74 | 0800 - Exterior Wall | Dryer Vents | clean all dryer vents | GC | Project | 11760 | 11760 | [15 empty] | GC assumed 100% @ budget
81 | 0800 - Exterior Wall | Shutters | Added $3000 for paint to match | GC | Project | 10200 | 10200 | [15 empty] | GC assumed 100% @ budget
121 |  | Gym flooring |  | AMN |  | 10000 | 0
25 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | replace deck-o-seal in both pools | GC | Project | 9600 | 9600 | [15 empty] | GC assumed 100% @ budget
52 | 0400 - Structure | Repair exterior stair railings | Minor repairs to balconies | GC | Project | 7000 | 7000 | [15 empty] | GC assumed 100% @ budget
54 | 0400 - Structure | Repair patio/balcony railings | resecure | GC | Project | 7000 | 7000 | [15 empty] | GC assumed 100% @ budget
65 | 0700 - Roofing | Flashing |  | GC | Project | 5600 | 5600 | [15 empty] | GC assumed 100% @ budget
47 | 0400 - Structure | Wall framing |  | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2134360
|  |  | Capital Plan Total (ex-BTL) |  |  | 2134360
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 13496
BTL (dropped per Adam): $0

## Amalfi at Tuscan Lakes
Amalfi at Tuscan Lakes — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
88 |  | Unit Upgrade- Unit type 1AGe | 773sqft, 1BR 1BA | GC | Project | 540512 | 540512 | [15 empty] | GC assumed 100% @ budget
87 |  | Unit Upgrade- Unit type 1AGc | 684sqft, 1BR 1BA | GC | Project | 352224 | 352224 | [15 empty] | GC assumed 100% @ budget
77 |  | Exterior building | Paint community | GC | Project | 328000 | 328000 | [15 empty] | GC assumed 100% @ budget
91 |  | Unit Upgrade- Unit type 2CGl | 1117sqft, 2BR 2BA | GC | Project | 270127 | 270127 | [15 empty] | GC assumed 100% @ budget
90 |  | Unit Upgrade- Unit type 1AZh | 946sqft, 1BR 1BA | GC | Project | 249588 | 249588 | [15 empty] | GC assumed 100% @ budget
23 | 83303 | Landscaping | Landscaping for curb and pool (place Holder) | GC | Project | 150000 | 150000 | [15 empty] | GC assumed 100% @ budget
131 |  | Pool Remodel | New vertical tile on side of pool wall to replace aged blue Fire pit in raised area if feasible New grill area with cou | GC | Project | 100000 | 100000 | [15 empty] | GC assumed 100% @ budget
100 |  | Ceiling Fans | Add to all living rooms | GC | Project | 90200 | 90200 | [15 empty] | GC assumed 100% @ budget
124 |  | Clubhouse / Office Redecorate (FFE) |  | Unmarked | Project | 80000 | 63309 | [15 empty] | GL (unmarked scope)
21 | 83205 | Fences & gates - site perimeter | Remove vines, repair fence and paint fence | GC | Project | 60000 | 60000 | [15 empty] | GC assumed 100% @ budget
24 | 83100 | Resurface swimming pool | Resurface pool, Replace tile | GC | Project | 58000 | 58000 | [15 empty] | GC assumed 100% @ budget
89 |  | Unit Upgrade- Unit type 1AGg | 894sqft, 1BR 1BA | GC | Project | 50764 | 50764 | [15 empty] | GC assumed 100% @ budget
123 |  | Clubhouse / Office Remodel | Replace carpet tile, some paint and finish refresh | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
154 |  | Replace breezeway lights | Replace breezeway, Garage and landscaping lights | GC | Project | 49860 | 49860 | [15 empty] | GC assumed 100% @ budget
26 | 83100 | Replace swimming pool deck | Clean and recoat pool deck | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
133 |  | Pool furniture | New furniture for pool, repurpose and re-sling existing and move to Sorrento | Unmarked | Project | 45000 | 28892 | [15 empty] | GL (unmarked scope)
98 |  | Unit Upgrade- Unit type 3CGo | 1381sqft, 3BR 2BA | GC | Project | 39307 | 39307 | [15 empty] | GC assumed 100% @ budget
153 |  | Common area light fixtures | Replace all wall packs | GC | Project | 38640 | 38640 | [15 empty] | GC assumed 100% @ budget
95 |  | Unit Upgrade- Unit type 2CGn3 | 1271sqft, 2BR 2BA | GC | Project | 37596 | 37596 | [15 empty] | GC assumed 100% @ budget
92 |  | Unit Upgrade- Unit type 2CGn | 1247sqft, 2BR 2BA | GC | Project | 36836 | 36836 | [15 empty] | GC assumed 100% @ budget
19 | 83300 | Landscape irrigation | inspect and repair irrigation | GC | Project | 34000 | 34000 | [15 empty] | GC assumed 100% @ budget
34 | 83219 | Carport and garage | Repair carport damage and paint | GC | Project | 29000 | 29000 | [15 empty] | GC assumed 100% @ budget
79 |  | Shutters | Replace bad shutters | GC | Project | 28000 | 28000 | [15 empty] | GC assumed 100% @ budget
99 |  | Unit Upgrade- Unit type 3CGp | 1477sqft, 3BR 2BA | GC | Project | 27022 | 27022 | [15 empty] | GC assumed 100% @ budget
97 |  | Unit Upgrade- Unit type 2CGo1 | 1376sqft, 2BR 2BA | GC | Project | 26058 | 26058 | [15 empty] | GC assumed 100% @ budget
94 |  | Unit Upgrade- Unit type 2CGn2 | 1259sqft, 2BR 2BA | GC | Project | 24866 | 24866 | [15 empty] | GC assumed 100% @ budget
93 |  | Unit Upgrade- Unit type 2CGn1 | 1256sqft, 2BR 2BA | GC | Project | 24734 | 24734 | [15 empty] | GC assumed 100% @ budget
149 |  | Dryer Vent cleaning |  | GC | Project | 24600 | 24600 | [15 empty] | GC assumed 100% @ budget
58 | 83202 | Asphalt composite shingle roofing | minor roof repairs | GC | Project | 23000 | 23000 | [15 empty] | GC assumed 100% @ budget
63 | 83439 | Gutters & downspouts | Clean down spouts and gutters | GC | Project | 23000 | 23000 | [15 empty] | GC assumed 100% @ budget
76 |  | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | GC | Project | 23000 | 23000 | [15 empty] | GC assumed 100% @ budget
78 |  | Repair / replace wood trim |  | GC | Project | 23000 | 23000 | [15 empty] | GC assumed 100% @ budget
25 | 83100 | Replace swimming pool coping | Replace deck-o-seal on pool and repair coping | GC | Project | 21000 | 21000 | [15 empty] | GC assumed 100% @ budget
75 |  | Repair stucco |  | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
127 |  | Mailboxes | Package locker or Fetch system needed | Unmarked | Project | 20000 | 0 | [15 empty] | GL (unmarked scope)
129 |  | Security Camera System | Need at least for entry drive, clubhouse, and amenity coverage | Unmarked | Project | 20000 | 7426 | [15 empty] | GL (unmarked scope)
152 |  | Fire and Sprinklers | replace emergency lights | GC | Project | 18560 | 18560 | [15 empty] | GC assumed 100% @ budget
14 | 83221 | Concrete pavement |  | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
30 | 83206 | Pergola | repair and stain all pergola | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
53 | 83104 | Repair balcony framing & decking | repair balcony band boards | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
65 | 83206 | Sealants & caulking |  | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
132 |  | Fitness Equipment | 2 Ellipticals, other allowance for repairs and new equipment | Unmarked | Project | 18000 | 11961 | [15 empty] | GL (unmarked scope)
15 | 83201 | Stripe parking areas |  | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
35 | 83111 | Dumpster enclosures | Repair dumpster enclosures | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
55 | 83206 | Expansion Joints | clean and seal expansion joints | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
128 |  | Fountain area Remodel | Address planter- either fill with rocks or fix irrigation Look at cabanas or shade over benches by reflecting pond Lock | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
70 |  | Repair / replace cement fiber siding | repair damaged siding | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
134 |  | Fitness center renovation | Add mirrors, 1-2 TVs | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
29 | 83205 | Fences & gates - swimming pool | Repair and paint pool fence | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
151 |  | Electrical distribution |  | GC | Project | 8500 | 8500 | [15 empty] | GC assumed 100% @ budget
52 | 83114 | Repair exterior stair railings | secure railings | GC | Project | 8300 | 8300 | [15 empty] | GC assumed 100% @ budget
54 | 83114 | Repair patio/balcony railings | secure railings | GC | Project | 8300 | 8300 | [15 empty] | GC assumed 100% @ budget
130 |  | EV Chargers | Likely will be no-cost to property, but providing allowance | Unmarked | Project | 8000 | 0 | [15 empty] | GL (unmarked scope)
135 |  | Golf Cart | Utility/Maintenance Cart | Unmarked | Project | 8000 | 0 | [15 empty] | GL (unmarked scope)
17 | 83520 | ADA parking & curb cuts |  | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
125 |  | Model Unit | Allowance for small additions/refresh | Unmarked | Project | 4000 | 8256 | [15 empty] | GL (unmarked scope)
126 |  | Computers | Not needed, allowance for 1 | Unmarked | Project | 1500 | 1817 | [15 empty] | GL (unmarked scope)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 3314095
|  |  | Contingency |  |  | 171121
|  |  | Contingency |  |  | 108322
|  |  | Capital Plan Total (ex-BTL) |  |  | 3593538
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 160723
BTL (dropped per Adam): $0

## Avila
Avila — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
67 |  | Exterior building |  | GC | Project | 400000 | 400000 | [15 empty] | GC assumed 100% @ budget
12 |  | Pavement |  | GC | Project | 150000 | 150000 | [15 empty] | GC assumed 100% @ budget
76 |  | Picnic Area Renovation |  | GC | Project | 150000 | 150000 | [15 empty] | GC assumed 100% @ budget
14 |  | Asphalt coating |  | GC | Project | 98000 | 98000 | [15 empty] | GC assumed 100% @ budget
37 |  | Jack & underpin foundations |  | GC | Project | 72000 | 72000 | [15 empty] | GC assumed 100% @ budget
58 |  | Repair / replace wood siding |  | GC | Project | 66000 | 66000 | [15 empty] | GC assumed 100% @ budget
17 |  | Landscape irrigation |  | GC | Project | 49000 | 49000 | [15 empty] | GC assumed 100% @ budget
10 |  | Storm sewer piping |  | GC | Project | 38800 | 38800 | [15 empty] | GC assumed 100% @ budget
87 |  | Common area light fixtures |  | GC | Project | 32400 | 32400 | [15 empty] | GC assumed 100% @ budget
33 |  | Carport and garage |  | GC | Project | 31000 | 31000 | [15 empty] | GC assumed 100% @ budget
18 |  | Erosion control |  | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
44 |  | Repair exterior stair treads and stringe |  | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
45 |  | Repair exterior stair railings |  | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
78 |  | Old Pool House by Pool 1 (West) |  | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
68 |  | Repair / replace wood trim |  | GC | Project | 28000 | 28000 | [15 empty] | GC assumed 100% @ budget
72 |  | Fire protection | 327 | GC | Project | 24525 | 24525 | [15 empty] | GC assumed 100% @ budget
49 |  | Asphalt composite shingle roofing |  | GC | Project | 23000 | 23000 | [15 empty] | GC assumed 100% @ budget
54 |  | Gutters & downspouts |  | GC | Project | 23000 | 23000 | [15 empty] | GC assumed 100% @ budget
63 |  | Tuck-pointing |  | GC | Project | 23000 | 23000 | [15 empty] | GC assumed 100% @ budget
86 |  | Electrical distribution |  | GC | Project | 22800 | 22800 | [15 empty] | GC assumed 100% @ budget
34 |  | Dumpster enclosures |  | GC | Project | 21000 | 21000 | [15 empty] | GC assumed 100% @ budget
46 |  | Repair balcony framing & decking |  | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
69 |  | storage room doors - exterior |  | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
80 |  | Dog Park |  | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
39 |  | Concrete deck / floor fill |  | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
75 |  | Clubhouse / Office Redecorate (FFE) |  | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
20 |  | Retaining walls |  | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
13 |  | Stripe parking areas |  | GC | Project | 13000 | 13000 | [15 empty] | GC assumed 100% @ budget
55 |  | Flashing |  | GC | Project | 11000 | 11000 | [15 empty] | GC assumed 100% @ budget
77 |  | Pool 1 (West) Renovation |  | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
27 |  | Fences & gates |  | GC | Project | 9600 | 9600 | [15 empty] | GC assumed 100% @ budget
23 |  | Replace swimming pool coping |  | GC | Project | 8600 | 8600 | [15 empty] | GC assumed 100% @ budget
16 |  | Sidewalks |  | GC | Project | 8400 | 8400 | [15 empty] | GC assumed 100% @ budget
56 |  | Sealants & caulking and paint |  | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
15 |  | ADA parking & curb cuts |  | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
25 |  | Repair / replace swimming pool pumps |  | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
47 |  | Repair patio/balcony railings |  | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
79 |  | Pool 2 (East) Renovation |  | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
35 |  | Maintenance Structure |  | GC | Project | 2500 | 2500 | [15 empty] | GC assumed 100% @ budget
40 |  | Wall framing |  | GC | Project | 1500 | 1500 | [15 empty] | GC assumed 100% @ budget
71 |  | Unit Repair |  | GC | Project | 1500 | 1500 | [15 empty] | GC assumed 100% @ budget
11 |  | Parking Equipment- wheel stops |  | GC | Project | 750 | 750 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1578975
|  |  | Capital Plan Total (ex-BTL) |  |  | 1578975
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 53449
BTL (dropped per Adam): $0

## Collin Creek
Collin Creek — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
90 | 0900 - FF&E in Units | Interior Update- Classic to Gold | Test smaller initial qty | PMC | Project | 500000 | 255167 | [15 empty] | GL PMC
91 | 0900 - FF&E in Units | Interior Update- Silver to Gold | Test smaller initial qty | PMC | Project | 450000 | 229651 | [15 empty] | GL PMC
80 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Project | 320000 | 320000 | [15 empty] | GC assumed 100% @ budget
42 | 0300 - Excavation & Foundations | Foundations | Additional scope identified by TAM | GC | Project | 172728 | 172728 | [15 empty] | GC assumed 100% @ budget
41 | 0300 - Excavation & Foundations | Jack & underpin foundations | Place holder for 5 building that show signs of foundation movement | GC | Project | 150000 | 150000 | [15 empty] | GC assumed 100% @ budget
22 | 0200 - Site Utilities & Improvements | Retaining walls | Replace railroad tie retaining walls | GC | Project | 120000 | 120000 | [15 empty] | GC assumed 100% @ budget
23 | 0200 - Site Utilities & Improvements | Landscaping | Trim Trees and sod building with erosion | GC | Project | 72000 | 72000 | [15 empty] | GC assumed 100% @ budget
28 | 0200 - Site Utilities & Improvements | Replace swimming pool deck- Primary pool | New decking to replace aggregate | GC | Project | 70000 | 70000 | [15 empty] | GC assumed 100% @ budget
135 | 1100- Specialties, Equipment & Furnishings | Package lockers | Luxer one- from Texas Package Solutions | PMC | Project | 70000 | 0 | [15 empty] | GL PMC
81 | 0800 - Exterior Wall | Repair / replace wood trim |  | GC | Project | 51000 | 51000 | [15 empty] | GC assumed 100% @ budget
48 | 0400 - Structure | Wall framing | Replace damaged gable vents and balcony structure | GC | Project | 43000 | 43000 | [15 empty] | GC assumed 100% @ budget
130 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | New exterior windows New flooring-rubber tiles Paint Ventilation/fans Electrical to doors for key Relocate TV above aero | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
14 | 0200 - Site Utilities & Improvements | Concrete pavement | repair pot holes and broken sidewalks | GC | Project | 39000 | 39000 | [15 empty] | GC assumed 100% @ budget
60 | 0700 - Roofing | Asphalt composite shingle roofing | minor roof repairs | GC | Project | 36000 | 36000 | [15 empty] | GC assumed 100% @ budget
127 | 1100- Specialties, Equipment & Furnishings | Pool enhancements- Primary Pool | 110 & 55 sqft of turf 2 corn hole boards w/custom logo chess/checkers shade structure Budget | PMC | Project | 36000 | 2899 | [15 empty] | GL PMC
123 | 1100- Specialties, Equipment & Furnishings | Gym Fitness Equipment | Upgraded package from Comm FIT, Basic also available fo $20k | PMC | Project | 34000 | 13734 | [15 empty] | GL PMC
20 | 0200 - Site Utilities & Improvements | Erosion control |  | GC | Project | 31000 | 31000 | [15 empty] | GC assumed 100% @ budget
26 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface pool | GC | Project | 31000 | 31000 | [15 empty] | GC assumed 100% @ budget
128 | 1100- Specialties, Equipment & Furnishings | Pool enhancements- Secondary Pool | New grill New fire pit Convert planters next to pool to turf or pavers | PMC | Project | 30000 | 2415 | [15 empty] | GL PMC
110 | 0900 - FF&E in Units | Range Queen |  | GC | Project | 29830 | 29830 | [15 empty] | GC assumed 100% @ budget
155 | 1600 - Electrical | Common area light fixtures |  | GC | Project | 29000 | 29000 | [15 empty] | GC assumed 100% @ budget
18 | 0200 - Site Utilities & Improvements | Sidewalks |  | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
156 | 1600 - Electrical | Replace breezeway lights |  | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
51 | 0400 - Structure | Roof deck | replace bad decking on roofs | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
125 | 1100- Specialties, Equipment & Furnishings | Pool furniture- Primary Pool |  | PMC | Project | 25000 | 27009 | [15 empty] | GL PMC
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Dumpster enclosures are scrubs replace with fencing and repair gates | GC | Project | 21000 | 21000 | [15 empty] | GC assumed 100% @ budget
24 | 0200 - Site Utilities & Improvements | Landscaping- Primary pool area | Turf or other plants instead of brown mulch and boxwood hedges in planters | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
65 | 0700 - Roofing | Gutters & downspouts | Clean down spouts and gutters | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
134 | 1100- Specialties, Equipment & Furnishings | Dog Park entrance area | Convert entry area to concrete. Adjust entry level to avoid erosion/wash out and raise gate to avoid contact with ground | GC | Project | 17000 | 17000 | [15 empty] | GC assumed 100% @ budget
76 | 0800 - Exterior Wall | Tuck-pointing |  | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
57 | 0400 - Structure | Expansion joints | clean and seal expansion joints | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
72 | 0800 - Exterior Wall | Repair / replace cement fiber siding | repair damaged siding | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
124 | 1100- Specialties, Equipment & Furnishings | Gym Flooring | Fitdek 8mm roll with install- Quotation # S07142 from Comm FIT | PMC | Project | 11000 | 1957 | [15 empty] | GL PMC
136 | 1100- Specialties, Equipment & Furnishings | Sport court surfacing |  | GC | Project | 11000 | 11000 | [15 empty] | GC assumed 100% @ budget
25 | 0200 - Site Utilities & Improvements | Landscaping- Secondary pool area | Areas by pool- new sod | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
39 | 0200 - Site Utilities & Improvements | Radon Remediation from lender report | Radon mitigation should be completed by a Texas-licensed contractor. When radon remains elevated over the EPA Action Lev | PMC | Project | 10000 | 40580 | [15 empty] | GL PMC
34 | 0200 - Site Utilities & Improvements | Playground equipment | Replace Fall zone in play ground | GC | Project | 9800 | 9800 | [15 empty] | GC assumed 100% @ budget
54 | 0400 - Structure | Repair balcony framing & decking | repair balcony band boards | GC | Project | 9700 | 9700 | [15 empty] | GC assumed 100% @ budget
15 | 0200 - Site Utilities & Improvements | Stripe parking areas |  | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
67 | 0700 - Roofing | Sealants & caulking and paint |  | GC | Project | 9000 | 9000 | [15 empty] | GC assumed 100% @ budget
35 | 0200 - Site Utilities & Improvements | Picnic areas | replace 2 grills | GC | Project | 8800 | 8800 | [15 empty] | GC assumed 100% @ budget
12 | 0200 - Site Utilities & Improvements | Storm sewer piping | clean out storm drain boxes | GC | Project | 8600 | 8600 | [15 empty] | GC assumed 100% @ budget
27 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Replace deck-o-seal on pool | GC | Project | 8600 | 8600 | [15 empty] | GC assumed 100% @ budget
137 | 1100- Specialties, Equipment & Furnishings | Gym hallway & Restrooms | Paint Toilets/fixtures New cove base Base | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
78 | 0800 - Exterior Wall | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts |  | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
129 | 1100- Specialties, Equipment & Furnishings | Pool area lighting fixtures | Update pole lighting- new fixtures on top and straighten poles | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
153 | 1600 - Electrical | Electrical distribution |  | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
31 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair and paint pool fences | GC | Project | 5600 | 5600 | [15 empty] | GC assumed 100% @ budget
133 | 1100- Specialties, Equipment & Furnishings | Dog Park upgrades | Move square dog jump paint jumps Wash station for dogs | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
53 | 0400 - Structure | Repair exterior stair railings | secure railings | GC | Project | 4200 | 4200 | [15 empty] | GC assumed 100% @ budget
55 | 0400 - Structure | Repair patio/balcony railings | secure railings | GC | Project | 4200 | 4200 | [15 empty] | GC assumed 100% @ budget
32 | 0200 - Site Utilities & Improvements | Pergola | repair and stain all pergola | GC | Project | 3100 | 3100 | [15 empty] | GC assumed 100% @ budget
132 | 1100- Specialties, Equipment & Furnishings | Laundry room furniture | Furniture in waiting area | PMC | Project | 2000 | 0 | [15 empty] | GL PMC
131 | 1100- Specialties, Equipment & Furnishings | Laundry room | Built in table instead of floating tables Replace broken window | GC | Project | 1500 | 1500 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2763458
|  |  | Contingency |  |  | 104542
|  |  | Contingency |  |  | 290000
|  |  | Contingency |  |  | 610000
|  |  | Capital Plan Total (ex-BTL) |  |  | 3768000
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 92406
BTL (dropped per Adam): $0

## Las Colinas Heights
Las Colinas Heights — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
109 | 0900 - FF&E in Units | PFC Units |  | PMC | Project | 1600000 | 0 | [15 empty] | GL PMC
93 | 0900 - FF&E in Units | Platinum upgrades |  | PMC | Project | 650000 | 886629 | [15 empty] | GL PMC
83 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Project | 595000 | 595000 | [15 empty] | GC assumed 100% @ budget
42 | 0200 - Site Utilities & Improvements | Las Colinas Association Estoppel Repairs | See list on separate tab | GC | Project | 330550 | 330550 | [15 empty] | GC assumed 100% @ budget
12 | 0200 - Site Utilities & Improvements | Storm sewer piping | clear storm drains, repair drains around pool two, clean and service lift pumps, install drainage is sub-terrain units | GC | Project | 225000 | 225000 | [15 empty] | GC assumed 100% @ budget
45 | 0300 - Excavation & Foundations | Jack & underpin foundations | Buildings 5,11,14,21,19,36,24,6,9,13,19,26 From PCA- $5,000- The foundation exhibits settlement/step cracking in the ext | GC | Project | 199985 | 199985 | [15 empty] | GC assumed 100% @ budget
29 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | Remove and replace pool deck on two of four pools add missing expansion boards on remaining two pools | GC | Project | 160000 | 160000 | [15 empty] | GC assumed 100% @ budget
43 | 0200 - Site Utilities & Improvements | Creek | Clean, and service fountain's in creek | GC | Project | 100000 | 100000 | [15 empty] | GC assumed 100% @ budget
145 | 1100- Specialties, Equipment & Furnishings | Pool area amenities- 2 pools |  | PMC | Project | 100000 | 4808 | [15 empty] | GL PMC
14 | 0200 - Site Utilities & Improvements | Concrete pavement | Repair concrete drive From PCA- $3,750- Isolated sections of the concrete pavement were observed to be cracked, settled, | GC | Project | 94000 | 94000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Sidewalks | replace missing expansion boards in sidewalks From PCA- $7,000- Several of the Subject's concrete sidewalk sections hav | GC | Project | 75000 | 75000 | [15 empty] | GC assumed 100% @ budget
65 | 0700 - Roofing | Tile roofing | remove and reset or replace clay tiles on 30 buildings | GC | Project | 65000 | 65000 | [15 empty] | GC assumed 100% @ budget
27 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface two of four pools | GC | Project | 61000 | 61000 | [15 empty] | GC assumed 100% @ budget
21 | 0200 - Site Utilities & Improvements | Erosion control | add dirt around each building | GC | Project | 60000 | 60000 | [15 empty] | GC assumed 100% @ budget
22 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Repair fence, columns and paint From PCA- $1,000- The concrete fencing on the southwest side was observed to be damaged | GC | Project | 51300 | 51300 | [15 empty] | GC assumed 100% @ budget
36 | 0200 - Site Utilities & Improvements | WDO Treatment | From PCA- Subsequent to the Site Visit a WDO inspection was conducted by Terminix Commercial on 2/3/23. Evidence of acti | PMC | Project | 51112 | 15586 | [15 empty] | GL PMC
129 | 0900 - FF&E in Units | Range Queen | Fire stops | GC | Project | 50985 | 50985 | [15 empty] | GC assumed 100% @ budget
143 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment |  | PMC | Project | 50000 | 50321 | [15 empty] | GL PMC
20 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
80 | 0800 - Exterior Wall | Repair stucco | repair cracked stucco | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
84 | 0800 - Exterior Wall | Repair / replace wood trim | From PCA- $1,000- The wood siding at buildings #10 and #12 was observed to be damaged. | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
26 | 0200 - Site Utilities & Improvements | Landscaping | Tree trim | GC | Project | 42000 | 42000 | [15 empty] | GC assumed 100% @ budget
170 | 1600 - Electrical | Replace breezeway lights | change breezeway lights to LED | GC | Project | 42000 | 42000 | [15 empty] | GC assumed 100% @ budget
137 | 1100- Specialties, Equipment & Furnishings | Clubhouse Furniture |  | PMC | Project | 40000 | 2946 | [15 empty] | GL PMC
144 | 1100- Specialties, Equipment & Furnishings | Pool furniture | To include installation of cabanas | PMC | Project | 40000 | 0 | [15 empty] | GL PMC
41 | 0200 - Site Utilities & Improvements | Carports / Garages | repair Car ports From PCA- $750- The metal carport by building #12 was observed to be damaged. | GC | Project | 36000 | 36000 | [15 empty] | GC assumed 100% @ budget
169 | 1600 - Electrical | Common area light fixtures | Change all 8 ft pole lights to LED | GC | Project | 36000 | 36000 | [15 empty] | GC assumed 100% @ budget
25 | 0200 - Site Utilities & Improvements | Retaining walls | repair cracks in retaining walls From PCA- $1,000- The retaining walls are in generally good condition, but there are se | GC | Project | 35600 | 35600 | [15 empty] | GC assumed 100% @ budget
141 | 1100- Specialties, Equipment & Furnishings | Audio systems |  | PMC | Project | 30000 | 0 | [15 empty] | GL PMC
155 | 1400 - Plumbing | Plumbing- General | 6 buildings with leaks | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
50 | 0400 - Structure | Concrete deck / floor fill | fill cracks in breezeways | GC | Project | 29000 | 29000 | [15 empty] | GC assumed 100% @ budget
55 | 0400 - Structure | Repair exterior stair treads and stringe |  | GC | Project | 29000 | 29000 | [15 empty] | GC assumed 100% @ budget
68 | 0700 - Roofing | Gutters & downspouts | clean and repin From PCA- $2,000- some of the metal gutters and the metal leaders of building #26 were observed to be d | GC | Project | 29000 | 29000 | [15 empty] | GC assumed 100% @ budget
77 | 0800 - Exterior Wall | Soffit repairs | repair damaged soffits | GC | Project | 29000 | 29000 | [15 empty] | GC assumed 100% @ budget
28 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | replace deck-o-seal on four pools | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
136 | 1100- Specialties, Equipment & Furnishings | Clubhouse Renovation | Hide cabling Look at replacing hexagonal mirrored tile on walls Kitchen upgrades? | PMC | Project | 25000 | 1720 | [15 empty] | GL PMC
32 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair Pool fence and paint | GC | Project | 24000 | 24000 | [15 empty] | GC assumed 100% @ budget
167 | 1600 - Electrical | Install CO Detector | From PCA- $12,950- Carbon Monoxide detectors were not observed as required. | GC | Project | 23310 | 23310 | [15 empty] | GC assumed 100% @ budget
128 | 0900 - FF&E in Units | Dryer Vents | Clean dryer vents | GC | Project | 23175 | 23175 | [15 empty] | GC assumed 100% @ budget
16 | 0200 - Site Utilities & Improvements | Parking equipment | add parking stops by fencing | GC | Project | 22000 | 22000 | [15 empty] | GC assumed 100% @ budget
23 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Fix Entrance Gates & Access Control | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
51 | 0400 - Structure | Roof pad |  | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
146 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | New flooring- rubber or epoxy | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
39 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair Dumpsters and paint | GC | Project | 19800 | 19800 | [15 empty] | GC assumed 100% @ budget
130 | 0900 - FF&E in Units | Install GFCI outlet in wet areas | From PCA- $11,750- 50% of the bathrooms of 2-bedroom units had Non-GFCI outlets. | GC | Project | 17625 | 17625 | [15 empty] | GC assumed 100% @ budget
54 | 0400 - Structure | Roof deck | replace decking and underlayment on roofs | GC | Project | 17500 | 17500 | [15 empty] | GC assumed 100% @ budget
30 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | inspect and repair/replace pool pumps | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
56 | 0400 - Structure | Repair exterior stair railings |  | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
57 | 0400 - Structure | Repair balcony framing & decking | repair 5 balconies | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
58 | 0400 - Structure | Repair patio/balcony railings | secure all railings | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
69 | 0700 - Roofing | Flashing | replace rotted flashing on doghouse meter rooms | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
70 | 0700 - Roofing | Sealants & caulking and paint |  | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
15 | 0200 - Site Utilities & Improvements | Stripe parking areas |  | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
52 | 0400 - Structure | Roof framing |  | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
135 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | repair and stain office catwalk balcony | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
127 | 0900 - FF&E in Units | Down Units | From PCA- $10,000- At the time of the site visit, 1 down unit (unit #4335) was observed due to subflooring damage accord | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
123 | 0900 - FF&E in Units | Repair Leaking at Unit Interiors | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 676 - evidence of a major lea | PMC | Project | 8500 | 56593 | [15 empty] | GL PMC
34 | 0200 - Site Utilities & Improvements | Pool Area repairs | From PCA- $7,000- The walls and ceilings of the swimming pool equipment rooms were observed to be damaged. The restrooms | GC | Project | 7000 | 7000 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts | add proper signage | GC | Project | 5600 | 5600 | [15 empty] | GC assumed 100% @ budget
163 | 1600 - Electrical | Electrical distribution | From PCA- $1,000- The Electrical Panel in the swimming pool equipment by the leasing office was observed to be without c | GC | Project | 5200 | 5200 | [15 empty] | GC assumed 100% @ budget
24 | 0200 - Site Utilities & Improvements | Access Control | Need more fobs, repair hardware & need software to program | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
168 | 1600 - Electrical | Fire suppression | From PCA- $2,000- No fire extinguishers were observed in any visited units. | GC | Project | 2500 | 2500 | [15 empty] | GC assumed 100% @ budget
125 | 0900 - FF&E in Units | Remove interior mold | From PCA- $2,000- CBRE observed conspicuous mold growth in the areas identified as walls and ceiling of the living room | PMC | Project | 2000 | 13316 | [15 empty] | GL PMC
165 | 1600 - Electrical | Fix/ test the fire riser | From PCA- $2,000- The fire sprinkler riser in building #10 has a red inspection tag. | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
18 | 0200 - Site Utilities & Improvements | Curbs & gutters | Sections of the concrete curbing were noted to be chipped, spalled, and damaged. Such sections were noted by the mainten | GC | Project | 1500 | 1500 | [15 empty] | GC assumed 100% @ budget
126 | 0900 - FF&E in Units | Remove Interior Mold in Unit 3951 | From PCA- $1,000- Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 3951 - majo | PMC | Project | 1000 | 6658 | [15 empty] | GL PMC
166 | 1600 - Electrical | Fix the fire alarm panel | From PCA- $1,000- A trouble indicator light was noted at the fire alarm panel of building #5. | GC | Project | 1000 | 1000 | [15 empty] | GC assumed 100% @ budget
164 | 1600 - Electrical | Switchgear/metering | From PCA- $700- The Electrical Panels in the swimming pool equipment by the leasing office and in the electrical room of | GC | Project | 700 | 700 | [15 empty] | GC assumed 100% @ budget
124 | 0900 - FF&E in Units | Fix Broken handrail in Unit 4425 | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 4425 - Handrail is broken and | PMC | Project | 500 | 0 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 5539442
|  |  | Contingency |  |  | 162465
|  |  | Capital Plan Total (ex-BTL) |  |  | 5701907
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 398037
BTL (dropped per Adam): $0

## Oak Forest
Oak Forest — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
79 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Project | 686000 | 686000 | [15 empty] | GC assumed 100% @ budget
119 | 1100- Specialties, Equipment & Furnishings | Video systems |  | PMC | Project | 250000 | 40715 | [15 empty] | GL PMC
21 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Repair and paint wooden fence and replace sections of damaged metal fence, Repair gate operators and ped gate closers | GC | Project | 185000 | 185000 | [15 empty] | GC assumed 100% @ budget
108 | 0900 - FF&E in Units | Washer/dryer |  | PMC | Project | 130000 | 0 | [15 empty] | GL PMC
23 | 0200 - Site Utilities & Improvements | Landscaping | Trim Trees and remove dead bushes | GC | Project | 85000 | 85000 | [15 empty] | GC assumed 100% @ budget
24 | 0200 - Site Utilities & Improvements | Resurface swimming pool | Resurface three pools with pebble tech plaster | GC | Project | 81000 | 81000 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | New clubhouse furniture | PMC | Project | 80000 | 59297 | [15 empty] | GL PMC
122 | 1100- Specialties, Equipment & Furnishings | Pool area enhancements | Address pool inspection items, upgraded pool deck | PMC | Project | 80000 | 23295 | [15 empty] | GL PMC
143 | 1600 - Electrical | Fire and Sprinklers | replace painted heads in units From PCA- $68,000- The fire and life safety system appeared to be in overall fair to ave | GC | Project | 68000 | 68000 | [15 empty] | GC assumed 100% @ budget
107 | 0900 - FF&E in Units | Range Queen | Fire stops | GC | Project | 66120 | 66120 | [15 empty] | GC assumed 100% @ budget
14 | 0200 - Site Utilities & Improvements | Concrete pavement | repair pot holes and broken sidewalks | GC | Project | 62000 | 62000 | [15 empty] | GC assumed 100% @ budget
47 | 0400 - Structure | Wall framing | Replace damaged gable vents and balcony structure | GC | Project | 62000 | 62000 | [15 empty] | GC assumed 100% @ budget
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Paint accent walls Create built in desk/counter Add glass wall and door to back right office for tenant discussions | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
80 | 0800 - Exterior Wall | Repair / replace wood trim |  | GC | Project | 48000 | 48000 | [15 empty] | GC assumed 100% @ budget
35 | 0200 - Site Utilities & Improvements | Carport and garage | Repair carport damage | GC | Project | 39000 | 39000 | [15 empty] | GC assumed 100% @ budget
59 | 0700 - Roofing | Asphalt composite shingle roofing | minor roof repairs | GC | Project | 38000 | 38000 | [15 empty] | GC assumed 100% @ budget
64 | 0700 - Roofing | Gutters & downspouts | Clean down spouts and gutters | GC | Project | 38000 | 38000 | [15 empty] | GC assumed 100% @ budget
76 | 0800 - Exterior Wall | Repair stucco |  | GC | Project | 38000 | 38000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | Inspect and repair irrigation. From PCA- $34,000- The landscaping and irrigation systems appeared to be in fair to ave | GC | Project | 34000 | 34000 | [15 empty] | GC assumed 100% @ budget
74 | 0800 - Exterior Wall | Dryer Vents | Clean dryer vents ($45@) & Vent cover replacements as needed ($3000) | GC | Project | 34000 | 34000 | [15 empty] | GC assumed 100% @ budget
77 | 0800 - Exterior Wall | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | GC | Project | 32000 | 32000 | [15 empty] | GC assumed 100% @ budget
20 | 0200 - Site Utilities & Improvements | Erosion control | From PCA- $25,500- Management reported erosion repairs in 2022, and Blackstone observed new rock groundcover at several | GC | Project | 31000 | 31000 | [15 empty] | GC assumed 100% @ budget
33 | 0200 - Site Utilities & Improvements | Picnic areas | replace 8 grills | GC | Project | 31000 | 31000 | [15 empty] | GC assumed 100% @ budget
120 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment |  | PMC | Project | 30000 | 42136 | [15 empty] | GL PMC
121 | 1100- Specialties, Equipment & Furnishings | Pool furniture- Office Pool | New furniture for office pool area only, repurpose existing good furniture to other 2 pools | PMC | Project | 30000 | 49605 | [15 empty] | GL PMC
18 | 0200 - Site Utilities & Improvements | Sidewalks | From PCA- $5,000- The concrete sidewalks and flatwork were observed to be in overall fair to good condition. Blackstone | GC | Project | 24000 | 24000 | [15 empty] | GC assumed 100% @ budget
25 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Replace deck-o-seal on pools | GC | Project | 21000 | 21000 | [15 empty] | GC assumed 100% @ budget
22 | 0200 - Site Utilities & Improvements | Retaining walls | Tuck Point retaining walls From PCA- $5,000- Blackstone observed cracking and/or missing stone components at retaining w | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
123 | 1100- Specialties, Equipment & Furnishings | Pool area enhancements | Activities, turf, etc | PMC | Project | 20000 | 0 | [15 empty] | GL PMC
30 | 0200 - Site Utilities & Improvements | Pergola | repair and stain all pergolas | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
53 | 0400 - Structure | Repair balcony framing & decking | repair balcony band boards | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
66 | 0700 - Roofing | Sealants & caulking and paint |  | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
29 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair and paint pool fences | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair dumpster enclosures | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
12 | 0200 - Site Utilities & Improvements | Storm sewer piping | clean out storm drain boxes | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
15 | 0200 - Site Utilities & Improvements | Stripe parking areas |  | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
32 | 0200 - Site Utilities & Improvements | Playground equipment | Replace Fall zone in play ground | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
55 | 0400 - Structure | Repair catwalks | clean and seal expansion joints | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
70 | 0800 - Exterior Wall | Repair / replace wood siding | repair damaged siding | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
75 | 0800 - Exterior Wall | Tuck-pointing |  | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
106 | 0900 - FF&E in Units | Radon Mitigation Systems: | Lender Mandate- In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the | PMC | Project | 10500 | 0 | [15 empty] | GL PMC
50 | 0400 - Structure | Roof deck | replace bad decking on roofs | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
52 | 0400 - Structure | Repair exterior stair railings | secure railings | GC | Project | 8300 | 8300 | [15 empty] | GC assumed 100% @ budget
54 | 0400 - Structure | Repair patio/balcony railings | secure railings | GC | Project | 8300 | 8300 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts |  | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
124 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | Close 2-3 wall openings between gym and bathroom hallway | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
125 | 1100- Specialties, Equipment & Furnishings | Fitness center adjacent restroom upgrade | Repair/replace partitions, touch up paint and base | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
105 | 0900 - FF&E in Units | Mold remediation | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan c | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2613720
|  |  | Contingency |  |  | 100000
|  |  | Contingency |  |  | 996280
|  |  | Contingency |  |  | 466000
|  |  | Contingency |  |  | 2784000
|  |  | Capital Plan Total (ex-BTL) |  |  | 6960000
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 156655
BTL (dropped per Adam): $0

## Oak Park
Oak Park — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
37 | Exterior Building & Site Work | Exterior Paint, Carpentry & Misc Repairs | Bldg. paint looks to be in good shape. Last painted 2017. Need to paint all metal except doors yr1 $201k. Pick and pull | Unmarked | Project | 1059500 | 938581 | [15 empty] | GL (unmarked scope)
69 | MEP | HVAC Equipment (HVAC FULL NEW REPLACEMEN | Based on eval from SRT there are 368 R22/Mixed refrigerant systems. Researching run rates for MT and AW I came up with a | Unmarked | Project | 646160 | 639431 | [15 empty] | GL (unmarked scope)
58 | Interior Units | Vacant Unit Deferred Maintenance |  | Unmarked | Project | 500000 | 117730 | [15 empty] | GL (unmarked scope)
76 | MEP | Water Piping & Plumbing | Replace (27 pairs) building valves that are barried, rusted, and don’t work $46k. unit 516 had an external repipe that n | Unmarked | Project | 401000 | 198926 | [15 empty] | GL (unmarked scope)
71 | MEP | Panel Replacement/GFCI | PH2 has Zinsco panels in all units. Need to replace breakers $346k. Per bid from Shields Electrical Services. 296 units | Unmarked | Project | 346005 | 383245 | [15 empty] | GL (unmarked scope)
22 | Common Area | Pool Area Repairs & Equipment | Replaster both pools at leasing offfice pool, refresh grill/pergola area, and repair expansion joints on deck replace gr | Unmarked | Project | 342164 | 454979 | [15 empty] | GL (unmarked scope)
70 | MEP | HVAC PM | Dryer vent cleaning 75/unit $45k. Replace dryer vents 65 ea. PM all a/c units $120k this include pm service and some par | Unmarked | Project | 341470 | 110179 | [15 empty] | GL (unmarked scope)
74 | MEP | Sewer Systems | Repairs sewer blockages and breaks. bldgs1,2,4,5,6,7,10,12,13,14,15,16,21,26 Bid from SRT. Also researched run rates on | Unmarked | Project | 253000 | 2334 | [15 empty] | GL (unmarked scope)
27 | Exterior Building & Site Work | Balconies | Rebuild 12 balconies called out by gc $68k. Pick and pull other balcony and land structural members including replacemen | Unmarked | Project | 243600 | 148350 | [15 empty] | GL (unmarked scope)
26 | Exterior Building & Site Work | Asphalt Milling/Paving/Sealcoat | Restripe some areas in Y1. Y2 fix major potholes and restripe after | Unmarked | Project | 243500 | 105364 | [15 empty] | GL (unmarked scope)
52 | Exterior Building & Site Work | Sports Court | See sports court taband add $25K for iron fence between soccer field and social area | Unmarked | Project | 227000 | 514328 | [15 empty] | GL (unmarked scope)
80 | Miscellaneous | Environmental - Asbestos Abatement | For as needed abatement Ph1 only | Unmarked | Project | 210000 | 122414 | [15 empty] | GL (unmarked scope)
54 | Exterior Building & Site Work | Tree/Plant Removal | Cut life safety trees for $60K. All trees removed are bid to be replaced w/ sod. Class B trim and removal of dead limbs | Unmarked | Project | 202000 | 223962 | [15 empty] | GL (unmarked scope)
36 | Exterior Building & Site Work | Exterior Lighting | Replace all metal halo building lights and fix 25% of carport lights | Unmarked | Project | 198710 | 143010 | [15 empty] | GL (unmarked scope)
39 | Exterior Building & Site Work | Fireplace & Flue | 95/ unit, need to confirm FP count 608 budgeted | Unmarked | Project | 173280 | 34688 | [15 empty] | GL (unmarked scope)
51 | Exterior Building & Site Work | Roof Replacements/Repairs | Roof PM needed on all bldgs- PM also includes fix dryer vent termination on roof, repair busted roof trust in attics- PH | Unmarked | Project | 156000 | 231180 | [15 empty] | GL (unmarked scope)
59 | Interior Units | Washers/Dryers |  | Unmarked | Project | 123000 | 0 | [15 empty] | GL (unmarked scope)
64 | MEP | Domestic Water Heaters | As needed replacements on PH2&3 review unit walks | Unmarked | Project | 105000 | 4620 | [15 empty] | GL (unmarked scope)
29 | Exterior Building & Site Work | Concrete Curb/Sidewalk | Sidewalk repairs and grinding 49k per bid from Sunland. Per Post PNA -ADA acess to common areas 16k. Includes $5k in le | Unmarked | Project | 95000 | 750 | [15 empty] | GL (unmarked scope)
40 | Exterior Building & Site Work | Foundations & Site Grading | Install Exterior peirs buildings 1,8,6.24 Watch list 2,13,15,26,31 | Unmarked | Project | 92000 | 0 | [15 empty] | GL (unmarked scope)
30 | Exterior Building & Site Work | Controlled Access Systems | Site uses Gate Wise Need to check Mo. Operating cost Call box is Linear and does not work and needs replaced. Also sev | Unmarked | Project | 90000 | 20147 | [15 empty] | GL (unmarked scope)
34 | Exterior Building & Site Work | Erosion Control/Drainage | Repair drainage and add swell back side bldgs. 11-13 $11k. Clean out and test all french drains through out property $15 | Unmarked | Project | 89000 | 101269 | [15 empty] | GL (unmarked scope)
63 | MEP | Domestic Water Boilers/Heat Exchangers & | Replace boiler 1 near building 14, 48.3k PM other 2 boilers 7k Bid from SRT | Unmarked | Project | 85300 | 93981 | [15 empty] | GL (unmarked scope)
15 | Admin/Marketing | Office Furniture/Finishes | Refresh on furnitre per Post | Unmarked | Project | 85000 | 6260 | [15 empty] | GL (unmarked scope)
48 | Exterior Building & Site Work | Patio Doors/Sliders | replace 5 sliders per yr | Unmarked | Project | 77000 | 85 | [15 empty] | GL (unmarked scope)
44 | Exterior Building & Site Work | Handrail/Railings | Fixing balcony handrails and misc metal fencing repairs | Unmarked | Project | 76000 | 55360 | [15 empty] | GL (unmarked scope)
75 | MEP | Sprinkler Systems | Ph 3 dry heads due for10yr UL testing next yr. if replacement needed after testing 800 ea including SRR @64k waiting met | Unmarked | Project | 76000 | 0 | [15 empty] | GL (unmarked scope)
41 | Exterior Building & Site Work | General Site Fencing | Repair wood perim fencing. Replace middle pool fencing for $24.5K | Unmarked | Project | 74500 | 124690 | [15 empty] | GL (unmarked scope)
82 | Miscellaneous | Lead Paint/Radon Remediation | To maintain paint on all ph1 balcony handrails. Yr 1 plan is to paint all railings in the exterior scope. | Unmarked | Project | 70000 | 0 | [15 empty] | GL (unmarked scope)
68 | MEP | Fire Safety Systems | The fire and life safety system appeared to be in overall fair to average condition. The AFSS risers were last inspected | Unmarked | Project | 68000 | 5711 | [15 empty] | GL (unmarked scope)
65 | MEP | Drain Clean/Jet Lines/Video | Scrape and clean cast iron sewers in ph1&2 19k. Hyrdo jet all of Ph3 2k | Unmarked | Project | 67000 | 42606 | [15 empty] | GL (unmarked scope)
43 | Exterior Building & Site Work | Gutters & Downspouts | Gutter tune up($23k) and add Raindrop gutter guard($131k)to prevent future damage or maintance needs | Unmarked | Project | 63000 | 35600 | [15 empty] | GL (unmarked scope)
38 | Exterior Building & Site Work | Exterior Stairs | ~20% of switch backs on ph2 were replaced. Additional needing replacement. Rebuild 6 SWB landing 60k per Crest. 10k for | Unmarked | Project | 60000 | 49795 | [15 empty] | GL (unmarked scope)
31 | Exterior Building & Site Work | Covered Parking & Misc Parking Items | Repair handful of carports in Y1, and then 1 or 2 a year in outyears. | Unmarked | Project | 55000 | 57741 | [15 empty] | GL (unmarked scope)
50 | Exterior Building & Site Work | Retaining Walls | general tuck point repairs to retaining walls Includes $5k in lender mandates- Blackstone observed cracking and/or miss | Unmarked | Project | 52000 | 41380 | [15 empty] | GL (unmarked scope)
19 | Common Area | Common Corridors Rehab | Power wash breezeways - has valet waste | Unmarked | Project | 50000 | 0 | [15 empty] | GL (unmarked scope)
21 | Common Area | Mailboxes | Wish list item from PM, new mail boxes there are 7 mail rooms, Budgteing for 2 replacements 55k. And some in out yrs. A | Unmarked | Project | 50000 | 0 | [15 empty] | GL (unmarked scope)
47 | Exterior Building & Site Work | Landscape Enhancements | Updgrade front curb appeal, office, pools, and entry drive fence line | Unmarked | Project | 50000 | 143923 | [15 empty] | GL (unmarked scope)
16 | Admin/Marketing | Vehicles/Carts | Have 3 working maint, 1 leasing, budgeting for 2 gators, 1 leasing and 1 maintenance (used) | Unmarked | Project | 48000 | 125664 | [15 empty] | GL (unmarked scope)
85 | Miscellaneous | Structural Repairs | LS Repairs- Fill in potholes in yards 16k.TM to sure up LS balconies includes labor/super/estimated material needed $30k | Unmarked | Project | 46000 | 0 | [15 empty] | GL (unmarked scope)
23 | Common Area | Pool Furniture/Finishes | Pool furniture needed at leasing pool- space holder 25k | Unmarked | Project | 45000 | 58118 | [15 empty] | GL (unmarked scope)
42 | Exterior Building & Site Work | Grill Station | Refresh of pool grilling areas including replacement of grills included line 24. Removal of gazebo on line 94.This is t | Unmarked | Project | 40000 | 109552 | [15 empty] | GL (unmarked scope)
53 | Exterior Building & Site Work | Storm Water Management/Retention Ponds | Maintain storm drains | Unmarked | Project | 40000 | 17205 | [15 empty] | GL (unmarked scope)
87 | Miscellaneous | Video Surveillance System | 19 new cameras replacing NVR and reusing some of existing 35k. 25 cameras and NRV per Post PNA | Unmarked | Project | 35150 | 84704 | [15 empty] | GL (unmarked scope)
10 | Admin/Marketing | Club House/Leasing Center Addition/Alter | Need to replace front door to meet ADA 10k. 20k per post PNA to replace some other doors and update bathroom | Unmarked | Project | 35000 | 38925 | [15 empty] | GL (unmarked scope)
55 | Exterior Building & Site Work | Windows | As needed replacements. Single pain windows | Unmarked | Project | 35000 | 14100 | [15 empty] | GL (unmarked scope)
73 | MEP | PM/Clean Meter Stack | Repalced main meter panels as needed through out hold | Unmarked | Project | 35000 | 0 | [15 empty] | GL (unmarked scope)
33 | Exterior Building & Site Work | Dumpster Enclosures | Per bid from Norman. Repair and stain dumpster enclosures | Unmarked | Project | 32000 | 7966 | [15 empty] | GL (unmarked scope)
12 | Admin/Marketing | Fitness Center & Equipment | Site has new equipment and new floors room has repair needs and still needs paint,Add TVs lights/fans water despenser 15 | Unmarked | Project | 28000 | 8979 | [15 empty] | GL (unmarked scope)
81 | Miscellaneous | Environmental - Pest Control Exterminati | Waiting on bid for treatment. 35/unit space holder and 15k spaceholder for termite | Unmarked | Project | 21295 | 48447 | [15 empty] | GL (unmarked scope)
13 | Admin/Marketing | Model Furniture/Finishes | model furniture discussed 15k spaceholder | Unmarked | Project | 20000 | 7163 | [15 empty] | GL (unmarked scope)
32 | Exterior Building & Site Work | Dog Park | Ali numbers are high ($9K for refresh + $35K for new dogpark). FCP believes they can do add new park for $15K and refres | Unmarked | Project | 20000 | 34842 | [15 empty] | GL (unmarked scope)
77 | MEP | Wiring | Wiring PM/Cleanup throughout property includes securing meter banks | Unmarked | Project | 20000 | 21812 | [15 empty] | GL (unmarked scope)
66 | MEP | Fire Extinguishers | missing or dischaged 5lb fire extinguisher. | Unmarked | Project | 16650 | 233339 | [15 empty] | GL (unmarked scope)
62 | MEP | CO/Smoke Detectors | Verify if we need CO detectors for code. 471 have smoke detectors. $35 / unit | Unmarked | Project | 16450 | 21264 | [15 empty] | GL (unmarked scope)
28 | Exterior Building & Site Work | Brick Repair/Point-Up | Per bid from Norman. | Unmarked | Project | 15000 | 310 | [15 empty] | GL (unmarked scope)
84 | Miscellaneous | Maintenance Shop | Clean up maintence shop and storages | Unmarked | Project | 15000 | 0 | [15 empty] | GL (unmarked scope)
83 | Miscellaneous | Radon Mitigation Systems | In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the subject propert | Unmarked | Project | 10500 | 0 | [15 empty] | GL (unmarked scope)
11 | Admin/Marketing | Computers | do we need computer? | Unmarked | Project | 10000 | 1985 | [15 empty] | GL (unmarked scope)
20 | Common Area | Laundry Center | Has two laundry center need to refresh both 5k ea. | Unmarked | Project | 10000 | 5620 | [15 empty] | GL (unmarked scope)
46 | Exterior Building & Site Work | Irrigation | Per Superior Edge evaluated system and found 10k in repairs. Per bid. Includes $34k in lender mandates- The landscaping | Unmarked | Project | 10000 | 29287 | [15 empty] | GL (unmarked scope)
67 | MEP | Fire Life Safety Work | Ph3 only PM Riser closets 5k. Panels are still using pots lines to communicate, recommend canceling these to save mone | Unmarked | Project | 10000 | 41243 | [15 empty] | GL (unmarked scope)
86 | Miscellaneous | Tools/Miscellaneous Equipment | Misc tools | Unmarked | Project | 10000 | 37248 | [15 empty] | GL (unmarked scope)
14 | Admin/Marketing | Monument Sign | Monument looked good. All building signage looks old and drab. Space holder 15k to replace bldg signs at $85ea | Unmarked | Project | 8300 | 2042 | [15 empty] | GL (unmarked scope)
35 | Exterior Building & Site Work | Exterior Doors (Other) | Replace Misc mech rm doors | Unmarked | Project | 5000 | 10036 | [15 empty] | GL (unmarked scope)
49 | Exterior Building & Site Work | Playground & Site Furniture | Top off existing playground. 5k. See line 53 for new playground on Sport court. | Unmarked | Project | 5000 | 7250 | [15 empty] | GL (unmarked scope)
45 | Exterior Building & Site Work | Concrete Steps - Handrails | Lender mandate- Blackstone observed concrete steps with four or more risers and no handrails at Buildings 9 and 14. Blac | Unmarked | Project | 3000 | 0 | [15 empty] | GL (unmarked scope)
60 | Interior Units | Apparent Mold Growth - Unit 110 | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan c | Unmarked | Project | 2000 | 38 | [15 empty] | GL (unmarked scope)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 7843534
|  |  | CM Fee |  |  | 534592 | 245052
|  |  | Contingency |  |  | 572778
|  |  | Capital Plan Total (ex-BTL) |  |  | 8950904
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 21246
BTL (dropped per Adam): $0

## Sorrento at Tuscan Lakes
Sorrento at Tuscan Lakes — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
124 | 0900 - FF&E in Units | Unit Upgrade- Unit type 2CGl | 1117sqft, 2BR 2BA | GC | Project | 455418 | 455418 | [15 empty] | GC assumed 100% @ budget
88 | 0900 - FF&E in Units | Unit Upgrade- Unit type 1AGc | 683sqft, 1BR 1BA | GC | Project | 259134 | 259134 | [15 empty] | GC assumed 100% @ budget
76 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Project | 210000 | 210000 | [15 empty] | GC assumed 100% @ budget
97 | 0900 - FF&E in Units | Unit Upgrade- Unit type 1AGe | 779sqft, 1BR 1BA | GC | Project | 162437 | 162437 | [15 empty] | GC assumed 100% @ budget
23 | 0200 - Site Utilities & Improvements | Landscaping | Curb appeal is bad and dated (place Holder) | GC | Project | 150000 | 150000 | [15 empty] | GC assumed 100% @ budget
115 | 0900 - FF&E in Units | Unit Upgrade- Unit type 1AZh | 946sqft, 1BR 1BA | GC | Project | 128310 | 128310 | [15 empty] | GC assumed 100% @ budget
186 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | New flooring at a minimum, preferably new paint as well Remove window curtains Convert business center counter to booth | GC | Project | 90000 | 90000 | [15 empty] | GC assumed 100% @ budget
187 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | Most or all furniture will need to be replaced, it is very dated | Unmarked | Project | 90000 | 108179 | [15 empty] | GL (unmarked scope)
160 | 0900 - FF&E in Units | Unit Upgrade- Unit type 3CGo | 1381sqft, 3BR 2BA | GC | Project | 75687 | 75687 | [15 empty] | GC assumed 100% @ budget
133 | 0900 - FF&E in Units | Unit Upgrade- Unit type 2CGn | 1259sqft, 2BR 2BA | GC | Project | 70140 | 70140 | [15 empty] | GC assumed 100% @ budget
178 | 0900 - FF&E in Units | Ceiling Fans | Add to all living rooms | GC | Project | 56100 | 56100 | [15 empty] | GC assumed 100% @ budget
21 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Remove vegitation from fence repair and Paint | GC | Project | 51000 | 51000 | [15 empty] | GC assumed 100% @ budget
142 | 0900 - FF&E in Units | Unit Upgrade- Unit type 2CGn1 | 1271sqft, 2BR 2BA | GC | Project | 42546 | 42546 | [15 empty] | GC assumed 100% @ budget
34 | 0200 - Site Utilities & Improvements | Carport and garage | Repair carport damage and paint | GC | Project | 39000 | 39000 | [15 empty] | GC assumed 100% @ budget
24 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface pool | GC | Project | 38000 | 38000 | [15 empty] | GC assumed 100% @ budget
77 | 0800 - Exterior Wall | Repair / replace wood trim |  | GC | Project | 36000 | 36000 | [15 empty] | GC assumed 100% @ budget
217 | 1600 - Electrical | Replace breezeway lights | Change breezeway lights, landscape lights | GC | Project | 32570 | 32570 | [15 empty] | GC assumed 100% @ budget
196 | 1100- Specialties, Equipment & Furnishings | Pool furniture | Move furniture from Amalfi, supplement with bistro tables/chairs, sectionals, other seating, cabanas | Unmarked | Project | 30000 | 12636 | [15 empty] | GL (unmarked scope)
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
106 | 0900 - FF&E in Units | Unit Upgrade- Unit type 1AGg | 894sqft, 1BR 1BA | GC | Project | 22726 | 22726 | [15 empty] | GC assumed 100% @ budget
14 | 0200 - Site Utilities & Improvements | Concrete pavement | repair pot holes and broken sidewalks | GC | Project | 22000 | 22000 | [15 empty] | GC assumed 100% @ budget
192 | 1100- Specialties, Equipment & Furnishings | Security Camera System | Need at least for entry drive, clubhouse, and amenity coverage | Unmarked | Project | 20000 | 7426 | [15 empty] | GL (unmarked scope)
194 | 1100- Specialties, Equipment & Furnishings | Pool Remodel | Allowance, the pool area was in decent shape | Unmarked | Project | 20000 | 10113 | [15 empty] | GL (unmarked scope)
216 | 1600 - Electrical | Common area light fixtures | Change wall Packs | GC | Project | 18720 | 18720 | [15 empty] | GC assumed 100% @ budget
30 | 0200 - Site Utilities & Improvements | Pergola | repair and stain all pergolas | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
65 | 0700 - Roofing | Sealants & caulking | Seal where windows meet stucco | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
72 | 0800 - Exterior Wall | Masonry repairs | Presure wash Stone walls | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
75 | 0800 - Exterior Wall | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
212 | 1500- HVAC | Dryer Vent cleaning |  | GC | Project | 15300 | 15300 | [15 empty] | GC assumed 100% @ budget
35 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair dumpster enclosures and paint | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
58 | 0700 - Roofing | Asphalt composite shingle roofing | minor roof repairs | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
190 | 1100- Specialties, Equipment & Furnishings | Mailboxes | Package locker or Fetch system needed | Unmarked | Project | 15000 | 0 | [15 empty] | GL (unmarked scope)
151 | 0900 - FF&E in Units | Unit Upgrade- Unit type 2CGo | 1367sqft, 2BR 2BA | GC | Project | 14646 | 14646 | [15 empty] | GC assumed 100% @ budget
63 | 0700 - Roofing | Gutters & downspouts | Clean down spouts and gutters | GC | Project | 13000 | 13000 | [15 empty] | GC assumed 100% @ budget
26 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | Crack Fill and clean | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
53 | 0400 - Structure | Repair balcony framing & decking | repair balcony band boards | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
55 | 0400 - Structure | Expansion Joints | clean and seal expansion joints | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
69 | 0800 - Exterior Wall | Repair / replace cement fiber siding | repair damaged siding | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
74 | 0800 - Exterior Wall | Repair stucco |  | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
78 | 0800 - Exterior Wall | Shutters | Replace bad shutters | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
15 | 0200 - Site Utilities & Improvements | Stripe parking areas |  | GC | Project | 10500 | 10500 | [15 empty] | GC assumed 100% @ budget
50 | 0400 - Structure | Roof deck | replace bad decking on roofs | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
195 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | In good shape, allowance for minor equipment repairs & replacements | Unmarked | Project | 10000 | 4664 | [15 empty] | GL (unmarked scope)
197 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | Allowance, not much needed | Unmarked | Project | 10000 | 4664 | [15 empty] | GL (unmarked scope)
215 | 1600 - Electrical | Fire and Sprinklers | replace emergency lights | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
29 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair and paint pool fence | GC | Project | 8900 | 8900 | [15 empty] | GC assumed 100% @ budget
52 | 0400 - Structure | Repair exterior stair railings | secure railings | GC | Project | 8300 | 8300 | [15 empty] | GC assumed 100% @ budget
54 | 0400 - Structure | Repair patio/balcony railings | secure railings | GC | Project | 8300 | 8300 | [15 empty] | GC assumed 100% @ budget
25 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Replace deck-o-seal on pools | GC | Project | 8200 | 8200 | [15 empty] | GC assumed 100% @ budget
214 | 1600 - Electrical | Electrical distribution | repair electric issues with lights | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts |  | GC | Project | 4800 | 4800 | [15 empty] | GC assumed 100% @ budget
188 | 1100- Specialties, Equipment & Furnishings | Model Unit | Allowance for small additions/refresh | Unmarked | Project | 4000 | 8799 | [15 empty] | GL (unmarked scope)
198 | 1100- Specialties, Equipment & Furnishings | Golf Cart | Repair & replace battery in old leasing cart from Amalfi | Unmarked | Project | 2000 | 1793 | [15 empty] | GL (unmarked scope)
189 | 1100- Specialties, Equipment & Furnishings | Computers | Not needed, allowance for 1 | Unmarked | Project | 1500 | 2913 | [15 empty] | GL (unmarked scope)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2479733
|  |  | CM Fee |  |  | 127848
|  |  | Contingency |  |  | 77226
|  |  | Capital Plan Total (ex-BTL) |  |  | 2684807
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 53919
BTL (dropped per Adam): $0

## The Grand at Hill Street
The Grand at Hill Street — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
20 | 0200 - Site Utilities & Improvements | Parking Lot | 26 | GC | Project | 130000 | 130000 | [15 empty] | GC assumed 100% @ budget
111 | 0900 - FF&E in Units | Turf Upgrade |  | GC | Project | 80000 | 80000 | [15 empty] | GC assumed 100% @ budget
119 | 1100- Specialties, Equipment & Furnishings | Convert Conference room to package room |  | GC | Project | 65000 | 65000 | [15 empty] | GC assumed 100% @ budget
113 | 1100- Specialties, Equipment & Furnishings | Signage - entry |  | PMC | Project | 40000 | 74976 | [15 empty] | GL PMC
117 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel |  | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
109 | 0900 - FF&E in Units | Fire protection | 200 | GC | Project | 21000 | 21000 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Signage - site |  | PMC | Project | 20000 | 37488 | [15 empty] | GL PMC
17 | 0200 - Site Utilities & Improvements | Pavement |  | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
89 | 0800 - Exterior Wall | Look at sealing cedar/wood wall partitio |  | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
120 | 1100- Specialties, Equipment & Furnishings | Package Room Conversion |  | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
83 | 0800 - Exterior Wall | Repair / replace wood trim |  | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
121 | 1100- Specialties, Equipment & Furnishings | Dog Park |  | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
116 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel |  | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
143 | 1600 - Electrical | Fire Sprinklers |  | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
145 | 1600 - Electrical | Fire alarms |  | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
144 | 1600 - Electrical | Fire extinguishers |  | GC | Project | 1000 | 1000 | [15 empty] | GC assumed 100% @ budget
118 | 1100- Specialties, Equipment & Furnishings | ADA compliance |  | PMC | Project | 50 | 0 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 454050
|  |  | Capital Plan Total (ex-BTL) |  |  | 454050
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 172038
BTL (dropped per Adam): $0

## The Hightone (Allora Denton)
The Hightone (Allora Denton) — 10-Year Capital Plan
Acquired 2023. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
120 | Radon | Retest and Mitigate as needed |  | GC | Project | 123000 | 123000 | [15 empty] | GC assumed 100% @ budget
123 | Roofing Systems | Downspout repairs and gutter installatio | Rout downspouts away from the building and onto grass landscaping or concrete sidewalks / pavements to prevent erosion o | GC | Project | 68500 | 68500 | [15 empty] | GC assumed 100% @ budget
119 | 1100- Specialties, Equipment & Furnishings | Carports (Determine Upon Stabilization) | Tenants have requested covered parking, consider as value add | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Trash Compactor (Determine Upon Stabiliz | Look at adding to reduce trash collection fees | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
118 | 1100- Specialties, Equipment & Furnishings | Pool furniture (Determine Upon Stabiliza | Budget for new chaises since all are wicker, Cabanas, umbrellas | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
104 | 0900 - FF&E in Units | Fire Stops |  | GC | Project | 37000 | 37000 | [15 empty] | GC assumed 100% @ budget
108 | 1100- Specialties, Equipment & Furnishings | Signage - entry | Monument Sign | PMC | Project | 30000 | 46414 | [15 empty] | GL PMC
21 | 0200 - Site Utilities & Improvements | Landscaping | the new shrubs look to be struggling to take root, some will need to be replace this summer | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | Landscape irrigation | Irrigation drip line look to be questionable in multiple areas test and repair lines | GC | Project | 22000 | 22000 | [15 empty] | GC assumed 100% @ budget
109 | 1100- Specialties, Equipment & Furnishings | Signage - site | Rebrand signage | PMC | Project | 20000 | 108353 | [15 empty] | GL PMC
18 | 0200 - Site Utilities & Improvements | Erosion control | down spouts empty onto river rock drainage, some are short others are long storm water has already caused erosion in so | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
124 | Fair Housing |  | Reconfigure the walkway accessing the western and southwestern dumpster enclosures to provide a 60-inch turning radius P | GC | Project | 17000 | 17000 | [15 empty] | GC assumed 100% @ budget · Yr-1 only (not in 10-yr plan)
125 | 1100- Specialties, Equipment & Furnishings | Dog Park | Dog Park refresh- sail shades, benches, water station | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
117 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment (Determine Upon Stabil | Add rowing machine | PMC | Project | 4000 | 237 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 509500
|  |  | Capital Plan Total (ex-BTL) |  |  | 509500
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 22781
BTL (dropped per Adam): $0

## Allora Bella Terra
Allora Bella Terra — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
77 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Project | 345000 | 345000 | [15 empty] | GC assumed 100% @ budget
90 | 0900 - FF&E in Units | Flooring | Replace carpet throughout with LVP | GC | Project | 272700 | 272700 | [15 empty] | GC assumed 100% @ budget
119 | 1100- Specialties, Equipment & Furnishings | Pool Furniture & Games | Need 4-6 new in pool loungers, lounge seating, games, lounge seating needed by fire place | GC | Project | 60000 | 60000 | [15 empty] | GC assumed 100% @ budget
92 | 0900 - FF&E in Units | Pet yard enclosures | About 10 units we could add yards to | GC | Project | 58000 | 58000 | [15 empty] | GC assumed 100% @ budget
21 | 0200 - Site Utilities & Improvements | Landscaping | Add landscaping in planters around pool. Look at hardier fan palms, can be smaller to reduce cost. | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
76 | 0800 - Exterior Wall | Interior Hallway painting | Breezeway paint | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Iif we are ok with the tuscan, somewhat dated look, there is minimal scope ($10k). | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
126 | 1100- Specialties, Equipment & Furnishings | Package Lockers | No need, have fetch, but can look at adding package lockers outside of mail area | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
105 | 0900 - FF&E in Units | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | GC | Project | 36338 | 36338 | [15 empty] | GC assumed 100% @ budget
22 | 0200 - Site Utilities & Improvements | Landscaping- entry & in front of office | PCA- $19,500- Address bare areas throughout property Add seasonal color, add turf where needed | GC | Project | 35000 | 35000 | [15 empty] | GC assumed 100% @ budget
152 | 1600 - Electrical | Common area light fixtures | Replace pole lights with LED | GC | Project | 31000 | 31000 | [15 empty] | GC assumed 100% @ budget
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | Same as the renovation scope, this can either be minimal (need to reupholster some items) if we keep the theme, or it wi | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
118 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Pool speaker needs repair, add lights in 6 planters. Turf around perimeter, bigger TV under gazebo | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
129 | 1100- Specialties, Equipment & Furnishings | Repair or Repalce the Fire Extinguisher | From MEP Report- The fire extinguisher cabinets throughout the residentail building breezeways are corroding. | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Paint perimeter fence | GC | Project | 26500 | 26500 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair Irrigation | GC | Project | 22600 | 22600 | [15 empty] | GC assumed 100% @ budget
32 | 0200 - Site Utilities & Improvements | Carports / Garages | Repair and paint Garages | GC | Project | 22000 | 22000 | [15 empty] | GC assumed 100% @ budget
121 | 1100- Specialties, Equipment & Furnishings | Dog Park | Rubber matting for dog wash room, water station, shade structure, benches | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
122 | 1100- Specialties, Equipment & Furnishings | Unit Model Update | Add model furniture in 1 br unit, outside stepping stones in yard? | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
128 | 1100- Specialties, Equipment & Furnishings | EV Chargers | Look at level 1 chargers for garages, manager feels they can upcharge | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
34 | 0200 - Site Utilities & Improvements | Pet yards | paint pet yard fencing | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
59 | 0700 - Roofing | Asphalt composite shingle roofing | Roof inspection and minor repairs | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
106 | 0900 - FF&E in Units | Unit deferred maintenance | Painted sprinkler heads (82 total sprinklers observed in 42 units) | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
117 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Good equipment currently, request for cross fit equipment | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
150 | 1600 - Electrical | Perform Infrared (IR) Scanning | From MEP Report- The facility staff was not aware of IR scanning having been performed at the property. | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
25 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | anti entrapment devices | GC | Project | 12800 | 12800 | [15 empty] | GC assumed 100% @ budget
46 | 0400 - Structure | Repair exterior stair railings | Secure railings | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
47 | 0400 - Structure | Expansion Joints | Seal expansion joints | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
70 | 0800 - Exterior Wall | Repair / replace cement fiber siding |  | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
78 | 0800 - Exterior Wall | Repair / replace wood trim | minor trim replacement | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
27 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Paint pool fence | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
33 | 0200 - Site Utilities & Improvements | Dumpster enclosures | PCA- $1,500- Repair/replace gate as required Paint enclosure | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
149 | 1600 - Electrical | Electrical distribution | inspect and repair electric to pole lights | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
10 | 0200 - Site Utilities & Improvements | Storm sewer piping | add stone around storm drains | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
31 | 0200 - Site Utilities & Improvements | Outdoor Fireplaces | Repair 2 outdoor fireplaces | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
113 | 1100- Specialties, Equipment & Furnishings | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
136 | 1400 - Plumbing | Scope and Clear the Sewer Lines | From MEP Report- Maintenance records were not provided before the report delvery date | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
144 | 1500- HVAC | Replace the Refrigerant Line Insulation | From MEP Report- The insulation on the refrigerant lines at nearly all of the condensing units is deteriorated and at on | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
61 | 0700 - Roofing | Tile roofing | Repairs to clay tile roofs | GC | Project | 4500 | 4500 | [15 empty] | GC assumed 100% @ budget
65 | 0700 - Roofing | Flashing | Repair flashing over clay tile | GC | Project | 4500 | 4500 | [15 empty] | GC assumed 100% @ budget
135 | 1400 - Plumbing | Water pressure regulator / back-flow pre | Inspect and repair PVB's | GC | Project | 3500 | 3500 | [15 empty] | GC assumed 100% @ budget
137 | 1400 - Plumbing | Inspect and Clean Oil-Water Separator | From MEP Report- Maintenance records were not supplied prior to the report delivery date. Therefore, Partner recommends | GC | Project | 3500 | 3500 | [15 empty] | GC assumed 100% @ budget
116 | 1100- Specialties, Equipment & Furnishings | Fitness Center Remodel | Misc needs, fitness center looked good | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
127 | 1100- Specialties, Equipment & Furnishings | Car wash area equipment | Hose or vacuum replacement, misc items | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
143 | 1500- HVAC | Inspect and Repair Condenser Electrical | From MEP Report- There were multiple electrical connections observed at condensing units where the weather tight flexibl | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1420738
|  |  | CM Fee |  |  | 111150 | 111150
|  |  | Contingency |  |  | 802262 | 802262
|  |  | Capital Plan Total (ex-BTL) |  |  | 2334150
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Avonmora
Avonmora — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
52 | 84433 | Asphalt composite shingle roofing | Replace all roofs. Metal, flash, vents, and ridge | GC | Project | 1344500 | 1344500 | [15 empty] | GC assumed 100% @ budget
70 | 84207 | Interior Update Placeholder | Paint cabinets and new hardware, Flooring, resurface counters Appliances if possible | PMC | Project | 1140000 | 0 | [15 empty] | GL PMC
60 | 84101 | Exterior painting | repaint buildings 100% paintable | GC | Project | 260000 | 260000 | [15 empty] | GC assumed 100% @ budget
22 | 84303 | Perimeter fencing access control | Add thorny Pyracantha hedges alongside the fence which will grow into a natural barrier Shrubs are $80-$165 each install | GC | Project | 160000 | 160000 | [15 empty] | GC assumed 100% @ budget
34 | 84435 | Jack & underpin foundations | Foundations on 3 buildings | GC | Project | 93000 | 93000 | [15 empty] | GC assumed 100% @ budget
23 | 84303 | Landscaping | Landscape enhancements in office area and front entrances and 13-8 buildings on Wickersham Zeroscape | GC | Project | 85000 | 85000 | [15 empty] | GC assumed 100% @ budget
26 | 84361 | Pool Deck | Replace pool deck with new stamped stained concrete | GC | Project | 85000 | 85000 | [15 empty] | GC assumed 100% @ budget
27 | 84219 | Maintenance Shop Structure | Add Shop for golf carts | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
41 | 84104 | Repair balcony framing & decking | rebuild three balcony towers | GC | Project | 46000 | 46000 | [15 empty] | GC assumed 100% @ budget
134 | 84112 | Common area light fixtures | exterior building security lighting are pole lights and need new fixtures | GC | Project | 38000 | 38000 | [15 empty] | GC assumed 100% @ budget
24 | 84361 | Repair / replace swimming pool pumps | remove splash pad and fill, add turf for sitting area | GC | Project | 35000 | 35000 | [15 empty] | GC assumed 100% @ budget
102 | 84360 | Pool Furniture | All new pool furniture and games | PMC | Project | 35000 | 0 | [15 empty] | GL PMC
19 | 84517 | Erosion | Backfill areas of erosion in Dog park, and throughout property | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
25 | 84361 | Fences & gates - swimming pool | Pool fence replacement | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
101 | 84361 | Pool Area Remodel | Add plants or metal art in planters Landscape enhancements | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
15 | 84385 | Storm sewer piping | Regrade area for proper drainage south west of creek | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
17 | 84221 | Sidewalks | repair trip hazards | GC | Project | 21000 | 21000 | [15 empty] | GC assumed 100% @ budget
96 | 84116 | Clubhouse / Office Remodel | Sitting area by leasing- New lounge furniture, replace shelving with art and TVs. Doors out to pool, pergola outside, s | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
135 | 84112 | exterior lights | replace pool lights and correct electric for pool lights | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
58 | 84105 | Repair / replace wood siding | repair loose siding | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
18 | 84434 | Retaining walls | Repair three retaining walls | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
28 | 84219 | Carports / Garages | repair car ports | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
61 | 84113 | Repair / replace soffits | repair stairwell soffit | GC | Project | 14500 | 14500 | [15 empty] | GC assumed 100% @ budget
29 | 84111 | Dumpster enclosures | dumpster repairs | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
59 | 84206 | Repair stucco | repair damaged stucco | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
62 | 84105 | Repair / replace wood trim | wood replacement | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
87 | 84304 | Sub Floor Repairs | Sub Floors | PMC | Project | 10000 | 0 | [15 empty] | GL PMC
39 | 84114 | Repair exterior stair treads and stringe | replace 80 stair treads | GC | Project | 9250 | 9250 | [15 empty] | GC assumed 100% @ budget
63 | 84206 | Shutters | replace 50 pairs of shutters | GC | Project | 9000 | 9000 | [15 empty] | GC assumed 100% @ budget
53 | 84202 | Gutters & downspouts | Repair and replace damaged or missing gutters | GC | Project | 8300 | 8300 | [15 empty] | GC assumed 100% @ budget
16 | 84201 | ADA parking & curb cuts | strip and repaint ADA ramps | GC | Project | 7800 | 7800 | [15 empty] | GC assumed 100% @ budget
54 | 84433 | Sealants & caulking and paint | sealant for stucco expansion joints | GC | Project | 5300 | 5300 | [15 empty] | GC assumed 100% @ budget
40 | 84121 | Repair exterior stair railings | repair and secure stair rails | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
106 | 84130 | Dog Park | Add benches and table | GC | Project | 4000 | 4000 | [15 empty] | GC assumed 100% @ budget
95 | 84905 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | PMC | Project | 1000 | 0 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 3700650
|  |  | Contingency |  |  | 20000 | 20000
|  |  | Capital Plan Total (ex-BTL) |  |  | 3720650
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Bridgepoint
Bridgepoint — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
93 | 0900 - FF&E in Units | bpa2 | See unit upgrade calc for detail | GC | Project | 524112 | 524112 | [15 empty] | GC assumed 100% @ budget
95 | 0900 - FF&E in Units | bpb1 | See unit upgrade calc for detail | GC | Project | 260843 | 260843 | [15 empty] | GC assumed 100% @ budget
146 | 1500- HVAC | Replace AC condenser | Air conditioners at 40% conversion to 410-a, but not all replaced inside and out. Contingency for replacement of R-22 u | GC | Project | 210000 | 210000 | [15 empty] | GC assumed 100% @ budget
79 | 0800 - Exterior Wall | Exterior building | paint community | GC | Project | 209000 | 209000 | [15 empty] | GC assumed 100% @ budget
97 | 0900 - FF&E in Units | bpb2 | See unit upgrade calc for detail | GC | Project | 192250 | 192250 | [15 empty] | GC assumed 100% @ budget
89 | 0900 - FF&E in Units | bps1 | See unit upgrade calc for detail | GC | Project | 174599 | 174599 | [15 empty] | GC assumed 100% @ budget
91 | 0900 - FF&E in Units | bpa1 | See unit upgrade calc for detail | GC | Project | 160560 | 160560 | [15 empty] | GC assumed 100% @ budget
94 | 0900 - FF&E in Units | bpa2u | See unit upgrade calc for detail | GC | Project | 153398 | 153398 | [15 empty] | GC assumed 100% @ budget
96 | 0900 - FF&E in Units | bpb1u | See unit upgrade calc for detail | GC | Project | 127272 | 127272 | [15 empty] | GC assumed 100% @ budget
98 | 0900 - FF&E in Units | bpb2u | See unit upgrade calc for detail | GC | Project | 113914 | 113914 | [15 empty] | GC assumed 100% @ budget
103 | 0900 - FF&E in Units | Washers & Dryers- Basic front load | From Grid report 28 have connections, 115 have full size W/D, 45 don’t have connections | GC | Project | 109250 | 109250 | [15 empty] | GC assumed 100% @ budget
12 | 0200 - Site Utilities & Improvements | concrete pavement | Patch and repair damaged areas, replace existing speed bumps with monolithic speed bumps PCA Item- Linear cracking was o | GC | Project | 70000 | 70000 | [15 empty] | GC assumed 100% @ budget
42 | 0300 - Excavation & Foundations | Jack & underpin foundations | Placeholder for foundation repairs on "2 buildings" | GC | Project | 70000 | 70000 | [15 empty] | GC assumed 100% @ budget
22 | 0200 - Site Utilities & Improvements | Landscaping | Add river rock in high visibility bare areas Add french drains to address areas with flooding, particularly flooded uni | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
145 | 1500- HVAC | HVAC | Install AC pads on all units sitting on dirt, secure all unit access control panels MEP Item- Split system units - Cond | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
90 | 0900 - FF&E in Units | bps1u | See unit upgrade calc for detail | GC | Project | 40336 | 40336 | [15 empty] | GC assumed 100% @ budget
92 | 0900 - FF&E in Units | bpa1u | See unit upgrade calc for detail | GC | Project | 38813 | 38813 | [15 empty] | GC assumed 100% @ budget
23 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface | GC | Project | 38000 | 38000 | [15 empty] | GC assumed 100% @ budget
16 | 0200 - Site Utilities & Improvements | Sidewalks | Mortar expansion joints between curb and sidewalk PCA Item- Differential settlement between the curb and the sidewalk w | GC | Project | 36000 | 36000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Straighten and add additional side to wooden privacy fence between communities | GC | Project | 35000 | 35000 | [15 empty] | GC assumed 100% @ budget
119 | 1100- Specialties, Equipment & Furnishings | Pool Furniture | All new furniture, move current tables and chairs to other areas at property | GC | Project | 35000 | 35000 | [15 empty] | GC assumed 100% @ budget
82 | 0800 - Exterior Wall | Replace unit entry doors - exterior | Placeholder to replace up to 50 doors throughout property | GC | Project | 31500 | 31500 | [15 empty] | GC assumed 100% @ budget
153 | 1600 - Electrical | Common area light fixtures | Replace wall packs on buildings | GC | Project | 31000 | 31000 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Work with designer on options for Repaint Other finishes including backsplash and counters New art on walls New TV above | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
120 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Area Remodel | Grill by pool- turf under entire grill area, add gazebo, convert pergola over grill to gazebo | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
154 | 1600 - Electrical | Replace additional lights | Replace pole light fixtures | GC | Project | 28000 | 28000 | [15 empty] | GC assumed 100% @ budget
18 | 0200 - Site Utilities & Improvements | Erosion control |  | GC | Project | 25500 | 25500 | [15 empty] | GC assumed 100% @ budget
109 | 1100- Specialties, Equipment & Furnishings | Signage - Entry Monument | Explore adding monument sign | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
106 | 0900 - FF&E in Units | Pet Yards | Test 4 per yards on tour path- turf with vinyl or iron fence and privacy screen | GC | Project | 24000 | 24000 | [15 empty] | GC assumed 100% @ budget
10 | 0200 - Site Utilities & Improvements | Storm sewer piping | Clean out yard drains PCA Item- It was reported that storm water ponds around Building 2 and 6. Partner observed sandbag | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
123 | 1100- Specialties, Equipment & Furnishings | Dog Park | Water/Wash Station with concrete pad ($6k) Add gazebo or shade sail Furniture next to laundry area | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
151 | 1600 - Electrical | Electrical distribution | Inspect and repair lighting controllers on all buildings "additional wiring requirements are not included" MEP Item- Ele | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
52 | 0400 - Structure | Repair exterior stair treads and stringe | replace 140 stair treads across property | GC | Project | 18900 | 18900 | [15 empty] | GC assumed 100% @ budget
13 | 0200 - Site Utilities & Improvements | Stripe parking areas | Entire property | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | Landscape irrigation | Inspect and repair Irrigation | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
33 | 0200 - Site Utilities & Improvements | Carports / Garages | Repair and paint | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
30 | 0200 - Site Utilities & Improvements | Dog Park | Replace 225 ft of fencing, replace bench with moveable bench | GC | Project | 17400 | 17400 | [15 empty] | GC assumed 100% @ budget
47 | 0400 - Structure | Concrete deck / floor fill |  | GC | Project | 17000 | 17000 | [15 empty] | GC assumed 100% @ budget
65 | 0700 - Roofing | Gutters & downspouts | repitch and clean | GC | Project | 17000 | 17000 | [15 empty] | GC assumed 100% @ budget
66 | 0700 - Roofing | Flashing | siding flashing | GC | Project | 17000 | 17000 | [15 empty] | GC assumed 100% @ budget
80 | 0800 - Exterior Wall | Repair / replace wood trim | replace rotted trim/fascia/band boards | GC | Project | 17000 | 17000 | [15 empty] | GC assumed 100% @ budget
117 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Add more equipment along walkway, add storage | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
111 | 1100- Specialties, Equipment & Furnishings | Signage - Building identification | New to match paint | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
116 | 1100- Specialties, Equipment & Furnishings | Fitness Center Remodel | Paint, add lighting, add water fountain, add 2 TVs, look at adding fans | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
118 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Look at adding storage, other misc landscaping and needs | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
121 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Furniture | Add picnic tables, chairs, games | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
122 | 1100- Specialties, Equipment & Furnishings | Sports Courts | Convert old tennis court to pickleball- need to resurface and stripe, and add nets, bring surrounding soil back up to sl | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
25 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | pressure wash, replace expansion joint materials and deck o seal | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
29 | 0200 - Site Utilities & Improvements | Pergola court | repair, stain and seal pergolas over grill areas | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
21 | 0200 - Site Utilities & Improvements | Landscaping | remove dead tree stumps on site | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
131 | 1100- Specialties, Equipment & Furnishings | Security Camera System | No urgent need, would be nice to have for monitoring | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
141 | 1400 - Plumbing | Sanitary sewer piping | MEP Item- Industry best practices typically include clearing sanitary waste lines every 18- to 24-months. Partner recomm | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
104 | 0900 - FF&E in Units | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | GC | Project | 9570 | 9570 | [15 empty] | GC assumed 100% @ budget
24 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | retile pool | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair door and paint | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
15 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts | Repair damaged curbs | GC | Project | 9300 | 9300 | [15 empty] | GC assumed 100% @ budget
28 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | paint and repair | GC | Project | 9300 | 9300 | [15 empty] | GC assumed 100% @ budget
67 | 0700 - Roofing | Sealants & caulking |  | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
107 | 0900 - FF&E in Units | Down Unit | PCA Item- Unit 514 was observed to be down due to a recent fire that was started by a candle in the bathroom of the unit | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | Office chairs and other miscellaneous Items | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
135 | 1100- Specialties, Equipment & Furnishings | Golf Cart | Need maintenance cart | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
53 | 0400 - Structure | Repair exterior stair railings | secure stair railings | GC | Project | 5100 | 5100 | [15 empty] | GC assumed 100% @ budget
113 | 1100- Specialties, Equipment & Furnishings | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
71 | 0800 - Exterior Wall | Repair / replace cement fiber siding |  | GC | Project | 3400 | 3400 | [15 empty] | GC assumed 100% @ budget
74 | 0800 - Exterior Wall | Dryer Vents | Just cleaned, no cleaning needed. Need to replace some flappers | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
127 | 1100- Specialties, Equipment & Furnishings | Computers | 2 new comupters for clubhouse resident use | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
48 | 0400 - Structure | Wall framing | seal penetrations in landings | GC | Project | 1700 | 1700 | [15 empty] | GC assumed 100% @ budget
37 | 0200 - Site Utilities & Improvements | Compactor door out of place | TAM team has bid to repair | GC | Project | 1500 | 1500 | [15 empty] | GC assumed 100% @ budget
133 | 1100- Specialties, Equipment & Furnishings | Fire Extinguishers | PCA Item- Expired certification tags were present at the fire extinguishers in common area breezeways. Servicing and re- | PMC | Project | 1000 | 7663 | [15 empty] | GL PMC
126 | 1100- Specialties, Equipment & Furnishings | Access Control System | Replace keypad on fitness center door | GC | Project | 500 | 500 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 3389015
|  |  | CM Fee |  |  | 174000 | 174000
|  |  | Contingency |  |  | 90985 | 90985
|  |  | Capital Plan Total (ex-BTL) |  |  | 3654000
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 24723
BTL (dropped per Adam): $0

## Cityscape
Cityscape — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
141 | 83515 | Green Initiatives | Green Program | GC | Project | 100000 | 100000 | [15 empty] | GC assumed 100% @ budget
112 | 84239 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | PMC | Project | 28634 | 44122 | [15 empty] | GL PMC
21 | 84102 | Concrete pavement | Remove and replace 10,000 LF of failing expansion joint material | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
16 | 84303 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
120 | 84116 | Clubhouse / Office Remodel | Add controlled access for clubhouse for rentals | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
122 | 84190 | Fitness Center Remodel | Add lighting around perimeter soffit | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
238 |  | Standardized Calc: |  |  |  | 14 | 0
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 171648
|  |  | CM Fee |  |  | 9440 | 9440
|  |  | Contingency |  |  | 17163 | 17163
|  |  | Capital Plan Total (ex-BTL) |  |  | 198252
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 10733
BTL (dropped per Adam): $0

## Discovery Park
Discovery Park — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
22 | 0200 - Site Utilities & Improvements | Carports | Look at adding, garages are sold out so there is a need | GC | Project | 152000 | 152000 | [15 empty] | GC assumed 100% @ budget
11 | 0200 - Site Utilities & Improvements | Concrete Pavement | From PCA- Replace the large area of prior-repaired concrete pavement near the southwest corner of Building 1 due to sign | GC | Project | 43750 | 43750 | [15 empty] | GC assumed 100% @ budget
129 | 1100- Specialties, Equipment & Furnishings | Pool Furniture | New side tables, new lounge seating or at least replace cushions on existing wicker seating. 1-2 new cabanas or more cha | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
161 | 1600 - Electrical | Fire and Sprinklers | Add anti freeze to hallway and patio sprinkler systems | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
20 | 0200 - Site Utilities & Improvements | Resurface swimming pool | Resurface Pool | GC | Project | 35000 | 35000 | [15 empty] | GC assumed 100% @ budget
112 | 0900 - FF&E in Units | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | GC | Project | 30069 | 30069 | [15 empty] | GC assumed 100% @ budget
127 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Allowance for supplemental equipment and replacements for cycling room and gym | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
140 | 1100- Specialties, Equipment & Furnishings | Rubber Mats for Breezeway transitions fo |  | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair Irrigation | GC | Project | 22600 | 22600 | [15 empty] | GC assumed 100% @ budget
13 | 0200 - Site Utilities & Improvements | Concrete Pavement | From PCA- Allowance to replace the deteriorated sealant in the concrete pavement joints | GC | Project | 21700 | 21700 | [15 empty] | GC assumed 100% @ budget
45 | 0200 - Site Utilities & Improvements | Dryer Vents | Clean, fix any flapper valves | GC | Project | 21225 | 21225 | [15 empty] | GC assumed 100% @ budget
44 | 0200 - Site Utilities & Improvements | Soffit beam supports appear to be separa |  | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
121 | 1100- Specialties, Equipment & Furnishings | Signage- Monument | Look at adding monument sign | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
154 | 1500- HVAC | Repair HVAC in fitness center |  | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
160 | 1600 - Electrical | Electrical distribution | Electric for car ports- Remove if we don’t add car ports | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
123 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | Misc items, new pool table? | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
24 | 0200 - Site Utilities & Improvements | Pet yards | paint pet yard fencing | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
54 | 0400 - Structure | Roof deck | Secure Decking while doing roof tune-up | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
67 | 0700 - Roofing | Asphalt composite shingle roofing | Roof inspection and minor repairs | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
119 | 1100- Specialties, Equipment & Furnishings | Signage - Building identification | Need better signage at leasing office, new garage number signs to replace current faded ones, new window shade branded d | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
133 | 1100- Specialties, Equipment & Furnishings | Dog Park | Water/Wash Station with concrete pad ($6k) Shade sail or pergola Look at adding additional Dog Park across road | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
162 | 1600 - Electrical | Common area light fixtures | Lighting for carports | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
113 | 0900 - FF&E in Units | Fire protection | Fix heads with overspray- allowance | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
122 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Placeholder for minor items | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
37 | 0200 - Site Utilities & Improvements | Dog Park Fence | Repair and repaint fence, replace or fix broken gate hinge and bring latches down to FHAA compliant height | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
46 | 0200 - Site Utilities & Improvements | Garages | Replace at least 6 dented garage doors (G115 is the worst) | GC | Project | 8800 | 8800 | [15 empty] | GC assumed 100% @ budget
80 | 0800 - Exterior Wall | Repair / replace wood trim | minor trim replacement | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
124 | 1100- Specialties, Equipment & Furnishings | Indoor Basketball Area Repairs | Restripe basketball court Fix leak in roof and repair damage at ceiling Repair wall chips behind hoop Fix chipped paint | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
10 | 0200 - Site Utilities & Improvements | Storm sewer piping | add stone around storm drains | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
78 | 0800 - Exterior Wall | Repair / replace cement fiber siding |  | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
21 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | anti entrapment devices | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
136 | 1100- Specialties, Equipment & Furnishings | Access Control System | Need to add access control at 2 doors from pool to business center and to restrooms | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
18 | 0200 - Site Utilities & Improvements | Accessibility | From PCA- Ramps are provided on the first floor of the buildings to address changes in the slab elevations. Handrails ar | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
75 | 0700 - Roofing | Articulating Lift Rental |  | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
114 | 0900 - FF&E in Units | Unit deferred maintenance | Sub floor repairs | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
128 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Replace bamboo screen around pool equipment room with better screen, misc repairs and pool equipment | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
12 | 0200 - Site Utilities & Improvements | Concrete Pavement | From PCA- Allowance to repair all areas of random pavement cracks scattered throughout the parking areas | GC | Project | 4500 | 4500 | [15 empty] | GC assumed 100% @ budget
23 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Paint enclosure | GC | Project | 4500 | 4500 | [15 empty] | GC assumed 100% @ budget
146 | 1400 - Plumbing | Water pressure regulator / back-flow pre | inspect and repair PVB's | GC | Project | 3500 | 3500 | [15 empty] | GC assumed 100% @ budget
15 | 0200 - Site Utilities & Improvements | Sidewalk Railing | From PCA- Install a guardrail along the east edge of the wide sidewalk leading to the maintenance garage where the adjac | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
16 | 0200 - Site Utilities & Improvements | Concrete Stairs | From PCA- Due to the muddy, deteriorated landscape conditions at the fire sprinkler riser room of Building 1 discussed i | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | Accessibility | From PCA- Install edge protection at the base of the guardrail along the west side of the pool deck for FHAA compliance | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
49 | 0300 - Excavation & Foundations | Foundation Repair | Review all exposed areas and appropriately repair any foundation cracking such as the ones noted near garage G505 on Bui | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
126 | 1100- Specialties, Equipment & Furnishings | Fitness Center Remodel | Allowance for minor repairs | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
125 | 1100- Specialties, Equipment & Furnishings | Indoor Basketball Area Furniture | Replace 2 long benches | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
132 | 1100- Specialties, Equipment & Furnishings | Business Center & Office Computers | 1 computer is cracked and needs to be replaced. | PMC | Project | 1500 | 5287 | [15 empty] | GL PMC
14 | 0200 - Site Utilities & Improvements | Sidewalk Repair | From PCA- Area of heaving adjacent to the pavement curb near the southwest corner of Building 4 and deteriorated sealant | GC | Project | 1000 | 1000 | [15 empty] | GC assumed 100% @ budget
142 | 1100- Specialties, Equipment & Furnishings | Cigarette Urns | Per Shelly, look at adding smoking urns where needed to reduce cigarette butts throughout property | GC | Project | 1000 | 1000 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 784444
|  |  | CM Fee |  |  | 40222 | 40222
|  |  | Contingency |  |  | 20000 | 20000
|  |  | Capital Plan Total (ex-BTL) |  |  | 844666
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Hampton Courts
Hampton Courts — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
71 | 7200-0013 | Paint community - working with Keys | Paint community - working with Keys | GC | Project | 340000 | 340000 | [15 empty] | GC assumed 100% @ budget
101 | 7400-0041 | 170 units we could add washer dryers - | 170 units we could add washer dryers - Team to order stock and install on turn, reno, WO, PM | PMC | Project | 221000 | 0 | [15 empty] | GL PMC
147 | 7200-0033 | PCA Item- $690,000- The maintenance supe | PCA Item- $690,000- The maintenance supervisor reported that roughly 50% of the heat pump condensers are from the origin | PMC | Project | 200000 | 0 | [15 empty] | GL PMC
17 | 7200-0064 | Seal Coat asphalt PCA Item- $1,725- Limi | Seal Coat asphalt PCA Item- $1,725- Limited surface linear cracking and “map” or “alligator” cracking were noted along t | GC | Project | 81000 | 81000 | [15 empty] | GC assumed 100% @ budget
140 | 7200-0007 | PCA Item- $276,000- The maintenance supe | PCA Item- $276,000- The maintenance supervisor reported that roughly 50% of the domestic water heaters are from the orig | PMC | Project | 80000 | 0 | [15 empty] | GL PMC
117 | 7200-0027 | New furniture - Keys | New furniture - Keys | PMC | Project | 75000 | 0 | [15 empty] | GL PMC
116 | 7200-0032 | New carpeting in corridor and on stairs, | New carpeting in corridor and on stairs, lots of drywall repairs | GC | Project | 60000 | 60000 | [15 empty] | GC assumed 100% @ budget
121 | 7200-0061 | Supplement or replace furniture, add gam | Supplement or replace furniture, add games - Keys | PMC | Project | 60000 | 0 | [15 empty] | GL PMC
63 | 7200-0002 | Clubhouse needs new roof, property recei | Clubhouse needs new roof, property received bid for $40-$50k to replace | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
130 | 7200-0055 | Needed, would need to find space outside | Needed, would need to find space outside or repurpose laundry room if possible - explore options | PMC | Project | 50000 | 0 | [15 empty] | GL PMC
19 | 7200-0045 | Initial property tree trim around buildi | Initial property tree trim around buildings, landscape cleanup, entry and tour path enhancements, etc. PCA Item- $5,000- | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
119 | 7200-0074 | New equipment to supplement existing - K | New equipment to supplement existing - Keys | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
124 | 7200-0059 | Pickleball courts in decent shape, budge | Pickleball courts in decent shape, budget for resurfacing and concrete repair since blue surface is loose in places with | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
62 | 7200-0012 | Seal edges of delaminated cedar | Seal edges of delaminated cedar | GC | Project | 36000 | 36000 | [15 empty] | GC assumed 100% @ budget
154 | 7200-0040 | Replace wall packs | Replace wall packs | GC | Project | 36000 | 36000 | [15 empty] | GC assumed 100% @ budget
59 | 7200-0002 | Roof tune up include chimney | Roof tune up include chimney | GC | Project | 34000 | 34000 | [15 empty] | GC assumed 100% @ budget
105 | 7400-0038 | LowPro (Pair covers 4 burner range)- For | LowPro (Pair covers 4 burner range)- For range top microwaves (assuming current hoods are replaced with OTR microwaves) | PMC | Project | 32258 | 0 | [15 empty] | GL PMC
15 | 7200-0064 | Repair pot holes | Repair pot holes | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
100 | 7400-0040 | 99 units with missing GFCIs in the kitch | 99 units with missing GFCIs in the kitchen across different buildings and renovation levels - Team to order stock and in | PMC | Project | 29700 | 0 | [15 empty] | GL PMC
70 | 7200-0012 | Replace rotted cedar siding | Replace rotted cedar siding | GC | Project | 27000 | 27000 | [15 empty] | GC assumed 100% @ budget
122 | 7200-0060 | Look at adding a picnic area or enhance | Look at adding a picnic area or enhance existing grill, add gazebo - Keys | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
72 | 7200-0012 | Replace rotted fascia and trim - work i | Replace rotted fascia and trim - work in conjunction with bat removal | GC | Project | 24000 | 24000 | [15 empty] | GC assumed 100% @ budget
153 | 7200-0040 | inspect and repair electric for exposed | inspect and repair electric for exposed electrical lines in lighting systems . PCA Item- $3,000- Repair electrical distr | GC | Project | 21000 | 21000 | [15 empty] | GC assumed 100% @ budget
103 | 7200-0041 | Done every fall, budget for cleaning aft | Done every fall, budget for cleaning after takeover | GC | Project | 20700 | 20700 | [15 empty] | GC assumed 100% @ budget
16 | 7200-0064 | Stripe Parking | Stripe Parking | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
109 | 7400-0032 | Evidence of water infiltration observed | Evidence of water infiltration observed (20)- Units - COMPLETE BEFORE TAKEOVER | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
18 | 7200-0064 | Repair trip hazards PCA Item- $3,000- A | Repair trip hazards PCA Item- $3,000- A significant area of heaved concrete was observed in the sidewalk at the south of | GC | Project | 18500 | 18500 | [15 empty] | GC assumed 100% @ budget
61 | 7200-0017 | secure and clean gutters | secure and clean gutters | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
126 | 7200-0037 | New furniture in model unit - Keys | New furniture in model unit - Keys | PMC | Project | 18000 | 0 | [15 empty] | GL PMC
73 | 7200-0023 | Replace damaged storage doors | Replace damaged storage doors | GC | Project | 17000 | 17000 | [15 empty] | GC assumed 100% @ budget
112 | 7400-0053 | Allowance | Allowance | PMC | Project | 15000 | 0 | [15 empty] | GL PMC
118 | 7200-0032 | Paint, lighting, flooring is ok - frost | Paint, lighting, flooring is ok - frost the glass and possibly add sound dampening panels to upper walls | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
125 | 7200-0048 | Allowance for Dog Park enhancements - ad | Allowance for Dog Park enhancements - adding enzyme injector | PMC | Project | 15000 | 0 | [15 empty] | GL PMC
133 |  | Have 10 cameras and good coverage, allow | Have 10 cameras and good coverage, allowance for some additional cameras | PMC | Project | 15000 | 0 | [15 empty] | GL PMC
134 | 7200-0066 | Need storage for maintenance and invento | Need storage for maintenance and inventory - maintenance shop clean up first. If still not enough space, add used Conex | PMC | Project | 15000 | 0 | [15 empty] | GL PMC
48 | 7200-0016 | Repair loose pickets | Repair loose pickets | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
60 | 7200-0002 | Seal flat roof on club building - option | Seal flat roof on club building - option to replace soon to fail skylight. Pushes cost to $30k | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
20 | 7200-0057 | Anti entrapment devices | Anti entrapment devices | GC | Project | 12800 | 12800 | [15 empty] | GC assumed 100% @ budget
155 | 7200-0040 | Replace pole lights around pool | Replace pole lights around pool | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
150 | 7200-0033 | HVAC lines are under sized, need to repl | HVAC lines are under sized, need to replace. - As needed | PMC | Project | 10000 | 0 | [15 empty] | GL PMC
49 | 7400-0015 | Repair Balconies | Repair Balconies | GC | Project | 9000 | 9000 | [15 empty] | GC assumed 100% @ budget
50 | 7200-0016 | secure railings | secure railings | GC | Project | 8600 | 8600 | [15 empty] | GC assumed 100% @ budget
23 | 7200-0081 | Repair and paint compactor enclosure | Repair and paint compactor enclosure | GC | Project | 8500 | 8500 | [15 empty] | GC assumed 100% @ budget
46 | 7200-0012 | replace damaged framing in gable ends | replace damaged framing in gable ends | GC | Project | 8500 | 8500 | [15 empty] | GC assumed 100% @ budget
148 | 7200-0033 | PCA Item- $8,500- Insulation at the refr | PCA Item- $8,500- Insulation at the refrigerant lines for a majority of the outdoor condensing units were observed to be | GC | Project | 8500 | 8500 | [15 empty] | GC assumed 100% @ budget
24 | 7200-0064 | PCA Item- $6,000- Provide accessible pat | PCA Item- $6,000- Provide accessible path of travel from municipal sidewalk to leasing office entrance. | GC | Project | 7000 | 7000 | [15 empty] | GC assumed 100% @ budget
47 | 7200-0016 | secure railings | secure railings | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
21 | 7200-0069 | Adjust closers on pool gates | Adjust closers on pool gates | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
141 | 7200-0007 | PCA Item- $5,000- The clubhouse domestic | PCA Item- $5,000- The clubhouse domestic water heater is origional; to the 1986 construction. Electric, storage-type wat | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
22 | 7200-0061 | Replace grill | Replace grill | GC | Project | 4000 | 4000 | [15 empty] | GC assumed 100% @ budget
131 | 7200-0029 | 4 new computers needed | 4 new computers needed | PMC | Project | 4000 | 0 | [15 empty] | GL PMC
149 | 7200-0033 | PCA Item- $4,000- The ductwork within th | PCA Item- $4,000- The ductwork within the clubhouse displayed evident signs of dust accumulation, observable upon visibl | GC | Project | 4000 | 4000 | [15 empty] | GC assumed 100% @ budget
51 | 7200-0015 | PCA Item- $2,500- At Building A, two ext | PCA Item- $2,500- At Building A, two exterior stair conditions requiring repair were noted. At the uppermost landing of | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
108 | 7400-0028 | PCA Item- $2,000- Complete flooring/appl | PCA Item- $2,000- Complete flooring/appliance replacement at Unit F102.- COMPLETE BEFORE TAKEOVER | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
139 | 7200-0047 | PCA Item- $2,000- At the front of Buildi | PCA Item- $2,000- At the front of Building M, the adjacent asphalt parking lot and drive aisle were observed to be satur | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
107 | 7400-0032 | PCA Item- $1,000- Remove and replace sus | PCA Item- $1,000- Remove and replace suspect microbial growth-damaged ceiling at Unit A107 bathroom - COMPLETE BEFORE TA | GC | Project | 1000 | 1000 | [15 empty] | GC assumed 100% @ budget
106 | 7400-0034 | PCA Item- $500- At vacant Unit E105, sta | PCA Item- $500- At vacant Unit E105, standing water was observed on the floor - COMPLETE BEFORE TAKEOVER | GC | Project | 500 | 500 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1990358
|  |  | CM Fee |  |  | 104518 | 104518
|  |  | Contingency |  |  | 100000 | 100000
|  |  | Capital Plan Total (ex-BTL) |  |  | 2194875
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Harbor Terrace
Harbor Terrace — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
95 | 51150-00 | See Unit Renovation Calculator for detai |  | UUP |  | 400000 | 0
66 | 51061-00 | Repair areas of roofs that hold water an |  | DFM |  | 48000 | 0
140 | 51130-00 | Curent boiler is a 2002 Raypax boilet wh |  | DFM |  | 45000 | 0
58 | 51072-00 | There are two balconies that appear to h |  | DFM |  | 30000 | 0
122 | 51160-00 | Patio Level Enhancements |  | AMN |  | 30000 | 0
153 | 51141-00 | Replace garage lighting with LED |  | DFM |  | 22500 | 0
16 | 51045-00 | Initial property tree trim, landscape cl | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
139 | 51158-00 | Numerous copper water lines have been re |  | DFM |  | 15000 | 0
112 | 51180-00 | LowPro (Pair covers 4 burner range)- For |  | DFM |  | 11103 | 0
121 | 51160-00 | Miscellaneous needs |  | AMN |  | 10000 | 0
18 | 51053-00 | Restripe parking garage | Restripe parking garage | GC | Project | 9700 | 9700 | [15 empty] | GC assumed 100% @ budget
57 | 51072-00 | Replace areas of soft decking |  | DFM |  | 7500 | 0
17 | 51130-00 | All floor drains have been painted over | All floor drains have been painted over and should have the covers cleaned or replaced | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
59 | 51993-01 | Request copy of completed inspection, or |  | DFM |  | 5000 | 0
158 | 51993-01 | PCA Item- Based on prelimuinary load cal |  | DFM |  | 5000 | 0
67 | 51062-00 | Seal parapet wall flashing |  | DFM |  | 4500 | 0
96 | 52111-00 | Equity PCR Item 8.0- Water damaged ceili |  | DFM |  | 1500 | 0
135 | 51993-01 | PCA Item- Current operation permits expi |  | DFM |  | 1500 | 0
134 | 51993-01 | PCA Item- Expired certification tags wer |  | DFM |  | 750 | 0
19 | 51032-00 | Equity PCR Item 7.0- ADA-compliant parki | Equity PCR Item 7.0- ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibi | GC | Project | 300 | 300 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 668853
|  |  | CM Fee |  |  | 53100
|  |  | Contingency |  |  | 393147
|  |  | Capital Plan Total (ex-BTL) |  |  | 1115100
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 3568
BTL (dropped per Adam): $0

## Marquee
Marquee — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
78 | 51080-00 | Exterior building | Paint community Using Elastomaric paint Equity PCA Item 4.3.1- Exterior paint appeared to be in fair condition. The rec | GC | Project | 250000 | 250000 | [15 empty] | GC assumed 100% @ budget
113 | 51158-00 | Water Savings Project | Echelon proposal for water savings devices | PMC | Project | 138000 | 21858 | [15 empty] | GL PMC
157 | 51140-00 | Electrical distribution | Equity PCA Item 5.3- Stab-Lok brand breaker panels manufactured by Federal Pacific Electric (FPE) were observed in appro | PMC | Project | 118000 | 8547 | [15 empty] | GL PMC
94 | 51150-00 | Interior Update Placeholder | Match renovated units with upcoming available classic units | PMC | Project | 112000 | 22164 | [15 empty] | GL PMC
77 | 51080-00 | Interior Hallway painting | Paint interior hallways and staircases | GC | Project | 89000 | 89000 | [15 empty] | GC assumed 100% @ budget
79 | 51073-00 | Replace unit entry doors - exterior | Replace 28 back doors | GC | Project | 70800 | 70800 | [15 empty] | GC assumed 100% @ budget
146 | 51110-00 | Common area water heaters / boilers | Replace two ray pak boilers and one upright 199,000 but heater | PMC | Project | 65000 | 0 | [15 empty] | GL PMC
21 | 51050-00 | Parking Pavement & Seal Coat | Equity PCA Item 3.2.2- Linear cracking was noted at the drive aisle on the eastern side of the subject property, adjacen | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
76 | 51075-00 | Repair stucco | repair remaining areas of delaminated stucco and cracked stucco | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
18 | 51026-00 | Repair / replace swimming pool heaters | replace hot tub heater | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
128 | 51992-00 | Termite treatment & Repairs | Refer to Orkin WDIR dated 9/25/24 for details | PMC | Project | 25000 | 0 | [15 empty] | GL PMC
125 | 51011-00 | Pool & Spa Area Furniture & Games | Match furniture style in main pool area, possibly move some irems from pool to spa area | PMC | Project | 20000 | 0 | [15 empty] | GL PMC
130 | 51160-05 | Unit Model Update | New furniture in model unit, definitely enhance lighting in model | PMC | Project | 20000 | 0 | [15 empty] | GL PMC
137 | 51993-00 | Security Camera System | Needed, especially at pedestrian gates | PMC | Project | 20000 | 0 | [15 empty] | GL PMC
65 | 51071-00 | Gutters & downspouts | secure and clean gutters | GC | Project | 19000 | 19000 | [15 empty] | GC assumed 100% @ budget
15 | 51053-00 | Stripe parking areas | Restripe parking lot | GC | Project | 18000 | 18000 | [15 empty] | GC assumed 100% @ budget
16 | 51043-00 | Landscaping | Tree trim away from buildings | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
67 | 51062-00 | Sealants & caulking | Seal seams windows prior to paint | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
66 | 51062-00 | Flashing | Seal seams on parapet walls | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
105 | 51993-01 | Smoke & CO detectors | Per LADBS Declaration- Required complaince with Section 91.8603 LAMC Either confirm they are already installed or plan f | PMC | Project | 11800 | 0 | [15 empty] | GL PMC
110 | 51993-01 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | PMC | Project | 11797 | 855 | [15 empty] | GL PMC
23 | 51045-00 | Landscape Enhancements | Add turf or better landscaping in bare areas | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
124 | 51160-00 | Pool & Spa Area Remodel | Add shade screens to each area along parking lot fence, possibly add turf in planter areas. | PMC | Project | 10000 | 0 | [15 empty] | GL PMC
52 | 51090-00 | Concrete deck / floor fill | Repair cracked areas on catwalks | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
54 | 51077-00 | Repair patio/balcony railings | Repair catwalk railings | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
20 | 51163-00 | Dumpster enclosures | repair and paint compacter enclosure | GC | Project | 8500 | 8500 | [15 empty] | GC assumed 100% @ budget
123 | 51028-00 | Fitness Equipment | Replace treadmill, supplemental items | PMC | Project | 8000 | 1581 | [15 empty] | GL PMC
141 | 51994-00 | Golf Cart | Maintenance Cart | PMC | Project | 7500 | 0 | [15 empty] | GL PMC
53 | 51072-00 | Repair exterior stair treads and stringe | secure railings | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
19 | 51076-00 | Fences & gates - swimming pool | adjust closers on pool gates amd paint pool fence | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
106 | 51073-00 | Impact Glazing/Film for Sliding Glass Do | Per LADBS Declaration- Required complaince with Section 96.302 LAMC Contingency for roughly 15-20 sliding doors in Build | PMC | Project | 5000 | 4800 | [15 empty] | GL PMC
121 | 51169-00 | Clubhouse / Office Furniture | Allowance for supplemental items | PMC | Project | 5000 | 0 | [15 empty] | GL PMC
17 | 51026-00 | Repair / replace swimming pool pumps | Install anti entrapment divise on pool pumps | GC | Project | 4300 | 4300 | [15 empty] | GC assumed 100% @ budget
119 | 51180-00 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | PMC | Project | 2000 | 9210 | [15 empty] | GL PMC
120 | 51169-00 | Clubhouse / Office Remodel | No needs, flooring ok, misc amount for repairs and paint if needed | PMC | Project | 2000 | 0 | [15 empty] | GL PMC
122 | 51160-00 | Fitness Center Remodel | No needs, flooring ok, misc amount for repairs and paint if needed | PMC | Project | 2000 | 0 | [15 empty] | GL PMC
135 | 51168-00 | Mailbox Repairs | Repair broken mailbox doors | GC | Project | 1500 | 1500 | [15 empty] | GC assumed 100% @ budget
22 | 51032-00 | ADA Signage | Equity PCA Item 7.0- A lack of signage identifying the van-accessible parking space at the leasing office was observed | GC | Project | 150 | 150 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1232147
|  |  | CM Fee |  |  | 61607 | 61607
|  |  | Contingency |  |  | 61607 | 61607
|  |  | Capital Plan Total (ex-BTL) |  |  | 1355362
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 25179
BTL (dropped per Adam): $0

## Navigator Villas
Navigator Villas — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
98 | 84207 | 2x2 TH A- Renovated | See Unit Renovation Calculator for detail | PMC | Project | 176906 | 0 | [15 empty] | GL PMC
101 | 84207 | 2x2 TH B- Renovated | See Unit Renovation Calculator for detail | PMC | Project | 168206 | 0 | [15 empty] | GL PMC
99 | 84207 | 2x2 TH B- Classic | See Unit Renovation Calculator for detail | PMC | Project | 68015 | 0 | [15 empty] | GL PMC
96 | 84207 | 2x2 TH A- Classic | See Unit Renovation Calculator for detail | PMC | Project | 52319 | 0 | [15 empty] | GL PMC
97 | 84207 | 2x2 TH A- Classic- Upgraded Flooring Pla | See Unit Renovation Calculator for detail | PMC | Project | 43502 | 0 | [15 empty] | GL PMC
100 | 84207 | 2x2 TH B- Classic- Upgraded Flooring Pla | See Unit Renovation Calculator for detail | PMC | Project | 43502 | 0 | [15 empty] | GL PMC
39 | 84219 | Carports / Garages | Repair and paint 15 Garage doors | GC | Project | 33000 | 33000 | [15 empty] | GC assumed 100% @ budget
154 | 84210 | Common area light fixtures | Wall Pack replacement | GC | Project | 31000 | 31000 | [15 empty] | GC assumed 100% @ budget
64 | 84433 | Asphalt composite shingle roofing | Roof inspection and minor repairs | GC | Project | 29000 | 29000 | [15 empty] | GC assumed 100% @ budget
28 | 84300 | Landscaping | Add landscaping in planters around pool | PMC | Project | 26000 | 14820 | [15 empty] | GL PMC
24 | 84300 | Landscape irrigation | Inspect and repair Irrigation | PMC | Project | 22000 | 4763 | [15 empty] | GL PMC
104 | 84239 | Fire Stops | LowPro - For range top microwaves | PMC | Project | 20570 | 48953 | [15 empty] | GL PMC
146 | 84220 | Replace AC condenser | AC Condenser | PMC | Project | 20000 | 0 | [15 empty] | GL PMC
31 | 84095 | Replace swimming pool deck | Presure wash pool deck (reduced to $6,000) | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
103 | 84106 | Clean Dryer Vents | Dryer Vent Cleaning | GC | Project | 13200 | 13200 | [15 empty] | GC assumed 100% @ budget
32 | 84095 | Repair / replace swimming pool pumps | Anti entrapment devices | GC | Project | 12800 | 12800 | [15 empty] | GC assumed 100% @ budget
95 | 84207 | 2x2 Duplex A- Renovated | See Unit Renovation Calculator for detail | PMC | Project | 8489 | 0 | [15 empty] | GL PMC
34 | 84095 | Fences & gates - swimming pool | Paint pool fence | GC | Project | 8400 | 8400 | [15 empty] | GC assumed 100% @ budget
57 | 84121 | Repair exterior stair railings | Secure railings | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
61 | 84102 | Expansion Joints | Seal expansion joints | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
76 | 84105 | Repair / replace cement fiber siding | replace bad siding and paint to match | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
85 | 84105 | Repair / replace wood trim | Minor trim replacement | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
151 | 84210 | Electrical distribution | Inspect and repair electric pole lights | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
70 | 84433 | Flashing | repair flashing over clay tile | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
19 | 84221 | concrete pavement | replace broken curbs | GC | Project | 6250 | 6250 | [15 empty] | GC assumed 100% @ budget
36 | 84340 | Playground equipment | Add mulch to playground | PMC | Project | 6200 | 574 | [15 empty] | GL PMC
94 | 84207 | 2x2 Duplex A- Classic | See Unit Renovation Calculator for detail | PMC | Project | 5003 | 0 | [15 empty] | GL PMC
131 | 84450 | Security Camera System | Only cameras on the leasing office and gym, no expressed need for additional cameras, maybe add for package lockers | PMC | Project | 5000 | 0 | [15 empty] | GL PMC
113 | 84208 | Clubhouse / Office Remodel | No clubhouse, office in good shape. Misc allowance for paint, etc | PMC | Project | 2000 | 28000 | [15 empty] | GL PMC
114 | 84208 | Clubhouse / Office Furniture | Placeholder for misc items. | PMC | Project | 2000 | 4274 | [15 empty] | GL PMC
22 | 84201 | Add Accessible Van Parking Space | The accessible parking space in front of the leasing office is not van-accessible; | PMC | Project | 450 | 13308 | [15 empty] | GL PMC
116 | 84209 | Install sink drain insulation in the fit | There is no sink drain insulation provided in the fitness area bathroom. | PMC | Project | 250 | 1918 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 864061
|  |  | CM Fee |  |  | 44203 | 44203
|  |  | Contingency |  |  | 20000 | 20000
|  |  | Capital Plan Total (ex-BTL) |  |  | 928264
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 120594
BTL (dropped per Adam): $0

## Presidium Edgestone
Presidium Edgestone — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
139 | 83515 | Green Initiatives | Green Program | GC | Project | 100000 | 100000 | [15 empty] | GC assumed 100% @ budget
14 | 84115 | Sidewalks | Replace crushed granite path with concrete on front of community 600 LF 4 ft wide | GC | Project | 41200 | 41200 | [15 empty] | GC assumed 100% @ budget
17 | 84303 | Landscaping | Add turf and tree rings with rock to tree lines by rec area and parking lot side outside of pool to prevent erosion | GC | Project | 37300 | 37300 | [15 empty] | GC assumed 100% @ budget
107 | 83520 | Add Shower/Tub ADA compliant grab bars | Seller has completed half of the units, budget for 94 remaining units. All units are 1 bath | GC | Project | 32900 | 32900 | [15 empty] | GC assumed 100% @ budget
42 | 84219 | Add Carports | Add 8 carports to test | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
16 | 84205 | Fences & gates - site perimeter | Scrape and Paint perimeter fence. 3700 LF of fence PCA Item- A portion of the perimeter fencing on the south section of | GC | Project | 29600 | 29600 | [15 empty] | GC assumed 100% @ budget
109 | 84211 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | GC | Project | 22206 | 22206 | [15 empty] | GC assumed 100% @ budget
15 | 84302 | Landscape irrigation | Adjust irrigation to not cause erosion to A/C pads | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
19 | 84105 | Pergola court | Pressure wash and seal pavers in seating area | GC | Project | 8700 | 8700 | [15 empty] | GC assumed 100% @ budget
23 | 84517 | Drainage | PCA Item- Ponding was observed along the exterior walls the parking garages M and L, south of Building 8. Regrading of t | GC | Project | 7000 | 7000 | [15 empty] | GC assumed 100% @ budget
18 | 84205 | Fences & gates - swimming pool | Repair and paint | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
20 | 84340 | Playground equipment | Repair, scrape and paint pet park fence | GC | Project | 6800 | 6800 | [15 empty] | GC assumed 100% @ budget
50 | 84120 | Repair Corridor Walls | PCA Item- Cracking was observed in several areas of the corridor walls and ceilings throughout Building 1. This appears | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
70 | 84113 | Sealants & caulking and paint | Cut out and reseal lintels' on garage doors with elastomeric caulk 60 garages | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
29 | 84361 | Repair swimming pool coping | Section of pool coping has separated from the deck, either repair with new sealant or re-set section of coping | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
133 | 84239 | Fire Lane Gates - Regulatory Compliance | PCA Item- All opticom sensors must work, or gates must remain open. On new and existing buildings, the address must be l | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
134 | 84905 | Elevator Permits | PCA Item- Current operation permits were not posted in each elevator cab. Property management should schedule re-inspect | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
135 | 84239 | Fire Riser Inspection | PCA Item- A yellow inspection tag was observed at the fire riser at Building 1 for a defective flow switch. Expired tags | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
137 | 84239 | Fire Alarm Certification | PCA Item - A current annual fire alarm certification tag was not present at the fire alarm control panel. According to t | PMC | Project | 2500 | 0 | [15 empty] | GL PMC
22 | 84115 | Sidewalks | PCA Item- Potential trip hazards consisting of vertical separation were noted at the walkway southwest of the main build | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
136 | 84239 | Fire Extinguisher Inspection | PCA Item- Expired certification tags were present at the fire extinguishers Servicing and re-certification of the fire e | PMC | Project | 1500 | 0 | [15 empty] | GL PMC
24 | 84103 | ADA Parking Signage | PCA Item - ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at th | GC | Project | 1000 | 1000 | [15 empty] | GC assumed 100% @ budget
243 |  | Standardized Calc: |  |  |  | 495 | 0
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 366002
|  |  | CM Fee |  |  | 20103 | 20103
|  |  | Contingency |  |  | 36551 | 36551
|  |  | Capital Plan Total (ex-BTL) |  |  | 422655
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 693
BTL (dropped per Adam): $675,000

## The Arbors
The Arbors — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
136 | 51140-00 | Electrical distribution | Place holder to replace Zinsco Load center in each unit ( Zinsco breakers have not been formally recalled however are co | GC | Project | 380000 | 380000 | [15 empty] | GC assumed 100% @ budget
14 | 51132-00 | Gas, Water, Sanitary Sewer Piping | Active leak on East side of community with temp line to the boilers this will have to be repaired and the gas lines will | GC | Project | 200000 | 200000 | [15 empty] | GC assumed 100% @ budget
63 | 51080-00 | Exterior building | Paint exterior From PCA- 4.3.1- The paint finish on the apartment buildings was noted to be chipping and worn. Based on | GC | Project | 200000 | 200000 | [15 empty] | GC assumed 100% @ budget
41 | 51072-00 | Repair balcony framing & decking | Place Holder to have all balconies inspected and repaired | GC | Project | 160000 | 160000 | [15 empty] | GC assumed 100% @ budget
16 | 51050-00 | Pavement | East side of community has deteriorated drives that need to be milled and overlayed From PCA- 3.2.1- The concrete draina | GC | Project | 108000 | 108000 | [15 empty] | GC assumed 100% @ budget
15 | 51200-00 | Gas Submeter Replacements | Need to replace old submeters, 10% will be inspected each year by Orange County Weights & Measures. Summary from propert | GC | Project | 96000 | 96000 | [15 empty] | GC assumed 100% @ budget
27 | 51172-00 | Carports / Garages | Replace rotted wood and paint parking buildings Exterior only | GC | Project | 95000 | 95000 | [15 empty] | GC assumed 100% @ budget
131 | 51120-00 | HVAC | Contingency for HVAC replacements From PCA- 5.2- While generally reported to be functional, approximately 80% of the uni | GC | Project | 75000 | 75000 | [15 empty] | GC assumed 100% @ budget
107 | 51011-00 | Pool Furniture- 2 pools | New furniture & games | GC | Project | 70000 | 70000 | [15 empty] | GC assumed 100% @ budget
123 | 51110-00 | Common area water heaters / boilers | 3 Boilers are reported to be original, contingency for replacement. 1 goes out frequently and they have a bid for $21k t | GC | Project | 63000 | 63000 | [15 empty] | GC assumed 100% @ budget
24 | 51022-00 | Replace swimming pool deck | Both pool decks need to be cleaned, etched and coated. Replacing decks add $60k totalAt Leasing pool- look at changing e | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
116 | 51168-00 | Package Lockers | Add package locker system | PMC | Project | 50000 | 0 | [15 empty] | GL PMC
18 | 51053-00 | Asphalt Coating | West side of community needs to be seal coated and crack fill From PCA- 3.2.2- Damaged pavement consisting of linear cra | GC | Project | 49000 | 49000 | [15 empty] | GC assumed 100% @ budget
30 | 51992-00 | Termite Treatment & Repairs | WDIR treatment and repairs will be required by lender within 60-90 days of closing. Reference Terminix report and quote | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
119 | 51998-00 | New storage units by leasing office pool | Add 8 new units against car port wall, behind existing storage units | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
53 | 51061-00 | Asphalt composite shingle roofing | Reportedly roofs were replaced on unit building 4 years ago however the ancillary buildings were not done. Allowance fo | GC | Project | 35000 | 35000 | [15 empty] | GC assumed 100% @ budget
22 | 51023-00 | Resurface swimming pool | Resurface two hot tubs | GC | Project | 32000 | 32000 | [15 empty] | GC assumed 100% @ budget
62 | 51160-00 | Interior Hallway painting | Paint hallways and front doors, Stripe stair treads in breezeways to address trip hazards | GC | Project | 32000 | 32000 | [15 empty] | GC assumed 100% @ budget
19 | 51043-00 | Landscaping | Tree trim and landscape maintenance throughout From PCA- 3.2.4- Overgrown trees were observed to be in contact with the | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
137 | 51141-00 | Replace breezeway lights | Replace ceiling lights in breezeways | GC | Project | 28000 | 28000 | [15 empty] | GC assumed 100% @ budget
64 | 51082-00 | Repair / replace wood trim | Replace rotted trim and fascia | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
21 | 51076-00 | Fences & gates - site perimeter | Paint Iron fencing on perimeter of community | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
20 | 51046-00 | Landscape irrigation | Inspect and repair | GC | Project | 21000 | 21000 | [15 empty] | GC assumed 100% @ budget
104 | 51160-00 | Fitness Center Remodel | Fix front door, add lighting, replace fan with something more commercial, add mini split HVAC, new larger TV, add rubber | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
106 | 51011-00 | Pool Area Remodel- 2 pools | Allowance for lighting, other enhancements | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
26 | 51076-00 | Fences & gates - swimming pool | Repair gates and paint At gym pool- fix exit gate eye level hinge so it doesn't protrude | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
61 | 51075-00 | Repair stucco |  | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
96 | 51031-00 | Signage - Entry Monument | Refresh 1 sign, replace the other, replace wall banner facing Fairhaven | PMC | Project | 15000 | 29576 | [15 empty] | GL PMC
101 | 51169-00 | Leasing Office Remodel | Refresh paint on accent wall to brighten space, flooring, add lighting | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
109 | 51160-04 | Picnic/Grill Furniture | Allowance for new grills, furniture & misc items, move concrete furniture from pool to picnic area | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
114 | 51993-00 | Access Control System | Add at entry gates and fitness center | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
117 | 51166-00 | Laundry rooms- one on each side | Paint refresh, replace track lighting, resurface or replace counter, look at adding equipment From PCA- 4.3.3- Worn doo | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
127 | 51134-00 | Sanitary sewer piping | Sewer Pipe Jetting | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
17 | 51053-00 | Stripe parking areas | Re-stripe From PCA- 3.2.2- The seal coat and stall striping appeared to be in fair condition. Based on the observed cond | GC | Project | 14500 | 14500 | [15 empty] | GC assumed 100% @ budget
23 | 51021-00 | Replace swimming pool coping | Deck o seal both pools | GC | Project | 14500 | 14500 | [15 empty] | GC assumed 100% @ budget
54 | 51071-00 | Gutters & downspouts | Clean, re-pitch and resecure gutters | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
60 | 51075-00 | Repair / replace wood siding | Replace rotted siding | GC | Project | 14000 | 14000 | [15 empty] | GC assumed 100% @ budget
25 | 51026-00 | Repair / replace swimming pool pumps | Anti entrapment devices | GC | Project | 12900 | 12900 | [15 empty] | GC assumed 100% @ budget
89 | 51090-00 | Unit Patio Concrete | From PCA- 3.2.3- Uplifting concrete patio slabs was observed at Units 136, 139, and 107. The upheaval appears to be due, | GC | Project | 10500 | 10500 | [15 empty] | GC assumed 100% @ budget
97 | 51032-00 | Signage - Site | Refresh | PMC | Project | 10000 | 17469 | [15 empty] | GL PMC
105 | 51028-00 | Fitness Equipment | Refresh equipment, add stair stepper | PMC | Project | 10000 | 8000 | [15 empty] | GL PMC
110 | 51027-00 | Sports Courts | Resurface, look at pickleball, replace basketball system if that stays | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
28 | 51163-00 | Dumpster enclosures | Repair and Paint | GC | Project | 9000 | 9000 | [15 empty] | GC assumed 100% @ budget
40 | 51077-00 | Repair exterior stair railings | Secure rails | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
43 | 51070-00 | Expansion Joints | Re-seal expansions | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
55 | 51062-00 | Flashing | replace damaged z bar on siding replacement | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
56 | 51062-00 | Sealants & caulking | caulk and seal | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
111 | 51029-00 | Dog Park | Water/Wash Station with concrete pad | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
91 | 51993-01 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | PMC | Project | 7656 | 0 | [15 empty] | GL PMC
90 | 51993-01 | C02 Dectors | Install CO2 detectors | PMC | Project | 7200 | 0 | [15 empty] | GL PMC
120 | 51998-00 | Tools & Equipment | Maintenance tools, equipment, & inventory | PMC | Project | 7000 | 654 | [15 empty] | GL PMC
42 | 51077-00 | Repair patio/balcony railings | Secure rails | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
103 | 51995-00 | Computers | Allowance for new office computers and software, printer, office supplies | PMC | Project | 4000 | 0 | [15 empty] | GL PMC
113 | 51180-00 | Property Photo Shoot | Professional photos and vdeo of remodeled exterior areas, unit interiors when applicable | PMC | Project | 4000 | 5102 | [15 empty] | GL PMC
100 | 51990-00 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | PMC | Project | 3000 | 10357 | [15 empty] | GL PMC
29 | 51169-00 | ADA Accessibility | From PCA- 7.0- Parking areas that provide self-parking for employees and visitors must provide ADA-compliant parking spa | GC | Project | 2000 | 2000 | [15 empty] | GC assumed 100% @ budget
102 | 51995-00 | Leasing Office Furniture | Ok, small allowance | PMC | Project | 2000 | 1243 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2269256
|  |  | CM Fee |  |  | 116966 | 116966
|  |  | Contingency |  |  | 70064 | 70064
|  |  | Capital Plan Total (ex-BTL) |  |  | 2456286
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 77516
BTL (dropped per Adam): $300,000

## Village at Broadstone
Village at Broadstone — 10-Year Capital Plan
Acquired 2024. ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
89 | 0900 - FF&E in Units | A2 | Classic | GC | Project | 532909 | 532909 | [15 empty] | GC assumed 100% @ budget
92 | 0900 - FF&E in Units | B3 | Classic | GC | Project | 427214 | 427214 | [15 empty] | GC assumed 100% @ budget
91 | 0900 - FF&E in Units | B2 | Classic | GC | Project | 420525 | 420525 | [15 empty] | GC assumed 100% @ budget
93 | 0900 - FF&E in Units | C1 | Classic | GC | Project | 272985 | 272985 | [15 empty] | GC assumed 100% @ budget
78 | 0800 - Exterior Wall | Exterior Paint | Paint one coat of SW Superpaint on the siding, trim, shutters, doors, railings and ammenities. | GC | Project | 270000 | 270000 | [15 empty] | GC assumed 100% @ budget
95 | 0900 - FF&E in Units | A2 | Partial Reno- Flooring | GC | Project | 184968 | 184968 | [15 empty] | GC assumed 100% @ budget
90 | 0900 - FF&E in Units | B1 | Classic | GC | Project | 148907 | 148907 | [15 empty] | GC assumed 100% @ budget
97 | 0900 - FF&E in Units | B2 | Partial Reno- Flooring | GC | Project | 139230 | 139230 | [15 empty] | GC assumed 100% @ budget
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | New flooring, paint in the clubhouse to modernize it, using Bell Apex clubhouse as a target finish level. | GC | Project | 130000 | 130000 | [15 empty] | GC assumed 100% @ budget
88 | 0900 - FF&E in Units | A1 | Classic | GC | Project | 129331 | 129331 | [15 empty] | GC assumed 100% @ budget
98 | 0900 - FF&E in Units | B3 | Partial Reno- Flooring | GC | Project | 125874 | 125874 | [15 empty] | GC assumed 100% @ budget
18 | 0200 - Site Utilities & Improvements | Landscape Irrigation & Drainage | Repair, replace and troubleshoot exhisting irrigation system. | GC | Project | 81000 | 81000 | [15 empty] | GC assumed 100% @ budget
99 | 0900 - FF&E in Units | C1 | Partial Reno- Flooring | GC | Project | 78713 | 78713 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | New FF&E | GC | Project | 70000 | 70000 | [15 empty] | GC assumed 100% @ budget
58 | 0700 - Roofing | Roof Repairs | Remove rusted nails on pipe boots across the community. Install new rain collars, screws, and seal bottom flanges. Remov | GC | Project | 57000 | 57000 | [15 empty] | GC assumed 100% @ budget
96 | 0900 - FF&E in Units | B1 | Partial Reno- Flooring | GC | Project | 47544 | 47544 | [15 empty] | GC assumed 100% @ budget
94 | 0900 - FF&E in Units | A1 | Partial Reno- Flooring | GC | Project | 45402 | 45402 | [15 empty] | GC assumed 100% @ budget
118 | 1100- Specialties, Equipment & Furnishings | Pool Furniture | New furniture to replace existing strap, new lounge seating, bar stools, cornhole, other games | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
138 | 1400 - Plumbing | Fire Sprinklers | PCA Item- $40,818- Replace deficient sprinkler heads, per inspection report. | GC | Project | 40818 | 40818 | [15 empty] | GC assumed 100% @ budget
22 | 0200 - Site Utilities & Improvements | Landscaping Enhancements | Remove, add plants. | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
104 | 0900 - FF&E in Units | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | GC | Project | 35063 | 35063 | [15 empty] | GC assumed 100% @ budget
116 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Need new equipment, stairstepper, have rack, need more weights | GC | Project | 35000 | 35000 | [15 empty] | GC assumed 100% @ budget
21 | 0200 - Site Utilities & Improvements | Tree Trim & Shrub Cutback | Trim trees & reduce shrubs where appropriate. Remove dead tree throughout all 3 phases to prevent any future damage to b | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
11 | 0200 - Site Utilities & Improvements | Stripe parking areas | Clean parking lot of debris and oil, crack fill 3000lf. Apply one coat of latex sealer and stripe to existing layout. In | GC | Project | 29000 | 29000 | [15 empty] | GC assumed 100% @ budget
149 | 1600 - Electrical | Replace all balcony ceiling lights & bre | Replace dated fixtures | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
106 | 0900 - FF&E in Units | Drier vents | Clean drier vents | GC | Project | 22500 | 22500 | [15 empty] | GC assumed 100% @ budget
84 | 0800 - Exterior Wall | Window screens | Contingency to remove and replace some of the 1/2 screens on the windows of the residential units and clubhouse. | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
122 | 1100- Specialties, Equipment & Furnishings | Unit Model Update | New furniture in model unit | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
29 | 0200 - Site Utilities & Improvements | Grill stations | Upgrade grill stations with new Bull Outlaw grill heads, granite countertops and gas timers. Repair and paint pergolas. | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
80 | 0800 - Exterior Wall | Shutters | Paint or replace faded shutters | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
119 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Area Remodel | For 2 grill areas outside of pool-Add full covered pergola over grill | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
121 | 1100- Specialties, Equipment & Furnishings | Dog Park | Water/Wash Station with concrete pad Shade sail or pergola | GC | Project | 15000 | 15000 | [15 empty] | GC assumed 100% @ budget
77 | 0800 - Exterior Wall | Bldg. Exterior Cladding | Repair damaged fiber cement siding and trim. Secure shutters. Repair damaged metal fascia, metal row lock flashing and v | GC | Project | 14500 | 14500 | [15 empty] | GC assumed 100% @ budget
101 | 0900 - FF&E in Units | B3 | Premium Reno- SS Appliances & Flooring | GC | Project | 13986 | 13986 | [15 empty] | GC assumed 100% @ budget
17 | 0200 - Site Utilities & Improvements | Sidewalks | Remove and replace approx 375sf of concrete sidewalk. Perform approx. 40EA grinds at lifted sidewalk seams. | GC | Project | 12000 | 12000 | [15 empty] | GC assumed 100% @ budget
100 | 0900 - FF&E in Units | A2 | Premium Reno- SS Appliances & Flooring | GC | Project | 11560 | 11560 | [15 empty] | GC assumed 100% @ budget
143 | 1500- HVAC | HVAC Replacements | Cost to replace two units at $5,200/unit | GC | Project | 10400 | 10400 | [15 empty] | GC assumed 100% @ budget
14 | 0200 - Site Utilities & Improvements | Compactor Ramp | Build an ADA ramp at the compactor. | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
69 | 0800 - Exterior Wall | Soffit/roof fascia repair | Repair where failing, building 5 & others | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
117 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Move gate/fencing in so that the grill area can be used when the pool is closed, add TV above sink under pool grill perg | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
150 | 1600 - Electrical | Fire and Life Safety | Repair pull stations throughout the property. Install a riser room sign where missing, install fire extinguishers and re | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
152 | 1600 - Electrical | Common area light fixtures | Possibly replace remaining halogen parking lot pole lights with LED | GC | Project | 10000 | 10000 | [15 empty] | GC assumed 100% @ budget
28 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Add fence between pool and grill area, repair broken pool gate latch | GC | Project | 9500 | 9500 | [15 empty] | GC assumed 100% @ budget
31 | 0200 - Site Utilities & Improvements | Playground equipment | Add mulch and plastic coat damaged landings | GC | Project | 8000 | 8000 | [15 empty] | GC assumed 100% @ budget
144 | 1500- HVAC | Replace Refrigerant Line Insulation | From MEPFLS Report- Insulation at the refrigerant lines at the outdoor condensing units were observed to be deteriorated | GC | Project | 7500 | 7500 | [15 empty] | GC assumed 100% @ budget
102 | 0900 - FF&E in Units | C1 | Premium Reno- SS Appliances & Flooring | GC | Project | 7156 | 7156 | [15 empty] | GC assumed 100% @ budget
139 | 1400 - Plumbing | Provide Drain Pans for Domestic Hot Wate | From MEPFLS Report- Several domestic water heaters in residential units were observed to be missing drain pans. Partner | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
140 | 1400 - Plumbing | Scope and Clear Sewer Lines | From MEPFLS Report- Recent scoping and clearing of the sanitary drain lines was not reported; therefore, Partner recomme | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
19 | 0200 - Site Utilities & Improvements | Irrigation Repairs | 4 Rain bird 5000, 15 Rain bird 1806, 6 MP Rotator Nozzles, 33 Rain bird Nozzles, 2 Wireless Rain sensors, 7 zones not ru | GC | Project | 4400 | 4400 | [15 empty] | GC assumed 100% @ budget
115 | 1100- Specialties, Equipment & Furnishings | Fitness Center Remodel | Add conduit for power and data cables to TVs | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
120 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Furniture | Add benches by cornhole, misc furniture | GC | Project | 3000 | 3000 | [15 empty] | GC assumed 100% @ budget
109 | 1100- Specialties, Equipment & Furnishings | Signage - Site | Change signage for leasing hours since they are not open Sundays, add hanging clock for Sunday hours | PMC | Project | 250 | 0 | [15 empty] | GL PMC
127 | 1100- Specialties, Equipment & Furnishings | Correct and Close OpenViolation | PCA Item- $100- Open code violation report by building department (expired permit) should be corrected and closed. | PMC | Project | 100 | 0 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 3729334
|  |  | CM Fee |  |  | 186467 | 186467
|  |  | Capital Plan Total (ex-BTL) |  |  | 3915800
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Avenues of Kennesaw
Avenues of Kennesaw — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
77 | 84101 | Exterior building | Repaint community, west side will need special process in order to seal Masonite to prevent future delamination | GC | Project | 733600 | 733600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733600 |  |  |  |  | GC (pay app)
107 | 82480 | Washer & Dryer in Unit | Washer & Dryer Modifications | GC | Project | 493324 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493324 |  |  |  |  | GC tagged, not on pay app
92 | 84207 | Interior Unit Upgrades | Interior Unit Upgrades | GC | Project | 300585 | 0 |  |  | 300585 | 0 | 300585 | 0 | 300585 | 0 | 0 | 0 | 1202340 |  |  |  |  | GC tagged, not on pay app
75 | 84206 | Repair / replace cement fiber siding | Replace rotted Masonite siding with Hardie on west side Equity PCA Item- 4.3.1- Replacement of deteriorated and damaged | GC | Project | 220000 | 220000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 |  |  |  |  | GC (pay app)
80 | 83436 | Windows | Equity PCA Item- 4.3.2- Phased Replacement of dwelling window units from wood framed to aluminum framed - West Campus Eq | GC | Project | 215740 | 203240 |  |  | 215740 | 0 | 215740 | 0 | 215740 | 0 | 215740 | 0 | 2157400 |  |  |  |  | GC (pay app)
151 | 84905 | Water Intrusion Remediation | The SOW will include replacing bathroom vent fans and cleaning dirty AC coils, removing dry water staining and repaintin | GC | Project | 200000 | 200000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 |  |  |  |  | GC (pay app)
64 | 84433 | Asphalt composite shingle roofing | Roof repairs Equity PCA Item- 4.4.1- Allowance for replacement of shingles and possible decking | GC | Project | 190919 | 190919 |  |  | 190918 | 0 | 190918 | 0 | 190918 | 0 | 190918 | 0 | 1909185 |  |  |  |  | GC (pay app)
127 | 84390 | Sports Courts | Resurface 3 courts, fix net and stripe for pickleball as well, add pergola, seating, etc. | GC | Project | 175000 | 175000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 |  |  |  |  | GC (pay app)
55 | 84104 | Repair balcony framing & decking | Repair balconies Equity PCA Item- 4.1- Rout and seal all cracks in the concrete patios. Periodically monitor for further | GC | Project | 150000 | 150000 |  |  | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 330000 |  |  |  |  | GC (pay app)
78 | 84105 | Repair / replace wood trim | Replace damaged trim Equity PCA Item- 4.5- Allowance to refurbish wood trim and balconies around subject property where | GC | Project | 124000 | 124000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124000 |  |  |  |  | GC (pay app)
53 | 84114 | Repair exterior stair treads and stringe | Replace 90 wood and concrete stair treads. Replace damaged railing on stair cases. Equity PCA Item- 4.2- The wood-framed | GC | Project | 94000 | 94000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114000 |  |  |  |  | GC (pay app)
18 | 84204 | Pavement | Repair potholes on both sides of community Equity PCA Item- 3.2.2- Linear cracking, "map", or "alligator | GC | Project | 80000 | 80000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280000 |  |  |  |  | GC (pay app)
14 | 84303 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | PMC | Project | 75000 | 165469 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GL PMC
24 | 84517 | Erosion control | Fill eroded areas around buildings Equity PCA Item- 3.2.4-Significant areas of missing or lost ground cover were noted | GC | Project | 70000 | 70000 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 10000 | 0 | 165000 |  |  |  |  | GC (pay app)
124 | 84360 | Pool Furniture | New furniture at 2 pools | PMC | Project | 70000 | 9000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 |  |  |  |  | GL PMC
56 | 84121 | Repair patio/balcony railings | Repair balcony railings | GC | Project | 68000 | 68000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 |  |  |  |  | GC (pay app)
65 | 83439 | Gutters & downspouts | Clean, repitch, and secure gutters. Ongoing gutter cleanout. Equity PCA Item- 4.4.2- Allowance for replacement of gutte | GC | Project | 66000 | 66000 |  |  | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 156000 |  |  |  |  | GC (pay app)
109 | 84239 | Fire Stops | Mix of Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods and LowPro (Pair covers 4 burner range)- For r | PMC | Project | 61944 | 47962 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61944 |  |  |  |  | GL PMC
27 | 84095 | Resurface swimming pool | Resurface both pools, Replace missing pool tile at water line | GC | Project | 60000 | 60000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GC (pay app)
135 | 84275 | Entry gates | None, can look at adding but there are 4 access drives | GC | Project | 60000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GC tagged, not on pay app
143 | 84209 | Water pressure regulator / back-flow pre | Equity PCA Item- 5.1- Observed water heaters were often not provided with drain pans and lacked discharge piping from th | GC | Project | 52500 | 52500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500 |  |  |  |  | GC (pay app)
20 | 84204 | Asphalt Coating | Crack fill cracks over 1/2 inch | GC | Project | 50000 | 50000 |  |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 200000 |  |  |  |  | GC (pay app)
66 | 84433 | Flashing | Repair damaged flashing | GC | Project | 50000 | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 |  |  |  |  | GC (pay app)
137 | 84450 | Security Camera System | Security Cameras | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
22 | 84115 | Sidewalks | Remove and replace areas of trip hazards Lender PCA (Walkw | GC | Project | 46000 | 46000 |  |  | 3000 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 | 73000 |  |  |  |  | GC (pay app)
153 | 83515 | Green Program - Echelon Water Savings | Installation of aerators on faucets and shower heads | GC | Project | 42312 | 42312 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42312 |  |  |  |  | GC (pay app)
97 | 84106 | Clean Dryer vents | Dryer Vent Cleaning | GC | Project | 39300 | 39300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78600 |  |  |  |  | GC (pay app)
68 | 84433 | Repair/Replace roof pipe vents | Equity PCA Item- 4.4.1- Allowance for replacement of all pipe penetrations lot wide | GC | Project | 38750 | 38750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38750 |  |  |  |  | GC (pay app)
31 | 84361 | Swimming pool lighting | Replace pool lights | GC | Project | 36000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 |  |  |  |  | GC (pay app)
163 | 84210 | Common area light fixtures | Replace wall pack lights | GC | Project | 36000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000 |  |  |  |  | GC (pay app)
162 | 84210 | Electrical distribution | inspect, repair or replace lighting controllers | GC | Project | 33000 | 33000 |  |  | 0 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 73000 |  |  |  |  | GC (pay app)
76 | 84120 | Breezeways - Interior Coordiors | Repair soffits | GC | Project | 32000 | 32000 |  |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 62000 |  |  |  |  | GC (pay app)
57 | 84102 | Expansion Joints | Property Expansion Joints | GC | Project | 32000 | 32000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 |  |  |  |  | GC (pay app)
29 | 84361 | Replace swimming pool deck | Pressure wash pool decks, , level paver trip hazards | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 |  |  |  |  | GC (pay app)
34 | 84219 | Carports / Garages | Repair garage siding and trim Equi | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GC (pay app)
35 | 84111 | Dumpster enclosures | Repair compactor areas | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GC (pay app)
79 | 84206 | Shutters | Replace damaged shutters | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
123 | 84361 | Pool Area Remodel | Turf areas around pool | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
148 | 84400 | Fire Sprinkler Risers | Equity PCA Item- 5.5.1- The following risers were observed to have missing 5-year riser inspection tags: 500E, 600E, 300 | PMC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
19 | 84201 | Stripe parking areas | Stripe Parking Areas | GC | Project | 28000 | 28000 |  |  | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 112000 |  |  |  |  | GC (pay app)
51 | 84430 | Concrete deck / floor fill | Grind and seal cracks in light weight concrete landings | GC | Project | 27000 | 27000 |  |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 57000 |  |  |  |  | GC (pay app)
155 | 83225 | Condensate drain overflow sensors | Equity PCA Item- 5.2- The fan coil units were not fitted with condensate drain overflow sensors. As installed, clogged d | GC | Project | 26200 | 26200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26200 |  |  |  |  | GC (pay app)
164 | 84210 | Electrical Repairs | Equity PCA Item- 5.3- General electrical deficiencies were observed including GFCI outlets , exit lighting, receptacle c | GC | Project | 26000 | 26000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
17 | 84385 | Storm sewer piping | Clear drains around buildings | GC | Project | 25000 | 25000 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 0 | 125000 |  |  |  |  | GC (pay app)
26 | 84434 | Retaining walls | Repair fences on retaining walls Equity PCA Item- 4.1- The segmental retaining walls at the East Aparments contained loo | GC | Project | 25000 | 25000 |  |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 65000 |  |  |  |  | GC (pay app)
113 | 84290 | Signage - Entry Monument | Reface or possibly enlarge 2 monument signs | PMC | Project | 25000 | 25101 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
145 | 84470 | Plumbing Repairs | Plumbing Fixture Leaks, Ongoing repairs due to high number of work orders. Plumbing Repairs: Ongoing repair of water lea | PMC | Project | 23000 | 15546 |  |  | 15000 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | 158000 |  |  |  |  | GL PMC
118 | 84208 | Clubhouse / Office Remodel | Minor refresh & repairs | GC | Project | 20000 | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
119 | 84208 | Clubhouse / Office Furniture | Misc furniture items | PMC | Project | 20000 | 106226 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
32 | 84205 | Fences & gates - swimming pool | Adjust gates and repair gate latches | GC | Project | 18000 | 18000 |  |  | 0 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 58000 |  |  |  |  | GC (pay app)
67 | 84433 | Sealants & caulking | Roof Sealants & Caulking | GC | Project | 18000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 |  |  |  |  | GC (pay app)
149 | 84400 | Fire Sprinklers | Equity PCA Item- 5.5.1- General fire sprinkler deficiencies were observed. The observed general deficiencies included da | PMC | Project | 16030 | 600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16030 |  |  |  |  | GL PMC
158 | 83225 | HVAC Preventative Maintenance | Equity PCA Item- 5.2- The fan coil units were observed with dirty coils and filters at Units 318E, 1017W, 303E. Partner | GC | Project | 15750 | 15750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15750 |  |  |  |  | GC (pay app)
122 | 84190 | Fitness Equipment | Equipment repairs and some new equipment | PMC | Project | 15000 | 3712 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
159 | 83225 | HVAC Preventative Maintenance | Equity PCA Item- 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | GC | Project | 13100 | 13100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13100 |  |  |  |  | GC (pay app)
52 | 84433 | Roof deck | Roof Deck Repairs | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 23000 |  |  |  |  | GC (pay app)
165 | 84239 | Emergency Lighting | Equity PCA Item- 5.3- Emergency lights were not installed at any West buildings. Installation of emergency lighting is r | GC | Project | 10800 | 10800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10800 |  |  |  |  | GC (pay app)
33 | 84203 | Outdoor Kitchen | Pressure wash area and allowance for grill repairs or replacement with charcoal | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
121 | 84190 | Fitness Center Remodel | Paint and misc repairs | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
132 | 84208 | Veritas After School Care | Housing Authority Program (Veritas) - Additional School Room | PMC | Project | 10000 | 53113 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
150 | 84905 | Radon Remediation | Radon Mitigation | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
147 | 84211 | Fire Alarm Deficiencies | Equity PCA Item- 5.5.1- The fire alarm annual inspection report was not provided. Reports often include recommendations | PMC | Project | 9000 | 78487 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 |  |  |  |  | GL PMC
152 | 84209 | Office Faucet | Office Faucet Replacement | GC | Project | 8000 | 8000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC (pay app)
110 | 82460 | Unit deferred maintenance | Equity PCA Item- 8.0- Address potential water intrusion, Unit 403 East. Equity PCA Item- 8.0- Address potential microbia | GC | Project | 6500 | 6500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | GC (pay app)
28 | 84361 | Replace swimming pool coping | Repair or replace broken coping Lender | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
37 | 83520 | ADA Compliance | Equity PCA Item- 7.0- Reconfigure leasing office restroom for ADA compliance | GC | Project | 4500 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  |  |  | GC (pay app)
146 | 84211 | Fire Protection Deficiencies | Equity PCA Item- 5.5.1- General fire protection deficiencies were observed. The observed general deficiencies included | PMC | Project | 4500 | 39243 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  |  |  | GL PMC
133 | 84260 | Mailboxes | Lender PCA (Mailbox Repair): Several mailboxes were noted to contain damaged or missing doors. Repair of the mailboxes i | PMC | Project | 500 | 5894 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GL PMC
144 | 84400 | Sprinkler piping |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 96000 | 0 | 0 | 0 | 192000
23 | 84302 | Landscape irrigation |  | DFM |  | 0 | 0 |  |  | 15000 | 0 | 15000 | 0 | 17000 | 0 | 17000 | 0 | 158999
21 | 83520 | ADA parking & curb cuts |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 75000
25 | 84205 | Fences & gates - site perimeter |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 60000
54 | 84121 | Repair exterior stair railings |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
30 | 84361 | Repair / replace swimming pool pumps |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 20000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 4667854 | [11 empty] | 11463834
|  |  | CM Fee |  |  | 271220 | [11 empty] | 843710
|  |  | Contingency |  |  | 258304 | [11 empty] | 803533
|  |  | Capital Plan Total (ex-BTL) |  |  | 5197378 | [11 empty] | 13111078
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $4,606,835

## Azur Aparments
Azur Aparments — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
73 | 0800 - Exterior Wall | Exterior building | Paint Community Lender PCR Item- $62,400- The exterior walls appeared to be in generally good to fair condition. Isolat | GC | Project | 208000 | 145600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208000 |  |  |  |  | GC (pay app)
12 | 0200 - Site Utilities & Improvements | Pavement | Large areas of asphalt paving Lender PCR Item- $6,000- Several pot holes and areas of “alligatoring”and general deterior | GC | Project | 91000 | 63700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 |  |  |  |  | GC (pay app)
104 | 0900 - FF&E in Units | Turf private yards | Approximately 96 units with yards that we can turf | GC | Project | 86400 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86400 |  |  |  |  | GC tagged, not on pay app
14 | 0200 - Site Utilities & Improvements | Asphalt Coating | Seal coat lot Equity PCA Item 3.2.2- $42,000- The seal coating appeared to be generally worn with several areas of loos | GC | Project | 80000 | 56000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 |  |  |  |  | GC (pay app)
147 | 1500- HVAC | Separate AC condenser | Separate Condensers to achieve 12 inches between units, add equiptment pads as needed | GC | Project | 41600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41600 |  |  |  |  | GC tagged, not on pay app
116 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | New furniture in clubhouse, supplement furniture in office | GC | Project | 40000 | 28000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
120 | 1100- Specialties, Equipment & Furnishings | Pool Furniture & Games |  | GC | Project | 40000 | 28000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
19 | 0200 - Site Utilities & Improvements | Resurface swimming pool |  | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC tagged, not on pay app
50 | 0400 - Structure | Repair exterior stair railings | Repair and Paint | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC tagged, not on pay app
107 | 0900 - FF&E in Units | Unit deferred maintenance | There are 8 down units- all of Building #16 is down due to fire Appx. 57 units noted to have prior water stains on the d | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC tagged, not on pay app
16 | 0200 - Site Utilities & Improvements | Landscape irrigation | Inspect and repair irrigation | GC | Project | 29000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 |  |  |  |  | GC tagged, not on pay app
74 | 0800 - Exterior Wall | Repair / replace wood trim |  | GC | Project | 28000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC tagged, not on pay app
17 | 0200 - Site Utilities & Improvements | Erosion control |  | GC | Project | 26000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC tagged, not on pay app
49 | 0400 - Structure | Repair exterior stair treads and stringe | Replace bad stair treads | GC | Project | 26000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC tagged, not on pay app
11 | 0200 - Site Utilities & Improvements | Storm sewer piping | Replace drainage on pool deck with larger channel drains and connect to proper drain | GC | Project | 25000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC tagged, not on pay app
10 | 0200 - Site Utilities & Improvements | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC tagged, not on pay app
51 | 0400 - Structure | Repair balcony framing & decking |  | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC tagged, not on pay app
75 | 0800 - Exterior Wall | storage room doors - exterior | Replace damaged storage room doors | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC tagged, not on pay app
119 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Look at adding shade areas over pool and grill | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC tagged, not on pay app
121 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Area Remodel | Add grill area with gazebo and furniture by mail area | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC tagged, not on pay app
47 | 0400 - Structure | Concrete deck / floor fill | Entrance landings | GC | Project | 18000 | 12600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
60 | 0700 - Roofing | Asphalt composite shingle roofing | Minor roof repairs | GC | Project | 17000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 |  |  |  |  | GC tagged, not on pay app
61 | 0700 - Roofing | Gutters & downspouts | Clean gutters | GC | Project | 17000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 |  |  |  |  | GC tagged, not on pay app
71 | 0800 - Exterior Wall | Repair / replace cement fiber siding | Replace damaged siding in breezeways | GC | Project | 17000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 |  |  |  |  | GC tagged, not on pay app
23 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair dumpster enclosures | GC | Project | 16000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC tagged, not on pay app
94 | 0900 - FF&E in Units | Clean Drier vents |  | GC | Project | 15600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 |  |  |  |  | GC tagged, not on pay app
124 | 1100- Specialties, Equipment & Furnishings | Dog Park | Look at adding more furniture, jumps, shade | GC | Project | 15000 | 10500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
18 | 0200 - Site Utilities & Improvements | Retaining walls | Replace damaged railroad tie wall | GC | Project | 12000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC tagged, not on pay app
72 | 0800 - Exterior Wall | Tuck-pointing | Tuck point and caulk | GC | Project | 12000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC tagged, not on pay app
13 | 0200 - Site Utilities & Improvements | Stripe parking areas |  | GC | Project | 11000 | 7700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 |  |  |  |  | GC (pay app)
139 | 1400 - Plumbing | Domestic water piping | Insulate main water lines going into buildings Equity PCA Item 5.1- $5,000-The domestic water piping at the central dome | GC | Project | 11000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 |  |  |  |  | GC tagged, not on pay app
155 | 1600 - Electrical | CO Detectors | Residential units were not provided with CO detectors. Residential units had wood burning fireplaces. Partner recommends | PMC | Project | 10400 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 |  |  |  |  | GL PMC
105 | 0900 - FF&E in Units | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | GC | Project | 10048 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10048 |  |  |  |  | GC tagged, not on pay app
39 | 0200 - Site Utilities & Improvements | Arbor Realty Trust Deferred Maintenance | Items noted from lender inspection, items due 11/11/24 & 4/9/25. Property owner only completing November items | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC tagged, not on pay app
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Flooring & paint ok, look at additional HVAC or insulation in roof since it gets very hot in clubhouse. Misc repairs a | GC | Project | 10000 | 7000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
122 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Furniture |  | GC | Project | 10000 | 7000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
127 | 1100- Specialties, Equipment & Furnishings | Access Control System | Office alarm and restore night drop box for keys needed | GC | Project | 10000 | 7000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
22 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair and paint Equity PCA Item 3.2.7- $7,500- Partner observed some areas of damaged fencing along the northwest peri | GC | Project | 9600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 |  |  |  |  | GC tagged, not on pay app
136 | 1100- Specialties, Equipment & Furnishings | Golf Cart | Need leasing cart | GC | Project | 9000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 |  |  |  |  | GC tagged, not on pay app
20 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Deck o seal | GC | Project | 8600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8600 |  |  |  |  | GC tagged, not on pay app
152 | 1600 - Electrical | Electrical distribution | Repair house panels issues | GC | Project | 8500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC tagged, not on pay app
25 | 0200 - Site Utilities & Improvements | Fences & Gates - Site Perimeter | Lender PCR Item- $7,500- Partner observed some areas of damaged fencing along the northwest perimeter as well as a porti | GC | Project | 7500 | 5250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC (pay app)
148 | 1500- HVAC | HVAC Condensing Refrigerant Line Insulat | Equity PCA Item 5.2- $7,500- Many of the ground mounted AC condensing units were found to have insulation missing from t | GC | Project | 7500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC tagged, not on pay app
154 | 1600 - Electrical | Fire Extinguishers | Lender PCR Item- $1,500- The common fire extinguisher at the resident postal boxes structure had an expired tag from 201 | GC | Project | 7100 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7100 |  |  |  |  | GC tagged, not on pay app
15 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts | Replace ADA signage | GC | Project | 6800 | 4760 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 |  |  |  |  | GC (pay app)
21 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | Anti entrapment devices | GC | Project | 6800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 |  |  |  |  | GC tagged, not on pay app
63 | 0700 - Roofing | Sealants & caulking |  | GC | Project | 6800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 |  |  |  |  | GC tagged, not on pay app
153 | 1600 - Electrical | Unit Electrical Panel Repairs | Equity PCA Item 5.3- $5,200- During the inspection it was noted that many of the electrical panels within the apartments | GC | Project | 5200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200 |  |  |  |  | GC tagged, not on pay app
62 | 0700 - Roofing | Flashing |  | GC | Project | 3400 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400 |  |  |  |  | GC tagged, not on pay app
114 | 1100- Specialties, Equipment & Furnishings | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | GC | Project | 2500 | 1750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 |  |  |  |  | GC (pay app)
130 | 1100- Specialties, Equipment & Furnishings | Grills | Misc repairs | GC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC tagged, not on pay app
24 | 0200 - Site Utilities & Improvements | Accessibility | Lender PCR Item- $1,350- Lack of accessible toilet room at the leasing office including lack of lever hardware, toilet g | GC | Project | 1650 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 |  |  |  |  | GC tagged, not on pay app
48 | 0400 - Structure | Wall framing |  | GC | Project | 1500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GC tagged, not on pay app
103 | 0900 - FF&E in Units | Unit Exhaust Fan | Equity PCA Item 5.2- $500- Apartment 502 was noted to have a missing exhaust fan in one of its bathrooms that did not ha | GC | Project | 500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GC tagged, not on pay app
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1227998 | [11 empty] | 1227998
|  |  | CM Fee |  |  | 77884 | [11 empty] | 77884
|  |  | Contingency |  |  | 329680 | [11 empty] | 329680
|  |  | Capital Plan Total (ex-BTL) |  |  | 1635562 | [11 empty] | 1635562
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Cambridge Square
Cambridge Square — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
73 | 84433 | Asphalt composite shingle roofing | Half of the roofs have been redone recently. Still need to replace 9 roofs throughout property | GC | Project | 495000 | 495000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495000 |  |  |  |  | GC (pay app)
93 | 84101 | Exterior building | Paint community LPCA - Select areas of building exteriors were observed to have dryrot damage in locations throughout th | GC | Project | 250000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 |  |  |  |  | GC (pay app)
102 | 84207 | Interior Update Placeholder | Contingency for interiors | PMC | Project | 225000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 |  |  |  |  | GL PMC
94 | 84105 | Repair / replace wood trim | Replace rotted fascia and trim | GC | Project | 185000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 |  |  |  |  | GC (pay app)
85 | 84206 | Repair / replace cement fiber siding | Replace damaged horizontal siding where needed | GC | Project | 88500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88500 |  |  |  |  | GC (pay app)
86 | 84206 | Repair / replace wood shingles | Replace any damage faux cedar shake | GC | Project | 85000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 |  |  |  |  | GC (pay app)
28 | 84205 | Fences & gates - site perimeter | Replace fences between units | GC | Project | 75000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
130 | 84190 | Fitness Center Remodel | Convert other clubhouse (high ceiling) into a fitness center | GC | Project | 75000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
18 | 84095 | Resurface swimming pool | Two pools - resurface 2 pools | GC | Project | 50000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
19 | 84361 | Pool maintenance | Deck cleaning & Equipment repair/replacement | GC | Project | 50000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
17 | 84204 | Asphalt Coating | Fill asphalt cracks, seal coat | GC | Project | 47500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47500 |  |  |  |  | GC (pay app)
141 | 84260 | Mailboxes | Current boxes are damaged | GC | Project | 46500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46500 |  |  |  |  | GC (pay app)
40 | 84111 | Dumpster enclosures | Replace exisiting dumpster enclosures with new structures throughout property | GC | Project | 45000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
95 | 84105 | Shutters | Repair/replacement of damaged shutters throughout | GC | Project | 45000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
16 | 83307 | Landscape Cleanup and Enhancements | Tree trim | PMC | Project | 42500 | 17654 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42500 |  |  |  |  | GL PMC
22 | 84204 | Pavement | Replace areas of potholes | GC | Project | 36000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
69 | 84121 | Repair patio/balcony railings | Scrap and paint, secure | GC | Project | 36000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
78 | 84202 | Gutters & downspouts | Secure and clean gutters | GC | Project | 36000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
79 | 84433 | Flashing | Flashing around chimneys to be replaced as needed | GC | Project | 35000 | 35000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
167 | 84210 | Replace breezeway lights | Replace doorway sconces | GC | Project | 32100 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32100 |  |  |  |  | GC (pay app)
68 | 84104 | Repair balcony framing & decking | SB 721 needed, minor repairs included. Anything more extensive will need a change order. Catwalk railing potentially too | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
166 | 84210 | Common area light fixtures | Replace pole lights with LED | GC | Project | 28000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (pay app)
165 | 84210 | Electrical distribution | Inspect and repair lighting controllers on all buildings | GC | Project | 26000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
80 | 84433 | Sealants & caulking | Roof Sealants and Caulking | GC | Project | 25000 | 25000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
127 | 84208 | Office Clubhouse | Clubhouse upgrades - Move office to pool clubhouse room. | GC | Project | 25000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
26 | 84300 | Landscape irrigation | Inspect and repair irrigation | GC | Project | 22500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 |  |  |  |  | GC (pay app)
23 | 84201 | Stripe parking areas | Stripe Parking Area | GC | Project | 22000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
118 | 84239 | Fire Stops | Install Fire Stops | PMC | Project | 21105 | 65853 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21105 |  |  |  |  | GL PMC
156 | 84209 | Seismic Strapping | Seismic Strapping - LPCA - The water heaters lacked seismic bracing straps. Provision of adequate seismic bracing is rec | GC | Project | 20100 | 20100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20100 |  |  |  |  | GC (pay app)
25 | 84115 | Sidewalks | LPCA (PR-90) - Potential trip hazards consisting of vertical and horizontal separation and significantly cracked and dam | GC | Project | 20000 | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
90 | 84102 | Repair stucco | Repair Exterior Stucco - Keep existing look of property. | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
144 | 84275 | Security/ fire alarm systems | Install controlled access system for common areas | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
70 | 84102 | Expansion joints | Seal expansion joints | GC | Project | 14000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
67 | 84121 | Repair exterior stair railings | Scrap and paint, secure stair railings | GC | Project | 12500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 |  |  |  |  | GC (pay app)
119 | 83236 | CO Detectors | Install CO Detectors | PMC | Project | 12060 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12060 |  |  |  |  | GL PMC
66 | 84114 | Repair exterior stair treads and stringe | Scrap and paint, secure stair treads | GC | Project | 8500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
24 | 83520 | ADA parking & curb cuts | LPCA - Add van accessible parking stall near leasing office | GC | Project | 6000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (pay app)
100 | 83301 | WDO | Wood Destroying Organisms- LPCA - Select areas of building exteriors were observed to have dryrot damage in locations th | PMC | Project | 2500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 |  |  |  |  | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2315365 | [11 empty] | 2315365
|  |  | CM Fee |  |  | 121557 | [11 empty] | 121557
|  |  | Contingency |  |  | 115768 | [11 empty] | 115768
|  |  | Capital Plan Total (ex-BTL) |  |  | 2552690 | [11 empty] | 2552690
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 10365
BTL (dropped per Adam): $2,440,608

## Candlewood
Candlewood — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
43 | 51172-00 | Carports / Garages | Significant wood rotting at stand alone carports. Need to replace all rotted wood and fix all damaged stucco on all 3 st | GC | Project | 340000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000 |  |  |  |  | GC tagged, not on pay app
104 | 51080-00 | Exterior Paint | Item No. 11: Budget for pressure washing, preparation, caulking, stucco wall repairs, and painting of building exteriors | GC | Project | 283500 | 283500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632169 |  |  |  |  | GC (pay app)
16 | 51053-00 | Asphalt Coating | Fill, seal and coat of parking area at back of property. Mix of asphalt and concrete repairs needed (approx 80% asphalt) | GC | Project | 173000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173000 |  |  |  |  | GC tagged, not on pay app
97 | 51080-00 | Exterior building repairs | Due to extensive repairs at the 3 stand alone carports need to repaint entire structures to match exisiting color scheme | GC | Project | 135000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 |  |  |  |  | GC tagged, not on pay app
141 | 51160-00 | Pool Area Remodel | Building A: replace umbrellas and furniture Building B: repurpose middle space and replace plants. | PMC | Project | 75000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GL PMC
15 | 51043-00 | Landscape Cleanup and Enhancements | Item No. 1: Trim trees along the perimeter throughout the site to prevent the accumulation of debris and tree leaves ove | PMC | Project | 50000 | 10850 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
30 | 51023-00 | Resurface swimming pool | Item No. 6: Allowance to resurface both pools and one spa, including repairing any cracks around the pool decks and repl | GC | Project | 50000 | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
64 | 51062-00 | Roof framing | Replace/repair any wood rotting on carport roof decking on all 3 stand alone carports. | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC tagged, not on pay app
179 | 51141-00 | Common Area Light Fixtures | Change all patio/balcony lights to LED flush mounted lights | GC | Project | 28350 | 28350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28350 |  |  |  |  | GC (pay app)
44 | 51134-00 | Storm Sewer Piping | 50% of storm water drains on balconies need to be repaired/replaced due to paint/damage. | GC | Project | 25988 | 25988 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25988 |  |  |  |  | GC (pay app)
82 | 51071-00 | Gutters & downspouts | Replace gutters at the 3 stand alone carports | GC | Project | 22500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 |  |  |  |  | GC tagged, not on pay app
128 | 51180-00 | Radon Mitigation | 1.1.5 - Elevated levels of radon were detected in Building 9830 - Unit 123 and Building 9850 - Unit 118. The sponsor has | PMC | Project | 20000 | 28975 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
21 | 51053-00 | Stripe parking areas | Restripe Parking Area including carports. | GC | Project | 19000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 |  |  |  |  | GC tagged, not on pay app
178 | 51140-00 | Electrical - Load Centers | Item No. 23: Ensure that all apartment load centers have the proper index identifying circuit number and devices served. | GC | Project | 9450 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9450 |  |  |  |  | GC tagged, not on pay app
66 | 51062-00 | Roof deck | Roof Deck Repairs | GC | Project | 7500 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC (pay app)
158 | 51993-01 | Electrical Load Tests | Item No. 29: Perform the required 5-year load test. Posted placard expired 6/11/2018. | PMC | Project | 7200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 |  |  |  |  | GL PMC
176 | 51140-00 | Electrical distribution systems | Item No. 21: Allowance to provide periodic maintenance of the electrical distribution systems including infrared scans, | GC | Project | 6000 | 0 |  |  | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 24000 |  |  |  |  | GC tagged, not on pay app
86 | 51062-00 | Roof Maintenance | Item No. 15: Allowance for annual roof maintenance on all roof areas including inspection and repair of flashing, sealan | GC | Project | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5500 | 0 | 5500 | 0 | 114000 |  |  |  |  | GC tagged, not on pay app
27 | 51076-00 | Fences & gates - site perimeter | Item No. 4: Allowance for periodic fencing repairs, including property perimeter wood slat fencing and CMU fencing along | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 15000 |  |  |  |  | GC (pay app)
126 | 52111-00 | Unit deferred maintenance (cont.) - 1 | Item No. 17: Allowance for repairs in bathrooms showing evidence of minor ceiling damage. Seen in Units C311 with tape i | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
105 | 51993-01 | Balconies | Item No. 13: Engage a specialty consultant to survey 100% of apartment balconies associated with observed deterioration | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
127 | 52111-00 | Unit deferred maintenance (cont.) -2 | Item No. 18: Allowance for remediation of organic growth in isolated areas, especially in bathrooms where exhaust fans a | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
157 | 51993-01 | Elevator Tests | Item No. 28: Perform the annual elevator tests and post the most recent certificates. Cab certificates expired 6/29/2024 | PMC | Project | 4800 | 28842 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 |  |  |  |  | GL PMC
177 | 51140-00 | Meter Banks - Rust and Corrosion | Item No. 22: Remove rust and corrosion from the multi-meter assemblies and paint with a matching rust inhibitive paint. | GC | Project | 4500 | 32000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  |  |  | GC (pay app)
125 | 52111-00 | Unit deferred maintenance | Item No. 3: Repair cracked concrete at Unit A119 patio. | GC | Project | 2500 | 2500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 |  |  |  |  | GC (pay app)
69 | 51072-00 | Repair balcony framing & decking | 3.2.7 - The balcony deck surface at unit A303 was buckled and standing water observed. The deck surface should be repair | GC | Project | 2250 | 2250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 |  |  |  |  | GC (pay app)
70 | 51062-00 | Roof Drainage | 3.2.9 - Areas of roof ponding were noted on all roofs. Although ponding may decrease the useful life of the roof, deckin | GC | Project | 2250 | 2250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 |  |  |  |  | GC (pay app)
17 | 51050-00 | Asphalt Pavement | 3.1.6 - Isolated asphalt cracking was observed in the rear drive aisles and areas near the entrance gates. Repair is rec | GC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC tagged, not on pay app
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1325788 | [11 empty] | 1816457
|  |  | CM Fee |  |  | 77528 | [11 empty] | 149852
|  |  | Contingency |  |  | 132579 | [11 empty] | 132579
|  |  | Capital Plan Total (ex-BTL) |  |  | 1535895 | [11 empty] | 2098887
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 194606
BTL (dropped per Adam): $1,048,000

## Canyon Villa
Canyon Villa — 10-Year Capital Plan
10-yr figures pending review (source-plan inconsistency)
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
42 | 83000-3400 | Exterior building Paint | Paint Community EPCA - Perform maintenance needs on the exterior elevated elements as recommended in the EEE Report prep | GC | Project | 354000 | 45646 | [15 empty] | GC (GL fallback)
32 | 83000-7600 | SB721 Repairs | Various SB721 repairs | GC | Project | 100000 | 12894 | [15 empty] | GC (GL fallback)
37 | 83000-6100 | Roof Cleanup and treatment | Roof Cleaning & Moss Treatment | GC | Project | 72000 | 9284 | [15 empty] | GC (GL fallback)
23 | 80000-6800 | Termite treatment | Includes inspection/treatment of Drywood, Subterranean and Dampwood termites) LPCA - According to provided information, | GC | Project | 54900 | 7079 | [15 empty] | GC (GL fallback)
61 | 80000-4800 | Replace transformer | EPCA - Contact the local utility to replace one utility transformer exhibiting significant corrosion. The unit is neares | GC | Project | 50000 | 6447 | [15 empty] | GC (GL fallback)
16 | 83000-2000 | Asphalt Coating | R&R 1500 SF of potholes in concrete pavement LPCA - Cracking in the concrete driving lanes and parking areas was observe | GC | Project | 45000 | 5802 | [15 empty] | GC (GL fallback)
28 | 83000-2400 | Repair balcony framing & decking | Repair damaged patio framing | GC | Project | 38000 | 4900 | [15 empty] | GC (GL fallback)
62 | 80000-4800 | Install GFCI protection | EPCA - Install GFCI protection on the counter-height kitchen power outlets. Only 1 protected outlet was observed in each | PMC | Project | 36600 | 0 | [15 empty] | GL PMC
35 | 83000-6100 | Modified bitumen membrane roof Repairs | Roof repairs on 35 roofs | GC | Project | 35000 | 4513 | [15 empty] | GC (GL fallback)
25 | 83000-2800 | Concrete deck / floor fill | Seal cracks in landing | GC | Project | 32000 | 4126 | [15 empty] | GC (GL fallback)
26 | 83000-7100 | Repair exterior stair treads and stringe | Repair stair tread and stringers | GC | Project | 32000 | 4126 | [15 empty] | GC (GL fallback)
38 | 800 | Gutters & downspouts | Clean and secure gutters and down spouts | GC | Project | 32000 | 4126 | [15 empty] | GC (GL fallback)
60 | 83000-3200 | Common area light fixtures | replace exterior building lights and post lights | GC | Project | 32000 | 4126 | [15 empty] | GC (GL fallback)
19 | 83000-3900 | Fences & gates - site perimeter | Repair Iron fence and paint | GC | Project | 25000 | 3224 | [15 empty] | GC (GL fallback)
34 | 83000-6100 | Roofing | Tune up clay tile and repair flashing LPCA - Organic materials were observed on the clay/concrete mission tiles. Cleanin | GC | Project | 25000 | 3224 | [15 empty] | GC (GL fallback)
39 | 83000-6100 | Sealants & caulking | Seal & Caulk Roofing Areas | GC | Project | 25000 | 3224 | [15 empty] | GC (GL fallback)
43 | 83000-3700 | Repair / replace wood trim | Replace all rotted fascia throughout property | GC | Project | 25000 | 3224 | [15 empty] | GC (GL fallback)
17 | 83000-2000 | Stripe parking areas | Stripe parking lot LPCA - Pavement markings and striping appeared to be in fair condition. Reapplication of pavement mar | GC | Project | 22000 | 2837 | [15 empty] | GC (GL fallback)
49 | 80000-1700 | Fire/Life Safety System - Smoke/CO alarm | EPCA - Budget to replace the existing combination smoke/CO alarms based on age and useful life. The NFPA requires that s | PMC | Project | 20720 | 0 | [15 empty] | GL PMC
48 | 80000-1700 | Security/ fire alarm systems | LPCA (PR-90) - An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and rec | GC | Project | 20000 | 2579 | [15 empty] | GC (GL fallback)
52 | 80000-5200 | Galvanized Pipe Replacement | EPCA - Allowance for periodic domestic and sanitary piping repairs or replacements based on age and EUL (year 1 upfront, | PMC | Project | 20000 | 0 | [15 empty] | GL PMC
59 | 80000-4800 | Electrical distribution | Repair electric to pole lights and photo cells | GC | Project | 20000 | 2579 | [15 empty] | GC (GL fallback)
63 | 80000-4800 | Preventative Maintenance - Breaker Panel | EPCA - Perform preventative maintenance on the electrical systems throughout the site, including opening breaker panels, | PMC | Project | 18300 | 0 | [15 empty] | GL PMC
45 | 80000-6400 | Fire Protection | Fire Stops | PMC | Project | 17934 | 509 | [15 empty] | GL PMC
27 | 83000-7100 | Repair exterior stair railings | repair and secure stair railings | GC | Project | 16000 | 2063 | [15 empty] | GC (GL fallback)
29 | 83000-2400 | Repair patio/balcony railings | Secure all balcony railings LPCA - Paint along the balcony railing was observed to be chipping and peeling. Additionally | GC | Project | 16000 | 2063 | [15 empty] | GC (GL fallback)
36 | 83000-6100 | Flashing | Replace damaged drip edge on balconies. | GC | Project | 16000 | 2063 | [15 empty] | GC (GL fallback)
18 | 83000-2800 | Sidewalks | Repair Trip Hazards LPCA - Cracking in the concrete walkways was observed adjacent to Units 121, 140, 167, and 288. Repa | GC | Project | 15000 | 1934 | [15 empty] | GC (GL fallback)
21 | 83000-2600 | Carports / Garages | Repair carports | GC | Project | 15000 | 1934 | [15 empty] | GC (GL fallback)
41 | 83000-3700 | Repair stucco | Repairs to damaged stucco | GC | Project | 14000 | 1805 | [15 empty] | GC (GL fallback)
20 | 83000-5300 | Fences & gates - swimming pool | Repair and paint | GC | Project | 12000 | 1547 | [15 empty] | GC (GL fallback)
30 | 83000-7500 | Retaining Wall repairs | ESCA - Repair chips and broken sections of concrete on top of the concrete retaining wall. Repair to consist of placing | GC | Project | 4000 | 516 | [15 empty] | GC (GL fallback)
51 | 80000-5100 | Back-flow preventer | EPCA - The three irrigation backflow preventer assemblies were last inspected in February 2024 and are now past due for | PMC | Project | 1500 | 0 | [15 empty] | GL PMC
31 | 83000-7500 | Retaining Wall repairs | ESCA - Implement a protocol for regular maintenance and cleaning of the drainage system including removal of plants | GC | Project | 400 | 52 | [15 empty] | GC (GL fallback)
47 | 83000-4300 | Signage - Entry Monument | EPCA - Provide signage directing individuals from the accessible parking spaces to the leasing office entrance doors. | PMC | Project | 300 | 0 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1262654
|  |  | CM Fee |  |  | 64822 | 8358
|  |  | Contingency |  |  | 33781 | 4356
|  |  | Capital Plan Total (ex-BTL) |  |  | 1361257
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): amount pending review

## Chaparral
Chaparral — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
19 | 51050-00 | Asphalt pavement | Mill and overlay asphalt throughout entire property Includes Equity PCA Item 3.2.2- Asphalt Pavment; Mill and overlay ap | GC | Project | 740000 | 740000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740000 |  |  |  |  | GC (pay app)
21 | 51053-00 | Asphalt Coating | Double seal coat entire pavement throughout property | GC | Project | 525000 | 525000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 |  |  |  |  | GC (pay app)
97 | 51150-00 | Interior Update Placeholder | Placeholder Expense | PMC | Project | 296000 | 1706 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296000 |  |  |  |  | GL PMC
157 | 51158-00 | Natural Gas Seismic Shutoff Devices | Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices to prevent dang | GC | Project | 148000 | 148000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148000 |  |  |  |  | GC (pay app)
24 | 51023-00 | Resurface swimming pool | Resurface both pools, not including spas (completed recently) | GC | Project | 67500 | 67500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 |  |  |  |  | GC (pay app)
161 | 51141-00 | Common area light fixtures | Replace all pole lights with LED and change tennis court lights with LED | GC | Project | 55750 | 55750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55750 |  |  |  |  | GC (pay app)
27 | 51027-00 | Sport Court | Resurface and stripe for tennis & pickleball. Fencing and lighting repairs. Includes Equity PCA Item 3.2.9- Tennis Court | GC | Project | 55000 | 55000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 |  |  |  |  | GC (pay app)
41 | 51020-00 | Playground equipment | Playground Addition | GC | Project | 40000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC tagged, not on pay app
163 | 51993-00 | Fire Alarm Panels | Equity PCA Item- 5.5.2- Fire alarm control panels (FACP) at Buildings L and N were observed to with active trouble alarm | PMC | Project | 40000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GL PMC
26 | 51076-00 | Fences & gates - swimming pool | Scrap, prime and paint both pool fences. Add metal fence topper to extend height on gates and improve gate security. Pro | GC | Project | 37600 | 37600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37600 |  |  |  |  | GC (pay app)
20 | 51053-00 | Stripe parking areas | Stripe throughout property | GC | Project | 35000 | 35000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
137 | 51168-00 | Package Lockers (Defer Costs) | Accept small packages at office, otherwise deliver to door. Look at adding package lockers in enclosed room by 2nd pool. | GC | Project | 29600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29600 |  |  |  |  | GC tagged, not on pay app
160 | 51140-00 | Electrical distribution | Electrical Panels | GC | Project | 27000 | 27000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 |  |  |  |  | GC (pay app)
22 | 51091-00 | ADA parking & curb cuts | Restripe all handicap parking spots | GC | Project | 25000 | 25000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
120 | 51033-00 | Signage - Building identification | Unit number signage needed at doors | PMC | Project | 22200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 |  |  |  |  | GL PMC
18 | 51043-00 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | PMC | Project | 20000 | 7420 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
162 | 51141-00 | Replace breezeway lights | Replace all breezeway lights in stairwells with LED | GC | Project | 16500 | 16500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 |  |  |  |  | GC (pay app)
42 | 51160-04 | Picnic areas | Tables & Seating | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC tagged, not on pay app
129 | 51160-04 | Picnic/Grill Area Remodel | Remove and install new stand alone grils throughout property | GC | Project | 8500 | 8500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
144 | 51994-00 | Golf Cart | Have leasing cart but could use new one | PMC | Project | 8000 | 16562 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GL PMC
25 | 51021-00 | Replace swimming pool coping | Deck-o-seal coping around both pools | GC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (pay app)
125 | 51160-00 | Fitness Center Remodel (Defer Costs) | Paint & Reupholster ($5,000) | GC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC tagged, not on pay app
140 | 51993-00 | Security Camera System | Have 23 cameras, need 2-4 more cameras to cover side views | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
23 | 51091-00 | Sidewalks | Replace cracked sidewalks throughout property | GC | Project | 4500 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  |  |  | GC (pay app)
156 | 51122-00 | HVAC Exterior Condensing Unit Refrigeran | Equity PCA Item- 5.1- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | GC | Project | 3700 | 3700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 |  |  |  |  | GC (pay app)
38 | 51076-00 | Fences & gates - swimming pool | Reinforce or increase size of pool gate gate posts at both pools | GC | Project | 3000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GC (pay app)
31 | 51085-00 | Retaining walls | Equity PCA Item 3.2.5- Install weepholes on southern perimeter concrete masonry retaining walls | GC | Project | 2400 | 2400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 |  |  |  |  | GC (pay app)
146 | 51158-00 | Domestic Water Service Main | Equity PCA Item- 5.1- The east domestic water service backflow prevention device was observed with an active drip leak. | GC | Project | 2000 | 2000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC (pay app)
34 | 51021-00 | West Poolhouse | Equity PCA Item 3.2.9- Eliminate step between pool surround and poolhouse interior to provide wheelchair accessible rout | GC | Project | 1250 | 1250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 |  |  |  |  | GC (pay app)
154 | 51120-00 | HVAC inspection and maintenance | Add HVAC pads to 3 units at the leasing office. Currently sitting on ground with debris around. | GC | Project | 750 | 750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 |  |  |  |  | GC (pay app)
147 | 51158-00 | Domestic Water Hose Bibs | Equity PCA Item- 5.1- Hose bibs were observed with active drip leaks on the exterior risers of apartment buildings E and | GC | Project | 500 | 500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GC (pay app)
36 | 51026-00 | Pool Equipment | Includes Equity PCA Item 3.2.9- Repair active leaks observed at East and West pool heater PVC distribution piping | GC | Project | 300 | 300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 |  |  |  |  | GC (pay app)
45 | 51158-00 | ADA Accessibility | Equity PCA Item- 7.1- Provide compliant scald-protection underneath leasing office men's restroom sink | GC | Project | 200 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | GC (pay app)
148 | 51158-00 | Water Heater T&P Valve Discharge | Equity PCA Item- 5.1- The water heater at unit A9 was observed lacking piping from the T&P valve to the building exterio | GC | Project | 200 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | GC (pay app)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2241450 | [11 empty] | 2241450
|  |  | CM Fee |  |  | 116447 | [11 empty] | 116447
|  |  | Contingency |  |  | 87488 | [11 empty] | 87488
|  |  | Capital Plan Total (ex-BTL) |  |  | 2445384 | [11 empty] | 2445384
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 27056
BTL (dropped per Adam): $0

## Crestmark
Crestmark — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
90 | 84101 | Paint/finish | Repaint full site | PMC | Project | 334000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434200 |  |  |  |  | GL PMC
85 | 84113 | Siding- Water Intrusion | Address water intrusion near bay windows - 32 units | GC | Project | 160000 | 80000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 |  |  |  |  | GC (pay app)
16 | 84204 | Asphalt Coating | Seal Coat and Crack Fill | PMC | Project | 144000 | 6391 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144000 |  |  |  |  | GL PMC
88 | 84105 | Repair / replace vinyl siding | Repair Vinyl siding / trim / flashing | PMC | Project | 85000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 |  |  |  |  | GL PMC
95 | 84105 | Repair / replace wood trim | Replace rotten wood throughout | PMC | Project | 83500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83500 |  |  |  |  | GL PMC
17 | 84095 | Resurface swimming pool | Resurface both pools | GC | Project | 79000 | 79000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79000 |  |  |  |  | GC (pay app)
29 | 84303 | Landscaping | Curb Appeal | PMC | Project | 75000 | 88873 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GL PMC
136 | 84390 | Sports Courts | Convert tennis court to pickle ball court | GC | Project | 75000 | 22500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
141 | 84005 | Mailboxes | New Mailboxes | PMC | Project | 65000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 |  |  |  |  | GL PMC
132 | 84360 | Pool Area Furniture | Split between the two pools | PMC | Project | 60000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GL PMC
134 | 84203 | Picnic/Grill Area Remodel | Pool 1: $25K & Pool 2: $15K | PMC | Project | 40000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GL PMC
119 | 84239 | Fire Stops | Fire stops | PMC | Project | 36740 | 15411 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36740 |  |  |  |  | GL PMC
74 | 84433 | Asphalt composite shingle roofing | Standard roof tune up on ridge, vault and pipe jacks | GC | Project | 32000 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
18 | 84361 | Replace swimming pool deck | Level pavers and presure wash | GC | Project | 31000 | 31000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31000 |  |  |  |  | GC (pay app)
42 | 84195 | Playground | Replace/repair playground equipment next to blacktop courts | PMC | Project | 30000 | 2300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
69 | 84104 | Repair balcony framing & decking | Repair 3 landing with structural issues | GC | Project | 30000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
127 | 84116 | Clubhouse | Update color scheme and game room | PMC | Project | 30000 | 3425 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
149 | 83375 | Golf Cart | Maintenace carts; property has 2 maintenance carts & 1 6-seat leasing | PMC | Project | 30000 | 12840 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
21 | 84201 | Stripe parking areas | Restripe of parking lot | PMC | Project | 28000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GL PMC
20 | 84219 | Carports / Garages | Repairs to garage door - The garage door at 14C was observed damaged and should be repaired or replaced at this time. | PMC | Project | 26000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GL PMC
15 | 84201 | Pavement | Repair potholes | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77606 |  |  |  |  | GC (pay app)
37 | 84361 | Pool Area | Pool bathroom upgrades - 1st Call to verify scope | PMC | Project | 25000 | 39730 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
103 | 83236 | Install CO Detectors | CO detectors were not observed in the units. The fireplaces are reportedly gas-fired units and require a CO detector. In | PMC | Project | 20040 | 35518 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20040 |  |  |  |  | GL PMC
130 | 84190 | Fitness Center: New Equipment | Supplement existing equipment & redo bathrooms | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GL PMC
120 | 84304 | Unit deferred maintenance | Repair mechanical closet subfloors | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
167 | 84210 | Replace breezeway lights | Inspect and replace emergency lighting | GC | Project | 19000 | 19000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 |  |  |  |  | GC (pay app)
19 | 84361 | Fences & gates - swimming pool | Repair fence and gates | GC | Project | 18000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
79 | 84202 | Gutters & downspouts | Clean and repitch gutters throughout property | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
108 | 84106 | Clean Drier vents | clean dryer vents and replace damaged covers | GC | Project | 16700 | 16700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16700 |  |  |  |  | GC (pay app)
53 | 84102 | Concrete deck / floor fill | Rout and seal landings | GC | Project | 16000 | 16000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
161 | 84217 | Replace AC condenser | Add insulation to Condensing unit lines | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
112 | 83330 | Install GCI Outlets | Non-GFCI outlets were observed in the pool restrooms and some secondary bathrooms of the apartment units, including 8-81 | PMC | Project | 10020 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10020 |  |  |  |  | GL PMC
30 | 84206 | Pressure wash Breezeways | Pressure Washing - Breezeways | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
123 | 84290 | Signage - Entry Monument | Noted during concept walk | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
28 | 84205 | Fences & gates - site perimeter | The motor for automated gates at Crestmark Drive were reported to be inoperable. Repairs are recommended at this time. | PMC | Project | 7000 | 1823 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 |  |  |  |  | GL PMC
68 | 84121 | Repair exterior stair railings | Secure railings | GC | Project | 7000 | 7000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 |  |  |  |  | GC (pay app)
70 | 84121 | Repair patio/balcony railings | Secure railings | GC | Project | 7000 | 7000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 |  |  |  |  | GC (pay app)
24 | 84115 | Sidewalks | PNA - Sidewalk Cracks LPCA - Sidewalks were observed to be in good to fair condition with cracks noted in isolated area | PMC | Project | 5000 | 1650 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
27 | 84111 | Fences & gates - compactor | The gates on the trash compactor enclosures are either damaged or missing. Repairs are recommended at this time. | PMC | Project | 5000 | 1302 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
124 | 84103 | Signage - Site | Added based on Kevin DD email feedback | PMC | Project | 5000 | 2062 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
25 | 84300 | Landscape irrigation | A leak from the irrigation system was observed at the site stairs between building 5 and the leasing office/clubhouse bu | PMC | Project | 1500 | 877 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
87 | 84105 | Flashing/Siding | A section of metal flashing is missing on the west side of the clock tower. Repairs are recommended. | PMC | Project | 700 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 |  |  |  |  | GL PMC
145 |  | Security Camera System |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1755200 | [11 empty] | 1923006
|  |  | CM Fee |  |  | 92148 | [11 empty] | 97288
|  |  | Contingency |  |  | 87760 | [11 empty] | 22760
|  |  | Capital Plan Total (ex-BTL) |  |  | 1935108 | [11 empty] | 2043054
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 98579
BTL (dropped per Adam): $0

## Cypress Bend
Cypress Bend — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
80 | 84101 | Exterior building | PNA - Exterior painting. PCA 4.3.1- Exterior cleaning, painting, sealing | GC | Project | 195000 | 167100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 |  |  |  |  | GC (pay app)
20 | 84205 | Fences & gates - site perimeter | PNA - Repair perimater fencing | GC | Project | 43000 | 43000 |  |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 73000 |  |  |  |  | GC (pay app)
55 | 84121 | Repair exterior stair railings | PNA - Replace damaged railing on staircases. PCA 4.5 - Rust and corrosion was observed on the metal stringers, handrai | GC | Project | 39000 | 39000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 |  |  |  |  | GC (pay app)
19 | 84517 | Erosion control | PNA - Fill in erosion areas around buildings. | GC | Project | 29000 | 29000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 |  |  |  |  | GC (pay app)
112 | 84239 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | PMC | Project | 22440 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22440 |  |  |  |  | GL PMC
17 | 84204 | Pavement | PNA - Repair Potholes PCA 3.2.2 - Areas of linear cracking and isolated spalling around linear cracks was observed at t | GC | Project | 21000 | 21000 |  |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 61000 |  |  |  |  | GC (pay app)
113 | 84304 | Unit deferred maintenance | Major Repairs Floors 18 Bedrooms 13 Living Rooms 3 Kitchens 2 Kitchen Countertop Resurface 2 Interior Door Replacement E | PMC | Project | 21000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GL PMC
155 | 84220 | AC condenser | PNA - Reposistion A/C condensers to achive 12" between units | GC | Project | 20000 | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
133 | 84280 | Unit Model Update | New furniture in model unit | PMC | Project | 18000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GL PMC
21 | 84111 | Dumpster enclosures | PNA - Repair dumpster enclosures PCA 3.2.7 - Areas of damaged wood fencing was observed east adjacent to Building 12, n | GC | Project | 16000 | 16000 |  |  | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
159 | 84217 | HVAC Preventative Maintenance | PCA - 5.2 Supply and return air vents were observed with buildup of debris and need cleaning in buildings 10 and 12 due | GC | Project | 15600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 |  |  |  |  | GC tagged, not on pay app
22 | 84201 | Stripe parking areas | Stripe Parking | GC | Project | 15000 | 4500 |  |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
16 | 84303 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 37500 |  |  |  |  | GL PMC
54 | 84110 | Concrete deck / floor fill | Grind and seal cracks in light weight concrete landings | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
82 | 84106 | Drier vents | PNA - Clean all dryer vents. PCA 5.2 Some of the dryer vents appeared to be damaged and full of debris. Cracked or vents | GC | Project | 14400 | 14400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 |  |  |  |  | GC (pay app)
18 | 84115 | Sidewalks | PNA - Remove and replace areas of trip hazards. PCA 3.2.3 -Areas of linear cracking was observed in the concrete walkwa | GC | Project | 14000 | 14000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
67 | 84433 | Asphalt composite shingle roofing | PNA - Roof tune up. PCA 4.4.1 - Unit 606 was observed to have water staining on the ceiling indicative of a roof leak. | GC | Project | 13000 | 13000 |  |  | 13000 | 0 | 13000 | 0 | 25000 | 0 | 25000 | 0 | 214000 |  |  |  |  | GC (pay app)
131 | 84195 | Playground | PCA 3.2.9 - Partner observed that the ground cover beneath the play equipment consisted of grass. According to the Consu | PMC | Project | 11250 | 12048 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 |  |  |  |  | GL PMC
116 | 84103 | Signage | Budget for wall signage, current is dated. | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
143 | 83440 | Tools & Equipment | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools | PMC | Project | 10000 | 866 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
81 | 84105 | Repair / replace wood trim | PNA - Replace damaged trim | GC | Project | 8000 | 8000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
144 | 83375 | Golf Cart | Don't have any carts, nowhere to park them. Could budget for one | PMC | Project | 8000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GL PMC
68 | 84202 | Gutters & downspouts | PNA - Clean, repitch, and secure gutters. PCA 4.4.2 - Building 1 was observed to have a missing gutter system on the so | GC | Project | 7500 | 7500 |  |  | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 17500 |  |  |  |  | GC (pay app)
78 | 84206 | Repair / replace cement fiber siding | PNA - Siding repairs. PCA 4.3.1 - Damaged fiber cement lap board siding was observed on the east elevation of Building | GC | Project | 7500 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC (pay app)
110 | 82206 | Garabage Disposals | Interior Replacements | PMC | Project | 7500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GL PMC
79 | 84120 | Breezeways | PNA - Repair soffits | GC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
70 | 84433 | Sealants & caulking | Roof Sealants | GC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (pay app)
69 | 84433 | Flashing | Repair damaged flashing | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
122 | 84306 | Clubhouse / Office Furniture | No clubhouse, allowance for office furniture | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
123 | 82140 | Computers | Budget for 2 replacement | PMC | Project | 4000 | 9877 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 |  |  |  |  | GL PMC
121 | 84208 | Clubhouse / Office Remodel | PCA 7.1 - Installation of grab bars adjacent to the commode in the leasing office | PMC | Project | 500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GL PMC
117 | 84103 | Signage - Site | PCA 7.1 - Installation of ADA vertical identification parking signage | PMC | Project | 450 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 |  |  |  |  | GL PMC
24 | 84221 | ADA parking & curb cuts | PCA 7.1 - Installation of an access aisle adjacent to the accessible parking stall north adjacent to Building 10 | GC | Project | 250 | 250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 |  |  |  |  | GC (pay app)
158 | 84220 | PTAC Unit |  | DFM |  | 0 | 0 |  |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 623390 | [11 empty] | 1190890
|  |  | CM Fee |  |  | 38857 | [11 empty] | 136420
|  |  | Contingency |  |  | 77339 | [11 empty] | 77339
|  |  | Capital Plan Total (ex-BTL) |  |  | 739586 | [11 empty] | 1404648
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $1,537,500

## Cypress Bend Village
Cypress Bend Village — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
69 | 84101 | Exterior building | PNA - Repaint community PCA 4.3.1 - Areas of damaged siding were observed on the east and south elevations of Building | GC | Project | 198000 | 185750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396000 |  |  |  |  | GC (pay app)
145 | 84220 | Replace forced air unit | PCA 5.2 - Split-system furnace/fan coil, Replace | GC | Project | 78000 | 23400 |  |  | 78000 | 0 | 78000 | 0 | 78000 | 0 | 78000 | 0 | 780000 |  |  |  |  | GC (pay app)
15 | 84385 | Storm sewer piping | PNA - Add drainage behing 4 building and connect to downspouts | GC | Project | 75000 | 75000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
131 | 84450 | Security Camera System | Manager says system is ok, maybe add license plate reader and a few cameras | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
21 | 84095 | Resurface swimming pool | Swimming Pool | GC | Project | 42000 | 18600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84000 |  |  |  |  | GC (pay app)
47 | 84114 | Repair exterior stair treads, stringers, | PNA - Replace damaged railing on stair cases PCA 4.5 - Areas of rust and corrosion was observed on the steel stingers an | GC | Project | 35000 | 35000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
117 | 84361 | Pool Area Remodel | Add gazebo, turf next to clubhouse | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
104 | 84304 | Unit Deferred Maintenance | 2 Units have mold: (1-601, 1-610) 97% of water heaters > 10 years old Major Repairs Flooring repair: 17 Bedrooms 18 Livi | PMC | Project | 26000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GL PMC
116 | 84190 | Fitness Equipment | Add equipment | PMC | Project | 25000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
17 | 84204 | Stripe parking areas | Stripe Parking | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 69000 |  |  |  |  | GC (pay app)
20 | 83517 | Erosion control / Tree trimming | PNA - Fill eroded areas around buildings; PCA - 3.2.4- Areas of soil erosion were observed on the northeast corner ad e | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 54000 |  |  |  |  | GC (pay app)
103 | 84239 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | PMC | Project | 23375 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23375 |  |  |  |  | GL PMC
16 | 84204 | Pavement | PNA - Repair Potholes PCA 3.2.2 - Linear cracking was observed in the drive aisles and parking spaces at the entrance d | GC | Project | 20000 | 20000 |  |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
124 | 84280 | Model Unit Update | New furniture in model unit | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
146 | 84218 | Replace AC condenser | PCA 5.2 -Many of the condensing units were installed in an improper manner. Limited units were observed set on pads that | GC | Project | 20000 | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
57 | 84433 | Asphalt composite shingle roofing | PNA - Roof tune up | GC | Project | 18000 | 18000 |  |  | 18000 | 0 | 18000 | 0 | 25000 | 0 | 25000 | 0 | 229000 |  |  |  |  | GC (pay app)
48 | 84121 | Repair patio/balcony railings | PNA - Repair balcony railings | GC | Project | 18000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
91 | 84106 | Drier vents | PNA - Clean drier vents and repair as needed. PCA 5.2 - Some of the dryer vents appeared to be damaged and full of debri | GC | Project | 16660 | 24500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16660 |  |  |  |  | GC (pay app)
25 | 84111 | Dumpster enclosures | PNA - Repair compactor areas | GC | Project | 16000 | 16000 |  |  | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 0 | 36000 |  |  |  |  | GC (pay app)
118 | 84360 | Pool Furniture | New furniture | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
123 | 84130 | Dog Park | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
19 | 84221 | Sidewalks | PNA - remove and replace areas of trip hazards PCA 3.2.3 - Potential tripping hazards due to heaved concrete sections w | GC | Project | 14400 | 14400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 |  |  |  |  | GC (pay app)
18 | 84204 | ADA parking & curb cuts | PNA - Add rail around ADA Ramp to units PCA - Installation of vertical identification signage at parking space | GC | Project | 14000 | 14000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
23 | 84361 | Replace swimming pool deck | PNA - Pressure wash pool decks | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
46 | 84206 | Concrete deck / floor fill | PNA - Grind and seal cracks in light weight concrete landings | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
134 | 84905 | Restoration & Remediation | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
135 | 83375 | Golf Cart | Budget for maintenance cart. Don't have leasing cart, budget for one in case it is needed | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
58 | 84202 | Gutters & downspouts | PNA - Clean, repitch, and secure gutters | GC | Project | 9500 | 9500 |  |  | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 24500 |  |  |  |  | GC (pay app)
70 | 84105 | Repair / replace wood trim | Replace damaged trim | GC | Project | 8000 | 8000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
49 | 84102 | Expansion Joints | Building Expansion Joints | GC | Project | 8000 | 8000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC (pay app)
112 | 84208 | Clubhouse / Office Remodel | No clubhouse, allowance for office | PMC | Project | 7500 | 3871 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GL PMC
22 | 84361 | Replace swimming pool coping | PNA - Replace deck-o-seal | GC | Project | 6500 | 6500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 |  |  |  |  | GC (pay app)
24 | 84361 | Fences & gates - swimming pool | PNA - Adjust gates and repair gate latches | GC | Project | 6500 | 6500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | GC (pay app)
68 | 84120 | Breezeways | Repair soffits | GC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
59 | 84433 | Flashing | PNA - Repair damaged flashing | GC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (pay app)
60 | 84433 | Sealants & caulking | Roof Sealants | GC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (pay app)
114 | 83265 | Computers | Budget for 3 replacement | PMC | Project | 6000 | 75832 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GL PMC
26 | 84205 | Fences & gates - site perimeter | PCA 3.2.7 - Isolated areas of damaged fencing was observed north adjacent to Building 12, south adjacent to Building 4, | GC | Project | 980 | 980 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 2980 |  |  |  |  | GC (pay app)
28 | 84095 | Repair / replace swimming pool pumps |  | DFM |  | 0 | 0 |  |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 932415 | [11 empty] | 2283415
|  |  | CM Fee |  |  | 52133 | [11 empty] | 159171
|  |  | Contingency |  |  | 103516 | [11 empty] | 103516
|  |  | Capital Plan Total (ex-BTL) |  |  | 1088065 | [11 empty] | 2546102
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $900,000

## David Ave
David Ave — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
172 | 51140-00 | Electrical Panel Disconnects & Meter Ban | Phased replacement of 2 main meter banks Equity PCA Item- 5.3- The main disconnects and meter banks were manufactured by | GC | Project | 120000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 |  |  |  |  | GC (pay app)
70 | 51077-00 | Increase rail height | Raise catwalk rail height to 42" per SB 721 report | GC | Project | 100000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  |  |  |  | GC (pay app)
101 | 51080-00 | Exterior building Paint | Paint community | GC | Project | 98000 | 98000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198980 |  |  |  |  | GC (pay app)
18 | 51023-00 | Resurface swimming pool | Resurface two pools | GC | Project | 92000 | 27600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122000 |  |  |  |  | GC (pay app)
17 | 51053-00 | Asphalt Coating | Seal asphalt Includes Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in fair con | GC | Project | 61000 | 61000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64840 |  |  |  |  | GC (pay app)
69 | 51072-00 | Repair balcony framing & decking | Repairs for 2 walkways and stairwells per SB721 report from Medro, contingency for additional repairs PCA 4.5- As no doc | GC | Project | 55000 | 49862 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 |  |  |  |  | GC (pay app)
102 | 51082-00 | Repair / replace wood trim Repair or rep | Replace rotted fascia and trim PCA 4.2. - Repair or replace damaged wood trim and stucco at elevated walkways and soffi | GC | Project | 36000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
164 | 51990-00 | Green Program - Energy Retrofit | Echelon upfront costs | PMC | Project | 35760 | 2436 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35760 |  |  |  |  | GL PMC
159 | 51130-00 | Galvanized Pipe Replacement | Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone to developing pinhol | GC | Project | 30000 | 0 |  |  | 0 | 0 | 30000 | 0 | 0 | 0 | 30000 | 0 | 90000 |  |  |  |  | GC tagged, not on pay app
94 | 51075-00 | Repair / replace wood shingles | Replace window walls with Hardie Horizontal | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
56 | 51092-00 | Install metal hardware connections at po | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces. | GC | Project | 22500 | 22500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 |  |  |  |  | GC (pay app)
58 | 51070-00 | 3040 David – Engineered repair design to | PCA 4.2. -3040 David – Engineered repair design to remediate damaged beam at TUP. | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
68 | 51077-00 | Repair exterior stair railings | Secure railings on all catwalks | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
82 | 51062-00 | Sealants & caulking | Prep and seal exterior | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
140 | 51011-00 | Pool Furniture | No furniture, need to add for 2 pools | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
20 | 51076-00 | Fences & gates - swimming pool | Adjust closers on pool gates | GC | Project | 12800 | 12800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800 |  |  |  |  | GC (pay app)
19 | 51026-00 | Repair / replace swimming pool pumps | Anti entrapment devices | GC | Project | 12600 | 3780 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12600 |  |  |  |  | GC (pay app)
21 | 51172-00 | Carports / Garages | Repair and paint carport supports | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
183 |  | Carpet Replacement |  | DFM |  | 11000 | 0 |  |  | 11000 | 0 | 11000 | 0 | 11000 | 0 | 11000 | 0 | 110000
188 |  | Appliance Replacement |  | DFM |  | 10208 | 0 |  |  | 10208 | 0 | 10208 | 0 | 10208 | 0 | 10208 | 0 | 102080
59 | 51070-00 | Remediation of exposed wood beams exhibi | PCA 4.2 - Remediation of exposed wood beams exhibiting deterioration at TUP regions. | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
184 |  | Vinyl Replacement |  | DFM |  | 8250 | 0 |  |  | 8250 | 0 | 8250 | 0 | 8250 | 0 | 8250 | 0 | 82500
60 | 51070-00 | Replace edge beams in-kind at TUP areas, | PCA 4.2. Replace edge beams in-kind at TUP areas, where needed. | GC | Project | 8000 | 8000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC (pay app)
81 | 51071-00 | Gutters & downspouts Replace missing or | Secure and clean gutters PCA 4.4.1. -Replace missing or crushed downspouts. | GC | Project | 8000 | 8000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC (pay app)
160 | 51130-00 | Stormwater Pipe Repair | Number based on actual bid; $285 per cleanout, est. 10 cleanouts. $402 per storm drain, 4 cleanouts. $129 per flow test, | GC | Project | 6746 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6746 |  |  |  |  | GC tagged, not on pay app
47 | 51992-00 | Termite Remediation | Drywood termites treatment | PMC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GL PMC
141 | 51160-04 | Picnic/Grill Area Remodel | Allowance for grill/outdoor kitchen upgrades | PMC | Project | 6000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GL PMC
162 | 51130-00 | Natural Gas Seismic Shutoff | Will confirm with Gas utility company if needed Equity PCA Item- 5.1- The natural gas services were not equipped with au | GC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (pay app)
191 |  | Wall-mounted unit heaters, Ongoing Repla |  | DFM |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
174 | 51140-00 | Electrical service and distribution, Ong | Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B (Recomme | GC | Project | 5000 | 1500 |  |  | 4000 | 0 | 4000 | 0 | 4000 | 0 | 4000 | 0 | 41000 |  |  |  |  | GC (pay app)
61 | 51090-00 | Repair or replace damaged concrete tread | PCA 4.2.- Repair or replace damaged concrete treads at stairs. | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
139 | 51160-00 | Pool Area Remodel | Allowance | PMC | Project | 5000 | 2400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
161 | 51134-00 | Sanitary Sewer Piping | Equity PCA Item- 5.1- The sanitary waste system was original to construction. Typically, sections were replaced as neede | PMC | Project | 4000 | 7211 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 |  |  |  |  | GL PMC
57 | 51090-00 | Rout and seal cracks in concrete slab-on | PCA 4.1 Rout and seal cracks in concrete slab-on-grade. | GC | Project | 3000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GC (pay app)
62 | 51077-00 | Clean and repaint steel stair frame with | PCA 4.2. -Clean and repaint steel stair frame with surface corrosion. | GC | Project | 3000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GC (pay app)
158 | 51130-00 | Back-flow preventer | Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. Municipalities typically r | PMC | Project | 3000 | 2184 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GL PMC
190 |  | Through-wall AC Units, Ongoing Replaceme |  | DFM |  | 2500 | 0 |  |  | 2500 | 0 | 2500 | 0 | 2500 | 0 | 2500 | 0 | 25000
136 | 51160-06 | Common area FF&E, Replace | FF& E - Common Areas | GC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 10000 |  |  |  |  | GC tagged, not on pay app
142 | 51160-04 | Picnic/Grill Furniture | Allowance for furniture | PMC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GL PMC
138 | 51169-00 | Leasing Office Restroom Accessibility | Equity PCA Item- 7.1- The leasing office restroom is provided with a full vanity at the lavatory. Replacement of the va | GC | Project | 1550 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550 |  |  |  |  | GC tagged, not on pay app
171 | 51993-01 | Fire Department Violations - Engage expe | Lender PCA Item- There are outstanding fire department violations. CBRE recommends engaging an expeditor to clear all ou | PMC | Project | 1500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
63 | 51062-00 | Replace missing vent tops. | PCA4.4.1 - Replace missing vent tops. | GC | Project | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GC (pay app)
173 | 51140-00 | Replace Electrical Meter Panel at Buildi | Equity PCA Item- 5.3- A metal panel was missing on the wiring trough at the meter enclosure at Building 3. The missing p | PMC | Project | 500 | 156 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GL PMC
86 | 51061-00 | Roof replacement - Roof B & C |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 30432 | 0 | 30432 | 0 | 91296
90 | 51062-00 | Annual roof maintenance |  | DFM |  | 0 | 0 |  |  | 5270 | 0 | 5270 | 0 | 5270 | 0 | 5270 | 0 | 47430
80 | 51062-00 | Roof- Asphalt Shingles |  | DFM |  | 0 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 45000
89 | 51061-00 | Roof replacement - Roof F |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 14700 | 0 | 14700 | 0 | 44100
85 | 51061-00 | Roof replacement - Roof A |  | DFM |  | 0 | 0 |  |  | 15216 | 0 | 15216 | 0 | 0 | 0 | 0 | 0 | 30432
88 | 51061-00 | Roof replacement - Roof E |  | DFM |  | 0 | 0 |  |  | 7350 | 0 | 7350 | 0 | 7350 | 0 | 0 | 0 | 22050
79 | 51062-00 | Roof- Built Up Roof |  | DFM |  | 0 | 0 |  |  | 2000 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 18000
163 | 51130-00 | Domestic Hot Water Heater, Replace |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
34 | 51026-00 | Pool Filtration/Circulation Equipment |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
135 | 51169-00 | Leasing office floor/wall finishes, Repl |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 3500
71 | 51993-01 | CA SB721 Re-inspection |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 901914 | [11 empty] | 1804164
|  |  | CM Fee |  |  | 47350 | [11 empty] | 94719
|  |  | Contingency |  |  | 45096 | [11 empty] | 90208
|  |  | Capital Plan Total (ex-BTL) |  |  | 994360 | [11 empty] | 1989091
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 218059
BTL (dropped per Adam): $0

## Elliot Baymeadows
Elliot Baymeadows — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
95 | 84101 | Exterior Building Painting | Heavy pressure wash and prep for mildew and paint community | GC | Project | 675000 | 405000 |  |  | 0 | 0 | 0 | 0 | 158400 | 0 | 158400 | 0 | 991800 |  |  |  |  | GC (pay app)
105 | 84207 | Unit Interior Replacements (Classics) | Classic Units | GC | Project | 466000 | 0 |  |  | 466000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932000 |  |  |  |  | GC tagged, not on pay app
104 | 84207 | Unit Interior Replacements (Partials) | Partial Units | GC | Project | 414000 | 0 |  |  | 414000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828000 |  |  |  |  | GC tagged, not on pay app
75 | 84433 | Asphalt composite shingle roofing | Roof tune up | GC | Project | 160000 | 160000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 |  |  |  |  | GC (pay app)
15 | 84303 | Landscape Cleanup and Enhancements | Tree trim, foliage cut back throughout | GC | Project | 100000 | 90000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  |  |  |  | GC (pay app)
44 | 84390 | Sports Courts PCA 3.2.9 - Repair tennis | Placeholder for repurposing of sports court area. Could include turf installation for soccer Tennis/sports court were ob | GC | Project | 75000 | 75000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
166 | 84210 | Common area light fixtures | Pole lights, buildings lights, and amenities courts | GC | Project | 72000 | 72000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 |  |  |  |  | GC (pay app)
29 | 84095 | Resurface swimming pool | Two pools - Resurface | GC | Project | 70000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 |  |  |  |  | GC tagged, not on pay app
162 | 84220 | Replace AC condenser | Contingent HVAC replacement - projections taken from EPCA | GC | Project | 69490 | 0 |  |  | 0 | 0 | 69490 | 0 | 69490 | 0 | 69490 | 0 | 625410 |  |  |  |  | GC tagged, not on pay app
135 | 84361 | Pool Area Remodel | Allocation for two pools | PMC | Project | 50000 | 19703 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
67 | 84114 | Repair exterior stair treads and stringe | Repair failing wood stair cases | GC | Project | 43000 | 80000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43000 |  |  |  |  | GC (pay app)
100 | 84102 | Chimney Cap Covers | Fabricate and replace rusted out and failing chimney covers | GC | Project | 43000 | 43000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43000 |  |  |  |  | GC (pay app)
77 | 84433 | Flashing | Roof Flashing | GC | Project | 40000 | 40000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
133 | 84195 | Fitness Center Remodel | New equipment, refurbishment of existing equipment | PMC | Project | 40000 | 49616 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GL PMC
86 | 84102 | Repair / replace wood siding | Replace failing siding | GC | Project | 38000 | 30400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 |  |  |  |  | GC (pay app)
161 | 84218 | Replace forced air unit | Level and replace AC pads | GC | Project | 35200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35200 |  |  |  |  | GC tagged, not on pay app
136 | 84360 | Pool Furniture | Allocation for two pools | PMC | Project | 35000 | 537 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GL PMC
167 | 84210 | Replace breezeway lights | Entry lights | GC | Project | 32100 | 32100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32100 |  |  |  |  | GC (pay app)
21 | 84219 | Parking equipment | Need more info from Mark | GC | Project | 32000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC tagged, not on pay app
24 | 84302 | Landscape irrigation PCA 3.2.11 - Evalua | Irrigation in fair to poor condition. Electrical wiring in the control panel appeared to be cut and maintenance personne | PMC | Project | 32000 | 22824 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GL PMC
115 | 84239 | Fire Stops | Fire Stops | PMC | Project | 29920 | 59840 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29920 |  |  |  |  | GL PMC
23 | 84115 | Sidewalks | Sidewalk Repairs | GC | Project | 28000 | 21000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (pay app)
96 | 84113 | Repair / replace wood trim | Wood Trim Repairs | GC | Project | 28000 | 22400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (pay app)
22 | 84204 | Parking pavement PCA 3.2.2 - Repair poth | Linear cracking, "map" or "alligator" cracking, and pothole formation were noted throughout the drive aisles adjacent to | GC | Project | 26500 | 32500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26500 |  |  |  |  | GC (pay app)
106 | 84106 | Dryer Vents | Clean dryer vents | GC | Project | 26400 | 26400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 |  |  |  |  | GC (pay app)
169 | 84210 | Electrical service and distribution, Ong | CBRE recommends verifying that the non-GFCI outlets in the secondary bathrooms are on the same circuit as the GFCI outle | GC | Project | 23000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 |  |  |  |  | GC tagged, not on pay app
20 | 84201 | Stripe parking areas PCA 7.0 - install p | Parking Lot Striping | GC | Project | 22000 | 22000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
25 | 84517 | Erosion control | Site Erosion Control | GC | Project | 22000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC tagged, not on pay app
82 | 84433 | Sealants & caulking and paint | Roof Sealants & Caulking | GC | Project | 20000 | 16000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
134 | 84230 | Package lockers | Add Lockers | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
141 | 84280 | Unit Model Update | New furniture in model unit | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
170 | 83236 | Smoke detectors PCA 5.5.2 - Replace all | In dwelling units observed, smoke detectors were only mounted in the hallways or living room areas, not in the sleeping | PMC | Project | 17600 | 5535 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17600 |  |  |  |  | GL PMC
168 | 84330 | Electrical Panel Disconnects & Meter Ban | Electrical systems are approaching 40-years-old and are exposed to the weather. IR scans can identify loose connections, | GC | Project | 14000 | 12600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
49 | 83301 | WDO Repairs PCR - WDO Repairs - WDO repo | Subsequent to the site visit, a WDO inspection was conducted by Busy Bee Termite, and their findings indicate evidence o | PMC | Project | 12000 | 356 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GL PMC
157 | 84385 | Sanitary Sewer Piping PCA 5.1 - Sewer sc | Due to the age of the site, Partner recommends a sewer scoping of all waste lines. This scoping can tell if there are br | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
171 | 83236 | CO Detectors PCR (PR-90) - Provide CO de | Carbon Monoxide detectors were not observed as required. A recommendation has been included to install CO detectors in a | PMC | Project | 8800 | 2767 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800 |  |  |  |  | GL PMC
48 | 83301 | Termite treatment PCR - Termite damage r | Subsequent to the site visit, a WDO inspection wasconducted by Busy Bee Termite, and their findings indicate visible sig | PMC | Project | 7500 | 223 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GL PMC
158 | 84476 | Domestic Hot Water Heater Replacement | Contingent hot water heater replacement | PMC | Project | 7040 | 4600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7040 |  |  |  |  | GL PMC
26 | 84205 | Fences & gates - site perimeter PCR - Re | The motor for the automated gates were reported and observed to be inoperable. Repairs are recommended at this time. | PMC | Project | 2500 | 1600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 |  |  |  |  | GL PMC
47 | 83301 | Termite Repairs PCR - Termite Damage Rep | Evidence of termite damage was observed on the door frame of the poop pump room, near the fitness center building. All d | PMC | Project | 700 | 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 |  |  |  |  | GL PMC
159 | 84218 | PCR - Water heater repairs | Minor damage was observed at the water heater pan in units 609 and 1709. A cover plate for the control panel is also mis | PMC | Project | 700 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 |  |  |  |  | GL PMC
34 | 83270 | Maintenance Shop PCR - Overhead door rep | Minor damage was observed on the overhead door trim at the maintenance shop. Repairs are recommended | PMC | Project | 350 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 |  |  |  |  | GL PMC
17 | 84204 | Asphalt Overlay |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215000
79 | 84433 | Roof- Asphalt Shingles |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 246125 | 0 | 984500
183 | 82201 | 82201 - Water Heater Replacement |  |  |  | 0 | 0 |  |  | 0 | 0 | 7040 | 0 | 7040 | 0 | 7040 | 0 | 56320
16 | 84095 | Resurface swimming pool |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000
18 | 84205 | Fences & gates - swimming pool |  |  |  | 0 | 0 |  |  | 0 | 0 | 7700 | 0 | 0 | 0 | 0 | 0 | 7700
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2868800 | [11 empty] | 6915040
|  |  | CM Fee |  |  | 143440 | [11 empty] | 143440
|  |  | Capital Plan Total (ex-BTL) |  |  | 3012240 | [11 empty] | 7058480
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 32871
BTL (dropped per Adam): $0

## Foster Creek
Foster Creek — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
94 | 84101 | Exterior building Paint | Repaint Community | GC | Project | 320000 | 96000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 |  |  |  |  | GC (pay app)
93 | 84113 | Breezeway soffit repairs | Repair soffits - Could be changed to $120k | GC | Project | 160000 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 0 | 187000 |  |  |  |  | GC (pay app)
200 | 83210 | 83210 - Electrical | Outlets and switches replacement program | PMC | Project | 102000 | 81929 |  |  | 102000 | 0 | 102000 | 0 | 0 | 0 | 0 | 0 | 306000 |  |  |  |  | GL PMC
46 | 84450 | Security Camreas System | Add additional security camreas systems to the property | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
70 | 84121 | Repair patio/balcony railings Equty PCA | Repair balconies railings Balcony Repairs | GC | Project | 40000 | 12000 |  |  | 2100 | 0 | 2100 | 0 | 2100 | 0 | 2100 | 0 | 58900 |  |  |  |  | GC (pay app)
196 | 84130 | Dog Park & Grilling Area | Dog Park & Grilling Area | PMC | Project | 35000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 38600 |  |  |  |  | GL PMC
72 | 84121 | Repair exterior stair railings | Repair wooden railings on stairs | GC | Project | 35000 | 10500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
87 | 84102 | Repair / replace wood siding Lender PCA | Replace damaged T 1-11 siding on mansards Damaged T1-11 siding was present at Building G (Phase II). Repair is recommen | GC | Project | 34000 | 10200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 |  |  |  |  | GC (pay app)
164 | 84210 | General Electrical Services Equity PCA 3 | Replace wall packs | GC | Project | 32000 | 32000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
24 | 84115 | Sidewalks Lender PCA 3.1.7 Equity PCA 3. | Remove and replace areas of trip hazards. Cracked concrete was observed adjacent to the entrance to Building C. Repair | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 34500 |  |  |  |  | GC (pay app)
79 | 84433 | Modified bitumen membrane roof Repairs | Repairs to flat roofs. Equity PCA did not mention roof as an immediate need, but did mention as a replacement in YR 1 | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
25 | 84204 | Asphalt Pavement Lender PCA 3.1.6 Equity | Lender PCA 3.1.6 Damaged asphalt pavement consisting of linear cracking, alligator cracking, potholes, and surface ravel | GC | Project | 24250 | 24250 |  |  | 67703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159656 |  |  |  |  | GC (pay app)
71 | 84430 | Concrete deck / floor fill | np1 sealant to cracks in landing | GC | Project | 19000 | 19000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 |  |  |  |  | GC (pay app)
81 | 83439 | Gutters & downspouts | Clear scuppers and roof drains | GC | Project | 19000 | 19000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 |  |  |  |  | GC (pay app)
95 | 84113 | Repair / replace wood trim Equity PCA 3. | Replace damaged trim | GC | Project | 16000 | 4800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 26000 |  |  |  |  | GC (pay app)
42 | 84111 | Dumpster enclosures Equity PCA 3.2.2 | Repair dumpster inclosures. Replaced Damaged Dumpster Gates | GC | Project | 16000 | 4800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
103 | 84905 | Moisture and Microbial Growth Equity PCA | Proactive rewire bathroom fan to light switch. Mold & Moisture Removal | GC | Project | 15215 | 15215 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15215 |  |  |  |  | GC (pay app)
114 | 84211 | Fire Stops | Install Fire Stops | PMC | Project | 15215 | 105065 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15215 |  |  |  |  | GL PMC
27 | 84517 | Storm Water Management Equity PCA 3.2.1 | Erosion Repairs | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 27000 |  |  |  |  | GC (pay app)
194 | 83103 | Signage | Building Signage | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
168 | 84330 | GFCI Receptacles Equity PCA 3.4.4 | Missing GFCI receptacles | PMC | Project | 13500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 |  |  |  |  | GL PMC
76 | 84433 | Asphalt composite shingle roofing | Roof Tune Up | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 88402 | 0 | 0 | 0 | 0 | 0 | 100402 |  |  |  |  | GC (pay app)
120 | 82460 | Down Unit Renovation (C-309) Lender PCA | Unit C-309 was observed in poor condition and is considered ‘down’. A notice affixed to the door by the King County Sher | PMC | Project | 10800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10800 |  |  |  |  | GL PMC
89 | 84102 | Repair / replace vinyl siding Lender PC | Isolated areas of warped vinyl lap siding were observed at the leasing office and Buildings B and C of Phase I. Repairs | GC | Project | 10000 | 3000 |  |  | 4040 | 0 | 4040 | 0 | 4040 | 0 | 4040 | 0 | 46360 |  |  |  |  | GC (pay app)
15 | 84303 | Landscape Cleanup and Enhancements Equit | Install Landscaping and Mulch - North of Building 15042 | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
83 | 84433 | Sealants & caulking and paint | Roof Sealants & Caulking | GC | Project | 8500 | 2550 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 71500 |  |  |  |  | GC (pay app)
82 | 84433 | Flashing | Repair damaged flashing | GC | Project | 8500 | 2550 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
47 | 84275 | Key Pad and Auto Locking Door | Add to gym door | PMC | Project | 7500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GL PMC
121 | 82460 | Damaged Unit Repair (C-209) Lender PCA | Additionally, Unit C-209 was observed in fair condition. The unit has water damage to finishes from the unit above (C-30 | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
198 | 83209 | 83209 - Plumbing | Plumbing Work Orders | PMC | Project | 3500 | 29571 |  |  | 2800 | 0 | 2450 | 0 | 1750 | 0 | 0 | 0 | 10500 |  |  |  |  | GL PMC
108 | 84106 | Clean Dryer vents | Clean dryer vents. Get a unit count of units with W/D | PMC | Project | 2250 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 |  |  |  |  | GL PMC
199 | 83209 | 83209 - Plumbing | Water Leaks Behind Sheetrock | PMC | Project | 1667 | 14084 |  |  | 1333 | 0 | 1100 | 0 | 900 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
23 | 83520 | ADA parking & curb cuts Lender PCA 5.4 | The subject property does not provide van-accessible parking spaces at the Leasing Office. Installation of one van-acces | GC | Project | 1600 | 1600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 |  |  |  |  | GC (pay app)
165 | 84330 | Improperly supported meter bank Equity P | Meter bank supports | GC | Project | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GC (pay app)
207 | 84190 | 83305 - Fitness Equipment |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 40000
197 | 83208 | 83208 - Office/Clubhouse/Lobby Improveme |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10409 | 0 | 10409
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1118497 | [11 empty] | 1782407
|  |  | CM Fee |  |  | 50470 | [11 empty] | 50470
|  |  | Contingency |  |  | 48067 | [11 empty] | 48067
|  |  | Capital Plan Total (ex-BTL) |  |  | 1217034 | [11 empty] | 1880944
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 100109
BTL (dropped per Adam): $1,355,504

## Foxdale Village
Foxdale Village — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
91 | 51075-00 | Repair / replace wood shingles | Replace T-111 siding with Hardie. Equity PCA Item 4.3.1- $19,800- Damaged and deteriorated T1-11 siding was present at n | GC | Project | 1033200 | 1033200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1033200 |  |  |  |  | GC (pay app)
93 | 51080-00 | Exterior building paint | Paint community Equity PCA Item 3.2.7- $15,000- The paint finish on the wood fencing throughout the site was observed t | GC | Project | 401800 | 401800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401800 |  |  |  |  | GC (pay app)
20 | 51050-00 | Asphalt Coating | Fill asphalt cracks and seal coat parking lot Equity PCA Item 3.2.2- $110,500- Damaged pavement consisting of linear cra | GC | Project | 182000 | 182000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 53600 | 0 | 235600 |  |  |  |  | GC (pay app)
94 | 51082-00 | Repair / replace wood trim | Replace trim and damaged fascia | GC | Project | 179500 | 179500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179500 |  |  |  |  | GC (pay app)
133 | 51169-00 | Clubhouse / Office Remodel | Paint, Repair, and replace carpet in office, explore repurposing community center for fitness center or other use | GC | Project | 150000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179250 |  |  |  |  | GC tagged, not on pay app
121 | 51160-00 | Green Program - Echelon Energy Retrofit | Energy Retrofit | GC | Project | 116000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116000 |  |  |  |  | GC tagged, not on pay app
21 | 51050-00 | Add Parking Spaces | Parking is an issue at the property, explore adding lot area or gaining spaced via restriping | GC | Project | 100000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  |  |  |  | GC (pay app)
79 | 51061-00 | Roofing | 19 roofs appear to be TPO- replace one roof and repair 19 roofs yr2 A, C, D, E, F, G, H, I, J, K, M, N, P, R, T, V, X, | GC | Project | 97500 | 88000 |  |  | 527513 | 0 | 527513 | 0 | 527513 | 0 | 0 | 0 | 1763478 |  |  |  |  | GC (pay app)
53 | 51072-00 | Concrete deck / floor fill | 25 Balcony or landing replacements | GC | Project | 90000 | 90000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 |  |  |  |  | GC (pay app)
125 | 51157-00 | Unit deferred maintenance | Flooring replacement needed: kitchen (26), living room (13), bedroom (31), and bathroom (7) Equity PCA Item 6.5.2- $341, | PMC | Project | 85400 | 42108 |  |  | 85400 | 0 | 85400 | 0 | 85400 | 0 | 0 | 0 | 341600 |  |  |  |  | GL PMC
92 | 51075-00 | Repair stucco | Repair damaged stucco | GC | Project | 75000 | 75000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
25 | 51993-00 | Replace camera / security equipment | Replace camera and security equipment | PMC | Project | 51000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 |  |  |  |  | GL PMC
54 | 51070-00 | Wall framing | Replace damaged framing in gable ends | GC | Project | 50000 | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
69 | 51077-00 | Repair patio/balcony railings | Patio fence repairs | GC | Project | 48000 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 |  |  |  |  | GC (pay app)
71 | 51075-00 | Expansion Joints | Replace stucco expansion joints | GC | Project | 48000 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 |  |  |  |  | GC (pay app)
24 | 51043-00 | Landscaping | Tree trim Equity PCA Item 3.2.4- $5,000- Overgrown tress were observed throughout the subject property. Many of the ove | GC | Project | 42000 | 42000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 |  |  |  |  | GC (pay app)
22 | 51091-00 | Sidewalks | Replace trip hazards Lender PCR Item- $3,000- Sidewalks were observed to have uneven edges, resulting in trip hazards. T | GC | Project | 36000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
68 | 51070-00 | Replace equipment screen | PCA 4.4.1 - Replace equipment screen | GC | Project | 36000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
23 | 51046-00 | Landscape irrigation | Inspect and repair irrigation | GC | Project | 32000 | 32000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
40 | 51029-00 | Playground | Fall zone on 4 playgrounds, misc equipment repairs and replacements | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC tagged, not on pay app
134 | 51160-06 | Clubhouse / Office Furniture | Clubhouse Furniture | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC tagged, not on pay app
81 | 51071-00 | Gutters & downspouts | Clean and repair gutters | GC | Project | 29274 | 29274 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29274 |  |  |  |  | GC (pay app)
162 | 51140-00 | Electrical distribution | Inspect and repair lighting controllers on all buildings Contingency for electrical panel upgrades/replacements starting | GC | Project | 27500 | 25000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 |  |  |  |  | GC (pay app)
80 | 51062-00 | Roofing Maintenance | PCA 4.4.1 All roof sections: Annual maintenance | GC | Project | 25243 | 0 |  |  | 25243 | 0 | 25243 | 0 | 25243 | 0 | 25243 | 0 | 252430 |  |  |  |  | GC (pay app)
55 | 51072-00 | Repair exterior stair treads and stringe | Secure railings | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
56 | 51072-00 | Repair balcony framing & decking | Balcony Decking | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
82 | 51062-00 | Flashing | Replace damaged flashing | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
83 | 51062-00 | Sealants & caulking | Seal transition to stucco from siding | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
18 | 51130-00 | Storm sewer piping | Clean storm drains | GC | Project | 22000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC tagged, not on pay app
19 | 51053-00 | Stripe parking areas | Restripe parking lot | GC | Project | 21000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC tagged, not on pay app
60 | 51076-00 | Repair masonary fence | PCA 4.2 - Remediation and/or sectional replacement of masonry perimeter fence. | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
61 | 51090-00 | Repair concrete stairs | PCA 4.2 - Repair or replace damaged concrete treads at stairs. | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
63 | 51070-00 | Repair exposed wood beams | PCA 4.2 -Remediate wood deterioration of exterior exposed wood beams and vertical braces | GC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
123 | 51993-00 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | PMC | Project | 14129 | 60523 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14129 |  |  |  |  | GL PMC
59 | 51070-00 | Replace damaged wood | PCA 4.2 -Allowance for replacement of damaged wood framing during exterior cladding replacement. | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
65 | 51075-00 | Replace deteriorated roof-lines | PCA 4.4.1 - Replace deteriorated wood siding at roof-lines | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
66 | 51062-00 | Replace roof hatch | PCA 4.4.1 - Replace roof hatch and install safety railing | GC | Project | 7000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 |  |  |  |  | GC (pay app)
122 | 52111-00 | Deferred Maintenance - Remove Mold | Lender PCR Item- $6,000- Mold was observed in the bathrooms of many units. The units include the following: Unit 1350-52 | PMC | Project | 6000 | 25702 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GL PMC
166 | 51993-01 | Infrared Scan of Electrical Equipment | Equity PCA Item 5.3- $6,000- An infrared (IR) scan tag was observed at an electrical service entrance, the date on the t | GC | Project | 6000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC tagged, not on pay app
126 | 52111-00 | Down Units | Lender PCR Item- $5,500- At the time of the site visit, one (1) down unit (Unit 1350-513) was observed due to fire damag | GC | Project | 5500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 |  |  |  |  | GC tagged, not on pay app
57 | 51045-00 | Landscaping -Leasing office | PCA 4.1 -Leasing Office – Allowance for landscaping remediation at ledge extension | GC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
58 | 51090-00 | Repair cracks in leasing office | PCA -4.1 - Leasing Office – Allowance for spalling and crack repairs at concrete slab ledge extension, and potential sec | GC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
62 | 51070-00 | Inspect stair landing | PCA 4.2- Evaluate stair landing framing with borescope and replace any damaged framing, soffit material and rim joist as | GC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
64 | 51074-00 | Replace skylight lens | PCA 4.4.1 -Replace deteriorated or capped skylight lens | GC | Project | 3000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GC (pay app)
67 | 51062-00 | Replace missing vent tops | PCA 4.4.1 - Replace missing vent tops | GC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC (pay app)
164 | 51993-00 | Fire Alarm System | Lender PCR Item- $2,000- Repair the main fire alarm system which indicates "trouble" and perform the expired annual insp | PMC | Project | 1000 | 4284 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 |  |  |  |  | GL PMC
163 | 51140-00 | Electrical distribution | Electrical service and distribution equipment, Phased replacement | GC | Project | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 143500 | 0 | 861000 |  |  |  |  | GC tagged, not on pay app
157 | 51130-00 | Plumbing- Domestic water and sanitary dr |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 80000 | 0 | 80000 | 0 | 560000
180 | 50030-00 | Appliance Replacement |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 67952 | 0 | 67952 | 0 | 67952 | 0 | 543616
95 | 51074-00 | Windows |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 29290 | 0 | 29290 | 0 | 29290 | 0 | 234320
195 | 51160-06 | Common area flooring, Replace |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 29250 | 0 | 0 | 0 | 0 | 0 | 58500
165 | 51993-00 | Fire Alarm System |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
70 | 51993-01 | SB-721 |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 3269046 | [11 empty] | 7781697
|  |  | CM Fee |  |  | 193179 | [11 empty] | 554878
|  |  | Contingency |  |  | 351235 | [11 empty] | 1008870
|  |  | Capital Plan Total (ex-BTL) |  |  | 3813459 | [11 empty] | 9345445
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 216148
BTL (dropped per Adam): $2,307,000

## Latitude at the Commons
Latitude at the Commons — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
18 | 84204 | Asphalt Coating | Seal Coat parking lot | GC | Project | 89000 | 26700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89000 |  |  |  |  | GC (pay app)
34 | 84114 | Repair exterior stair treads and stringe | Stairs, Treads, and stringers are bare wood they are in good shape - need sealant | GC | Project | 72000 | 21600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 |  |  |  |  | GC (pay app)
35 | 84104 | Repair balcony framing & decking | Landings and balconies are bare wood - need sealant | GC | Project | 60000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GC (pay app)
42 | 84101 | Exterior building | Corner to corner point of repaired areas. | GC | Project | 54000 | 16200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 |  |  |  |  | GC (pay app)
17 | 84303 | Landscape Cleanup and Enhancements | Concept Walk - Tree trimming | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
40 | 84206 | Repair / replace cement fiber siding | Remove and replace buckling siding on 5 gable ends of buildings | GC | Project | 46000 | 13800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 |  |  |  |  | GC (pay app)
25 | 84095 | Resurface swimming pool | Resurface Pool | GC | Project | 45000 | 13500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
54 | 83375 | Golf Cart | Concept Walk - not included in personal property list. Currently have 4 carts on site | PMC | Project | 40000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GL PMC
46 | 83236 | Replace old smoke detectors | H - Majority of units. These devices have an EUL of 7-10. The majority of smoke detectors were of original installation. | PMC | Project | 32400 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 |  |  |  |  | GL PMC
52 | 84211 | Fire Stops | Install fire stops in every unit | PMC | Project | 28224 | 82476 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28224 |  |  |  |  | GL PMC
48 | 84106 | Clean Dryer vents | Dryer Vent Cleaning | GC | Project | 21600 | 6480 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21600 |  |  |  |  | GC (pay app)
45 | 83304 | Flooring Repairs | H - Repair carpets with trip hazards in units 115, 118, 121, 123, 127, 128, 133, 212, 234, 432, 613, 625, 827, 914, 922, | PMC | Project | 20736 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20736 |  |  |  |  | GL PMC
51 | 84215 | Patio screening on remaining units | Concept Walk - Add patio screen doors | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
65 | 84210 | Add lighting | Concept Walk - exterior lighting is lacking, should supplement the existing lighting to ensure it's well lit at night | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
37 | 83439 | Gutters & downspouts | Clean and repitch gutters throughout property H - The roof and gutters at Garage G is damaged. | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
38 | 84102 | Sealants & caulking | Seal all seams on face nailed siding | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
19 | 84201 | Stripe parking areas | Stripe Parking Lots | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
22 | 84204 | Pavement | Crack fill large crack running in the center of the drive aisle LPCA - Localized cracking was observed in the center of | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
43 | 84105 | Repair / replace wood trim | Replace rotted wood | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
24 | 84517 | Erosion control | Concept Walk - Required in two separate locations per management. They are currently digging a trench to release, howeve | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
26 | 84360 | Swimming pool furniture | Concept Walk - Pool umbrellas | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
21 | 83520 | ADA parking & curb cuts | Need ADA signage and poles LPCA - ADA compliant parking spaces are required to have a sign with the International Symbo | PMC | Project | 9000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 |  |  |  |  | GL PMC
63 | 84210 | Electrical Distribution | Repair timers or photo cells | GC | Project | 9000 | 2700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 |  |  |  |  | GC (pay app)
27 | 84111 | Dumpster enclosures | Paint Enclosures | GC | Project | 7500 | 2250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC (pay app)
20 | 84115 | Sidewalks | Sidewalk Repairs H - Sunken and uplifted sidewalks at the front of buildings | GC | Project | 5200 | 1560 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200 |  |  |  |  | GC (pay app)
66 | 84210 | LED Upgrade - Exterior Common Area Light | Hillmann Green Energy Audit - EEM No. 7 | PMC | Project | 4546 | 2222 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4546 |  |  |  |  | GL PMC
56 | 84476 | Domestic Hot Water Heater | H - Rust damage on the DHW heater for units 522, 925, and 1217 | GC | Project | 4485 | 1346 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4485 |  |  |  |  | GC (pay app)
49 | 84304 | Window Repairs | H - Windows in units 137, 213, and 417 are in need of repair. | PMC | Project | 2097 | 646 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2097 |  |  |  |  | GL PMC
23 | 84115 | Flatwork Repairs | LPCA (PR-90) - Two vertical-separation trip hazards were observed. One was at the north entrance to the breezeway of Bui | PMC | Project | 1000 | 503 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GL PMC
41 | 84120 | Breezeway Missing/Exposed Nails | H - Breezeway at building missing/exposed nails on the stairway for building 2184 and 2210 | GC | Project | 1000 | 300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GC (pay app)
64 | 84239 | Exit Sign | H - Exit sign is damaged at 2210 and 2175 buildings | GC | Project | 376 | 113 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 |  |  |  |  | GC (pay app)
47 | 83236 | Replace Smoke Detectors in observed unit | H - Smoke detectors missing in units: 212, 234, 726, 1021, 1114 | PMC | Project | 375 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 |  |  |  |  | GL PMC
50 | 83212 | Missing Kitchen cabinet drawer front | H - Unit 117 has missing drawer front in kitchen | PMC | Project | 200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | GL PMC
73 | 82208 | Split System Air Handler |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 175100 | 0 | 525300
74 | 82208 | Split System Condensing Unit |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 255000
86 | 84204 | Asphalt Sealing |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 85560 | 0 | 85560
91 | 84120 | General Façade & Floor Repairs in Breeze |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 60000
84 | 83436 | Unit - Window Caulking |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 48384 | 0 | 48384
87 | 84201 | Asphalt Striping |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18953 | 0 | 18953
90 | 84239 | Emergency Exit Signage w/o Lights |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 4512 | 0 | 4512 | 0 | 13536
83 | 82150 | Flooring in Mech Closets |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2550 | 0 | 2550 | 0 | 7650
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 735739 | [11 empty] | 1750122
|  |  | CM Fee |  |  | 50381 | [11 empty] | 50381
|  |  | Contingency |  |  | 271880 | [11 empty] | 271880
|  |  | Capital Plan Total (ex-BTL) |  |  | 1058000 | [11 empty] | 2072383
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 8191
BTL (dropped per Adam): $744,200

## Oak Park Monrovia
Oak Park Monrovia — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
175 | 51140-00 | Electrical Distribution Center and Unit | PCA 3.3.3 Exterior electrical service and distribution equipment was generally from the original construction and approx | GC | Project | 360000 | 108000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 |  |  |  |  | GC (pay app)
96 | 51080-00 | Exterior building | Paint Exterior of Property (incl. Parking Garages) | GC | Project | 234000 | 70200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521790 |  |  |  |  | GC (pay app)
70 | 51072-00 | Repair balcony framing & decking | DPCA 3.2.7 / EPCA 4.5 Select balconies at the buildings were observed to have deteriorated wood members at the balcony d | GC | Project | 140000 | 42000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 |  |  |  |  | GC (pay app)
95 | 51160-00 | Interior Hallway painting | Repair drywall and paint all interior hallways & Common Areas | GC | Project | 94000 | 28200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94000 |  |  |  |  | GC (pay app)
69 | 51077-00 | Repair patio/balcony railings | Repair/replace areas of rotted/failing wood railings on balconies. | GC | Project | 75000 | 22500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
46 | 51992-00 | Termite Remediation | Termite Remediation - tent and local treatment (per Ecola remediation proposal) | PMC | Project | 57400 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57400 |  |  |  |  | GL PMC
65 | 51070-00 | Roof framing | Inspect all mansard roofs and repair any damage to coping/façade of building to ensure areas are secure to prevent leaki | GC | Project | 47500 | 14250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47500 |  |  |  |  | GC (pay app)
93 | 51075-00 | Repair stucco | Repairs throughout property, also repair cement plaster at northeaster corner of western wing of parking garage. | GC | Project | 40000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
168 | 51990-00 | Seismic shut off valve - install | DPCA 3.3.6 / EPCA 5.3 -The observed natural gas services lacked seismic shutoff valves to prevent dangerous gas leaks in | GC | Project | 39000 | 11700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 |  |  |  |  | GC (pay app)
169 | 51120-00 | MAUs - Ventilation System | DPCA 3.3.1 / EPCA 5.2 The MAUs at each building were in poor overall condition. The unit at the North Building unit was | GC | Project | 32000 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
29 | 51043-00 | Landscaping | Tree trim - building clearance throughout property | PMC | Project | 28500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28500 |  |  |  |  | GL PMC
139 | 51160-00 | Common Area Greenspace Enhancements | Placeholder for greenspace improvements (e.g. dog park, bocce ball, etc.) | PMC | Project | 24000 | 5162 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GL PMC
177 | 51141-00 | Common area light fixtures | Replace all patio lighting with new LED lighting. | GC | Project | 23500 | 7050 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23500 |  |  |  |  | GC (pay app)
76 | 51060-00 | Asphalt composite shingle roofing | Repair and add proper flashing to the roofing of the ganged mains and meter bank closets. | GC | Project | 21500 | 6450 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21500 |  |  |  |  | GC (pay app)
26 | 51086-00 | Erosion control | Fill areas of erosion around buildings and flower beds throughout property. Specifically areas that have exposed PVC irr | GC | Project | 17500 | 5250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 |  |  |  |  | GC (pay app)
178 | 51141-00 | Replace garage lighting | Replace existing garage lighting with LED. | GC | Project | 15000 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
15 | 51045-00 | Landscape Cleanup and Enhancements | DPCA 3.1.4 / EPCA 3.2.4 - Landscape areas were observed to be eroded with exposed irrigation lines at significant areas | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
157 | 51134-00 | Hydro-jetting & Camera inspection | PCA 5.1 -It appears that no hydro-jetting and camera inspection has been performed at the property. Industry best practi | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
155 | 51130-00 | Stormwater sump pump system, replace | PCA 3.3.4. It was observed that the South Building parking garage had failed, and control panel could not be energized a | GC | Project | 8800 | 2640 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800 |  |  |  |  | GC (pay app)
45 | 51180-00 | Mold Remediation | Mold Remediation | PMC | Project | 6000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GL PMC
44 | 51172-00 | Carports / Garages | Repair damaged coating in parking structure at spots 65, 66 and 68. Also, extend routed and repair expansion joint at ra | GC | Project | 5250 | 1575 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 144000 | 0 | 149250 |  |  |  |  | GC (pay app)
126 | 51030-00 | Signage - Building identification | Adding signage to locate the leasing office - specifically on the North Building to guide tenants to the South Building | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
154 | 51130-00 | Water pressure regulator / back-flow pre | Install backflow prevention device at north building. Currently leaking. | GC | Project | 2000 | 600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC (pay app)
147 | 51140-00 | Smoke and Fire Detection System, central | PCA 3.3.10: Current inspection tags were not observed on the main control panel, building panels or elevator panels. Ins | PMC | Project | 1500 | 403 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
179 |  | Electrical breaker panels, Replace |  | DFM |  | 0 | 0 |  |  | 90000 | 0 | 90000 | 0 | 90000 | 0 | 0 | 0 | 270000
166 |  | Copper pipe, Replacement allowance |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 29417 | 0 | 29417 | 0 | 29417 | 0 | 205919
180 |  | Electrical main service equipment. Repla |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
167 |  | Packaged RTU unit, Replace |  | DFM |  | 0 | 0 |  |  | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52500
134 |  | Clubhouse / Office Furniture |  | AMN |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
20 |  | Carports / Garages |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 8000
71 |  | SB721 inspection |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
21 |  | Stripe parking areas |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 5760
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1297450 | [11 empty] | 2452419
|  |  | Contingency |  |  | 90693 | [11 empty] | 90693
|  |  | CM Fee |  |  | 69407 | [11 empty] | 127156
|  |  | Capital Plan Total (ex-BTL) |  |  | 1457550 | [11 empty] | 2670267
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $1,504,750

## Orchard Glen
Orchard Glen — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
52 | 51075-00 | Repair / replace wall shake shingles | Post cost is inclusive of dry rot repair Replace shake siding, T111 and window wall siding and repair textured siding | GC | Project | 921600 | 921600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 921600 |  |  |  |  | GC (pay app)
53 | 51080-00 | Exterior building paint | Exterior Painting | GC | Project | 433550 | 390195 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 867100 |  |  |  |  | GC (pay app)
48 | 51071-00 | Gutters & downspouts | Gutters & Downspout Repairs | GC | Project | 244800 | 244800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244800 |  |  |  |  | GC (pay app)
95 | 51990-00 | Green Up Program | Domestic Hot Water - Gas Tank Heater - Large, (0.95 TE), Qty 12, Apartments | PMC | Project | 187200 | 12212 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187200 |  |  |  |  | GL PMC
35 | 51992-00 | WDO Treatment/Repairs | LPCA - Subsequent to thesite visit,managementprovided a WDOinspection reportconducted on 4/29/25 by TerminixInternationa | PMC | Project | 160000 | 37109 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 |  |  |  |  | GL PMC
54 | 51082-00 | Repair / replace wood trim | EPCA 4.4.1 - Contingency for replacement of damaged wood decking and fascia during the first phase of roof replacements; | GC | Project | 151200 | 151200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302400 |  |  |  |  | GC (pay app)
18 | 51053-00 | Asphalt Coating | EPCA 3.2.2 - The asphalt seal coat and pavement markings and striping appeared to be in fair to poor condition. The seal | GC | Project | 121000 | 36300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121000 |  |  |  |  | GC (pay app)
99 | 51990-00 | Green Up Program | Water Fixture - WaterSense Certified Toilets, (0.8 gpf), Qty 240, 75% of Total Toilets | PMC | Project | 108960 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108960 |  |  |  |  | GL PMC
17 | 51045-00 | Landscape Cleanup and Enhancements | EPCA 4.4.1 - Cut back trees in contact with roofs. Initial tree trim, landscape cleanup, entry and tour path enhancement | GC | Project | 100000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  |  |  |  | GC tagged, not on pay app
46 | 51061-00 | Asphalt composite shingle roofing | EPCA 4.4.1 - Replacement of half of the shingled roofs within the next year. EPCA 4.4.1 - Replacement of half of the shi | GC | Project | 80000 | 24000 |  |  | 70000 | 0 | 70000 | 0 | 70000 | 0 | 70000 | 0 | 710000 |  |  |  |  | GC (pay app)
28 | 51085-00 | Retaining walls | The retaining walls appeared to be in fair condition. The walls appeared to exhibit lateral movement (leaning) and separ | GC | Project | 62900 | 62900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62900 |  |  |  |  | GC (pay app)
29 | 51023-00 | Resurface swimming pool | Pool Resurfacing | GC | Project | 51000 | 30600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 |  |  |  |  | GC (pay app)
39 | 51070-00 | Wall framing | replace damaged framing in chimney | GC | Project | 48000 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 |  |  |  |  | GC (pay app)
47 | 51062-00 | Repairs to roof systems | EPCA 4.4.1 - Immediate repairs to roof system to maintain water-tightness leading up to replacement. Immediate Repairs t | GC | Project | 45000 | 13500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
38 | 51072-00 | Concrete deck / floor fill | repair and paint balconies | GC | Project | 40000 | 40000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
30 | 51076-00 | Fences & gates - swimming pool | Swimming Pool Gate Repairs | GC | Project | 38000 | 38000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 |  |  |  |  | GC (pay app)
50 | 51062-00 | Flashing | Flashing Repairs | GC | Project | 38000 | 38000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 |  |  |  |  | GC (pay app)
25 | 51091-00 | Sidewalks | LPCA - limited sidewalk cracks were observed by the west playground equipment LPCA (PR-90) - a limited concrete sidewalk | GC | Project | 32000 | 32000 |  |  | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 54500 |  |  |  |  | GC (pay app)
22 | 51172-00 | Carports / Garages | Repair carports and paint post and pearling EPCA 4.4.1 - Repair of impact damage to metal carport canopies. EPCA 3.2.9 - | GC | Project | 28000 | 16800 |  |  | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 43000 |  |  |  |  | GC (pay app)
91 | 51131-00 | Stormwater Pipe Repair | Clean storm drains | GC | Project | 25000 | 25000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
44 | 51070-00 | Expansion joints | Repair exterior expansion joints | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
49 | 51062-00 | Sealants & caulking | Sealants and Caulking for Roof | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
90 | 51120-00 | Split HVAC System (Move to HVAC) | EPCA 5.2 - The split heat pump system serving the clubhouse is more than 20 years old. Based on age and EUL, replacement | PMC | Project | 24000 | 3786 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GL PMC
23 | 51053-00 | Stripe parking areas | Striping of Parking Lots | GC | Project | 23000 | 6900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 |  |  |  |  | GC (pay app)
93 | 51130-00 | Natural Gas Seismic Shutoff | EPCA 5.3 - Seismic shut-off valves were not installed on the natural gas services. The property is located in a seismic | GC | Project | 21000 | 21000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC (pay app)
57 | 52111-00 | Down Units | EPCA 6.5.2 - At the time of the site assessment, one residential unit (Unit 142) was identified to be in an un-rentable/ | PMC | Project | 20000 | 35021 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
98 | 51990-00 | Green Up Program | Water Fixture - WaterSense Certified Showerheads, (1.25 gpm), Qty 294, 92% of Total Showerheads | PMC | Project | 19110 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19110 |  |  |  |  | GL PMC
42 | 51077-00 | Balconies/handrails/guardrails | Patio fence repairs and paint EPCA 4.2 - Elevated balconies and walkways are provided with wood guardrails, where posts | GC | Project | 18000 | 72000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
107 | 51140-00 | Electrical service and distribution, Ong | inspect and repair lighting controllers on all buildings | GC | Project | 16000 | 16000 |  |  | 4800 | 0 | 4800 | 0 | 4800 | 0 | 4800 | 0 | 59200 |  |  |  |  | GC (pay app)
34 | 51090-00 | Replacement of damaged concrete treads a | EPCA 4.2 - The concrete stair treads were noted with cracks (varying degrees) and spalling areas with exposed steel rein | GC | Project | 16000 | 16000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
40 | 51072-00 | Balcony framing & decking | Repair balcony framing & decking | GC | Project | 16000 | 16000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
89 | 51130-00 | Back-flow preventer | EPCA 5.1 - The two 6" reduced pressure backflow prevention devices appear to be original and should be replaced. Annual | PMC | Project | 16000 | 142413 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GL PMC
20 | 51026-00 | Repair / replace swimming pool pumps | Pool Pumps | GC | Project | 6800 | 4080 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 |  |  |  |  | GC (pay app)
27 | 51076-00 | Fences & gates - site perimeter | EPCA 3.2.7 - Damage/deterioration of the metal security perimeter fencing and the welded steel pool fencing was noted in | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
97 | 51990-00 | Green Up Program | Water Fixture - Bathroom Aerators, (0.5 gpm 100% Aerator Replacement), Qty 320, Apartments | PMC | Project | 3200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 |  |  |  |  | GL PMC
96 | 51990-00 | Green Up Program | Water Fixture - Kitchen Aerators, (1.2 gpm 100% Aerator Replacement), Qty 288, Apartments | PMC | Project | 2880 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 |  |  |  |  | GL PMC
36 | 51992-00 | WDO Inspection | LPCA - Subsequent to the site visit, management provided a WDO inspection report conducted on 4/29/25 by Terminix Intern | PMC | Project | 2000 | 464 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GL PMC
24 | 51091-00 | Repair ADA deficiencies | LPCA - No ADA access aisles were observed in three ADA parking spaces. No insulation under the common area restroom sink | GC | Project | 1500 | 450 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GC (pay app)
56 | 52111-00 | Remove Microbial Growth | LPCA (PR-90) - CBRE observed microbial growth. Specifically, these conditions were observed at the bathtub of Unit 3873- | PMC | Project | 1100 | 30373 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 |  |  |  |  | GL PMC
21 | 51076-00 | Fences & gates - patios | EPCA 3.2.3 - The ground floor patio fence (wood guardrail) located between Units 85 and 87 was noted to be leaning outwa | GC | Project | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GC (pay app)
33 | 51070-00 | Replacement of metal standoff post bases | EPCA 4.2 - The metal standoff bases at the wood walkway and stair posts near Unit 169 were exhibiting corrosion and pote | GC | Project | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GC (pay app)
58 | 52111-00 | Damaged Ceiling | LPCA (PR-90) - During an additional inspection conducted by the Lender, ceiling damage and possible water intrusion were | PMC | Project | 700 | 1695 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 |  |  |  |  | GL PMC
19 | 51091-00 | Accessibility | EPCA 7.1 - The leasing office restroom lacked scald protection at the exposed lavatory piping. Installation is recommend | GC | Project | 400 | 400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 |  |  |  |  | GC (pay app)
59 | 51992-00 | Roach Treatment | LPCA (PR-90) - During an additional inspection conducted by the Lender, evidence of roaches was observed in Unit 1-10. C | PMC | Project | 350 | 81 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 |  |  |  |  | GL PMC
132 | 51200-00 | 83100 - Refurbishment |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 30000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 3179250 | [11 empty] | 4504700
|  |  | CM Fee |  |  | 174700 | [11 empty] | 303146
|  |  | Contingency |  |  | 166381 | [11 empty] | 288710
|  |  | Capital Plan Total (ex-BTL) |  |  | 3520331 | [11 empty] | 5096557
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 68129
BTL (dropped per Adam): $1,269,510

## Paddock Club
Paddock Club — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
18 | 84204 | Asphalt Coating | Crack fill and double seal coat asphalt throughout property. Lender PCA Item- Damaged pavement consisting of linear crac | GC | Project | 425000 | 425000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425000 |  |  |  |  | GC (pay app)
23 | 84303 | Landscaping | Tree trim around property, especially around the lake. Clean up of brush foliage around lakes, as well. 1st call biddin | GC | Project | 125000 | 125000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 |  |  |  |  | GC (pay app)
77 | 84105 | Repair / replace wood trim | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. Include ALL buildings throughout property. | GC | Project | 95000 | 95000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 |  |  |  |  | GC (pay app)
64 | 84433 | Asphalt composite shingle roofing | Moderate Roof Tune up on every building. This would include securing shingles, flashing, etc. Repairs of moderate water | GC | Project | 75000 | 75000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
75 | 84206 | Repair / replace cement fiber siding | Repair/replace areas of failed hardie board and paint to match throughout property | GC | Project | 68500 | 68500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68500 |  |  |  |  | GC (pay app)
76 | 84206 | Repair / replace vinyl siding | Repair areas of damaged vinyl siding and clean vinyl covered in mold and grime throughout property. Also, secure vinyl s | GC | Project | 68500 | 68500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68500 |  |  |  |  | GC (pay app)
21 | 84205 | Fences & gates - site perimeter | Repair deck walkways/fencing throughout property. Some areas have broken stairs and missing areas of pickets. Railing r | GC | Project | 50000 | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
120 | 84306 | Clubhouse / Office Furniture | Clubhouse Furniture | PMC | Project | 50000 | 66212 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
124 | 84360 | Pool Furniture | New furniture and games needed | PMC | Project | 50000 | 57216 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
159 | 84112 | Replace breezeway lights | Install LED pole lights on pre-existing posts throughout the propety | GC | Project | 50000 | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
24 | 84095 | Resurface swimming pool | Resurface main pool at clubhouse. | GC | Project | 42750 | 42750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42750 |  |  |  |  | GC (pay app)
20 | 84115 | Sidewalks | Repair cracked/broken sidewalks throughout property. | GC | Project | 40000 | 40000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
133 | 84305 | Package Lockers | Look at adding to laundry room. Budget 1 locker per 4-5 units @$400/locker | PMC | Project | 33600 | 13600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33600 |  |  |  |  | GL PMC
154 | 84217 | HVAC inspection and maintenance | Clean foliage around condensors and raise AC units with HVAC pads where needed. | GC | Project | 33600 | 33600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33600 |  |  |  |  | GC (pay app)
158 | 84112 | Common area light fixtures | Replace wallpacks on all buildings | GC | Project | 28000 | 28000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (pay app)
27 | 84105 | Pergola Court | Replace any damaged/rotted decking around the clubhouse and pool area. | GC | Project | 26500 | 26500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26500 |  |  |  |  | GC (pay app)
157 | 84210 | Electrical distribution | Electrical Distribution | GC | Project | 26000 | 26000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
98 | 84106 | Clean Drier vents | Clean dryer vents throughout property. | GC | Project | 25200 | 25200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 |  |  |  |  | GC (pay app)
17 | 84201 | Stripe parking areas | Stripe Parking Lots | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
108 | 82131 | Co 2 detectors | Install Co2 detectors in each unit. Lender PCR Item- Due to the presence of gas-fire water heaters at each unit, carbon | PMC | Project | 23520 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23520 |  |  |  |  | GL PMC
26 | 84361 | Repair swimming pool deck | Clean pool deck, fill cracks and seal. Also, clean and resurface concreted steps going down to pool from clubhouse. | GC | Project | 22500 | 22500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 |  |  |  |  | GC (pay app)
16 | 84303 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | PMC | Project | 20000 | 37500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
119 | 84208 | Clubhouse / Office Remodel | Placeholder budget, paint the blue framed wall areas - possibly use 1st call to renovate kitchen if budget permits | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC tagged, not on pay app
122 | 84190 | Fitness Equipment | Replace broken items, add equipment- functional trainer, stair stepper | PMC | Project | 18000 | 19675 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GL PMC
109 | 84239 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | PMC | Project | 16269 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16269 |  |  |  |  | GL PMC
19 | 84221 | ADA parking & curb cuts | Lender PCA Item- Inadequate number of accessible parking and van accessible parking spaces at the leasing office. Instal | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
22 | 84434 | Retaining walls | Repair retaining walls where railroad ties are rotted out. Lender PCA Item- Damage was observed at a section of retaini | GC | Project | 12500 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 |  |  |  |  | GC (pay app)
111 | 84431 | Hard turn/ renovation units | Lender PCA Item- Partner recommends completing the hard turn/ renovation in Units 130 and 281, which includes repair of | PMC | Project | 10000 | 17250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
123 | 84361 | Pool Area Remodel | Placeholder budget | PMC | Project | 10000 | 5620 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
137 | 84240 | Laundry Room Renovation | Replace fluorescent lights, clean fans and paint ceiling where needed, add TV - TAM to negotiate laundry contract to inc | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
131 | 84275 | Access Control System | Add at maintenance shop. Fix system so that it can track which residents enter and leave, the manager said the system ca | PMC | Project | 8000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GL PMC
29 | 84517 | Drainage | Add drainage in areas where water accumulates at base of retaining walls at building 17 | GC | Project | 6000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (pay app)
25 | 84361 | Replace swimming pool coping | Deck-O-Seal coping around pool. | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
121 | 84190 | Fitness Center Remodel | Flooring and walls ok, misc allowance - update lighting in boxing closet to match main gym and add Tonal or equivalent w | PMC | Project | 5000 | 5465 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
125 | 84203 | Picnic/Grill Area Remodel | Placeholder budget | PMC | Project | 5000 | 18550 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
126 | 84340 | Picnic/Grill Furniture | Placeholder budget | PMC | Project | 5000 | 7950 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
143 | 84209 | Plumbing Repairs | Lender PCR Item- Evidence of leaks and faulty piping was observed. According to the site escort, the piping leaks are re | PMC | Project | 4800 | 76513 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 |  |  |  |  | GL PMC
138 | 84240 | Laundry Room Furniture | Add seating | PMC | Project | 4000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 |  |  |  |  | GL PMC
107 | 83465 | Water Damage in Units | Lender PCA Item- Partner recommends repair of any damaged finishes subsequent to the plumbing repairs in Units 1 and 146 | PMC | Project | 3000 | 24082 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GL PMC
132 | 84260 | Mailboxes | Misc repairs - add concrete pad and USPS parcel boxes. | GC | Project | 2000 | 7000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC (pay app)
139 | 83265 | Office Computers | Have 2 new ones, budget for 1 new | PMC | Project | 2000 | 13592 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GL PMC
28 | 84103 | ADA Signage | Add ADA signage at clubhouse for wheelchair lift. | GC | Project | 850 | 850 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850 |  |  |  |  | GC (pay app)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1565089 | [11 empty] | 1565089
|  |  | CM Fee |  |  | 92400 | [11 empty] | 92400
|  |  | Contingency |  |  | 282911 | [11 empty] | 282911
|  |  | Capital Plan Total (ex-BTL) |  |  | 1940400 | [11 empty] | 1940400
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Rancho Cordova
Rancho Cordova — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
41 | 51080-00 | Exterior building | PNA - Repaint community | GC | Project | 188000 | 188000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 359000 |  |  |  |  | GC (pay app)
17 | 51050-00 | Asphalt Coating | Slurry Coat & Seal | GC | Project | 64000 | 64000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000 |  |  |  |  | GC (pay app)
51 | 51140-00 | Replace electric panels | EPCA - Budget for phased replacement of the apartment Zinsco electrical distribution panels based on age and a recall du | GC | Project | 47500 | 47500 |  |  | 47500 | 0 | 47500 | 0 | 47500 | 0 | 47500 | 0 | 237500 |  |  |  |  | GC (pay app)
25 | 51045-00 | Landscaping | PNA - Tree trim and branch removal | PMC | Project | 32000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 77000 |  |  |  |  | GL PMC
24 | 51076-00 | Patio and Fencing | EPCA - Repair areas of leaning wood patio enclosures as needed. Clean and restrain the fence with visible signs of deter | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
50 | 51141-00 | Replace Pole light fixtures | PNA - Pole lights throughout the parking lot LPCA - Replacement of pole lights throughout the parking area. | GC | Project | 28500 | 28500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28500 |  |  |  |  | GC (pay app)
34 | 51062-00 | Modified bitumen membrane Roof Repairs | PNA - Clean flat roofs and repair minor areas of potential water intrusion | GC | Project | 26000 | 26000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
49 | 51141-00 | Common area light fixtures | PNA - Building wall packs LPCA - Budget for installation of building wall packs throughout the site. | GC | Project | 18500 | 18500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 |  |  |  |  | GC (pay app)
32 | 51062-00 | Asphalt composite shingle roofing | PNA - Shingle roof tune up, loose and hanging shingles were observed | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 22500 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
21 | 51050-00 | Asphalt pavement | PNA - Remove and replace failing asphalt EPCA - All | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
39 | 51075-00 | Repair / replace wood siding | PNA - Replace rotted T1-11 | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
40 | 51075-00 | Repair stucco | PNA - Repair stucco, mansard/hip wall | GC | Project | 14000 | 14000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
47 | 52111-00 | Unit deferred maintenance | EPCA - Remediate select bathrooms with signs of organic growth observed in Units 16, 25, 35, 45, 61 & 70 LPCA - Unit 70 | PMC | Project | 12500 | 11546 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 |  |  |  |  | GL PMC
18 | 51053-00 | Stripe parking areas | PNA - Stripe parking areas | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 68000 |  |  |  |  | GC (pay app)
29 | 51070-00 | Exterior Wall framing | Building Framing repairs | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
45 | 51993-00 | Smoke Alarm | EPCA - Budget to replace the existing smoke alarms based on age and useful life. The NFPA requires that smoke alarms not | PMC | Project | 10920 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10920 |  |  |  |  | GL PMC
20 | 51091-00 | Sidewalks | PNA - Repair failing sidewalks | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 16000 |  |  |  |  | GC (pay app)
26 | 51029-00 | Playground equipment | PNA - Fall Zone Material | GC | Project | 9800 | 9800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800 |  |  |  |  | GC (pay app)
23 | 51076-00 | Fences & gates - site perimeter | PNA - Rough iron repairs | GC | Project | 8500 | 8500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 14500 |  |  |  |  | GC (pay app)
30 | 51090-00 | Expansion joints | Foundation Expansion Joint Repairs | GC | Project | 8500 | 8500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
36 | 51071-00 | Gutters & downspouts | PNA - Cleanout gutters and scuppers | GC | Project | 8500 | 8500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
42 | 51082-00 | Repair / replace wood trim | PNA - Repair/replace rotted trim | GC | Project | 8500 | 8500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
46 | 51993-00 | Fire Stops | Install Fire Stops | PMC | Project | 8075 | 6119 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8075 |  |  |  |  | GL PMC
27 | 51130-00 | Storm sewer piping | PNA - Clean out storm sewer catch basin | GC | Project | 8000 | 8000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC (pay app)
43 | 51075-00 | Repair/Replace Soffit | EPCA - Allowance to repair and replace all dry-rotted wood siding and soffits of the two-story residential buildings | GC | Project | 6500 | 6500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | GC (pay app)
37 | 51062-00 | Sealants & caulking | Roofing Sealants & Caulking Repairs | GC | Project | 4500 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  |  |  | GC (pay app)
19 | 51091-00 | ADA parking & curb cuts | Lender PCA - There is a van accessible parking space near the leasing office that is missing a pole-mounted sign. | PMC | Project | 350 | 101 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 |  |  |  |  | GL PMC
33 | 51061-00 | Built-Up Roof Systems |  |  |  | 0 | 0 |  |  | 225000 | 0 | 225000 | 0 | 0 | 0 | 4050 | 0 | 454050
81 | 51130-00 | 83209 - Plumbing |  |  |  | 0 | 0 |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 30000
35 | 51062-00 | Annual Roof Maintenance |  |  |  | 0 | 0 |  |  | 0 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 | 27500
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 622145 | [11 empty] | 1667695
|  |  | Contingency |  |  | 31107 | [11 empty] | 31107
|  |  | CM Fee |  |  | 32663 | [11 empty] | 32663
|  |  | Capital Plan Total (ex-BTL) |  |  | 685915 | [11 empty] | 1731465
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 55179
BTL (dropped per Adam): $1,022,056

## Regency & Lexington
Regency & Lexington — 10-Year Capital Plan
10-yr figures pending review (source-plan inconsistency)
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
41 | 51080-00 | Exterior building | Paint community | GC | Project | 239143 | 297600 | [15 empty] | GC (pay app)
34 | 51072-00 | Repair balcony framing & decking | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail PCA 4.2 - Repair wate | GC | Project | 189643 | 236000 | [15 empty] | GC (pay app)
100 | 51080-00 | Exterior building Paint | Paint community | GC | Project | 132857 | 0 | [15 empty] | GC tagged, not on pay app
90 | 51072-00 | Repair balcony framing & decking | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail | GC | Project | 105357 | 0 | [15 empty] | GC tagged, not on pay app
16 | 51053-00 | Asphalt Coating | Fill asphalt cracks Regency Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in go | GC | Project | 91929 | 42900 | [15 empty] | GC (pay app)
29 | 51092-00 | Install metal hardware | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces | GC | Project | 67500 | 107500 | [15 empty] | GC (pay app)
69 | 51053-00 | Asphalt Coating | Filll asphalt cracks | GC | Project | 51071 | 0 | [15 empty] | GC tagged, not on pay app
20 | 51023-00 | Resurface swimming pool | Resurface two pools | GC | Project | 44500 | 71200 | [15 empty] | GC (pay app)
73 | 51023-00 | Resurface swimming pool | Resurface two pools | GC | Project | 44500 | 0 | [15 empty] | GC tagged, not on pay app
83 | 51092-00 | Install metal hardware | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces | GC | Project | 40000 | 0 | [15 empty] | GC tagged, not on pay app
110 | 51130-00 | Galvanized Pipe Replacement | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone | GC | Project | 40000 | 0 | [15 empty] | GC tagged, not on pay app
58 | 51160-00 | Energy Retrofit | Echelon upfront costs | PMC | Project | 38441 | 0 | [15 empty] | GL PMC
42 | 51082-00 | Repair / replace wood trim | Replace rotted fascia and trim | GC | Project | 36000 | 57600 | [15 empty] | GC (pay app)
101 | 51082-00 | Repair / replace wood trim Repair expose | Replace rotted fascia and trim PCA 4.4.1 - Repair exposed lumber and elevation changes. | GC | Project | 36000 | 0 | [15 empty] | GC tagged, not on pay app
54 | 51130-00 | Galvanized Pipe Replacement | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. | GC | Project | 30000 | 0 | [15 empty] | GC tagged, not on pay app
86 | 51082-00 | Allowance to replace deteriorated wood t | PCA 4.2-Allowance to replace deteriorated wood trim, fascia, rim joists and sheathing at elevated walkways and landings. | GC | Project | 30000 | 24000 | [15 empty] | GC (pay app)
60 | 51140-00 | Electrical distribution | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Inf | GC | Project | 28143 | 13800 | [15 empty] | GC (pay app)
114 | 51160-00 | Energy Retrofit | Echelon upfront costs | PMC | Project | 27121 | 0 | [15 empty] | GL PMC
36 | 51062-00 | Asphalt composite shingle roofing Repair | Roof tune-up to include gravel. Reseal and secure gravel stop and drip edge. PCA 4.4.1 - Repair loose gravel stop and op | GC | Project | 27000 | 125000 | [15 empty] | GC (pay app)
47 | 51011-00 | Pool Furniture | No furniture currently, need chaises and other furniture for main pool. Tables/chairs and armcharis only for 2nd pool d | PMC | Project | 25000 | 0 | [15 empty] | GL PMC
52 | 51993-00 | Security Camera System | Don't have anything, budget for a new system | PMC | Project | 25000 | 0 | [15 empty] | GL PMC
107 | 51993-00 | Security Camera System | Don't have anything, budget for a new system | PMC | Project | 25000 | 0 | [15 empty] | GL PMC
17 | 51091-00 | ADA parking & curb cuts | Repair trip hazards | GC | Project | 24429 | 38000 | [15 empty] | GC (pay app)
40 | 51075-00 | Repair / replace wood siding | Replace rotted t-111 siding | GC | Project | 24000 | 48000 | [15 empty] | GC (pay app)
99 | 51075-00 | Repair / replace wood siding | Replace rotted t-111 siding | GC | Project | 24000 | 0 | [15 empty] | GC tagged, not on pay app
79 | 51992-00 | Termite Remediation | Lexington - Drywood termite local treatments | PMC | Project | 22000 | 20854 | [15 empty] | GL PMC
18 | 51046-00 | Landscape irrigation | Inspect and repair Irrigation | GC | Project | 20571 | 32000 | [15 empty] | GC (pay app)
93 | 51062-00 | Asphalt composite shingle roofing Repair | Roll roofing on roofs inspect and repair PCA 4.4.1 - Repair loose gravel stop and open perimeter flashing and membrane | GC | Project | 20000 | 0 | [15 empty] | GC tagged, not on pay app
25 | 51992-00 | Termite Remediation | Regency - Drywood termite local treatments | PMC | Project | 19000 | 18010 | [15 empty] | GL PMC
39 | 51062-00 | Sealants & caulking | Seal joints in t-111 | GC | Project | 18000 | 36000 | [15 empty] | GC (pay app)
97 | 51062-00 | Sealants & caulking | Seal joints in t-111 | GC | Project | 18000 | 0 | [15 empty] | GC tagged, not on pay app
119 | 51140-00 | Electrical distribution | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Infr | GC | Project | 17857 | 0 | [15 empty] | GC tagged, not on pay app
15 | 51130-00 | Storm sewer piping | Storm water drainage repairs in courtyards | GC | Project | 16714 | 0 | [15 empty] | GC tagged, not on pay app
26 | 51992-00 | Termite Remediation | Regency - Subterranean termite treatment and baiting | PMC | Project | 15400 | 14598 | [15 empty] | GL PMC
46 | 51160-00 | Pool Area Remodel | Expand pool fenced area to make space for furniture | GC | Project | 15000 | 0 | [15 empty] | GC tagged, not on pay app
70 | 51091-00 | ADA parking & curb cuts | Repair trip hazards | GC | Project | 13571 | 0 | [15 empty] | GC tagged, not on pay app
19 | 51043-00 | Landscaping | Tree trim | PMC | Project | 13000 | 300 | [15 empty] | GL PMC
72 | 51043-00 | Landscaping | Tree trim | PMC | Project | 13000 | 300 | [15 empty] | GL PMC
33 | 51077-00 | Repair exterior stair railings | Secure railings | GC | Project | 12000 | 24000 | [15 empty] | GC (pay app)
37 | 51071-00 | Gutters & downspouts Reconnect loose dow | Secure and clean gutters PCA 4.4.1 - Reconnect loose downspout. | GC | Project | 12000 | 24000 | [15 empty] | GC (pay app)
57 | 51130-00 | Natural Gas Seismic Shutoff | Will confirm with Gas utiliity company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equippe | GC | Project | 12000 | 6000 | [15 empty] | GC (pay app)
89 | 51077-00 | Repair exterior stair railings | Secure railings | GC | Project | 12000 | 0 | [15 empty] | GC tagged, not on pay app
94 | 51071-00 | Gutters & downspouts | Secure and clean gutters | GC | Project | 12000 | 0 | [15 empty] | GC tagged, not on pay app
71 | 51046-00 | Landscape irrigation | Inspect and repair Irrigation | GC | Project | 11429 | 0 | [15 empty] | GC tagged, not on pay app
80 | 51992-00 | Termite Remediation | Lexington - Subterranean termite treatment and baiting | PMC | Project | 10800 | 10237 | [15 empty] | GL PMC
14 | 51045-00 | Initial Lanscape Cleanup | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | PMC | Project | 10000 | 602 | [15 empty] | GL PMC
23 | 51050-00 | Parking Lot Cleaning | Power wash garage/parking walls and asphalt | GC | Project | 10000 | 20000 | [15 empty] | GC (pay app)
38 | 51062-00 | Flashing | Repair flashing between stucco and t-111 | GC | Project | 10000 | 20000 | [15 empty] | GC (pay app)
67 | 51045-00 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | PMC | Project | 10000 | 602 | [15 empty] | GL PMC
76 | 51050-00 | Parking Lot Cleaning | Power wash garage/parking walls and asphalt | GC | Project | 10000 | 0 | [15 empty] | GC tagged, not on pay app
82 | 51072-00 | Allowance to epoxy inject concrete toppi | PCA 4.2- Allowance to epoxy inject concrete topping slabs and apply elastomeric coating at elevated walkways. | GC | Project | 10000 | 3000 | [15 empty] | GC (pay app)
88 | 51075-00 | Allowance for exterior cladding replacem | PCA 4.2 -Allowance for exterior cladding replacement and replacement of any damaged wood framing. | GC | Project | 10000 | 8000 | [15 empty] | GC (pay app)
96 | 51062-00 | Flashing | Repair flashing between stucco and t-111 | GC | Project | 10000 | 0 | [15 empty] | GC tagged, not on pay app
68 | 51130-00 | Storm sewer piping | Storm water drainage repairs in courtyards | GC | Project | 9286 | 0 | [15 empty] | GC tagged, not on pay app
48 | 51160-04 | Picnic/Grill Area Remodel | Small grill area by pool, look at adding outdoor counter | PMC | Project | 8000 | 0 | [15 empty] | GL PMC
113 | 51130-00 | Natural Gas Seismic Shutoff | Will confirm with Gas utility company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equipped | GC | Project | 8000 | 0 | [15 empty] | GC tagged, not on pay app
55 | 51134-00 | Sanitary Sewer Piping | Number based on actual bid; $285 per cleanout, est. 12 cleanouts. $402 per storm drain, 11 cleanouts. Regency & Lexingto | PMC | Project | 7842 | 26166 | [15 empty] | GL PMC
24 | 51046-00 | Landscape irrigation | Irrigation repairs & upgrades | PMC | Project | 7500 | 2007 | [15 empty] | GL PMC
31 | 51070-00 | Replace sheathing | PCA 4.2 - Replace deteriorated sheathing and joists at roof eaves, as required. | GC | Project | 7500 | 7500 | [15 empty] | GC (pay app)
21 | 51026-00 | Repair / replace swimming pool pumps | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool d | GC | Project | 7000 | 11200 | [15 empty] | GC (pay app)
22 | 51076-00 | Fences & gates - swimming pool | Adjust closers on pool gates | GC | Project | 7000 | 14000 | [15 empty] | GC (pay app)
74 | 51026-00 | Repair / replace swimming pool pumps | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool d | GC | Project | 7000 | 0 | [15 empty] | GC tagged, not on pay app
75 | 51076-00 | Fences & gates - swimming pool | Adjust closers on pool gates | GC | Project | 7000 | 0 | [15 empty] | GC tagged, not on pay app
30 | 51998-00 | Shore Maintenance Shed | PCA 4.2- Maintenance Shed - Immediately temporarily shore the unsupported double top plate. Engage licensed engineer to | GC | Project | 6000 | 0 | [15 empty] | GC tagged, not on pay app
35 | 51075-00 | Expansion Joints | Expansion Joints | GC | Project | 6000 | 12000 | [15 empty] | GC (pay app)
50 | 51029-00 | Playground equipment | Add seating and/or picnic tables year 1, budget for equipment replacement in year 4. | GC | Project | 6000 | 10000 | [15 empty] | GC (pay app)
91 | 51075-00 | Expansion Joints | Expansion Joints | GC | Project | 6000 | 0 | [15 empty] | GC tagged, not on pay app
32 | 51172-00 | Allowance for sectional replacement of d | PCA 4.2 - Allowance for sectional replacement of damaged sheathing and joists at carports. | GC | Project | 5000 | 2500 | [15 empty] | GC (pay app)
44 | 51169-00 | Clubhouse / Office Remodel | No clubhouse, allowance for office | PMC | Project | 5000 | 0 | [15 empty] | GL PMC
111 | 51134-00 | Sanitary Sewer Piping | Number based on actual bid; $285 per cleanout, 8 cleanouts. $402 per storm drain, 6 cleanouts. Regency & Lexington Equit | PMC | Project | 4692 | 15655 | [15 empty] | GL PMC
27 | 51070-00 | Wall framing | Replace damaged framing in gable ends | GC | Project | 4500 | 9000 | [15 empty] | GC (pay app)
59 | 51120-00 | HVAC Replacement | Large Rheem HVAC unit outside office looks very old and may need to be replaced | GC | Project | 4500 | 0 | [15 empty] | GC tagged, not on pay app
81 | 51070-00 | Wall framing | Replace damaged framing in gable ends | GC | Project | 4500 | 0 | [15 empty] | GC tagged, not on pay app
87 | 51072-00 | Building G Balcony – sectional replaceme | PCA 4.2 -Building G Balcony – sectional replacement of deteriorated framing. | GC | Project | 4500 | 3600 | [15 empty] | GC (pay app)
116 | 51120-00 | HVAC Replacement | Large Rheem HVAC unit outside office looks very old and may need to be replaced | GC | Project | 4500 | 0 | [15 empty] | GC tagged, not on pay app
45 | 51160-06 | Clubhouse / Office Furniture | Need seating for reception area in leasing office. | PMC | Project | 4000 | 0 | [15 empty] | GL PMC
51 | 51990-02 | Need key trak for office | Key Track | PMC | Project | 3500 | 0 | [15 empty] | GL PMC
43 | 51075-00 | Repair stucco | Some walls next to windows need patching and paint | GC | Project | 3000 | 6000 | [15 empty] | GC (pay app)
49 | 51160-04 | Picnic/Grill Furniture | Picnic tables or tables/chairs needed | PMC | Project | 3000 | 0 | [15 empty] | GL PMC
102 | 51075-00 | Repair stucco | Some walls next to windows need patching and paint | GC | Project | 3000 | 0 | [15 empty] | GC tagged, not on pay app
109 | 51130-00 | Back-flow preventer | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. | PMC | Project | 3000 | 2474 | [15 empty] | GL PMC
112 | 51130-00 | Pipe Repair at Building 1 Boiler | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could p | GC | Project | 3000 | 0 | [15 empty] | GC tagged, not on pay app
53 | 51130-00 | Back-flow preventer | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. | PMC | Project | 2250 | 1856 | [15 empty] | GL PMC
85 | 51141-00 | Fill pitch pockets and flash parking lot | PCA 4.4.1 - Fill pitch pockets and flash parking lot light bases. | GC | Project | 2000 | 2000 | [15 empty] | GC (pay app)
56 | 51130-00 | Pipe Repair at Building 1 Boiler | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could p | GC | Project | 750 | 3750 | [15 empty] | GC (pay app)
28 | 51156-00 | Replace hardware | PCA 4.2 - Building C, Unit 37 – Immediately replace the existing bolts with adequately sized bolts and washers. | GC | Project | 500 | 500 | [15 empty] | GC (pay app)
84 | 51070-00 | Repair checked wood beams by epoxy injec | PCA 4.2- Repair checked wood beams by epoxy injection. | GC | Project | 500 | 500 | [15 empty] | GC (pay app)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1996796
|  |  | CM Fee |  |  | 70154
|  |  | CM Fee |  |  | 48322
|  |  | Contingency |  |  | 127553
|  |  | Contingency |  |  | 87858
|  |  | Capital Plan Total (ex-BTL) |  |  | 2330684
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 182918
BTL (dropped per Adam): amount pending review

## Renaissance
Renaissance — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
104 | 80000-6800 | Exterior repair for WDIR | Remediation of active termites | PMC | Project | 250000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 |  |  |  |  | GL PMC
34 | 83000-5100 | Replace swimming pool deck | PNA: Repairs to pool deck cracks and resurface. Bring depth markers, tile, and coping up to code | GC | Project | 100000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  |  |  |  | GC (GL fallback)
17 | 83000-8300 | Landscape Cleanup and Enhancements | PNA: Building clearance tree trim and cleanup. | PMC | Project | 84500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84500 |  |  |  |  | GL PMC
169 | 83000-3200 | Common area light fixtures | PNA: Replace all pole lights, wall packs throughout property. | GC | Project | 44600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44600 |  |  |  |  | GC (GL fallback)
82 | 83000-6100 | Gutters & downspouts | PNA: Secure and clean downspouts. Confirm this includes gutters and repinning | GC | Project | 36200 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36200 |  |  |  |  | GC (GL fallback)
170 | 83000-3200 | Replace breezeway lights | PNA: Replace all breezeway sconces to LED throughout property. | GC | Project | 27800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27800 |  |  |  |  | GC (GL fallback)
122 | 80000-6400 | Fire Stops | PNA: Fire stops | PMC | Project | 27244 | 9697 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27244 |  |  |  |  | GL PMC
22 | 83000-2800 | Concrete pavement | PNA: Repair damaged/ cracked swales throughtout property Lender PCA: At the time of the assessment, several concrete tri | PMC | Project | 2000 | 6500 |  |  | 34500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36500 |  |  |  |  | GL PMC
48 | 83000-6700 | Sports Court | PNA: Complete resurface of sports court and new lines for basketball court. | PMC | Project | 1200 | 2510 |  |  | 97050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98250 |  |  |  |  | GL PMC
44 | 83000-3700 | Dumpster enclosures | PNA: Damage cinderblocks at dumpster enclosures to be repaired. Lender PCA: Two of the refuse enclosures were observed w | PMC | Project | 1000 | 0 |  |  | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 |  |  |  |  | GL PMC
27 | 83000-6900 | Landscape irrigation | PNA: Inspect and repair irrigation Lender PCA: At the time of the assessment, standing water was observed in various ar | PMC | Project | 1000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GL PMC
62 | 83000-7000 | Repair or replace damaged concrete tread | Lender PCA: At the time of the assessment, a damaged concrete thread was observed at the stairs to the upper floor apart | PMC | Project | 500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GL PMC
147 | 80000-1700 | Security/ fire alarm systems | Lender PCA: At the time of the assessment, unit 143 was observed to have missing smoke detectors in the hallways and bed | PMC | Project | 100 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | GL PMC
97 | 83000-3400 | Exterior building painting | Including estimate from WDIR , to be in Yr 2 (Q4 of'27) | PMC | Project | 0 | 0 |  |  | 556000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556000 |  |  |  |  | GL PMC
18 | 83000-2200 | Asphalt Coating | PNA - Fill all alligator cracks, potholes and then seal coat throughout property. Also, speed bump repairs throughout pr | GC | Project | 0 | 0 |  |  | 271120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271120 |  |  |  |  | GC (GL fallback)
43 | 83000-2600 | Carport and garage | PNA: Repair any damaged carports throughtout property. Replace 31 garage doors throughout property - significant damage. | GC | Project | 0 | 2595 |  |  | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92400 |  |  |  |  | GC (GL fallback)
205 | 83000-6000 | 83202 - Exterior Roof Repairs |  | DFM |  | 0 | 0 |  |  | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 90000
199 | 83000-4100 | 83105 - Exterior Carpentry |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62550
207 | 83000-2000 | 83270 - Parking Seal, Stripe, Minor Repa |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 42000
81 | 83000-6100 | Tile roofing | PNA: Clay tile roofing - inspect and minor repairs | GC | Project | 0 | 0 |  |  | 39860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39860 |  |  |  |  | GC (GL fallback)
71 | 83000-7100 | Repair exterior stair railings | PNA: Secure railings and paint all metal stair railings. Currently significantly chipped. | GC | Project | 0 | 0 |  |  | 37800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37800 |  |  |  |  | GC (GL fallback)
26 | 83000-7100 | Sidewalks | Sidewalk Repairs | GC | Project | 0 | 0 |  |  | 33350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33350 |  |  |  |  | GC (GL fallback)
23 | 83000-2200 | Stripe parking areas | PNA: Stripe parking lot throughout property. | GC | Project | 0 | 0 |  |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (GL fallback)
46 | 83000-2200 | Parking Lot Concersion | Potential to convert unused parking lot, will evaluate further into hold | GC | Project | 0 | 0 |  |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (GL fallback)
89 | 83000-6500 | Repair / replace cement fiber siding | PNA: Maintenance shed needs to new siding replacment and paint. | GC | Project | 0 | 0 |  |  | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 |  |  |  |  | GC (GL fallback)
40 | 83000-1700 | Playground equipment | PNA: Current playground extremely faded, if wanting replacement will need to add more funds. Number given is for adding | GC | Project | 0 | 0 |  |  | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12600 |  |  |  |  | GC (GL fallback)
70 | 83000-7100 | Repair exterior stair treads and stringe | PNA: Secure Stair Treads & Stringers | GC | Project | 0 | 0 |  |  | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 |  |  |  |  | GC (GL fallback)
25 | 83000-2800 | ADA parking & curb cuts | PNA: Repair of any damaged curbs. | GC | Project | 0 | 0 |  |  | 10660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10660 |  |  |  |  | GC (GL fallback)
79 | 83000-6100 | Moss Treatment | Moss treatment and pine needle cleaning | GC | Project | 0 | 0 |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (GL fallback)
197 | 83000-5000 | 83100 - Pool |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 576144 | [11 empty] | 2081234
|  |  | CM Fee |  |  | 100269 | [11 empty] | 100269
|  |  | Contingency |  |  | 95494 | [11 empty] | 95494
|  |  | Capital Plan Total (ex-BTL) |  |  | 771907 | [11 empty] | 2276997
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 208046
BTL (dropped per Adam): $606,838

## Rosemont
Rosemont — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
17 | 84204 | Asphalt Repairs | Mill, cement stabilize and overlay all drive aisles throughout property. Includes Equity PCR Item 3.3.2- Mill and overla | GC | Project | 750000 | 750000 |  |  | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 925000 |  |  |  |  | GC (pay app)
147 | 84476 | Unit water heaters | Equity PCR Item- 5.1- Observed water heaters were not provided with drain pans. Additionally, most water heaters observe | GC | Project | 211000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211000 |  |  |  |  | GC tagged, not on pay app
68 | 84202 | Gutters & downspouts | Equity PCR Item 4.4.2- Gutters and downspouts should be installed at the roof eaves where not currently installed to hel | GC | Project | 130000 | 130000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 |  |  |  |  | GC (pay app)
51 | 84121 | Repair exterior stair railings | Secure and paint | GC | Project | 110000 | 110000 |  |  | 6000 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | 218000 |  |  |  |  | GC (pay app)
50 | 84114 | Repair exterior stair treads and stringe | Grind any rusted toe kick plates and red oxide prior to repaint. Replace damaged metal toe plates, as needed. Secure, a | GC | Project | 100000 | 100000 |  |  | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 190000 |  |  |  |  | GC (pay app)
75 | 84101 | Exterior building | Paint all metal throughout property | GC | Project | 90000 | 90000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 |  |  |  |  | GC (pay app)
65 | 84433 | Underlayment | Roof Underlayment | GC | Project | 88000 | 88000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88000 |  |  |  |  | GC (pay app)
23 | 84434 | Retaining walls | Replace missing or rotted timbers within existing retaining walls, replace some walls. Includes Lender PCR Item- Wood ti | GC | Project | 80000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 |  |  |  |  | GC tagged, not on pay app
64 | 84433 | Flashing | Roof Flashing | GC | Project | 79200 | 79200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79200 |  |  |  |  | GC (pay app)
24 | 84303 | Landscaping | Tree trim clearance of all buildings. Includes Equity PCR Item 3.2.4- Many trees were overhanging buildings and depositi | GC | Project | 60000 | 60000 |  |  | 26000 | 0 | 26000 | 0 | 26000 | 0 | 26000 | 0 | 320000 |  |  |  |  | GC (pay app)
127 | 84203 | Picnic/Grill Area Remodel | Add 1-2 outdoor grill/kitchen areas at the property with gazebo | GC | Project | 60000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GC tagged, not on pay app
52 | 84121 | Repair patio/balcony railings | Replace all bottom level patio fencing on each building | GC | Project | 55000 | 55000 |  |  | 3000 | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 | 109000 |  |  |  |  | GC (pay app)
108 | 84239 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | PMC | Project | 52009 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52009 |  |  |  |  | GL PMC
74 | 84206 | Repair / replace vinyl siding | Repair/replace damaged vinyl siding throughout property Includes Lender PCR Item- Dry rot was observed by the siding at | GC | Project | 52000 | 52000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 |  |  |  |  | GC (pay app)
63 | 84433 | Asphalt composite shingle roofing | Roofs were replaced in 2019- Initial and ongoing repairs, and contingency for phased replacements in yrs 9-10 | GC | Project | 50000 | 50000 |  |  | 25000 | 0 | 25000 | 0 | 25000 | 0 | 25000 | 0 | 325000 |  |  |  |  | GC (pay app)
86 | 84215 | Metal Entry Door Replacement and Repairs | Contingency for replacements and repairs | GC | Project | 50000 | 50000 |  |  | 50000 | 0 | 50000 | 0 | 50000 | 0 | 50000 | 0 | 300000 |  |  |  |  | GC (pay app)
35 | 84120 | Re-apply Coating on Walkways & Breezeway | Budget for initial repairs and contingency for ongoing replacements | GC | Project | 50000 | 50000 |  |  | 25000 | 0 | 25000 | 0 | 25000 | 0 | 25000 | 0 | 275000 |  |  |  |  | GC (pay app)
149 | 84385 | Sanitary sewer Repairs | Contingency to remove roots and blockages at several locations, per the sewer scoping. See final report in diligence fo | GC | Project | 50000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 7500 | 0 | 7500 | 0 | 125000 |  |  |  |  | GC tagged, not on pay app
137 | 84275 | New access gate at back entrance | Look at adding gate ro restrict access to dumpster area and prevent dumping | GC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC tagged, not on pay app
141 | 84219 | Carports | Look at adding carports for additional income | GC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC tagged, not on pay app
122 | 84360 | Leasing Pool Furniture | Supplement current furniture, add freestanding umbrellas, cornhole & ping pong, 2 cabanas, move some furniture to second | PMC | Project | 45000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GL PMC
22 | 84205 | Fences & gates - site perimeter | Repair any damaged wooden fencing around property | GC | Project | 40000 | 40000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
16 |  | Storm sewer piping | Address 7 areas of water intrusion throughout property | GC | Project | 36000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
129 | 84390 | Sports Court | Resurface, add 2 Pickleball nets. Keep running track, stripe for Pickleball courts Includes Equity PCR Item 3.2.9- The | GC | Project | 35000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC tagged, not on pay app
18 | 84201 | Stripe parking areas | Layout and stripe throughout property | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 58000 |  |  |  |  | GC (pay app)
85 | 84206 | Window Replacement and Repairs, includin | Contingency for replacements and repairs | GC | Project | 25000 | 25000 |  |  | 25000 | 0 | 25000 | 0 | 25000 | 0 | 25000 | 0 | 250000 |  |  |  |  | GC (pay app)
87 | 84215 | Sliding Balcony Door Replacement and Rep | Contingency for replacements and repairs | GC | Project | 25000 | 25000 |  |  | 25000 | 0 | 25000 | 0 | 25000 | 0 | 25000 | 0 | 250000 |  |  |  |  | GC (pay app)
119 | 84190 | Fitness Center Remodel | Need to replace lights, repair damaged walls, paint, repair flooring that is lifting, repair men's bathroom items | GC | Project | 25000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC tagged, not on pay app
106 | 82131 | Co 2 detectors | Install Co2 detectors in every unit | PMC | Project | 22000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GL PMC
15 | 84303 | Landscape Cleanup and Enhancements | Initial property landscape entry and tour path enhancements, etc | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
163 | 82131 | Smoke Detectors | Equity PCR Item 5.5.2- Smoke detectors not observed in bedrooms, Install | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
25 | 84111 | Dumpster enclosures | Replace fencing around dumpster/compactor enclosures | GC | Project | 18000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
154 | 84217 | Install P trap on HVAC condensate piping | Equity PCR Item 5.3- The interior fan coil units (FCUs) observed at the residential units lacked p-traps at the condens | GC | Project | 16880 | 16880 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16880 |  |  |  |  | GC (pay app)
143 | 83375 | Golf Cart | Need 1-2 leasing carts, have 2 maintenance carts | PMC | Project | 16000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GL PMC
128 | 84340 | Picnic/Grill Furniture | Furniture for new grill areas | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
132 | 84280 | Unit Model Update | Change out carpet, misc supplemental furniture, remove screen door since it is broken and obscures visibility in the mod | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
125 | 84195 | Playground Remodel | Replace swing sets, border and mulch as well as replacing grills with new stand alone ones at secondary park area | GC | Project | 13000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 |  |  |  |  | GC tagged, not on pay app
19 | 84221 | ADA parking & curb cuts | ADA Parking & Curb Cuts | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
26 | 84302 | Irrigation | Equity PCR Item 3.2.4- Although operation of the sprinkler system was not directly tested, property management reported | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC tagged, not on pay app
120 | 84190 | Fitness Equipment | Stair Stepper, other misc items | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
121 | 84361 | Leasing Pool Area Remodel | Replace wood/cable fence section in raised area with metal rail to match other fencing, other misc repairs | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC tagged, not on pay app
20 | 84115 | Sidewalks | Secure, scrape, sand & paint deck walkway from office area to sports complex. | GC | Project | 9500 | 9500 |  |  | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500 |  |  |  |  | GC (pay app)
156 | 84217 | HVAC inspection and maintenance | Clean debris/foliage from around condensors as well as leveling with condensor pads. Includes Equity PCR Item 5.2- Many | PMC | Project | 8500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GL PMC
126 | 84340 | Playground Furniture | Picnic tables and misc items | GC | Project | 8000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC tagged, not on pay app
130 | 84390 | Sports Court- Soccer | Replace shade sails | GC | Project | 8000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC tagged, not on pay app
155 | 84217 | Insulate HVAC lines | Equity PCR Item 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | GC | Project | 5375 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5375 |  |  |  |  | GC tagged, not on pay app
118 | 84306 | Clubhouse / Office Furniture | Not needed, misc allowance | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
124 | 84360 | Secondary Pool Furniture | Misc items & move items from main pool | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
114 | 84103 | Signage - Building identification | Misc replacement signage | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
117 | 84208 | Clubhouse / Office Remodel | Not needed, misc allowance | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
123 | 84361 | Secondary Pool Area Remodel | Need to fix cosmetic issues or possibly resurface | GC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC tagged, not on pay app
139 | 84450 | Security Camera System | Add cameras by mailboxes | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
134 | 84275 | Access Control System | Need to add access control for package lockers in fitness center | PMC | Project | 3000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GL PMC
116 | 84310 | Designer Fees | TBD scope | PMC | Project | 2500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 |  |  |  |  | GL PMC
21 | 84115 | Grind Sidewalk Trip Hazard | Lender PCR Item- Limited trip hazards were observed by Buildings 3825-A, 3777, and the Fitness Center Building. | GC | Project | 2100 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 |  |  |  |  | GC tagged, not on pay app
135 | 84260 | Mailboxes | Misc repairs | PMC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GL PMC
160 | 84239 | Inspect Fire Extinguishers | Lender PCR Item- Fire extinguishers are expired. | PMC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GL PMC
161 | 84211 | Fire Suppression System Inspection | Equity PCR Item 5.5.1- Annual Fire suppression system inspection for Building 3971-3975 | PMC | Project | 1000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GL PMC
162 | 84211 | Fire Alarm System Inspection | Equity PCR Item 5.5.2- Annual fire alarm system inspection for Building 3971-3975. | PMC | Project | 1000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GL PMC
76 | 84101 | Full Exterior Paint |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308000
57 | 84104 | Repair balcony framing & decking |  | DFM |  | 0 | 0 |  |  | 7500 | 0 | 7500 | 0 | 7500 | 0 | 7500 | 0 | 67500
30 | 84095 | Resurface swimming pool |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
32 | 84361 | Repair / Replace Swimming Pool Equipment |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2757064 | [11 empty] | 5315564
|  |  | CM Fee |  |  | 144746 | [11 empty] | 280451
|  |  | Contingency |  |  | 137853 | [11 empty] | 266453
|  |  | Capital Plan Total (ex-BTL) |  |  | 3039663 | [11 empty] | 5862468
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $3,484,000

## Swiss Gables
Swiss Gables — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
95 | 84101 | Exterior building Painting | Paint community including peal stop on all delaminated cedar Paint chipping was observed at the columns and posts of the | GC | Project | 189000 | 151200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239000 |  |  |  |  | GC (pay app)
72 | 84104 | Repair balcony framing & decking | Repair damaged patio and Catwalk framing Balcony repair allowance Deteriorating wood was present at the underside of the | GC | Project | 109000 | 81750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109000 |  |  |  |  | GC (pay app)
55 | 84120 | Concrete deck / floor fill | Seal cracks in landings and cat walks | GC | Project | 70000 | 56000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 |  |  |  |  | GC (pay app)
132 | 84211 | Seal Penetrations in Fire Walls and Smok | Penetrations in the fire and smoke barriers are in poor condition. Penetrations in the fire rated walls were observed as | GC | Project | 70000 | 21000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 |  |  |  |  | GC (pay app)
48 | 84219 | Carports / Garages | Repair damaged sheet rock and paint 1st floor parking garages | GC | Project | 66000 | 52800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000 |  |  |  |  | GC (pay app)
17 | 84204 | Asphalt Coating | Crack fill alligatored asphalt Damaged pavement consisting of linear cracking and alligator cracking was observed east o | GC | Project | 65000 | 19500 |  |  | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 135000 |  |  |  |  | GC (pay app)
96 | 84105 | Repair / replace wood trim | Replace all rotted trim throughout property All Facia is Custom Scalloped Facia | GC | Project | 45000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
22 | 84204 | Stripe parking areas | Stripe parking lot and garages | GC | Project | 36000 | 10800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
73 | 84121 | Repair patio/balcony railings | Secure all balcony and catwalk railings (custom pickets) | GC | Project | 35000 | 28000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
87 | 84206 | Repair / replace wood siding | Replace rotted T-111 siding Damaged soffits were observed along the elevated walkway at Building A, isolated areas at th | GC | Project | 35000 | 28000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
162 | 84210 | Common Area Light Fixtures | Replace parking garage and parking lot lights to LED | GC | Project | 32000 | 25600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
42 | 84340 | Playground equipment | Enhance playground equipment | PMC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
124 | 84103 | Signage - Building identification | Site Rebrand - New Building Signage/New Door Numbers | PMC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
122 | 84290 | Signage - Entry Monument | Site Rebrand - New Monument Sign | PMC | Project | 25000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
161 | 84210 | Electrical Distribution | Repair electric to pole lights and photo cells General electrical deficiencies were observed. The general deficiencies n | GC | Project | 24400 | 19520 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24400 |  |  |  |  | GC (pay app)
153 | 84385 | Sanitary Sewer Piping | Cleanout replacement; Hydrojet as needed | PMC | Project | 24150 | 3967 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24150 |  |  |  |  | GL PMC
77 | 84433 | Asphalt composite shingle roofing | Roof tune up on 7 buildings | GC | Project | 21000 | 21000 |  |  | 7500 | 0 | 7500 | 0 | 7500 | 0 | 7500 | 0 | 66000 |  |  |  |  | GC (pay app)
28 | 84205 | Fences & gates - site perimeter | Repair and paint fence | GC | Project | 21000 | 10500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC (pay app)
83 | 84433 | Flashing | Replace damaged drip edge on cat walks | GC | Project | 21000 | 16800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC (pay app)
25 | 84115 | Sidewalks | Repair trip Hazards Damaged concrete sidewalk was present at the walkway south of Building G. Repairs are recommended. R | GC | Project | 18000 | 10800 |  |  | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 24000 |  |  |  |  | GC (pay app)
133 | 84211 | General Fire Alarm Deficiencies | General fire alarm deficiencies were observed. The general deficiency noted is: expired smoke detectors throughout the b | PMC | Project | 16100 | 8112 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16100 |  |  |  |  | GL PMC
46 | 84111 | Dumpster enclosures | Replace fencing on all dumpster enclosures Custom Pickets | GC | Project | 15000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
82 | 83439 | Gutters & downspouts | Clean and secure gutters and down spouts | GC | Project | 14000 | 14000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
84 | 84433 | Sealants & caulking | Sealants & caulking | GC | Project | 14000 | 14000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
71 | 84121 | Repair exterior stair railings | Repair and secure stair railings | GC | Project | 12000 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
119 | 84211 | Fire protection | Fire protection - Fire Stops | PMC | Project | 10584 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10584 |  |  |  |  | GL PMC
16 | 84303 | Landscape Cleanup and Enhancements | Isolated locations of tree overgrowth at building elevations were observed. Tree trimming is recommended | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
164 | 84210 | Organize Electrical Wiring | The surface raceway in Building-C, unit C303, requires repair to ensure the proper protection and organization of electr | GC | Project | 5000 | 4000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
24 | 84115 | Curbing Repairs | Damaged curbing was present southeast of Building C and at the east entrance to Building E. Repairs are recommended. | GC | Project | 1500 | 2000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GC (pay app)
38 | 83520 | Install ADA-Compliant Curb Cut Ramps | ADA-compliant curb cut ramps are not present on accessible route at the subject property. Inclusion of ADA-compliant cur | PMC | Project | 1200 | 9265 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | GL PMC
39 | 83520 | Install ADA-Compliant Handrailing at Ram | The ramps within the accessible route do not appear to have ADA-compliant handrails. Reconfiguration of the handrails is | PMC | Project | 1200 | 9265 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | GL PMC
242 |  | 787.0370370370371 |  |  |  | 1000 | 0 |  |  | 1000 | 0 | 1000 | 0 | 1250 | 0 | 1500 | 0 | 17773
165 | 84210 | Electrical Buzzing Sound | An electrical buzzing sound coming from the underground vault adjacent to the main roadside transformer indicates a pote | GC | Project | 1000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GC tagged, not on pay app
241 |  | 9074.111111111111 |  |  |  | 823 | 0 |  |  | 823 | 0 | 893 | 0 | 967 | 0 | 852 | 0 | 11778
108 | 83236 | Install CO Detectors | Carbon monoxide detectors are not provided in dwelling units, and wood burning fireplaces were provided in the third flo | PMC | Project | 770 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770 |  |  |  |  | GL PMC
40 | 83520 | Install ADA-Compliant Door Hardware | The door at the designated accessible entrance does not appear to have ADA compliant hardware. Installation of ADA compl | PMC | Project | 450 | 3474 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 |  |  |  |  | GL PMC
37 | 83520 | Install ADA Van-Accessible Space | The accessible parking spaces did not appear to be generally correctly configured. The installation of one van-accessibl | PMC | Project | 400 | 3088 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 |  |  |  |  | GL PMC
154 | 84476 | Install Seismic Strapping | The water heater at the employee restroom in Building C lacked seismic bracing straps. Provision of adequate seismic bra | PMC | Project | 250 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 |  |  |  |  | GL PMC
243 |  | 0 |  |  |  | 177 | 0 |  |  | 177 | 0 | 107 | 0 | 283 | 0 | 648 | 0 | 5994
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1067004 | [11 empty] | 1271549
|  |  | CM Fee |  |  | 53250 | [11 empty] | 53250
|  |  | Capital Plan Total (ex-BTL) |  |  | 1120254 | [11 empty] | 1297804
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 15682
BTL (dropped per Adam): $636,028
Note: line detail sums to $1,324,800; the 10-yr total shown is Adam's stated $1,297,804 (7/21 ruling) — line drift Δ $26,996.

## The Ardent
The Ardent — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
97 | 84101 | Exterior Painting | Paint community including peal stop on all delaminated cedar | GC | Project | 916200 | 274860 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832400 |  |  |  |  | GC (pay app)
98 | 84113 | Repair / replace wood trim | Replace all rotted trim throughout property | GC | Project | 158000 | 47400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158000 |  |  |  |  | GC (pay app)
89 | 84102 | Repair / replace wood siding | Replace rotted siding and scrape and paint Cedar siding Recommended to evaluate wall cavity conditions and prioritize bu | GC | Project | 110000 | 33000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 |  |  |  |  | GC (pay app)
30 | 84303 | Landscaping | Trees were observed impeding on the building envelope at apartment buildings and also at the roofs of the carports. It i | GC | Project | 80000 | 0 |  |  | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 280000 |  |  |  |  | GC tagged, not on pay app
85 | 84433 | Roofing - Flashing | Replace damaged drip edge on balconies | GC | Project | 67400 | 20220 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201400 |  |  |  |  | GC (pay app)
46 | 84204 | Pavement | R&R 6000 SF of Potholes and the worst alligatored pavement | GC | Project | 60000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GC (pay app)
79 | 84433 | Asphalt composite shingle roofing | Roof tune up on 37 buildings Isolated areas of damaged and lifted asphalt shingles were observed at Buildings B and S. | GC | Project | 57000 | 17100 |  |  | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 297000 |  |  |  |  | GC (pay app)
42 | 84219 | Carports | Replace rotted facia on carports Isolated posts show significant deterioration and should be replaced immediately. Recom | GC | Project | 52000 | 15600 |  |  | 15000 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | 187000 |  |  |  |  | GC (pay app)
86 | 84433 | Roofing - Sealants & caulking | Roof Sealant & Caulking | GC | Project | 49000 | 14700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 |  |  |  |  | GC (pay app)
71 | 84104 | Repair balcony framing & decking | Repair damaged patio framing | GC | Project | 45000 | 13500 |  |  | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 290000 |  |  |  |  | GC (pay app)
93 | 84106 | Dryer Vents | Dryer Vent Cleaning | PMC | Project | 42750 | 16706 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42750 |  |  |  |  | GL PMC
122 | 84211 | Fire Protection | Includes adding fire stops in all units | PMC | Project | 42750 | 19836 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42750 |  |  |  |  | GL PMC
69 | 84114 | Repair exterior stair treads and stringe | Repair stair tread and stringers | GC | Project | 37000 | 11100 |  |  | 38110 | 0 | 39253 | 0 | 40431 | 0 | 41644 | 0 | 424164 |  |  |  |  | GC (pay app)
84 | 83439 | Gutters & downspouts | Clean and secure gutters and down spouts | GC | Project | 37000 | 11100 |  |  | 0 | 0 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 197000 |  |  |  |  | GC (pay app)
25 | 84115 | Sidewalks | Repair trip hazards Potential trip hazards consisting of damaged concrete and vertical and horizontal separation were pr | GC | Project | 32000 | 9600 |  |  | 15000 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | 167000 |  |  |  |  | GC (pay app)
54 | 84430 | Concrete deck / floor fill | Seal cracks in landings | GC | Project | 28000 | 8400 |  |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 88000 |  |  |  |  | GC (pay app)
43 | 84111 | Dumpster enclosures | Replace fencing on all dumpster enclosures | GC | Project | 27000 | 8100 |  |  | 15000 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | 162000 |  |  |  |  | GC (pay app)
90 | 84102 | Masonry Repairs | Repair Exterior Masonry Walls | GC | Project | 23500 | 7050 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47000 |  |  |  |  | GC (pay app)
72 | 84121 | Repair patio/balcony railings | Secure all balcony railings | GC | Project | 16000 | 4800 |  |  | 15000 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 0 | 151000 |  |  |  |  | GC (pay app)
37 | 84432 | Storm Sewer Piping | Clean Yard Basin | GC | Project | 14000 | 4200 |  |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 59000 |  |  |  |  | GC (pay app)
73 | 83426 | Exterior Doors - replacement doors at pa | Patio & Balcony Storage Doors | GC | Project | 12000 | 3600 |  |  | 12000 | 0 | 12000 | 0 | 12000 | 0 | 12000 | 0 | 120000 |  |  |  |  | GC (pay app)
70 | 84121 | Repair exterior stair railings | Repair and secure stair railings | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 57000 |  |  |  |  | GC (pay app)
51 | 84430 | Foundation - Seal pier and beam area | Replace damaged foundation vents | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
67 | 84211 | Fire - Draft Stops | Allowance to seal small penetrations in attic draft stops - Small openings were observed within the demising draft stop | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
74 | 84102 | Building Repairs & Exterior Walls | The exterior walls were observed with vegetative staining, peeling paint, and areas of damaged siding at the exterior wa | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
95 | 84113 | Breezeway soffit repairs | Add soffit vents at Phase 3 breezeways to improve attic ventilation and enhance moisture control; addresses incomplete v | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC tagged, not on pay app
39 | 84340 | Playground equipment | Replace fall zone mulch | GC | Project | 5400 | 1620 |  |  | 0 | 0 | 5500 | 0 | 0 | 0 | 5500 | 0 | 27400 |  |  |  |  | GC (pay app)
50 | 84432 | Drain piping |  | DFM |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
61 | 84110 | Stairs - Repair or replace damaged concr | Replace sill plate supporting stair landing post outside of Unit 24 at Building 03C - Still plate has signficant rot | GC | Project | 2000 | 600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC (pay app)
24 | 83520 | Curb cuts | Damaged concrete curbs were observed consisting of displacement and linear cracking were observed at the parking area pe | GC | Project | 1200 | 6000 |  |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21200 |  |  |  |  | GC (pay app)
17 | 84204 | Asphalt Coating | Crack fill, seal, and coat Damaged pavement consisting of pothole formation and alligator cracking was observed primaril | GC | Project | 1125 | 78000 |  |  | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261125 |  |  |  |  | GC (pay app)
107 | 84217 | Seismic Shutoff Valve | There is a natural gas line provided to Fitness Center B, and it is not provided with a seismic shutoff valve. Provide a | PMC | Project | 1000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GL PMC
106 | 84209 | Water Heater Strapping | This item is for compliance with Section 507.2 of the Washington Plumbing Code. This item can be carried out as part of | PMC | Project | 300 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 |  |  |  |  | GL PMC
76 | 84102 | Replace siding, based on early signs of |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000
75 | 84102 | Replace siding as needed. Including demo |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
124 | 82450 | Unit Interior Replacements |  | DFM |  | 0 | 0 |  |  | 300000 | 0 | 300000 | 0 | 300000 | 0 | 0 | 0 | 900000
96 | 84120 | Replace breezeway carpet with liquid app |  | DFM |  | 0 | 0 |  |  | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 289000
22 | 84204 | Seal & Stripe parking areas | Stripe Parking Lot | GC | Project | 0 | 9600 |  |  | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165300 |  |  |  |  | GC (pay app)
44 | 84390 | Sport Court Renovation: Tennis | Repair chain link fence around tennis court. Turn into pickleball | GC | Project | 0 | 15000 |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 64000 |  |  |  |  | GC (pay app)
133 | 84190 | Fitness Center Remodel (Gym 1 Phase II) | Turn yoga studio into pool lounge with Bay door | GC | Project | 0 | 15000 |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
199 | 83220 | 83220 - HVAC Equipment (HVAC FULL NEW RE |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000
163 | 84210 | Lighting - Common area light fixtures | Replace walkway pole lights - change to wall pack lights? ($5k) | GC | Project | 0 | 14400 |  |  | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 |  |  |  |  | GC (pay app)
34 | 84361 | Swimming Pool 1 (Phase I: Leasing Office | Repair cracked conrete & Update Pool Furniture | GC | Project | 0 | 10500 |  |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
35 | 84361 | Swimming Pool 2 (Phase I: Tennis Court) | Repair cracked conrete & Update Pool Furniture (Removed) | GC | Project | 0 | 0 |  |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC tagged, not on pay app
36 | 84361 | Swimming Pool 3 (Phase II) | Repair gate and paint fence Mark had $7.6K. Repair cracked concrete & Update Pool Furniture | GC | Project | 0 | 10500 |  |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
161 | 84210 | Electrical Distribution | Repair electric to pole lights and photo cells | GC | Project | 0 | 9600 |  |  | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
38 | 84114 | Replace Nature Walk Stair Structure |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
201 | 83300 | 83300 - Landscaping/Irrigation |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 30000
31 | 84095 | Resurface swimming pool | Resurface Swimming Pool | GC | Project | 0 | 7500 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
45 | 84390 | Sport Court Renovation: Basketball | Restripe & Add New Hoop | GC | Project | 0 | 7500 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
134 | 84190 | Fitness Center Remodel (Gym 2 Phase III) | Convert into golf simulator | GC | Project | 0 | 0 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC tagged, not on pay app
182 | 82260 | 82260 - Exterior Lighting | Increase lighting across the property - Defer | GC | Project | 0 | 0 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC tagged, not on pay app
194 | 83208 | 83208 - Office/Clubhouse/Lobby Improveme |  | AMN |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
190 | 83100 | 83100 - Pool Heaters |  | DFM |  | 0 | 0 |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
32 | 84361 | Replace swimming pool coping | Replace Pool Coping | GC | Project | 0 | 5250 |  |  | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 |  |  |  |  | GC (pay app)
140 | 84130 | Dog Park | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola | GC | Project | 0 | 0 |  |  | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC tagged, not on pay app
192 | 83105 | 83105 - Exterior Carpentry |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
196 | 83210 | 83210 - Electrical/Lighting |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 12000
197 | 83211 | 83211 - Fire Life Safety System Work |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
40 | 84121 | Refinish metal picket fencing and metal |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 11000
41 | 84205 | Replace stockade fencing at the east sid |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10200
193 | 83205 | 83205 - Fences/Gates |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
198 | 83212 | 83212 - Cabinets |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000
200 | 83270 | 83270 - Maintenance Shop |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1976625 | [11 empty] | 11267489
|  |  | CM Fee |  |  | 103773 | [11 empty] | 557366
|  |  | Contingency |  |  | 98831 | [11 empty] | 98831
|  |  | Capital Plan Total (ex-BTL) |  |  | 2179229 | [11 empty] | 11923686
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 23584
BTL (dropped per Adam): $3,668,094

## The Fairways
The Fairways — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
18 | 84204 | Asphalt Coating | Crack fill and double seal coat asphalt throughout property. Includes Lender PCR Item- Damaged pavement consisting of l | GC | Project | 298500 | 298500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298500 |  |  |  |  | GC (pay app)
53 | 84101 | Repair balcony framing & decking | Half the properties balconies are showing signs of weathering due to moisture/rot. Replace any rotted wood and scrap, sa | GC | Project | 95000 | 95000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 |  |  |  |  | GC (pay app)
21 | 84300 | Landscaping | Tree trim and clean up throughout property. 1st Call getting bid in conjunction with Paddocks to improve cost | GC | Project | 92800 | 92800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92800 |  |  |  |  | GC (pay app)
64 | 84433 | Asphalt composite shingle roofing | Replace flashing around all chimneys throughout property as well as a minor roof tune up to each building. Any significa | GC | Project | 50000 | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
124 | 84360 | Pool Furniture | Maybe budget for full replacement. Tables and chairs look ok, 24 chaises are ok but a cheaper style. Budget for new, a f | PMC | Project | 50000 | 75016 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
75 | 84206 | Repair / replace cement fiber siding | Repair/replace areas of failed hardie board and paint to match throughout property | GC | Project | 41500 | 41500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41500 |  |  |  |  | GC (pay app)
22 | 84095 | Resurface swimming pool | Resurface pool | GC | Project | 40000 | 32200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
76 | 84113 | Repair / replace wood trim | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. | GC | Project | 38500 | 38500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38500 |  |  |  |  | GC (pay app)
157 | 84210 | Replace breezeway lights | Breezeway Lighting | GC | Project | 37500 | 37500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 |  |  |  |  | GC (pay app)
24 | 84361 | Repair swimming pool deck | Clean pool deck, crack fill and seal. Repair the deck attached to pool deck and repaint/stain. Reinforce and lvel suppor | GC | Project | 35000 | 35000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
125 | 84203 | Picnic/Grill Area Remodel | Look at adding grills and outdoor kitchen, gazebo, landscaping or turf in planters, replace/fix lights | GC | Project | 30000 | 27000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
25 | 84130 | Dog Park | Replace chainlink fencing around dog park and replace with aluminum fencing. Add enzyme injector to irrigation valve | GC | Project | 26000 | 7800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
127 | 84390 | Sports Courts | Resurface and add 2 pickleball courts along with tennis | GC | Project | 25000 | 25000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
153 | 84218 | HVAC inspection and maintenance | Clean foliage around condensors throughout property. Raise units with HVAC pad as needed. | GC | Project | 24000 | 24000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
20 | 84221 | Sidewalks | Repair cracked/broken sidewalks throughout property. | GC | Project | 22000 | 22000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
156 | 84210 | Electrical distribution | Electrical Distribution | GC | Project | 22000 | 22000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
14 | 84300 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | PMC | Project | 20000 | 27840 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
98 | 84106 | Drier vents | Clean dryer vents throughout property. | GC | Project | 18000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
17 | 84221 | concrete pavement | Fill cracks and seal area next to dog park and sports court. | GC | Project | 17500 | 17500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 |  |  |  |  | GC (pay app)
108 | 82131 | CO detectors | Install CO detectors in each unit. Lender PCA Item- Due to the presence of gas-fire water heaters at each unit, carbon m | PMC | Project | 16800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16800 |  |  |  |  | GL PMC
119 | 84208 | Clubhouse / Office Remodel | Paint cabinets in kitchen with hardware, add backsplash, replace appliances, replace "snack shack" window to be function | GC | Project | 15000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
123 | 84361 | Pool Area Remodel | Games and placeholder budget - TV contacting Key Designs | PMC | Project | 15000 | 65776 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
15 | 84209 | Sanitary sewer piping | Add rocks around storm drains around property. Clean the area around the drain. | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
109 | 84239 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods TV to verify with Dan H on ordering | PMC | Project | 11723 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11723 |  |  |  |  | GL PMC
19 | 84201 | ADA parking & curb cuts | Include where needed in concrete/asphalt work | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
120 | 82140 | Clubhouse / Office Furniture | Looks good, misc supplemental items - Add a TV. TAM to order and install. Move the leasing desktop to back work area, pu | PMC | Project | 10000 | 10439 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
126 | 84195 | Picnic/Grill Furniture | Tables ok, possibly add games | PMC | Project | 10000 | 24300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
134 | 84206 | Storage Shed | Look at adding storage shed for appliances next to maintenance - enclose area to left of maintenance shop | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
16 | 84385 | Storm sewer piping | Improve current french drain towards the back right of the property. | GC | Project | 8500 | 8500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
51 | 84114 | Repair exterior stair treads and stringe | Secure. | GC | Project | 7500 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC (pay app)
52 | 84121 | Repair exterior stair railings | Secure. | GC | Project | 7500 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC (pay app)
131 | 84275 | Access Control System | Need for pool area and bathroom doors - just updating to keypad. Review for future FOB system for afterhours access on a | PMC | Project | 6000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GL PMC
128 | 84130 | Dog Park | Looks good, misc budget - add enzyme injector | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
158 | 84361 | Pool area lighting | Lights are all 110 and need to be rewired | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
23 | 84361 | Replace swimming pool coping | Deck-O-Seal coping around pool. And relocate pots off the new deck to avoid further damage | GC | Project | 4500 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  |  |  | GC (pay app)
26 | 84111 | Dumpster enclosures | Repair any damage on dumpster enclosure. | GC | Project | 2150 | 2150 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150 |  |  |  |  | GC (pay app)
27 | 84434 | Retaining walls | Retaining wall needs repair by sport court - replace with stone wall | GC | Project | 2000 | 2000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC (pay app)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1141973 | [11 empty] | 1141973
|  |  | CM Fee |  |  | 66000 | [11 empty] | 66000
|  |  | Contingency |  |  | 178027 | [11 empty] | 178027
|  |  | Capital Plan Total (ex-BTL) |  |  | 1386000 | [11 empty] | 1386000
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## The Lakes
The Lakes — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
18 | 84204 | Asphalt Coating | Lakes - Crack fill, seal and coating Revive - Crack fill, seal and coating | GC | Project | 455000 | 136500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455000 |  |  |  |  | GC (pay app)
76 | 84433 | Asphalt Composite Shingle Roofing | Lakes - Roof tune up on buildings 9 Revive - Replace Roofs | GC | Project | 428000 | 428000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487082 |  |  |  |  | GC (pay app)
96 | 84101 | Exterior Building Paint | Lakes - Paint community Revive - Paint community | GC | Project | 348000 | 104400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348000 |  |  |  |  | GC (pay app)
132 | 84190 | Fitness Center Remodel | Revive - Convert Leasing office into a Gym | GC | Project | 100000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  |  |  |  | GC (pay app)
30 | 84303 | Landscaping | Lakes - Tree trim and raise canopy | GC | Project | 64000 | 19200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000 |  |  |  |  | GC (pay app)
22 | 84205 | Fencing | Take down the chain-link fence separating properties. Add two paths for golf cart to travel between. Add walking path - | GC | Project | 50000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
54 | 84430 | Concrete Deck / Floor Fill | Lakes - Seal cracks in landings Revive - Seal cracks in landings | GC | Project | 41000 | 12300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41000 |  |  |  |  | GC (pay app)
17 | 84303 | Landscape Cleanup and Enhancements | Lakes - Landscape Enhancements Revive - Landscape Enhancements | PMC | Project | 40000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GL PMC
87 | 84102 | Repair / Replace Wood Siding | Lakes - Replace rotted siding and scrape and paint Cedar siding Revive - Replace rotted siding and scrape and paint Ceda | GC | Project | 40000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
97 | 84113 | Repair / Replace Wood Trim | Lakes - Replace all rotted trim throughout property Revive - Replace all rotted trim throughout property | GC | Project | 40000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
147 | 84450 | Security Camera System | Install new Security Cameras | PMC | Project | 35000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GL PMC
133 | 84208 | Cyber Café upgrade at Lakes | Lakes - Open up the side wall and expand the leasing area | GC | Project | 30000 | 9000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
26 | 84115 | Sidewalks Trip Hazard | Lakes - Repair trip hazards Revive - Repair trip hazards. A limited sidewalk crack was also observed by Building 2335. | GC | Project | 29000 | 8700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 |  |  |  |  | GC (pay app)
23 | 84201 | Stripe Parking Areas | Lakes - Stripe Parking Lot Revive - Stripe Parking Lot | GC | Project | 28000 | 8400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60760 |  |  |  |  | GC (pay app)
25 | 83520 | ADA Parking & Curb Cuts | Lakes - Concrete Modifications Revive - Concrete Modifications | GC | Project | 26000 | 7800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
29 | 84204 | Pavement | Lakes - R&R 2000 Sf of Potholes Revive - R&R 1500 sq ft pavement | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
43 | 84111 | Dumpster Enclosures | Lakes - Replace fencing on all dumpster enclosures Revive - Replace fencing on all dumpster enclosures | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
68 | 84114 | Repair Exterior Stair Treads and Stringe | Lakes - Repair stair tread and stringers Revive - Repair stair tread and stringers | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
121 | 84211 | Fire Stops | Add Fire Stops | PMC | Project | 24696 | 18931 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24696 |  |  |  |  | GL PMC
69 | 84121 | Repair Exterior Stair Railings | Lakes - Repair and secure stair railings Revive - Repair and secure stair railings | GC | Project | 24000 | 7200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
27 | 84432 | Storm Sewer Piping | Lakes - Clean Yard Basins of Debris Revive - Clean Yard Basins of Debris | GC | Project | 23000 | 6900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 |  |  |  |  | GC (pay app)
82 | 84433 | Flashing | Lakes - Replace damaged drip edge on balconies. Revive - Replace damaged drip edge on balconies. LRR - Damaged balconi | GC | Project | 22800 | 6840 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22800 |  |  |  |  | GC (pay app)
70 | 84104 | Repair Balcony Framing & Decking | Lakes - Repair damaged patio framing Revive - Repair damaged patio framing | GC | Project | 22000 | 6600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
71 | 84121 | Repair Patio/Balcony Railings | Lakes - Secure all balcony railings Revive - Secure all balcony railings | GC | Project | 22000 | 6600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
81 | 84202 | Gutters & Downspouts | Lakes - Clean and secure gutters and down spouts Revive - Clean and secure gutters and down spouts | GC | Project | 22000 | 22000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
83 | 84102 | Sealants & Caulking | Lakes - Roof Sealants & Caulking Revive - Roof Sealants & Caulking | GC | Project | 22000 | 22000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
38 | 84361 | Pool Area | Lakes - Enhance pool area with turf and a fireplace | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
36 | 84205 | Fences & Gates - Swimming Pool | Lakes - Repair gate and paint fence Revive - Repair gate and paint fence | GC | Project | 16200 | 4860 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30200 |  |  |  |  | GC (pay app)
28 | 84205 | Fences & Gates - Site Perimeter | Revive - Add ~200ft wall between Revive and comp with razor wire | GC | Project | 15000 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
130 | 83375 | Leasing Golf Cart | Get Leasing Golf Cart | PMC | Project | 15000 | 32400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
67 | 84433 | Roof Deck | Revive - Roof Deck Repairs | GC | Project | 13000 | 13000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 |  |  |  |  | GC (pay app)
156 | 84385 | Sanitary Sewer Piping | Lakes - Building C - Minor tree root intrusion. Recommended remediation: Dig approximately 4 feet and replace the affect | PMC | Project | 6600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 |  |  |  |  | GL PMC
107 | 82460 | Repair Microbial Growth | LRR - Limited areas of microbial growth was observed in the bedroom corner and closet wall of Unit 2347-1. Affected non- | PMC | Project | 900 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 |  |  |  |  | GL PMC
32 | 83520 | ADA Modifications | Revive - Common area restroom sink is not insulated at clubhouse. LRR- ADA sink insulation | PMC | Project | 350 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 |  |  |  |  | GL PMC
88 | 84101 | Paint/Finish |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 75600
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 2098546 | [11 empty] | 2279988
|  |  | CM Fee |  |  | 119624 | [11 empty] | 119624
|  |  | Contingency |  |  | 104927 | [11 empty] | 104927
|  |  | Capital Plan Total (ex-BTL) |  |  | 2323097 | [11 empty] | 2504539
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 14548
BTL (dropped per Adam): $0
Note: line detail sums to $2,504,539; the plan's Capital Plan Total is $2,646,169 — Δ $141,630 carried only in the plan's total column (pending review).

## The Vibe
The Vibe — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
52 | 84101 | Exterior building | PNA - Paint community including peal stop on all delaminated cedar LPCA - Faded paint finishes were observed at several | GC | Project | 592200 | 532980 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592200 |  |  |  |  | GC (pay app)
24 | 84095 | Resurface swimming pool | PNA - contingent amount to work on pool resurface | GC | Project | 70000 | 21000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 |  |  |  |  | GC (pay app)
16 | 84204 | Asphalt Coating | PNA - contingent amount to work on parking lot as needed. LPCA - Linear/alligator cracking and pothole formation was obs | GC | Project | 68000 | 40800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120250 |  |  |  |  | GC (pay app)
45 | 84050 | Asphalt composite shingle roofing | PNA - Roof tune up on 37 buildings | GC | Project | 40000 | 40000 |  |  | 25000 | 0 | 25000 | 0 | 25000 | 0 | 25000 | 0 | 265000 |  |  |  |  | GC (pay app)
27 | 84095 | Replace swimming pool deck | PNA - address existing cracking on pool decks and cosmetic enhacement | GC | Project | 40000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 |  |  |  |  | GC (pay app)
59 | 84450 | Security Camera System | Adding 9 security cameras (inc. installation, labor, etc.) | PMC | Project | 37000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 |  |  |  |  | GL PMC
66 | 84210 | Replace electrical panels | HPCA - Replace 8 Electrical Panels (Estimated Potential Recalled Heaters) | GC | Project | 36000 | 10800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
53 | 84105 | Repair / replace wood trim | PNA - Replace all rotted trim throughout property | GC | Project | 35000 | 35000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
17 | 84090 | Stripe parking areas | PNA - stripe parking lot | GC | Project | 32000 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
46 | 84050 | Gutters & downspouts | PNA - Clean and secure gutters and down spouts HPCA - Repair selective areas of damaged gutter; reconnect Downspouts to | GC | Project | 32000 | 32000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
38 | 84102 | Concrete deck / floor fill | PNA - seal cracks in landings | GC | Project | 26000 | 18200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
48 | 84050 | Sealants & caulking | Roof Sealant & Caulking | GC | Project | 26000 | 26000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
55 | 84239 | Fire Protection | Fire Stops | PMC | Project | 24675 | 2798 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24675 |  |  |  |  | GL PMC
22 | 84205 | Fences & gates - site perimeter | PNA - Pool fence is vinyl and post holding up the fence are rotting. Repair posts and repair fence | GC | Project | 24000 | 19200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
20 | 84080 | Sidewalks | PNA - Repair trip hazards HPCA - Concrete Walks/Steps - Trip Hazards/ADA | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
42 | 84104 | Repair balcony framing & decking | PNA - repair damaged patio framing | GC | Project | 18000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
50 | 84105 | Repair / replace wood siding | PNA - Replace rotted siding and scrape and paint Cedar siding | GC | Project | 18000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
30 | 84085 | Carports / Garages | PNA - Replace rotted facia on carports | GC | Project | 17000 | 17000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 |  |  |  |  | GC (pay app)
40 | 84114 | Repair exterior stair treads and stringe | PNA - repair stair tread and stringers | GC | Project | 16000 | 16000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
43 | 84205 | Repair patio/balcony railings | PNA - secure all balcony railings | GC | Project | 16000 | 16000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
21 | 84470 | Storm sewer piping | PNA - Clean yard basins of debree | GC | Project | 12000 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
29 | 84125 | Dumpster enclosures | PNA - Replace fencing on all dumpster enclosures | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
41 | 84205 | Repair exterior stair railings | PNA - repair and secure stair railings | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
47 | 84050 | Flashing | PNA - Replace damaged drip edge on balconies | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
57 | 84304 | Bathroom cleaning/klitz/painting with or | HPCA - Excessive damage repair and repainting | PMC | Project | 12000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GL PMC
68 | 84210 | Electrical distribution | PNA - Repair electric to pole lights and photo cells | GC | Project | 12000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
25 | 84095 | Pool Lift | HPCA - Add ADA lift to 1 pool | GC | Project | 9500 | 2850 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 |  |  |  |  | GC (pay app)
26 | 84095 | Pool Pumps | HPCA - Install variable speed pool pumps with VFD control | GC | Project | 8659 | 2598 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8659 |  |  |  |  | GC (pay app)
15 | 84300 | Landscape Cleanup and Enhancements | HPCA - Tree trimming/removal overhanging structures | PMC | Project | 7500 | 4077 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GL PMC
23 | 84080 | Move topsoil/mulch away from bldg. sidin | HPCA - Backfill exposed/undercut concrete steps and foundations | GC | Project | 7500 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC (pay app)
69 | 84210 | Common area light fixtures | PNA - Replace pole lights around pool | GC | Project | 7500 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GC (pay app)
64 | 84210 | Inspect defective ITE electrical panels | HPCA - Given the Bldg.'s were constructed between 1985 and 1986 there is the potential some of the Unit ITE Electrical P | GC | Project | 5250 | 5250 |  |  | 6000 | 0 | 6000 | 0 | 6000 | 0 | 6000 | 0 | 59250 |  |  |  |  | GC (pay app)
63 | 84218 | Inspect defective heaters | HPCA - Review Cadet Heaters and replace any Models installed between 1982 through 1999 Modles: FW, FX, LX, TK, ZA, Z, RA | GC | Project | 5250 | 5250 |  |  | 3400 | 0 | 3400 | 0 | 3400 | 0 | 3400 | 0 | 35850 |  |  |  |  | GC (pay app)
31 | 84432 | Drainage correction | HPCA - Drainage corrections at carports | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
51 | 84105 | Repair stucco | Exterior Stucco Repair | GC | Project | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
28 | 84122 | Playground area | HPCA - Add ADA path of travel to playground | GC | Project | 3500 | 1050 |  |  | 0 | 0 | 3135 | 0 | 0 | 0 | 0 | 0 | 6635 |  |  |  |  | GC (pay app)
65 | 842220 | Replace recalled heaters | HPCA - Replace 16 Recalled Heaters (Estimated Potential Recalled Heaters) | GC | Project | 3200 | 960 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 |  |  |  |  | GC (pay app)
56 | 84470 | Unit Water Leak Repairs | HPCA - Unit P104 Bathroom Water Leak Repairs | PMC | Project | 3000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GL PMC
19 | 84090 | ADA parking & curb cuts | Concrete Modifications | GC | Project | 2250 | 675 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 |  |  |  |  | GC (pay app)
61 | 84470 | Water Distribution and Domestic Hot Wate | Discuss with maintenace manager | PMC | Project | 2250 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 |  |  |  |  | GL PMC
70 | 84210 | Outlets & Dryer Vents | Contingent as needed | PMC | Project | 2000 | 5003 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GL PMC
39 | 84105 | Unit Deck Resurfacing | HPCA - Bldg. M Unit 302 Deck resurfacing. Exposed painted plywood at unit deck surface | GC | Project | 1200 | 360 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | GC (pay app)
18 | 84085 | Parking equipment | HPCA - Add ADA van stall at Carport | GC | Project | 500 | 150 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GC (pay app)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1336934 | [11 empty] | 1747919
|  |  | CM Fee |  |  | 78333 | [11 empty] | 78333
|  |  | Contingency |  |  | 229733 | [11 empty] | 229733
|  |  | Capital Plan Total (ex-BTL) |  |  | 1645000 | [11 empty] | 2055985
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 136404
BTL (dropped per Adam): $1,892,358

## Valera Riverside
Valera Riverside — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
126 | 84103 | Signage - Building identification | *Per Kevin for Signage Change/Rebrand | PMC | Project | 50000 | 3833 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
120 | 84239 | Fire Stops | Fire stops | PMC | Project | 25480 | 3345 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25480 |  |  |  |  | GL PMC
28 | 84434 | Retaining walls | Paint mural on retaining wall outside pool | PMC | Project | 25000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GL PMC
131 | 84190 | Fitness Center Remodel | additional equipment | PMC | Project | 20000 | 1814 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
36 | 84195 | Pergola | repair and stain bar and deck | GC | Project | 9500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 |  |  |  |  | GC (GL fallback)
18 | 84361 | Repair / replace swimming pool pumps | seal small cracks on pool deck | GC | Project | 6500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | GC (GL fallback)
145 | 84211 | Security/ fire alarm systems | Yellow, Non-Compliance tags were observed affixed to the sprinkler risers, dated May 2025. | PMC | Project | 5000 | 8924 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
46 | 84203 | Outdoor Kitchen | replace broken gas valve | GC | Project | 3000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GC (GL fallback)
95 |  | Exterior building (Paint) |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 637500 | 0 | 637500
17 |  | Resurface swimming pool |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 144480 | [11 empty] | 851980
|  |  | CM Fee |  |  | 7585 | [11 empty] | 7585
|  |  | Contingency |  |  | 7224 | [11 empty] | 7224
|  |  | Capital Plan Total (ex-BTL) |  |  | 159289 | [11 empty] | 866789
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 9853
BTL (dropped per Adam): $1,773,988

## Windward
Windward — 10-Year Capital Plan
Acquired 2025. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
167 | 84330 | Electrical Panel Disconnects & Meter Ban | Vistria: raise electrical panel replacements up front @ $2,300 a unit | GC | Project | 676200 | 202860 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676200 |  |  |  |  | GC (pay app)
115 | 84304 | Doors | Cost Reallocation from BTL Yr1: replace sliding doors at turnover (40% in Yr 1, 30% in Yr 2, 20% in Yr 3, and 10% in Yr | PMC | Project | 180000 | 1022 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 |  |  |  |  | GL PMC
16 | 84204 | Asphalt Coating | PNA: Seal Coat and Crack Fill (Decreased by $127380 and moved BTL in Yr 5) | GC | Project | 144000 | 43200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 31569 | 0 | 175569 |  |  |  |  | GC (pay app)
15 | 84303 | Landscape Cleanup and Enhancements | Tree trimming (Added in after PNA/Site Visit) | PMC | Project | 50000 | 19200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
125 | 84103 | Signage - Site | Post: Adding in signage to account for switching from Cortland signage | PMC | Project | 50000 | 1032 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
106 | 84431 | Flooring | Cost Reallocation from BTL Yr1: Adjusted amount to reflect replacing one unit's floors per month ($3k per turn) | PMC | Project | 36000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GL PMC
168 | 84210 | Common area light fixtures | Vistria: address adding exterior lighting around mailbox area (includes other lighting enhancements) | GC | Project | 35000 | 10500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
105 | 84431 | Appliances Package | Cost Reallocation from BTL Yr1: Adjusted amount to reflect appliance actuals on Cortland's past BTL | PMC | Project | 29680 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29680 |  |  |  |  | GL PMC
120 | 84211 | Fire Stops | PNA: Fire stops | PMC | Project | 28812 | 24990 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28812 |  |  |  |  | GL PMC
21 | 84201 | Stripe parking areas | Stripe Parking Lot Decreased $34,115 and moved BTL in Yr 9 | GC | Project | 28000 | 8400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 30907 | 0 | 58907 |  |  |  |  | GC (pay app)
162 | 84218 | Replace AC condenser | PNA: Add insulation to Condensing unit lines | GC | Project | 26000 | 7800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
22 | 84204 | Pavement Repairs | PNA: Repair potholes Lender PCA/Equity PCA: Damaged pavement consisting of linear cracking and alligator cracking, was o | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
75 | 84433 | Asphalt composite shingle roofing | PNA: Standard roof tune up on ridge, vallt and pipe jacks; Equity PCA: Roof replacement - asphalt shingles (Yr 10) (Decr | GC | Project | 22000 | 6600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196527 |  |  |  |  | GC (pay app)
109 | 84106 | Clean Dryer vents | Clean vents and replace missing covers (Added in after PNA/Site Visit) | GC | Project | 16170 | 4851 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16170 |  |  |  |  | GC (pay app)
80 | 84202 | Gutters & downspouts | PNA: Clean and repitch gutters throughout property | GC | Project | 16000 | 4800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
112 | 84476 | Water Heaters | Cost Reallocation from BTL Yr1: Adjusted amount to reflect water heater actuals on Cortland's past BTL | PMC | Project | 16000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GL PMC
114 | 84218 | HVAC inspection and maintenance | Cost Reallocation from BTL Yr1: Adjusted amount to reflect HVAC actuals on Cortland's past BTL | PMC | Project | 16000 | 9522 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GL PMC
150 | 83375 | Golf Cart | Post: Adding in new leasing golf cart | PMC | Project | 15000 | 5814 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
69 | 84121 | Exterior Stairs - Repair exterior stair | Post: Adding in painting of exterior railings | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
146 | 84450 | Security Camera System | Vistria: address adding security cameras to mailbox area | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
23 | 83520 | ADA parking & curb cuts | Equity PCA: No van-accessible parking space was present at the leasing office. Installation of one van-accessible space | PMC | Project | 1000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GL PMC
122 | 83236 | Carbon Monoxide/Smoke Detectors | Lender PCA: Two smoke-only detectors were observed in Units 16014 and 2004. This appeared to be a rare exception, and th | PMC | Project | 450 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 |  |  |  |  | GL PMC
95 | 84206 | Exterior building | Capitalized year 5 work: exterior painting, repairing stucco, replacing wood trim, replacing siding (Decreased by $38,01 | PMC | Project | 0 | 371 |  |  | 0 | 0 | 339155 | 0 | 0 | 0 | 0 | 0 | 339155 |  |  |  |  | GL PMC
156 | 84385 | Sanitary Sewer Piping |  | DFM |  | 0 | 0 |  |  | 23797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23797
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1431312 | [11 empty] | 2031267
|  |  | CM Fee |  |  | 57682 | [11 empty] | 57682
|  |  | Contingency |  |  | 56597 | [11 empty] | 101130
|  |  | Capital Plan Total (ex-BTL) |  |  | 1545590 | [11 empty] | 2190078
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 14233
BTL (dropped per Adam): $1,652,626

## Almaden 1930
Almaden 1930 — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
105 | 51080-00 | Paint community | PNA: Paint community - LRR | GC | Project | 233270 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233270 |  |  |  |  | GC (pay app)
170 | 51140-00 | Electrical Panel Disconnects & Meter Ban | Lender PCA: At unit electric panels, some panels did not have the breakers labeled. Immediate repairs are recommended fo | PMC | Project | 150000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 |  |  |  |  | GL PMC
56 | 51072-00 | Concrete deck / floor fill | PNA: Rebuild 20% of balconies | GC | Project | 124488 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124488 |  |  |  |  | GC (no pay app)
32 | 51043-00 | Landscaping | PNA: Remove dead tree branches and trim trees. EPCA: Trees were observed impeding on the building rooftops and facades o | GC | Project | 91350 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91350 |  |  |  |  | GC (no pay app)
89 | 51070-00 | Repair / replace wood siding | PNA: Replace rotted siding. EPCA: Partner observed deteriorated siding located below and near dryer vents at the communa | GC | Project | 69250 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69250 |  |  |  |  | GC (pay app)
33 | 51025-00 | Resurface swimming pool | PNA: Repair to pool shell and resurface pool | GC | Project | 68250 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68250 |  |  |  |  | GC (no pay app)
99 | 51070-00 | Repair / replace wood trim | PNA: Replace rotted fascia and trim | GC | Project | 58800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58800 |  |  |  |  | GC (no pay app)
78 | 51061-00 | Asphalt composite shingle roofing | PNA: Roof tune up and Roof replacements (Yr. 8): | GC | Project | 40950 | 29675 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40950 |  |  |  |  | GC (pay app)
84 | 51062-00 | Sealants & caulking | PNA: Seal between T-111 siding | GC | Project | 37800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37800 |  |  |  |  | GC (no pay app)
18 | 51045-00 | Landscape Cleanup and Enhancements | Post: General curb appeal enhancement | GC | Project | 35000 | 96250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
48 | 51992-00 | Termite Remediation | EPCA: Partner engaged Terminix for a termite and fungus/dryrot inspection at the subject property. Based on their findin | GC | Project | 35000 | 17500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (pay app)
19 | 51051-00 | Asphalt Coating | PNA: Repair asphalt, seal coat, and stripe. Lender PCA: The asphalt pavement has localized alligator cracking, and gener | GC | Project | 32970 | 700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32970 |  |  |  |  | GC (pay app)
131 | 51200-00 | Designer Fees | Post: Leasing office refresh | GC | Project | 32500 | 16250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500 |  |  |  |  | GC (pay app)
73 | 51072-00 | Repair balcony framing & decking | PNA: Add joist hangers to balcony joists | GC | Project | 30450 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30450 |  |  |  |  | GC (pay app)
28 | 51045-00 | Landscape irrigation | PNA: Inspect and repair irrigation | GC | Project | 29400 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29400 |  |  |  |  | GC (no pay app)
87 | 51062-00 | Flashing | PNA: Add z flash to replacement siding | GC | Project | 29400 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29400 |  |  |  |  | GC (no pay app)
159 | 51131-00 | Sanitary Sewer Piping | Jet main drain lines per scope | GC | Project | 28896 | 11000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28896 |  |  |  |  | GC (pay app)
22 | 51025-00 | Fences & gates - swimming pool | PNA: Repair and paint pool fence | GC | Project | 22050 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22050 |  |  |  |  | GC (no pay app)
137 | 51011-00 | Pool Furniture | Post: Pool furniture replacement | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
30 | 51077-00 | Fences & gates - site perimeter | PNA: Overlay wood fence on back of community. Lender PCA: Some of the chain link has been bowed slightly where cars have | GC | Project | 19950 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19950 |  |  |  |  | GC (no pay app)
35 | 51025-00 | Replace swimming pool deck | PNA: Pressure wash and seal brick pool deck | GC | Project | 18900 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18900 |  |  |  |  | GC (no pay app)
39 | 51130-00 | Storm sewer piping | PNA: Clean storm drains. EPCA: Debris was observed clogging storm drains. Clearing the debris is recommended | GC | Project | 18900 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18900 |  |  |  |  | GC (no pay app)
173 | 51140-00 | Electrical distribution | PNA: Inspect and repair lighting controllers on all buildings | GC | Project | 18900 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18900 |  |  |  |  | GC (pay app)
31 | 51085-00 | Retaining walls | PNA: Rebuild one section of retaining wall | GC | Project | 16800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16800 |  |  |  |  | GC (no pay app)
57 | 51070-00 | Wall framing | PNA: Replace damaged framing in gable ends | GC | Project | 14700 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14700 |  |  |  |  | GC (pay app)
23 | 51172-00 | Carports / Garages | PNA: Repair car ports and paint posts and pearling | GC | Project | 13650 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13650 |  |  |  |  | GC (pay app)
83 | 51071-00 | Gutters & downspouts | PNA: Secure and clean gutters. Lender PCA: Ac cracked concrete gutter was observed at the driveway entrance to the prope | GC | Project | 10551 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10551 |  |  |  |  | GC (no pay app)
49 | 51134-00 | Water distribution piping | PNA: Install sewer covers | GC | Project | 10500 | 14700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 |  |  |  |  | GC (pay app)
72 | 51077-00 | Repair exterior stair railings | PNA: Secure railings | GC | Project | 10500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 |  |  |  |  | GC (no pay app)
70 | 51072-00 | Balcony inspection | Lender PCA: Based on exterior appurtenances, this Property is subject to the State of California Law. According to a rec | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (no pay app)
34 | 51025-00 | Replace swimming pool coping | PNA: Replace decko seal | GC | Project | 9975 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9975 |  |  |  |  | GC (no pay app)
71 | 51093-00 | Repair exterior stair treads and stringe | PNA: Repair stair treads and stringers | GC | Project | 9975 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9975 |  |  |  |  | GC (no pay app)
76 | 51077-00 | Repair balcony railings | PNA: Secure railings | GC | Project | 9975 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9975 |  |  |  |  | GC (no pay app)
241 | 51070-00 | BTL Contingency Breakdown: |  |  |  | 7444 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7444
21 | 51025-00 | Repair / replace swimming pool pumps | PNA: Anti entrapment devices | GC | Project | 7140 | 63158 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7140 |  |  |  |  | GC (pay app)
171 | 51140-00 | Electrical IR Inspection | EPCA: Based on the age of the property and some of the electrical equipment, an IR survey is recommended. | GC | Project | 6130 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6130 |  |  |  |  | GC (no pay app)
26 | 51091-00 | ADA parking & curb cuts | Lender PCA: One van accessible space should be added at the leasing office. The restroom at the leasing office has acces | GC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GC (no pay app)
154 | 51990-00 | Smoke/fire detection | Lender PCA: Smoke detectors were generally present where required, however several units were observed where the tenant | GC | Project | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GC (pay app)
27 | 51091-00 | Sidewalks | Lender PCA: A cracked walkway was observed. Immediate repairs are recommended to repair the walkway. | GC | Project | 500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GC (no pay app)
242 | 51070-00 | Repair asphalt (Yr 5 and 10) |  |  |  | 300 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
243 | 51071-00 | Gutters and downspouts: |  |  |  | -7144 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7144
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1380470 | [11 empty] | 1380470
|  |  | CM Fee |  |  | 73654 | [11 empty] | 73654
|  |  | Contingency |  |  | 87089 | [11 empty] | 87089
|  |  | Capital Plan Total (ex-BTL) |  |  | 1541214 | [11 empty] | 1541214
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 5944
BTL (dropped per Adam): $45,600

## Ardmore Springs
Ardmore Springs — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
95 | 84101 | Exterior building | PNA: Paint community, iron will require special treatment | GC | Project | 300000 | 90000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 |  |  |  |  | GC (pay app)
105 | 82200 | Appliances Package | Post: Washer/Dryer installs | PMC | Project | 272400 | 80321 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272400 |  |  |  |  | GL PMC
129 | 84116 | Leasing office floor/wall finishes, Repl | Post: Remodel leasing office (Paint - 1st Call & Furniture - PMC) | GC | Project | 119850 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119850 |  |  |  |  | GC (no pay app)
43 | 84103 | Building entrance | Post: Signage replacements for rebranding | PMC | Project | 75000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GL PMC
134 | 84190 | Gym Equipment | Post: Replace gym equipment | PMC | Project | 50000 | 8571 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
122 | 84250 | Radon remediation | Per ESA: Radon remediation in 9 areas, ($3,500-$4,500 per location) EBI recommends completing pilot testing, building ch | GC | Project | 47750 | 14325 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47750 |  |  |  |  | GC (pay app)
16 | 84204 | Asphalt Coating | PNA: Repair potholes. Lender PCA: One area with a failed asphalt patch was noted in front of Building 11. Priority repai | GC | Project | 30000 | 9000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
140 | 84280 | Unit Model Update | Post: Set up model unit | PMC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
152 | 84239 | Fire stops | PNA: Fire stops | PMC | Project | 24696 | 41880 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24696 |  |  |  |  | GL PMC
75 | 84433 | Asphalt composite shingle roofing | PNA: Roof inspection and tune up | GC | Project | 22000 | 6600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
132 | 84190 | Fitness Center Remodel | PNA: Repair sheetrock and paint fitness center and package room | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
70 | 84104 | Repair balcony framing & decking | PNA: Repair vinyl on balcony band board ($10,000) and secure all patio railings ($6,500) | GC | Project | 16500 | 4950 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 |  |  |  |  | GC (pay app)
84 | 84433 | Flashing | PNA: Replace damaged flashing on breezeway roofs | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
80 | 84202 | Gutters & downspouts | PNA: Replace damaged gutter and downspouts, clean, re-pitch remaining | GC | Project | 11000 | 3300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 |  |  |  |  | GC (pay app)
26 | 83517 | Erosion control | PNA: Add rocks at downspout in eroded areas | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
87 | 84206 | Repair / replace cement fiber siding | PNA: Replace damaged siding and paint | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
102 | 84102 | Masonry Repairs | PNA: Pressure wash vinyl on posts and balcony head | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
93 | 84120 | Breezeway soffit repairs | PNA: Repair breezeway soffit | GC | Project | 9500 | 2850 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 |  |  |  |  | GC (pay app)
24 | 84221 | Sidewalks | PNA: Repair trip hazards | GC | Project | 8500 | 2550 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
69 | 84121 | Repair exterior stair railings | PNA: Secure stair rails | GC | Project | 8500 | 2550 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
81 | 84433 | Sealants & caulking | Roof Sealants and Caulking | GC | Project | 8500 | 2550 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
72 | 84206 | Expansion joints | Expansion Joints | GC | Project | 8000 | 2400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC (pay app)
88 | 84113 | Repair / replace wood shingles | PNA: Replace rotted trim and paint to match | GC | Project | 5000 | 1500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
156 | 84432 | Stormwater Pipe Repair | PNA: Clean storm sewer basins | GC | Project | 4000 | 1200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 |  |  |  |  | GC (pay app)
46 | 83160 | Mold and water remediation | Lender PCA: Approximately 12 sf of suspect mold was observed at the fire sprinkler room of Building 8, possibly from tes | PMC | Project | 2500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 |  |  |  |  | GL PMC
27 | 84205 | Fences & gates - site perimeter | Lender PCA: The site fencing near the pet wash station near the operable gate is damaged. Priority repairs are recommend | PMC | Project | 2000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | GL PMC
91 | 83212 | Tuck-pointing | Lender PCA: One stairstep cracked area was observed in the central part of an entrance arch of brick masonry facade at b | GC | Project | 1000 | 300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GC (pay app)
25 | 84302 | Landscape irrigation | Lender PCA: A broken irrigation line was observed at Building 6. Priorty repairs are recommended to repair the broken ir | PMC | Project | 500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GL PMC
171 | 83217 | Replace electric baseboard heater | Lender PCA: One electric baseboard heater located within the sprinkler system closet in building 8 was noted to have dis | PMC | Project | 500 | 1249 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GL PMC
90 | 83106 | Dryer Vents | Lender PCA: Three locations total, at Building 5 and 10, exhibit missing laundry vent covers which allows for moisture a | PMC | Project | 225 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 |  |  |  |  | GL PMC
23 | 84221 | ADA parking & curb cuts | Lender PCA: One ADA parking space at the leasing office has a post for an ADA sign, but the face is blank and missing th | PMC | Project | 150 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 |  |  |  |  | GL PMC
130 | 84116 | Leasing office | Lender PCA: The sinks at the leasing office bathroom do not appear to havescald/abrasion protection at the sink piping a | GC | Project | 150 | 35955 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 |  |  |  |  | GC (pay app)
169 | 84210 | Replace defective outlet | Lender PCA: One GFCI outlet at unit 4206 in the kitchen does not reset, and priorty repairs are recommended to replace t | PMC | Project | 30 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 |  |  |  |  | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1120251 | [11 empty] | 1120251
|  |  | CM Fee |  |  | 58813 | [11 empty] | 58813
|  |  | Contingency |  |  | 56013 | [11 empty] | 56013
|  |  | Capital Plan Total (ex-BTL) |  |  | 1235077 | [11 empty] | 1235077
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Bentley Parke
Bentley Parke — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
43 |  | Exterior building | PNA - Paint community 100% paintable 3.2.4. Painting, Exterior. The paint finish on the apartment buildings was observe | GC | Project | 382800 | 114840 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382800 |  |  |  |  | GC (pay app)
97 |  | Interior Upgrades | Raising Y1 of Unit Interior Upgrades upfront | PMC | Project | 260680 | 38010 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260680 |  |  |  |  | GL PMC
55 |  | Modified bitumen membrane roof repairs | PNA - Repairs to flat roofing and repairs with modified bit 3.2.8. - Built-up roof / Modified Bitumen | GC | Project | 75000 | 22800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
94 |  | Replace breezeway lights | PNA - R&R ceiling lights in breezeways with LED | GC | Project | 38600 | 11580 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38600 |  |  |  |  | GC (pay app)
110 |  | Drier vents | PNA - Remove vent covers, clean vent piping, and install new dryer vent covers | GC | Project | 38280 | 11484 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38280 |  |  |  |  | GC (pay app)
129 |  | Security/ fire alarm systems | Concept Walk - Add security cameras | PMC | Project | 35000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GL PMC
67 |  | Repair stucco | PNA - Repairs to stucco | GC | Project | 26000 | 7800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
122 |  | Clubhouse / Office remodel | Concept Walk - Convert staff room to a business center/cybercafe | PMC | Project | 25000 | 3750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
150 |  | BBQ Grill Area | Concept Walk - Add BBQ/Grill Area outside swimming pool fence | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
111 |  | Fire Stops | PNA - Fire stops | PMC | Project | 22736 | 1916 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22736 |  |  |  |  | GL PMC
30 |  | Carports / Garages | PNA - Repair carports | GC | Project | 22000 | 6600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
56 |  | Gutters & downspouts | PNA - Clean and repatch gutters throughout property | GC | Project | 21000 | 6300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC (pay app)
58 |  | Sealants & caulking | PNA - Seal windows as part of paint | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
44 |  | Repair exterior stair treads and stringe | PNA - Replace 40 broken stair treads | GC | Project | 18900 | 5670 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18900 |  |  |  |  | GC (pay app)
31 |  | Dumpster enclosures | PNA - Repair dumpster enclosures | GC | Project | 16000 | 4800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
48 |  | Expansion joints | PNA - Seal expansion joints | GC | Project | 16000 | 4800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
93 |  | Electrical distribution | PNA - Replace lighting controlers | GC | Project | 16000 | 4800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
32 |  | WDIR | WDIR Treatment per Inspection | PMC | Project | 15900 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15900 |  |  |  |  | GL PMC
57 |  | Flashing | PNA - Repair parapet wall flashing | GC | Project | 15600 | 4680 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 |  |  |  |  | GC (pay app)
39 |  | Concrete deck / floor fill | PNA - Repair landings | GC | Project | 15000 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
22 |  | Sidewalks and curbs | PNA - Grind trip hazards | GC | Project | 13000 | 3900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 |  |  |  |  | GC (pay app)
140 |  | Swimming pool deck | PNA - Presure wash pool deck | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
51 |  | Asphalt composite shingle roofing | PNA - Roof tune up 3.2.8 - Asphalt Shingle (3-tab). The inboard parapet asphalt shingle installation date was not provid | GC | Project | 10260 | 3078 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10260 |  |  |  |  | GC (pay app)
113 |  | Unit Deferred Maintenance | Down Unit Refurbishment (Unit 1405) - Damaged bedroom ceiling ($8,000) Roof Leak Repair (Unit 1405) - Repair Roof above | GC | Project | 9000 | 2400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 |  |  |  |  | GC (pay app)
115 |  | CA SB-721 Elevated Exterior Elements Ins | 3.2.7 - According to a recent State of California Law (SB 721), subject properties that contain “exterior elevated eleme | GC | Project | 6500 | 1950 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | GC (pay app)
143 |  | Swimming pool fencing / gates | PNA - Repair pool fence | GC | Project | 5600 | 1680 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 |  |  |  |  | GC (pay app)
17 |  | Storm sewer piping and drains | PNA - Clear drains on pool deck | GC | Project | 5000 | 1500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
141 |  | Swimming Pool Shower | Concept Walk - Re-tile shower | GC | Project | 5000 | 1500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
83 |  | Domestic Hot Water Heater, Replace | 3.3.5 - Water Heater Sesimic Strapping. The water heaters lacked one or both seismic bracing straps at observed units 10 | PMC | Project | 3000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GL PMC
112 |  | ADA - Leasing Office Restrooms | 5.4 - The plumbing under the lavatories within the publicly-accessible toilet rooms did not appear to be configured to p | PMC | Project | 300 | 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 |  |  |  |  | GL PMC
19 |  | Asphalt seal coating |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 115920 | 0 | 115920
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1175156 | [11 empty] | 1291076
|  |  | CM Fee |  |  | 61696 | [11 empty] | 61696
|  |  | Contingency |  |  | 58758 | [11 empty] | 58758
|  |  | Capital Plan Total (ex-BTL) |  |  | 1295609 | [11 empty] | 1411529
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Cherry Creek
Cherry Creek — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
71 | 51080-00 | Exterior paint | Lender PCA: Peeling paint was observed on the exterior stairway wall of building 7. Reapplication of exterior paint is r | GC | Project | 230000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 |  |  |  |  | GC (no pay app)
19 | 51053-00 | Asphalt seal coating | Lender PCA: Damaged pavement consisting of linear cracking was present at the drive aisles typical of the conditions not | GC | Project | 81000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 |  |  |  |  | GC (no pay app)
99 | 51140-00 | Electrical distribution - exterior | PNA: Place Holder for electric meter and load center replacement | GC | Project | 80000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 |  |  |  |  | GC (no pay app)
151 | 51023-00 | Swimming pool resurface | PNA: resurface pool | GC | Project | 52000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 |  |  |  |  | GC (no pay app)
66 | 51075-00 | Repair / replace wood shingles | PNA: Replace rotted fascia and trim | GC | Project | 46000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 |  |  |  |  | GC (no pay app)
86 | 50050-00 | Unit water heaters | PNA: replace two hot water heaters | GC | Project | 42000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 |  |  |  |  | GC (no pay app)
69 | 51075-00 | Stucco repairs | PNA: Stucco repairs | GC | Project | 40000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (no pay app)
32 | 51172-00 | Carports / Garages | PNA: Carport repairs and paint post and pearling | GC | Project | 36000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (no pay app)
60 | 51062-00 | Sealants & caulking | PNA: seal and prep stucco | GC | Project | 36000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (no pay app)
67 | 51159-00 | Wall framing | PNA: damaged framing on stair supports | GC | Project | 35000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (no pay app)
157 | 51011-00 | Pool furniture | Pool Furniture Straps, BBQ Grill Upgrade - Concept Walk | PMC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
20 | 51053-00 | Stripe parking areas | Stripe Parking Lots | GC | Project | 28000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (no pay app)
47 | 51072-00 | Repair Catwalks | PNA: secure catwalk railings | GC | Project | 28000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (no pay app)
45 | 51077-00 | Repair exterior stair railings | PNA: secure and paint railings | GC | Project | 26000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (no pay app)
41 | 51992-00 | Termite Remediation | Lender PCA: Termite remediation - Evidence of drywood termites for areas 2A, 2C, 2E, 2F, 2H, and 2I on the termite map. | PMC | Project | 23250 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23250 |  |  |  |  | GL PMC
156 | 51076-00 | Swimming pool fencing / gates | PNA: Repair fence and Paint | GC | Project | 22000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (no pay app)
17 | 51130-00 | Storm sewer piping and drains | PNA: clean storm drains | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (no pay app)
46 | 51077-00 | Repair patio/balcony railings/fences | Lender PCA: Deteriorated and damaged wood framing and trim were noted at balconies and upper landings including at build | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (no pay app)
58 | 51071-00 | Gutters & downspouts | Lender PCA: Leaf accumulation was noted in gutters across the site. Removal of the leaf debris is recommended. PNA: sec | GC | Project | 19000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 |  |  |  |  | GC (no pay app)
23 | 51091-00 | Sidewalks and curbs | PNA: Trip Hazards | GC | Project | 14000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (no pay app)
153 | 51022-00 | Swimming pool deck | PNA: deck o seal on pool | GC | Project | 14000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (no pay app)
30 | 51045-00 | Landscape Cleanup & Enhancements | Lender PCA: Trees were observed impeding on the building rooftop and facade between units 54 and 64. No portion of any t | PMC | Project | 12000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GL PMC
104 | 51141-00 | Pole lighting | Retrofit porch lights to LED - Concept Walk | GC | Project | 12000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (no pay app)
105 | 51141-00 | Breezeway and patio lights | Concept Walk: there are 13 breezeways (budgeting $750/unit) | GC | Project | 9750 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9750 |  |  |  |  | GC (no pay app)
154 | 51026-00 | Swimming pool pumps repair / replace | PNA: anti entrapment devices | GC | Project | 6800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 |  |  |  |  | GC (no pay app)
48 | 51090-00 | Expansion Joints | PNA: Stucco expansion joints | GC | Project | 6000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (no pay app)
42 | 51070-00 | Termite damage repairs | Lender PCA: Termite Damage - Repair and replace damaged materials noted on the termite report. Lender PCA: Termite Damag | PMC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GL PMC
65 | 84433 | Repair Roof Gambles | Lender PCA: Deteriorated and damaged roof gables were observed at buildings 6 and 7. Repair of the noted issues is recom | GC | Project | 3000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GC (no pay app)
138 | 51177-00 | Fire monitoring system | Fire Stops: Expire 2031 but some maybe old - approx. 50% - Concept Walk | PMC | Project | 3000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GL PMC
142 | 51993-00 | Security alarm systems | Lender PCA: An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recert | PMC | Project | 1500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
145 | 51164-00 | Elevators | Lender PCA: Current operation permits were not posted in each elevator cab. Property management should schedule reinspec | PMC | Project | 1500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
22 | 51091-00 | Sidewalks and curbs | Lender PCA: A potential trip hazard consisting of vertical and horizontal separation was observed to the northeast of bu | PMC | Project | 500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GL PMC
33 | 51163-00 | Dumpster enclosures | Lender PCA: The threshold height at the accessible leasing office entrance does not appear to be ADA-compliant. Installa | PMC | Project | 125 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 |  |  |  |  | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 983425 | [11 empty] | 983425
|  |  | CM Fee |  |  | 51630 | [11 empty] | 51630
|  |  | Contingency |  |  | 49171 | [11 empty] | 49171
|  |  | Capital Plan Total (ex-BTL) |  |  | 1084226 | [11 empty] | 1084226
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 10271
BTL (dropped per Adam): $0

## Clipper Cove
Clipper Cove — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
108 |  | Interior Upgrades | Concept Walk - Renovate classic units | PMC | Project | 1000000 | 133969 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 |  |  |  |  | GL PMC
18 |  | Parking lot repairs | PNA - Seal coat entire parking lot - add crack fill as needed | GC | Project | 430000 | 129000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430000 |  |  |  |  | GC (pay app)
70 |  | Exterior paint | PNA - Paint stucco, trim and wood rails | GC | Project | 428000 | 128400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428000 |  |  |  |  | GC (pay app)
43 |  | Repair exterior stair treads and stringe | PNA - Replace twenty failing exterior stair cases LPCA - Exterior stairs, balconies, and breezeways (near units 104 and | GC | Project | 360000 | 108000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 |  |  |  |  | GC (pay app)
128 |  | Patio Fence Enclosure | Concept Walk - Screened in porches for all unit stacks | GC | Project | 270000 | 81000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270000 |  |  |  |  | GC (pay app)
168 |  | Pool Area Upgrades | Concept Walk - Turf installation, landscape cleanup, lighting replacement, palm tree cleanup, etc. | GC | Project | 250000 | 75000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 |  |  |  |  | GC (pay app)
66 |  | Wall framing | PNA - Repair structural framing in areas that indicate failures | GC | Project | 210000 | 63000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 |  |  |  |  | GC (pay app)
159 |  | Tennis / sports court | Concept Walk - Tennis court repurpose ($100k) + repurpose racquetball court to maintenance/storage ($50k) LPCA - Tennis | GC | Project | 134854 | 40456 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134854 |  |  |  |  | GC (pay app)
134 |  | Clubhouse / Office redecorate (FFE) | Concept Walk - Leasing office / clubhouse redec and furniture | PMC | Project | 105000 | 14962 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 |  |  |  |  | GL PMC
133 |  | Clubhouse / Office remodel | Concept Walk - Clubhouse repaint, kitchen remodel, & flooring | GC | Project | 95000 | 28500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 |  |  |  |  | GC (pay app)
64 |  | Repair / replace siding | PNA - Pressure wash to remove mildew. Repair/replace damaged or broken vinyl siding matching the existing color | GC | Project | 92000 | 27600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 |  |  |  |  | GC (pay app)
44 |  | Repair exterior stair railings | PNA - Repair failing stair and catwalk railings | GC | Project | 86000 | 25800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86000 |  |  |  |  | GC (pay app)
27 |  | Erosion control and drainage | PNA - Erosion control around all buildings | GC | Project | 82500 | 24750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 |  |  |  |  | GC (pay app)
68 |  | Stucco repairs | PNA - Failing and damaged stucco was observed throughout the property | GC | Project | 82000 | 24600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000 |  |  |  |  | GC (pay app)
156 |  | Pool furniture | Concept Walk - 1st pool furniture + 2nd pool furniture | PMC | Project | 75000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GL PMC
19 |  | Asphalt seal coating | PNA - Repair broken or failing asphalt LPCA - Asphalt pavement | GC | Project | 68000 | 20400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68000 |  |  |  |  | GC (pay app)
57 |  | Gutters & downspouts | PNA - Repair, clean, reattach replace gutters throughout the property | GC | Project | 62500 | 18750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62500 |  |  |  |  | GC (pay app)
71 |  | Repair / replace wood trim | PNA - Rotted window trim and facia was observed, repairs would include paint to match | GC | Project | 52000 | 15600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 |  |  |  |  | GC (pay app)
29 |  | Landscape Cleanup & Enhancements | Concept Walk - Office landscape enhancements | GC | Project | 50000 | 8572 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
153 |  | Swimming pool pumps repair / replace | PNA - Repair the hot tub that is currently not working Concept Walk - Fill in hot tub and make seating area | GC | Project | 50000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
42 |  | Repair balcony framing & decking | PNA - Repair failing lightweight concrete on catwalk | GC | Project | 49000 | 14700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49000 |  |  |  |  | GC (pay app)
30 |  | Tree Trimming | PNA - Tree trim, get overgrowth off buildings | GC | Project | 48000 | 14400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 |  |  |  |  | GC (pay app)
105 |  | Lighing controller system | PNA - Common area light fixtures (building light LED retrofit) | GC | Project | 46000 | 13800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 |  |  |  |  | GC (pay app)
145 |  | Golf Cart | Concept Walk - 3 golf carts | PMC | Project | 45000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GL PMC
22 |  | Sidewalks and curbs | PNA - Replace failing areas of sidewalk LPCA - Trip hazards at concrete walkway | GC | Project | 42000 | 12600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 |  |  |  |  | GC (pay app)
32 |  | Dumpster enclosures | PNA - Repair dumpster enclosures | GC | Project | 42000 | 12600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 |  |  |  |  | GC (pay app)
28 |  | Landscape irrigation | Concept Walk - Irrigation LPCA - Irrigation | GC | Project | 40000 | 300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
103 |  | Pole lighting | PNA - Replace with LED fixture | GC | Project | 39000 | 11700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 |  |  |  |  | GC (pay app)
150 |  | Swimming pool resurface | PNA - Resurface the pool and hot tub at the leasing office | GC | Project | 38000 | 11400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 |  |  |  |  | GC (pay app)
126 |  | Stovetop fire suppression | PNA - Fire protection | PMC | Project | 37632 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37632 |  |  |  |  | GL PMC
23 |  | Detention pond fountain | Concept Walk - Installation of 6 lake fountains | GC | Project | 35000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GC (no pay app)
135 |  | Model Unit | Concept Walk - Update model to include appliances, cabinetry, flooring, & fixtures | PMC | Project | 35000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  |  |  | GL PMC
125 |  | Drier vents | PNA - Drier vents | PMC | Project | 28800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28800 |  |  |  |  | GL PMC
161 |  | Playground area and equipment | PNA - install fall zone borders and add fall zone material | GC | Project | 28000 | 8400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (pay app)
47 |  | Expansion Joints | PNA - Expansion joints | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
17 |  | Storm sewer piping and drains | PNA - Clean storm drains throughout property | GC | Project | 24000 | 7200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
20 |  | Stripe parking areas | PNA - Stripe parking areas | GC | Project | 24000 | 7200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
59 |  | Sealants & caulking | PNA - Sealants & caulking | GC | Project | 24000 | 7200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
94 |  | HVAC pipe insulation | PNA - Install linset insulation | GC | Project | 24000 | 7200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
41 |  | Termite damage repairs | LPCA - WDO Repairs | GC | Project | 19500 | 5850 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 |  |  |  |  | GC (pay app)
21 |  | ADA parking & ramps | PNA - Repairs to failing ADA ramps LPCA - ADA van-accessible parking | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
152 |  | Swimming pool deck | PNA - Powerwash decking on both pools | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
53 |  | Modified bitumen membrane repairs / repl | PNA - Replace the modified bit roofing on racquetball structures | GC | Project | 16500 | 4950 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 |  |  |  |  | GC (pay app)
98 |  | Electrical distribution - exterior | PNA - Electrical distribution LPCA - Electrical (open electrical boxes were observed near irrigation piping) | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
151 |  | Swimming pool coping and tile | PNA - Replace swimming pool coping | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
127 |  | Interior microbial growth treatment | LPCA - Localized water staining was observed at the ceiling of Unit 103.The unit appears to currently be used for miscel | PMC | Project | 1000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 4754286 | [11 empty] | 4754286
|  |  | CM Fee |  |  | 249600 | [11 empty] | 249600
|  |  | Contingency |  |  | 237714 | [11 empty] | 237714
|  |  | Capital Plan Total (ex-BTL) |  |  | 5241600 | [11 empty] | 5241600
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 218021
BTL (dropped per Adam): $0

## Cypress Ridge
Cypress Ridge — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
70 |  | Exterior paint | PNA - Paint community | GC | Project | 227400 | 68220 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227400 |  |  |  |  | GC (pay app)
29 |  | Landscape Cleanup & Enhancements | Concept Walk - landscape cleanup and ground cover | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
50 |  | Asphalt composite shingle roofing | PNA - Tune up roofs (building replacements as needed) TCAC - Asphalt shingle | GC | Project | 50000 | 15000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
161 |  | Playground area and equipment | Concept Walk - playground and fall zone | GC | Project | 45000 | 13500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (pay app)
68 |  | Stucco repairs | PNA - Patch cracked stucco LPCA - Horizontal cracking was noted at multiple facades including Units 2129, 2159, 2209, an | GC | Project | 40000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
20 |  | Stripe parking areas | PNA - Stripe parking lot | GC | Project | 28000 | 8400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (pay app)
19 |  | Asphalt Milling/Paving/SealCoat | PNA - Crack fill TCAC - Asphalt seal coat and striping | GC | Project | 27000 | 8100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 |  |  |  |  | GC (pay app)
57 |  | Gutters & downspouts | PNA - Repair downspouts and gutters | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
71 |  | Repair / replace wood trim | PNA - Repair / replace wood trim | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
18 |  | Parking Lots | PNA - repair potholes | GC | Project | 22000 | 6600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
47 |  | Expansion Joints | PNA - Expansion joints | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
59 |  | Sealants & caulking | PNA - Seal roof cracks LPCA (PR-90) - Evidence of discoloration was noted in the upper bedroom or bathroom ceilings at U | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
61 |  | Roof treatment / cleaning | LPCA - Organic growth including moss was noted on main and secondary asphalt-shingle roofs. Over time the organic materi | GC | Project | 18900 | 5670 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18900 |  |  |  |  | GC (pay app)
32 |  | Dumpster enclosures | PNA - Repair enclosures | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
98 |  | Electrical distribution - exterior | PNA - Repair lighting controllers | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
108 |  | Partial Renovation | Seller to address: LPCA - Units 65 and 103 are considered down units due to evictions that are currently in progress. Ma | PMC | Project | 17000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 |  |  |  |  | GL PMC
22 |  | Sidewalks and curbs | PNA - Grind trip hazards | GC | Project | 16000 | 4800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
130 |  | Signage - entry | Concept Walk - replace main ID and add directional signage | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
143 |  | Video systems | Concept Walk - replace inoperable cameras and add in dead zones | PMC | Project | 15000 | 47799 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
21 |  | ADA parking & ramps | PNA - Repair concrete on ramp | GC | Project | 14000 | 4200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
58 |  | Flashing | PNA - Flashing | GC | Project | 12000 | 3600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (pay app)
126 |  | Stovetop fire suppression | PNA - Fire stops | PMC | Project | 11956 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11956 |  |  |  |  | GL PMC
125 |  | Drier vents | PNA - Drier vents | PMC | Project | 11590 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11590 |  |  |  |  | GL PMC
160 |  | Outdoor kitchen, fire pits, and seating | Concept Walk - outdoor grills and seating area | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
41 |  | Termite damage repairs | LPCA - The WDO report also stated fungus/dryrot was observed. Partner recomments repairs. | GC | Project | 5000 | 1500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
43 |  | Repair exterior stair treads and stringe | LPCA - Subsequent to site inspection activities, Partner was notified that installation of EV charging station caused cr | GC | Project | 5000 | 1500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (pay app)
127 |  | Interior microbial growth treatment | Seller to address: LPCA (PR-90) - Water damage was observed at ceiling areas in the bathroom and bedroom of Unit 2 and t | PMC | Project | 3000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | GL PMC
40 |  | Termite Remediation | LPCA - Partner was provided with a WDO report by Redwood Empire Termite and Pest Control, dated January 25, 2026. The re | PMC | Project | 920 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 |  |  |  |  | GL PMC
25 |  | Site perimeter fencing | LPCA - Minor fence board damage was noted at a single location near Unit 2154. Repair of the noted issue is recommended. | PMC | Project | 750 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 |  |  |  |  | GL PMC
136 |  | Fire system - Code Violations | LPCA (PR-90) - There are open There are open fire code violations for expired fire extinguishers at 1815 Meda Ave. At th | PMC | Project | 500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 772016 | [11 empty] | 772016
|  |  | CM Fee |  |  | 40531 | [11 empty] | 40531
|  |  | Contingency |  |  | 38601 | [11 empty] | 38601
|  |  | Capital Plan Total (ex-BTL) |  |  | 851148 | [11 empty] | 851148
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Oslo
Oslo — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
108 |  | Capital Plan |  | Unmarked | Project | 95000 | 119427 | [15 empty] | GL (unmarked scope) · Yr-1 only (not in 10-yr plan)
37 |  | Common Area/Playground/Courts |  | AMN |  | 40000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
23 |  | Staircase |  | DFM |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
25 |  | Exterior Lighting |  | DFM |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
28 |  | Sidewalks |  | DFM |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
36 |  | Fitness Center & Equipment |  | AMN |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
41 |  | Asphalt Milling/Paving/Sealcoat |  | DFM |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
42 |  | Fences/Gates |  | DFM |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
65 |  | Landscaping/Irrigation |  | DFM |  | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000
99 | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | Dryer Vent Cleaning | Dryer Vent Cleaning - Contingency | PMC | Project | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000 |  |  |  |  | GL PMC
100 | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | Gutter Cleaning | Gutter Cleaning - Contingency | PMC | Project | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000 |  |  |  |  | GL PMC
101 | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | Plumbing | Plumbing Repairs - Contingency | PMC | Project | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000 |  |  |  |  | GL PMC
106 | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | Windows/Doors | Window/Door Repairs - Contingency | PMC | Project | 5000 | 0 |  |  | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 50000 |  |  |  |  | GL PMC
17 |  | Exterior Painting |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84000
38 |  | Parking Lots |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 23153 | 0 | 0 | 0 | 0 | 0 | 46306
75 |  | Pool Area Repairs & Equipment |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10150
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 190000 | [11 empty] | 730456
|  |  | CM Fee |  |  | 4988 | [11 empty] | 4988
|  |  | Contingency |  |  | 4750 | [11 empty] | 4750
|  |  | Capital Plan Total (ex-BTL) |  |  | 199738 | [11 empty] | 740194
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 38152
BTL (dropped per Adam): $923,670

## San Regis
San Regis — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
110 |  | ADA Accessibility | ADA Upgrades (responsible for 25 of 43 total required) | PMC | Project | 2321300 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2321300 |  |  |  |  | GL PMC
70 |  | Exterior paint | PNA - exterior building | GC | Project | 646000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646000 |  |  |  |  | GC (no pay app)
108 |  | Interior Upgrades | 2746679.999999999 | PMC | Project | 425380 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425380 |  |  |  |  | GL PMC
69 |  | Interior Hallway flooring / painting | PNA - paint hallways/breezeways | GC | Project | 156000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156000 |  |  |  |  | GC (no pay app)
128 |  | ADA Relocation Costs | ADA Relocation Costs | PMC | Project | 125000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 |  |  |  |  | GL PMC
133 |  | Clubhouse / Office remodel | Concept Walk - fix water leaks and prevent any continued deterioration in leasing office (2nd and 3rd floor) | GC | Project | 100000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  |  |  |  | GC (no pay app)
53 |  | Modified bitumen membrane repairs / repl | PNA - was not able to get on roofs but based on age suspect damage on all roofs and replace roof on office building | GC | Project | 95000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 |  |  |  |  | GC (no pay app)
104 |  | Breezeway and patio lights | PNA - replace breezeway and catwalk lighting to LED | GC | Project | 59800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59800 |  |  |  |  | GC (no pay app)
150 |  | Swimming pool resurface | PNA - resurface pool and hot tub | GC | Project | 58000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58000 |  |  |  |  | GC (no pay app)
159 |  | Tennis / sports court | Concept Walk - sports court furniture | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
42 |  | Repair balcony framing & decking | PNA - repair and recoat exposed walkways | GC | Project | 39500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39500 |  |  |  |  | GC (no pay app)
126 |  | Stovetop fire suppression | PNA - fire stops | PMC | Project | 38220 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38220 |  |  |  |  | GL PMC
152 |  | Swimming pool deck | PNA - repair cracks and seal | GC | Project | 38000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 |  |  |  |  | GC (no pay app)
40 |  | Termite Remediation | WDIR - findings from WDIR (placeholder) | GC | Project | 31500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31500 |  |  |  |  | GC (no pay app)
17 |  | Storm sewer piping and drains | PNA - clear parking lot drains | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (no pay app)
29 |  | Landscape Cleanup & Enhancements | Concept Walk - tree trim + landscape cleanup | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (no pay app)
68 |  | Stucco repairs | PNA - patch stucco and paint to match | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (no pay app)
156 |  | Pool furniture | Concept Walk - pool furniture | PMC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GL PMC
18 |  | Parking lot repairs | PNA - repair potholes | GC | Project | 28000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (no pay app)
20 |  | Stripe parking areas | PNA - stripe parking lot | GC | Project | 27000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 |  |  |  |  | GC (no pay app)
57 |  | Gutters & downspouts | PNA - replace crushed down spouts | GC | Project | 21000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC (no pay app)
59 |  | Sealants & caulking | PNA - sealants & caulking | GC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (no pay app)
58 |  | Flashing | PNA - flashing | GC | Project | 19800 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19800 |  |  |  |  | GC (no pay app)
98 |  | Electrical distribution - exterior | PNA - provide and install can light adapters to catwalk lighting and inspect and replace lighting controllers | GC | Project | 19500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 |  |  |  |  | GC (no pay app)
19 |  | Asphalt seal coating | PNA - crack fill | GC | Project | 19000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 |  |  |  |  | GC (no pay app)
32 |  | Dumpster enclosures | PNA - Prevent damage to hallway to parking lot | GC | Project | 18000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (no pay app)
21 |  | ADA parking & ramps | PNA - repair concrete on ramp | GC | Project | 14000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (no pay app)
22 |  | Sidewalks and curbs | PNA - grind trip hazards | GC | Project | 14000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (no pay app)
155 |  | Swimming pool fencing / gates | PNA - fences & gates - swimming pool | GC | Project | 14000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (no pay app)
83 |  | Domestic water piping | PNA - insulate hot water lines on office roofs | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (no pay app)
87 |  | Common area water heaters / boilers | PNA - insulate boiler lines on office roof | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (no pay app)
47 |  | Expansion Joints | PNA - seal joint | GC | Project | 8500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (no pay app)
136 |  | Fire suppression system | LPCA - The annual inspection and 5-year inspection tags were not current. Partner recommends obtaining current inspectio | PMC | Project | 1500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
144 |  | Elevators | LPCA - Current operation permits were not posted in each elevator cab. Partner recommends obtaining current inspection t | PMC | Project | 1500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 4549500 | [11 empty] | 4549500
|  |  | CM Fee |  |  | 238849 | [11 empty] | 238849
|  |  | Contingency |  |  | 227475 | [11 empty] | 227475
|  |  | Capital Plan Total (ex-BTL) |  |  | 5015824 | [11 empty] | 5015824
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 6516
BTL (dropped per Adam): $0

## Tribute Verdae
Tribute Verdae — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
50 | 84250 | Radon Long-Term Testing and Remediation | Post-Closing Radon Long-Term Testing and Remediation for 21 units | PMC | Project | 150000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 |  |  |  |  | GL PMC
21 | 84221 | Accessibility Exterior accessible route | Please refer to the accessibility report | GC | Project | 132850 | 39855 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132850 |  |  |  |  | GC (pay app)
31 | 84435 | Erosion control | Additional soil and regional turf to barren areas Barren turf was observed at isolated areas throughout, typical to sid | PMC | Project | 100000 | 9153 |  |  | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 280000 |  |  |  |  | GL PMC
33 | 84434 | Retaining walls | Add additional retaining wall between building 8 and 9 | GC | Project | 75000 | 22500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GC (pay app)
145 | 84130 | Dog Park | Purchasing new astroturf, benches, and shade | GC | Project | 75000 | 22500 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
43 | 84195 | Playground equipment | New Playground (Find Placement) | GC | Project | 65000 | 19500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 |  |  |  |  | GC (pay app)
51 | 84905 | Sustainability Improvements | Reserve for post-closing sustainability due diligence review and imrovements | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
60 | 84104 | Repair balcony framing & decking | Inspect & repair wood decking on breezeways. Some of the wood-framed upper floor balconies & breezeway landings were obs | GC | Project | 50000 | 15000 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
14 | 84204 | Asphalt Coating | Asphalt seal coat & striping | GC | Project | 46000 | 13800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | 0 | 92000 |  |  |  |  | GC (pay app)
89 | 84202 | Gutters & downspouts | Inspect and repair downspouts, splash blocks | GC | Project | 45000 | 13500 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
22 | 84201 | Accessibility Parking and route from par | Please refer to the accessibility report | GC | Project | 32000 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
161 | 84385 | Sanitary Sewer Piping | At sewer scope cleanouts numbers 9 and 2 joint separations were observed. It is recommended to replace or repair the joi | PMC | Project | 29500 | 4481 | [15 empty] | GL PMC · Yr-1 only (not in 10-yr plan)
59 | 84430 | Concrete deck / floor fill | Inspect route and seal concrete cracks The concrete patio in the northwest corner contained exposed and improperly term | GC | Project | 28000 | 8400 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
72 | 84206 | Pressure Wash | Pressure wash 1st floor of brick to remove clay spoils | GC | Project | 28000 | 8400 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
79 | 84104 | Repair balcony support posts | The bases at some balcony support posts are overhanging the concrete patio slab edge and not fully bearing on the concre | GC | Project | 25000 | 7500 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
29 | 84300 | Landscape irrigation | Inspect and repair irrigation prior to installing turf | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
27 | 84304 | Accessibility Dwelling units |  | DFM |  | 19200 | 0 |  |  | 19200 | 0 | 19200 | 0 | 19200 | 0 | 19200 | 0 | 192000
30 | 84435 | Erosion control | The grade around a few of the apartment buildings exhibited substantial runoff erosion and/or water ponding adjacent to | GC | Project | 15000 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (pay app)
19 | 84201 | Stripe parking areas | Restripe parking | GC | Project | 14000 | 4200 |  |  | 0 | 0 | 14000 | 0 | 0 | 0 | 14000 | 0 | 70000 |  |  |  |  | GC (pay app)
36 | 84361 | Swimming pool deck | Pressure wash deck | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
42 | 84385 | Storm sewer piping and drains | Add storm drains between bulding 8 and 9 | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
25 | 84116 | Accessibility Public toilets /common are | Please refer to the accessibility report | GC | Project | 6700 | 2010 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6700 |  |  |  |  | GC (pay app)
165 | 84217 | Refrigerant linesets insulation | Partner observed that the insulation on the exterior portion of the refrigerant linesets between the condensing units an | GC | Project | 6500 | 1950 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
23 | 84221 | Accessibility Exterior door approaches | Please refer to the accessibility report | GC | Project | 5250 | 1575 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250 |  |  |  |  | GC (pay app)
37 | 84361 | Swimming pool fencing / gates | Repair gate closers | GC | Project | 4000 | 1200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 |  |  |  |  | GC (pay app)
26 | 84116 | Accessibility Access to other items | Please refer to the accessibility report | GC | Project | 3650 | 1095 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3650 |  |  |  |  | GC (pay app)
54 | 84435 | Jack & underpin foundations | Inspect all building cut post tension cables and seal | GC | Project | 3000 | 900 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
78 | 84102 | Repair brick pier damage | The brick pier adjacent to garage 2202 was observed with damage, likely resulting from mechanical impact. The observed d | GC | Project | 2500 | 750 | [15 empty] | GC (pay app) · Yr-1 only (not in 10-yr plan)
24 | 84221 | Accessibility Interior access & access t | Please refer to the accessibility report | GC | Project | 750 | 225 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 |  |  |  |  | GC (pay app)
34 | Site Utilities & Improvements | Resurface swimming pool |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
38 | Site Utilities & Improvements | Pool Filtration/Circulation Equipment |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1051900 | [11 empty] | 1234700
|  |  | CM Fee |  |  | 51635
|  |  | Capital Plan Total (ex-BTL) |  |  | 1103535 | [11 empty] | 1234700
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Walnut Square
Walnut Square — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
95 | 84101 | Exterior building Painting | Paint community | GC | Project | 232000 | 69600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232000 |  |  |  |  | GC (pay app)
27 | 84205 | Fences & gates - site perimeter | Rebuild 2500 lf of wood fence, repair 2000 lf of iron fence and paint both | GC | Project | 192000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192000 |  |  |  |  | GC (no pay app)
15 | 84303 | Landscape Cleanup and Enhancements | Tree trim and landscape cleanup | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
129 | 84208 | Leasing office floor/wall finishes, Repl | Reflooring / repaint in office | GC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (no pay app)
130 | 84306 | Leasing office FF&E, Replace | Leasing office FF&E, Replace | GC | Project | 50000 | 4702 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GC (pay app)
38 | 84195 | Playground area | Turf around playground areas | GC | Project | 45000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 |  |  |  |  | GC (no pay app)
23 | 84221 | ADA parking & curb cuts | Remove and replace damaged curbs on community | GC | Project | 30000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (no pay app)
22 | 84204 | Pavement | Remove and replace pothole areas on site | GC | Project | 28000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (no pay app)
80 | 84202 | Gutters & downspouts | Clean and repitch gutters and repair down spouts throughout property | GC | Project | 28000 | 8400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (pay app)
168 | 84112 | Replace breezeway lights | Replace front door lights with mini LED wallpacks | GC | Project | 24000 | 2400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
87 | 84105 | Repair / replace cement fiber siding | Repair or replace damaged siding siding | GC | Project | 19000 | 5700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 |  |  |  |  | GC (pay app)
72 | 84206 | Expansion joints | Exterior Expansion Joints | GC | Project | 17000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 |  |  |  |  | GC (no pay app)
96 | 84105 | Repair / replace wood trim | Repair / replace wood trim | GC | Project | 16000 | 4800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (pay app)
109 | 84106 | Drier vents | Drier vents | GC | Project | 15675 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15675 |  |  |  |  | GC (no pay app)
42 | 84111 | Dumpster enclosures | Repair and paint | GC | Project | 14000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (no pay app)
18 | 84470 | Water Distribution Piping | Two different water leaks from meter boxes Allowance to repair city water main leaks at the property based on observed c | GC | Project | 12000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 |  |  |  |  | GC (no pay app)
24 | 84221 | Sidewalks | Grind trip hazards | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (no pay app)
68 | 84114 | Repair exterior stair treads and stringe | Resurface stairs to office | GC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (no pay app)
70 | 84121 | Repair patio/balcony railings | Secure balcony railings | GC | Project | 8500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (no pay app)
81 | 84433 | Flashing | Roof Flashing | GC | Project | 8500 | 2550 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
82 | 84433 | Sealants & caulking | Roof Sealants & caulking | GC | Project | 8500 | 2550 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
167 | 84112 | Common area light fixtures | Replace 6 missing pole lights Allowance to repair/replace emergency light fixtures in common areas based on expired tags | GC | Project | 8000 | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | GC (pay app)
166 | 84210 | Electrical distribution | Replace lightning controllers | GC | Project | 6000 | 7200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | GC (pay app)
35 | 84205 | Fences & gates - swimming pool | Repair and paint | GC | Project | 5600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 |  |  |  |  | GC (no pay app)
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 887775 | [11 empty] | 887775
|  |  | CM Fee |  |  | 46608 | [11 empty] | 46608
|  |  | Contingency |  |  | 44389 | [11 empty] | 44389
|  |  | Capital Plan Total (ex-BTL) |  |  | 978772 | [11 empty] | 978772
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 32889
BTL (dropped per Adam): $0

## Waterford
Waterford — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
89 | 84330 | Electrical Panel Disconnects & Meter Ban | Electrical Panel Replacements | GC | Project | 200000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 |  |  |  |  | GC (no pay app)
132 | 84095 | Swimming pool resurface | PNA: Outdoor pool covered assume needing resurface hot tub needs resurface Indoor pool has been painted All Four nee | GC | Project | 135000 | 40500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 |  |  |  |  | GC (pay app)
38 | 84221 | Concrete deck / floor fill | PNA: Repair catwalks and install new outdoor carpet | GC | Project | 81000 | 24300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 |  |  |  |  | GC (pay app)
117 | 84208 | Clubhouse / Office redecorate (FFE) | Concept Walk - Update clubhouse furniture and fixtures | PMC | Project | 75000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 |  |  |  |  | GL PMC
91 | 84112 | Common Area Lighting | PNA: replace both pole light on existing post, straiten posts and add a concrete curb, replace wall packs with LED | GC | Project | 73000 | 21900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73000 |  |  |  |  | GC (pay app)
30 | 84303 | Landscape Cleanup and Enhancements | Concept Walk - Tree trim and general curb appeal enhancement; Streetside cleanup around sign | PMC | Project | 50000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  |  |  | GL PMC
143 | 84340 | Playground area and equipment | Concept Walk - Install new playground | GC | Project | 40000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  |  |  |  | GC (pay app)
19 | 84201 | Parking lot repairs | PNA: repair potholes. Concept Walk - Replace speed bumps as needed | GC | Project | 38000 | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 |  |  |  |  | GC (pay app)
66 | 84206 | Breezeway soffit repairs | PNA: R&R ceiling lights in breezeways with LED | GC | Project | 33200 | 9960 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33200 |  |  |  |  | GC (pay app)
92 | 84112 | Breezeway Lighting | R&R ceiling lights in breezeway with LED | GC | Project | 33200 | 9960 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33200 |  |  |  |  | GC (pay app)
108 | 84106 | Drier vents | PNA: Remove vent covers, clean vent piping, and install new dryer vent covers | GC | Project | 33000 | 9900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 |  |  |  |  | GC (pay app)
134 | 84095 | Swimming pool deck | PNA: Repair cracks | GC | Project | 32000 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 |  |  |  |  | GC (pay app)
61 | 84206 | Repair / replace siding | PNA: Replace damaged Masonite and paint to match | GC | Project | 30000 | 9000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
90 | 84112 | Breezeway Lighting | PNA - Wiring for pole lights | GC | Project | 30000 | 9000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
20 | 84221 | Asphalt seal coating | PNA: Crack Fill | GC | Project | 29000 | 8700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 |  |  |  |  | GC (pay app)
50 | 84433 | Asphalt composite shingle roofing | PNA: roof tune up | GC | Project | 29000 | 8700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 |  |  |  |  | GC (pay app)
142 | 84203 | Outdoor kitchen, fire pits, and seating | PNA: Replace grill with Charcoal Grill to fit in island (8K). Concept Walk: placeholder for outdoor kitchen and shade st | GC | Project | 28000 | 8400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 |  |  |  |  | GC (pay app)
140 | 84113 | Pergola / shade covers | PNA: Repair, paint, and pressure was outdoor kitchen area | GC | Project | 26000 | 7800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
141 | 84390 | Tennis / sports court | Concept Walk - Resurface basketball court / replace goals | GC | Project | 25200 | 7560 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 |  |  |  |  | GC (pay app)
144 | 84130 | Pet park / pet washing station | Concept Walk: placeholder for adding gravel/turf | GC | Project | 25000 | 7500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
148 | 84280 | Model Unit | Concept Walk - Update model | PMC | Project | 25000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GL PMC
21 | MISSING | Curbing Repairs | PNA: Curbing Repairs | GC | Project | 24000 | 7200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 |  |  |  |  | GC (pay app)
31 | 84219 | Carports / Garages | PNA: Repair carports | GC | Project | 22000 | 6600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
55 | 84202 | Gutters & downspouts | PNA: Clean and repatch gutters throughout property | GC | Project | 21000 | 6300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC (pay app)
43 | 84114 | Repair exterior stair treads and stringe | PNA: inspect and secure railings on cat walks | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
56 | 84433 | Sealants & caulking | PNA: At band boards | GC | Project | 20000 | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
109 | 84239 | Fire Stops | Fire Stops | PMC | Project | 19600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19600 |  |  |  |  | GL PMC
32 | 84111 | Dumpster enclosures | PNA - Repair dumpster enclosures. | GC | Project | 18000 | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 |  |  |  |  | GC (pay app)
26 | 84205 | Site perimeter fencing | Concept Walk - Stain streetside perimeter fencing. Pressure wash interior perimeter fencing to remove moss buildup. | GC | Project | 16480 | 4944 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16480 |  |  |  |  | GC (pay app)
138 | 84360 | Pool furniture | Concept Walk - Add pool furniture | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
146 | 84190 | Fitness Center Remodel | Concept Walk: placeholder for fitness room/flooring paint in the lobby | GC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GC (no pay app)
23 | 84221 | Sidewalks and curbs | PNA: grind trip hazards | GC | Project | 14000 | 4200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
137 | 84205 | Swimming pool fencing / gates | PNA - Repair pool fence and gate. | GC | Project | 14000 | 4200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
149 | 83375 | Golf Carts | Concept Walk: need to purchase two new golf carts | PMC | Project | 12500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 |  |  |  |  | GL PMC
68 | 84206 | Repair / replace wood trim | PNA: R&R rotted wood trim and paint to match | GC | Project | 10000 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
52 | 84433 | Roof treatment / cleaning | PNA: Flashing | GC | Project | 9800 | 2940 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800 |  |  |  |  | GC (pay app)
150 | 84102 | Shed (Storage Space) | Concept Walk: The current shop is only 8x8 and lacks adequate storage space. | PMC | Project | 7500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 |  |  |  |  | GL PMC
133 | 84095 | Swimming pool coping and tile | Lender PCA: The pool and spa were down at the time of the site visit. Management reported the pool/spa area was closed d | GC | Project | 5000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | GC (no pay app)
73 | 84120 | Patio yard enclosures | Concept Walk - Installation of patior fencing where applicable | GC | Project | 3600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  |  |  |  | GC (no pay app)
123 | 84211 | Security/ fire alarm systems | Lender PCA: Valid inspection certificates were affixed to the fire sprinklers dated September 2025. While the systems we | PMC | Project | 1500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1339580 | [11 empty] | 1339580
|  |  | CM Fee |  |  | 70328 | [11 empty] | 70328
|  |  | Contingency |  |  | 66979 | [11 empty] | 66979
|  |  | Capital Plan Total (ex-BTL) |  |  | 1476887 | [11 empty] | 1476887
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## Willow Lakes
Willow Lakes — 10-Year Capital Plan
Acquired 2026. 10-year budget = capital plan excluding BTL. Year budgets from the plan's Expense-Yr columns; spend is current-year actual.
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
15 | 84303 | Landscape Enhancements | Tree trim, Increasing by 50K for curb appeal based on concept walk LPCA - Tree branches were observed in contact at Bui | PMC | Project | 95000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 |  |  |  |  | GL PMC
22 | 84221 | Concrete Curb/Sidewalk | Repair 2000 sq ft of concrete | GC | Project | 70000 | 96000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 |  |  |  |  | GC (pay app)
131 | 84360 | Pool Area Remodel | Refresh area with color and furniture. Split between the two pools | PMC | Project | 60000 | 49907 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 |  |  |  |  | GL PMC
166 | 84112 | Exterior Lighting | Replace breezeway lights - wall sconce, ceiling and garage lights | GC | Project | 59500 | 59500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59500 |  |  |  |  | GC (pay app)
27 | 84205 | Fences & gates - site perimeter | repair iron and wood fence and paint | GC | Project | 56000 | 66000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 |  |  |  |  | GC (pay app)
165 | 84112 | Exterior Lighting | Common area light fixtures - wall packs and pole light throughout | GC | Project | 39000 | 39000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 |  |  |  |  | GC (pay app)
160 | 84218 | Replace AC condenser | align condensers and insulate suction lines | GC | Project | 38000 | 38000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 |  |  |  |  | GC (pay app)
118 | 84239 | Fire Life Safety Work | Fire stops | PMC | Project | 36456 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36456 |  |  |  |  | GL PMC
23 | 83520 | ADA Compliance Expense | ADA landings on apartment entrances are cracking up and failing | GC | Project | 36000 | 36000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 |  |  |  |  | GC (pay app)
24 | 84115 | Sidewalks | repair trip hazards | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
26 | 84517 | Erosion control | Landscaping Erosion Control | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
70 | 84104 | Balconies | Repair Balcony Decks | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
96 | 84113 | Exterior Paint, Carpentry, & Misc. Repai | Repair / replace wood trim - replace rotted wood | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
136 | 84130 | Dog Run | Add lighting, dog amenities, and repairs to fencing | GC | Project | 30000 | 30000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 |  |  |  |  | GC (pay app)
53 | 84120 | Common Corridors Rehab | Grind and seal cracks in breezeways An isolated area of sectional cracking was noted on the main entrance drive and area | GC | Project | 26000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (no pay app)
75 | 84433 | Roof Replacements/Repairs | Roof tune up - Asphalt composite shingle roofing | GC | Project | 26000 | 26000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
87 | 84206 | Building - Exterior | replace siding that was caulked and painted over | GC | Project | 26000 | 26000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 |  |  |  |  | GC (pay app)
42 | 84111 | Dumpster enclosures | Build an enclosed area around roll off trash set up | GC | Project | 25000 | 25000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  |  |  |  | GC (pay app)
21 | 84204 | Asphalt Milling/Paving/Sealcoat | Stripe Parking Areas | GC | Project | 22000 | 22000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 |  |  |  |  | GC (pay app)
80 | 84202 | Roof/Gutters | Clean gutters and downspouts | GC | Project | 21000 | 21000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC (pay app)
164 | 84210 | Electrical/Lighting | Electrical distribution - repair lighting controlers | GC | Project | 21000 | 21000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 |  |  |  |  | GC (pay app)
90 | 84106 | Dryer Vents | Annual Dryer Vent Cleaning | GC | Project | 20460 | 20460 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20460 |  |  |  |  | GC (pay app)
88 | 84102 | Building Repairs | Masonry Repairs - Repair areas of damaged stone | GC | Project | 20000 | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GC (pay app)
122 | 84290 | Monument Sign | Enhance Signage (cordinate w/ church - add signage on their property) | PMC | Project | 20000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  |  |  |  | GL PMC
19 | 84361 | Pool Area Repairs & Equipment | Repair pool gates | GC | Project | 19000 | 9500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 |  |  |  |  | GC (pay app)
119 | 83236 | Smoke Alarms | Completed by Seller - Move to Contingency? | PMC | Project | 18600 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18600 |  |  |  |  | GL PMC
32 | 84361 | Pool Area Repairs & Equipment | seal small cracks on pool deck and clean | GC | Project | 16000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 |  |  |  |  | GC (no pay app)
129 | 84190 | Fitness Center | Moderate upgrades to the fitness center | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
148 | 83375 | Golf Cart | Add leasing cart | PMC | Project | 15000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  |  | GL PMC
153 | 84432 | Stormwater Piping | Clean out basin | GC | Project | 14000 | 14000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | GC (pay app)
68 | 84114 | Exterior Stairs | Repair exterior stair treads and stringers - Replace 90 stair treads | GC | Project | 12500 | 12500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 |  |  |  |  | GC (pay app)
35 | 84205 | Fences & gates | Pedestrian and Front Gate Improvements | GC | Project | 10000 | 19000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
102 | 84305 | Equipment, baracades and staging | Equipment & Staging (Details of Scope?) | GC | Project | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GC (pay app)
127 | 84116 | Club House/Leasing Center Addition/Alter | Leasing office floor/wall finishes - Light leasing office upgrade | PMC | Project | 10000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | GL PMC
31 | 84361 | Pool Area Repairs & Equipment | deck o seal | GC | Project | 9500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 |  |  |  |  | GC (no pay app)
36 | 84203 | Exterior Kitchen | replace grills | GC | Project | 9500 | 9500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 |  |  |  |  | GC (pay app)
69 | 84121 | Handrail / Railings | Repair Exterior Railings | GC | Project | 8500 | 8500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 |  |  |  |  | GC (pay app)
25 | 84361 | Pool Area Repairs & Equipment | LPCA - Excessive algae growth due to an inoperable aeration pump was observed at the south portion of the pond. | GC | Project | 2500 | 16000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 |  |  |  |  | GC (pay app)
20 | 84219 | Covered Parking & Misc. Parking Items | LPCA - Impact damage was observed at the garage door at the G-30 garage. Repairs are recommended. | PMC | Project | 1500 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | GL PMC
95 | 84101 | Exterior Painting |  | DFM |  | 0 | 0 |  |  | 0 | 0 | 385000 | 0 | 0 | 0 | 0 | 0 | 810000
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1039016 | [11 empty] | 1849016
|  |  | CM Fee |  |  | 54509 | [11 empty] | 74721
|  |  | Contingency |  |  | 51163 | [11 empty] | 70413
|  |  | Capital Plan Total (ex-BTL) |  |  | 1144688 | [11 empty] | 1994151
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 68798
BTL (dropped per Adam): $2,859,627

## Colonnade
Colonnade — 10-Year Capital Plan
Acquired . ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
44 | 51080-00 | Full Property Repaint | Full property repaint | GC | Project | 663000 | 663000 | [15 empty] | GC assumed 100% @ budget
21 | 51160-00 | Interior Hallway painting | Interior hallway repaint | GC | Project | 158900 | 158900 | [15 empty] | GC assumed 100% @ budget
120 | 51142-00 | Stab-Lok Panels | Stab-Lok brand breaker panels manufactured by Federal Pacific Electric (FPE) were observed in the units. These panels ha | GC | Project | 123200 | 123200 | [15 empty] | GC assumed 100% @ budget
22 | 51993-00 | Controlled access gates | Add controlled access to main entry, fitness center, pool, & any other main entry point | GC | Project | 100000 | 100000 | [15 empty] | GC assumed 100% @ budget
143 | 51028-00 | Fitness equipment | 7 pieces of new equipments | PMC | Project | 75000 | 0 | [15 empty] | GL PMC
131 | 51021-00 | Swimming pool coping and tile | Resurface pool ( pool is on 4th floor and will required extreme labor cost ) | GC | Project | 50000 | 50000 | [15 empty] | GC assumed 100% @ budget
136 | 51011-00 | Pool furniture | Furniture Upgrades | PMC | Project | 50000 | 0 | [15 empty] | GL PMC
140 | 51160-04 | Outdoor kitchen, fire pits, and seating | Kitchen and outdoor cooking area upgrades | PMC | Project | 50000 | 0 | [15 empty] | GL PMC
41 | 51180-00 | Equipment, Baracades, & Staging | Baracades & Staging | GC | Project | 45000 | 45000 | [15 empty] | GC assumed 100% @ budget
42 | 51077-00 | Repair exterior stair railings | Paint interior stairwells and iron | GC | Project | 38000 | 38000 | [15 empty] | GC assumed 100% @ budget
126 | 51990-00 | Startup Marketing | Rebrand of property signage | PMC | Project | 35000 | 0 | [15 empty] | GL PMC
65 | 51160-00 | Elevator Cabs | Full repairs of 3 elevator interiors. Wood panels, flooring, stainless doors | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
138 | 51070-00 | Pergola / shade covers | Repair and recoat pergola | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
54 | 51062-00 | Sealants & caulking | Roof Sealants & Caulking | GC | Project | 25300 | 25300 | [15 empty] | GC assumed 100% @ budget
115 | 51160-00 | Fitness center renovation | Full redeck of flooring and full repaint | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
53 | 51071-00 | Gutters & downspouts | Clean scuppers and roof drains | GC | Project | 24000 | 24000 | [15 empty] | GC assumed 100% @ budget
132 | 51022-00 | Swimming pool deck | Seal small cracks on pool deck and clean | GC | Project | 16000 | 16000 | [15 empty] | GC assumed 100% @ budget
142 | 51160-00 | Steam Sauna & Bathroom | FF&E facelift and upgrade | PMC | Project | 12000 | 0 | [15 empty] | GL PMC
106 | 51993-01 | Fire Stops | Add fire stops to 50% of units missing | PMC | Project | 10829 | 0 | [15 empty] | GL PMC
43 | 51075-00 | Façade repairs | Stucco deterioration was noted on the northern upper facade locations and organic build-up was noted. Repairs are recomm | GC | Project | 5000 | 5000 | [15 empty] | GC assumed 100% @ budget
125 | 51160-00 | Fountain Repairs | The water feature is reportedly leaking into the garage area and are not presently in use. Repair is recommended. | PMC | Project | 5000 | 0 | [15 empty] | GL PMC
23 | 51070-00 | Trellis Repairs | Deteriorated beam framing at the wood beam framed trellis structure was noted. Repair is recommended. | PMC | Project | 2500 | 0 | [15 empty] | GL PMC
121 | 51993-00 | Security/ fire alarm systems | An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recertification of | PMC | Project | 1500 | 0 | [15 empty] | GL PMC
122 | 51993-01 | Fire Sprinkler Certificaiton | The systems display lapsed certification. Recertification is required | PMC | Project | 1500 | 0 | [15 empty] | GL PMC
123 | 51993-01 | Fire extinguisher certification | The extinguishers displayed lapsed certification. Recertification is required. | PMC | Project | 1500 | 0 | [15 empty] | GL PMC
124 | 51993-01 | Elevator Inspection | A current cab certification permit was not provided and load test information was not displayed. Property management sho | PMC | Project | 1500 | 0 | [15 empty] | GL PMC
127 | 51992-00 | Pest Control | Rat droppings were observed at the emergency generator room. Engaging a pest contractor and treatment for pest control o | PMC | Project | 1500 | 0 | [15 empty] | GL PMC
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1577229
|  |  | CM Fee |  |  | 82805 | 82805
|  |  | Contingency |  |  | 78861 | 78861
|  |  | Capital Plan Total (ex-BTL) |  |  | 1738895
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0

## The Retreat
The Retreat — 10-Year Capital Plan
Acquired . ORIGINAL PLAN COMPLETE — current-year view only per Adam; out-year columns intentionally blank (see Banner for the 2026 budget).
← Back
Row | GL | GL Name | Scope of Work | Owner | Type | Yr 1 Budget | Spend | Remaining | % Spent | Yr 2 Budget | Yr 2 Spend | Yr 3 Budget | Yr 3 Spend | Yr 4 Budget | Yr 4 Spend | Yr 5 Budget | Yr 5 Spend | 10 yr Budget | 10 yr Spend | 10 yr Remaining | 10 yr % Spent | Actual Project % Complete | Basis
89 | 0900 - FF&E in Units | Appliances Package |  | PMC | Project | 486000 | 0 | [15 empty] | GL PMC
102 | 0900 - FF&E in Units | Ceramic tile | 324 Backsplash @ $700 | PMC | Project | 226800 | 0 | [15 empty] | GL PMC
118 | 1100- Specialties, Equipment & Furnishings | Tech Package per unit | 162 units x $700 | PMC | Project | 113400 | 0 | [15 empty] | GL PMC
21 | 0200 - Site Utilities & Improvements | Patio fencing | 20 Extended Dog yards @ $5k- Value add | GC | Project | 100000 | 100000 | [15 empty] | GC assumed 100% @ budget
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | Clubhouse furniture- quote #PS6143285 from Charter Furniture | PMC | Project | 92000 | 46776 | [15 empty] | GL PMC
31 | 0200 - Site Utilities & Improvements | Pickleball court | Install pickleball court behind clubhouse | GC | Project | 40000 | 40000 | [15 empty] | GC assumed 100% @ budget
121 | 1100- Specialties, Equipment & Furnishings | Pool furniture | Update pool furniture to include cabanas | PMC | Project | 40000 | 37994 | [15 empty] | GL PMC
120 |  | Fitness Equipment |  | AMN |  | 36157 | 0
29 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Replace entire dog park fence | GC | Project | 35000 | 35000 | [15 empty] | GC assumed 100% @ budget
32 | 0200 - Site Utilities & Improvements | Playground equipment | New Playground | GC | Project | 30000 | 30000 | [15 empty] | GC assumed 100% @ budget
106 | 0900 - FF&E in Units | Range Queen |  | PMC | Project | 29160 | 0 | [15 empty] | GL PMC
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Project | 26000 | 26000 | [15 empty] | GC assumed 100% @ budget
23 | 0200 - Site Utilities & Improvements | Landscaping | New palms, bare land, dead bushes, etc.. | GC | Project | 25000 | 25000 | [15 empty] | GC assumed 100% @ budget
111 | 1100- Specialties, Equipment & Furnishings | Signage - site |  | PMC | Project | 25000 | 3739 | [15 empty] | GL PMC
16 | 0200 - Site Utilities & Improvements | Parking equipment | add 15 speed bumps | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
18 | 0200 - Site Utilities & Improvements | Sidewalks | repair cracked concrete | GC | Project | 20000 | 20000 | [15 empty] | GC assumed 100% @ budget
59 | 0700 - Roofing | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | GC | Project | 16500 | 16500 | [15 empty] | GC assumed 100% @ budget
114 | 1100- Specialties, Equipment & Furnishings | Video Systems | Movie Room refresh | PMC | Project | 15000 | 0 | [15 empty] | GL PMC
123 | 1100- Specialties, Equipment & Furnishings | Golf Cart |  | PMC | Project | 14000 | 24807 | [15 empty] | GL PMC
107 | 0900 - FF&E in Units | Unit Model Update | New furniture in model unit | PMC | Project | 13000 | 0 | [15 empty] | GL PMC
74 | 0800 - Exterior Wall | Dryer Vents | Clean all dryer vents | GC | Project | 11340 | 11340 | [15 empty] | GC assumed 100% @ budget
119 | 1100- Specialties, Equipment & Furnishings | Audio systems | Audio systems - Game Room | PMC | Project | 10000 | 0 | [15 empty] | GL PMC
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Wall and glass door between game/movie rooms | GC | Project | 6500 | 6500 | [15 empty] | GC assumed 100% @ budget
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair Dumpsters and paint | GC | Project | 6000 | 6000 | [15 empty] | GC assumed 100% @ budget
140 | 1600 - Electrical | Replace Fire Alarm Panel |  | GC | Project | 1500 | 1500 | [15 empty] | GC assumed 100% @ budget
|  |  | Projects Subtotal (excl. Contingency & CM Fee) |  |  | 1438357
|  |  | Capital Plan Total (ex-BTL) |  |  | 1438357
|  |  | Unplanned CapEx Yr 1 (out-of-plan) |  |  |  | 0
BTL (dropped per Adam): $0