## Master List
Master Project List — Every Capital Plan Scope (all properties)
Every project/scope across all properties — completion + how billed. Filter/sort any column (e.g. by Acquired to see one cohort, by Status to see what's open).
Property | Acquired | Project | Scope of Work | GL Code | Owner | Type | Budget | Spent | Remaining | % Billed | Status
Emerald Pointe | 2015 | Pool Furniture Replacement | New Pool Furniture ($5,000) | 51010-00 | PMC | Capital Plan | 5000 | 12 | 4988 |  | In Progress
Emerald Pointe | 2015 | Pool Deck Repair | Seal Cracks Pool Deck ($700) Cracks were observed on the clubhouse pool deck. It appeared that there were attempts of re | 51021-00 | GC | Capital Plan | 700 | 700 | 0 |  | Completed
Emerald Pointe | 2015 | Pool Resurfacing | Resurface Pool Decks ($42,500) | 51023-00 | GC | Capital Plan | 42500 | 42500 | 0 |  | Completed
Emerald Pointe | 2015 | Court Resurfacing | Repair Basketball Court Cracks ($500) Asphalt pavement cracks was observed throughout the basketball court. Resealing cr | 51027-00 | GC | Capital Plan | 500 | 500 | 0 |  | Completed
Emerald Pointe | 2015 | Tree Trimming/Pruning & Removal | Tree Trimming ($25,000) | 51043-00 | PMC | Capital Plan | 25000 | 59 | 24941 |  | In Progress
Emerald Pointe | 2015 | Landscape Upgrades | Repair/Improve Landscape ($7,500) Many of the landscaping sprinkler systems are broken in multiple areas of theProperty. | 51045-00 | PMC | Capital Plan | 7500 | 18 | 7482 |  | In Progress
Emerald Pointe | 2015 | Irrigation System | Irrigation Repairs ($25,000) | 51046-00 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Emerald Pointe | 2015 | Roof Repairs | Roof Repairs ($15,000) | 51062-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Emerald Pointe | 2015 | Roof Cleaning | Roof Inspection & Cleaning ($10,000) | 51063-00 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Emerald Pointe | 2015 | Fence Repair/Replacement | Remove Pergolas ($15,000) | 51076-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Emerald Pointe | 2015 | Trim/Doors | Repair Damaged Door ($750) The maintenance room door located near the north pool was observed to bedamaged. Repairing th | 51082-00 | GC | Capital Plan | 750 | 750 | 0 |  | Completed
Emerald Pointe | 2015 | Decks/Balconies/Patio Repairs | Repair Deteriorating Wood on Patios ($15,000) | 51083-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Emerald Pointe | 2015 | Railings & Fences | Replace Landing Railings ($60,000) | 51084-00 | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Emerald Pointe | 2015 | Concrete/Foundation | Repair Concrete Pavement Cracks ($500) Concrete cracks were observed at the concrete pavement located adjacent to the ba | 51090-00 | GC | Capital Plan | 500 | 500 | 0 |  | Completed
Emerald Pointe | 2015 | Sidewalk/Curb Repair/Replacement | Repair Sidewalk Tripping Hazards ($2,500) | 51091-00 | GC | Capital Plan | 2500 | 2500 | 0 |  | Completed
Emerald Pointe | 2015 | Sidewalk/Curb Repair/Replacement | Repair Sidewalk Cracks ($700) A couple of the Subject's concrete sidewalk sections exhibit cracks. These conditions were | 51091-00 | GC | Capital Plan | 700 | 700 | 0 |  | Completed
Emerald Pointe | 2015 | Boiler Replacement | Repair Water Heater Leaks - Building 3 ($500) The water heater was leaking in Building 3 at the time of the assessment. | 51110-00 | PMC | Capital Plan | 500 | 1 | 499 |  | In Progress
Emerald Pointe | 2015 | Electrical Replacement | Replace Zinsco Electrical Subpanels ($525,000) Zinsco breakers were observed in the electrical subpanels inside all the | 51140-00 | GC | Capital Plan | 587000 | 587000 | 0 |  | Completed
Emerald Pointe | 2015 | Wiring | Repair Aluminum Wiring - Allowance ($225,000) Aluminum wiring was observed in the residential units. To mitigate aluminu | 51143-00 | GC | Capital Plan | 225000 | 225000 | 0 |  | Completed
Emerald Pointe | 2015 | Carpentry/Sheetrock | Repair Damaged Breezeway Ceiling ($1,000) A limited damaged of exterior breezeway ceiling finishes located by Building 2 | 51159-00 | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Emerald Pointe | 2015 | Termite/Pest Control | Termite Remediation ($249,500) WDI infestation noted at rafter tail, water heater closet door jam, and water heater clos | 51992-00 | GC | Capital Plan | 249500 | 249500 | 0 |  | Completed
Emerald Pointe | 2015 | Contingency Amount | Contingency | 51180-00 | GC | Contingency | 64432 | 64432 | 0 |  | Reserve
Emerald Pointe | 2015 | Construction Supervision Expense | CM Fees | 51190-00 | GC | Capital Plan | 67654 | 67654 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Storm sewer piping | Clean storm sewer basins | 84432 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Asphalt & Pavement | Mill cement stabilize and repave asphalt part of drive esles and repair concrete potholes on phase two Repair concrete | 84204 | GC | Capital Plan | 400000 | 400000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Stripe parking areas | Stripe Parking | 84201 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Sidewalks | Repair trip Hazards | 84115 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Erosion control | Add soil to eroded areas Repair erosion at drainage channel - Minor erosion was observed in the drainage channel at the | 84517 | GC | Capital Plan | 1200 | 1200 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Fences & gates - site perimeter | Replace perimater fence on three sides of community Repair perimeter fencing - Collapsed fence panels were observed alon | 84205 | GC | Capital Plan | 95000 | 95000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Tree Trimming - Landscaping | Tree trim | 84303 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Fences & gates - swimming pool | Rerair and paint pool fence | 84095 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Pergola court | Repair and paint purgola in culdasac | 84105 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Dumpster enclosures | repair and paint | 84111 | GC | Capital Plan | 9800 | 9800 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Concrete Repairs - Repair washed out walkway at unit 23 | Repair wash out walkway at unit 2301 - The front entry concrete walkway to unit 2301 was noted as damaged from flooding | 84221 | PMC | Capital Plan | 750 | 750 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Repair ADA accessway and wheel stop | Repair ADA accessway and wheel stop - the accessway from the ADA parking lot, between Crescent Village 1 and 2 on the no | 84221 | GC | Capital Plan | 1800 | 1800 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Repair patio/balcony railings | secure all patio railings Repair exterior railings on east side of the property - Peeling and flaking paint was specifi | 84121 | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Expansion Joints | Building Expansion Joints | 84206 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Gutters & downspouts | Replace damaged gutter and downspouts, Clean, re-pitch remaining | 84202 | GC | Capital Plan | 9800 | 9800 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Roof Flashing | replace damaged flashing | 84433 | GC | Capital Plan | 4000 | 4000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Roof - Sealants & caulking | Roof Sealants | 84433 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Replace AC condenser | Install installation and separate condensing units | 84220 | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Electrical distribution | repair lighting control system | 84210 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Crescent Village 1 & 2 | 2017 | Common area light fixtures | repair /replace leaning or broken poles and pole lights throughout the community | 84210 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
Viewcrest Village | 2021 | Grind Sidewalk Trip Hazard | Trip hazards were specifically observed by Buildings 3342, 3423, 3412, 3413, 3430, 1542, 3427. | 84221.0 | PMC | Capital Plan | 3062 | 765 | 2297 |  | In Progress
Viewcrest Village | 2021 | Sidewalk - Seal Concrete Cracks | Limited areas of concrete sidewalk were observed with cracks. These area were specifically were observed by Units 3472C | 84221.0 | PMC | Capital Plan | 750 | 187 | 563 |  | In Progress
Viewcrest Village | 2021 | Concrete Crack - Building 8 | Sidewalk exhibiting crack in concrete | 84221.0 | PMC | Capital Plan | 625 | 156 | 469 |  | In Progress
Viewcrest Village | 2021 | Leasing office | Spot reno (new FF&E) | 84116.0 | PMC | Capital Plan | 35000 | 8746 | 26254 |  | In Progress
Viewcrest Village | 2021 | Meter Boxes - Repair/replace meter/cable housing | Replace on all buildings | 84210.0 | PMC | Capital Plan | 25000 | 6247 | 18753 |  | In Progress
Viewcrest Village | 2021 | Roof Replacement | Replace 12 roofs | 84433.0 | GC | Capital Plan | 372000 | 372000 | 0 |  | Completed
Viewcrest Village | 2021 | Gutters & downspouts | Repair and replace damaged or missing gutters | 84202.0 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Viewcrest Village | 2021 | Flashing | Replace flashing on 12 remaining roofs | 84433.0 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Viewcrest Village | 2021 | Roof Repairs - Repair/replace sofits | Repair/replace missing or poorly maintained sofits to improve airflow | 84433.0 | GC | Capital Plan | 12500 | 12500 | 0 |  | Completed
Viewcrest Village | 2021 | Repair / replace vinyl siding | Replace failing siding as needed | 84206.0 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Viewcrest Village | 2021 | Exterior painting | Community Paint | 84101.0 | GC | Capital Plan | 375000 | 375000 | 0 |  | Completed
Viewcrest Village | 2021 | Repair / replace wood trim | Replace bad areas of Fascia | 84105.0 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Viewcrest Village | 2021 | HVAC Repair - Heating System | Cadet wall heaters were observed in 3-BR units. | 84217.0 | PMC | Capital Plan | 3188 | 796 | 2391 |  | In Progress
Viewcrest Village | 2021 | Fire System Work - Clear Fire Department Violations | The fire inspection report dated March 27, 2023, cited violations, including extension cords hanging from the ceiling an | 84211.0 | PMC | Capital Plan | 375 | 94 | 281 |  | In Progress
Viewcrest Village | 2021 | Electrical Panels - Replace FPE Stab-Lok Panels | It was reported that approximately 20% of the units still have FPE stab-lok panels. | 84330.0 | GC | Capital Plan | 126000 | 126000 | 0 |  | Completed
Viewcrest Village | 2021 | Electrical Meters - Electrical audit and grounding repa | Audit meters for proper housing, mounting and grounding and repair/replace as needed | 84210.0 | GC | Capital Plan | 51000 | 51000 | 0 |  | Completed
Viewcrest Village | 2021 | Appliances - Repair Washer/Dryer Hookups | Approximately 10-15 units have improperly installed hookups. | 82480.0 | PMC | Capital Plan | 9375 | 2343 | 7032 |  | In Progress
Viewcrest Village | 2021 | Interior Other - Bathroom tub mold | Mold at the bottom of the tub surround was observed at Unit 3412, 1512, 1538B, 1579, 4 out of 30 units that were inspect | 83160.0 | PMC | Capital Plan | 2500 | 625 | 1875 |  | In Progress
Viewcrest Village | 2021 | Pest Control - Interior pest control | Two vacant units, 3419B and 1512B have been found to have fleas throughout. Pest control treatment has been scheduled fo | 83170.0 | PMC | Capital Plan | 2000 | 500 | 1500 |  | In Progress
Encore Crossing | 2022 | Storm sewer piping |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Encore Crossing | 2022 | Concrete pavement | Repair | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Encore Crossing | 2022 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Encore Crossing | 2022 | Parking equipment | add 10 speed bumps | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Encore Crossing | 2022 | Parking Lot | Install 27 car stops in front of iron fencing Phase 1 | 0200 - Site Utilities & Improvements | GC | Capital Plan | 4050 | 4050 | 0 |  | Completed
Encore Crossing | 2022 | Sidewalks | repair cracked concrete | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Encore Crossing | 2022 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Encore Crossing | 2022 | Fences & gates - site perimeter | $40k = Repair wood fence and paint, $40k = Repair (3) entrance gates. $15k iron fence repairs Phase 1 | 0200 - Site Utilities & Improvements | GC | Capital Plan | 95000 | 95000 | 0 |  | Completed
Encore Crossing | 2022 | Landscaping | remove dead shrubs and change entrance island shrubs. DD $60k placeholder for landscape enhancement | 0200 - Site Utilities & Improvements | GC | Capital Plan | 110000 | 110000 | 0 |  | Completed
Encore Crossing | 2022 | Resurface swimming pool | Resurface Phase I | 0200 - Site Utilities & Improvements | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
Encore Crossing | 2022 | Replace swimming pool coping | replace deck-o-seal in both pools | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9200 | 9200 | 0 |  | Completed
Encore Crossing | 2022 | Replace swimming pool deck | Pressure wash and coat pool deck in phase two | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18900 | 18900 | 0 |  | Completed
Encore Crossing | 2022 | Repair / replace swimming pool pumps | Phase 2 pool fountain repair | 0200 - Site Utilities & Improvements | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Encore Crossing | 2022 | Fences & gates - swimming pool | repair dog park and Pool fences and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Encore Crossing | 2022 | Pool Area Enhancement | Value-add enhancement to pool area, to inlcude turf installation, outdoor kitchen, fire pit area | 0200 - Site Utilities & Improvements | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Encore Crossing | 2022 | Dumpster enclosures | Repair Dumpsters and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Encore Crossing | 2022 | Building entrance | Entrance upgrade | 0200 - Site Utilities & Improvements | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Encore Crossing | 2022 | Carports / Garages | Replace 10 garage doors | 0200 - Site Utilities & Improvements | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Encore Crossing | 2022 | Carports / Garages | Repair/replace 15 garage door openers/ placeholder for purchase of openers | 0200 - Site Utilities & Improvements | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Encore Crossing | 2022 | Dog Park | Placeholder for upgrade of equipment in dog park | 0200 - Site Utilities & Improvements | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Encore Crossing | 2022 | Wall framing |  | 0400 - Structure | GC | Capital Plan | 8200 | 8200 | 0 |  | Completed
Encore Crossing | 2022 | Repair exterior stair railings |  | 0400 - Structure | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Encore Crossing | 2022 | Repair balcony framing & decking |  | 0400 - Structure | GC | Capital Plan | 18500 | 18500 | 0 |  | Completed
Encore Crossing | 2022 | Repair patio/balcony railings |  | 0400 - Structure | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Encore Crossing | 2022 | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | 0700 - Roofing | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Encore Crossing | 2022 | Gutters & downspouts | clean and repin | 0700 - Roofing | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Encore Crossing | 2022 | Flashing |  | 0700 - Roofing | GC | Capital Plan | 5600 | 5600 | 0 |  | Completed
Encore Crossing | 2022 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Capital Plan | 5600 | 5600 | 0 |  | Completed
Encore Crossing | 2022 | Repair / replace wood siding | Added $8000 for paint to match | 0800 - Exterior Wall | GC | Capital Plan | 25200 | 25200 | 0 |  | Completed
Encore Crossing | 2022 | Dryer Vents | Clean 256 dryer vents ($35 per) and replace (100) dryer vents | 0800 - Exterior Wall | GC | Capital Plan | 13960 | 13960 | 0 |  | Completed
Encore Crossing | 2022 | Tuck-pointing |  | 0800 - Exterior Wall | GC | Capital Plan | 3800 | 3800 | 0 |  | Completed
Encore Crossing | 2022 | Repair / replace wood trim | Added $8000 for paint to match | 0800 - Exterior Wall | GC | Capital Plan | 26900 | 26900 | 0 |  | Completed
Encore Crossing | 2022 | Shutters | Replace missing shutters and paint to match | 0800 - Exterior Wall | GC | Capital Plan | 10200 | 10200 | 0 |  | Completed
Encore Crossing | 2022 | Interior Update Placeholder |  | 0900 - FF&E in Units | PMC | Capital Plan | 960000 | 332 | 959668 |  | In Progress
Encore Crossing | 2022 | Range Queen |  | 0900 - FF&E in Units | PMC | Capital Plan | 32040 | 0 | 32040 |  | Not Started
Encore Crossing | 2022 | Signage - site | Front monument sign & lighting | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 25000 | 29319 | -4319 |  | Completed
Encore Crossing | 2022 | Signage - building identification | New signage throughout, includes logo design and all new collateral | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 20000 | 23455 | -3455 |  | Completed
Encore Crossing | 2022 | Clubhouse / Office Remodel | Per Mark, placeholder for office redecoration x 2 (Includes adding sliding glass doors out to pool and opening up wall t | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 125000 | 125000 | 0 |  | Completed
Encore Crossing | 2022 | Clubhouse / Office Redecorate (FFE) | Office redecoration placeholder | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 50000 | 131158 | -81158 |  | Completed
Encore Crossing | 2022 | Audio systems | Audio system for 2 pool areas | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Encore Crossing | 2022 | Video systems | Installation of new system (placeholder) | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Encore Crossing | 2022 | Fitness Equipment | New fitness equipment | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 50000 | 67319 | -17319 |  | Completed
Encore Crossing | 2022 | Pool furniture | New pool furniture (2 pools) | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 60000 | 206 | 59794 |  | In Progress
Encore Crossing | 2022 | Fitness center renovation | Install new gym floor phase 2 and paint | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Encore Crossing | 2022 | Golf Cart | Repair (2) golf carts- changed to 3 new golf carts | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 10000 | 69808 | -59808 |  | Completed
Encore Crossing | 2022 | Electrical distribution |  | 1600 - Electrical | GC | Capital Plan | 6600 | 6600 | 0 |  | Completed
Encore Crossing | 2022 | Common area light fixtures | replace garage light fixtures | 1600 - Electrical | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
Encore Crossing | 2022 | Replace breezeway lights | Replace breezeway fixtures with led | 1600 - Electrical | GC | Capital Plan | 28600 | 28600 | 0 |  | Completed
Island Villas | 2022 | Storm sewer piping |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Island Villas | 2022 | Concrete pavement | Repair | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Island Villas | 2022 | Stripe parking areas | Includes $5k for painting curbs at closing | 0200 - Site Utilities & Improvements | GC | Capital Plan | 13000 | 13000 | 0 |  | Completed
Island Villas | 2022 | Parking equipment | add 10 speed bumps | 0200 - Site Utilities & Improvements | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
Island Villas | 2022 | Sidewalks | repair cracked concrete | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Island Villas | 2022 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Island Villas | 2022 | Erosion control | replace dirt missing due to erosion | 0200 - Site Utilities & Improvements | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Island Villas | 2022 | Fences & gates - site perimeter | Replace wood fence and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 154000 | 154000 | 0 |  | Completed
Island Villas | 2022 | Retaining walls | build retaining wall at site exit | 0200 - Site Utilities & Improvements | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Island Villas | 2022 | Landscaping | remove dead shrubs and change entrance island shrubs, landscaping around pool and planters for 2nd pool. Installation of | 0200 - Site Utilities & Improvements | GC | Capital Plan | 100000 | 100000 | 0 |  | Completed
Island Villas | 2022 | Resurface swimming pool | resurface pool by office | 0200 - Site Utilities & Improvements | GC | Capital Plan | 41000 | 41000 | 0 |  | Completed
Island Villas | 2022 | Replace swimming pool coping | replace deck-o-seal in both pools | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9600 | 9600 | 0 |  | Completed
Island Villas | 2022 | Replace swimming pool deck | Replace pool deck w/ stamp stain concrete (main pool) and repairs to 2nd pool deck | 0200 - Site Utilities & Improvements | GC | Capital Plan | 80000 | 80000 | 0 |  | Completed
Island Villas | 2022 | Fences & gates - swimming pool | repair dog park and Pool fences and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Island Villas | 2022 | Pool Area | Install (2) pool cabanas, turf in outdoor kitchen area | 0200 - Site Utilities & Improvements | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Island Villas | 2022 | Dumpster enclosures | Repair Dumpsters and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Island Villas | 2022 | Carports / Garages | Replace 6 garage doors and paint garages | 0200 - Site Utilities & Improvements | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
Island Villas | 2022 | Wall framing |  | 0400 - Structure | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Island Villas | 2022 | Repair exterior stair railings | Minor repairs to balconies | 0400 - Structure | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Island Villas | 2022 | Repair balcony framing & decking | Fill cracks in decking | 0400 - Structure | GC | Capital Plan | 18500 | 18500 | 0 |  | Completed
Island Villas | 2022 | Repair patio/balcony railings | resecure | 0400 - Structure | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Island Villas | 2022 | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | 0700 - Roofing | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Island Villas | 2022 | Cleaning Blue Algae | Treating/cleaning blue algae on roofs ($4k per building) | 0700 - Roofing | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Island Villas | 2022 | Gutters & downspouts | replace missing elbows and splash blocks | 0700 - Roofing | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Island Villas | 2022 | Flashing |  | 0700 - Roofing | GC | Capital Plan | 5600 | 5600 | 0 |  | Completed
Island Villas | 2022 | Sealants & caulking and paint | Seal all face nails in siding | 0700 - Roofing | GC | Capital Plan | 67200 | 67200 | 0 |  | Completed
Island Villas | 2022 | Repair / replace wood siding | Added $8000 for paint to match | 0800 - Exterior Wall | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Island Villas | 2022 | Dryer Vents | clean all dryer vents | 0800 - Exterior Wall | GC | Capital Plan | 11760 | 11760 | 0 |  | Completed
Island Villas | 2022 | Repair / replace wood trim | Added $7500 for paint to match | 0800 - Exterior Wall | GC | Capital Plan | 22500 | 22500 | 0 |  | Completed
Island Villas | 2022 | Shutters | Added $3000 for paint to match | 0800 - Exterior Wall | GC | Capital Plan | 10200 | 10200 | 0 |  | Completed
Island Villas | 2022 | Interior Update Placeholder |  | 0900 - FF&E in Units | PMC | Capital Plan | 749760 | 592172 | 157588 |  | In Progress
Island Villas | 2022 | Range Queen |  | 0900 - FF&E in Units | PMC | Capital Plan | 30240 | 0 | 30240 |  | Not Started
Island Villas | 2022 | Signage - entry | New Monument Sign at corner | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 25000 | 7329 | 17671 |  | In Progress
Island Villas | 2022 | Signage - site | Bldg ID signs, common area signage | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 15000 | 4397 | 10603 |  | In Progress
Island Villas | 2022 | Clubhouse / Office Remodel | Re-paint / new flooring for office | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Island Villas | 2022 | Clubhouse / Office Redecorate (FFE) |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 35000 | 53745 | -18745 |  | Completed
Island Villas | 2022 | Security/ fire alarm systems | Placeholder for installation of cameras | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 60000 | 30339 | 29661 |  | In Progress
Island Villas | 2022 | Audio systems | Speaker system for main pool area | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Island Villas | 2022 | Fitness Equipment | New gym equipment | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 30000 | 19034 | 10966 |  | In Progress
Island Villas | 2022 | Pool furniture | Include additional tables/sitting areas | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 30000 | 4650 | 25350 |  | In Progress
Island Villas | 2022 | Fitness center renovation | Remove wall to enlarge gym area & install flooring/paint | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Island Villas | 2022 | Electrical distribution | repair outside GFCI'S | 1600 - Electrical | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Island Villas | 2022 | Common area light fixtures | replace garage light fixtures and wall packs | 1600 - Electrical | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Concrete pavement |  | 83221 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Stripe parking areas |  | 83201 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | ADA parking & curb cuts |  | 83520 | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Landscape irrigation | inspect and repair irrigation | 83300 | GC | Capital Plan | 34000 | 34000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Fences & gates - site perimeter | Remove vines, repair fence and paint fence | 83205 | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Landscaping | Landscaping for curb and pool (place Holder) | 83303 | GC | Capital Plan | 150000 | 150000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Resurface swimming pool | Resurface pool, Replace tile | 83100 | GC | Capital Plan | 58000 | 58000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Replace swimming pool coping | Replace deck-o-seal on pool and repair coping | 83100 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Replace swimming pool deck | Clean and recoat pool deck | 83100 | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Fences & gates - swimming pool | Repair and paint pool fence | 83205 | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Pergola | repair and stain all pergola | 83206 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Carport and garage | Repair carport damage and paint | 83219 | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Dumpster enclosures | Repair dumpster enclosures | 83111 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair exterior stair railings | secure railings | 83114 | GC | Capital Plan | 8300 | 8300 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair balcony framing & decking | repair balcony band boards | 83104 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair patio/balcony railings | secure railings | 83114 | GC | Capital Plan | 8300 | 8300 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Expansion Joints | clean and seal expansion joints | 83206 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Asphalt composite shingle roofing | minor roof repairs | 83202 | GC | Capital Plan | 23000 | 23000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Gutters & downspouts | Clean down spouts and gutters | 83439 | GC | Capital Plan | 23000 | 23000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Sealants & caulking |  | 83206 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair / replace cement fiber siding | repair damaged siding |  | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair stucco |  |  | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies |  | GC | Capital Plan | 23000 | 23000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Exterior building | Paint community |  | GC | Capital Plan | 328000 | 328000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Repair / replace wood trim |  |  | GC | Capital Plan | 23000 | 23000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Shutters | Replace bad shutters |  | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGc | 684sqft, 1BR 1BA |  | GC | Capital Plan | 352224 | 352224 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGe | 773sqft, 1BR 1BA |  | GC | Capital Plan | 540512 | 540512 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGg | 894sqft, 1BR 1BA |  | GC | Capital Plan | 50764 | 50764 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AZh | 946sqft, 1BR 1BA |  | GC | Capital Plan | 249588 | 249588 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGl | 1117sqft, 2BR 2BA |  | GC | Capital Plan | 270127 | 270127 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn | 1247sqft, 2BR 2BA |  | GC | Capital Plan | 36836 | 36836 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn1 | 1256sqft, 2BR 2BA |  | GC | Capital Plan | 24734 | 24734 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn2 | 1259sqft, 2BR 2BA |  | GC | Capital Plan | 24866 | 24866 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn3 | 1271sqft, 2BR 2BA |  | GC | Capital Plan | 37596 | 37596 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGo1 | 1376sqft, 2BR 2BA |  | GC | Capital Plan | 26058 | 26058 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 3CGo | 1381sqft, 3BR 2BA |  | GC | Capital Plan | 39307 | 39307 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 3CGp | 1477sqft, 3BR 2BA |  | GC | Capital Plan | 27022 | 27022 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Ceiling Fans | Add to all living rooms |  | GC | Capital Plan | 90200 | 90200 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Clubhouse / Office Remodel | Replace carpet tile, some paint and finish refresh |  | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Clubhouse / Office Redecorate (FFE) |  |  | Unmarked | Capital Plan | 80000 | 63309 | 16691 |  | In Progress
Amalfi at Tuscan Lakes | 2023 | Model Unit | Allowance for small additions/refresh |  | Unmarked | Capital Plan | 4000 | 8256 | -4256 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Computers | Not needed, allowance for 1 |  | Unmarked | Capital Plan | 1500 | 1817 | -317 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Mailboxes | Package locker or Fetch system needed |  | Unmarked | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Amalfi at Tuscan Lakes | 2023 | Fountain area Remodel | Address planter- either fill with rocks or fix irrigation Look at cabanas or shade over benches by reflecting pond Lock |  | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Security Camera System | Need at least for entry drive, clubhouse, and amenity coverage |  | Unmarked | Capital Plan | 20000 | 7426 | 12574 |  | In Progress
Amalfi at Tuscan Lakes | 2023 | EV Chargers | Likely will be no-cost to property, but providing allowance |  | Unmarked | Capital Plan | 8000 | 0 | 8000 |  | Not Started
Amalfi at Tuscan Lakes | 2023 | Pool Remodel | New vertical tile on side of pool wall to replace aged blue Fire pit in raised area if feasible New grill area with cou |  | GC | Capital Plan | 100000 | 100000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Fitness Equipment | 2 Ellipticals, other allowance for repairs and new equipment |  | Unmarked | Capital Plan | 18000 | 11961 | 6039 |  | In Progress
Amalfi at Tuscan Lakes | 2023 | Pool furniture | New furniture for pool, repurpose and re-sling existing and move to Sorrento |  | Unmarked | Capital Plan | 45000 | 28892 | 16108 |  | In Progress
Amalfi at Tuscan Lakes | 2023 | Fitness center renovation | Add mirrors, 1-2 TVs |  | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Golf Cart | Utility/Maintenance Cart |  | Unmarked | Capital Plan | 8000 | 0 | 8000 |  | Not Started
Amalfi at Tuscan Lakes | 2023 | Dryer Vent cleaning |  |  | GC | Capital Plan | 24600 | 24600 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Electrical distribution |  |  | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Fire and Sprinklers | replace emergency lights |  | GC | Capital Plan | 18560 | 18560 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Common area light fixtures | Replace all wall packs |  | GC | Capital Plan | 38640 | 38640 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Replace breezeway lights | Replace breezeway, Garage and landscaping lights |  | GC | Capital Plan | 49860 | 49860 | 0 |  | Completed
Amalfi at Tuscan Lakes | 2023 | Contingency |  |  | Unmarked | Contingency | 108322 | 0 | 108322 |  | Reserve
Amalfi at Tuscan Lakes | 2023 | Construction Management Fee |  |  | Unmarked | Contingency | 171121 | 0 | 171121 |  | Reserve
Avila | 2023 | Storm sewer piping | Clear drainage lines increase by 15,000 due to areas of bad water flow ( water infiltration into ground floor units ) | 0200 - Site Utilities & Improvements | GC | Capital Plan | 38800 | 38800 | 0 |  | Completed
Avila | 2023 | Parking Equipment- wheel stops | Lender Mandate- At the time of the site visit, some concrete wheel stops were observed to be damaged. Such damaged wheel | 0200 - Site Utilities & Improvements | GC | Capital Plan | 750 | 750 | 0 |  | Completed
Avila | 2023 | Pavement | Large areas of asphalt paving, speed bump repair Includes $2,500 in lender mandates- The asphalt pavement has localized | 0200 - Site Utilities & Improvements | GC | Capital Plan | 150000 | 150000 | 0 |  | Completed
Avila | 2023 | Stripe parking areas | Restripe lot, repaint curbs and fire lanes | 0200 - Site Utilities & Improvements | GC | Capital Plan | 13000 | 13000 | 0 |  | Completed
Avila | 2023 | Asphalt coating | Seal coat lot | 0200 - Site Utilities & Improvements | GC | Capital Plan | 98000 | 98000 | 0 |  | Completed
Avila | 2023 | ADA parking & curb cuts | Replace ADA signage | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Avila | 2023 | Sidewalks | Lender Mandate- Several of the Subject's concrete sidewalk sections have settled or heaved over the years causing trippi | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8400 | 8400 | 0 |  | Completed
Avila | 2023 | Landscape irrigation | Inspect and repair irrigation Increased by 20000 due to amount of issues with Irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 49000 | 49000 | 0 |  | Completed
Avila | 2023 | Erosion control |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avila | 2023 | Retaining walls | Repair cracks in retaining walls Includes $3,000 in lender mandates- The railroad tie retaining wall located on the west | 0200 - Site Utilities & Improvements | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Avila | 2023 | Replace swimming pool coping | Deck o seal | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8600 | 8600 | 0 |  | Completed
Avila | 2023 | Repair / replace swimming pool pumps | anti entrapment devices | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Avila | 2023 | Fences & gates | repair and paint Includes $2,000 in lender mandates- The metal panels fencing on the west side of the property was obse | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9600 | 9600 | 0 |  | Completed
Avila | 2023 | Carport and garage | repair and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Avila | 2023 | Dumpster enclosures | Repair dumpster enclosures | 0200 - Site Utilities & Improvements | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Avila | 2023 | Maintenance Structure | Lender Mandate- The batt insulation of the maintenance shop was observed to be damaged and in poor condition. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 2500 | 2500 | 0 |  | Completed
Avila | 2023 | Jack & underpin foundations | Foundation in three buildings | 0300 - Excavation & Foundations | GC | Capital Plan | 72000 | 72000 | 0 |  | Completed
Avila | 2023 | Concrete deck / floor fill | entrance landings | 0400 - Structure | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Avila | 2023 | Wall framing |  | 0400 - Structure | GC | Capital Plan | 1500 | 1500 | 0 |  | Completed
Avila | 2023 | Repair exterior stair treads and stringers | replace bad stair treads | 0400 - Structure | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avila | 2023 | Repair exterior stair railings | Repair and Paint | 0400 - Structure | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avila | 2023 | Repair balcony framing & decking |  | 0400 - Structure | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Avila | 2023 | Repair patio/balcony railings | secure railings | 0400 - Structure | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Avila | 2023 | Asphalt composite shingle roofing | Minor roof repairs | 0700 - Roofing | GC | Capital Plan | 23000 | 23000 | 0 |  | Completed
Avila | 2023 | Gutters & downspouts | Clean gutters | 0700 - Roofing | GC | Capital Plan | 23000 | 23000 | 0 |  | Completed
Avila | 2023 | Flashing | Increase by 10,000 for Kickout flashing at hip walls | 0700 - Roofing | GC | Capital Plan | 11000 | 11000 | 0 |  | Completed
Avila | 2023 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Avila | 2023 | Repair / replace wood siding | Replace damaged t 11 siding Increase cost by 30000 in lower window walls and hip walls | 0800 - Exterior Wall | GC | Capital Plan | 66000 | 66000 | 0 |  | Completed
Avila | 2023 | Tuck-pointing | Tuck point and caulk | 0800 - Exterior Wall | GC | Capital Plan | 23000 | 23000 | 0 |  | Completed
Avila | 2023 | Exterior building | changed to Paint the total community 100% paintable | 0800 - Exterior Wall | GC | Capital Plan | 400000 | 400000 | 0 |  | Completed
Avila | 2023 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
Avila | 2023 | storage room doors - exterior | Replace damaged storage room doors | 0800 - Exterior Wall | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Avila | 2023 | Unit Repair | Lender Mandate- The ceiling tiles of units #111 and #2211 were observed to be stained. Replacing the stained ceiling til | 0900 - FF&E in Units | GC | Capital Plan | 1500 | 1500 | 0 |  | Completed
Avila | 2023 | Fire protection | Clean drier vents | 0900 - FF&E in Units | GC | Capital Plan | 24525 | 24525 | 0 |  | Completed
Avila | 2023 | Clubhouse / Office Redecorate (FFE) |  | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Avila | 2023 | Picnic Area Renovation | Add turf soccer field with goals and playground structure on one side. Add pavilion near picnic area, resurface remaini | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 150000 | 150000 | 0 |  | Completed
Avila | 2023 | Pool 1 (West) Renovation | Turf grass areas | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Avila | 2023 | Old Pool House by Pool 1 (West) | Convert pool house to rentable party space, new sliding doors | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avila | 2023 | Pool 2 (East) Renovation | Repair wood fence at pump house, Remove rock and art in red brick planter, replace with turf, Repair grill counter, Repa | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Avila | 2023 | Dog Park | Add dog park fencing (no jumps), signage, & wash station | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Avila | 2023 | Electrical distribution | Repair lighting Electric and anchor weather heads increase weather head repairs by 10,000 due to more locations | 1600 - Electrical | GC | Capital Plan | 22800 | 22800 | 0 |  | Completed
Avila | 2023 | Common area light fixtures | Replace building Wall Packs with LED | 1600 - Electrical | GC | Capital Plan | 32400 | 32400 | 0 |  | Completed
Collin Creek | 2023 | Storm sewer piping | clean out storm drain boxes | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8600 | 8600 | 0 |  | Completed
Collin Creek | 2023 | Concrete pavement | repair pot holes and broken sidewalks | 0200 - Site Utilities & Improvements | GC | Capital Plan | 39000 | 39000 | 0 |  | Completed
Collin Creek | 2023 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Collin Creek | 2023 | ADA parking & curb cuts |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Collin Creek | 2023 | Sidewalks |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Collin Creek | 2023 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Collin Creek | 2023 | Erosion control |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Collin Creek | 2023 | Retaining walls | Replace railroad tie retaining walls | 0200 - Site Utilities & Improvements | GC | Capital Plan | 120000 | 120000 | 0 |  | Completed
Collin Creek | 2023 | Landscaping | Trim Trees and sod building with erosion | 0200 - Site Utilities & Improvements | GC | Capital Plan | 72000 | 72000 | 0 |  | Completed
Collin Creek | 2023 | Landscaping- Primary pool area | Turf or other plants instead of brown mulch and boxwood hedges in planters | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Collin Creek | 2023 | Landscaping- Secondary pool area | Areas by pool- new sod | 0200 - Site Utilities & Improvements | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Collin Creek | 2023 | Resurface swimming pool | resurface pool | 0200 - Site Utilities & Improvements | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Collin Creek | 2023 | Replace swimming pool coping | Replace deck-o-seal on pool | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8600 | 8600 | 0 |  | Completed
Collin Creek | 2023 | Replace swimming pool deck- Primary pool | New decking to replace aggregate | 0200 - Site Utilities & Improvements | GC | Capital Plan | 70000 | 70000 | 0 |  | Completed
Collin Creek | 2023 | Fences & gates - swimming pool | Repair and paint pool fences | 0200 - Site Utilities & Improvements | GC | Capital Plan | 5600 | 5600 | 0 |  | Completed
Collin Creek | 2023 | Pergola | repair and stain all pergola | 0200 - Site Utilities & Improvements | GC | Capital Plan | 3100 | 3100 | 0 |  | Completed
Collin Creek | 2023 | Playground equipment | Replace Fall zone in play ground | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9800 | 9800 | 0 |  | Completed
Collin Creek | 2023 | Picnic areas | replace 2 grills | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8800 | 8800 | 0 |  | Completed
Collin Creek | 2023 | Dumpster enclosures | Dumpster enclosures are scrubs replace with fencing and repair gates | 0200 - Site Utilities & Improvements | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Collin Creek | 2023 | Radon Remediation from lender report | Radon mitigation should be completed by a Texas-licensed contractor. When radon remains elevated over the EPA Action Lev | 0200 - Site Utilities & Improvements | PMC | Capital Plan | 10000 | 40580 | -30580 |  | Completed
Collin Creek | 2023 | Jack & underpin foundations | Place holder for 5 building that show signs of foundation movement | 0300 - Excavation & Foundations | GC | Capital Plan | 150000 | 150000 | 0 |  | Completed
Collin Creek | 2023 | Foundations | Additional scope identified by TAM | 0300 - Excavation & Foundations | GC | Capital Plan | 172728 | 172728 | 0 |  | Completed
Collin Creek | 2023 | Wall framing | Replace damaged gable vents and balcony structure | 0400 - Structure | GC | Capital Plan | 43000 | 43000 | 0 |  | Completed
Collin Creek | 2023 | Roof deck | replace bad decking on roofs | 0400 - Structure | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Collin Creek | 2023 | Repair exterior stair railings | secure railings | 0400 - Structure | GC | Capital Plan | 4200 | 4200 | 0 |  | Completed
Collin Creek | 2023 | Repair balcony framing & decking | repair balcony band boards | 0400 - Structure | GC | Capital Plan | 9700 | 9700 | 0 |  | Completed
Collin Creek | 2023 | Repair patio/balcony railings | secure railings | 0400 - Structure | GC | Capital Plan | 4200 | 4200 | 0 |  | Completed
Collin Creek | 2023 | Expansion joints | clean and seal expansion joints | 0400 - Structure | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Collin Creek | 2023 | Asphalt composite shingle roofing | minor roof repairs | 0700 - Roofing | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Collin Creek | 2023 | Gutters & downspouts | Clean down spouts and gutters | 0700 - Roofing | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Collin Creek | 2023 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Capital Plan | 9000 | 9000 | 0 |  | Completed
Collin Creek | 2023 | Repair / replace cement fiber siding | repair damaged siding | 0800 - Exterior Wall | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Collin Creek | 2023 | Tuck-pointing |  | 0800 - Exterior Wall | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Collin Creek | 2023 | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | 0800 - Exterior Wall | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Collin Creek | 2023 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Capital Plan | 320000 | 320000 | 0 |  | Completed
Collin Creek | 2023 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Capital Plan | 51000 | 51000 | 0 |  | Completed
Collin Creek | 2023 | Interior Update- Classic to Gold | Test smaller initial qty | 0900 - FF&E in Units | PMC | Capital Plan | 500000 | 255167 | 244833 |  | In Progress
Collin Creek | 2023 | Interior Update- Silver to Gold | Test smaller initial qty | 0900 - FF&E in Units | PMC | Capital Plan | 450000 | 229651 | 220349 |  | In Progress
Collin Creek | 2023 | Range Queen |  | 0900 - FF&E in Units | GC | Capital Plan | 29830 | 29830 | 0 |  | Completed
Collin Creek | 2023 | Gym Fitness Equipment | Upgraded package from Comm FIT, Basic also available fo $20k | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 34000 | 13734 | 20266 |  | In Progress
Collin Creek | 2023 | Gym Flooring | Fitdek 8mm roll with install- Quotation # S07142 from Comm FIT | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 11000 | 1957 | 9043 |  | In Progress
Collin Creek | 2023 | Pool furniture- Primary Pool |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 25000 | 27009 | -2009 |  | Completed
Collin Creek | 2023 | Pool enhancements- Primary Pool | 110 & 55 sqft of turf 2 corn hole boards w/custom logo chess/checkers shade structure Budget | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 36000 | 2899 | 33101 |  | In Progress
Collin Creek | 2023 | Pool enhancements- Secondary Pool | New grill New fire pit Convert planters next to pool to turf or pavers | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 30000 | 2415 | 27585 |  | In Progress
Collin Creek | 2023 | Pool area lighting fixtures | Update pole lighting- new fixtures on top and straighten poles | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Collin Creek | 2023 | Fitness center renovation | New exterior windows New flooring-rubber tiles Paint Ventilation/fans Electrical to doors for key Relocate TV above aero | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Collin Creek | 2023 | Laundry room | Built in table instead of floating tables Replace broken window | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 1500 | 1500 | 0 |  | Completed
Collin Creek | 2023 | Laundry room furniture | Furniture in waiting area | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Collin Creek | 2023 | Dog Park upgrades | Move square dog jump paint jumps Wash station for dogs | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Collin Creek | 2023 | Dog Park entrance area | Convert entry area to concrete. Adjust entry level to avoid erosion/wash out and raise gate to avoid contact with ground | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 17000 | 17000 | 0 |  | Completed
Collin Creek | 2023 | Package lockers | Luxer one- from Texas Package Solutions | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 70000 | 0 | 70000 |  | Not Started
Collin Creek | 2023 | Sport court surfacing |  | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 11000 | 11000 | 0 |  | Completed
Collin Creek | 2023 | Gym hallway & Restrooms | Paint Toilets/fixtures New cove base Base | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Collin Creek | 2023 | Electrical distribution |  | 1600 - Electrical | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Collin Creek | 2023 | Common area light fixtures |  | 1600 - Electrical | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Collin Creek | 2023 | Replace breezeway lights |  | 1600 - Electrical | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Collin Creek | 2023 | Contingency- Deferred Maintenance |  | Contingency | Unmarked | Contingency | 290000 | 0 | 290000 |  | Reserve
Collin Creek | 2023 | Contingency- Amenities |  | Contingency | Unmarked | Contingency | 104542 | 0 | 104542 |  | Reserve
Collin Creek | 2023 | Contingency- Unit Upgrades |  | Contingency | PMC | Contingency | 610000 | 0 | 610000 |  | Reserve
Las Colinas Heights | 2023 | Storm sewer piping | clear storm drains, repair drains around pool two, clean and service lift pumps, install drainage is sub-terrain units | 0200 - Site Utilities & Improvements | GC | Capital Plan | 225000 | 225000 | 0 |  | Completed
Las Colinas Heights | 2023 | Concrete pavement | Repair concrete drive From PCA- $3,750- Isolated sections of the concrete pavement were observed to be cracked, settled, | 0200 - Site Utilities & Improvements | GC | Capital Plan | 94000 | 94000 | 0 |  | Completed
Las Colinas Heights | 2023 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Las Colinas Heights | 2023 | Parking equipment | add parking stops by fencing | 0200 - Site Utilities & Improvements | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
Las Colinas Heights | 2023 | ADA parking & curb cuts | add proper signage | 0200 - Site Utilities & Improvements | GC | Capital Plan | 5600 | 5600 | 0 |  | Completed
Las Colinas Heights | 2023 | Curbs & gutters | Sections of the concrete curbing were noted to be chipped, spalled, and damaged. Such sections were noted by the mainten | 0200 - Site Utilities & Improvements | GC | Capital Plan | 1500 | 1500 | 0 |  | Completed
Las Colinas Heights | 2023 | Sidewalks | replace missing expansion boards in sidewalks From PCA- $7,000- Several of the Subject's concrete sidewalk sections hav | 0200 - Site Utilities & Improvements | GC | Capital Plan | 75000 | 75000 | 0 |  | Completed
Las Colinas Heights | 2023 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Las Colinas Heights | 2023 | Erosion control | add dirt around each building | 0200 - Site Utilities & Improvements | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Las Colinas Heights | 2023 | Fences & gates - site perimeter | Repair fence, columns and paint From PCA- $1,000- The concrete fencing on the southwest side was observed to be damaged | 0200 - Site Utilities & Improvements | GC | Capital Plan | 51300 | 51300 | 0 |  | Completed
Las Colinas Heights | 2023 | Fences & gates - site perimeter | Fix Entrance Gates & Access Control | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Las Colinas Heights | 2023 | Access Control | Need more fobs, repair hardware & need software to program | 0200 - Site Utilities & Improvements | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Las Colinas Heights | 2023 | Retaining walls | repair cracks in retaining walls From PCA- $1,000- The retaining walls are in generally good condition, but there are se | 0200 - Site Utilities & Improvements | GC | Capital Plan | 35600 | 35600 | 0 |  | Completed
Las Colinas Heights | 2023 | Landscaping | Tree trim | 0200 - Site Utilities & Improvements | GC | Capital Plan | 42000 | 42000 | 0 |  | Completed
Las Colinas Heights | 2023 | Resurface swimming pool | resurface two of four pools | 0200 - Site Utilities & Improvements | GC | Capital Plan | 61000 | 61000 | 0 |  | Completed
Las Colinas Heights | 2023 | Replace swimming pool coping | replace deck-o-seal on four pools | 0200 - Site Utilities & Improvements | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Las Colinas Heights | 2023 | Replace swimming pool deck | Remove and replace pool deck on two of four pools add missing expansion boards on remaining two pools | 0200 - Site Utilities & Improvements | GC | Capital Plan | 160000 | 160000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair / replace swimming pool pumps | inspect and repair/replace pool pumps | 0200 - Site Utilities & Improvements | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Fences & gates - swimming pool | Repair Pool fence and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Las Colinas Heights | 2023 | Pool Area repairs | From PCA- $7,000- The walls and ceilings of the swimming pool equipment rooms were observed to be damaged. The restrooms | 0200 - Site Utilities & Improvements | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Las Colinas Heights | 2023 | WDO Treatment | From PCA- Subsequent to the Site Visit a WDO inspection was conducted by Terminix Commercial on 2/3/23. Evidence of acti | 0200 - Site Utilities & Improvements | PMC | Capital Plan | 51112 | 15586 | 35526 |  | In Progress
Las Colinas Heights | 2023 | Dumpster enclosures | Repair Dumpsters and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 19800 | 19800 | 0 |  | Completed
Las Colinas Heights | 2023 | Carports / Garages | repair Car ports From PCA- $750- The metal carport by building #12 was observed to be damaged. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Las Colinas Heights | 2023 | Las Colinas Association Estoppel Repairs | See list on separate tab | 0200 - Site Utilities & Improvements | GC | Capital Plan | 330550 | 330550 | 0 |  | Completed
Las Colinas Heights | 2023 | Creek | Clean, and service fountain's in creek | 0200 - Site Utilities & Improvements | GC | Capital Plan | 100000 | 100000 | 0 |  | Completed
Las Colinas Heights | 2023 | Jack & underpin foundations | Buildings 5,11,14,21,19,36,24,6,9,13,19,26 From PCA- $5,000- The foundation exhibits settlement/step cracking in the ext | 0300 - Excavation & Foundations | GC | Capital Plan | 199985 | 199985 | 0 |  | Completed
Las Colinas Heights | 2023 | Concrete deck / floor fill | fill cracks in breezeways | 0400 - Structure | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Las Colinas Heights | 2023 | Roof pad |  | 0400 - Structure | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Las Colinas Heights | 2023 | Roof framing |  | 0400 - Structure | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Las Colinas Heights | 2023 | Roof deck | replace decking and underlayment on roofs | 0400 - Structure | GC | Capital Plan | 17500 | 17500 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair exterior stair treads and stringers |  | 0400 - Structure | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair exterior stair railings |  | 0400 - Structure | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair balcony framing & decking | repair 5 balconies | 0400 - Structure | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair patio/balcony railings | secure all railings | 0400 - Structure | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Tile roofing | remove and reset or replace clay tiles on 30 buildings | 0700 - Roofing | GC | Capital Plan | 65000 | 65000 | 0 |  | Completed
Las Colinas Heights | 2023 | Gutters & downspouts | clean and repin From PCA- $2,000- some of the metal gutters and the metal leaders of building #26 were observed to be d | 0700 - Roofing | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Las Colinas Heights | 2023 | Flashing | replace rotted flashing on doghouse meter rooms | 0700 - Roofing | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Las Colinas Heights | 2023 | Soffit repairs | repair damaged soffits | 0800 - Exterior Wall | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair stucco | repair cracked stucco | 0800 - Exterior Wall | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Las Colinas Heights | 2023 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Capital Plan | 595000 | 595000 | 0 |  | Completed
Las Colinas Heights | 2023 | Repair / replace wood trim | From PCA- $1,000- The wood siding at buildings #10 and #12 was observed to be damaged. | 0800 - Exterior Wall | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Las Colinas Heights | 2023 | Platinum upgrades |  | 0900 - FF&E in Units | PMC | Capital Plan | 650000 | 886629 | -236629 |  | Completed
Las Colinas Heights | 2023 | PFC Units |  | 0900 - FF&E in Units | PMC | Capital Plan | 1600000 | 0 | 1600000 |  | Not Started
Las Colinas Heights | 2023 | Repair Leaking at Unit Interiors | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 676 - evidence of a major lea | 0900 - FF&E in Units | PMC | Capital Plan | 8500 | 56593 | -48093 |  | Completed
Las Colinas Heights | 2023 | Fix Broken handrail in Unit 4425 | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 4425 - Handrail is broken and | 0900 - FF&E in Units | PMC | Capital Plan | 500 | 0 | 500 |  | Not Started
Las Colinas Heights | 2023 | Remove interior mold | From PCA- $2,000- CBRE observed conspicuous mold growth in the areas identified as walls and ceiling of the living room | 0900 - FF&E in Units | PMC | Capital Plan | 2000 | 13316 | -11316 |  | Completed
Las Colinas Heights | 2023 | Remove Interior Mold in Unit 3951 | From PCA- $1,000- Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 3951 - majo | 0900 - FF&E in Units | PMC | Capital Plan | 1000 | 6658 | -5658 |  | Completed
Las Colinas Heights | 2023 | Down Units | From PCA- $10,000- At the time of the site visit, 1 down unit (unit #4335) was observed due to subflooring damage accord | 0900 - FF&E in Units | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Las Colinas Heights | 2023 | Dryer Vents | Clean dryer vents | 0900 - FF&E in Units | GC | Capital Plan | 23175 | 23175 | 0 |  | Completed
Las Colinas Heights | 2023 | Range Queen | Fire stops | 0900 - FF&E in Units | GC | Capital Plan | 50985 | 50985 | 0 |  | Completed
Las Colinas Heights | 2023 | Install GFCI outlet in wet areas | From PCA- $11,750- 50% of the bathrooms of 2-bedroom units had Non-GFCI outlets. | 0900 - FF&E in Units | GC | Capital Plan | 17625 | 17625 | 0 |  | Completed
Las Colinas Heights | 2023 | Clubhouse / Office Remodel | repair and stain office catwalk balcony | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Las Colinas Heights | 2023 | Clubhouse Renovation | Hide cabling Look at replacing hexagonal mirrored tile on walls Kitchen upgrades? | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 25000 | 1720 | 23280 |  | In Progress
Las Colinas Heights | 2023 | Clubhouse Furniture |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 40000 | 2946 | 37054 |  | In Progress
Las Colinas Heights | 2023 | Audio systems |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Las Colinas Heights | 2023 | Fitness Equipment |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 50000 | 50321 | -321 |  | Completed
Las Colinas Heights | 2023 | Pool furniture | To include installation of cabanas | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
Las Colinas Heights | 2023 | Pool area amenities- 2 pools |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 100000 | 4808 | 95192 |  | In Progress
Las Colinas Heights | 2023 | Fitness center renovation | New flooring- rubber or epoxy | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Las Colinas Heights | 2023 | Plumbing- General | 6 buildings with leaks | 1400 - Plumbing | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Las Colinas Heights | 2023 | Electrical distribution | From PCA- $1,000- The Electrical Panel in the swimming pool equipment by the leasing office was observed to be without c | 1600 - Electrical | GC | Capital Plan | 5200 | 5200 | 0 |  | Completed
Las Colinas Heights | 2023 | Switchgear/metering | From PCA- $700- The Electrical Panels in the swimming pool equipment by the leasing office and in the electrical room of | 1600 - Electrical | GC | Capital Plan | 700 | 700 | 0 |  | Completed
Las Colinas Heights | 2023 | Fix/ test the fire riser | From PCA- $2,000- The fire sprinkler riser in building #10 has a red inspection tag. | 1600 - Electrical | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Las Colinas Heights | 2023 | Fix the fire alarm panel | From PCA- $1,000- A trouble indicator light was noted at the fire alarm panel of building #5. | 1600 - Electrical | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Las Colinas Heights | 2023 | Install CO Detector | From PCA- $12,950- Carbon Monoxide detectors were not observed as required. | 1600 - Electrical | GC | Capital Plan | 23310 | 23310 | 0 |  | Completed
Las Colinas Heights | 2023 | Fire suppression | From PCA- $2,000- No fire extinguishers were observed in any visited units. | 1600 - Electrical | GC | Capital Plan | 2500 | 2500 | 0 |  | Completed
Las Colinas Heights | 2023 | Common area light fixtures | Change all 8 ft pole lights to LED | 1600 - Electrical | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Las Colinas Heights | 2023 | Replace breezeway lights | change breezeway lights to LED | 1600 - Electrical | GC | Capital Plan | 42000 | 42000 | 0 |  | Completed
Las Colinas Heights | 2023 | Contingency- Other |  | Contingency | Unmarked | Contingency | 162465 | 0 | 162465 |  | Reserve
Oak Forest | 2023 | Storm sewer piping | clean out storm drain boxes | 0200 - Site Utilities & Improvements | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Oak Forest | 2023 | Concrete pavement | repair pot holes and broken sidewalks | 0200 - Site Utilities & Improvements | GC | Capital Plan | 62000 | 62000 | 0 |  | Completed
Oak Forest | 2023 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Oak Forest | 2023 | ADA parking & curb cuts |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Oak Forest | 2023 | Sidewalks | From PCA- $5,000- The concrete sidewalks and flatwork were observed to be in overall fair to good condition. Blackstone | 0200 - Site Utilities & Improvements | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Oak Forest | 2023 | Landscape irrigation | Inspect and repair irrigation. From PCA- $34,000- The landscaping and irrigation systems appeared to be in fair to ave | 0200 - Site Utilities & Improvements | GC | Capital Plan | 34000 | 34000 | 0 |  | Completed
Oak Forest | 2023 | Erosion control | From PCA- $25,500- Management reported erosion repairs in 2022, and Blackstone observed new rock groundcover at several | 0200 - Site Utilities & Improvements | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Oak Forest | 2023 | Fences & gates - site perimeter | Repair and paint wooden fence and replace sections of damaged metal fence, Repair gate operators and ped gate closers | 0200 - Site Utilities & Improvements | GC | Capital Plan | 185000 | 185000 | 0 |  | Completed
Oak Forest | 2023 | Retaining walls | Tuck Point retaining walls From PCA- $5,000- Blackstone observed cracking and/or missing stone components at retaining w | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Oak Forest | 2023 | Landscaping | Trim Trees and remove dead bushes | 0200 - Site Utilities & Improvements | GC | Capital Plan | 85000 | 85000 | 0 |  | Completed
Oak Forest | 2023 | Resurface swimming pool | Resurface three pools with pebble tech plaster | 0200 - Site Utilities & Improvements | GC | Capital Plan | 81000 | 81000 | 0 |  | Completed
Oak Forest | 2023 | Replace swimming pool coping | Replace deck-o-seal on pools | 0200 - Site Utilities & Improvements | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Oak Forest | 2023 | Fences & gates - swimming pool | Repair and paint pool fences | 0200 - Site Utilities & Improvements | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Oak Forest | 2023 | Pergola | repair and stain all pergolas | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Oak Forest | 2023 | Playground equipment | Replace Fall zone in play ground | 0200 - Site Utilities & Improvements | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Oak Forest | 2023 | Picnic areas | replace 8 grills | 0200 - Site Utilities & Improvements | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Oak Forest | 2023 | Carport and garage | Repair carport damage | 0200 - Site Utilities & Improvements | GC | Capital Plan | 39000 | 39000 | 0 |  | Completed
Oak Forest | 2023 | Dumpster enclosures | Repair dumpster enclosures | 0200 - Site Utilities & Improvements | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Oak Forest | 2023 | Wall framing | Replace damaged gable vents and balcony structure | 0400 - Structure | GC | Capital Plan | 62000 | 62000 | 0 |  | Completed
Oak Forest | 2023 | Roof deck | replace bad decking on roofs | 0400 - Structure | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Oak Forest | 2023 | Repair exterior stair railings | secure railings | 0400 - Structure | GC | Capital Plan | 8300 | 8300 | 0 |  | Completed
Oak Forest | 2023 | Repair balcony framing & decking | repair balcony band boards | 0400 - Structure | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Oak Forest | 2023 | Repair patio/balcony railings | secure railings | 0400 - Structure | GC | Capital Plan | 8300 | 8300 | 0 |  | Completed
Oak Forest | 2023 | Repair catwalks | clean and seal expansion joints | 0400 - Structure | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Oak Forest | 2023 | Asphalt composite shingle roofing | minor roof repairs | 0700 - Roofing | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Oak Forest | 2023 | Gutters & downspouts | Clean down spouts and gutters | 0700 - Roofing | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Oak Forest | 2023 | Sealants & caulking and paint |  | 0700 - Roofing | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Oak Forest | 2023 | Repair / replace wood siding | repair damaged siding | 0800 - Exterior Wall | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Oak Forest | 2023 | Dryer Vents | Clean dryer vents ($45@) & Vent cover replacements as needed ($3000) | 0800 - Exterior Wall | GC | Capital Plan | 34000 | 34000 | 0 |  | Completed
Oak Forest | 2023 | Tuck-pointing |  | 0800 - Exterior Wall | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Oak Forest | 2023 | Repair stucco |  | 0800 - Exterior Wall | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Oak Forest | 2023 | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | 0800 - Exterior Wall | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
Oak Forest | 2023 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Capital Plan | 686000 | 686000 | 0 |  | Completed
Oak Forest | 2023 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Capital Plan | 48000 | 48000 | 0 |  | Completed
Oak Forest | 2023 | Mold remediation | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan c | 0900 - FF&E in Units | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Oak Forest | 2023 | Radon Mitigation Systems: | Lender Mandate- In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the | 0900 - FF&E in Units | PMC | Capital Plan | 10500 | 0 | 10500 |  | Not Started
Oak Forest | 2023 | Range Queen | Fire stops | 0900 - FF&E in Units | GC | Capital Plan | 66120 | 66120 | 0 |  | Completed
Oak Forest | 2023 | Washer/dryer |  | 0900 - FF&E in Units | PMC | Capital Plan | 130000 | 0 | 130000 |  | Not Started
Oak Forest | 2023 | Clubhouse / Office Remodel | Paint accent walls Create built in desk/counter Add glass wall and door to back right office for tenant discussions | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Oak Forest | 2023 | Clubhouse / Office Redecorate (FFE) | New clubhouse furniture | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 80000 | 59297 | 20703 |  | In Progress
Oak Forest | 2023 | Video systems |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 250000 | 40715 | 209285 |  | In Progress
Oak Forest | 2023 | Fitness Equipment |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 30000 | 42136 | -12136 |  | Completed
Oak Forest | 2023 | Pool furniture- Office Pool | New furniture for office pool area only, repurpose existing good furniture to other 2 pools | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 30000 | 49605 | -19605 |  | Completed
Oak Forest | 2023 | Pool area enhancements | Address pool inspection items, upgraded pool deck | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 80000 | 23295 | 56705 |  | In Progress
Oak Forest | 2023 | Pool area enhancements | Activities, turf, etc | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Oak Forest | 2023 | Fitness center renovation | Close 2-3 wall openings between gym and bathroom hallway | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Oak Forest | 2023 | Fitness center adjacent restroom upgrades | Repair/replace partitions, touch up paint and base | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Oak Forest | 2023 | Fire and Sprinklers | replace painted heads in units From PCA- $68,000- The fire and life safety system appeared to be in overall fair to ave | 1600 - Electrical | GC | Capital Plan | 68000 | 68000 | 0 |  | Completed
Oak Forest | 2023 | Contingency- Deferred Maintenance |  | Contingency | Unmarked | Contingency | 466000 | 0 | 466000 |  | Reserve
Oak Forest | 2023 | Contingency- Amenities |  | Contingency | Unmarked | Contingency | 100000 | 0 | 100000 |  | Reserve
Oak Forest | 2023 | Contingency- Unit Upgrades |  | Contingency | Unmarked | Contingency | 2784000 | 0 | 2784000 |  | Reserve
Oak Forest | 2023 | Contingency- Other |  | Contingency | Unmarked | Contingency | 996280 | 0 | 996280 |  | Reserve
Oak Park | 2023 | Club House/Leasing Center Addition/Alteration | Need to replace front door to meet ADA 10k. 20k per post PNA to replace some other doors and update bathroom | Admin/Marketing | Unmarked | Capital Plan | 35000 | 38925 | -3925 |  | Completed
Oak Park | 2023 | Computers | do we need computer? | Admin/Marketing | Unmarked | Capital Plan | 10000 | 1985 | 8015 |  | In Progress
Oak Park | 2023 | Fitness Center & Equipment | Site has new equipment and new floors room has repair needs and still needs paint,Add TVs lights/fans water despenser 15 | Admin/Marketing | Unmarked | Capital Plan | 28000 | 8979 | 19021 |  | In Progress
Oak Park | 2023 | Model Furniture/Finishes | model furniture discussed 15k spaceholder | Admin/Marketing | Unmarked | Capital Plan | 20000 | 7163 | 12837 |  | In Progress
Oak Park | 2023 | Monument Sign | Monument looked good. All building signage looks old and drab. Space holder 15k to replace bldg signs at $85ea | Admin/Marketing | Unmarked | Capital Plan | 8300 | 2042 | 6258 |  | In Progress
Oak Park | 2023 | Office Furniture/Finishes | Refresh on furnitre per Post | Admin/Marketing | Unmarked | Capital Plan | 85000 | 6260 | 78740 |  | In Progress
Oak Park | 2023 | Vehicles/Carts | Have 3 working maint, 1 leasing, budgeting for 2 gators, 1 leasing and 1 maintenance (used) | Admin/Marketing | Unmarked | Capital Plan | 48000 | 125664 | -77664 |  | Completed
Oak Park | 2023 | Common Corridors Rehab | Power wash breezeways - has valet waste | Common Area | Unmarked | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Oak Park | 2023 | Laundry Center | Has two laundry center need to refresh both 5k ea. | Common Area | Unmarked | Capital Plan | 10000 | 5620 | 4380 |  | In Progress
Oak Park | 2023 | Mailboxes | Wish list item from PM, new mail boxes there are 7 mail rooms, Budgteing for 2 replacements 55k. And some in out yrs. A | Common Area | Unmarked | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Oak Park | 2023 | Pool Area Repairs & Equipment | Replaster both pools at leasing offfice pool, refresh grill/pergola area, and repair expansion joints on deck replace gr | Common Area | Unmarked | Capital Plan | 342164 | 454979 | -112815 |  | Completed
Oak Park | 2023 | Pool Furniture/Finishes | Pool furniture needed at leasing pool- space holder 25k | Common Area | Unmarked | Capital Plan | 45000 | 58118 | -13118 |  | Completed
Oak Park | 2023 | Asphalt Milling/Paving/Sealcoat | Restripe some areas in Y1. Y2 fix major potholes and restripe after | Exterior Building & Site Work | Unmarked | Capital Plan | 243500 | 105364 | 138136 |  | In Progress
Oak Park | 2023 | Balconies | Rebuild 12 balconies called out by gc $68k. Pick and pull other balcony and land structural members including replacemen | Exterior Building & Site Work | Unmarked | Capital Plan | 243600 | 148350 | 95250 |  | In Progress
Oak Park | 2023 | Brick Repair/Point-Up | Per bid from Norman. | Exterior Building & Site Work | Unmarked | Capital Plan | 15000 | 310 | 14690 |  | In Progress
Oak Park | 2023 | Concrete Curb/Sidewalk | Sidewalk repairs and grinding 49k per bid from Sunland. Per Post PNA -ADA acess to common areas 16k. Includes $5k in le | Exterior Building & Site Work | Unmarked | Capital Plan | 95000 | 750 | 94250 |  | In Progress
Oak Park | 2023 | Controlled Access Systems | Site uses Gate Wise Need to check Mo. Operating cost Call box is Linear and does not work and needs replaced. Also sev | Exterior Building & Site Work | Unmarked | Capital Plan | 90000 | 20147 | 69853 |  | In Progress
Oak Park | 2023 | Covered Parking & Misc Parking Items | Repair handful of carports in Y1, and then 1 or 2 a year in outyears. | Exterior Building & Site Work | Unmarked | Capital Plan | 55000 | 57741 | -2741 |  | Completed
Oak Park | 2023 | Dog Park | Ali numbers are high ($9K for refresh + $35K for new dogpark). FCP believes they can do add new park for $15K and refres | Exterior Building & Site Work | Unmarked | Capital Plan | 20000 | 34842 | -14842 |  | Completed
Oak Park | 2023 | Dumpster Enclosures | Per bid from Norman. Repair and stain dumpster enclosures | Exterior Building & Site Work | Unmarked | Capital Plan | 32000 | 7966 | 24034 |  | In Progress
Oak Park | 2023 | Erosion Control/Drainage | Repair drainage and add swell back side bldgs. 11-13 $11k. Clean out and test all french drains through out property $15 | Exterior Building & Site Work | Unmarked | Capital Plan | 89000 | 101269 | -12269 |  | Completed
Oak Park | 2023 | Exterior Doors (Other) | Replace Misc mech rm doors | Exterior Building & Site Work | Unmarked | Capital Plan | 5000 | 10036 | -5036 |  | Completed
Oak Park | 2023 | Exterior Lighting | Replace all metal halo building lights and fix 25% of carport lights | Exterior Building & Site Work | Unmarked | Capital Plan | 198710 | 143010 | 55700 |  | In Progress
Oak Park | 2023 | Exterior Paint, Carpentry & Misc Repairs | Bldg. paint looks to be in good shape. Last painted 2017. Need to paint all metal except doors yr1 $201k. Pick and pull | Exterior Building & Site Work | Unmarked | Capital Plan | 1059500 | 938581 | 120919 |  | In Progress
Oak Park | 2023 | Exterior Stairs | ~20% of switch backs on ph2 were replaced. Additional needing replacement. Rebuild 6 SWB landing 60k per Crest. 10k for | Exterior Building & Site Work | Unmarked | Capital Plan | 60000 | 49795 | 10205 |  | In Progress
Oak Park | 2023 | Fireplace & Flue | 95/ unit, need to confirm FP count 608 budgeted | Exterior Building & Site Work | Unmarked | Capital Plan | 173280 | 34688 | 138592 |  | In Progress
Oak Park | 2023 | Foundations & Site Grading | Install Exterior peirs buildings 1,8,6.24 Watch list 2,13,15,26,31 | Exterior Building & Site Work | Unmarked | Capital Plan | 92000 | 0 | 92000 |  | Not Started
Oak Park | 2023 | General Site Fencing | Repair wood perim fencing. Replace middle pool fencing for $24.5K | Exterior Building & Site Work | Unmarked | Capital Plan | 74500 | 124690 | -50190 |  | Completed
Oak Park | 2023 | Grill Station | Refresh of pool grilling areas including replacement of grills included line 24. Removal of gazebo on line 94.This is t | Exterior Building & Site Work | Unmarked | Capital Plan | 40000 | 109552 | -69552 |  | Completed
Oak Park | 2023 | Gutters & Downspouts | Gutter tune up($23k) and add Raindrop gutter guard($131k)to prevent future damage or maintance needs | Exterior Building & Site Work | Unmarked | Capital Plan | 63000 | 35600 | 27400 |  | In Progress
Oak Park | 2023 | Handrail/Railings | Fixing balcony handrails and misc metal fencing repairs | Exterior Building & Site Work | Unmarked | Capital Plan | 76000 | 55360 | 20640 |  | In Progress
Oak Park | 2023 | Concrete Steps - Handrails | Lender mandate- Blackstone observed concrete steps with four or more risers and no handrails at Buildings 9 and 14. Blac | Exterior Building & Site Work | Unmarked | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Oak Park | 2023 | Irrigation | Per Superior Edge evaluated system and found 10k in repairs. Per bid. Includes $34k in lender mandates- The landscaping | Exterior Building & Site Work | Unmarked | Capital Plan | 10000 | 29287 | -19287 |  | Completed
Oak Park | 2023 | Landscape Enhancements | Updgrade front curb appeal, office, pools, and entry drive fence line | Exterior Building & Site Work | Unmarked | Capital Plan | 50000 | 143923 | -93923 |  | Completed
Oak Park | 2023 | Patio Doors/Sliders | replace 5 sliders per yr | Exterior Building & Site Work | Unmarked | Capital Plan | 77000 | 85 | 76915 |  | In Progress
Oak Park | 2023 | Playground & Site Furniture | Top off existing playground. 5k. See line 53 for new playground on Sport court. | Exterior Building & Site Work | Unmarked | Capital Plan | 5000 | 7250 | -2250 |  | Completed
Oak Park | 2023 | Retaining Walls | general tuck point repairs to retaining walls Includes $5k in lender mandates- Blackstone observed cracking and/or miss | Exterior Building & Site Work | Unmarked | Capital Plan | 52000 | 41380 | 10620 |  | In Progress
Oak Park | 2023 | Roof Replacements/Repairs | Roof PM needed on all bldgs- PM also includes fix dryer vent termination on roof, repair busted roof trust in attics- PH | Exterior Building & Site Work | Unmarked | Capital Plan | 156000 | 231180 | -75180 |  | Completed
Oak Park | 2023 | Sports Court | See sports court taband add $25K for iron fence between soccer field and social area | Exterior Building & Site Work | Unmarked | Capital Plan | 227000 | 514328 | -287328 |  | Completed
Oak Park | 2023 | Storm Water Management/Retention Ponds | Maintain storm drains | Exterior Building & Site Work | Unmarked | Capital Plan | 40000 | 17205 | 22795 |  | In Progress
Oak Park | 2023 | Tree/Plant Removal | Cut life safety trees for $60K. All trees removed are bid to be replaced w/ sod. Class B trim and removal of dead limbs | Exterior Building & Site Work | Unmarked | Capital Plan | 202000 | 223962 | -21962 |  | Completed
Oak Park | 2023 | Windows | As needed replacements. Single pain windows | Exterior Building & Site Work | Unmarked | Capital Plan | 35000 | 14100 | 20900 |  | In Progress
Oak Park | 2023 | Vacant Unit Deferred Maintenance |  | Interior Units | Unmarked | Capital Plan | 500000 | 117730 | 382270 |  | In Progress
Oak Park | 2023 | Washers/Dryers |  | Interior Units | Unmarked | Capital Plan | 123000 | 0 | 123000 |  | Not Started
Oak Park | 2023 | Apparent Mold Growth - Unit 110 | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan c | Interior Units | Unmarked | Capital Plan | 2000 | 38 | 1962 |  | In Progress
Oak Park | 2023 | CO/Smoke Detectors | Verify if we need CO detectors for code. 471 have smoke detectors. $35 / unit | MEP | Unmarked | Capital Plan | 16450 | 21264 | -4814 |  | Completed
Oak Park | 2023 | Domestic Water Boilers/Heat Exchangers & Related Work | Replace boiler 1 near building 14, 48.3k PM other 2 boilers 7k Bid from SRT | MEP | Unmarked | Capital Plan | 85300 | 93981 | -8681 |  | Completed
Oak Park | 2023 | Domestic Water Heaters | As needed replacements on PH2&3 review unit walks | MEP | Unmarked | Capital Plan | 105000 | 4620 | 100380 |  | In Progress
Oak Park | 2023 | Drain Clean/Jet Lines/Video | Scrape and clean cast iron sewers in ph1&2 19k. Hyrdo jet all of Ph3 2k | MEP | Unmarked | Capital Plan | 67000 | 42606 | 24394 |  | In Progress
Oak Park | 2023 | Fire Extinguishers | missing or dischaged 5lb fire extinguisher. | MEP | Unmarked | Capital Plan | 16650 | 233339 | -216689 |  | Completed
Oak Park | 2023 | Fire Life Safety Work | Ph3 only PM Riser closets 5k. Panels are still using pots lines to communicate, recommend canceling these to save mone | MEP | Unmarked | Capital Plan | 10000 | 41243 | -31243 |  | Completed
Oak Park | 2023 | Fire Safety Systems | The fire and life safety system appeared to be in overall fair to average condition. The AFSS risers were last inspected | MEP | Unmarked | Capital Plan | 68000 | 5711 | 62289 |  | In Progress
Oak Park | 2023 | HVAC Equipment (HVAC FULL NEW REPLACEMENT) | Based on eval from SRT there are 368 R22/Mixed refrigerant systems. Researching run rates for MT and AW I came up with a | MEP | Unmarked | Capital Plan | 646160 | 639431 | 6729 |  | In Progress
Oak Park | 2023 | HVAC PM | Dryer vent cleaning 75/unit $45k. Replace dryer vents 65 ea. PM all a/c units $120k this include pm service and some par | MEP | Unmarked | Capital Plan | 341470 | 110179 | 231291 |  | In Progress
Oak Park | 2023 | Panel Replacement/GFCI | PH2 has Zinsco panels in all units. Need to replace breakers $346k. Per bid from Shields Electrical Services. 296 units | MEP | Unmarked | Capital Plan | 346005 | 383245 | -37240 |  | Completed
Oak Park | 2023 | PM/Clean Meter Stack | Repalced main meter panels as needed through out hold | MEP | Unmarked | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Oak Park | 2023 | Sewer Systems | Repairs sewer blockages and breaks. bldgs1,2,4,5,6,7,10,12,13,14,15,16,21,26 Bid from SRT. Also researched run rates on | MEP | Unmarked | Capital Plan | 253000 | 2334 | 250666 |  | In Progress
Oak Park | 2023 | Sprinkler Systems | Ph 3 dry heads due for10yr UL testing next yr. if replacement needed after testing 800 ea including SRR @64k waiting met | MEP | Unmarked | Capital Plan | 76000 | 0 | 76000 |  | Not Started
Oak Park | 2023 | Water Piping & Plumbing | Replace (27 pairs) building valves that are barried, rusted, and don’t work $46k. unit 516 had an external repipe that n | MEP | Unmarked | Capital Plan | 401000 | 198926 | 202074 |  | In Progress
Oak Park | 2023 | Wiring | Wiring PM/Cleanup throughout property includes securing meter banks | MEP | Unmarked | Capital Plan | 20000 | 21812 | -1812 |  | Completed
Oak Park | 2023 | Environmental - Asbestos Abatement | For as needed abatement Ph1 only | Miscellaneous | Unmarked | Capital Plan | 210000 | 122414 | 87586 |  | In Progress
Oak Park | 2023 | Environmental - Pest Control Extermination | Waiting on bid for treatment. 35/unit space holder and 15k spaceholder for termite | Miscellaneous | Unmarked | Capital Plan | 21295 | 48447 | -27152 |  | Completed
Oak Park | 2023 | Lead Paint/Radon Remediation | To maintain paint on all ph1 balcony handrails. Yr 1 plan is to paint all railings in the exterior scope. | Miscellaneous | Unmarked | Capital Plan | 70000 | 0 | 70000 |  | Not Started
Oak Park | 2023 | Radon Mitigation Systems | In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the subject propert | Miscellaneous | Unmarked | Capital Plan | 10500 | 0 | 10500 |  | Not Started
Oak Park | 2023 | Maintenance Shop | Clean up maintence shop and storages | Miscellaneous | Unmarked | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Oak Park | 2023 | Structural Repairs | LS Repairs- Fill in potholes in yards 16k.TM to sure up LS balconies includes labor/super/estimated material needed $30k | Miscellaneous | Unmarked | Capital Plan | 46000 | 0 | 46000 |  | Not Started
Oak Park | 2023 | Tools/Miscellaneous Equipment | Misc tools | Miscellaneous | Unmarked | Capital Plan | 10000 | 37248 | -27248 |  | Completed
Oak Park | 2023 | Video Surveillance System | 19 new cameras replacing NVR and reusing some of existing 35k. 25 cameras and NRV per Post PNA | Miscellaneous | Unmarked | Capital Plan | 35150 | 84704 | -49554 |  | Completed
Oak Park | 2023 | Contingency |  | Contingency and Fees | Unmarked | Contingency | 572778 | 0 | 572778 |  | Reserve
Oak Park | 2023 | FCP CM Fees |  | Contingency and Fees | Unmarked | CM Fee | 534592 | 245052 | 289541 |  | Reserve
Sorrento at Tuscan Lakes | 2023 | Concrete pavement | repair pot holes and broken sidewalks | 0200 - Site Utilities & Improvements | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 10500 | 10500 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | ADA parking & curb cuts |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 4800 | 4800 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Fences & gates - site perimeter | Remove vegitation from fence repair and Paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 51000 | 51000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Landscaping | Curb appeal is bad and dated (place Holder) | 0200 - Site Utilities & Improvements | GC | Capital Plan | 150000 | 150000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Resurface swimming pool | resurface pool | 0200 - Site Utilities & Improvements | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Replace swimming pool coping | Replace deck-o-seal on pools | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8200 | 8200 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Replace swimming pool deck | Crack Fill and clean | 0200 - Site Utilities & Improvements | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Fences & gates - swimming pool | Repair and paint pool fence | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8900 | 8900 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Pergola | repair and stain all pergolas | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Carport and garage | Repair carport damage and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 39000 | 39000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Dumpster enclosures | Repair dumpster enclosures and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Roof deck | replace bad decking on roofs | 0400 - Structure | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair exterior stair railings | secure railings | 0400 - Structure | GC | Capital Plan | 8300 | 8300 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair balcony framing & decking | repair balcony band boards | 0400 - Structure | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair patio/balcony railings | secure railings | 0400 - Structure | GC | Capital Plan | 8300 | 8300 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Expansion Joints | clean and seal expansion joints | 0400 - Structure | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Asphalt composite shingle roofing | minor roof repairs | 0700 - Roofing | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Gutters & downspouts | Clean down spouts and gutters | 0700 - Roofing | GC | Capital Plan | 13000 | 13000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Sealants & caulking | Seal where windows meet stucco | 0700 - Roofing | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair / replace cement fiber siding | repair damaged siding | 0800 - Exterior Wall | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Masonry repairs | Presure wash Stone walls | 0800 - Exterior Wall | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair stucco |  | 0800 - Exterior Wall | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | 0800 - Exterior Wall | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Capital Plan | 210000 | 210000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Shutters | Replace bad shutters | 0800 - Exterior Wall | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGc | 683sqft, 1BR 1BA | 0900 - FF&E in Units | GC | Capital Plan | 259134 | 259134 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGe | 779sqft, 1BR 1BA | 0900 - FF&E in Units | GC | Capital Plan | 162437 | 162437 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AGg | 894sqft, 1BR 1BA | 0900 - FF&E in Units | GC | Capital Plan | 22726 | 22726 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 1AZh | 946sqft, 1BR 1BA | 0900 - FF&E in Units | GC | Capital Plan | 128310 | 128310 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGl | 1117sqft, 2BR 2BA | 0900 - FF&E in Units | GC | Capital Plan | 455418 | 455418 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn | 1259sqft, 2BR 2BA | 0900 - FF&E in Units | GC | Capital Plan | 70140 | 70140 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGn1 | 1271sqft, 2BR 2BA | 0900 - FF&E in Units | GC | Capital Plan | 42546 | 42546 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 2CGo | 1367sqft, 2BR 2BA | 0900 - FF&E in Units | GC | Capital Plan | 14646 | 14646 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Unit Upgrade- Unit type 3CGo | 1381sqft, 3BR 2BA | 0900 - FF&E in Units | GC | Capital Plan | 75687 | 75687 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Ceiling Fans | Add to all living rooms | 0900 - FF&E in Units | GC | Capital Plan | 56100 | 56100 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Clubhouse / Office Remodel | New flooring at a minimum, preferably new paint as well Remove window curtains Convert business center counter to booth | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 90000 | 90000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Clubhouse / Office Redecorate (FFE) | Most or all furniture will need to be replaced, it is very dated | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 90000 | 108179 | -18179 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Model Unit | Allowance for small additions/refresh | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 4000 | 8799 | -4799 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Computers | Not needed, allowance for 1 | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 1500 | 2913 | -1413 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Mailboxes | Package locker or Fetch system needed | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Sorrento at Tuscan Lakes | 2023 | Security Camera System | Need at least for entry drive, clubhouse, and amenity coverage | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 20000 | 7426 | 12574 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Pool Remodel | Allowance, the pool area was in decent shape | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 20000 | 10113 | 9887 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Fitness Equipment | In good shape, allowance for minor equipment repairs & replacements | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 10000 | 4664 | 5336 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Pool furniture | Move furniture from Amalfi, supplement with bistro tables/chairs, sectionals, other seating, cabanas | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 30000 | 12636 | 17364 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Fitness center renovation | Allowance, not much needed | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 10000 | 4664 | 5336 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Golf Cart | Repair & replace battery in old leasing cart from Amalfi | 1100- Specialties, Equipment & Furnishings | Unmarked | Capital Plan | 2000 | 1793 | 207 |  | In Progress
Sorrento at Tuscan Lakes | 2023 | Dryer Vent cleaning |  | 1500- HVAC | GC | Capital Plan | 15300 | 15300 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Electrical distribution | repair electric issues with lights | 1600 - Electrical | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Fire and Sprinklers | replace emergency lights | 1600 - Electrical | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Common area light fixtures | Change wall Packs | 1600 - Electrical | GC | Capital Plan | 18720 | 18720 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Replace breezeway lights | Change breezeway lights, landscape lights | 1600 - Electrical | GC | Capital Plan | 32570 | 32570 | 0 |  | Completed
Sorrento at Tuscan Lakes | 2023 | Contingency |  | Contingency & Fees | Unmarked | Contingency | 77226 | 0 | 77226 |  | Reserve
Sorrento at Tuscan Lakes | 2023 | Construction Management Fee |  | Contingency & Fees | Unmarked | CM Fee | 127848 | 0 | 127848 |  | Reserve
The Grand at Hill Street | 2023 | Pavement | Replace Pavers with Stamped stained concrete | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Parking Lot | Extend the parking lot at the northern end of the property for $5k/parking spot to create potentially 26 new spaces | 0200 - Site Utilities & Improvements | GC | Capital Plan | 130000 | 130000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Repair / replace wood trim | Remove and replace damaged wood on garage buildings and paint to match | 0800 - Exterior Wall | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Look at sealing cedar/wood wall partitions |  | 0800 - Exterior Wall | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Fire protection | Fire stops | 0900 - FF&E in Units | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Turf back yards of first floor units that have crushed |  | 0900 - FF&E in Units | GC | Capital Plan | 80000 | 80000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Signage - entry | New monument and building sign for rebrand | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 40000 | 74976 | -34976 |  | Completed
The Grand at Hill Street | 2023 | Signage - site | New property signage throughout for rebrand | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 20000 | 37488 | -17488 |  | Completed
The Grand at Hill Street | 2023 | Clubhouse / Office Remodel | Install motorized door opener on garage style door/window | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Add ceiling fans at ground floor and 2nd floor around c |  | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
The Grand at Hill Street | 2023 | ADA compliance | The accessible designated parking spaces in front of the leasing office were not configured with signage indicating they | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 50 | 0 | 50 |  | Not Started
The Grand at Hill Street | 2023 | Convert Conference room to package room | Includes $15k for renovation expense & $50k for lockers | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 65000 | 65000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Convert current package room to convenience market |  | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Dog Park | Add Pergola /Bench | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Fire Sprinklers | Current inspection tags were not observed on the riser as they were showing their initial installation/inspection sticke | 1600 - Electrical | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Fire extinguishers | Current inspection tags were not observed on the fire extinguishers. Servicing and recertification of the fire extinguis | 1600 - Electrical | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
The Grand at Hill Street | 2023 | Fire alarms | Current inspection tags were not observed on the main control panel as they were showing their initial installation/insp | 1600 - Electrical | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Landscape irrigation | Irrigation drip line look to be questionable in multiple areas test and repair lines | 0200 - Site Utilities & Improvements | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Erosion control | down spouts empty onto river rock drainage, some are short others are long storm water has already caused erosion in so | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Landscaping | the new shrubs look to be struggling to take root, some will need to be replace this summer | 0200 - Site Utilities & Improvements | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Fire Stops |  | 0900 - FF&E in Units | GC | Capital Plan | 37000 | 37000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Signage - entry | Monument Sign | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 30000 | 46414 | -16414 |  | Completed
The Hightone (Allora Denton) | 2023 | Signage - site | Rebrand signage | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 20000 | 108353 | -88353 |  | Completed
The Hightone (Allora Denton) | 2023 | Trash Compactor (Determine Upon Stabilization) | Look at adding to reduce trash collection fees | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Fitness Equipment (Determine Upon Stabilization) | Add rowing machine | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 4000 | 237 | 3763 |  | In Progress
The Hightone (Allora Denton) | 2023 | Pool furniture (Determine Upon Stabilization) | Budget for new chaises since all are wicker, Cabanas, umbrellas | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Carports (Determine Upon Stabilization) | Tenants have requested covered parking, consider as value add | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Retest and Mitigate as needed |  | Radon | GC | Capital Plan | 123000 | 123000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Downspout repairs and gutter installations | Rout downspouts away from the building and onto grass landscaping or concrete sidewalks / pavements to prevent erosion o | Roofing Systems | GC | Capital Plan | 68500 | 68500 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 |  | Reconfigure the walkway accessing the western and southwestern dumpster enclosures to provide a 60-inch turning radius P | Fair Housing | GC | Capital Plan | 17000 | 17000 | 0 |  | Completed
The Hightone (Allora Denton) | 2023 | Dog Park | Dog Park refresh- sail shades, benches, water station | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Storm sewer piping | add stone around storm drains | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Allora Bella Terra | 2024 | Landscape irrigation | inspect and repair Irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 22600 | 22600 | 0 |  | Completed
Allora Bella Terra | 2024 | Fences & gates - site perimeter | Paint perimeter fence | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26500 | 26500 | 0 |  | Completed
Allora Bella Terra | 2024 | Landscaping | Add landscaping in planters around pool. Look at hardier fan palms, can be smaller to reduce cost. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Allora Bella Terra | 2024 | Landscaping- entry & in front of office | PCA- $19,500- Address bare areas throughout property Add seasonal color, add turf where needed | 0200 - Site Utilities & Improvements | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair / replace swimming pool pumps | anti entrapment devices | 0200 - Site Utilities & Improvements | GC | Capital Plan | 12800 | 12800 | 0 |  | Completed
Allora Bella Terra | 2024 | Fences & gates - swimming pool | Paint pool fence | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Allora Bella Terra | 2024 | Outdoor Fireplaces | Repair 2 outdoor fireplaces | 0200 - Site Utilities & Improvements | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Allora Bella Terra | 2024 | Carports / Garages | Repair and paint Garages | 0200 - Site Utilities & Improvements | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
Allora Bella Terra | 2024 | Dumpster enclosures | PCA- $1,500- Repair/replace gate as required Paint enclosure | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Allora Bella Terra | 2024 | Pet yards | paint pet yard fencing | 0200 - Site Utilities & Improvements | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair exterior stair railings | Secure railings | 0400 - Structure | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Allora Bella Terra | 2024 | Expansion Joints | Seal expansion joints | 0400 - Structure | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Allora Bella Terra | 2024 | Asphalt composite shingle roofing | Roof inspection and minor repairs | 0700 - Roofing | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Tile roofing | Repairs to clay tile roofs | 0700 - Roofing | GC | Capital Plan | 4500 | 4500 | 0 |  | Completed
Allora Bella Terra | 2024 | Flashing | Repair flashing over clay tile | 0700 - Roofing | GC | Capital Plan | 4500 | 4500 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair / replace cement fiber siding |  | 0800 - Exterior Wall | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Allora Bella Terra | 2024 | Interior Hallway painting | Breezeway paint | 0800 - Exterior Wall | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Allora Bella Terra | 2024 | Exterior building | Paint community | 0800 - Exterior Wall | GC | Capital Plan | 345000 | 345000 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair / replace wood trim | minor trim replacement | 0800 - Exterior Wall | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Allora Bella Terra | 2024 | Flooring | Replace carpet throughout with LVP | 0900 - FF&E in Units | GC | Capital Plan | 272700 | 272700 | 0 |  | Completed
Allora Bella Terra | 2024 | Pet yard enclosures | About 10 units we could add yards to | 0900 - FF&E in Units | GC | Capital Plan | 58000 | 58000 | 0 |  | Completed
Allora Bella Terra | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 0900 - FF&E in Units | GC | Capital Plan | 36338 | 36338 | 0 |  | Completed
Allora Bella Terra | 2024 | Unit deferred maintenance | Painted sprinkler heads (82 total sprinklers observed in 42 units) | 0900 - FF&E in Units | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Allora Bella Terra | 2024 | Clubhouse / Office Remodel | Iif we are ok with the tuscan, somewhat dated look, there is minimal scope ($10k). | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Allora Bella Terra | 2024 | Clubhouse / Office Furniture | Same as the renovation scope, this can either be minimal (need to reupholster some items) if we keep the theme, or it wi | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Allora Bella Terra | 2024 | Fitness Center Remodel | Misc needs, fitness center looked good | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Allora Bella Terra | 2024 | Fitness Equipment | Good equipment currently, request for cross fit equipment | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Pool Area Remodel | Pool speaker needs repair, add lights in 6 planters. Turf around perimeter, bigger TV under gazebo | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Allora Bella Terra | 2024 | Pool Furniture & Games | Need 4-6 new in pool loungers, lounge seating, games, lounge seating needed by fire place | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Allora Bella Terra | 2024 | Dog Park | Rubber matting for dog wash room, water station, shade structure, benches | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Allora Bella Terra | 2024 | Unit Model Update | Add model furniture in 1 br unit, outside stepping stones in yard? | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Allora Bella Terra | 2024 | Package Lockers | No need, have fetch, but can look at adding package lockers outside of mail area | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Allora Bella Terra | 2024 | Car wash area equipment | Hose or vacuum replacement, misc items | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Allora Bella Terra | 2024 | EV Chargers | Look at level 1 chargers for garages, manager feels they can upcharge | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Allora Bella Terra | 2024 | Repair or Repalce the Fire Extinguisher Cabinets | From MEP Report- The fire extinguisher cabinets throughout the residentail building breezeways are corroding. | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Allora Bella Terra | 2024 | Water pressure regulator / back-flow preventer | Inspect and repair PVB's | 1400 - Plumbing | GC | Capital Plan | 3500 | 3500 | 0 |  | Completed
Allora Bella Terra | 2024 | Scope and Clear the Sewer Lines | From MEP Report- Maintenance records were not provided before the report delvery date | 1400 - Plumbing | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Allora Bella Terra | 2024 | Inspect and Clean Oil-Water Separator | From MEP Report- Maintenance records were not supplied prior to the report delivery date. Therefore, Partner recommends | 1400 - Plumbing | GC | Capital Plan | 3500 | 3500 | 0 |  | Completed
Allora Bella Terra | 2024 | Inspect and Repair Condenser Electrical Connection | From MEP Report- There were multiple electrical connections observed at condensing units where the weather tight flexibl | 1500- HVAC | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Allora Bella Terra | 2024 | Replace the Refrigerant Line Insulation | From MEP Report- The insulation on the refrigerant lines at nearly all of the condensing units is deteriorated and at on | 1500- HVAC | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Allora Bella Terra | 2024 | Electrical distribution | inspect and repair electric to pole lights | 1600 - Electrical | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Allora Bella Terra | 2024 | Perform Infrared (IR) Scanning | From MEP Report- The facility staff was not aware of IR scanning having been performed at the property. | 1600 - Electrical | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Allora Bella Terra | 2024 | Common area light fixtures | Replace pole lights with LED | 1600 - Electrical | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Allora Bella Terra | 2024 | Contingency |  | Contingency & Fees | GC | Contingency | 802262 | 802262 | 0 |  | Reserve
Allora Bella Terra | 2024 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 111150 | 111150 | 0 |  | Reserve
Avonmora | 2024 | Storm sewer piping | Regrade area for proper drainage south west of creek | 84385 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Avonmora | 2024 | ADA parking & curb cuts | strip and repaint ADA ramps | 84201 | GC | Capital Plan | 7800 | 7800 | 0 |  | Completed
Avonmora | 2024 | Sidewalks | repair trip hazards | 84221 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Avonmora | 2024 | Retaining walls | Repair three retaining walls | 84434 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Avonmora | 2024 | Erosion | Backfill areas of erosion in Dog park, and throughout property | 84517 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avonmora | 2024 | Perimeter fencing access control | Add thorny Pyracantha hedges alongside the fence which will grow into a natural barrier Shrubs are $80-$165 each install | 84303 | GC | Capital Plan | 160000 | 160000 | 0 |  | Completed
Avonmora | 2024 | Landscaping | Landscape enhancements in office area and front entrances and 13-8 buildings on Wickersham Zeroscape | 84303 | GC | Capital Plan | 85000 | 85000 | 0 |  | Completed
Avonmora | 2024 | Repair / replace swimming pool pumps | remove splash pad and fill, add turf for sitting area | 84361 | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Avonmora | 2024 | Fences & gates - swimming pool | Pool fence replacement | 84361 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avonmora | 2024 | Pool Deck | Replace pool deck with new stamped stained concrete | 84361 | GC | Capital Plan | 85000 | 85000 | 0 |  | Completed
Avonmora | 2024 | Maintenance Shop Structure | Add Shop for golf carts | 84219 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Avonmora | 2024 | Carports / Garages | repair car ports | 84219 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Avonmora | 2024 | Dumpster enclosures | dumpster repairs | 84111 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Avonmora | 2024 | Jack & underpin foundations | Foundations on 3 buildings | 84435 | GC | Capital Plan | 93000 | 93000 | 0 |  | Completed
Avonmora | 2024 | Repair exterior stair treads and stringers | replace 80 stair treads | 84114 | GC | Capital Plan | 9250 | 9250 | 0 |  | Completed
Avonmora | 2024 | Repair exterior stair railings | repair and secure stair rails | 84121 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Avonmora | 2024 | Repair balcony framing & decking | rebuild three balcony towers | 84104 | GC | Capital Plan | 46000 | 46000 | 0 |  | Completed
Avonmora | 2024 | Asphalt composite shingle roofing | Replace all roofs. Metal, flash, vents, and ridge | 84433 | GC | Capital Plan | 1344500 | 1344500 | 0 |  | Completed
Avonmora | 2024 | Gutters & downspouts | Repair and replace damaged or missing gutters | 84202 | GC | Capital Plan | 8300 | 8300 | 0 |  | Completed
Avonmora | 2024 | Sealants & caulking and paint | sealant for stucco expansion joints | 84433 | GC | Capital Plan | 5300 | 5300 | 0 |  | Completed
Avonmora | 2024 | Repair / replace wood siding | repair loose siding | 84105 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Avonmora | 2024 | Repair stucco | repair damaged stucco | 84206 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Avonmora | 2024 | Exterior painting | repaint buildings 100% paintable | 84101 | GC | Capital Plan | 260000 | 260000 | 0 |  | Completed
Avonmora | 2024 | Repair / replace soffits | repair stairwell soffit | 84113 | GC | Capital Plan | 14500 | 14500 | 0 |  | Completed
Avonmora | 2024 | Repair / replace wood trim | wood replacement | 84105 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Avonmora | 2024 | Shutters | replace 50 pairs of shutters | 84206 | GC | Capital Plan | 9000 | 9000 | 0 |  | Completed
Avonmora | 2024 | Interior Update Placeholder | Paint cabinets and new hardware, Flooring, resurface counters Appliances if possible | 84207 | PMC | Capital Plan | 1140000 | 0 | 1140000 |  | Not Started
Avonmora | 2024 | Sub Floor Repairs | Sub Floors | 84304 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Avonmora | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 84905 | PMC | Capital Plan | 1000 | 0 | 1000 |  | Not Started
Avonmora | 2024 | Clubhouse / Office Remodel | Sitting area by leasing- New lounge furniture, replace shelving with art and TVs. Doors out to pool, pergola outside, s | 84116 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Avonmora | 2024 | Pool Area Remodel | Add plants or metal art in planters Landscape enhancements | 84361 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avonmora | 2024 | Pool Furniture | All new pool furniture and games | 84360 | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Avonmora | 2024 | Dog Park | Add benches and table | 84130 | GC | Capital Plan | 4000 | 4000 | 0 |  | Completed
Avonmora | 2024 | Common area light fixtures | exterior building security lighting are pole lights and need new fixtures | 84112 | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Avonmora | 2024 | exterior lights | replace pool lights and correct electric for pool lights | 84112 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Avonmora | 2024 | Contingency | Contingency Amount | 84510 | GC | Contingency | 20000 | 20000 | 0 |  | Reserve
Bridgepoint | 2024 | Storm sewer piping | Clean out yard drains PCA Item- It was reported that storm water ponds around Building 2 and 6. Partner observed sandbag | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Bridgepoint | 2024 | concrete pavement | Patch and repair damaged areas, replace existing speed bumps with monolithic speed bumps PCA Item- Linear cracking was o | 0200 - Site Utilities & Improvements | GC | Capital Plan | 70000 | 70000 | 0 |  | Completed
Bridgepoint | 2024 | Stripe parking areas | Entire property | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Bridgepoint | 2024 | ADA parking & curb cuts | Repair damaged curbs | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9300 | 9300 | 0 |  | Completed
Bridgepoint | 2024 | Sidewalks | Mortar expansion joints between curb and sidewalk PCA Item- Differential settlement between the curb and the sidewalk w | 0200 - Site Utilities & Improvements | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Bridgepoint | 2024 | Landscape irrigation | Inspect and repair Irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Bridgepoint | 2024 | Erosion control |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 25500 | 25500 | 0 |  | Completed
Bridgepoint | 2024 | Fences & gates - site perimeter | Straighten and add additional side to wooden privacy fence between communities | 0200 - Site Utilities & Improvements | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Bridgepoint | 2024 | Landscaping | remove dead tree stumps on site | 0200 - Site Utilities & Improvements | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Bridgepoint | 2024 | Landscaping | Add river rock in high visibility bare areas Add french drains to address areas with flooding, particularly flooded uni | 0200 - Site Utilities & Improvements | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Bridgepoint | 2024 | Resurface swimming pool | resurface | 0200 - Site Utilities & Improvements | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Bridgepoint | 2024 | Replace swimming pool coping | retile pool | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Bridgepoint | 2024 | Replace swimming pool deck | pressure wash, replace expansion joint materials and deck o seal | 0200 - Site Utilities & Improvements | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Bridgepoint | 2024 | Fences & gates - swimming pool | paint and repair | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9300 | 9300 | 0 |  | Completed
Bridgepoint | 2024 | Pergola court | repair, stain and seal pergolas over grill areas | 0200 - Site Utilities & Improvements | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Bridgepoint | 2024 | Dog Park | Replace 225 ft of fencing, replace bench with moveable bench | 0200 - Site Utilities & Improvements | GC | Capital Plan | 17400 | 17400 | 0 |  | Completed
Bridgepoint | 2024 | Carports / Garages | Repair and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Bridgepoint | 2024 | Dumpster enclosures | Repair door and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Bridgepoint | 2024 | Compactor door out of place | TAM team has bid to repair | 0200 - Site Utilities & Improvements | GC | Capital Plan | 1500 | 1500 | 0 |  | Completed
Bridgepoint | 2024 | Jack & underpin foundations | Placeholder for foundation repairs on "2 buildings" | 0300 - Excavation & Foundations | GC | Capital Plan | 70000 | 70000 | 0 |  | Completed
Bridgepoint | 2024 | Concrete deck / floor fill |  | 0400 - Structure | GC | Capital Plan | 17000 | 17000 | 0 |  | Completed
Bridgepoint | 2024 | Wall framing | seal penetrations in landings | 0400 - Structure | GC | Capital Plan | 1700 | 1700 | 0 |  | Completed
Bridgepoint | 2024 | Repair exterior stair treads and stringers | replace 140 stair treads across property | 0400 - Structure | GC | Capital Plan | 18900 | 18900 | 0 |  | Completed
Bridgepoint | 2024 | Repair exterior stair railings | secure stair railings | 0400 - Structure | GC | Capital Plan | 5100 | 5100 | 0 |  | Completed
Bridgepoint | 2024 | Gutters & downspouts | repitch and clean | 0700 - Roofing | GC | Capital Plan | 17000 | 17000 | 0 |  | Completed
Bridgepoint | 2024 | Flashing | siding flashing | 0700 - Roofing | GC | Capital Plan | 17000 | 17000 | 0 |  | Completed
Bridgepoint | 2024 | Sealants & caulking |  | 0700 - Roofing | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Bridgepoint | 2024 | Repair / replace cement fiber siding |  | 0800 - Exterior Wall | GC | Capital Plan | 3400 | 3400 | 0 |  | Completed
Bridgepoint | 2024 | Dryer Vents | Just cleaned, no cleaning needed. Need to replace some flappers | 0800 - Exterior Wall | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Bridgepoint | 2024 | Exterior building | paint community | 0800 - Exterior Wall | GC | Capital Plan | 209000 | 209000 | 0 |  | Completed
Bridgepoint | 2024 | Repair / replace wood trim | replace rotted trim/fascia/band boards | 0800 - Exterior Wall | GC | Capital Plan | 17000 | 17000 | 0 |  | Completed
Bridgepoint | 2024 | Replace unit entry doors - exterior | Placeholder to replace up to 50 doors throughout property | 0800 - Exterior Wall | GC | Capital Plan | 31500 | 31500 | 0 |  | Completed
Bridgepoint | 2024 | bps1 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 174599 | 174599 | 0 |  | Completed
Bridgepoint | 2024 | bps1u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 40336 | 40336 | 0 |  | Completed
Bridgepoint | 2024 | bpa1 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 160560 | 160560 | 0 |  | Completed
Bridgepoint | 2024 | bpa1u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 38813 | 38813 | 0 |  | Completed
Bridgepoint | 2024 | bpa2 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 524112 | 524112 | 0 |  | Completed
Bridgepoint | 2024 | bpa2u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 153398 | 153398 | 0 |  | Completed
Bridgepoint | 2024 | bpb1 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 260843 | 260843 | 0 |  | Completed
Bridgepoint | 2024 | bpb1u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 127272 | 127272 | 0 |  | Completed
Bridgepoint | 2024 | bpb2 | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 192250 | 192250 | 0 |  | Completed
Bridgepoint | 2024 | bpb2u | See unit upgrade calc for detail | 0900 - FF&E in Units | GC | Capital Plan | 113914 | 113914 | 0 |  | Completed
Bridgepoint | 2024 | Washers & Dryers- Basic front load | From Grid report 28 have connections, 115 have full size W/D, 45 don’t have connections | 0900 - FF&E in Units | GC | Capital Plan | 109250 | 109250 | 0 |  | Completed
Bridgepoint | 2024 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 0900 - FF&E in Units | GC | Capital Plan | 9570 | 9570 | 0 |  | Completed
Bridgepoint | 2024 | Pet Yards | Test 4 per yards on tour path- turf with vinyl or iron fence and privacy screen | 0900 - FF&E in Units | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Bridgepoint | 2024 | Down Unit | PCA Item- Unit 514 was observed to be down due to a recent fire that was started by a candle in the bathroom of the unit | 0900 - FF&E in Units | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Bridgepoint | 2024 | Signage - Entry Monument | Explore adding monument sign | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Bridgepoint | 2024 | Signage - Building identification | New to match paint | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Bridgepoint | 2024 | Clubhouse / Office Remodel | Work with designer on options for Repaint Other finishes including backsplash and counters New art on walls New TV above | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Bridgepoint | 2024 | Clubhouse / Office Furniture | Office chairs and other miscellaneous Items | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Bridgepoint | 2024 | Fitness Center Remodel | Paint, add lighting, add water fountain, add 2 TVs, look at adding fans | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Fitness Equipment | Add more equipment along walkway, add storage | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Bridgepoint | 2024 | Pool Area Remodel | Look at adding storage, other misc landscaping and needs | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Pool Furniture | All new furniture, move current tables and chairs to other areas at property | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Bridgepoint | 2024 | Picnic/Grill Area Remodel | Grill by pool- turf under entire grill area, add gazebo, convert pergola over grill to gazebo | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Bridgepoint | 2024 | Picnic/Grill Furniture | Add picnic tables, chairs, games | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Sports Courts | Convert old tennis court to pickleball- need to resurface and stripe, and add nets, bring surrounding soil back up to sl | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Bridgepoint | 2024 | Dog Park | Water/Wash Station with concrete pad ($6k) Add gazebo or shade sail Furniture next to laundry area | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Bridgepoint | 2024 | Access Control System | Replace keypad on fitness center door | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 500 | 500 | 0 |  | Completed
Bridgepoint | 2024 | Computers | 2 new comupters for clubhouse resident use | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Bridgepoint | 2024 | Security Camera System | No urgent need, would be nice to have for monitoring | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Bridgepoint | 2024 | Fire Extinguishers | PCA Item- Expired certification tags were present at the fire extinguishers in common area breezeways. Servicing and re- | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 1000 | 7663 | -6663 |  | Completed
Bridgepoint | 2024 | Golf Cart | Need maintenance cart | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Bridgepoint | 2024 | Sanitary sewer piping | MEP Item- Industry best practices typically include clearing sanitary waste lines every 18- to 24-months. Partner recomm | 1400 - Plumbing | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Bridgepoint | 2024 | HVAC | Install AC pads on all units sitting on dirt, secure all unit access control panels MEP Item- Split system units - Cond | 1500- HVAC | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Bridgepoint | 2024 | Replace AC condenser | Air conditioners at 40% conversion to 410-a, but not all replaced inside and out. Contingency for replacement of R-22 u | 1500- HVAC | GC | Capital Plan | 210000 | 210000 | 0 |  | Completed
Bridgepoint | 2024 | Electrical distribution | Inspect and repair lighting controllers on all buildings "additional wiring requirements are not included" MEP Item- Ele | 1600 - Electrical | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Bridgepoint | 2024 | Common area light fixtures | Replace wall packs on buildings | 1600 - Electrical | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Bridgepoint | 2024 | Replace additional lights | Replace pole light fixtures | 1600 - Electrical | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
Bridgepoint | 2024 | Contingency |  | Contingency & Fees | GC | Contingency | 90985 | 90985 | 0 |  | Reserve
Bridgepoint | 2024 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 174000 | 174000 | 0 |  | Reserve
Cityscape | 2024 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84303 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Cityscape | 2024 | Concrete pavement | Remove and replace 10,000 LF of failing expansion joint material | 84102 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Cityscape | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84239 | PMC | Capital Plan | 28634 | 44122 | -15487 |  | Completed
Cityscape | 2024 | Clubhouse / Office Remodel | Add controlled access for clubhouse for rentals | 84116 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Cityscape | 2024 | Fitness Center Remodel | Add lighting around perimeter soffit | 84190 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Cityscape | 2024 | Green Initiatives | Green Program | 83515 | GC | Capital Plan | 100000 | 100000 | 0 |  | Completed
Cityscape | 2024 | Contingency | Contingency Amount | 84510 | GC | Contingency | 17163 | 17163 | 0 |  | Reserve
Cityscape | 2024 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 9440 | 9440 | 0 |  | Reserve
Discovery Park | 2024 | Storm sewer piping | add stone around storm drains | 0200 - Site Utilities & Improvements | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Discovery Park | 2024 | Concrete Pavement | From PCA- Replace the large area of prior-repaired concrete pavement near the southwest corner of Building 1 due to sign | 0200 - Site Utilities & Improvements | GC | Capital Plan | 43750 | 43750 | 0 |  | Completed
Discovery Park | 2024 | Concrete Pavement | From PCA- Allowance to repair all areas of random pavement cracks scattered throughout the parking areas | 0200 - Site Utilities & Improvements | GC | Capital Plan | 4500 | 4500 | 0 |  | Completed
Discovery Park | 2024 | Concrete Pavement | From PCA- Allowance to replace the deteriorated sealant in the concrete pavement joints | 0200 - Site Utilities & Improvements | GC | Capital Plan | 21700 | 21700 | 0 |  | Completed
Discovery Park | 2024 | Sidewalk Repair | From PCA- Area of heaving adjacent to the pavement curb near the southwest corner of Building 4 and deteriorated sealant | 0200 - Site Utilities & Improvements | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Discovery Park | 2024 | Sidewalk Railing | From PCA- Install a guardrail along the east edge of the wide sidewalk leading to the maintenance garage where the adjac | 0200 - Site Utilities & Improvements | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Concrete Stairs | From PCA- Due to the muddy, deteriorated landscape conditions at the fire sprinkler riser room of Building 1 discussed i | 0200 - Site Utilities & Improvements | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Accessibility | From PCA- Install edge protection at the base of the guardrail along the west side of the pool deck for FHAA compliance | 0200 - Site Utilities & Improvements | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Accessibility | From PCA- Ramps are provided on the first floor of the buildings to address changes in the slab elevations. Handrails ar | 0200 - Site Utilities & Improvements | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Discovery Park | 2024 | Landscape irrigation | inspect and repair Irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 22600 | 22600 | 0 |  | Completed
Discovery Park | 2024 | Resurface swimming pool | Resurface Pool | 0200 - Site Utilities & Improvements | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Discovery Park | 2024 | Repair / replace swimming pool pumps | anti entrapment devices | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Discovery Park | 2024 | Carports | Look at adding, garages are sold out so there is a need | 0200 - Site Utilities & Improvements | GC | Capital Plan | 152000 | 152000 | 0 |  | Completed
Discovery Park | 2024 | Dumpster enclosures | Paint enclosure | 0200 - Site Utilities & Improvements | GC | Capital Plan | 4500 | 4500 | 0 |  | Completed
Discovery Park | 2024 | Pet yards | paint pet yard fencing | 0200 - Site Utilities & Improvements | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Dog Park Fence | Repair and repaint fence, replace or fix broken gate hinge and bring latches down to FHAA compliant height | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Discovery Park | 2024 | Soffit beam supports appear to be separating in some lo |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Discovery Park | 2024 | Dryer Vents | Clean, fix any flapper valves | 0200 - Site Utilities & Improvements | GC | Capital Plan | 21225 | 21225 | 0 |  | Completed
Discovery Park | 2024 | Garages | Replace at least 6 dented garage doors (G115 is the worst) | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8800 | 8800 | 0 |  | Completed
Discovery Park | 2024 | Foundation Repair | Review all exposed areas and appropriately repair any foundation cracking such as the ones noted near garage G505 on Bui | 0300 - Excavation & Foundations | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Roof deck | Secure Decking while doing roof tune-up | 0400 - Structure | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Asphalt composite shingle roofing | Roof inspection and minor repairs | 0700 - Roofing | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Articulating Lift Rental |  | 0700 - Roofing | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Discovery Park | 2024 | Repair / replace cement fiber siding |  | 0800 - Exterior Wall | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Discovery Park | 2024 | Repair / replace wood trim | minor trim replacement | 0800 - Exterior Wall | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Discovery Park | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 0900 - FF&E in Units | GC | Capital Plan | 30069 | 30069 | 0 |  | Completed
Discovery Park | 2024 | Fire protection | Fix heads with overspray- allowance | 0900 - FF&E in Units | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Discovery Park | 2024 | Unit deferred maintenance | Sub floor repairs | 0900 - FF&E in Units | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Discovery Park | 2024 | Signage - Building identification | Need better signage at leasing office, new garage number signs to replace current faded ones, new window shade branded d | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Signage- Monument | Look at adding monument sign | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Discovery Park | 2024 | Clubhouse / Office Remodel | Placeholder for minor items | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Discovery Park | 2024 | Clubhouse / Office Furniture | Misc items, new pool table? | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Discovery Park | 2024 | Indoor Basketball Area Repairs | Restripe basketball court Fix leak in roof and repair damage at ceiling Repair wall chips behind hoop Fix chipped paint | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Discovery Park | 2024 | Indoor Basketball Area Furniture | Replace 2 long benches | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Discovery Park | 2024 | Fitness Center Remodel | Allowance for minor repairs | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Discovery Park | 2024 | Fitness Equipment | Allowance for supplemental equipment and replacements for cycling room and gym | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Discovery Park | 2024 | Pool Area Remodel | Replace bamboo screen around pool equipment room with better screen, misc repairs and pool equipment | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Discovery Park | 2024 | Pool Furniture | New side tables, new lounge seating or at least replace cushions on existing wicker seating. 1-2 new cabanas or more cha | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Discovery Park | 2024 | Business Center & Office Computers | 1 computer is cracked and needs to be replaced. | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 1500 | 5287 | -3787 |  | Completed
Discovery Park | 2024 | Dog Park | Water/Wash Station with concrete pad ($6k) Shade sail or pergola Look at adding additional Dog Park across road | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Access Control System | Need to add access control at 2 doors from pool to business center and to restrooms | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Discovery Park | 2024 | Rubber Mats for Breezeway transitions for Non-Slip Surf |  | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Discovery Park | 2024 | Cigarette Urns | Per Shelly, look at adding smoking urns where needed to reduce cigarette butts throughout property | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Discovery Park | 2024 | Water pressure regulator / back-flow preventer | inspect and repair PVB's | 1400 - Plumbing | GC | Capital Plan | 3500 | 3500 | 0 |  | Completed
Discovery Park | 2024 | Repair HVAC in fitness center |  | 1500- HVAC | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Discovery Park | 2024 | Electrical distribution | Electric for car ports- Remove if we don’t add car ports | 1600 - Electrical | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Discovery Park | 2024 | Fire and Sprinklers | Add anti freeze to hallway and patio sprinkler systems | 1600 - Electrical | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Discovery Park | 2024 | Common area light fixtures | Lighting for carports | 1600 - Electrical | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Discovery Park | 2024 | Contingency |  | Contingency & Fees | GC | Contingency | 20000 | 20000 | 0 |  | Reserve
Discovery Park | 2024 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 40222 | 40222 | 0 |  | Reserve
Hampton Courts | 2024 | Repair pot holes | Repair pot holes | 7200-0064 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Hampton Courts | 2024 | Stripe Parking | Stripe Parking | 7200-0064 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Hampton Courts | 2024 | Seal Coat asphalt PCA Item- $1,725- Limited surface lin | Seal Coat asphalt PCA Item- $1,725- Limited surface linear cracking and “map” or “alligator” cracking were noted along t | 7200-0064 | GC | Capital Plan | 81000 | 81000 | 0 |  | Completed
Hampton Courts | 2024 | Repair trip hazards PCA Item- $3,000- A significant are | Repair trip hazards PCA Item- $3,000- A significant area of heaved concrete was observed in the sidewalk at the south of | 7200-0064 | GC | Capital Plan | 18500 | 18500 | 0 |  | Completed
Hampton Courts | 2024 | Initial property tree trim around buildings, landscape | Initial property tree trim around buildings, landscape cleanup, entry and tour path enhancements, etc. PCA Item- $5,000- | 7200-0045 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Hampton Courts | 2024 | Anti entrapment devices | Anti entrapment devices | 7200-0057 | GC | Capital Plan | 12800 | 12800 | 0 |  | Completed
Hampton Courts | 2024 | Adjust closers on pool gates | Adjust closers on pool gates | 7200-0069 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Hampton Courts | 2024 | Replace grill | Replace grill | 7200-0061 | GC | Capital Plan | 4000 | 4000 | 0 |  | Completed
Hampton Courts | 2024 | Repair and paint compactor enclosure | Repair and paint compactor enclosure | 7200-0081 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $6,000- Provide accessible path of travel fro | PCA Item- $6,000- Provide accessible path of travel from municipal sidewalk to leasing office entrance. | 7200-0064 | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Hampton Courts | 2024 | replace damaged framing in gable ends | replace damaged framing in gable ends | 7200-0012 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Hampton Courts | 2024 | secure railings | secure railings | 7200-0016 | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Hampton Courts | 2024 | Repair loose pickets | Repair loose pickets | 7200-0016 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Hampton Courts | 2024 | Repair Balconies | Repair Balconies | 7400-0015 | GC | Capital Plan | 9000 | 9000 | 0 |  | Completed
Hampton Courts | 2024 | secure railings | secure railings | 7200-0016 | GC | Capital Plan | 8600 | 8600 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $2,500- At Building A, two exterior stair con | PCA Item- $2,500- At Building A, two exterior stair conditions requiring repair were noted. At the uppermost landing of | 7200-0015 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Hampton Courts | 2024 | Roof tune up include chimney | Roof tune up include chimney | 7200-0002 | GC | Capital Plan | 34000 | 34000 | 0 |  | Completed
Hampton Courts | 2024 | Seal flat roof on club building - option to replace soo | Seal flat roof on club building - option to replace soon to fail skylight. Pushes cost to $30k | 7200-0002 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Hampton Courts | 2024 | secure and clean gutters | secure and clean gutters | 7200-0017 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Hampton Courts | 2024 | Seal edges of delaminated cedar | Seal edges of delaminated cedar | 7200-0012 | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Hampton Courts | 2024 | Clubhouse needs new roof, property received bid for $40 | Clubhouse needs new roof, property received bid for $40-$50k to replace | 7200-0002 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Hampton Courts | 2024 | Replace rotted cedar siding | Replace rotted cedar siding | 7200-0012 | GC | Capital Plan | 27000 | 27000 | 0 |  | Completed
Hampton Courts | 2024 | Paint community - working with Keys | Paint community - working with Keys | 7200-0013 | GC | Capital Plan | 340000 | 340000 | 0 |  | Completed
Hampton Courts | 2024 | Replace rotted fascia and trim - work in conjunction w | Replace rotted fascia and trim - work in conjunction with bat removal | 7200-0012 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Hampton Courts | 2024 | Replace damaged storage doors | Replace damaged storage doors | 7200-0023 | GC | Capital Plan | 17000 | 17000 | 0 |  | Completed
Hampton Courts | 2024 | 99 units with missing GFCIs in the kitchen across diffe | 99 units with missing GFCIs in the kitchen across different buildings and renovation levels - Team to order stock and in | 7400-0040 | PMC | Capital Plan | 29700 | 0 | 29700 |  | Not Started
Hampton Courts | 2024 | 170 units we could add washer dryers - Team to order s | 170 units we could add washer dryers - Team to order stock and install on turn, reno, WO, PM | 7400-0041 | PMC | Capital Plan | 221000 | 0 | 221000 |  | Not Started
Hampton Courts | 2024 | Done every fall, budget for cleaning after takeover | Done every fall, budget for cleaning after takeover | 7200-0041 | GC | Capital Plan | 20700 | 20700 | 0 |  | Completed
Hampton Courts | 2024 | LowPro (Pair covers 4 burner range)- For range top micr | LowPro (Pair covers 4 burner range)- For range top microwaves (assuming current hoods are replaced with OTR microwaves) | 7400-0038 | PMC | Capital Plan | 32258 | 0 | 32258 |  | Not Started
Hampton Courts | 2024 | PCA Item- $500- At vacant Unit E105, standing water was | PCA Item- $500- At vacant Unit E105, standing water was observed on the floor - COMPLETE BEFORE TAKEOVER | 7400-0034 | GC | Capital Plan | 500 | 500 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $1,000- Remove and replace suspect microbial | PCA Item- $1,000- Remove and replace suspect microbial growth-damaged ceiling at Unit A107 bathroom - COMPLETE BEFORE TA | 7400-0032 | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $2,000- Complete flooring/appliance replaceme | PCA Item- $2,000- Complete flooring/appliance replacement at Unit F102.- COMPLETE BEFORE TAKEOVER | 7400-0028 | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Hampton Courts | 2024 | Evidence of water infiltration observed (20)- Units - C | Evidence of water infiltration observed (20)- Units - COMPLETE BEFORE TAKEOVER | 7400-0032 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Hampton Courts | 2024 | Allowance | Allowance | 7400-0053 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Hampton Courts | 2024 | New carpeting in corridor and on stairs, lots of drywal | New carpeting in corridor and on stairs, lots of drywall repairs | 7200-0032 | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Hampton Courts | 2024 | New furniture - Keys | New furniture - Keys | 7200-0027 | PMC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Hampton Courts | 2024 | Paint, lighting, flooring is ok - frost the glass and p | Paint, lighting, flooring is ok - frost the glass and possibly add sound dampening panels to upper walls | 7200-0032 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Hampton Courts | 2024 | New equipment to supplement existing - Keys | New equipment to supplement existing - Keys | 7200-0074 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Hampton Courts | 2024 | Supplement or replace furniture, add games - Keys | Supplement or replace furniture, add games - Keys | 7200-0061 | PMC | Capital Plan | 60000 | 0 | 60000 |  | Not Started
Hampton Courts | 2024 | Look at adding a picnic area or enhance existing grill, | Look at adding a picnic area or enhance existing grill, add gazebo - Keys | 7200-0060 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Hampton Courts | 2024 | Pickleball courts in decent shape, budget for resurfaci | Pickleball courts in decent shape, budget for resurfacing and concrete repair since blue surface is loose in places with | 7200-0059 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Hampton Courts | 2024 | Allowance for Dog Park enhancements - adding enzyme inj | Allowance for Dog Park enhancements - adding enzyme injector | 7200-0048 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Hampton Courts | 2024 | New furniture in model unit - Keys | New furniture in model unit - Keys | 7200-0037 | PMC | Capital Plan | 18000 | 0 | 18000 |  | Not Started
Hampton Courts | 2024 | Needed, would need to find space outside or repurpose l | Needed, would need to find space outside or repurpose laundry room if possible - explore options | 7200-0055 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Hampton Courts | 2024 | 4 new computers needed | 4 new computers needed | 7200-0029 | PMC | Capital Plan | 4000 | 0 | 4000 |  | Not Started
Hampton Courts | 2024 | Have 10 cameras and good coverage, allowance for some a | Have 10 cameras and good coverage, allowance for some additional cameras |  | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Hampton Courts | 2024 | Need storage for maintenance and inventory - maintenanc | Need storage for maintenance and inventory - maintenance shop clean up first. If still not enough space, add used Conex | 7200-0066 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Hampton Courts | 2024 | PCA Item- $2,000- At the front of Building M, the adjac | PCA Item- $2,000- At the front of Building M, the adjacent asphalt parking lot and drive aisle were observed to be satur | 7200-0047 | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $276,000- The maintenance supervisor reported | PCA Item- $276,000- The maintenance supervisor reported that roughly 50% of the domestic water heaters are from the orig | 7200-0007 | PMC | Capital Plan | 80000 | 0 | 80000 |  | Not Started
Hampton Courts | 2024 | PCA Item- $5,000- The clubhouse domestic water heater i | PCA Item- $5,000- The clubhouse domestic water heater is origional; to the 1986 construction. Electric, storage-type wat | 7200-0007 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $690,000- The maintenance supervisor reported | PCA Item- $690,000- The maintenance supervisor reported that roughly 50% of the heat pump condensers are from the origin | 7200-0033 | PMC | Capital Plan | 200000 | 0 | 200000 |  | Not Started
Hampton Courts | 2024 | PCA Item- $8,500- Insulation at the refrigerant lines f | PCA Item- $8,500- Insulation at the refrigerant lines for a majority of the outdoor condensing units were observed to be | 7200-0033 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Hampton Courts | 2024 | PCA Item- $4,000- The ductwork within the clubhouse dis | PCA Item- $4,000- The ductwork within the clubhouse displayed evident signs of dust accumulation, observable upon visibl | 7200-0033 | GC | Capital Plan | 4000 | 4000 | 0 |  | Completed
Hampton Courts | 2024 | HVAC lines are under sized, need to replace. - As neede | HVAC lines are under sized, need to replace. - As needed | 7200-0033 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Hampton Courts | 2024 | inspect and repair electric for exposed electrical line | inspect and repair electric for exposed electrical lines in lighting systems . PCA Item- $3,000- Repair electrical distr | 7200-0040 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Hampton Courts | 2024 | Replace wall packs | Replace wall packs | 7200-0040 | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Hampton Courts | 2024 | Replace pole lights around pool | Replace pole lights around pool | 7200-0040 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Hampton Courts | 2024 | Contingency Amount | Contingency Amount | 7200-0083 | GC | Contingency | 100000 | 100000 | 0 |  | Reserve
Hampton Courts | 2024 | CM Fee | CM Fee | 7200-0084 | GC | CM Fee | 104518 | 104518 | 0 |  | Reserve
Harbor Terrace | 2024 | Initial property tree trim, landscape cleanup, entry an | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 51045-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Harbor Terrace | 2024 | All floor drains have been painted over and should have | All floor drains have been painted over and should have the covers cleaned or replaced | 51130-00 | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Harbor Terrace | 2024 | Restripe parking garage | Restripe parking garage | 51053-00 | GC | Capital Plan | 9700 | 9700 | 0 |  | Completed
Harbor Terrace | 2024 | Equity PCR Item 7.0- ADA-compliant parking spaces are r | Equity PCR Item 7.0- ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibi | 51032-00 | GC | Capital Plan | 300 | 300 | 0 |  | Completed
Marquee | 2024 | Stripe parking areas | Restripe parking lot | 51053-00 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Marquee | 2024 | Landscaping | Tree trim away from buildings | 51043-00 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Marquee | 2024 | Repair / replace swimming pool pumps | Install anti entrapment divise on pool pumps | 51026-00 | GC | Capital Plan | 4300 | 4300 | 0 |  | Completed
Marquee | 2024 | Repair / replace swimming pool heaters | replace hot tub heater | 51026-00 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Marquee | 2024 | Fences & gates - swimming pool | adjust closers on pool gates amd paint pool fence | 51076-00 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Marquee | 2024 | Dumpster enclosures | repair and paint compacter enclosure | 51163-00 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Marquee | 2024 | Parking Pavement & Seal Coat | Equity PCA Item 3.2.2- Linear cracking was noted at the drive aisle on the eastern side of the subject property, adjacen | 51050-00 | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Marquee | 2024 | ADA Signage | Equity PCA Item 7.0- A lack of signage identifying the van-accessible parking space at the leasing office was observed | 51032-00 | GC | Capital Plan | 150 | 150 | 0 |  | Completed
Marquee | 2024 | Landscape Enhancements | Add turf or better landscaping in bare areas | 51045-00 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Marquee | 2024 | Concrete deck / floor fill | Repair cracked areas on catwalks | 51090-00 | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Marquee | 2024 | Repair exterior stair treads and stringers | secure railings | 51072-00 | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Marquee | 2024 | Repair patio/balcony railings | Repair catwalk railings | 51077-00 | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Marquee | 2024 | Gutters & downspouts | secure and clean gutters | 51071-00 | GC | Capital Plan | 19000 | 19000 | 0 |  | Completed
Marquee | 2024 | Flashing | Seal seams on parapet walls | 51062-00 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Marquee | 2024 | Sealants & caulking | Seal seams windows prior to paint | 51062-00 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Marquee | 2024 | Repair stucco | repair remaining areas of delaminated stucco and cracked stucco | 51075-00 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Marquee | 2024 | Interior Hallway painting | Paint interior hallways and staircases | 51080-00 | GC | Capital Plan | 89000 | 89000 | 0 |  | Completed
Marquee | 2024 | Exterior building | Paint community Using Elastomaric paint Equity PCA Item 4.3.1- Exterior paint appeared to be in fair condition. The rec | 51080-00 | GC | Capital Plan | 250000 | 250000 | 0 |  | Completed
Marquee | 2024 | Replace unit entry doors - exterior | Replace 28 back doors | 51073-00 | GC | Capital Plan | 70800 | 70800 | 0 |  | Completed
Marquee | 2024 | Interior Update Placeholder | Match renovated units with upcoming available classic units | 51150-00 | PMC | Capital Plan | 112000 | 22164 | 89836 |  | In Progress
Marquee | 2024 | Smoke & CO detectors | Per LADBS Declaration- Required complaince with Section 91.8603 LAMC Either confirm they are already installed or plan f | 51993-01 | PMC | Capital Plan | 11800 | 0 | 11800 |  | Not Started
Marquee | 2024 | Impact Glazing/Film for Sliding Glass Doors | Per LADBS Declaration- Required complaince with Section 96.302 LAMC Contingency for roughly 15-20 sliding doors in Build | 51073-00 | PMC | Capital Plan | 5000 | 4800 | 200 |  | In Progress
Marquee | 2024 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 51993-01 | PMC | Capital Plan | 11797 | 855 | 10943 |  | In Progress
Marquee | 2024 | Water Savings Project | Echelon proposal for water savings devices | 51158-00 | PMC | Capital Plan | 138000 | 21858 | 116142 |  | In Progress
Marquee | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 51180-00 | PMC | Capital Plan | 2000 | 9210 | -7210 |  | Completed
Marquee | 2024 | Clubhouse / Office Remodel | No needs, flooring ok, misc amount for repairs and paint if needed | 51169-00 | PMC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Marquee | 2024 | Clubhouse / Office Furniture | Allowance for supplemental items | 51169-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Marquee | 2024 | Fitness Center Remodel | No needs, flooring ok, misc amount for repairs and paint if needed | 51160-00 | PMC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Marquee | 2024 | Fitness Equipment | Replace treadmill, supplemental items | 51028-00 | PMC | Capital Plan | 8000 | 1581 | 6419 |  | In Progress
Marquee | 2024 | Pool & Spa Area Remodel | Add shade screens to each area along parking lot fence, possibly add turf in planter areas. | 51160-00 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Marquee | 2024 | Pool & Spa Area Furniture & Games | Match furniture style in main pool area, possibly move some irems from pool to spa area | 51011-00 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Marquee | 2024 | Termite treatment & Repairs | Refer to Orkin WDIR dated 9/25/24 for details | 51992-00 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Marquee | 2024 | Unit Model Update | New furniture in model unit, definitely enhance lighting in model | 51160-05 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Marquee | 2024 | Mailbox Repairs | Repair broken mailbox doors | 51168-00 | GC | Capital Plan | 1500 | 1500 | 0 |  | Completed
Marquee | 2024 | Security Camera System | Needed, especially at pedestrian gates | 51993-00 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Marquee | 2024 | Golf Cart | Maintenance Cart | 51994-00 | PMC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Marquee | 2024 | Common area water heaters / boilers | Replace two ray pak boilers and one upright 199,000 but heater | 51110-00 | PMC | Capital Plan | 65000 | 0 | 65000 |  | Not Started
Marquee | 2024 | Electrical distribution | Equity PCA Item 5.3- Stab-Lok brand breaker panels manufactured by Federal Pacific Electric (FPE) were observed in appro | 51140-00 | PMC | Capital Plan | 118000 | 8547 | 109453 |  | In Progress
Marquee | 2024 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 61607 | 61607 | 0 |  | Reserve
Marquee | 2024 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 61607 | 61607 | 0 |  | Reserve
Navigator Villas | 2024 | concrete pavement | replace broken curbs | 84221 | GC | Capital Plan | 6250 | 6250 | 0 |  | Completed
Navigator Villas | 2024 | Add Accessible Van Parking Space | The accessible parking space in front of the leasing office is not van-accessible; | 84201 | PMC | Capital Plan | 450 | 13308 | -12858 |  | Completed
Navigator Villas | 2024 | Landscape irrigation | Inspect and repair Irrigation | 84300 | PMC | Capital Plan | 22000 | 4763 | 17237 |  | In Progress
Navigator Villas | 2024 | Landscaping | Add landscaping in planters around pool | 84300 | PMC | Capital Plan | 26000 | 14820 | 11180 |  | In Progress
Navigator Villas | 2024 | Replace swimming pool deck | Presure wash pool deck (reduced to $6,000) | 84095 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Navigator Villas | 2024 | Repair / replace swimming pool pumps | Anti entrapment devices | 84095 | GC | Capital Plan | 12800 | 12800 | 0 |  | Completed
Navigator Villas | 2024 | Fences & gates - swimming pool | Paint pool fence | 84095 | GC | Capital Plan | 8400 | 8400 | 0 |  | Completed
Navigator Villas | 2024 | Playground equipment | Add mulch to playground | 84340 | PMC | Capital Plan | 6200 | 574 | 5626 |  | In Progress
Navigator Villas | 2024 | Carports / Garages | Repair and paint 15 Garage doors | 84219 | GC | Capital Plan | 33000 | 33000 | 0 |  | Completed
Navigator Villas | 2024 | Repair exterior stair railings | Secure railings | 84121 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | Expansion Joints | Seal expansion joints | 84102 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | Asphalt composite shingle roofing | Roof inspection and minor repairs | 84433 | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Navigator Villas | 2024 | Flashing | repair flashing over clay tile | 84433 | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Navigator Villas | 2024 | Repair / replace cement fiber siding | replace bad siding and paint to match | 84105 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | Repair / replace wood trim | Minor trim replacement | 84105 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | 2x2 Duplex A- Classic | See Unit Renovation Calculator for detail | 84207 | PMC | Capital Plan | 5003 | 0 | 5003 |  | Not Started
Navigator Villas | 2024 | 2x2 Duplex A- Renovated | See Unit Renovation Calculator for detail | 84207 | PMC | Capital Plan | 8489 | 0 | 8489 |  | Not Started
Navigator Villas | 2024 | 2x2 TH A- Classic | See Unit Renovation Calculator for detail | 84207 | PMC | Capital Plan | 52319 | 0 | 52319 |  | Not Started
Navigator Villas | 2024 | 2x2 TH A- Classic- Upgraded Flooring Placeholder | See Unit Renovation Calculator for detail | 84207 | PMC | Capital Plan | 43502 | 0 | 43502 |  | Not Started
Navigator Villas | 2024 | 2x2 TH A- Renovated | See Unit Renovation Calculator for detail | 84207 | PMC | Capital Plan | 176906 | 0 | 176906 |  | Not Started
Navigator Villas | 2024 | 2x2 TH B- Classic | See Unit Renovation Calculator for detail | 84207 | PMC | Capital Plan | 68015 | 0 | 68015 |  | Not Started
Navigator Villas | 2024 | 2x2 TH B- Classic- Upgraded Flooring Placeholder | See Unit Renovation Calculator for detail | 84207 | PMC | Capital Plan | 43502 | 0 | 43502 |  | Not Started
Navigator Villas | 2024 | 2x2 TH B- Renovated | See Unit Renovation Calculator for detail | 84207 | PMC | Capital Plan | 168206 | 0 | 168206 |  | Not Started
Navigator Villas | 2024 | Clean Dryer Vents | Dryer Vent Cleaning | 84106 | GC | Capital Plan | 13200 | 13200 | 0 |  | Completed
Navigator Villas | 2024 | Fire Stops | LowPro - For range top microwaves | 84239 | PMC | Capital Plan | 20570 | 48953 | -28383 |  | Completed
Navigator Villas | 2024 | Clubhouse / Office Remodel | No clubhouse, office in good shape. Misc allowance for paint, etc | 84208 | PMC | Capital Plan | 2000 | 28000 | -26000 |  | Completed
Navigator Villas | 2024 | Clubhouse / Office Furniture | Placeholder for misc items. | 84208 | PMC | Capital Plan | 2000 | 4274 | -2274 |  | Completed
Navigator Villas | 2024 | Install sink drain insulation in the fitness area bathr | There is no sink drain insulation provided in the fitness area bathroom. | 84209 | PMC | Capital Plan | 250 | 1918 | -1668 |  | Completed
Navigator Villas | 2024 | Security Camera System | Only cameras on the leasing office and gym, no expressed need for additional cameras, maybe add for package lockers | 84450 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Navigator Villas | 2024 | Replace AC condenser | AC Condenser | 84220 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Navigator Villas | 2024 | Electrical distribution | Inspect and repair electric pole lights | 84210 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Navigator Villas | 2024 | Common area light fixtures | Wall Pack replacement | 84210 | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Navigator Villas | 2024 | Contingency | Contingency Amount | 84510 | GC | Contingency | 20000 | 20000 | 0 |  | Reserve
Navigator Villas | 2024 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 44203 | 44203 | 0 |  | Reserve
Presidium Edgestone | 2024 | Sidewalks | Replace crushed granite path with concrete on front of community 600 LF 4 ft wide | 84115 | GC | Capital Plan | 41200 | 41200 | 0 |  | Completed
Presidium Edgestone | 2024 | Landscape irrigation | Adjust irrigation to not cause erosion to A/C pads | 84302 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Presidium Edgestone | 2024 | Fences & gates - site perimeter | Scrape and Paint perimeter fence. 3700 LF of fence PCA Item- A portion of the perimeter fencing on the south section of | 84205 | GC | Capital Plan | 29600 | 29600 | 0 |  | Completed
Presidium Edgestone | 2024 | Landscaping | Add turf and tree rings with rock to tree lines by rec area and parking lot side outside of pool to prevent erosion | 84303 | GC | Capital Plan | 37300 | 37300 | 0 |  | Completed
Presidium Edgestone | 2024 | Fences & gates - swimming pool | Repair and paint | 84205 | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Presidium Edgestone | 2024 | Pergola court | Pressure wash and seal pavers in seating area | 84105 | GC | Capital Plan | 8700 | 8700 | 0 |  | Completed
Presidium Edgestone | 2024 | Playground equipment | Repair, scrape and paint pet park fence | 84340 | GC | Capital Plan | 6800 | 6800 | 0 |  | Completed
Presidium Edgestone | 2024 | Sidewalks | PCA Item- Potential trip hazards consisting of vertical separation were noted at the walkway southwest of the main build | 84115 | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Presidium Edgestone | 2024 | Drainage | PCA Item- Ponding was observed along the exterior walls the parking garages M and L, south of Building 8. Regrading of t | 84517 | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Presidium Edgestone | 2024 | ADA Parking Signage | PCA Item - ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at th | 84103 | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Presidium Edgestone | 2024 | Repair swimming pool coping | Section of pool coping has separated from the deck, either repair with new sealant or re-set section of coping | 84361 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Presidium Edgestone | 2024 | Add Carports | Add 8 carports to test | 84219 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Presidium Edgestone | 2024 | Repair Corridor Walls | PCA Item- Cracking was observed in several areas of the corridor walls and ceilings throughout Building 1. This appears | 84120 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Presidium Edgestone | 2024 | Sealants & caulking and paint | Cut out and reseal lintels' on garage doors with elastomeric caulk 60 garages | 84113 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Presidium Edgestone | 2024 | Add Shower/Tub ADA compliant grab bars | Seller has completed half of the units, budget for 94 remaining units. All units are 1 bath | 83520 | GC | Capital Plan | 32900 | 32900 | 0 |  | Completed
Presidium Edgestone | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84211 | GC | Capital Plan | 22206 | 22206 | 0 |  | Completed
Presidium Edgestone | 2024 | Fire Lane Gates - Regulatory Compliance | PCA Item- All opticom sensors must work, or gates must remain open. On new and existing buildings, the address must be l | 84239 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Presidium Edgestone | 2024 | Elevator Permits | PCA Item- Current operation permits were not posted in each elevator cab. Property management should schedule re-inspect | 84905 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Presidium Edgestone | 2024 | Fire Riser Inspection | PCA Item- A yellow inspection tag was observed at the fire riser at Building 1 for a defective flow switch. Expired tags | 84239 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Presidium Edgestone | 2024 | Fire Extinguisher Inspection | PCA Item- Expired certification tags were present at the fire extinguishers Servicing and re-certification of the fire e | 84239 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Presidium Edgestone | 2024 | Fire Alarm Certification | PCA Item - A current annual fire alarm certification tag was not present at the fire alarm control panel. According to t | 84239 | PMC | Capital Plan | 2500 | 0 | 2500 |  | Not Started
Presidium Edgestone | 2024 | Green Initiatives | Green Program | 83515 | GC | Capital Plan | 100000 | 100000 | 0 |  | Completed
Presidium Edgestone | 2024 | Contingency | Contingency Amount | 84510 | GC | Contingency | 36551 | 36551 | 0 |  | Reserve
Presidium Edgestone | 2024 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 20103 | 20103 | 0 |  | Reserve
The Arbors | 2024 | Gas, Water, Sanitary Sewer Piping | Active leak on East side of community with temp line to the boilers this will have to be repaired and the gas lines will | 51132-00 | GC | Capital Plan | 200000 | 200000 | 0 |  | Completed
The Arbors | 2024 | Gas Submeter Replacements | Need to replace old submeters, 10% will be inspected each year by Orange County Weights & Measures. Summary from propert | 51200-00 | GC | Capital Plan | 96000 | 96000 | 0 |  | Completed
The Arbors | 2024 | Pavement | East side of community has deteriorated drives that need to be milled and overlayed From PCA- 3.2.1- The concrete draina | 51050-00 | GC | Capital Plan | 108000 | 108000 | 0 |  | Completed
The Arbors | 2024 | Stripe parking areas | Re-stripe From PCA- 3.2.2- The seal coat and stall striping appeared to be in fair condition. Based on the observed cond | 51053-00 | GC | Capital Plan | 14500 | 14500 | 0 |  | Completed
The Arbors | 2024 | Asphalt Coating | West side of community needs to be seal coated and crack fill From PCA- 3.2.2- Damaged pavement consisting of linear cra | 51053-00 | GC | Capital Plan | 49000 | 49000 | 0 |  | Completed
The Arbors | 2024 | Landscaping | Tree trim and landscape maintenance throughout From PCA- 3.2.4- Overgrown trees were observed to be in contact with the | 51043-00 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
The Arbors | 2024 | Landscape irrigation | Inspect and repair | 51046-00 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
The Arbors | 2024 | Fences & gates - site perimeter | Paint Iron fencing on perimeter of community | 51076-00 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
The Arbors | 2024 | Resurface swimming pool | Resurface two hot tubs | 51023-00 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
The Arbors | 2024 | Replace swimming pool coping | Deck o seal both pools | 51021-00 | GC | Capital Plan | 14500 | 14500 | 0 |  | Completed
The Arbors | 2024 | Replace swimming pool deck | Both pool decks need to be cleaned, etched and coated. Replacing decks add $60k totalAt Leasing pool- look at changing e | 51022-00 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
The Arbors | 2024 | Repair / replace swimming pool pumps | Anti entrapment devices | 51026-00 | GC | Capital Plan | 12900 | 12900 | 0 |  | Completed
The Arbors | 2024 | Fences & gates - swimming pool | Repair gates and paint At gym pool- fix exit gate eye level hinge so it doesn't protrude | 51076-00 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
The Arbors | 2024 | Carports / Garages | Replace rotted wood and paint parking buildings Exterior only | 51172-00 | GC | Capital Plan | 95000 | 95000 | 0 |  | Completed
The Arbors | 2024 | Dumpster enclosures | Repair and Paint | 51163-00 | GC | Capital Plan | 9000 | 9000 | 0 |  | Completed
The Arbors | 2024 | ADA Accessibility | From PCA- 7.0- Parking areas that provide self-parking for employees and visitors must provide ADA-compliant parking spa | 51169-00 | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
The Arbors | 2024 | Termite Treatment & Repairs | WDIR treatment and repairs will be required by lender within 60-90 days of closing. Reference Terminix report and quote | 51992-00 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
The Arbors | 2024 | Repair exterior stair railings | Secure rails | 51077-00 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Repair balcony framing & decking | Place Holder to have all balconies inspected and repaired | 51072-00 | GC | Capital Plan | 160000 | 160000 | 0 |  | Completed
The Arbors | 2024 | Repair patio/balcony railings | Secure rails | 51077-00 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
The Arbors | 2024 | Expansion Joints | Re-seal expansions | 51070-00 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Asphalt composite shingle roofing | Reportedly roofs were replaced on unit building 4 years ago however the ancillary buildings were not done. Allowance fo | 51061-00 | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
The Arbors | 2024 | Gutters & downspouts | Clean, re-pitch and resecure gutters | 51071-00 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
The Arbors | 2024 | Flashing | replace damaged z bar on siding replacement | 51062-00 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Sealants & caulking | caulk and seal | 51062-00 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Repair / replace wood siding | Replace rotted siding | 51075-00 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
The Arbors | 2024 | Repair stucco |  | 51075-00 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
The Arbors | 2024 | Interior Hallway painting | Paint hallways and front doors, Stripe stair treads in breezeways to address trip hazards | 51160-00 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
The Arbors | 2024 | Exterior building | Paint exterior From PCA- 4.3.1- The paint finish on the apartment buildings was noted to be chipping and worn. Based on | 51080-00 | GC | Capital Plan | 200000 | 200000 | 0 |  | Completed
The Arbors | 2024 | Repair / replace wood trim | Replace rotted trim and fascia | 51082-00 | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
The Arbors | 2024 | Unit Patio Concrete | From PCA- 3.2.3- Uplifting concrete patio slabs was observed at Units 136, 139, and 107. The upheaval appears to be due, | 51090-00 | GC | Capital Plan | 10500 | 10500 | 0 |  | Completed
The Arbors | 2024 | C02 Dectors | Install CO2 detectors | 51993-01 | PMC | Capital Plan | 7200 | 0 | 7200 |  | Not Started
The Arbors | 2024 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 51993-01 | PMC | Capital Plan | 7656 | 0 | 7656 |  | Not Started
The Arbors | 2024 | Signage - Entry Monument | Refresh 1 sign, replace the other, replace wall banner facing Fairhaven | 51031-00 | PMC | Capital Plan | 15000 | 29576 | -14576 |  | Completed
The Arbors | 2024 | Signage - Site | Refresh | 51032-00 | PMC | Capital Plan | 10000 | 17469 | -7469 |  | Completed
The Arbors | 2024 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 51990-00 | PMC | Capital Plan | 3000 | 10357 | -7357 |  | Completed
The Arbors | 2024 | Leasing Office Remodel | Refresh paint on accent wall to brighten space, flooring, add lighting | 51169-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | Leasing Office Furniture | Ok, small allowance | 51995-00 | PMC | Capital Plan | 2000 | 1243 | 757 |  | In Progress
The Arbors | 2024 | Computers | Allowance for new office computers and software, printer, office supplies | 51995-00 | PMC | Capital Plan | 4000 | 0 | 4000 |  | Not Started
The Arbors | 2024 | Fitness Center Remodel | Fix front door, add lighting, replace fan with something more commercial, add mini split HVAC, new larger TV, add rubber | 51160-00 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
The Arbors | 2024 | Fitness Equipment | Refresh equipment, add stair stepper | 51028-00 | PMC | Capital Plan | 10000 | 8000 | 2000 |  | In Progress
The Arbors | 2024 | Pool Area Remodel- 2 pools | Allowance for lighting, other enhancements | 51011-00 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
The Arbors | 2024 | Pool Furniture- 2 pools | New furniture & games | 51011-00 | GC | Capital Plan | 70000 | 70000 | 0 |  | Completed
The Arbors | 2024 | Picnic/Grill Furniture | Allowance for new grills, furniture & misc items, move concrete furniture from pool to picnic area | 51160-04 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | Sports Courts | Resurface, look at pickleball, replace basketball system if that stays | 51027-00 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
The Arbors | 2024 | Dog Park | Water/Wash Station with concrete pad | 51029-00 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
The Arbors | 2024 | Property Photo Shoot | Professional photos and vdeo of remodeled exterior areas, unit interiors when applicable | 51180-00 | PMC | Capital Plan | 4000 | 5102 | -1102 |  | Completed
The Arbors | 2024 | Access Control System | Add at entry gates and fitness center | 51993-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | Package Lockers | Add package locker system | 51168-00 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
The Arbors | 2024 | Laundry rooms- one on each side | Paint refresh, replace track lighting, resurface or replace counter, look at adding equipment From PCA- 4.3.3- Worn doo | 51166-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | New storage units by leasing office pool | Add 8 new units against car port wall, behind existing storage units | 51998-00 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
The Arbors | 2024 | Tools & Equipment | Maintenance tools, equipment, & inventory | 51998-00 | PMC | Capital Plan | 7000 | 654 | 6346 |  | In Progress
The Arbors | 2024 | Common area water heaters / boilers | 3 Boilers are reported to be original, contingency for replacement. 1 goes out frequently and they have a bid for $21k t | 51110-00 | GC | Capital Plan | 63000 | 63000 | 0 |  | Completed
The Arbors | 2024 | Sanitary sewer piping | Sewer Pipe Jetting | 51134-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
The Arbors | 2024 | HVAC | Contingency for HVAC replacements From PCA- 5.2- While generally reported to be functional, approximately 80% of the uni | 51120-00 | GC | Capital Plan | 75000 | 75000 | 0 |  | Completed
The Arbors | 2024 | Electrical distribution | Place holder to replace Zinsco Load center in each unit ( Zinsco breakers have not been formally recalled however are co | 51140-00 | GC | Capital Plan | 380000 | 380000 | 0 |  | Completed
The Arbors | 2024 | Replace breezeway lights | Replace ceiling lights in breezeways | 51141-00 | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
The Arbors | 2024 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 70064 | 70064 | 0 |  | Reserve
The Arbors | 2024 | Construction Management Fee | CM Fees | 51190-00 | GC | CM Fee | 116966 | 116966 | 0 |  | Reserve
Village at Broadstone | 2024 | Stripe parking areas | Clean parking lot of debris and oil, crack fill 3000lf. Apply one coat of latex sealer and stripe to existing layout. In | 0200 - Site Utilities & Improvements | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Village at Broadstone | 2024 | Compactor Ramp | Build an ADA ramp at the compactor. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Sidewalks | Remove and replace approx 375sf of concrete sidewalk. Perform approx. 40EA grinds at lifted sidewalk seams. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Village at Broadstone | 2024 | Landscape Irrigation & Drainage | Repair, replace and troubleshoot exhisting irrigation system. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 81000 | 81000 | 0 |  | Completed
Village at Broadstone | 2024 | Irrigation Repairs | 4 Rain bird 5000, 15 Rain bird 1806, 6 MP Rotator Nozzles, 33 Rain bird Nozzles, 2 Wireless Rain sensors, 7 zones not ru | 0200 - Site Utilities & Improvements | GC | Capital Plan | 4400 | 4400 | 0 |  | Completed
Village at Broadstone | 2024 | Tree Trim & Shrub Cutback | Trim trees & reduce shrubs where appropriate. Remove dead tree throughout all 3 phases to prevent any future damage to b | 0200 - Site Utilities & Improvements | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Village at Broadstone | 2024 | Landscaping Enhancements | Remove, add plants. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Village at Broadstone | 2024 | Fences & gates - swimming pool | Add fence between pool and grill area, repair broken pool gate latch | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Village at Broadstone | 2024 | Grill stations | Upgrade grill stations with new Bull Outlaw grill heads, granite countertops and gas timers. Repair and paint pergolas. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Village at Broadstone | 2024 | Playground equipment | Add mulch and plastic coat damaged landings | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Village at Broadstone | 2024 | Roof Repairs | Remove rusted nails on pipe boots across the community. Install new rain collars, screws, and seal bottom flanges. Remov | 0700 - Roofing | GC | Capital Plan | 57000 | 57000 | 0 |  | Completed
Village at Broadstone | 2024 | Soffit/roof fascia repair | Repair where failing, building 5 & others | 0800 - Exterior Wall | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Bldg. Exterior Cladding | Repair damaged fiber cement siding and trim. Secure shutters. Repair damaged metal fascia, metal row lock flashing and v | 0800 - Exterior Wall | GC | Capital Plan | 14500 | 14500 | 0 |  | Completed
Village at Broadstone | 2024 | Exterior Paint | Paint one coat of SW Superpaint on the siding, trim, shutters, doors, railings and ammenities. | 0800 - Exterior Wall | GC | Capital Plan | 270000 | 270000 | 0 |  | Completed
Village at Broadstone | 2024 | Shutters | Paint or replace faded shutters | 0800 - Exterior Wall | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Village at Broadstone | 2024 | Window screens | Contingency to remove and replace some of the 1/2 screens on the windows of the residential units and clubhouse. | 0800 - Exterior Wall | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Village at Broadstone | 2024 | A1 | Classic | 0900 - FF&E in Units | GC | Capital Plan | 129331 | 129331 | 0 |  | Completed
Village at Broadstone | 2024 | A2 | Classic | 0900 - FF&E in Units | GC | Capital Plan | 532909 | 532909 | 0 |  | Completed
Village at Broadstone | 2024 | B1 | Classic | 0900 - FF&E in Units | GC | Capital Plan | 148907 | 148907 | 0 |  | Completed
Village at Broadstone | 2024 | B2 | Classic | 0900 - FF&E in Units | GC | Capital Plan | 420525 | 420525 | 0 |  | Completed
Village at Broadstone | 2024 | B3 | Classic | 0900 - FF&E in Units | GC | Capital Plan | 427214 | 427214 | 0 |  | Completed
Village at Broadstone | 2024 | C1 | Classic | 0900 - FF&E in Units | GC | Capital Plan | 272985 | 272985 | 0 |  | Completed
Village at Broadstone | 2024 | A1 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Capital Plan | 45402 | 45402 | 0 |  | Completed
Village at Broadstone | 2024 | A2 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Capital Plan | 184968 | 184968 | 0 |  | Completed
Village at Broadstone | 2024 | B1 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Capital Plan | 47544 | 47544 | 0 |  | Completed
Village at Broadstone | 2024 | B2 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Capital Plan | 139230 | 139230 | 0 |  | Completed
Village at Broadstone | 2024 | B3 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Capital Plan | 125874 | 125874 | 0 |  | Completed
Village at Broadstone | 2024 | C1 | Partial Reno- Flooring | 0900 - FF&E in Units | GC | Capital Plan | 78713 | 78713 | 0 |  | Completed
Village at Broadstone | 2024 | A2 | Premium Reno- SS Appliances & Flooring | 0900 - FF&E in Units | GC | Capital Plan | 11560 | 11560 | 0 |  | Completed
Village at Broadstone | 2024 | B3 | Premium Reno- SS Appliances & Flooring | 0900 - FF&E in Units | GC | Capital Plan | 13986 | 13986 | 0 |  | Completed
Village at Broadstone | 2024 | C1 | Premium Reno- SS Appliances & Flooring | 0900 - FF&E in Units | GC | Capital Plan | 7156 | 7156 | 0 |  | Completed
Village at Broadstone | 2024 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 0900 - FF&E in Units | GC | Capital Plan | 35063 | 35063 | 0 |  | Completed
Village at Broadstone | 2024 | Drier vents | Clean drier vents | 0900 - FF&E in Units | GC | Capital Plan | 22500 | 22500 | 0 |  | Completed
Village at Broadstone | 2024 | Signage - Site | Change signage for leasing hours since they are not open Sundays, add hanging clock for Sunday hours | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 250 | 0 | 250 |  | Not Started
Village at Broadstone | 2024 | Clubhouse / Office Remodel | New flooring, paint in the clubhouse to modernize it, using Bell Apex clubhouse as a target finish level. | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 130000 | 130000 | 0 |  | Completed
Village at Broadstone | 2024 | Clubhouse / Office Furniture | New FF&E | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 70000 | 70000 | 0 |  | Completed
Village at Broadstone | 2024 | Fitness Center Remodel | Add conduit for power and data cables to TVs | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Village at Broadstone | 2024 | Fitness Equipment | Need new equipment, stairstepper, have rack, need more weights | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Village at Broadstone | 2024 | Pool Area Remodel | Move gate/fencing in so that the grill area can be used when the pool is closed, add TV above sink under pool grill perg | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Pool Furniture | New furniture to replace existing strap, new lounge seating, bar stools, cornhole, other games | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Village at Broadstone | 2024 | Picnic/Grill Area Remodel | For 2 grill areas outside of pool-Add full covered pergola over grill | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Village at Broadstone | 2024 | Picnic/Grill Furniture | Add benches by cornhole, misc furniture | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Village at Broadstone | 2024 | Dog Park | Water/Wash Station with concrete pad Shade sail or pergola | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Village at Broadstone | 2024 | Unit Model Update | New furniture in model unit | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Village at Broadstone | 2024 | Correct and Close OpenViolation | PCA Item- $100- Open code violation report by building department (expired permit) should be corrected and closed. | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 100 | 0 | 100 |  | Not Started
Village at Broadstone | 2024 | Fire Sprinklers | PCA Item- $40,818- Replace deficient sprinkler heads, per inspection report. | 1400 - Plumbing | GC | Capital Plan | 40818 | 40818 | 0 |  | Completed
Village at Broadstone | 2024 | Provide Drain Pans for Domestic Hot Water Heaters | From MEPFLS Report- Several domestic water heaters in residential units were observed to be missing drain pans. Partner | 1400 - Plumbing | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Village at Broadstone | 2024 | Scope and Clear Sewer Lines | From MEPFLS Report- Recent scoping and clearing of the sanitary drain lines was not reported; therefore, Partner recomme | 1400 - Plumbing | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Village at Broadstone | 2024 | HVAC Replacements | Cost to replace two units at $5,200/unit | 1500- HVAC | GC | Capital Plan | 10400 | 10400 | 0 |  | Completed
Village at Broadstone | 2024 | Replace Refrigerant Line Insulation | From MEPFLS Report- Insulation at the refrigerant lines at the outdoor condensing units were observed to be deteriorated | 1500- HVAC | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Village at Broadstone | 2024 | Replace all balcony ceiling lights & breezeway lights | Replace dated fixtures | 1600 - Electrical | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Village at Broadstone | 2024 | Fire and Life Safety | Repair pull stations throughout the property. Install a riser room sign where missing, install fire extinguishers and re | 1600 - Electrical | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Common area light fixtures | Possibly replace remaining halogen parking lot pole lights with LED | 1600 - Electrical | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Village at Broadstone | 2024 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 186467 | 186467 | 0 |  | Reserve
Avenues of Kennesaw | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84303 | PMC | Capital Plan | 75000 | 165469 | -90469 |  | Completed
Avenues of Kennesaw | 2025 | Storm sewer piping | Clear drains around buildings | 84385 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Pavement | Repair potholes on both sides of community Equity PCA Item- 3.2.2- Linear cracking, "map", or "alligator | 84204 | GC | Capital Plan | 80000 | 80000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Stripe parking areas | Stripe Parking Areas | 84201 | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Asphalt Coating | Crack fill cracks over 1/2 inch | 84204 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Sidewalks | Remove and replace areas of trip hazards Lender PCA (Walkw | 84115 | GC | Capital Plan | 46000 | 46000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Erosion control | Fill eroded areas around buildings Equity PCA Item- 3.2.4-Significant areas of missing or lost ground cover were noted | 84517 | GC | Capital Plan | 70000 | 70000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Retaining walls | Repair fences on retaining walls Equity PCA Item- 4.1- The segmental retaining walls at the East Aparments contained loo | 84434 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Resurface swimming pool | Resurface both pools, Replace missing pool tile at water line | 84095 | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Replace swimming pool coping | Repair or replace broken coping Lender | 84361 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Replace swimming pool deck | Pressure wash pool decks, , level paver trip hazards | 84361 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Swimming pool lighting | Replace pool lights | 84361 | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Fences & gates - swimming pool | Adjust gates and repair gate latches | 84205 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Outdoor Kitchen | Pressure wash area and allowance for grill repairs or replacement with charcoal | 84203 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Carports / Garages | Repair garage siding and trim Equi | 84219 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Dumpster enclosures | Repair compactor areas | 84111 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | ADA Compliance | Equity PCA Item- 7.0- Reconfigure leasing office restroom for ADA compliance | 83520 | GC | Capital Plan | 4500 | 4500 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Concrete deck / floor fill | Grind and seal cracks in light weight concrete landings | 84430 | GC | Capital Plan | 27000 | 27000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Roof deck | Roof Deck Repairs | 84433 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair exterior stair treads and stringers | Replace 90 wood and concrete stair treads. Replace damaged railing on stair cases. Equity PCA Item- 4.2- The wood-framed | 84114 | GC | Capital Plan | 94000 | 94000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair balcony framing & decking | Repair balconies Equity PCA Item- 4.1- Rout and seal all cracks in the concrete patios. Periodically monitor for further | 84104 | GC | Capital Plan | 150000 | 150000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair patio/balcony railings | Repair balcony railings | 84121 | GC | Capital Plan | 68000 | 68000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Expansion Joints | Property Expansion Joints | 84102 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Asphalt composite shingle roofing | Roof repairs Equity PCA Item- 4.4.1- Allowance for replacement of shingles and possible decking | 84433 | GC | Capital Plan | 190919 | 190919 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Gutters & downspouts | Clean, repitch, and secure gutters. Ongoing gutter cleanout. Equity PCA Item- 4.4.2- Allowance for replacement of gutte | 83439 | GC | Capital Plan | 66000 | 66000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Flashing | Repair damaged flashing | 84433 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Sealants & caulking | Roof Sealants & Caulking | 84433 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair/Replace roof pipe vents | Equity PCA Item- 4.4.1- Allowance for replacement of all pipe penetrations lot wide | 84433 | GC | Capital Plan | 38750 | 38750 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair / replace cement fiber siding | Replace rotted Masonite siding with Hardie on west side Equity PCA Item- 4.3.1- Replacement of deteriorated and damaged | 84206 | GC | Capital Plan | 220000 | 220000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Breezeways - Interior Coordiors | Repair soffits | 84120 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Exterior building | Repaint community, west side will need special process in order to seal Masonite to prevent future delamination | 84101 | GC | Capital Plan | 733600 | 733600 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Repair / replace wood trim | Replace damaged trim Equity PCA Item- 4.5- Allowance to refurbish wood trim and balconies around subject property where | 84105 | GC | Capital Plan | 124000 | 124000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Shutters | Replace damaged shutters | 84206 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Windows | Equity PCA Item- 4.3.2- Phased Replacement of dwelling window units from wood framed to aluminum framed - West Campus Eq | 83436 | GC | Capital Plan | 215740 | 203240 | 12500 |  | In Progress
Avenues of Kennesaw | 2025 | Interior Unit Upgrades | Interior Unit Upgrades | 84207 | GC | Capital Plan | 300585 | 0 | 300585 |  | Not Started
Avenues of Kennesaw | 2025 | Clean Dryer vents | Dryer Vent Cleaning | 84106 | GC | Capital Plan | 39300 | 39300 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Washer & Dryer in Unit | Washer & Dryer Modifications | 82480 | GC | Capital Plan | 493324 | 0 | 493324 |  | Not Started
Avenues of Kennesaw | 2025 | Fire Stops | Mix of Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods and LowPro (Pair covers 4 burner range)- For r | 84239 | PMC | Capital Plan | 61944 | 47962 | 13982 |  | In Progress
Avenues of Kennesaw | 2025 | Unit deferred maintenance | Equity PCA Item- 8.0- Address potential water intrusion, Unit 403 East. Equity PCA Item- 8.0- Address potential microbia | 82460 | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Signage - Entry Monument | Reface or possibly enlarge 2 monument signs | 84290 | PMC | Capital Plan | 25000 | 25062 | -62 |  | Completed
Avenues of Kennesaw | 2025 | Clubhouse / Office Remodel | Minor refresh & repairs | 84208 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Clubhouse / Office Furniture | Misc furniture items | 84208 | PMC | Capital Plan | 20000 | 106226 | -86226 |  | Completed
Avenues of Kennesaw | 2025 | Fitness Center Remodel | Paint and misc repairs | 84190 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Fitness Equipment | Equipment repairs and some new equipment | 84190 | PMC | Capital Plan | 15000 | 3712 | 11288 |  | In Progress
Avenues of Kennesaw | 2025 | Pool Area Remodel | Turf areas around pool | 84361 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Pool Furniture | New furniture at 2 pools | 84360 | PMC | Capital Plan | 70000 | 9000 | 61000 |  | In Progress
Avenues of Kennesaw | 2025 | Sports Courts | Resurface 3 courts, fix net and stripe for pickleball as well, add pergola, seating, etc. | 84390 | GC | Capital Plan | 175000 | 175000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Veritas After School Care | Housing Authority Program (Veritas) - Additional School Room | 84208 | PMC | Capital Plan | 10000 | 53113 | -43113 |  | Completed
Avenues of Kennesaw | 2025 | Mailboxes | Lender PCA (Mailbox Repair): Several mailboxes were noted to contain damaged or missing doors. Repair of the mailboxes i | 84260 | PMC | Capital Plan | 500 | 5894 | -5394 |  | Completed
Avenues of Kennesaw | 2025 | Entry gates | None, can look at adding but there are 4 access drives | 84275 | GC | Capital Plan | 60000 | 0 | 60000 |  | Not Started
Avenues of Kennesaw | 2025 | Security Camera System | Security Cameras | 84450 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Avenues of Kennesaw | 2025 | Water pressure regulator / back-flow preventer | Equity PCA Item- 5.1- Observed water heaters were often not provided with drain pans and lacked discharge piping from th | 84209 | GC | Capital Plan | 52500 | 52500 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Plumbing Repairs | Plumbing Fixture Leaks, Ongoing repairs due to high number of work orders. Plumbing Repairs: Ongoing repair of water lea | 84470 | PMC | Capital Plan | 23000 | 14641 | 8359 |  | In Progress
Avenues of Kennesaw | 2025 | Fire Protection Deficiencies | Equity PCA Item- 5.5.1- General fire protection deficiencies were observed. The observed general deficiencies included | 84211 | PMC | Capital Plan | 4500 | 39243 | -34743 |  | Completed
Avenues of Kennesaw | 2025 | Fire Alarm Deficiencies | Equity PCA Item- 5.5.1- The fire alarm annual inspection report was not provided. Reports often include recommendations | 84211 | PMC | Capital Plan | 9000 | 78487 | -69487 |  | Completed
Avenues of Kennesaw | 2025 | Fire Sprinkler Risers | Equity PCA Item- 5.5.1- The following risers were observed to have missing 5-year riser inspection tags: 500E, 600E, 300 | 84400 | PMC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Avenues of Kennesaw | 2025 | Fire Sprinklers | Equity PCA Item- 5.5.1- General fire sprinkler deficiencies were observed. The observed general deficiencies included da | 84400 | PMC | Capital Plan | 16030 | 600 | 15430 |  | In Progress
Avenues of Kennesaw | 2025 | Radon Remediation | Radon Mitigation | 84905 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Water Intrusion Remediation | The SOW will include replacing bathroom vent fans and cleaning dirty AC coils, removing dry water staining and repaintin | 84905 | GC | Capital Plan | 200000 | 200000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Office Faucet | Office Faucet Replacement | 84209 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Green Program - Echelon Water Savings | Installation of aerators on faucets and shower heads | 83515 | GC | Capital Plan | 42312 | 42312 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Condensate drain overflow sensors | Equity PCA Item- 5.2- The fan coil units were not fitted with condensate drain overflow sensors. As installed, clogged d | 83225 | GC | Capital Plan | 26200 | 26200 | 0 |  | Completed
Avenues of Kennesaw | 2025 | HVAC Preventative Maintenance | Equity PCA Item- 5.2- The fan coil units were observed with dirty coils and filters at Units 318E, 1017W, 303E. Partner | 83225 | GC | Capital Plan | 15750 | 15750 | 0 |  | Completed
Avenues of Kennesaw | 2025 | HVAC Preventative Maintenance | Equity PCA Item- 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | 83225 | GC | Capital Plan | 13100 | 13100 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Electrical distribution | inspect, repair or replace lighting controllers | 84210 | GC | Capital Plan | 33000 | 33000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Common area light fixtures | Replace wall pack lights | 84210 | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Electrical Repairs | Equity PCA Item- 5.3- General electrical deficiencies were observed including GFCI outlets , exit lighting, receptacle c | 84210 | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Emergency Lighting | Equity PCA Item- 5.3- Emergency lights were not installed at any West buildings. Installation of emergency lighting is r | 84239 | GC | Capital Plan | 10800 | 10800 | 0 |  | Completed
Avenues of Kennesaw | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 258304 | 0 | 258304 |  | Reserve
Avenues of Kennesaw | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 271220 | 0 | 271220 |  | Reserve
Azur Aparments | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Storm sewer piping | Replace drainage on pool deck with larger channel drains and connect to proper drain | 0200 - Site Utilities & Improvements | GC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Azur Aparments | 2025 | Pavement | Large areas of asphalt paving Lender PCR Item- $6,000- Several pot holes and areas of “alligatoring”and general deterior | 0200 - Site Utilities & Improvements | GC | Capital Plan | 91000 | 63700 | 27300 |  | In Progress
Azur Aparments | 2025 | Stripe parking areas |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 11000 | 7700 | 3300 |  | In Progress
Azur Aparments | 2025 | Asphalt Coating | Seal coat lot Equity PCA Item 3.2.2- $42,000- The seal coating appeared to be generally worn with several areas of loos | 0200 - Site Utilities & Improvements | GC | Capital Plan | 80000 | 56000 | 24000 |  | In Progress
Azur Aparments | 2025 | ADA parking & curb cuts | Replace ADA signage | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6800 | 4760 | 2040 |  | In Progress
Azur Aparments | 2025 | Landscape irrigation | Inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 29000 | 0 | 29000 |  | Not Started
Azur Aparments | 2025 | Erosion control |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26000 | 0 | 26000 |  | Not Started
Azur Aparments | 2025 | Retaining walls | Replace damaged railroad tie wall | 0200 - Site Utilities & Improvements | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Azur Aparments | 2025 | Resurface swimming pool |  | 0200 - Site Utilities & Improvements | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Azur Aparments | 2025 | Replace swimming pool coping | Deck o seal | 0200 - Site Utilities & Improvements | GC | Capital Plan | 8600 | 0 | 8600 |  | Not Started
Azur Aparments | 2025 | Repair / replace swimming pool pumps | Anti entrapment devices | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6800 | 0 | 6800 |  | Not Started
Azur Aparments | 2025 | Fences & gates - swimming pool | Repair and paint Equity PCA Item 3.2.7- $7,500- Partner observed some areas of damaged fencing along the northwest peri | 0200 - Site Utilities & Improvements | GC | Capital Plan | 9600 | 0 | 9600 |  | Not Started
Azur Aparments | 2025 | Dumpster enclosures | Repair dumpster enclosures | 0200 - Site Utilities & Improvements | GC | Capital Plan | 16000 | 0 | 16000 |  | Not Started
Azur Aparments | 2025 | Accessibility | Lender PCR Item- $1,350- Lack of accessible toilet room at the leasing office including lack of lever hardware, toilet g | 0200 - Site Utilities & Improvements | GC | Capital Plan | 1650 | 0 | 1650 |  | Not Started
Azur Aparments | 2025 | Fences & Gates - Site Perimeter | Lender PCR Item- $7,500- Partner observed some areas of damaged fencing along the northwest perimeter as well as a porti | 0200 - Site Utilities & Improvements | GC | Capital Plan | 7500 | 5250 | 2250 |  | In Progress
Azur Aparments | 2025 | Arbor Realty Trust Deferred Maintenance Items | Items noted from lender inspection, items due 11/11/24 & 4/9/25. Property owner only completing November items | 0200 - Site Utilities & Improvements | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Azur Aparments | 2025 | Concrete deck / floor fill | Entrance landings | 0400 - Structure | GC | Capital Plan | 18000 | 12600 | 5400 |  | In Progress
Azur Aparments | 2025 | Wall framing |  | 0400 - Structure | GC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Azur Aparments | 2025 | Repair exterior stair treads and stringers | Replace bad stair treads | 0400 - Structure | GC | Capital Plan | 26000 | 0 | 26000 |  | Not Started
Azur Aparments | 2025 | Repair exterior stair railings | Repair and Paint | 0400 - Structure | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Azur Aparments | 2025 | Repair balcony framing & decking |  | 0400 - Structure | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Asphalt composite shingle roofing | Minor roof repairs | 0700 - Roofing | GC | Capital Plan | 17000 | 0 | 17000 |  | Not Started
Azur Aparments | 2025 | Gutters & downspouts | Clean gutters | 0700 - Roofing | GC | Capital Plan | 17000 | 0 | 17000 |  | Not Started
Azur Aparments | 2025 | Flashing |  | 0700 - Roofing | GC | Capital Plan | 3400 | 0 | 3400 |  | Not Started
Azur Aparments | 2025 | Sealants & caulking |  | 0700 - Roofing | GC | Capital Plan | 6800 | 0 | 6800 |  | Not Started
Azur Aparments | 2025 | Repair / replace cement fiber siding | Replace damaged siding in breezeways | 0800 - Exterior Wall | GC | Capital Plan | 17000 | 0 | 17000 |  | Not Started
Azur Aparments | 2025 | Tuck-pointing | Tuck point and caulk | 0800 - Exterior Wall | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Azur Aparments | 2025 | Exterior building | Paint Community Lender PCR Item- $62,400- The exterior walls appeared to be in generally good to fair condition. Isolat | 0800 - Exterior Wall | GC | Capital Plan | 208000 | 145600 | 62400 |  | In Progress
Azur Aparments | 2025 | Repair / replace wood trim |  | 0800 - Exterior Wall | GC | Capital Plan | 28000 | 0 | 28000 |  | Not Started
Azur Aparments | 2025 | storage room doors - exterior | Replace damaged storage room doors | 0800 - Exterior Wall | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Clean Drier vents |  | 0900 - FF&E in Units | GC | Capital Plan | 15600 | 0 | 15600 |  | Not Started
Azur Aparments | 2025 | Unit Exhaust Fan | Equity PCA Item 5.2- $500- Apartment 502 was noted to have a missing exhaust fan in one of its bathrooms that did not ha | 0900 - FF&E in Units | GC | Capital Plan | 500 | 0 | 500 |  | Not Started
Azur Aparments | 2025 | Turf private yards | Approximately 96 units with yards that we can turf | 0900 - FF&E in Units | GC | Capital Plan | 86400 | 0 | 86400 |  | Not Started
Azur Aparments | 2025 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 0900 - FF&E in Units | GC | Capital Plan | 10048 | 0 | 10048 |  | Not Started
Azur Aparments | 2025 | Unit deferred maintenance | There are 8 down units- all of Building #16 is down due to fire Appx. 57 units noted to have prior water stains on the d | 0900 - FF&E in Units | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Azur Aparments | 2025 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 2500 | 1750 | 750 |  | In Progress
Azur Aparments | 2025 | Clubhouse / Office Remodel | Flooring & paint ok, look at additional HVAC or insulation in roof since it gets very hot in clubhouse. Misc repairs a | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 10000 | 7000 | 3000 |  | In Progress
Azur Aparments | 2025 | Clubhouse / Office Furniture | New furniture in clubhouse, supplement furniture in office | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 28000 | 12000 |  | In Progress
Azur Aparments | 2025 | Pool Area Remodel | Look at adding shade areas over pool and grill | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Pool Furniture & Games |  | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 40000 | 28000 | 12000 |  | In Progress
Azur Aparments | 2025 | Picnic/Grill Area Remodel | Add grill area with gazebo and furniture by mail area | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Azur Aparments | 2025 | Picnic/Grill Furniture |  | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 10000 | 7000 | 3000 |  | In Progress
Azur Aparments | 2025 | Dog Park | Look at adding more furniture, jumps, shade | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 15000 | 10500 | 4500 |  | In Progress
Azur Aparments | 2025 | Access Control System | Office alarm and restore night drop box for keys needed | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 10000 | 7000 | 3000 |  | In Progress
Azur Aparments | 2025 | Grills | Misc repairs | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Azur Aparments | 2025 | Golf Cart | Need leasing cart | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 9000 | 0 | 9000 |  | Not Started
Azur Aparments | 2025 | Domestic water piping | Insulate main water lines going into buildings Equity PCA Item 5.1- $5,000-The domestic water piping at the central dome | 1400 - Plumbing | GC | Capital Plan | 11000 | 0 | 11000 |  | Not Started
Azur Aparments | 2025 | Separate AC condenser | Separate Condensers to achieve 12 inches between units, add equiptment pads as needed | 1500- HVAC | GC | Capital Plan | 41600 | 0 | 41600 |  | Not Started
Azur Aparments | 2025 | HVAC Condensing Refrigerant Line Insulation | Equity PCA Item 5.2- $7,500- Many of the ground mounted AC condensing units were found to have insulation missing from t | 1500- HVAC | GC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Azur Aparments | 2025 | Electrical distribution | Repair house panels issues | 1600 - Electrical | GC | Capital Plan | 8500 | 0 | 8500 |  | Not Started
Azur Aparments | 2025 | Unit Electrical Panel Repairs | Equity PCA Item 5.3- $5,200- During the inspection it was noted that many of the electrical panels within the apartments | 1600 - Electrical | GC | Capital Plan | 5200 | 0 | 5200 |  | Not Started
Azur Aparments | 2025 | Fire Extinguishers | Lender PCR Item- $1,500- The common fire extinguisher at the resident postal boxes structure had an expired tag from 201 | 1600 - Electrical | GC | Capital Plan | 7100 | 0 | 7100 |  | Not Started
Azur Aparments | 2025 | CO Detectors | Residential units were not provided with CO detectors. Residential units had wood burning fireplaces. Partner recommends | 1600 - Electrical | PMC | Capital Plan | 10400 | 0 | 10400 |  | Not Started
Azur Aparments | 2025 | Contingency |  | Contingency & Fees | GC | Contingency | 329680 | 0 | 329680 |  | Reserve
Azur Aparments | 2025 | Construction Management Fee |  | Contingency & Fees | GC | CM Fee | 77884 | 0 | 77884 |  | Reserve
Cambridge Square | 2025 | Landscape Cleanup and Enhancements | Tree trim | 83307.0 | PMC | Capital Plan | 42500 | 13240 | 29260 |  | In Progress
Cambridge Square | 2025 | Asphalt Coating | Fill asphalt cracks, seal coat | 84204.0 | GC | Capital Plan | 47500 | 0 | 47500 |  | Not Started
Cambridge Square | 2025 | Resurface swimming pool | Two pools - resurface 2 pools | 84095.0 | GC | Capital Plan | 50000 | 15000 | 35000 |  | In Progress
Cambridge Square | 2025 | Pool maintenance | Deck cleaning & Equipment repair/replacement | 84361.0 | GC | Capital Plan | 50000 | 15000 | 35000 |  | In Progress
Cambridge Square | 2025 | Pavement | Replace areas of potholes | 84204.0 | GC | Capital Plan | 36000 | 0 | 36000 |  | Not Started
Cambridge Square | 2025 | Stripe parking areas | Stripe Parking Area | 84201.0 | GC | Capital Plan | 22000 | 0 | 22000 |  | Not Started
Cambridge Square | 2025 | ADA parking & curb cuts | LPCA - Add van accessible parking stall near leasing office | 83520.0 | GC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
Cambridge Square | 2025 | Sidewalks | LPCA (PR-90) - Potential trip hazards consisting of vertical and horizontal separation and significantly cracked and dam | 84115.0 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Cambridge Square | 2025 | Landscape irrigation | Inspect and repair irrigation | 84300.0 | GC | Capital Plan | 22500 | 0 | 22500 |  | Not Started
Cambridge Square | 2025 | Fences & gates - site perimeter | Replace fences between units | 84205.0 | GC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Cambridge Square | 2025 | Dumpster enclosures | Replace exisiting dumpster enclosures with new structures throughout property | 84111.0 | GC | Capital Plan | 45000 | 0 | 45000 |  | Not Started
Cambridge Square | 2025 | Repair exterior stair treads and stringers | Scrap and paint, secure stair treads | 84114.0 | GC | Capital Plan | 8500 | 0 | 8500 |  | Not Started
Cambridge Square | 2025 | Repair exterior stair railings | Scrap and paint, secure stair railings | 84121.0 | GC | Capital Plan | 12500 | 0 | 12500 |  | Not Started
Cambridge Square | 2025 | Repair balcony framing & decking | SB 721 needed, minor repairs included. Anything more extensive will need a change order. Catwalk railing potentially too | 84104.0 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Cambridge Square | 2025 | Repair patio/balcony railings | Scrap and paint, secure | 84121.0 | GC | Capital Plan | 36000 | 0 | 36000 |  | Not Started
Cambridge Square | 2025 | Expansion joints | Seal expansion joints | 84102.0 | GC | Capital Plan | 14000 | 0 | 14000 |  | Not Started
Cambridge Square | 2025 | Asphalt composite shingle roofing | Half of the roofs have been redone recently. Still need to replace 9 roofs throughout property | 84433.0 | GC | Capital Plan | 495000 | 495000 | 0 |  | Completed
Cambridge Square | 2025 | Gutters & downspouts | Secure and clean gutters | 84202.0 | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Cambridge Square | 2025 | Flashing | Flashing around chimneys to be replaced as needed | 84433.0 | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Cambridge Square | 2025 | Sealants & caulking | Roof Sealants and Caulking | 84433.0 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Cambridge Square | 2025 | Repair / replace cement fiber siding | Replace damaged horizontal siding where needed | 84206.0 | GC | Capital Plan | 88500 | 0 | 88500 |  | Not Started
Cambridge Square | 2025 | Repair / replace wood shingles | Replace any damage faux cedar shake | 84206.0 | GC | Capital Plan | 85000 | 0 | 85000 |  | Not Started
Cambridge Square | 2025 | Repair stucco | Repair Exterior Stucco - Keep existing look of property. | 84102.0 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Cambridge Square | 2025 | Exterior building | Paint community LPCA - Select areas of building exteriors were observed to have dryrot damage in locations throughout th | 84101.0 | GC | Capital Plan | 250000 | 0 | 250000 |  | Not Started
Cambridge Square | 2025 | Repair / replace wood trim | Replace rotted fascia and trim | 84105.0 | GC | Capital Plan | 185000 | 0 | 185000 |  | Not Started
Cambridge Square | 2025 | Shutters | Repair/replacement of damaged shutters throughout | 84105.0 | GC | Capital Plan | 45000 | 0 | 45000 |  | Not Started
Cambridge Square | 2025 | WDO | Wood Destroying Organisms- LPCA - Select areas of building exteriors were observed to have dryrot damage in locations th | 83301.0 | PMC | Capital Plan | 2500 | 0 | 2500 |  | Not Started
Cambridge Square | 2025 | Interior Update Placeholder | Contingency for interiors | 84207.0 | PMC | Capital Plan | 225000 | 0 | 225000 |  | Not Started
Cambridge Square | 2025 | Fire Stops | Install Fire Stops | 84239.0 | PMC | Capital Plan | 21105 | 49233 | -28128 |  | Completed
Cambridge Square | 2025 | CO Detectors | Install CO Detectors | 83236.0 | PMC | Capital Plan | 12060 | 0 | 12060 |  | Not Started
Cambridge Square | 2025 | Office Clubhouse | Clubhouse upgrades - Move office to pool clubhouse room. | 84208.0 | GC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Cambridge Square | 2025 | Fitness Center Remodel | Convert other clubhouse (high ceiling) into a fitness center | 84190.0 | GC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Cambridge Square | 2025 | Mailboxes | Current boxes are damaged | 84260.0 | GC | Capital Plan | 46500 | 0 | 46500 |  | Not Started
Cambridge Square | 2025 | Security/ fire alarm systems | Install controlled access system for common areas | 84275.0 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Cambridge Square | 2025 | Seismic Strapping | Seismic Strapping - LPCA - The water heaters lacked seismic bracing straps. Provision of adequate seismic bracing is rec | 84209.0 | GC | Capital Plan | 20100 | 20100 | 0 |  | Completed
Cambridge Square | 2025 | Electrical distribution | Inspect and repair lighting controllers on all buildings | 84210.0 | GC | Capital Plan | 26000 | 0 | 26000 |  | Not Started
Cambridge Square | 2025 | Common area light fixtures | Replace pole lights with LED | 84210.0 | GC | Capital Plan | 28000 | 0 | 28000 |  | Not Started
Cambridge Square | 2025 | Replace breezeway lights | Replace doorway sconces | 84210.0 | GC | Capital Plan | 32100 | 0 | 32100 |  | Not Started
Cambridge Square | 2025 | Contingency | Construction Contingency | 84510.0 | GC | Contingency | 115768 | 0 | 115768 |  | Reserve
Cambridge Square | 2025 | Construction Management Fee | CM Fee | 84505.0 | GC | CM Fee | 121557 | 0 | 121557 |  | Reserve
Candlewood | 2025 | Landscape Cleanup and Enhancements | Item No. 1: Trim trees along the perimeter throughout the site to prevent the accumulation of debris and tree leaves ove | 51043-00 | PMC | Capital Plan | 50000 | 10850 | 39150 |  | In Progress
Candlewood | 2025 | Asphalt Coating | Fill, seal and coat of parking area at back of property. Mix of asphalt and concrete repairs needed (approx 80% asphalt) | 51053-00 | GC | Capital Plan | 173000 | 0 | 173000 |  | Not Started
Candlewood | 2025 | Asphalt Pavement | 3.1.6 - Isolated asphalt cracking was observed in the rear drive aisles and areas near the entrance gates. Repair is rec | 51050-00 | GC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Candlewood | 2025 | Stripe parking areas | Restripe Parking Area including carports. | 51053-00 | GC | Capital Plan | 19000 | 0 | 19000 |  | Not Started
Candlewood | 2025 | Fences & gates - site perimeter | Item No. 4: Allowance for periodic fencing repairs, including property perimeter wood slat fencing and CMU fencing along | 51076-00 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Candlewood | 2025 | Resurface swimming pool | Item No. 6: Allowance to resurface both pools and one spa, including repairing any cracks around the pool decks and repl | 51023-00 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Candlewood | 2025 | Carports / Garages | Significant wood rotting at stand alone carports. Need to replace all rotted wood and fix all damaged stucco on all 3 st | 51172-00 | GC | Capital Plan | 340000 | 0 | 340000 |  | Not Started
Candlewood | 2025 | Storm Sewer Piping | 50% of storm water drains on balconies need to be repaired/replaced due to paint/damage. | 51134-00 | GC | Capital Plan | 25988 | 25988 | 0 |  | Completed
Candlewood | 2025 | Roof framing | Replace/repair any wood rotting on carport roof decking on all 3 stand alone carports. | 51062-00 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Candlewood | 2025 | Roof deck | Roof Deck Repairs | 51062-00 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Candlewood | 2025 | Repair balcony framing & decking | 3.2.7 - The balcony deck surface at unit A303 was buckled and standing water observed. The deck surface should be repair | 51072-00 | GC | Capital Plan | 2250 | 2250 | 0 |  | Completed
Candlewood | 2025 | Roof Drainage | 3.2.9 - Areas of roof ponding were noted on all roofs. Although ponding may decrease the useful life of the roof, deckin | 51062-00 | GC | Capital Plan | 2250 | 2250 | 0 |  | Completed
Candlewood | 2025 | Gutters & downspouts | Replace gutters at the 3 stand alone carports | 51071-00 | GC | Capital Plan | 22500 | 0 | 22500 |  | Not Started
Candlewood | 2025 | Roof Maintenance | Item No. 15: Allowance for annual roof maintenance on all roof areas including inspection and repair of flashing, sealan | 51062-00 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Candlewood | 2025 | Exterior building repairs | Due to extensive repairs at the 3 stand alone carports need to repaint entire structures to match exisiting color scheme | 51080-00 | GC | Capital Plan | 135000 | 0 | 135000 |  | Not Started
Candlewood | 2025 | Exterior Paint | Item No. 11: Budget for pressure washing, preparation, caulking, stucco wall repairs, and painting of building exteriors | 51080-00 | GC | Capital Plan | 283500 | 283500 | 0 |  | Completed
Candlewood | 2025 | Balconies | Item No. 13: Engage a specialty consultant to survey 100% of apartment balconies associated with observed deterioration | 51993-01 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Candlewood | 2025 | Unit deferred maintenance | Item No. 3: Repair cracked concrete at Unit A119 patio. | 52111-00 | GC | Capital Plan | 2500 | 2500 | 0 |  | Completed
Candlewood | 2025 | Unit deferred maintenance (cont.) - 1 | Item No. 17: Allowance for repairs in bathrooms showing evidence of minor ceiling damage. Seen in Units C311 with tape i | 52111-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Candlewood | 2025 | Unit deferred maintenance (cont.) -2 | Item No. 18: Allowance for remediation of organic growth in isolated areas, especially in bathrooms where exhaust fans a | 52111-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Candlewood | 2025 | Radon Mitigation | 1.1.5 - Elevated levels of radon were detected in Building 9830 - Unit 123 and Building 9850 - Unit 118. The sponsor has | 51180-00 | PMC | Capital Plan | 20000 | 28975 | -8975 |  | Completed
Candlewood | 2025 | Pool Area Remodel | Building A: replace umbrellas and furniture Building B: repurpose middle space and replace plants. | 51160-00 | PMC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Candlewood | 2025 | Elevator Tests | Item No. 28: Perform the annual elevator tests and post the most recent certificates. Cab certificates expired 6/29/2024 | 51993-01 | PMC | Capital Plan | 4800 | 28842 | -24042 |  | Completed
Candlewood | 2025 | Electrical Load Tests | Item No. 29: Perform the required 5-year load test. Posted placard expired 6/11/2018. | 51993-01 | PMC | Capital Plan | 7200 | 0 | 7200 |  | Not Started
Candlewood | 2025 | Electrical distribution systems | Item No. 21: Allowance to provide periodic maintenance of the electrical distribution systems including infrared scans, | 51140-00 | GC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
Candlewood | 2025 | Meter Banks - Rust and Corrosion | Item No. 22: Remove rust and corrosion from the multi-meter assemblies and paint with a matching rust inhibitive paint. | 51140-00 | GC | Capital Plan | 4500 | 32000 | -27500 |  | Completed
Candlewood | 2025 | Electrical - Load Centers | Item No. 23: Ensure that all apartment load centers have the proper index identifying circuit number and devices served. | 51140-00 | GC | Capital Plan | 9450 | 0 | 9450 |  | Not Started
Candlewood | 2025 | Common Area Light Fixtures | Change all patio/balcony lights to LED flush mounted lights | 51141-00 | GC | Capital Plan | 28350 | 28350 | 0 |  | Completed
Candlewood | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 132579 | 0 | 132579 |  | Reserve
Candlewood | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 72918 | 0 | 72918 |  | Reserve
Canyon Villa | 2025 | Asphalt Coating | R&R 1500 SF of potholes in concrete pavement LPCA - Cracking in the concrete driving lanes and parking areas was observe | 83000-2000 | GC | Capital Plan | 45000 | 5802 | 39198 |  | In Progress
Canyon Villa | 2025 | Stripe parking areas | Stripe parking lot LPCA - Pavement markings and striping appeared to be in fair condition. Reapplication of pavement mar | 83000-2000 | GC | Capital Plan | 22000 | 2837 | 19163 |  | In Progress
Canyon Villa | 2025 | Sidewalks | Repair Trip Hazards LPCA - Cracking in the concrete walkways was observed adjacent to Units 121, 140, 167, and 288. Repa | 83000-2800 | GC | Capital Plan | 15000 | 1934 | 13066 |  | In Progress
Canyon Villa | 2025 | Fences & gates - site perimeter | Repair Iron fence and paint | 83000-3900 | GC | Capital Plan | 25000 | 3224 | 21776 |  | In Progress
Canyon Villa | 2025 | Fences & gates - swimming pool | Repair and paint | 83000-5300 | GC | Capital Plan | 12000 | 1547 | 10453 |  | In Progress
Canyon Villa | 2025 | Carports / Garages | Repair carports | 83000-2600 | GC | Capital Plan | 15000 | 1934 | 13066 |  | In Progress
Canyon Villa | 2025 | Termite treatment | Includes inspection/treatment of Drywood, Subterranean and Dampwood termites) LPCA - According to provided information, | 80000-6800 | GC | Capital Plan | 54900 | 7079 | 47821 |  | In Progress
Canyon Villa | 2025 | Concrete deck / floor fill | Seal cracks in landing | 83000-2800 | GC | Capital Plan | 32000 | 4126 | 27874 |  | In Progress
Canyon Villa | 2025 | Repair exterior stair treads and stringers | Repair stair tread and stringers | 83000-7100 | GC | Capital Plan | 32000 | 4126 | 27874 |  | In Progress
Canyon Villa | 2025 | Repair exterior stair railings | repair and secure stair railings | 83000-7100 | GC | Capital Plan | 16000 | 2063 | 13937 |  | In Progress
Canyon Villa | 2025 | Repair balcony framing & decking | Repair damaged patio framing | 83000-2400 | GC | Capital Plan | 38000 | 4900 | 33100 |  | In Progress
Canyon Villa | 2025 | Repair patio/balcony railings | Secure all balcony railings LPCA - Paint along the balcony railing was observed to be chipping and peeling. Additionally | 83000-2400 | GC | Capital Plan | 16000 | 2063 | 13937 |  | In Progress
Canyon Villa | 2025 | Retaining Wall repairs | ESCA - Repair chips and broken sections of concrete on top of the concrete retaining wall. Repair to consist of placing | 83000-7500 | GC | Capital Plan | 4000 | 516 | 3484 |  | In Progress
Canyon Villa | 2025 | Retaining Wall repairs | ESCA - Implement a protocol for regular maintenance and cleaning of the drainage system including removal of plants | 83000-7500 | GC | Capital Plan | 400 | 52 | 348 |  | In Progress
Canyon Villa | 2025 | SB721 Repairs | Various SB721 repairs | 83000-7600 | GC | Capital Plan | 100000 | 12894 | 87106 |  | In Progress
Canyon Villa | 2025 | Roofing | Tune up clay tile and repair flashing LPCA - Organic materials were observed on the clay/concrete mission tiles. Cleanin | 83000-6100 | GC | Capital Plan | 25000 | 3224 | 21776 |  | In Progress
Canyon Villa | 2025 | Modified bitumen membrane roof Repairs | Roof repairs on 35 roofs | 83000-6100 | GC | Capital Plan | 35000 | 4513 | 30487 |  | In Progress
Canyon Villa | 2025 | Flashing | Replace damaged drip edge on balconies. | 83000-6100 | GC | Capital Plan | 16000 | 2063 | 13937 |  | In Progress
Canyon Villa | 2025 | Roof Cleanup and treatment | Roof Cleaning & Moss Treatment | 83000-6100 | GC | Capital Plan | 72000 | 9284 | 62716 |  | In Progress
Canyon Villa | 2025 | Gutters & downspouts | Clean and secure gutters and down spouts | 800 | GC | Capital Plan | 32000 | 4126 | 27874 |  | In Progress
Canyon Villa | 2025 | Sealants & caulking | Seal & Caulk Roofing Areas | 83000-6100 | GC | Capital Plan | 25000 | 3224 | 21776 |  | In Progress
Canyon Villa | 2025 | Repair stucco | Repairs to damaged stucco | 83000-3700 | GC | Capital Plan | 14000 | 1805 | 12195 |  | In Progress
Canyon Villa | 2025 | Exterior building Paint | Paint Community EPCA - Perform maintenance needs on the exterior elevated elements as recommended in the EEE Report prep | 83000-3400 | GC | Capital Plan | 354000 | 45646 | 308354 |  | In Progress
Canyon Villa | 2025 | Repair / replace wood trim | Replace all rotted fascia throughout property | 83000-3700 | GC | Capital Plan | 25000 | 3224 | 21776 |  | In Progress
Canyon Villa | 2025 | Fire Protection | Fire Stops | 80000-6400 | PMC | Capital Plan | 17934 | 509 | 17425 |  | In Progress
Canyon Villa | 2025 | Signage - Entry Monument | EPCA - Provide signage directing individuals from the accessible parking spaces to the leasing office entrance doors. | 83000-4300 | PMC | Capital Plan | 300 | 0 | 300 |  | Not Started
Canyon Villa | 2025 | Security/ fire alarm systems | LPCA (PR-90) - An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and rec | 80000-1700 | GC | Capital Plan | 20000 | 2579 | 17421 |  | In Progress
Canyon Villa | 2025 | Fire/Life Safety System - Smoke/CO alarm | EPCA - Budget to replace the existing combination smoke/CO alarms based on age and useful life. The NFPA requires that s | 80000-1700 | PMC | Capital Plan | 20720 | 0 | 20720 |  | Not Started
Canyon Villa | 2025 | Back-flow preventer | EPCA - The three irrigation backflow preventer assemblies were last inspected in February 2024 and are now past due for | 80000-5100 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Canyon Villa | 2025 | Galvanized Pipe Replacement | EPCA - Allowance for periodic domestic and sanitary piping repairs or replacements based on age and EUL (year 1 upfront, | 80000-5200 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Canyon Villa | 2025 | Electrical distribution | Repair electric to pole lights and photo cells | 80000-4800 | GC | Capital Plan | 20000 | 2579 | 17421 |  | In Progress
Canyon Villa | 2025 | Common area light fixtures | replace exterior building lights and post lights | 83000-3200 | GC | Capital Plan | 32000 | 4126 | 27874 |  | In Progress
Canyon Villa | 2025 | Replace transformer | EPCA - Contact the local utility to replace one utility transformer exhibiting significant corrosion. The unit is neares | 80000-4800 | GC | Capital Plan | 50000 | 6447 | 43553 |  | In Progress
Canyon Villa | 2025 | Install GFCI protection | EPCA - Install GFCI protection on the counter-height kitchen power outlets. Only 1 protected outlet was observed in each | 80000-4800 | PMC | Capital Plan | 36600 | 0 | 36600 |  | Not Started
Canyon Villa | 2025 | Preventative Maintenance - Breaker Panels | EPCA - Perform preventative maintenance on the electrical systems throughout the site, including opening breaker panels, | 80000-4800 | PMC | Capital Plan | 18300 | 0 | 18300 |  | Not Started
Canyon Villa | 2025 | Contingency | Contingency Amount | 80000-7700 | GC | Contingency | 33781 | 4356 | 29425 |  | Reserve
Canyon Villa | 2025 | Construction Management Fee | CM Fees | 80000-7200 | GC | CM Fee | 64822 | 8358 | 56463 |  | Reserve
Chaparral | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 51043-00 | PMC | Capital Plan | 20000 | 7420 | 12580 |  | In Progress
Chaparral | 2025 | Asphalt pavement | Mill and overlay asphalt throughout entire property Includes Equity PCA Item 3.2.2- Asphalt Pavment; Mill and overlay ap | 51050-00 | GC | Capital Plan | 740000 | 740000 | 0 |  | Completed
Chaparral | 2025 | Stripe parking areas | Stripe throughout property | 51053-00 | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Chaparral | 2025 | Asphalt Coating | Double seal coat entire pavement throughout property | 51053-00 | GC | Capital Plan | 525000 | 525000 | 0 |  | Completed
Chaparral | 2025 | ADA parking & curb cuts | Restripe all handicap parking spots | 51091-00 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Chaparral | 2025 | Sidewalks | Replace cracked sidewalks throughout property | 51091-00 | GC | Capital Plan | 4500 | 4500 | 0 |  | Completed
Chaparral | 2025 | Resurface swimming pool | Resurface both pools, not including spas (completed recently) | 51023-00 | GC | Capital Plan | 67500 | 67500 | 0 |  | Completed
Chaparral | 2025 | Replace swimming pool coping | Deck-o-seal coping around both pools | 51021-00 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Chaparral | 2025 | Fences & gates - swimming pool | Scrap, prime and paint both pool fences. Add metal fence topper to extend height on gates and improve gate security. Pro | 51076-00 | GC | Capital Plan | 37600 | 37600 | 0 |  | Completed
Chaparral | 2025 | Sport Court | Resurface and stripe for tennis & pickleball. Fencing and lighting repairs. Includes Equity PCA Item 3.2.9- Tennis Court | 51027-00 | GC | Capital Plan | 55000 | 55000 | 0 |  | Completed
Chaparral | 2025 | Retaining walls | Equity PCA Item 3.2.5- Install weepholes on southern perimeter concrete masonry retaining walls | 51085-00 | GC | Capital Plan | 2400 | 2400 | 0 |  | Completed
Chaparral | 2025 | West Poolhouse | Equity PCA Item 3.2.9- Eliminate step between pool surround and poolhouse interior to provide wheelchair accessible rout | 51021-00 | GC | Capital Plan | 1250 | 1250 | 0 |  | Completed
Chaparral | 2025 | Pool Equipment | Includes Equity PCA Item 3.2.9- Repair active leaks observed at East and West pool heater PVC distribution piping | 51026-00 | GC | Capital Plan | 300 | 300 | 0 |  | Completed
Chaparral | 2025 | Fences & gates - swimming pool | Reinforce or increase size of pool gate gate posts at both pools | 51076-00 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
Chaparral | 2025 | Playground equipment | Playground Addition | 51020-00 | GC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
Chaparral | 2025 | Picnic areas | Tables & Seating | 51160-04 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Chaparral | 2025 | ADA Accessibility | Equity PCA Item- 7.1- Provide compliant scald-protection underneath leasing office men's restroom sink | 51158-00 | GC | Capital Plan | 200 | 200 | 0 |  | Completed
Chaparral | 2025 | Interior Update Placeholder | Placeholder Expense | 51150-00 | PMC | Capital Plan | 296000 | 1706 | 294294 |  | In Progress
Chaparral | 2025 | Signage - Building identification | Unit number signage needed at doors | 51033-00 | PMC | Capital Plan | 22200 | 0 | 22200 |  | Not Started
Chaparral | 2025 | Fitness Center Remodel (Defer Costs) | Paint & Reupholster ($5,000) | 51160-00 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Chaparral | 2025 | Picnic/Grill Area Remodel | Remove and install new stand alone grils throughout property | 51160-04 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Chaparral | 2025 | Package Lockers (Defer Costs) | Accept small packages at office, otherwise deliver to door. Look at adding package lockers in enclosed room by 2nd pool. | 51168-00 | GC | Capital Plan | 29600 | 0 | 29600 |  | Not Started
Chaparral | 2025 | Security Camera System | Have 23 cameras, need 2-4 more cameras to cover side views | 51993-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Chaparral | 2025 | Golf Cart | Have leasing cart but could use new one | 51994-00 | PMC | Capital Plan | 8000 | 16562 | -8562 |  | Completed
Chaparral | 2025 | Domestic Water Service Main | Equity PCA Item- 5.1- The east domestic water service backflow prevention device was observed with an active drip leak. | 51158-00 | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Chaparral | 2025 | Domestic Water Hose Bibs | Equity PCA Item- 5.1- Hose bibs were observed with active drip leaks on the exterior risers of apartment buildings E and | 51158-00 | GC | Capital Plan | 500 | 500 | 0 |  | Completed
Chaparral | 2025 | Water Heater T&P Valve Discharge | Equity PCA Item- 5.1- The water heater at unit A9 was observed lacking piping from the T&P valve to the building exterio | 51158-00 | GC | Capital Plan | 200 | 200 | 0 |  | Completed
Chaparral | 2025 | HVAC inspection and maintenance | Add HVAC pads to 3 units at the leasing office. Currently sitting on ground with debris around. | 51120-00 | GC | Capital Plan | 750 | 750 | 0 |  | Completed
Chaparral | 2025 | HVAC Exterior Condensing Unit Refrigerant Line Insulati | Equity PCA Item- 5.1- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | 51122-00 | GC | Capital Plan | 3700 | 3700 | 0 |  | Completed
Chaparral | 2025 | Natural Gas Seismic Shutoff Devices | Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices to prevent dang | 51158-00 | GC | Capital Plan | 148000 | 148000 | 0 |  | Completed
Chaparral | 2025 | Electrical distribution | Electrical Panels | 51140-00 | GC | Capital Plan | 27000 | 27000 | 0 |  | Completed
Chaparral | 2025 | Common area light fixtures | Replace all pole lights with LED and change tennis court lights with LED | 51141-00 | GC | Capital Plan | 55750 | 55750 | 0 |  | Completed
Chaparral | 2025 | Replace breezeway lights | Replace all breezeway lights in stairwells with LED | 51141-00 | GC | Capital Plan | 16500 | 16500 | 0 |  | Completed
Chaparral | 2025 | Fire Alarm Panels | Equity PCA Item- 5.5.2- Fire alarm control panels (FACP) at Buildings L and N were observed to with active trouble alarm | 51993-00 | PMC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
Chaparral | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 87488 | 0 | 87488 |  | Reserve
Chaparral | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 116447 | 0 | 116447 |  | Reserve
Crestmark | 2025 | Pavement | Repair potholes | 84201 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
Crestmark | 2025 | Asphalt Coating | Seal Coat and Crack Fill | 84204 | PMC | Capital Plan | 144000 | 6391 | 137609 |  | In Progress
Crestmark | 2025 | Resurface swimming pool | Resurface both pools | 84095 | GC | Capital Plan | 79000 | 79000 | 0 |  | Completed
Crestmark | 2025 | Replace swimming pool deck | Level pavers and presure wash | 84361 | GC | Capital Plan | 31000 | 31000 | 0 |  | Completed
Crestmark | 2025 | Fences & gates - swimming pool | Repair fence and gates | 84361 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Crestmark | 2025 | Carports / Garages | Repairs to garage door - The garage door at 14C was observed damaged and should be repaired or replaced at this time. | 84219 | PMC | Capital Plan | 26000 | 0 | 26000 |  | Not Started
Crestmark | 2025 | Stripe parking areas | Restripe of parking lot | 84201 | PMC | Capital Plan | 28000 | 0 | 28000 |  | Not Started
Crestmark | 2025 | Sidewalks | PNA - Sidewalk Cracks LPCA - Sidewalks were observed to be in good to fair condition with cracks noted in isolated area | 84115 | PMC | Capital Plan | 5000 | 1650 | 3350 |  | In Progress
Crestmark | 2025 | Landscape irrigation | A leak from the irrigation system was observed at the site stairs between building 5 and the leasing office/clubhouse bu | 84300 | PMC | Capital Plan | 1500 | 877 | 623 |  | In Progress
Crestmark | 2025 | Fences & gates - compactor | The gates on the trash compactor enclosures are either damaged or missing. Repairs are recommended at this time. | 84111 | PMC | Capital Plan | 5000 | 1302 | 3698 |  | In Progress
Crestmark | 2025 | Fences & gates - site perimeter | The motor for automated gates at Crestmark Drive were reported to be inoperable. Repairs are recommended at this time. | 84205 | PMC | Capital Plan | 7000 | 1823 | 5177 |  | In Progress
Crestmark | 2025 | Landscaping | Curb Appeal | 84303 | PMC | Capital Plan | 75000 | 88873 | -13873 |  | Completed
Crestmark | 2025 | Pressure wash Breezeways | Pressure Washing - Breezeways | 84206 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Crestmark | 2025 | Pool Area | Pool bathroom upgrades - 1st Call to verify scope | 84361 | PMC | Capital Plan | 25000 | 4966 | 20034 |  | In Progress
Crestmark | 2025 | Playground | Replace/repair playground equipment next to blacktop courts | 84195 | PMC | Capital Plan | 30000 | 2300 | 27700 |  | In Progress
Crestmark | 2025 | Concrete deck / floor fill | Rout and seal landings | 84102 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Crestmark | 2025 | Repair exterior stair railings | Secure railings | 84121 | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Crestmark | 2025 | Repair balcony framing & decking | Repair 3 landing with structural issues | 84104 | GC | Capital Plan | 30000 | 15000 | 15000 |  | In Progress
Crestmark | 2025 | Repair patio/balcony railings | Secure railings | 84121 | GC | Capital Plan | 7000 | 7000 | 0 |  | Completed
Crestmark | 2025 | Asphalt composite shingle roofing | Standard roof tune up on ridge, vault and pipe jacks | 84433 | GC | Capital Plan | 32000 | 9600 | 22400 |  | In Progress
Crestmark | 2025 | Gutters & downspouts | Clean and repitch gutters throughout property | 84202 | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
Crestmark | 2025 | Siding- Water Intrusion | Address water intrusion near bay windows - 32 units | 84113 | GC | Capital Plan | 160000 | 80000 | 80000 |  | In Progress
Crestmark | 2025 | Flashing/Siding | A section of metal flashing is missing on the west side of the clock tower. Repairs are recommended. | 84105 | PMC | Capital Plan | 700 | 0 | 700 |  | Not Started
Crestmark | 2025 | Repair / replace vinyl siding | Repair Vinyl siding / trim / flashing | 84105 | PMC | Capital Plan | 85000 | 0 | 85000 |  | Not Started
Crestmark | 2025 | Paint/finish | Repaint full site | 84101 | PMC | Capital Plan | 334000 | 0 | 334000 |  | Not Started
Crestmark | 2025 | Repair / replace wood trim | Replace rotten wood throughout | 84105 | PMC | Capital Plan | 83500 | 0 | 83500 |  | Not Started
Crestmark | 2025 | Install CO Detectors | CO detectors were not observed in the units. The fireplaces are reportedly gas-fired units and require a CO detector. In | 83236 | PMC | Capital Plan | 20040 | 35518 | -15478 |  | Completed
Crestmark | 2025 | Clean Drier vents | clean dryer vents and replace damaged covers | 84106 | GC | Capital Plan | 16700 | 16700 | 0 |  | Completed
Crestmark | 2025 | Install GCI Outlets | Non-GFCI outlets were observed in the pool restrooms and some secondary bathrooms of the apartment units, including 8-81 | 83330 | PMC | Capital Plan | 10020 | 0 | 10020 |  | Not Started
Crestmark | 2025 | Fire Stops | Fire stops | 84239 | PMC | Capital Plan | 36740 | 15411 | 21329 |  | In Progress
Crestmark | 2025 | Unit deferred maintenance | Repair mechanical closet subfloors | 84304 | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
Crestmark | 2025 | Signage - Entry Monument | Noted during concept walk | 84290 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Crestmark | 2025 | Signage - Site | Added based on Kevin DD email feedback | 84103 | PMC | Capital Plan | 5000 | 2062 | 2938 |  | In Progress
Crestmark | 2025 | Clubhouse | Update color scheme and game room | 84116 | PMC | Capital Plan | 30000 | 3425 | 26575 |  | In Progress
Crestmark | 2025 | Fitness Center: New Equipment | Supplement existing equipment & redo bathrooms | 84190 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Crestmark | 2025 | Pool Area Furniture | Split between the two pools | 84360 | PMC | Capital Plan | 60000 | 0 | 60000 |  | Not Started
Crestmark | 2025 | Picnic/Grill Area Remodel | Pool 1: $25K & Pool 2: $15K | 84203 | PMC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
Crestmark | 2025 | Sports Courts | Convert tennis court to pickle ball court | 84390 | GC | Capital Plan | 75000 | 22500 | 52500 |  | In Progress
Crestmark | 2025 | Mailboxes | New Mailboxes | 84005 | PMC | Capital Plan | 65000 | 0 | 65000 |  | Not Started
Crestmark | 2025 | Golf Cart | Maintenace carts; property has 2 maintenance carts & 1 6-seat leasing | 83375 | PMC | Capital Plan | 30000 | 12840 | 17160 |  | In Progress
Crestmark | 2025 | Replace AC condenser | Add insulation to Condensing unit lines | 84217 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Crestmark | 2025 | Replace breezeway lights | Inspect and replace emergency lighting | 84210 | GC | Capital Plan | 19000 | 19000 | 0 |  | Completed
Crestmark | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 87760 | 0 | 87760 |  | Reserve
Crestmark | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 92148 | 0 | 92148 |  | Reserve
Cypress Bend | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84303 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Cypress Bend | 2025 | Pavement | PNA - Repair Potholes PCA 3.2.2 - Areas of linear cracking and isolated spalling around linear cracks was observed at t | 84204 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Cypress Bend | 2025 | Sidewalks | PNA - Remove and replace areas of trip hazards. PCA 3.2.3 -Areas of linear cracking was observed in the concrete walkwa | 84115 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Cypress Bend | 2025 | Erosion control | PNA - Fill in erosion areas around buildings. | 84517 | GC | Capital Plan | 29000 | 29000 | 0 |  | Completed
Cypress Bend | 2025 | Fences & gates - site perimeter | PNA - Repair perimater fencing | 84205 | GC | Capital Plan | 43000 | 43000 | 0 |  | Completed
Cypress Bend | 2025 | Dumpster enclosures | PNA - Repair dumpster enclosures PCA 3.2.7 - Areas of damaged wood fencing was observed east adjacent to Building 12, n | 84111 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Cypress Bend | 2025 | Stripe parking areas | Stripe Parking | 84201 | GC | Capital Plan | 15000 | 4500 | 10500 |  | In Progress
Cypress Bend | 2025 | ADA parking & curb cuts | PCA 7.1 - Installation of an access aisle adjacent to the accessible parking stall north adjacent to Building 10 | 84221 | GC | Capital Plan | 250 | 250 | 0 |  | Completed
Cypress Bend | 2025 | Concrete deck / floor fill | Grind and seal cracks in light weight concrete landings | 84110 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Cypress Bend | 2025 | Repair exterior stair railings | PNA - Replace damaged railing on staircases. PCA 4.5 - Rust and corrosion was observed on the metal stringers, handrai | 84121 | GC | Capital Plan | 39000 | 39000 | 0 |  | Completed
Cypress Bend | 2025 | Asphalt composite shingle roofing | PNA - Roof tune up. PCA 4.4.1 - Unit 606 was observed to have water staining on the ceiling indicative of a roof leak. | 84433 | GC | Capital Plan | 13000 | 13000 | 0 |  | Completed
Cypress Bend | 2025 | Gutters & downspouts | PNA - Clean, repitch, and secure gutters. PCA 4.4.2 - Building 1 was observed to have a missing gutter system on the so | 84202 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Cypress Bend | 2025 | Flashing | Repair damaged flashing | 84433 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Cypress Bend | 2025 | Sealants & caulking | Roof Sealants | 84433 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Cypress Bend | 2025 | Repair / replace cement fiber siding | PNA - Siding repairs. PCA 4.3.1 - Damaged fiber cement lap board siding was observed on the east elevation of Building | 84206 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Cypress Bend | 2025 | Breezeways | PNA - Repair soffits | 84120 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Cypress Bend | 2025 | Exterior building | PNA - Exterior painting. PCA 4.3.1- Exterior cleaning, painting, sealing | 84101 | GC | Capital Plan | 195000 | 167100 | 27900 |  | In Progress
Cypress Bend | 2025 | Repair / replace wood trim | PNA - Replace damaged trim | 84105 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Cypress Bend | 2025 | Drier vents | PNA - Clean all dryer vents. PCA 5.2 Some of the dryer vents appeared to be damaged and full of debris. Cracked or vents | 84106 | GC | Capital Plan | 14400 | 14400 | 0 |  | Completed
Cypress Bend | 2025 | Garabage Disposals | Interior Replacements | 82206 | PMC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Cypress Bend | 2025 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84239 | PMC | Capital Plan | 22440 | 0 | 22440 |  | Not Started
Cypress Bend | 2025 | Unit deferred maintenance | Major Repairs Floors 18 Bedrooms 13 Living Rooms 3 Kitchens 2 Kitchen Countertop Resurface 2 Interior Door Replacement E | 84304 | PMC | Capital Plan | 21000 | 0 | 21000 |  | Not Started
Cypress Bend | 2025 | Signage | Budget for wall signage, current is dated. | 84103 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Cypress Bend | 2025 | Signage - Site | PCA 7.1 - Installation of ADA vertical identification parking signage | 84103 | PMC | Capital Plan | 450 | 0 | 450 |  | Not Started
Cypress Bend | 2025 | Clubhouse / Office Remodel | PCA 7.1 - Installation of grab bars adjacent to the commode in the leasing office | 84208 | PMC | Capital Plan | 500 | 0 | 500 |  | Not Started
Cypress Bend | 2025 | Clubhouse / Office Furniture | No clubhouse, allowance for office furniture | 84306 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Cypress Bend | 2025 | Computers | Budget for 2 replacement | 82140 | PMC | Capital Plan | 4000 | 9877 | -5877 |  | Completed
Cypress Bend | 2025 | Playground | PCA 3.2.9 - Partner observed that the ground cover beneath the play equipment consisted of grass. According to the Consu | 84195 | PMC | Capital Plan | 11250 | 12048 | -798 |  | Completed
Cypress Bend | 2025 | Unit Model Update | New furniture in model unit | 84280 | PMC | Capital Plan | 18000 | 0 | 18000 |  | Not Started
Cypress Bend | 2025 | Tools & Equipment | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools | 83440 | PMC | Capital Plan | 10000 | 866 | 9134 |  | In Progress
Cypress Bend | 2025 | Golf Cart | Don't have any carts, nowhere to park them. Could budget for one | 83375 | PMC | Capital Plan | 8000 | 0 | 8000 |  | Not Started
Cypress Bend | 2025 | AC condenser | PNA - Reposistion A/C condensers to achive 12" between units | 84220 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Cypress Bend | 2025 | HVAC Preventative Maintenance | PCA - 5.2 Supply and return air vents were observed with buildup of debris and need cleaning in buildings 10 and 12 due | 84217 | GC | Capital Plan | 15600 | 0 | 15600 |  | Not Started
Cypress Bend | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 77339 | 0 | 77339 |  | Reserve
Cypress Bend | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 42724 | 0 | 42724 |  | Reserve
Cypress Bend Village | 2025 | Storm sewer piping | PNA - Add drainage behing 4 building and connect to downspouts | 84385 | GC | Capital Plan | 75000 | 75000 | 0 |  | Completed
Cypress Bend Village | 2025 | Pavement | PNA - Repair Potholes PCA 3.2.2 - Linear cracking was observed in the drive aisles and parking spaces at the entrance d | 84204 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Cypress Bend Village | 2025 | Stripe parking areas | Stripe Parking | 84204 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Cypress Bend Village | 2025 | ADA parking & curb cuts | PNA - Add rail around ADA Ramp to units PCA - Installation of vertical identification signage at parking space | 84204 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Cypress Bend Village | 2025 | Sidewalks | PNA - remove and replace areas of trip hazards PCA 3.2.3 - Potential tripping hazards due to heaved concrete sections w | 84221 | GC | Capital Plan | 14400 | 14400 | 0 |  | Completed
Cypress Bend Village | 2025 | Erosion control / Tree trimming | PNA - Fill eroded areas around buildings; PCA - 3.2.4- Areas of soil erosion were observed on the northeast corner ad e | 83517 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Cypress Bend Village | 2025 | Resurface swimming pool | Swimming Pool | 84095 | GC | Capital Plan | 42000 | 18600 | 23400 |  | In Progress
Cypress Bend Village | 2025 | Replace swimming pool coping | PNA - Replace deck-o-seal | 84361 | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Cypress Bend Village | 2025 | Replace swimming pool deck | PNA - Pressure wash pool decks | 84361 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Cypress Bend Village | 2025 | Fences & gates - swimming pool | PNA - Adjust gates and repair gate latches | 84361 | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Cypress Bend Village | 2025 | Dumpster enclosures | PNA - Repair compactor areas | 84111 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Cypress Bend Village | 2025 | Fences & gates - site perimeter | PCA 3.2.7 - Isolated areas of damaged fencing was observed north adjacent to Building 12, south adjacent to Building 4, | 84205 | GC | Capital Plan | 980 | 980 | 0 |  | Completed
Cypress Bend Village | 2025 | Concrete deck / floor fill | PNA - Grind and seal cracks in light weight concrete landings | 84206 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Cypress Bend Village | 2025 | Repair exterior stair treads, stringers, and railings | PNA - Replace damaged railing on stair cases PCA 4.5 - Areas of rust and corrosion was observed on the steel stingers an | 84114 | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
Cypress Bend Village | 2025 | Repair patio/balcony railings | PNA - Repair balcony railings | 84121 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Cypress Bend Village | 2025 | Expansion Joints | Building Expansion Joints | 84102 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Cypress Bend Village | 2025 | Asphalt composite shingle roofing | PNA - Roof tune up | 84433 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Cypress Bend Village | 2025 | Gutters & downspouts | PNA - Clean, repitch, and secure gutters | 84202 | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Cypress Bend Village | 2025 | Flashing | PNA - Repair damaged flashing | 84433 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Cypress Bend Village | 2025 | Sealants & caulking | Roof Sealants | 84433 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Cypress Bend Village | 2025 | Breezeways | Repair soffits | 84120 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Cypress Bend Village | 2025 | Exterior building | PNA - Repaint community PCA 4.3.1 - Areas of damaged siding were observed on the east and south elevations of Building | 84101 | GC | Capital Plan | 198000 | 185750 | 12250 |  | In Progress
Cypress Bend Village | 2025 | Repair / replace wood trim | Replace damaged trim | 84105 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Cypress Bend Village | 2025 | Drier vents | PNA - Clean drier vents and repair as needed. PCA 5.2 - Some of the dryer vents appeared to be damaged and full of debri | 84106 | GC | Capital Plan | 16660 | 24500 | -7840 |  | Completed
Cypress Bend Village | 2025 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84239 | PMC | Capital Plan | 23375 | 0 | 23375 |  | Not Started
Cypress Bend Village | 2025 | Unit Deferred Maintenance | 2 Units have mold: (1-601, 1-610) 97% of water heaters > 10 years old Major Repairs Flooring repair: 17 Bedrooms 18 Livi | 84304 | PMC | Capital Plan | 26000 | 0 | 26000 |  | Not Started
Cypress Bend Village | 2025 | Clubhouse / Office Remodel | No clubhouse, allowance for office | 84208 | PMC | Capital Plan | 7500 | 3871 | 3629 |  | In Progress
Cypress Bend Village | 2025 | Computers | Budget for 3 replacement | 83265 | PMC | Capital Plan | 6000 | 75832 | -69832 |  | Completed
Cypress Bend Village | 2025 | Fitness Equipment | Add equipment | 84190 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Cypress Bend Village | 2025 | Pool Area Remodel | Add gazebo, turf next to clubhouse | 84361 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Cypress Bend Village | 2025 | Pool Furniture | New furniture | 84360 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Cypress Bend Village | 2025 | Dog Park | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola | 84130 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Cypress Bend Village | 2025 | Model Unit Update | New furniture in model unit | 84280 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Cypress Bend Village | 2025 | Security Camera System | Manager says system is ok, maybe add license plate reader and a few cameras | 84450 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Cypress Bend Village | 2025 | Restoration & Remediation | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools | 84905 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Cypress Bend Village | 2025 | Golf Cart | Budget for maintenance cart. Don't have leasing cart, budget for one in case it is needed | 83375 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Cypress Bend Village | 2025 | Replace forced air unit | PCA 5.2 - Split-system furnace/fan coil, Replace | 84220 | GC | Capital Plan | 78000 | 23400 | 54600 |  | In Progress
Cypress Bend Village | 2025 | Replace AC condenser | PCA 5.2 -Many of the condensing units were installed in an improper manner. Limited units were observed set on pads that | 84218 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Cypress Bend Village | 2025 | Contingency | Contingency | 84510 | GC | Contingency | 103516 | 0 | 103516 |  | Reserve
Cypress Bend Village | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 57309 | 0 | 57309 |  | Reserve
David Ave | 2025 | Asphalt Coating | Seal asphalt Includes Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in fair con | 51053-00 | GC | Capital Plan | 61000 | 61000 | 0 |  | Completed
David Ave | 2025 | Resurface swimming pool | Resurface two pools | 51023-00 | GC | Capital Plan | 92000 | 27600 | 64400 |  | In Progress
David Ave | 2025 | Repair / replace swimming pool pumps | Anti entrapment devices | 51026-00 | GC | Capital Plan | 12600 | 3780 | 8820 |  | In Progress
David Ave | 2025 | Fences & gates - swimming pool | Adjust closers on pool gates | 51076-00 | GC | Capital Plan | 12800 | 12800 | 0 |  | Completed
David Ave | 2025 | Carports / Garages | Repair and paint carport supports | 51172-00 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
David Ave | 2025 | Termite Remediation | Drywood termites treatment | 51992-00 | PMC | Capital Plan | 6000 | 6000 | 0 |  | Completed
David Ave | 2025 | Install metal hardware connections at post-to-beam and | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces. | 51092-00 | GC | Capital Plan | 22500 | 22500 | 0 |  | Completed
David Ave | 2025 | Rout and seal cracks in concrete slab-on-grade. | PCA 4.1 Rout and seal cracks in concrete slab-on-grade. | 51090-00 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
David Ave | 2025 | 3040 David – Engineered repair design to remediate dama | PCA 4.2. -3040 David – Engineered repair design to remediate damaged beam at TUP. | 51070-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
David Ave | 2025 | Remediation of exposed wood beams exhibiting deteriorat | PCA 4.2 - Remediation of exposed wood beams exhibiting deterioration at TUP regions. | 51070-00 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
David Ave | 2025 | Replace edge beams in-kind at TUP areas, where needed. | PCA 4.2. Replace edge beams in-kind at TUP areas, where needed. | 51070-00 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
David Ave | 2025 | Repair or replace damaged concrete treads at stairs. | PCA 4.2.- Repair or replace damaged concrete treads at stairs. | 51090-00 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
David Ave | 2025 | Clean and repaint steel stair frame with surface corros | PCA 4.2. -Clean and repaint steel stair frame with surface corrosion. | 51077-00 | GC | Capital Plan | 3000 | 3000 | 0 |  | Completed
David Ave | 2025 | Replace missing vent tops. | PCA4.4.1 - Replace missing vent tops. | 51062-00 | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
David Ave | 2025 | Repair exterior stair railings | Secure railings on all catwalks | 51077-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
David Ave | 2025 | Repair balcony framing & decking | Repairs for 2 walkways and stairwells per SB721 report from Medro, contingency for additional repairs PCA 4.5- As no doc | 51072-00 | GC | Capital Plan | 55000 | 49862 | 5138 |  | In Progress
David Ave | 2025 | Increase rail height | Raise catwalk rail height to 42" per SB 721 report | 51077-00 | GC | Capital Plan | 100000 | 30000 | 70000 |  | In Progress
David Ave | 2025 | Gutters & downspouts Replace missing or crushed downspo | Secure and clean gutters PCA 4.4.1. -Replace missing or crushed downspouts. | 51071-00 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
David Ave | 2025 | Sealants & caulking | Prep and seal exterior | 51062-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
David Ave | 2025 | Repair / replace wood shingles | Replace window walls with Hardie Horizontal | 51075-00 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
David Ave | 2025 | Exterior building Paint | Paint community | 51080-00 | GC | Capital Plan | 98000 | 98000 | 0 |  | Completed
David Ave | 2025 | Repair / replace wood trim Repair or replace damaged wo | Replace rotted fascia and trim PCA 4.2. - Repair or replace damaged wood trim and stucco at elevated walkways and soffi | 51082-00 | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
David Ave | 2025 | Common area FF&E, Replace | FF& E - Common Areas | 51160-06 | GC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
David Ave | 2025 | Leasing Office Restroom Accessibility | Equity PCA Item- 7.1- The leasing office restroom is provided with a full vanity at the lavatory. Replacement of the va | 51169-00 | GC | Capital Plan | 1550 | 0 | 1550 |  | Not Started
David Ave | 2025 | Pool Area Remodel | Allowance | 51160-00 | PMC | Capital Plan | 5000 | 2400 | 2600 |  | In Progress
David Ave | 2025 | Pool Furniture | No furniture, need to add for 2 pools | 51011-00 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
David Ave | 2025 | Picnic/Grill Area Remodel | Allowance for grill/outdoor kitchen upgrades | 51160-04 | PMC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
David Ave | 2025 | Picnic/Grill Furniture | Allowance for furniture | 51160-04 | PMC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
David Ave | 2025 | Back-flow preventer | Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. Municipalities typically r | 51130-00 | PMC | Capital Plan | 3000 | 2184 | 816 |  | In Progress
David Ave | 2025 | Galvanized Pipe Replacement | Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone to developing pinhol | 51130-00 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
David Ave | 2025 | Stormwater Pipe Repair | Number based on actual bid; $285 per cleanout, est. 10 cleanouts. $402 per storm drain, 4 cleanouts. $129 per flow test, | 51130-00 | GC | Capital Plan | 6746 | 0 | 6746 |  | Not Started
David Ave | 2025 | Sanitary Sewer Piping | Equity PCA Item- 5.1- The sanitary waste system was original to construction. Typically, sections were replaced as neede | 51134-00 | PMC | Capital Plan | 4000 | 7211 | -3211 |  | Completed
David Ave | 2025 | Natural Gas Seismic Shutoff | Will confirm with Gas utility company if needed Equity PCA Item- 5.1- The natural gas services were not equipped with au | 51130-00 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
David Ave | 2025 | Green Program - Energy Retrofit | Echelon upfront costs | 51990-00 | PMC | Capital Plan | 35760 | 2436 | 33324 |  | In Progress
David Ave | 2025 | Fire Department Violations - Engage expeditor to clear | Lender PCA Item- There are outstanding fire department violations. CBRE recommends engaging an expeditor to clear all ou | 51993-01 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
David Ave | 2025 | Electrical Panel Disconnects & Meter Banks | Phased replacement of 2 main meter banks Equity PCA Item- 5.3- The main disconnects and meter banks were manufactured by | 51140-00 | GC | Capital Plan | 120000 | 36000 | 84000 |  | In Progress
David Ave | 2025 | Replace Electrical Meter Panel at Building 3 | Equity PCA Item- 5.3- A metal panel was missing on the wiring trough at the meter enclosure at Building 3. The missing p | 51140-00 | PMC | Capital Plan | 500 | 156 | 344 |  | In Progress
David Ave | 2025 | Electrical service and distribution, Ongoing Repalcemen | Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B (Recomme | 51140-00 | GC | Capital Plan | 5000 | 1500 | 3500 |  | In Progress
David Ave | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 45096 | 0 | 45096 |  | Reserve
David Ave | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 47350 | 0 | 47350 |  | Reserve
Elliot Baymeadows | 2025 | Landscape Cleanup and Enhancements | Tree trim, foliage cut back throughout | 84303 | GC | Capital Plan | 100000 | 90000 | 10000 |  | In Progress
Elliot Baymeadows | 2025 | Stripe parking areas PCA 7.0 - install proper access ai | Parking Lot Striping | 84201 | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Parking equipment | Need more info from Mark | 84219 | GC | Capital Plan | 32000 | 0 | 32000 |  | Not Started
Elliot Baymeadows | 2025 | Parking pavement PCA 3.2.2 - Repair pothole formation | Linear cracking, "map" or "alligator" cracking, and pothole formation were noted throughout the drive aisles adjacent to | 84204 | GC | Capital Plan | 26500 | 32500 | -6000 |  | Completed
Elliot Baymeadows | 2025 | Sidewalks | Sidewalk Repairs | 84115 | GC | Capital Plan | 28000 | 21000 | 7000 |  | In Progress
Elliot Baymeadows | 2025 | Landscape irrigation PCA 3.2.11 - Evaluate system, repa | Irrigation in fair to poor condition. Electrical wiring in the control panel appeared to be cut and maintenance personne | 84302 | PMC | Capital Plan | 32000 | 22824 | 9176 |  | In Progress
Elliot Baymeadows | 2025 | Erosion control | Site Erosion Control | 84517 | GC | Capital Plan | 22000 | 0 | 22000 |  | Not Started
Elliot Baymeadows | 2025 | Fences & gates - site perimeter PCR - Repair inoperable | The motor for the automated gates were reported and observed to be inoperable. Repairs are recommended at this time. | 84205 | PMC | Capital Plan | 2500 | 1600 | 900 |  | In Progress
Elliot Baymeadows | 2025 | Resurface swimming pool | Two pools - Resurface | 84095 | GC | Capital Plan | 70000 | 0 | 70000 |  | Not Started
Elliot Baymeadows | 2025 | Maintenance Shop PCR - Overhead door repair (Maintenanc | Minor damage was observed on the overhead door trim at the maintenance shop. Repairs are recommended | 83270 | PMC | Capital Plan | 350 | 0 | 350 |  | Not Started
Elliot Baymeadows | 2025 | Sports Courts PCA 3.2.9 - Repair tennis and sports cour | Placeholder for repurposing of sports court area. Could include turf installation for soccer Tennis/sports court were ob | 84390 | GC | Capital Plan | 75000 | 75000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Termite Repairs PCR - Termite Damage Repairs | Evidence of termite damage was observed on the door frame of the poop pump room, near the fitness center building. All d | 83301 | PMC | Capital Plan | 700 | 21 | 679 |  | In Progress
Elliot Baymeadows | 2025 | Termite treatment PCR - Termite damage repairs | Subsequent to the site visit, a WDO inspection wasconducted by Busy Bee Termite, and their findings indicate visible sig | 83301 | PMC | Capital Plan | 7500 | 223 | 7277 |  | In Progress
Elliot Baymeadows | 2025 | WDO Repairs PCR - WDO Repairs - WDO report | Subsequent to the site visit, a WDO inspection was conducted by Busy Bee Termite, and their findings indicate evidence o | 83301 | PMC | Capital Plan | 12000 | 356 | 11644 |  | In Progress
Elliot Baymeadows | 2025 | Repair exterior stair treads and stringers | Repair failing wood stair cases | 84114 | GC | Capital Plan | 43000 | 80000 | -37000 |  | Completed
Elliot Baymeadows | 2025 | Asphalt composite shingle roofing | Roof tune up | 84433 | GC | Capital Plan | 160000 | 160000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Flashing | Roof Flashing | 84433 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Sealants & caulking and paint | Roof Sealants & Caulking | 84433 | GC | Capital Plan | 20000 | 16000 | 4000 |  | In Progress
Elliot Baymeadows | 2025 | Repair / replace wood siding | Replace failing siding | 84102 | GC | Capital Plan | 38000 | 30400 | 7600 |  | In Progress
Elliot Baymeadows | 2025 | Exterior Building Painting | Heavy pressure wash and prep for mildew and paint community | 84101 | GC | Capital Plan | 675000 | 405000 | 270000 |  | In Progress
Elliot Baymeadows | 2025 | Repair / replace wood trim | Wood Trim Repairs | 84113 | GC | Capital Plan | 28000 | 22400 | 5600 |  | In Progress
Elliot Baymeadows | 2025 | Chimney Cap Covers | Fabricate and replace rusted out and failing chimney covers | 84102 | GC | Capital Plan | 43000 | 43000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Unit Interior Replacements (Partials) | Partial Units | 84207 | GC | Capital Plan | 414000 | 0 | 414000 |  | Not Started
Elliot Baymeadows | 2025 | Unit Interior Replacements (Classics) | Classic Units | 84207 | GC | Capital Plan | 466000 | 0 | 466000 |  | Not Started
Elliot Baymeadows | 2025 | Dryer Vents | Clean dryer vents | 84106 | GC | Capital Plan | 26400 | 26400 | 0 |  | Completed
Elliot Baymeadows | 2025 | Fire Stops | Fire Stops | 84239 | PMC | Capital Plan | 29920 | 59840 | -29920 |  | Completed
Elliot Baymeadows | 2025 | Fitness Center Remodel | New equipment, refurbishment of existing equipment | 84195 | PMC | Capital Plan | 40000 | 49616 | -9616 |  | Completed
Elliot Baymeadows | 2025 | Package lockers | Add Lockers | 84230 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Elliot Baymeadows | 2025 | Pool Area Remodel | Allocation for two pools | 84361 | PMC | Capital Plan | 50000 | 16765 | 33235 |  | In Progress
Elliot Baymeadows | 2025 | Pool Furniture | Allocation for two pools | 84360 | PMC | Capital Plan | 35000 | 537 | 34463 |  | In Progress
Elliot Baymeadows | 2025 | Unit Model Update | New furniture in model unit | 84280 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Elliot Baymeadows | 2025 | Sanitary Sewer Piping PCA 5.1 - Sewer scoping | Due to the age of the site, Partner recommends a sewer scoping of all waste lines. This scoping can tell if there are br | 84385 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Elliot Baymeadows | 2025 | Domestic Hot Water Heater Replacement | Contingent hot water heater replacement | 84476 | PMC | Capital Plan | 7040 | 4600 | 2440 |  | In Progress
Elliot Baymeadows | 2025 | PCR - Water heater repairs | Minor damage was observed at the water heater pan in units 609 and 1709. A cover plate for the control panel is also mis | 84218 | PMC | Capital Plan | 700 | 0 | 700 |  | Not Started
Elliot Baymeadows | 2025 | Replace forced air unit | Level and replace AC pads | 84218 | GC | Capital Plan | 35200 | 0 | 35200 |  | Not Started
Elliot Baymeadows | 2025 | Replace AC condenser | Contingent HVAC replacement - projections taken from EPCA | 84220 | GC | Capital Plan | 69490 | 0 | 69490 |  | Not Started
Elliot Baymeadows | 2025 | Common area light fixtures | Pole lights, buildings lights, and amenities courts | 84210 | GC | Capital Plan | 72000 | 72000 | 0 |  | Completed
Elliot Baymeadows | 2025 | Replace breezeway lights | Entry lights | 84210 | GC | Capital Plan | 32100 | 32100 | 0 |  | Completed
Elliot Baymeadows | 2025 | Electrical Panel Disconnects & Meter Banks PCA 5.3 - IR | Electrical systems are approaching 40-years-old and are exposed to the weather. IR scans can identify loose connections, | 84330 | GC | Capital Plan | 14000 | 12600 | 1400 |  | In Progress
Elliot Baymeadows | 2025 | Electrical service and distribution, Ongoing Repalcemen | CBRE recommends verifying that the non-GFCI outlets in the secondary bathrooms are on the same circuit as the GFCI outle | 84210 | GC | Capital Plan | 23000 | 0 | 23000 |  | Not Started
Elliot Baymeadows | 2025 | Smoke detectors PCA 5.5.2 - Replace all smoke detectors | In dwelling units observed, smoke detectors were only mounted in the hallways or living room areas, not in the sleeping | 83236 | PMC | Capital Plan | 17600 | 5535 | 12065 |  | In Progress
Elliot Baymeadows | 2025 | CO Detectors PCR (PR-90) - Provide CO detectors PCA 5.5 | Carbon Monoxide detectors were not observed as required. A recommendation has been included to install CO detectors in a | 83236 | PMC | Capital Plan | 8800 | 2767 | 6033 |  | In Progress
Elliot Baymeadows | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 143440 | 0 | 143440 |  | Reserve
Foster Creek | 2025 | Landscape Cleanup and Enhancements Equity PCA 3.2.2 | Install Landscaping and Mulch - North of Building 15042 | 84303 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Foster Creek | 2025 | ADA parking & curb cuts Lender PCA 5.4 Equity PCA 4.1 | The subject property does not provide van-accessible parking spaces at the Leasing Office. Installation of one van-acces | 83520 | GC | Capital Plan | 1600 | 1600 | 0 |  | Completed
Foster Creek | 2025 | Sidewalks Lender PCA 3.1.7 Equity PCA 3.2.4 | Remove and replace areas of trip hazards. Cracked concrete was observed adjacent to the entrance to Building C. Repair | 84115 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Foster Creek | 2025 | Asphalt Pavement Lender PCA 3.1.6 Equity PCA 3.2.4 | Lender PCA 3.1.6 Damaged asphalt pavement consisting of linear cracking, alligator cracking, potholes, and surface ravel | 84204 | GC | Capital Plan | 24250 | 24250 | 0 |  | Completed
Foster Creek | 2025 | Storm Water Management Equity PCA 3.2.1 | Erosion Repairs | 84517 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Foster Creek | 2025 | Dumpster enclosures Equity PCA 3.2.2 | Repair dumpster inclosures. Replaced Damaged Dumpster Gates | 84111 | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
Foster Creek | 2025 | Security Camreas System | Add additional security camreas systems to the property | 84450 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Foster Creek | 2025 | Key Pad and Auto Locking Door | Add to gym door | 84275 | PMC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Foster Creek | 2025 | Repair patio/balcony railings Equty PCA 3.3.5 | Repair balconies railings Balcony Repairs | 84121 | GC | Capital Plan | 40000 | 12000 | 28000 |  | In Progress
Foster Creek | 2025 | Concrete deck / floor fill | np1 sealant to cracks in landing | 84430 | GC | Capital Plan | 19000 | 19000 | 0 |  | Completed
Foster Creek | 2025 | Repair exterior stair railings | Repair wooden railings on stairs | 84121 | GC | Capital Plan | 35000 | 10500 | 24500 |  | In Progress
Foster Creek | 2025 | Asphalt composite shingle roofing | Roof Tune Up | 84433 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Foster Creek | 2025 | Modified bitumen membrane roof Repairs | Repairs to flat roofs. Equity PCA did not mention roof as an immediate need, but did mention as a replacement in YR 1 | 84433 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Foster Creek | 2025 | Gutters & downspouts | Clear scuppers and roof drains | 83439 | GC | Capital Plan | 19000 | 19000 | 0 |  | Completed
Foster Creek | 2025 | Flashing | Repair damaged flashing | 84433 | GC | Capital Plan | 8500 | 2550 | 5950 |  | In Progress
Foster Creek | 2025 | Sealants & caulking and paint | Roof Sealants & Caulking | 84433 | GC | Capital Plan | 8500 | 2550 | 5950 |  | In Progress
Foster Creek | 2025 | Repair / replace wood siding Lender PCA 3.2.4 Equity PC | Replace damaged T 1-11 siding on mansards Damaged T1-11 siding was present at Building G (Phase II). Repair is recommen | 84102 | GC | Capital Plan | 34000 | 10200 | 23800 |  | In Progress
Foster Creek | 2025 | Repair / replace vinyl siding Lender PCA 3.2.4 | Isolated areas of warped vinyl lap siding were observed at the leasing office and Buildings B and C of Phase I. Repairs | 84102 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Foster Creek | 2025 | Breezeway soffit repairs | Repair soffits - Could be changed to $120k | 84113 | GC | Capital Plan | 160000 | 48000 | 112000 |  | In Progress
Foster Creek | 2025 | Exterior building Paint | Repaint Community | 84101 | GC | Capital Plan | 320000 | 96000 | 224000 |  | In Progress
Foster Creek | 2025 | Repair / replace wood trim Equity PCA 3.3.3 | Replace damaged trim | 84113 | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
Foster Creek | 2025 | Moisture and Microbial Growth Equity PCA 4.6 | Proactive rewire bathroom fan to light switch. Mold & Moisture Removal | 84905 | GC | Capital Plan | 15215 | 15215 | 0 |  | Completed
Foster Creek | 2025 | Clean Dryer vents | Clean dryer vents. Get a unit count of units with W/D | 84106 | PMC | Capital Plan | 2250 | 0 | 2250 |  | Not Started
Foster Creek | 2025 | Fire Stops | Install Fire Stops | 84211 | PMC | Capital Plan | 15215 | 88158 | -72943 |  | Completed
Foster Creek | 2025 | Down Unit Renovation (C-309) Lender PCA 3.4.2 | Unit C-309 was observed in poor condition and is considered ‘down’. A notice affixed to the door by the King County Sher | 82460 | PMC | Capital Plan | 10800 | 0 | 10800 |  | Not Started
Foster Creek | 2025 | Damaged Unit Repair (C-209) Lender PCA 3.4.2 Equity PC | Additionally, Unit C-209 was observed in fair condition. The unit has water damage to finishes from the unit above (C-30 | 82460 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Foster Creek | 2025 | General Electrical Services Equity PCA 3.4.4 | Replace wall packs | 84210 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
Foster Creek | 2025 | Improperly supported meter bank Equity PCA 3.4.4 | Meter bank supports | 84330 | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Foster Creek | 2025 | GFCI Receptacles Equity PCA 3.4.4 | Missing GFCI receptacles | 84330 | PMC | Capital Plan | 13500 | 0 | 13500 |  | Not Started
Foster Creek | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 48067 | 0 | 48067 |  | Reserve
Foster Creek | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 50470 | 0 | 50470 |  | Reserve
Foster Creek | 2025 | Signage | Building Signage | 83103 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Foster Creek | 2025 | Dog Park & Grilling Area | Dog Park & Grilling Area | 84130 | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Foster Creek | 2025 | 83209 - Plumbing | Plumbing Work Orders | 83209 | PMC | Capital Plan | 3500 | 29571 | -26071 |  | Completed
Foster Creek | 2025 | 83209 - Plumbing | Water Leaks Behind Sheetrock | 83209 | PMC | Capital Plan | 1667 | 14084 | -12417 |  | Completed
Foster Creek | 2025 | 83210 - Electrical | Outlets and switches replacement program | 83210 | PMC | Capital Plan | 102000 | 25343 | 76657 |  | In Progress
Foxdale Village | 2025 | Storm sewer piping | Clean storm drains | 51130-00 | GC | Capital Plan | 22000 | 0 | 22000 |  | Not Started
Foxdale Village | 2025 | Stripe parking areas | Restripe parking lot | 51053-00 | GC | Capital Plan | 21000 | 0 | 21000 |  | Not Started
Foxdale Village | 2025 | Asphalt Coating | Fill asphalt cracks and seal coat parking lot Equity PCA Item 3.2.2- $110,500- Damaged pavement consisting of linear cra | 51050-00 | GC | Capital Plan | 182000 | 182000 | 0 |  | Completed
Foxdale Village | 2025 | Add Parking Spaces | Parking is an issue at the property, explore adding lot area or gaining spaced via restriping | 51050-00 | GC | Capital Plan | 100000 | 0 | 100000 |  | Not Started
Foxdale Village | 2025 | Sidewalks | Replace trip hazards Lender PCR Item- $3,000- Sidewalks were observed to have uneven edges, resulting in trip hazards. T | 51091-00 | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Foxdale Village | 2025 | Landscape irrigation | Inspect and repair irrigation | 51046-00 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
Foxdale Village | 2025 | Landscaping | Tree trim Equity PCA Item 3.2.4- $5,000- Overgrown tress were observed throughout the subject property. Many of the ove | 51043-00 | GC | Capital Plan | 42000 | 42000 | 0 |  | Completed
Foxdale Village | 2025 | Replace camera / security equipment | Replace camera and security equipment | 51993-00 | PMC | Capital Plan | 51000 | 0 | 51000 |  | Not Started
Foxdale Village | 2025 | Playground | Fall zone on 4 playgrounds, misc equipment repairs and replacements | 51029-00 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Foxdale Village | 2025 | Concrete deck / floor fill | 25 Balcony or landing replacements | 51072-00 | GC | Capital Plan | 90000 | 90000 | 0 |  | Completed
Foxdale Village | 2025 | Wall framing | Replace damaged framing in gable ends | 51070-00 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Foxdale Village | 2025 | Repair exterior stair treads and stringers | Secure railings | 51072-00 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Foxdale Village | 2025 | Repair balcony framing & decking | Balcony Decking | 51072-00 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Foxdale Village | 2025 | Landscaping -Leasing office | PCA 4.1 -Leasing Office – Allowance for landscaping remediation at ledge extension | 51045-00 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Foxdale Village | 2025 | Repair cracks in leasing office | PCA -4.1 - Leasing Office – Allowance for spalling and crack repairs at concrete slab ledge extension, and potential sec | 51090-00 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Foxdale Village | 2025 | Replace damaged wood | PCA 4.2 -Allowance for replacement of damaged wood framing during exterior cladding replacement. | 51070-00 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Foxdale Village | 2025 | Repair masonary fence | PCA 4.2 - Remediation and/or sectional replacement of masonry perimeter fence. | 51076-00 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Foxdale Village | 2025 | Repair concrete stairs | PCA 4.2 - Repair or replace damaged concrete treads at stairs. | 51090-00 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Foxdale Village | 2025 | Inspect stair landing | PCA 4.2- Evaluate stair landing framing with borescope and replace any damaged framing, soffit material and rim joist as | 51070-00 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Foxdale Village | 2025 | Repair exposed wood beams | PCA 4.2 -Remediate wood deterioration of exterior exposed wood beams and vertical braces | 51070-00 | GC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Foxdale Village | 2025 | Replace skylight lens | PCA 4.4.1 -Replace deteriorated or capped skylight lens | 51074-00 | GC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Foxdale Village | 2025 | Replace deteriorated roof-lines | PCA 4.4.1 - Replace deteriorated wood siding at roof-lines | 51075-00 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Foxdale Village | 2025 | Replace roof hatch | PCA 4.4.1 - Replace roof hatch and install safety railing | 51062-00 | GC | Capital Plan | 7000 | 0 | 7000 |  | Not Started
Foxdale Village | 2025 | Replace missing vent tops | PCA 4.4.1 - Replace missing vent tops | 51062-00 | GC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Foxdale Village | 2025 | Replace equipment screen | PCA 4.4.1 - Replace equipment screen | 51070-00 | GC | Capital Plan | 36000 | 0 | 36000 |  | Not Started
Foxdale Village | 2025 | Repair patio/balcony railings | Patio fence repairs | 51077-00 | GC | Capital Plan | 48000 | 48000 | 0 |  | Completed
Foxdale Village | 2025 | Expansion Joints | Replace stucco expansion joints | 51075-00 | GC | Capital Plan | 48000 | 48000 | 0 |  | Completed
Foxdale Village | 2025 | Roofing | 19 roofs appear to be TPO- replace one roof and repair 19 roofs yr2 A, C, D, E, F, G, H, I, J, K, M, N, P, R, T, V, X, | 51061-00 | GC | Capital Plan | 97500 | 88000 | 9500 |  | In Progress
Foxdale Village | 2025 | Roofing Maintenance | PCA 4.4.1 All roof sections: Annual maintenance | 51062-00 | GC | Capital Plan | 25243 | 0 | 25243 |  | Not Started
Foxdale Village | 2025 | Gutters & downspouts | Clean and repair gutters | 51071-00 | GC | Capital Plan | 29274 | 29274 | 0 |  | Completed
Foxdale Village | 2025 | Flashing | Replace damaged flashing | 51062-00 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Foxdale Village | 2025 | Sealants & caulking | Seal transition to stucco from siding | 51062-00 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Foxdale Village | 2025 | Repair / replace wood shingles | Replace T-111 siding with Hardie. Equity PCA Item 4.3.1- $19,800- Damaged and deteriorated T1-11 siding was present at n | 51075-00 | GC | Capital Plan | 1033200 | 1033200 | 0 |  | Completed
Foxdale Village | 2025 | Repair stucco | Repair damaged stucco | 51075-00 | GC | Capital Plan | 75000 | 75000 | 0 |  | Completed
Foxdale Village | 2025 | Exterior building paint | Paint community Equity PCA Item 3.2.7- $15,000- The paint finish on the wood fencing throughout the site was observed t | 51080-00 | GC | Capital Plan | 401800 | 401800 | 0 |  | Completed
Foxdale Village | 2025 | Repair / replace wood trim | Replace trim and damaged fascia | 51082-00 | GC | Capital Plan | 179500 | 179500 | 0 |  | Completed
Foxdale Village | 2025 | Green Program - Echelon Energy Retrofit | Energy Retrofit | 51160-00 | GC | Capital Plan | 116000 | 0 | 116000 |  | Not Started
Foxdale Village | 2025 | Deferred Maintenance - Remove Mold | Lender PCR Item- $6,000- Mold was observed in the bathrooms of many units. The units include the following: Unit 1350-52 | 52111-00 | PMC | Capital Plan | 6000 | 25702 | -19702 |  | Completed
Foxdale Village | 2025 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 51993-00 | PMC | Capital Plan | 14129 | 60523 | -46394 |  | Completed
Foxdale Village | 2025 | Unit deferred maintenance | Flooring replacement needed: kitchen (26), living room (13), bedroom (31), and bathroom (7) Equity PCA Item 6.5.2- $341, | 51157-00 | PMC | Capital Plan | 85400 | 42108 | 43292 |  | In Progress
Foxdale Village | 2025 | Down Units | Lender PCR Item- $5,500- At the time of the site visit, one (1) down unit (Unit 1350-513) was observed due to fire damag | 52111-00 | GC | Capital Plan | 5500 | 0 | 5500 |  | Not Started
Foxdale Village | 2025 | Clubhouse / Office Remodel | Paint, Repair, and replace carpet in office, explore repurposing community center for fitness center or other use | 51169-00 | GC | Capital Plan | 150000 | 0 | 150000 |  | Not Started
Foxdale Village | 2025 | Clubhouse / Office Furniture | Clubhouse Furniture | 51160-06 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Foxdale Village | 2025 | Electrical distribution | Inspect and repair lighting controllers on all buildings Contingency for electrical panel upgrades/replacements starting | 51140-00 | GC | Capital Plan | 27500 | 25000 | 2500 |  | In Progress
Foxdale Village | 2025 | Electrical distribution | Electrical service and distribution equipment, Phased replacement | 51140-00 | GC | Capital Plan | 57400 | 0 | 57400 |  | Not Started
Foxdale Village | 2025 | Fire Alarm System | Lender PCR Item- $2,000- Repair the main fire alarm system which indicates "trouble" and perform the expired annual insp | 51993-00 | PMC | Capital Plan | 1000 | 4284 | -3284 |  | Completed
Foxdale Village | 2025 | Infrared Scan of Electrical Equipment | Equity PCA Item 5.3- $6,000- An infrared (IR) scan tag was observed at an electrical service entrance, the date on the t | 51993-01 | GC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
Foxdale Village | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 351235 | 0 | 351235 |  | Reserve
Foxdale Village | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 183884 | 0 | 183884 |  | Reserve
Latitude at the Commons | 2025 | Landscape Cleanup and Enhancements | Concept Walk - Tree trimming | 84303 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Latitude at the Commons | 2025 | Asphalt Coating | Seal Coat parking lot | 84204 | GC | Capital Plan | 89000 | 26700 | 62300 |  | In Progress
Latitude at the Commons | 2025 | Stripe parking areas | Stripe Parking Lots | 84201 | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
Latitude at the Commons | 2025 | Sidewalks | Sidewalk Repairs H - Sunken and uplifted sidewalks at the front of buildings | 84115 | GC | Capital Plan | 5200 | 1560 | 3640 |  | In Progress
Latitude at the Commons | 2025 | ADA parking & curb cuts | Need ADA signage and poles LPCA - ADA compliant parking spaces are required to have a sign with the International Symbo | 83520 | PMC | Capital Plan | 9000 | 0 | 9000 |  | Not Started
Latitude at the Commons | 2025 | Pavement | Crack fill large crack running in the center of the drive aisle LPCA - Localized cracking was observed in the center of | 84204 | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
Latitude at the Commons | 2025 | Flatwork Repairs | LPCA (PR-90) - Two vertical-separation trip hazards were observed. One was at the north entrance to the breezeway of Bui | 84115 | PMC | Capital Plan | 1000 | 503 | 497 |  | In Progress
Latitude at the Commons | 2025 | Erosion control | Concept Walk - Required in two separate locations per management. They are currently digging a trench to release, howeve | 84517 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Latitude at the Commons | 2025 | Resurface swimming pool | Resurface Pool | 84095 | GC | Capital Plan | 45000 | 13500 | 31500 |  | In Progress
Latitude at the Commons | 2025 | Swimming pool furniture | Concept Walk - Pool umbrellas | 84360 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Latitude at the Commons | 2025 | Dumpster enclosures | Paint Enclosures | 84111 | GC | Capital Plan | 7500 | 2250 | 5250 |  | In Progress
Latitude at the Commons | 2025 | Repair exterior stair treads and stringers | Stairs, Treads, and stringers are bare wood they are in good shape - need sealant | 84114 | GC | Capital Plan | 72000 | 21600 | 50400 |  | In Progress
Latitude at the Commons | 2025 | Repair balcony framing & decking | Landings and balconies are bare wood - need sealant | 84104 | GC | Capital Plan | 60000 | 18000 | 42000 |  | In Progress
Latitude at the Commons | 2025 | Gutters & downspouts | Clean and repitch gutters throughout property H - The roof and gutters at Garage G is damaged. | 83439 | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
Latitude at the Commons | 2025 | Sealants & caulking | Seal all seams on face nailed siding | 84102 | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
Latitude at the Commons | 2025 | Repair / replace cement fiber siding | Remove and replace buckling siding on 5 gable ends of buildings | 84206 | GC | Capital Plan | 46000 | 13800 | 32200 |  | In Progress
Latitude at the Commons | 2025 | Breezeway Missing/Exposed Nails | H - Breezeway at building missing/exposed nails on the stairway for building 2184 and 2210 | 84120 | GC | Capital Plan | 1000 | 300 | 700 |  | In Progress
Latitude at the Commons | 2025 | Exterior building | Corner to corner point of repaired areas. | 84101 | GC | Capital Plan | 54000 | 16200 | 37800 |  | In Progress
Latitude at the Commons | 2025 | Repair / replace wood trim | Replace rotted wood | 84105 | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
Latitude at the Commons | 2025 | Flooring Repairs | H - Repair carpets with trip hazards in units 115, 118, 121, 123, 127, 128, 133, 212, 234, 432, 613, 625, 827, 914, 922, | 83304.0 | PMC | Capital Plan | 20736 | 0 | 20736 |  | Not Started
Latitude at the Commons | 2025 | Replace old smoke detectors | H - Majority of units. These devices have an EUL of 7-10. The majority of smoke detectors were of original installation. | 83236 | PMC | Capital Plan | 32400 | 0 | 32400 |  | Not Started
Latitude at the Commons | 2025 | Replace Smoke Detectors in observed units | H - Smoke detectors missing in units: 212, 234, 726, 1021, 1114 | 83236 | PMC | Capital Plan | 375 | 0 | 375 |  | Not Started
Latitude at the Commons | 2025 | Clean Dryer vents | Dryer Vent Cleaning | 84106 | GC | Capital Plan | 21600 | 6480 | 15120 |  | In Progress
Latitude at the Commons | 2025 | Window Repairs | H - Windows in units 137, 213, and 417 are in need of repair. | 84304.0 | PMC | Capital Plan | 2097 | 646 | 1451 |  | In Progress
Latitude at the Commons | 2025 | Missing Kitchen cabinet drawer front | H - Unit 117 has missing drawer front in kitchen | 83212 | PMC | Capital Plan | 200 | 0 | 200 |  | Not Started
Latitude at the Commons | 2025 | Patio screening on remaining units | Concept Walk - Add patio screen doors | 84215 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Latitude at the Commons | 2025 | Fire Stops | Install fire stops in every unit | 84211 | PMC | Capital Plan | 28224 | 80719 | -52495 |  | Completed
Latitude at the Commons | 2025 | Golf Cart | Concept Walk - not included in personal property list. Currently have 4 carts on site | 83375 | PMC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
Latitude at the Commons | 2025 | Domestic Hot Water Heater | H - Rust damage on the DHW heater for units 522, 925, and 1217 | 84476 | GC | Capital Plan | 4485 | 1346 | 3140 |  | In Progress
Latitude at the Commons | 2025 | Electrical Distribution | Repair timers or photo cells | 84210 | GC | Capital Plan | 9000 | 2700 | 6300 |  | In Progress
Latitude at the Commons | 2025 | Exit Sign | H - Exit sign is damaged at 2210 and 2175 buildings | 84239 | GC | Capital Plan | 376 | 113 | 263 |  | In Progress
Latitude at the Commons | 2025 | Add lighting | Concept Walk - exterior lighting is lacking, should supplement the existing lighting to ensure it's well lit at night | 84210 | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
Latitude at the Commons | 2025 | LED Upgrade - Exterior Common Area Lighting | Hillmann Green Energy Audit - EEM No. 7 | 84210 | PMC | Capital Plan | 4546 | 2222 | 2324 |  | In Progress
Latitude at the Commons | 2025 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 271880 | 0 | 271880 |  | Reserve
Latitude at the Commons | 2025 | Construction Management Fee | CM Fees | 84505.0 | GC | CM Fee | 50381 | 0 | 50381 |  | Reserve
Oak Park Monrovia | 2025 | Landscape Cleanup and Enhancements | DPCA 3.1.4 / EPCA 3.2.4 - Landscape areas were observed to be eroded with exposed irrigation lines at significant areas | 51045-00 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Oak Park Monrovia | 2025 | Erosion control | Fill areas of erosion around buildings and flower beds throughout property. Specifically areas that have exposed PVC irr | 51086-00 | GC | Capital Plan | 17500 | 5250 | 12250 |  | In Progress
Oak Park Monrovia | 2025 | Landscaping | Tree trim - building clearance throughout property | 51043-00 | PMC | Capital Plan | 28500 | 0 | 28500 |  | Not Started
Oak Park Monrovia | 2025 | Carports / Garages | Repair damaged coating in parking structure at spots 65, 66 and 68. Also, extend routed and repair expansion joint at ra | 51172-00 | GC | Capital Plan | 5250 | 1575 | 3675 |  | In Progress
Oak Park Monrovia | 2025 | Mold Remediation | Mold Remediation | 51180-00 | PMC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
Oak Park Monrovia | 2025 | Termite Remediation | Termite Remediation - tent and local treatment (per Ecola remediation proposal) | 51992-00 | PMC | Capital Plan | 57400 | 0 | 57400 |  | Not Started
Oak Park Monrovia | 2025 | Roof framing | Inspect all mansard roofs and repair any damage to coping/façade of building to ensure areas are secure to prevent leaki | 51070-00 | GC | Capital Plan | 47500 | 14250 | 33250 |  | In Progress
Oak Park Monrovia | 2025 | Repair patio/balcony railings | Repair/replace areas of rotted/failing wood railings on balconies. | 51077-00 | GC | Capital Plan | 75000 | 22500 | 52500 |  | In Progress
Oak Park Monrovia | 2025 | Repair balcony framing & decking | DPCA 3.2.7 / EPCA 4.5 Select balconies at the buildings were observed to have deteriorated wood members at the balcony d | 51072-00 | GC | Capital Plan | 140000 | 42000 | 98000 |  | In Progress
Oak Park Monrovia | 2025 | Asphalt composite shingle roofing | Repair and add proper flashing to the roofing of the ganged mains and meter bank closets. | 51060-00 | GC | Capital Plan | 21500 | 6450 | 15050 |  | In Progress
Oak Park Monrovia | 2025 | Repair stucco | Repairs throughout property, also repair cement plaster at northeaster corner of western wing of parking garage. | 51075-00 | GC | Capital Plan | 40000 | 12000 | 28000 |  | In Progress
Oak Park Monrovia | 2025 | Interior Hallway painting | Repair drywall and paint all interior hallways & Common Areas | 51160-00 | GC | Capital Plan | 94000 | 28200 | 65800 |  | In Progress
Oak Park Monrovia | 2025 | Exterior building | Paint Exterior of Property (incl. Parking Garages) | 51080-00 | GC | Capital Plan | 234000 | 70200 | 163800 |  | In Progress
Oak Park Monrovia | 2025 | Signage - Building identification | Adding signage to locate the leasing office - specifically on the North Building to guide tenants to the South Building | 51030-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Oak Park Monrovia | 2025 | Common Area Greenspace Enhancements | Placeholder for greenspace improvements (e.g. dog park, bocce ball, etc.) | 51160-00 | PMC | Capital Plan | 24000 | 5162 | 18838 |  | In Progress
Oak Park Monrovia | 2025 | Smoke and Fire Detection System, central panel | PCA 3.3.10: Current inspection tags were not observed on the main control panel, building panels or elevator panels. Ins | 51140-00 | PMC | Capital Plan | 1500 | 403 | 1097 |  | In Progress
Oak Park Monrovia | 2025 | Water pressure regulator / back-flow preventer | Install backflow prevention device at north building. Currently leaking. | 51130-00 | GC | Capital Plan | 2000 | 600 | 1400 |  | In Progress
Oak Park Monrovia | 2025 | Stormwater sump pump system, replace | PCA 3.3.4. It was observed that the South Building parking garage had failed, and control panel could not be energized a | 51130-00 | GC | Capital Plan | 8800 | 2640 | 6160 |  | In Progress
Oak Park Monrovia | 2025 | Hydro-jetting & Camera inspection | PCA 5.1 -It appears that no hydro-jetting and camera inspection has been performed at the property. Industry best practi | 51134-00 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Oak Park Monrovia | 2025 | Seismic shut off valve - install | DPCA 3.3.6 / EPCA 5.3 -The observed natural gas services lacked seismic shutoff valves to prevent dangerous gas leaks in | 51990-00 | GC | Capital Plan | 39000 | 11700 | 27300 |  | In Progress
Oak Park Monrovia | 2025 | MAUs - Ventilation System | DPCA 3.3.1 / EPCA 5.2 The MAUs at each building were in poor overall condition. The unit at the North Building unit was | 51120-00 | GC | Capital Plan | 32000 | 9600 | 22400 |  | In Progress
Oak Park Monrovia | 2025 | Electrical Distribution Center and Unit Electrical Pane | PCA 3.3.3 Exterior electrical service and distribution equipment was generally from the original construction and approx | 51140-00 | GC | Capital Plan | 360000 | 108000 | 252000 |  | In Progress
Oak Park Monrovia | 2025 | Common area light fixtures | Replace all patio lighting with new LED lighting. | 51141-00 | GC | Capital Plan | 23500 | 7050 | 16450 |  | In Progress
Oak Park Monrovia | 2025 | Replace garage lighting | Replace existing garage lighting with LED. | 51141-00 | GC | Capital Plan | 15000 | 4500 | 10500 |  | In Progress
Oak Park Monrovia | 2025 | Contingency | Construction Contingency | 51175-00 | GC | Contingency | 90693 | 0 | 90693 |  | Reserve
Oak Park Monrovia | 2025 | Construction Management Fee | CM Fees | 51190-00 | GC | CM Fee | 69407 | 0 | 69407 |  | Reserve
Orchard Glen | 2025 | Landscape Cleanup and Enhancements | EPCA 4.4.1 - Cut back trees in contact with roofs. Initial tree trim, landscape cleanup, entry and tour path enhancement | 51045-00 | GC | Capital Plan | 100000 | 0 | 100000 |  | Not Started
Orchard Glen | 2025 | Asphalt Coating | EPCA 3.2.2 - The asphalt seal coat and pavement markings and striping appeared to be in fair to poor condition. The seal | 51053-00 | GC | Capital Plan | 121000 | 36300 | 84700 |  | In Progress
Orchard Glen | 2025 | Accessibility | EPCA 7.1 - The leasing office restroom lacked scald protection at the exposed lavatory piping. Installation is recommend | 51091-00 | GC | Capital Plan | 400 | 400 | 0 |  | Completed
Orchard Glen | 2025 | Repair / replace swimming pool pumps | Pool Pumps | 51026-00 | GC | Capital Plan | 6800 | 4080 | 2720 |  | In Progress
Orchard Glen | 2025 | Fences & gates - patios | EPCA 3.2.3 - The ground floor patio fence (wood guardrail) located between Units 85 and 87 was noted to be leaning outwa | 51076-00 | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Orchard Glen | 2025 | Carports / Garages | Repair carports and paint post and pearling EPCA 4.4.1 - Repair of impact damage to metal carport canopies. EPCA 3.2.9 - | 51172-00 | GC | Capital Plan | 28000 | 16800 | 11200 |  | In Progress
Orchard Glen | 2025 | Stripe parking areas | Striping of Parking Lots | 51053-00 | GC | Capital Plan | 23000 | 6900 | 16100 |  | In Progress
Orchard Glen | 2025 | Repair ADA deficiencies | LPCA - No ADA access aisles were observed in three ADA parking spaces. No insulation under the common area restroom sink | 51091-00 | GC | Capital Plan | 1500 | 450 | 1050 |  | In Progress
Orchard Glen | 2025 | Sidewalks | LPCA - limited sidewalk cracks were observed by the west playground equipment LPCA (PR-90) - a limited concrete sidewalk | 51091-00 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
Orchard Glen | 2025 | Fences & gates - site perimeter | EPCA 3.2.7 - Damage/deterioration of the metal security perimeter fencing and the welded steel pool fencing was noted in | 51076-00 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Orchard Glen | 2025 | Retaining walls | The retaining walls appeared to be in fair condition. The walls appeared to exhibit lateral movement (leaning) and separ | 51085-00 | GC | Capital Plan | 62900 | 62900 | 0 |  | Completed
Orchard Glen | 2025 | Resurface swimming pool | Pool Resurfacing | 51023-00 | GC | Capital Plan | 51000 | 30600 | 20400 |  | In Progress
Orchard Glen | 2025 | Fences & gates - swimming pool | Swimming Pool Gate Repairs | 51076-00 | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Orchard Glen | 2025 | Replacement of metal standoff post bases | EPCA 4.2 - The metal standoff bases at the wood walkway and stair posts near Unit 169 were exhibiting corrosion and pote | 51070-00 | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Orchard Glen | 2025 | Replacement of damaged concrete treads at stairs | EPCA 4.2 - The concrete stair treads were noted with cracks (varying degrees) and spalling areas with exposed steel rein | 51090-00 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Orchard Glen | 2025 | WDO Treatment/Repairs | LPCA - Subsequent to thesite visit,managementprovided a WDOinspection reportconducted on 4/29/25 by TerminixInternationa | 51992-00 | PMC | Capital Plan | 160000 | 37109 | 122891 |  | In Progress
Orchard Glen | 2025 | WDO Inspection | LPCA - Subsequent to the site visit, management provided a WDO inspection report conducted on 4/29/25 by Terminix Intern | 51992-00 | PMC | Capital Plan | 2000 | 464 | 1536 |  | In Progress
Orchard Glen | 2025 | Concrete deck / floor fill | repair and paint balconies | 51072-00 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Orchard Glen | 2025 | Wall framing | replace damaged framing in chimney | 51070-00 | GC | Capital Plan | 48000 | 48000 | 0 |  | Completed
Orchard Glen | 2025 | Balcony framing & decking | Repair balcony framing & decking | 51072-00 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Orchard Glen | 2025 | Balconies/handrails/guardrails | Patio fence repairs and paint EPCA 4.2 - Elevated balconies and walkways are provided with wood guardrails, where posts | 51077-00 | GC | Capital Plan | 18000 | 72000 | -54000 |  | Completed
Orchard Glen | 2025 | Expansion joints | Repair exterior expansion joints | 51070-00 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Orchard Glen | 2025 | Asphalt composite shingle roofing | EPCA 4.4.1 - Replacement of half of the shingled roofs within the next year. EPCA 4.4.1 - Replacement of half of the shi | 51061-00 | GC | Capital Plan | 80000 | 24000 | 56000 |  | In Progress
Orchard Glen | 2025 | Repairs to roof systems | EPCA 4.4.1 - Immediate repairs to roof system to maintain water-tightness leading up to replacement. Immediate Repairs t | 51062-00 | GC | Capital Plan | 45000 | 13500 | 31500 |  | In Progress
Orchard Glen | 2025 | Gutters & downspouts | Gutters & Downspout Repairs | 51071-00 | GC | Capital Plan | 244800 | 244800 | 0 |  | Completed
Orchard Glen | 2025 | Sealants & caulking | Sealants and Caulking for Roof | 51062-00 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Orchard Glen | 2025 | Flashing | Flashing Repairs | 51062-00 | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Orchard Glen | 2025 | Repair / replace wall shake shingles | Post cost is inclusive of dry rot repair Replace shake siding, T111 and window wall siding and repair textured siding | 51075-00 | GC | Capital Plan | 921600 | 921600 | 0 |  | Completed
Orchard Glen | 2025 | Exterior building paint | Exterior Painting | 51080-00 | GC | Capital Plan | 433550 | 390195 | 43355 |  | In Progress
Orchard Glen | 2025 | Repair / replace wood trim | EPCA 4.4.1 - Contingency for replacement of damaged wood decking and fascia during the first phase of roof replacements; | 51082-00 | GC | Capital Plan | 151200 | 151200 | 0 |  | Completed
Orchard Glen | 2025 | Remove Microbial Growth | LPCA (PR-90) - CBRE observed microbial growth. Specifically, these conditions were observed at the bathtub of Unit 3873- | 52111-00 | PMC | Capital Plan | 1100 | 30373 | -29273 |  | Completed
Orchard Glen | 2025 | Down Units | EPCA 6.5.2 - At the time of the site assessment, one residential unit (Unit 142) was identified to be in an un-rentable/ | 52111-00 | PMC | Capital Plan | 20000 | 35021 | -15021 |  | Completed
Orchard Glen | 2025 | Damaged Ceiling | LPCA (PR-90) - During an additional inspection conducted by the Lender, ceiling damage and possible water intrusion were | 52111-00 | PMC | Capital Plan | 700 | 1695 | -995 |  | Completed
Orchard Glen | 2025 | Roach Treatment | LPCA (PR-90) - During an additional inspection conducted by the Lender, evidence of roaches was observed in Unit 1-10. C | 51992-00 | PMC | Capital Plan | 350 | 81 | 269 |  | In Progress
Orchard Glen | 2025 | Back-flow preventer | EPCA 5.1 - The two 6" reduced pressure backflow prevention devices appear to be original and should be replaced. Annual | 51130-00 | PMC | Capital Plan | 16000 | 142413 | -126413 |  | Completed
Orchard Glen | 2025 | Split HVAC System (Move to HVAC) | EPCA 5.2 - The split heat pump system serving the clubhouse is more than 20 years old. Based on age and EUL, replacement | 51120-00 | PMC | Capital Plan | 24000 | 3786 | 20214 |  | In Progress
Orchard Glen | 2025 | Stormwater Pipe Repair | Clean storm drains | 51131-00 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Orchard Glen | 2025 | Natural Gas Seismic Shutoff | EPCA 5.3 - Seismic shut-off valves were not installed on the natural gas services. The property is located in a seismic | 51130-00 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Orchard Glen | 2025 | Green Up Program | Domestic Hot Water - Gas Tank Heater - Large, (0.95 TE), Qty 12, Apartments | 51990-00 | PMC | Capital Plan | 187200 | 12212 | 174988 |  | In Progress
Orchard Glen | 2025 | Green Up Program | Water Fixture - Kitchen Aerators, (1.2 gpm 100% Aerator Replacement), Qty 288, Apartments | 51990-00 | PMC | Capital Plan | 2880 | 0 | 2880 |  | Not Started
Orchard Glen | 2025 | Green Up Program | Water Fixture - Bathroom Aerators, (0.5 gpm 100% Aerator Replacement), Qty 320, Apartments | 51990-00 | PMC | Capital Plan | 3200 | 0 | 3200 |  | Not Started
Orchard Glen | 2025 | Green Up Program | Water Fixture - WaterSense Certified Showerheads, (1.25 gpm), Qty 294, 92% of Total Showerheads | 51990-00 | PMC | Capital Plan | 19110 | 0 | 19110 |  | Not Started
Orchard Glen | 2025 | Green Up Program | Water Fixture - WaterSense Certified Toilets, (0.8 gpf), Qty 240, 75% of Total Toilets | 51990-00 | PMC | Capital Plan | 108960 | 0 | 108960 |  | Not Started
Orchard Glen | 2025 | Electrical service and distribution, Ongoing Repalcemen | inspect and repair lighting controllers on all buildings | 51140-00 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Orchard Glen | 2025 | Contingency | Contingency Amount | 51180-00 | GC | Contingency | 166381 | 0 | 166381 |  | Reserve
Orchard Glen | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 174700 | 0 | 174700 |  | Reserve
Paddock Club | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84303 | PMC | Capital Plan | 20000 | 37500 | -17500 |  | Completed
Paddock Club | 2025 | Stripe parking areas | Stripe Parking Lots | 84201 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Paddock Club | 2025 | Asphalt Coating | Crack fill and double seal coat asphalt throughout property. Lender PCA Item- Damaged pavement consisting of linear crac | 84204 | GC | Capital Plan | 425000 | 425000 | 0 |  | Completed
Paddock Club | 2025 | ADA parking & curb cuts | Lender PCA Item- Inadequate number of accessible parking and van accessible parking spaces at the leasing office. Instal | 84221 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Paddock Club | 2025 | Sidewalks | Repair cracked/broken sidewalks throughout property. | 84115 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Paddock Club | 2025 | Fences & gates - site perimeter | Repair deck walkways/fencing throughout property. Some areas have broken stairs and missing areas of pickets. Railing r | 84205 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Paddock Club | 2025 | Retaining walls | Repair retaining walls where railroad ties are rotted out. Lender PCA Item- Damage was observed at a section of retaini | 84434 | GC | Capital Plan | 12500 | 48000 | -35500 |  | Completed
Paddock Club | 2025 | Landscaping | Tree trim around property, especially around the lake. Clean up of brush foliage around lakes, as well. 1st call biddin | 84303 | GC | Capital Plan | 125000 | 125000 | 0 |  | Completed
Paddock Club | 2025 | Resurface swimming pool | Resurface main pool at clubhouse. | 84095 | GC | Capital Plan | 42750 | 42750 | 0 |  | Completed
Paddock Club | 2025 | Replace swimming pool coping | Deck-O-Seal coping around pool. | 84361 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Paddock Club | 2025 | Repair swimming pool deck | Clean pool deck, fill cracks and seal. Also, clean and resurface concreted steps going down to pool from clubhouse. | 84361 | GC | Capital Plan | 22500 | 22500 | 0 |  | Completed
Paddock Club | 2025 | Pergola Court | Replace any damaged/rotted decking around the clubhouse and pool area. | 84105 | GC | Capital Plan | 26500 | 26500 | 0 |  | Completed
Paddock Club | 2025 | ADA Signage | Add ADA signage at clubhouse for wheelchair lift. | 84103 | GC | Capital Plan | 850 | 850 | 0 |  | Completed
Paddock Club | 2025 | Drainage | Add drainage in areas where water accumulates at base of retaining walls at building 17 | 84517 | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
Paddock Club | 2025 | Asphalt composite shingle roofing | Moderate Roof Tune up on every building. This would include securing shingles, flashing, etc. Repairs of moderate water | 84433 | GC | Capital Plan | 75000 | 75000 | 0 |  | Completed
Paddock Club | 2025 | Repair / replace cement fiber siding | Repair/replace areas of failed hardie board and paint to match throughout property | 84206 | GC | Capital Plan | 68500 | 68500 | 0 |  | Completed
Paddock Club | 2025 | Repair / replace vinyl siding | Repair areas of damaged vinyl siding and clean vinyl covered in mold and grime throughout property. Also, secure vinyl s | 84206 | GC | Capital Plan | 68500 | 68500 | 0 |  | Completed
Paddock Club | 2025 | Repair / replace wood trim | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. Include ALL buildings throughout property. | 84105 | GC | Capital Plan | 95000 | 95000 | 0 |  | Completed
Paddock Club | 2025 | Clean Drier vents | Clean dryer vents throughout property. | 84106 | GC | Capital Plan | 25200 | 25200 | 0 |  | Completed
Paddock Club | 2025 | Water Damage in Units | Lender PCA Item- Partner recommends repair of any damaged finishes subsequent to the plumbing repairs in Units 1 and 146 | 83465 | PMC | Capital Plan | 3000 | 12530 | -9530 |  | Completed
Paddock Club | 2025 | Co 2 detectors | Install Co2 detectors in each unit. Lender PCR Item- Due to the presence of gas-fire water heaters at each unit, carbon | 82131 | PMC | Capital Plan | 23520 | 0 | 23520 |  | Not Started
Paddock Club | 2025 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | 84239 | PMC | Capital Plan | 16269 | 0 | 16269 |  | Not Started
Paddock Club | 2025 | Hard turn/ renovation units | Lender PCA Item- Partner recommends completing the hard turn/ renovation in Units 130 and 281, which includes repair of | 84431 | PMC | Capital Plan | 10000 | 17250 | -7250 |  | Completed
Paddock Club | 2025 | Clubhouse / Office Remodel | Placeholder budget, paint the blue framed wall areas - possibly use 1st call to renovate kitchen if budget permits | 84208 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Paddock Club | 2025 | Clubhouse / Office Furniture | Clubhouse Furniture | 84306 | PMC | Capital Plan | 50000 | 66212 | -16212 |  | Completed
Paddock Club | 2025 | Fitness Center Remodel | Flooring and walls ok, misc allowance - update lighting in boxing closet to match main gym and add Tonal or equivalent w | 84190 | PMC | Capital Plan | 5000 | 5465 | -465 |  | Completed
Paddock Club | 2025 | Fitness Equipment | Replace broken items, add equipment- functional trainer, stair stepper | 84190 | PMC | Capital Plan | 18000 | 19675 | -1675 |  | Completed
Paddock Club | 2025 | Pool Area Remodel | Placeholder budget | 84361 | PMC | Capital Plan | 10000 | 5620 | 4380 |  | In Progress
Paddock Club | 2025 | Pool Furniture | New furniture and games needed | 84360 | PMC | Capital Plan | 50000 | 57216 | -7216 |  | Completed
Paddock Club | 2025 | Picnic/Grill Area Remodel | Placeholder budget | 84203 | PMC | Capital Plan | 5000 | 18550 | -13550 |  | Completed
Paddock Club | 2025 | Picnic/Grill Furniture | Placeholder budget | 84340 | PMC | Capital Plan | 5000 | 7950 | -2950 |  | Completed
Paddock Club | 2025 | Access Control System | Add at maintenance shop. Fix system so that it can track which residents enter and leave, the manager said the system ca | 84275 | PMC | Capital Plan | 8000 | 0 | 8000 |  | Not Started
Paddock Club | 2025 | Mailboxes | Misc repairs - add concrete pad and USPS parcel boxes. | 84260 | GC | Capital Plan | 2000 | 7000 | -5000 |  | Completed
Paddock Club | 2025 | Package Lockers | Look at adding to laundry room. Budget 1 locker per 4-5 units @$400/locker | 84305 | PMC | Capital Plan | 33600 | 13600 | 20000 |  | In Progress
Paddock Club | 2025 | Laundry Room Renovation | Replace fluorescent lights, clean fans and paint ceiling where needed, add TV - TAM to negotiate laundry contract to inc | 84240 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Paddock Club | 2025 | Laundry Room Furniture | Add seating | 84240 | PMC | Capital Plan | 4000 | 0 | 4000 |  | Not Started
Paddock Club | 2025 | Office Computers | Have 2 new ones, budget for 1 new | 83265 | PMC | Capital Plan | 2000 | 13592 | -11592 |  | Completed
Paddock Club | 2025 | Plumbing Repairs | Lender PCR Item- Evidence of leaks and faulty piping was observed. According to the site escort, the piping leaks are re | 84209 | PMC | Capital Plan | 4800 | 75638 | -70838 |  | Completed
Paddock Club | 2025 | HVAC inspection and maintenance | Clean foliage around condensors and raise AC units with HVAC pads where needed. | 84217 | GC | Capital Plan | 33600 | 33600 | 0 |  | Completed
Paddock Club | 2025 | Electrical distribution | Electrical Distribution | 84210 | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Paddock Club | 2025 | Common area light fixtures | Replace wallpacks on all buildings | 84112 | GC | Capital Plan | 28000 | 28000 | 0 |  | Completed
Paddock Club | 2025 | Replace breezeway lights | Install LED pole lights on pre-existing posts throughout the propety | 84112 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Paddock Club | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 282911 | 0 | 282911 |  | Reserve
Paddock Club | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 92400 | 0 | 92400 |  | Reserve
Rancho Cordova | 2025 | Asphalt Coating | Slurry Coat & Seal | 51050-00 | GC | Capital Plan | 64000 | 64000 | 0 |  | Completed
Rancho Cordova | 2025 | Stripe parking areas | PNA - Stripe parking areas | 51053-00 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Rancho Cordova | 2025 | ADA parking & curb cuts | Lender PCA - There is a van accessible parking space near the leasing office that is missing a pole-mounted sign. | 51091-00 | PMC | Capital Plan | 350 | 101 | 249 |  | In Progress
Rancho Cordova | 2025 | Sidewalks | PNA - Repair failing sidewalks | 51091-00 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Rancho Cordova | 2025 | Asphalt pavement | PNA - Remove and replace failing asphalt EPCA - All | 51050-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Rancho Cordova | 2025 | Fences & gates - site perimeter | PNA - Rough iron repairs | 51076-00 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Rancho Cordova | 2025 | Patio and Fencing | EPCA - Repair areas of leaning wood patio enclosures as needed. Clean and restrain the fence with visible signs of deter | 51076-00 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Rancho Cordova | 2025 | Landscaping | PNA - Tree trim and branch removal | 51045-00 | PMC | Capital Plan | 32000 | 0 | 32000 |  | Not Started
Rancho Cordova | 2025 | Playground equipment | PNA - Fall Zone Material | 51029-00 | GC | Capital Plan | 9800 | 9800 | 0 |  | Completed
Rancho Cordova | 2025 | Storm sewer piping | PNA - Clean out storm sewer catch basin | 51130-00 | GC | Capital Plan | 8000 | 8000 | 0 |  | Completed
Rancho Cordova | 2025 | Exterior Wall framing | Building Framing repairs | 51070-00 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
Rancho Cordova | 2025 | Expansion joints | Foundation Expansion Joint Repairs | 51090-00 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Rancho Cordova | 2025 | Asphalt composite shingle roofing | PNA - Shingle roof tune up, loose and hanging shingles were observed | 51062-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Rancho Cordova | 2025 | Modified bitumen membrane Roof Repairs | PNA - Clean flat roofs and repair minor areas of potential water intrusion | 51062-00 | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Rancho Cordova | 2025 | Gutters & downspouts | PNA - Cleanout gutters and scuppers | 51071-00 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Rancho Cordova | 2025 | Sealants & caulking | Roofing Sealants & Caulking Repairs | 51062-00 | GC | Capital Plan | 4500 | 4500 | 0 |  | Completed
Rancho Cordova | 2025 | Repair / replace wood siding | PNA - Replace rotted T1-11 | 51075-00 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
Rancho Cordova | 2025 | Repair stucco | PNA - Repair stucco, mansard/hip wall | 51075-00 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Rancho Cordova | 2025 | Exterior building | PNA - Repaint community | 51080-00 | GC | Capital Plan | 188000 | 188000 | 0 |  | Completed
Rancho Cordova | 2025 | Repair / replace wood trim | PNA - Repair/replace rotted trim | 51082-00 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Rancho Cordova | 2025 | Repair/Replace Soffit | EPCA - Allowance to repair and replace all dry-rotted wood siding and soffits of the two-story residential buildings | 51075-00 | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
Rancho Cordova | 2025 | Smoke Alarm | EPCA - Budget to replace the existing smoke alarms based on age and useful life. The NFPA requires that smoke alarms not | 51993-00 | PMC | Capital Plan | 10920 | 0 | 10920 |  | Not Started
Rancho Cordova | 2025 | Fire Stops | Install Fire Stops | 51993-00 | PMC | Capital Plan | 8075 | 6119 | 1956 |  | In Progress
Rancho Cordova | 2025 | Unit deferred maintenance | EPCA - Remediate select bathrooms with signs of organic growth observed in Units 16, 25, 35, 45, 61 & 70 LPCA - Unit 70 | 52111-00 | PMC | Capital Plan | 12500 | 11546 | 954 |  | In Progress
Rancho Cordova | 2025 | Common area light fixtures | PNA - Building wall packs LPCA - Budget for installation of building wall packs throughout the site. | 51141-00 | GC | Capital Plan | 18500 | 18500 | 0 |  | Completed
Rancho Cordova | 2025 | Replace Pole light fixtures | PNA - Pole lights throughout the parking lot LPCA - Replacement of pole lights throughout the parking area. | 51141-00 | GC | Capital Plan | 28500 | 28500 | 0 |  | Completed
Rancho Cordova | 2025 | Replace electric panels | EPCA - Budget for phased replacement of the apartment Zinsco electrical distribution panels based on age and a recall du | 51140-00 | GC | Capital Plan | 47500 | 47500 | 0 |  | Completed
Rancho Cordova | 2025 | Contingency | Contingency | 51180-00 | GC | Contingency | 31107 | 0 | 31107 |  | Reserve
Rancho Cordova | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 32663 | 0 | 32663 |  | Reserve
Regency & Lexington | 2025 | Initial Lanscape Cleanup | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 51045-00 | PMC | Capital Plan | 10000 | 602 | 9398 |  | In Progress
Regency & Lexington | 2025 | Storm sewer piping | Storm water drainage repairs in courtyards | 51130-00 | GC | Capital Plan | 16714 | 0 | 16714 |  | Not Started
Regency & Lexington | 2025 | Asphalt Coating | Fill asphalt cracks Regency Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in go | 51053-00 | GC | Capital Plan | 91929 | 42900 | 49029 |  | In Progress
Regency & Lexington | 2025 | ADA parking & curb cuts | Repair trip hazards | 51091-00 | GC | Capital Plan | 24429 | 38000 | -13571 |  | Completed
Regency & Lexington | 2025 | Landscape irrigation | Inspect and repair Irrigation | 51046-00 | GC | Capital Plan | 20571 | 32000 | -11429 |  | Completed
Regency & Lexington | 2025 | Landscaping | Tree trim | 51043-00 | PMC | Capital Plan | 13000 | 300 | 12700 |  | In Progress
Regency & Lexington | 2025 | Resurface swimming pool | Resurface two pools | 51023-00 | GC | Capital Plan | 44500 | 71200 | -26700 |  | Completed
Regency & Lexington | 2025 | Repair / replace swimming pool pumps | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool d | 51026-00 | GC | Capital Plan | 7000 | 11200 | -4200 |  | Completed
Regency & Lexington | 2025 | Fences & gates - swimming pool | Adjust closers on pool gates | 51076-00 | GC | Capital Plan | 7000 | 14000 | -7000 |  | Completed
Regency & Lexington | 2025 | Parking Lot Cleaning | Power wash garage/parking walls and asphalt | 51050-00 | GC | Capital Plan | 10000 | 20000 | -10000 |  | Completed
Regency & Lexington | 2025 | Landscape irrigation | Irrigation repairs & upgrades | 51046-00 | PMC | Capital Plan | 7500 | 2007 | 5493 |  | In Progress
Regency & Lexington | 2025 | Termite Remediation | Regency - Drywood termite local treatments | 51992-00 | PMC | Capital Plan | 19000 | 18010 | 990 |  | In Progress
Regency & Lexington | 2025 | Termite Remediation | Regency - Subterranean termite treatment and baiting | 51992-00 | PMC | Capital Plan | 15400 | 14598 | 802 |  | In Progress
Regency & Lexington | 2025 | Wall framing | Replace damaged framing in gable ends | 51070-00 | GC | Capital Plan | 4500 | 9000 | -4500 |  | Completed
Regency & Lexington | 2025 | Replace hardware | PCA 4.2 - Building C, Unit 37 – Immediately replace the existing bolts with adequately sized bolts and washers. | 51156-00 | GC | Capital Plan | 500 | 500 | 0 |  | Completed
Regency & Lexington | 2025 | Install metal hardware | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces | 51092-00 | GC | Capital Plan | 67500 | 107500 | -40000 |  | Completed
Regency & Lexington | 2025 | Shore Maintenance Shed | PCA 4.2- Maintenance Shed - Immediately temporarily shore the unsupported double top plate. Engage licensed engineer to | 51998-00 | GC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
Regency & Lexington | 2025 | Replace sheathing | PCA 4.2 - Replace deteriorated sheathing and joists at roof eaves, as required. | 51070-00 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
Regency & Lexington | 2025 | Allowance for sectional replacement of damaged sheathin | PCA 4.2 - Allowance for sectional replacement of damaged sheathing and joists at carports. | 51172-00 | GC | Capital Plan | 5000 | 2500 | 2500 |  | In Progress
Regency & Lexington | 2025 | Repair exterior stair railings | Secure railings | 51077-00 | GC | Capital Plan | 12000 | 24000 | -12000 |  | Completed
Regency & Lexington | 2025 | Repair balcony framing & decking | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail PCA 4.2 - Repair wate | 51072-00 | GC | Capital Plan | 189643 | 236000 | -46357 |  | Completed
Regency & Lexington | 2025 | Expansion Joints | Expansion Joints | 51075-00 | GC | Capital Plan | 6000 | 12000 | -6000 |  | Completed
Regency & Lexington | 2025 | Asphalt composite shingle roofing Repair loose gravel s | Roof tune-up to include gravel. Reseal and secure gravel stop and drip edge. PCA 4.4.1 - Repair loose gravel stop and op | 51062-00 | GC | Capital Plan | 27000 | 125000 | -98000 |  | Completed
Regency & Lexington | 2025 | Gutters & downspouts Reconnect loose downspout. | Secure and clean gutters PCA 4.4.1 - Reconnect loose downspout. | 51071-00 | GC | Capital Plan | 12000 | 24000 | -12000 |  | Completed
Regency & Lexington | 2025 | Flashing | Repair flashing between stucco and t-111 | 51062-00 | GC | Capital Plan | 10000 | 20000 | -10000 |  | Completed
Regency & Lexington | 2025 | Sealants & caulking | Seal joints in t-111 | 51062-00 | GC | Capital Plan | 18000 | 36000 | -18000 |  | Completed
Regency & Lexington | 2025 | Repair / replace wood siding | Replace rotted t-111 siding | 51075-00 | GC | Capital Plan | 24000 | 48000 | -24000 |  | Completed
Regency & Lexington | 2025 | Exterior building | Paint community | 51080-00 | GC | Capital Plan | 239143 | 297600 | -58457 |  | Completed
Regency & Lexington | 2025 | Repair / replace wood trim | Replace rotted fascia and trim | 51082-00 | GC | Capital Plan | 36000 | 57600 | -21600 |  | Completed
Regency & Lexington | 2025 | Repair stucco | Some walls next to windows need patching and paint | 51075-00 | GC | Capital Plan | 3000 | 6000 | -3000 |  | Completed
Regency & Lexington | 2025 | Clubhouse / Office Remodel | No clubhouse, allowance for office | 51169-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Regency & Lexington | 2025 | Clubhouse / Office Furniture | Need seating for reception area in leasing office. | 51160-06 | PMC | Capital Plan | 4000 | 0 | 4000 |  | Not Started
Regency & Lexington | 2025 | Pool Area Remodel | Expand pool fenced area to make space for furniture | 51160-00 | GC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Regency & Lexington | 2025 | Pool Furniture | No furniture currently, need chaises and other furniture for main pool. Tables/chairs and armcharis only for 2nd pool d | 51011-00 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Regency & Lexington | 2025 | Picnic/Grill Area Remodel | Small grill area by pool, look at adding outdoor counter | 51160-04 | PMC | Capital Plan | 8000 | 0 | 8000 |  | Not Started
Regency & Lexington | 2025 | Picnic/Grill Furniture | Picnic tables or tables/chairs needed | 51160-04 | PMC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Regency & Lexington | 2025 | Playground equipment | Add seating and/or picnic tables year 1, budget for equipment replacement in year 4. | 51029-00 | GC | Capital Plan | 6000 | 10000 | -4000 |  | Completed
Regency & Lexington | 2025 | Need key trak for office | Key Track | 51990-02 | PMC | Capital Plan | 3500 | 0 | 3500 |  | Not Started
Regency & Lexington | 2025 | Security Camera System | Don't have anything, budget for a new system | 51993-00 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Regency & Lexington | 2025 | Back-flow preventer | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. | 51130-00 | PMC | Capital Plan | 2250 | 1856 | 394 |  | In Progress
Regency & Lexington | 2025 | Galvanized Pipe Replacement | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. | 51130-00 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Regency & Lexington | 2025 | Sanitary Sewer Piping | Number based on actual bid; $285 per cleanout, est. 12 cleanouts. $402 per storm drain, 11 cleanouts. Regency & Lexingto | 51134-00 | PMC | Capital Plan | 7842 | 26166 | -18324 |  | Completed
Regency & Lexington | 2025 | Pipe Repair at Building 1 Boiler | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could p | 51130-00 | GC | Capital Plan | 750 | 3750 | -3000 |  | Completed
Regency & Lexington | 2025 | Natural Gas Seismic Shutoff | Will confirm with Gas utiliity company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equippe | 51130-00 | GC | Capital Plan | 12000 | 6000 | 6000 |  | In Progress
Regency & Lexington | 2025 | Energy Retrofit | Echelon upfront costs | 51160-00 | PMC | Capital Plan | 38441 | 0 | 38441 |  | Not Started
Regency & Lexington | 2025 | HVAC Replacement | Large Rheem HVAC unit outside office looks very old and may need to be replaced | 51120-00 | GC | Capital Plan | 4500 | 0 | 4500 |  | Not Started
Regency & Lexington | 2025 | Electrical distribution | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Inf | 51140-00 | GC | Capital Plan | 28143 | 13800 | 14343 |  | In Progress
Regency & Lexington | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 127553 | 0 | 127553 |  | Reserve
Regency & Lexington | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 70154 | 0 | 70154 |  | Reserve
Regency & Lexington | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 51045-00 | PMC | Capital Plan | 10000 | 602 | 9398 |  | In Progress
Regency & Lexington | 2025 | Storm sewer piping | Storm water drainage repairs in courtyards | 51130-00 | GC | Capital Plan | 9286 | 0 | 9286 |  | Not Started
Regency & Lexington | 2025 | Asphalt Coating | Filll asphalt cracks | 51053-00 | GC | Capital Plan | 51071 | 0 | 51071 |  | Not Started
Regency & Lexington | 2025 | ADA parking & curb cuts | Repair trip hazards | 51091-00 | GC | Capital Plan | 13571 | 0 | 13571 |  | Not Started
Regency & Lexington | 2025 | Landscape irrigation | Inspect and repair Irrigation | 51046-00 | GC | Capital Plan | 11429 | 0 | 11429 |  | Not Started
Regency & Lexington | 2025 | Landscaping | Tree trim | 51043-00 | PMC | Capital Plan | 13000 | 300 | 12700 |  | In Progress
Regency & Lexington | 2025 | Resurface swimming pool | Resurface two pools | 51023-00 | GC | Capital Plan | 44500 | 0 | 44500 |  | Not Started
Regency & Lexington | 2025 | Repair / replace swimming pool pumps | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool d | 51026-00 | GC | Capital Plan | 7000 | 0 | 7000 |  | Not Started
Regency & Lexington | 2025 | Fences & gates - swimming pool | Adjust closers on pool gates | 51076-00 | GC | Capital Plan | 7000 | 0 | 7000 |  | Not Started
Regency & Lexington | 2025 | Parking Lot Cleaning | Power wash garage/parking walls and asphalt | 51050-00 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Regency & Lexington | 2025 | Termite Remediation | Lexington - Drywood termite local treatments | 51992-00 | PMC | Capital Plan | 22000 | 20854 | 1146 |  | In Progress
Regency & Lexington | 2025 | Termite Remediation | Lexington - Subterranean termite treatment and baiting | 51992-00 | PMC | Capital Plan | 10800 | 10237 | 563 |  | In Progress
Regency & Lexington | 2025 | Wall framing | Replace damaged framing in gable ends | 51070-00 | GC | Capital Plan | 4500 | 0 | 4500 |  | Not Started
Regency & Lexington | 2025 | Allowance to epoxy inject concrete topping slabs and ap | PCA 4.2- Allowance to epoxy inject concrete topping slabs and apply elastomeric coating at elevated walkways. | 51072-00 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Regency & Lexington | 2025 | Install metal hardware | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces | 51092-00 | GC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
Regency & Lexington | 2025 | Repair checked wood beams by epoxy injection. | PCA 4.2- Repair checked wood beams by epoxy injection. | 51070-00 | GC | Capital Plan | 500 | 500 | 0 |  | Completed
Regency & Lexington | 2025 | Fill pitch pockets and flash parking lot light bases. | PCA 4.4.1 - Fill pitch pockets and flash parking lot light bases. | 51141-00 | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
Regency & Lexington | 2025 | Allowance to replace deteriorated wood trim, fascia, ri | PCA 4.2-Allowance to replace deteriorated wood trim, fascia, rim joists and sheathing at elevated walkways and landings. | 51082-00 | GC | Capital Plan | 30000 | 24000 | 6000 |  | In Progress
Regency & Lexington | 2025 | Building G Balcony – sectional replacement of deteriora | PCA 4.2 -Building G Balcony – sectional replacement of deteriorated framing. | 51072-00 | GC | Capital Plan | 4500 | 3600 | 900 |  | In Progress
Regency & Lexington | 2025 | Allowance for exterior cladding replacement and replace | PCA 4.2 -Allowance for exterior cladding replacement and replacement of any damaged wood framing. | 51075-00 | GC | Capital Plan | 10000 | 8000 | 2000 |  | In Progress
Regency & Lexington | 2025 | Repair exterior stair railings | Secure railings | 51077-00 | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Regency & Lexington | 2025 | Repair balcony framing & decking | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail | 51072-00 | GC | Capital Plan | 105357 | 0 | 105357 |  | Not Started
Regency & Lexington | 2025 | Expansion Joints | Expansion Joints | 51075-00 | GC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
Regency & Lexington | 2025 | Asphalt composite shingle roofing Repair loose gravel s | Roll roofing on roofs inspect and repair PCA 4.4.1 - Repair loose gravel stop and open perimeter flashing and membrane | 51062-00 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Regency & Lexington | 2025 | Gutters & downspouts | Secure and clean gutters | 51071-00 | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Regency & Lexington | 2025 | Flashing | Repair flashing between stucco and t-111 | 51062-00 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Regency & Lexington | 2025 | Sealants & caulking | Seal joints in t-111 | 51062-00 | GC | Capital Plan | 18000 | 0 | 18000 |  | Not Started
Regency & Lexington | 2025 | Repair / replace wood siding | Replace rotted t-111 siding | 51075-00 | GC | Capital Plan | 24000 | 0 | 24000 |  | Not Started
Regency & Lexington | 2025 | Exterior building Paint | Paint community | 51080-00 | GC | Capital Plan | 132857 | 0 | 132857 |  | Not Started
Regency & Lexington | 2025 | Repair / replace wood trim Repair exposed lumber and el | Replace rotted fascia and trim PCA 4.4.1 - Repair exposed lumber and elevation changes. | 51082-00 | GC | Capital Plan | 36000 | 0 | 36000 |  | Not Started
Regency & Lexington | 2025 | Repair stucco | Some walls next to windows need patching and paint | 51075-00 | GC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Regency & Lexington | 2025 | Security Camera System | Don't have anything, budget for a new system | 51993-00 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Regency & Lexington | 2025 | Back-flow preventer | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. | 51130-00 | PMC | Capital Plan | 3000 | 2474 | 526 |  | In Progress
Regency & Lexington | 2025 | Galvanized Pipe Replacement | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone | 51130-00 | GC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
Regency & Lexington | 2025 | Sanitary Sewer Piping | Number based on actual bid; $285 per cleanout, 8 cleanouts. $402 per storm drain, 6 cleanouts. Regency & Lexington Equit | 51134-00 | PMC | Capital Plan | 4692 | 15655 | -10963 |  | Completed
Regency & Lexington | 2025 | Pipe Repair at Building 1 Boiler | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could p | 51130-00 | GC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Regency & Lexington | 2025 | Natural Gas Seismic Shutoff | Will confirm with Gas utility company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equipped | 51130-00 | GC | Capital Plan | 8000 | 0 | 8000 |  | Not Started
Regency & Lexington | 2025 | Energy Retrofit | Echelon upfront costs | 51160-00 | PMC | Capital Plan | 27121 | 0 | 27121 |  | Not Started
Regency & Lexington | 2025 | HVAC Replacement | Large Rheem HVAC unit outside office looks very old and may need to be replaced | 51120-00 | GC | Capital Plan | 4500 | 0 | 4500 |  | Not Started
Regency & Lexington | 2025 | Electrical distribution | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Infr | 51140-00 | GC | Capital Plan | 17857 | 0 | 17857 |  | Not Started
Regency & Lexington | 2025 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 87858 | 0 | 87858 |  | Reserve
Regency & Lexington | 2025 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 48322 | 0 | 48322 |  | Reserve
Renaissance | 2025 | Landscape Cleanup and Enhancements | PNA: Building clearance tree trim and cleanup. | 83000-8300 | PMC | Capital Plan | 84500 | 0 | 84500 |  | Not Started
Renaissance | 2025 | Asphalt Coating | PNA - Fill all alligator cracks, potholes and then seal coat throughout property. Also, speed bump repairs throughout pr | 83000-2200 | GC | Capital Plan | 271120 | 0 | 271120 |  | Not Started
Renaissance | 2025 | Concrete pavement | PNA: Repair damaged/ cracked swales throughtout property Lender PCA: At the time of the assessment, several concrete tri | 83000-2800 | PMC | Capital Plan | 36500 | 6500 | 30000 |  | In Progress
Renaissance | 2025 | Stripe parking areas | PNA: Stripe parking lot throughout property. | 83000-2200 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Renaissance | 2025 | ADA parking & curb cuts | PNA: Repair of any damaged curbs. | 83000-2800 | GC | Capital Plan | 10660 | 0 | 10660 |  | Not Started
Renaissance | 2025 | Sidewalks | Sidewalk Repairs | 83000-7100 | GC | Capital Plan | 33350 | 0 | 33350 |  | Not Started
Renaissance | 2025 | Landscape irrigation | PNA: Inspect and repair irrigation Lender PCA: At the time of the assessment, standing water was observed in various ar | 83000-6900 | PMC | Capital Plan | 31200 | 0 | 31200 |  | Not Started
Renaissance | 2025 | Replace swimming pool deck | PNA: Repairs to pool deck cracks and resurface. Bring depth markers, tile, and coping up to code | 83000-5100 | GC | Capital Plan | 100000 | 0 | 100000 |  | Not Started
Renaissance | 2025 | Playground equipment | PNA: Current playground extremely faded, if wanting replacement will need to add more funds. Number given is for adding | 83000-1700 | GC | Capital Plan | 12600 | 0 | 12600 |  | Not Started
Renaissance | 2025 | Carport and garage | PNA: Repair any damaged carports throughtout property. Replace 31 garage doors throughout property - significant damage. | 83000-2600 | GC | Capital Plan | 92400 | 2595 | 89805 |  | In Progress
Renaissance | 2025 | Dumpster enclosures | PNA: Damage cinderblocks at dumpster enclosures to be repaired. Lender PCA: Two of the refuse enclosures were observed w | 83000-3700 | PMC | Capital Plan | 18500 | 0 | 18500 |  | Not Started
Renaissance | 2025 | Parking Lot Concersion | Potential to convert unused parking lot, will evaluate further into hold | 83000-2200 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Renaissance | 2025 | Sports Court | PNA: Complete resurface of sports court and new lines for basketball court. | 83000-6700 | PMC | Capital Plan | 98250 | 2510 | 95740 |  | In Progress
Renaissance | 2025 | Repair or replace damaged concrete treads at stairs. | Lender PCA: At the time of the assessment, a damaged concrete thread was observed at the stairs to the upper floor apart | 83000-7000 | PMC | Capital Plan | 500 | 0 | 500 |  | Not Started
Renaissance | 2025 | Repair exterior stair treads and stringers | PNA: Secure Stair Treads & Stringers | 83000-7100 | GC | Capital Plan | 12200 | 0 | 12200 |  | Not Started
Renaissance | 2025 | Repair exterior stair railings | PNA: Secure railings and paint all metal stair railings. Currently significantly chipped. | 83000-7100 | GC | Capital Plan | 37800 | 0 | 37800 |  | Not Started
Renaissance | 2025 | Moss Treatment | Moss treatment and pine needle cleaning | 83000-6100 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Renaissance | 2025 | Tile roofing | PNA: Clay tile roofing - inspect and minor repairs | 83000-6100 | GC | Capital Plan | 39860 | 0 | 39860 |  | Not Started
Renaissance | 2025 | Gutters & downspouts | PNA: Secure and clean downspouts. Confirm this includes gutters and repinning | 83000-6100 | GC | Capital Plan | 36200 | 0 | 36200 |  | Not Started
Renaissance | 2025 | Repair / replace cement fiber siding | PNA: Maintenance shed needs to new siding replacment and paint. | 83000-6500 | GC | Capital Plan | 18500 | 0 | 18500 |  | Not Started
Renaissance | 2025 | Exterior building painting | Including estimate from WDIR , to be in Yr 2 (Q4 of'27) | 83000-3400 | PMC | Capital Plan | 556000 | 0 | 556000 |  | Not Started
Renaissance | 2025 | Exterior repair for WDIR | Remediation of active termites | 80000-6800 | PMC | Capital Plan | 250000 | 0 | 250000 |  | Not Started
Renaissance | 2025 | Fire Stops | PNA: Fire stops | 80000-6400 | PMC | Capital Plan | 27244 | 9697 | 17547 |  | In Progress
Renaissance | 2025 | Security/ fire alarm systems | Lender PCA: At the time of the assessment, unit 143 was observed to have missing smoke detectors in the hallways and bed | 80000-1700 | PMC | Capital Plan | 100 | 0 | 100 |  | Not Started
Renaissance | 2025 | Common area light fixtures | PNA: Replace all pole lights, wall packs throughout property. | 83000-3200 | GC | Capital Plan | 44600 | 0 | 44600 |  | Not Started
Renaissance | 2025 | Replace breezeway lights | PNA: Replace all breezeway sconces to LED throughout property. | 83000-3200 | GC | Capital Plan | 27800 | 0 | 27800 |  | Not Started
Renaissance | 2025 | Contingency | Contingency Amount | 80000-7200 | GC | Contingency | 95494 | 0 | 95494 |  | Reserve
Renaissance | 2025 | Construction Management Fee | CM Fee | 80000-7200 | GC | CM Fee | 100269 | 0 | 100269 |  | Reserve
Rosemont | 2025 | Landscape Cleanup and Enhancements | Initial property landscape entry and tour path enhancements, etc | 84303 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Rosemont | 2025 | Storm sewer piping | Address 7 areas of water intrusion throughout property |  | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Rosemont | 2025 | Asphalt Repairs | Mill, cement stabilize and overlay all drive aisles throughout property. Includes Equity PCR Item 3.3.2- Mill and overla | 84204 | GC | Capital Plan | 750000 | 750000 | 0 |  | Completed
Rosemont | 2025 | Stripe parking areas | Layout and stripe throughout property | 84201 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Rosemont | 2025 | ADA parking & curb cuts | ADA Parking & Curb Cuts | 84221 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Rosemont | 2025 | Sidewalks | Secure, scrape, sand & paint deck walkway from office area to sports complex. | 84115 | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Rosemont | 2025 | Grind Sidewalk Trip Hazard | Lender PCR Item- Limited trip hazards were observed by Buildings 3825-A, 3777, and the Fitness Center Building. | 84115 | GC | Capital Plan | 2100 | 0 | 2100 |  | Not Started
Rosemont | 2025 | Fences & gates - site perimeter | Repair any damaged wooden fencing around property | 84205 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
Rosemont | 2025 | Retaining walls | Replace missing or rotted timbers within existing retaining walls, replace some walls. Includes Lender PCR Item- Wood ti | 84434 | GC | Capital Plan | 80000 | 0 | 80000 |  | Not Started
Rosemont | 2025 | Landscaping | Tree trim clearance of all buildings. Includes Equity PCR Item 3.2.4- Many trees were overhanging buildings and depositi | 84303 | GC | Capital Plan | 60000 | 60000 | 0 |  | Completed
Rosemont | 2025 | Dumpster enclosures | Replace fencing around dumpster/compactor enclosures | 84111 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
Rosemont | 2025 | Irrigation | Equity PCR Item 3.2.4- Although operation of the sprinkler system was not directly tested, property management reported | 84302 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Rosemont | 2025 | Re-apply Coating on Walkways & Breezeways | Budget for initial repairs and contingency for ongoing replacements | 84120 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Rosemont | 2025 | Repair exterior stair treads and stringers | Grind any rusted toe kick plates and red oxide prior to repaint. Replace damaged metal toe plates, as needed. Secure, a | 84114 | GC | Capital Plan | 100000 | 100000 | 0 |  | Completed
Rosemont | 2025 | Repair exterior stair railings | Secure and paint | 84121 | GC | Capital Plan | 110000 | 110000 | 0 |  | Completed
Rosemont | 2025 | Repair patio/balcony railings | Replace all bottom level patio fencing on each building | 84121 | GC | Capital Plan | 55000 | 55000 | 0 |  | Completed
Rosemont | 2025 | Asphalt composite shingle roofing | Roofs were replaced in 2019- Initial and ongoing repairs, and contingency for phased replacements in yrs 9-10 | 84433 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Rosemont | 2025 | Flashing | Roof Flashing | 84433 | GC | Capital Plan | 79200 | 79200 | 0 |  | Completed
Rosemont | 2025 | Underlayment | Roof Underlayment | 84433 | GC | Capital Plan | 88000 | 88000 | 0 |  | Completed
Rosemont | 2025 | Gutters & downspouts | Equity PCR Item 4.4.2- Gutters and downspouts should be installed at the roof eaves where not currently installed to hel | 84202 | GC | Capital Plan | 130000 | 130000 | 0 |  | Completed
Rosemont | 2025 | Repair / replace vinyl siding | Repair/replace damaged vinyl siding throughout property Includes Lender PCR Item- Dry rot was observed by the siding at | 84206 | GC | Capital Plan | 52000 | 52000 | 0 |  | Completed
Rosemont | 2025 | Exterior building | Paint all metal throughout property | 84101 | GC | Capital Plan | 90000 | 90000 | 0 |  | Completed
Rosemont | 2025 | Window Replacement and Repairs, including frames | Contingency for replacements and repairs | 84206 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Rosemont | 2025 | Metal Entry Door Replacement and Repairs | Contingency for replacements and repairs | 84215 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Rosemont | 2025 | Sliding Balcony Door Replacement and Repairs | Contingency for replacements and repairs | 84215 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Rosemont | 2025 | Co 2 detectors | Install Co2 detectors in every unit | 82131 | PMC | Capital Plan | 22000 | 0 | 22000 |  | Not Started
Rosemont | 2025 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | 84239 | PMC | Capital Plan | 52009 | 0 | 52009 |  | Not Started
Rosemont | 2025 | Signage - Building identification | Misc replacement signage | 84103 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Designer Fees | TBD scope | 84310 | PMC | Capital Plan | 2500 | 0 | 2500 |  | Not Started
Rosemont | 2025 | Clubhouse / Office Remodel | Not needed, misc allowance | 84208 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Clubhouse / Office Furniture | Not needed, misc allowance | 84306 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Fitness Center Remodel | Need to replace lights, repair damaged walls, paint, repair flooring that is lifting, repair men's bathroom items | 84190 | GC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Rosemont | 2025 | Fitness Equipment | Stair Stepper, other misc items | 84190 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Rosemont | 2025 | Leasing Pool Area Remodel | Replace wood/cable fence section in raised area with metal rail to match other fencing, other misc repairs | 84361 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Rosemont | 2025 | Leasing Pool Furniture | Supplement current furniture, add freestanding umbrellas, cornhole & ping pong, 2 cabanas, move some furniture to second | 84360 | PMC | Capital Plan | 45000 | 0 | 45000 |  | Not Started
Rosemont | 2025 | Secondary Pool Area Remodel | Need to fix cosmetic issues or possibly resurface | 84361 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Secondary Pool Furniture | Misc items & move items from main pool | 84360 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Playground Remodel | Replace swing sets, border and mulch as well as replacing grills with new stand alone ones at secondary park area | 84195 | GC | Capital Plan | 13000 | 0 | 13000 |  | Not Started
Rosemont | 2025 | Playground Furniture | Picnic tables and misc items | 84340 | GC | Capital Plan | 8000 | 0 | 8000 |  | Not Started
Rosemont | 2025 | Picnic/Grill Area Remodel | Add 1-2 outdoor grill/kitchen areas at the property with gazebo | 84203 | GC | Capital Plan | 60000 | 0 | 60000 |  | Not Started
Rosemont | 2025 | Picnic/Grill Furniture | Furniture for new grill areas | 84340 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Rosemont | 2025 | Sports Court | Resurface, add 2 Pickleball nets. Keep running track, stripe for Pickleball courts Includes Equity PCR Item 3.2.9- The | 84390 | GC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Rosemont | 2025 | Sports Court- Soccer | Replace shade sails | 84390 | GC | Capital Plan | 8000 | 0 | 8000 |  | Not Started
Rosemont | 2025 | Unit Model Update | Change out carpet, misc supplemental furniture, remove screen door since it is broken and obscures visibility in the mod | 84280 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Rosemont | 2025 | Access Control System | Need to add access control for package lockers in fitness center | 84275 | PMC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Rosemont | 2025 | Mailboxes | Misc repairs | 84260 | PMC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Rosemont | 2025 | New access gate at back entrance | Look at adding gate ro restrict access to dumpster area and prevent dumping | 84275 | GC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Rosemont | 2025 | Security Camera System | Add cameras by mailboxes | 84450 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Rosemont | 2025 | Carports | Look at adding carports for additional income | 84219 | GC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Rosemont | 2025 | Golf Cart | Need 1-2 leasing carts, have 2 maintenance carts | 83375 | PMC | Capital Plan | 16000 | 0 | 16000 |  | Not Started
Rosemont | 2025 | Unit water heaters | Equity PCR Item- 5.1- Observed water heaters were not provided with drain pans. Additionally, most water heaters observe | 84476 | GC | Capital Plan | 211000 | 0 | 211000 |  | Not Started
Rosemont | 2025 | Sanitary sewer Repairs | Contingency to remove roots and blockages at several locations, per the sewer scoping. See final report in diligence fo | 84385 | GC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Rosemont | 2025 | Install P trap on HVAC condensate piping | Equity PCR Item 5.3- The interior fan coil units (FCUs) observed at the residential units lacked p-traps at the condens | 84217 | GC | Capital Plan | 16880 | 16880 | 0 |  | Completed
Rosemont | 2025 | Insulate HVAC lines | Equity PCR Item 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the uni | 84217 | GC | Capital Plan | 5375 | 0 | 5375 |  | Not Started
Rosemont | 2025 | HVAC inspection and maintenance | Clean debris/foliage from around condensors as well as leveling with condensor pads. Includes Equity PCR Item 5.2- Many | 84217 | PMC | Capital Plan | 8500 | 0 | 8500 |  | Not Started
Rosemont | 2025 | Inspect Fire Extinguishers | Lender PCR Item- Fire extinguishers are expired. | 84239 | PMC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Rosemont | 2025 | Fire Suppression System Inspection | Equity PCR Item 5.5.1- Annual Fire suppression system inspection for Building 3971-3975 | 84211 | PMC | Capital Plan | 1000 | 0 | 1000 |  | Not Started
Rosemont | 2025 | Fire Alarm System Inspection | Equity PCR Item 5.5.2- Annual fire alarm system inspection for Building 3971-3975. | 84211 | PMC | Capital Plan | 1000 | 0 | 1000 |  | Not Started
Rosemont | 2025 | Smoke Detectors | Equity PCR Item 5.5.2- Smoke detectors not observed in bedrooms, Install | 82131 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Rosemont | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 137853 | 0 | 137853 |  | Reserve
Rosemont | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 144746 | 0 | 144746 |  | Reserve
Swiss Gables | 2025 | Landscape Cleanup and Enhancements | Isolated locations of tree overgrowth at building elevations were observed. Tree trimming is recommended | 84303 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Swiss Gables | 2025 | Asphalt Coating | Crack fill alligatored asphalt Damaged pavement consisting of linear cracking and alligator cracking was observed east o | 84204 | GC | Capital Plan | 65000 | 19500 | 45500 |  | In Progress
Swiss Gables | 2025 | Stripe parking areas | Stripe parking lot and garages | 84204 | GC | Capital Plan | 36000 | 10800 | 25200 |  | In Progress
Swiss Gables | 2025 | Curbing Repairs | Damaged curbing was present southeast of Building C and at the east entrance to Building E. Repairs are recommended. | 84115 | GC | Capital Plan | 1500 | 2000 | -500 |  | Completed
Swiss Gables | 2025 | Sidewalks | Repair trip Hazards Damaged concrete sidewalk was present at the walkway south of Building G. Repairs are recommended. R | 84115 | GC | Capital Plan | 18000 | 10800 | 7200 |  | In Progress
Swiss Gables | 2025 | Fences & gates - site perimeter | Repair and paint fence | 84205 | GC | Capital Plan | 21000 | 10500 | 10500 |  | In Progress
Swiss Gables | 2025 | Install ADA Van-Accessible Space | The accessible parking spaces did not appear to be generally correctly configured. The installation of one van-accessibl | 83520 | PMC | Capital Plan | 400 | 3088 | -2688 |  | Completed
Swiss Gables | 2025 | Install ADA-Compliant Curb Cut Ramps | ADA-compliant curb cut ramps are not present on accessible route at the subject property. Inclusion of ADA-compliant cur | 83520 | PMC | Capital Plan | 1200 | 9265 | -8065 |  | Completed
Swiss Gables | 2025 | Install ADA-Compliant Handrailing at Ramp | The ramps within the accessible route do not appear to have ADA-compliant handrails. Reconfiguration of the handrails is | 83520 | PMC | Capital Plan | 1200 | 9265 | -8065 |  | Completed
Swiss Gables | 2025 | Install ADA-Compliant Door Hardware | The door at the designated accessible entrance does not appear to have ADA compliant hardware. Installation of ADA compl | 83520 | PMC | Capital Plan | 450 | 3474 | -3024 |  | Completed
Swiss Gables | 2025 | Playground equipment | Enhance playground equipment | 84340 | PMC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Swiss Gables | 2025 | Dumpster enclosures | Replace fencing on all dumpster enclosures Custom Pickets | 84111 | GC | Capital Plan | 15000 | 12000 | 3000 |  | In Progress
Swiss Gables | 2025 | Carports / Garages | Repair damaged sheet rock and paint 1st floor parking garages | 84219 | GC | Capital Plan | 66000 | 52800 | 13200 |  | In Progress
Swiss Gables | 2025 | Concrete deck / floor fill | Seal cracks in landings and cat walks | 84120 | GC | Capital Plan | 70000 | 56000 | 14000 |  | In Progress
Swiss Gables | 2025 | Repair exterior stair railings | Repair and secure stair railings | 84121 | GC | Capital Plan | 12000 | 9600 | 2400 |  | In Progress
Swiss Gables | 2025 | Repair balcony framing & decking | Repair damaged patio and Catwalk framing Balcony repair allowance Deteriorating wood was present at the underside of the | 84104 | GC | Capital Plan | 109000 | 81750 | 27250 |  | In Progress
Swiss Gables | 2025 | Repair patio/balcony railings | Secure all balcony and catwalk railings (custom pickets) | 84121 | GC | Capital Plan | 35000 | 28000 | 7000 |  | In Progress
Swiss Gables | 2025 | Asphalt composite shingle roofing | Roof tune up on 7 buildings | 84433 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Swiss Gables | 2025 | Gutters & downspouts | Clean and secure gutters and down spouts | 83439 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Swiss Gables | 2025 | Flashing | Replace damaged drip edge on cat walks | 84433 | GC | Capital Plan | 21000 | 16800 | 4200 |  | In Progress
Swiss Gables | 2025 | Sealants & caulking | Sealants & caulking | 84433 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Swiss Gables | 2025 | Repair / replace wood siding | Replace rotted T-111 siding Damaged soffits were observed along the elevated walkway at Building A, isolated areas at th | 84206 | GC | Capital Plan | 35000 | 28000 | 7000 |  | In Progress
Swiss Gables | 2025 | Exterior building Painting | Paint community including peal stop on all delaminated cedar Paint chipping was observed at the columns and posts of the | 84101 | GC | Capital Plan | 189000 | 151200 | 37800 |  | In Progress
Swiss Gables | 2025 | Repair / replace wood trim | Replace all rotted trim throughout property All Facia is Custom Scalloped Facia | 84105 | GC | Capital Plan | 45000 | 36000 | 9000 |  | In Progress
Swiss Gables | 2025 | Install CO Detectors | Carbon monoxide detectors are not provided in dwelling units, and wood burning fireplaces were provided in the third flo | 83236 | PMC | Capital Plan | 770 | 0 | 770 |  | Not Started
Swiss Gables | 2025 | Fire protection | Fire protection - Fire Stops | 84211 | PMC | Capital Plan | 10584 | 0 | 10584 |  | Not Started
Swiss Gables | 2025 | Signage - Entry Monument | Site Rebrand - New Monument Sign | 84290 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Swiss Gables | 2025 | Signage - Building identification | Site Rebrand - New Building Signage/New Door Numbers | 84103 | PMC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Swiss Gables | 2025 | Seal Penetrations in Fire Walls and Smoke Barriers | Penetrations in the fire and smoke barriers are in poor condition. Penetrations in the fire rated walls were observed as | 84211 | GC | Capital Plan | 70000 | 21000 | 49000 |  | In Progress
Swiss Gables | 2025 | General Fire Alarm Deficiencies | General fire alarm deficiencies were observed. The general deficiency noted is: expired smoke detectors throughout the b | 84211 | PMC | Capital Plan | 16100 | 4185 | 11915 |  | In Progress
Swiss Gables | 2025 | Sanitary Sewer Piping | Cleanout replacement; Hydrojet as needed | 84385 | PMC | Capital Plan | 24150 | 3967 | 20183 |  | In Progress
Swiss Gables | 2025 | Install Seismic Strapping | The water heater at the employee restroom in Building C lacked seismic bracing straps. Provision of adequate seismic bra | 84476 | PMC | Capital Plan | 250 | 0 | 250 |  | Not Started
Swiss Gables | 2025 | Electrical Distribution | Repair electric to pole lights and photo cells General electrical deficiencies were observed. The general deficiencies n | 84210 | GC | Capital Plan | 24400 | 19520 | 4880 |  | In Progress
Swiss Gables | 2025 | Common Area Light Fixtures | Replace parking garage and parking lot lights to LED | 84210 | GC | Capital Plan | 32000 | 25600 | 6400 |  | In Progress
Swiss Gables | 2025 | Organize Electrical Wiring | The surface raceway in Building-C, unit C303, requires repair to ensure the proper protection and organization of electr | 84210 | GC | Capital Plan | 5000 | 4000 | 1000 |  | In Progress
Swiss Gables | 2025 | Electrical Buzzing Sound | An electrical buzzing sound coming from the underground vault adjacent to the main roadside transformer indicates a pote | 84210 | GC | Capital Plan | 1000 | 0 | 1000 |  | Not Started
Swiss Gables | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 53250 | 0 | 53250 |  | Reserve
The Ardent | 2025 | Asphalt Coating | Crack fill, seal, and coat Damaged pavement consisting of pothole formation and alligator cracking was observed primaril | 84204 | GC | Capital Plan | 260000 | 78000 | 182000 |  | In Progress
The Ardent | 2025 | Seal & Stripe parking areas | Stripe Parking Lot | 84204 | GC | Capital Plan | 32000 | 9600 | 22400 |  | In Progress
The Ardent | 2025 | Curb cuts | Damaged concrete curbs were observed consisting of displacement and linear cracking were observed at the parking area pe | 83520 | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
The Ardent | 2025 | Sidewalks | Repair trip hazards Potential trip hazards consisting of damaged concrete and vertical and horizontal separation were pr | 84115 | GC | Capital Plan | 32000 | 9600 | 22400 |  | In Progress
The Ardent | 2025 | Landscaping | Trees were observed impeding on the building envelope at apartment buildings and also at the roofs of the carports. It i | 84303 | GC | Capital Plan | 80000 | 0 | 80000 |  | Not Started
The Ardent | 2025 | Resurface swimming pool | Resurface Swimming Pool | 84095 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
The Ardent | 2025 | Replace swimming pool coping | Replace Pool Coping | 84361 | GC | Capital Plan | 17500 | 5250 | 12250 |  | In Progress
The Ardent | 2025 | Swimming Pool 1 (Phase I: Leasing Office) | Repair cracked conrete & Update Pool Furniture | 84361 | GC | Capital Plan | 35000 | 10500 | 24500 |  | In Progress
The Ardent | 2025 | Swimming Pool 2 (Phase I: Tennis Court) | Repair cracked conrete & Update Pool Furniture (Removed) | 84361 | GC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
The Ardent | 2025 | Swimming Pool 3 (Phase II) | Repair gate and paint fence Mark had $7.6K. Repair cracked concrete & Update Pool Furniture | 84361 | GC | Capital Plan | 35000 | 10500 | 24500 |  | In Progress
The Ardent | 2025 | Storm Sewer Piping | Clean Yard Basin | 84432 | GC | Capital Plan | 14000 | 4200 | 9800 |  | In Progress
The Ardent | 2025 | Playground equipment | Replace fall zone mulch | 84340 | GC | Capital Plan | 5400 | 1620 | 3780 |  | In Progress
The Ardent | 2025 | Carports | Replace rotted facia on carports Isolated posts show significant deterioration and should be replaced immediately. Recom | 84219 | GC | Capital Plan | 52000 | 15600 | 36400 |  | In Progress
The Ardent | 2025 | Dumpster enclosures | Replace fencing on all dumpster enclosures | 84111 | GC | Capital Plan | 27000 | 8100 | 18900 |  | In Progress
The Ardent | 2025 | Sport Court Renovation: Tennis | Repair chain link fence around tennis court. Turn into pickleball | 84390 | GC | Capital Plan | 50000 | 15000 | 35000 |  | In Progress
The Ardent | 2025 | Sport Court Renovation: Basketball | Restripe & Add New Hoop | 84390 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
The Ardent | 2025 | Pavement | R&R 6000 SF of Potholes and the worst alligatored pavement | 84204 | GC | Capital Plan | 60000 | 18000 | 42000 |  | In Progress
The Ardent | 2025 | Foundation - Seal pier and beam area | Replace damaged foundation vents | 84430 | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
The Ardent | 2025 | Concrete deck / floor fill | Seal cracks in landings | 84430 | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
The Ardent | 2025 | Stairs - Repair or replace damaged concrete treads at s | Replace sill plate supporting stair landing post outside of Unit 24 at Building 03C - Still plate has signficant rot | 84110 | GC | Capital Plan | 2000 | 600 | 1400 |  | In Progress
The Ardent | 2025 | Fire - Draft Stops | Allowance to seal small penetrations in attic draft stops - Small openings were observed within the demising draft stop | 84211 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
The Ardent | 2025 | Repair exterior stair treads and stringers | Repair stair tread and stringers | 84114 | GC | Capital Plan | 37000 | 11100 | 25900 |  | In Progress
The Ardent | 2025 | Repair exterior stair railings | Repair and secure stair railings | 84121 | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
The Ardent | 2025 | Repair balcony framing & decking | Repair damaged patio framing | 84104 | GC | Capital Plan | 45000 | 13500 | 31500 |  | In Progress
The Ardent | 2025 | Repair patio/balcony railings | Secure all balcony railings | 84121 | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
The Ardent | 2025 | Exterior Doors - replacement doors at patio and balcony | Patio & Balcony Storage Doors | 83426 | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
The Ardent | 2025 | Building Repairs & Exterior Walls | The exterior walls were observed with vegetative staining, peeling paint, and areas of damaged siding at the exterior wa | 84102 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
The Ardent | 2025 | Asphalt composite shingle roofing | Roof tune up on 37 buildings Isolated areas of damaged and lifted asphalt shingles were observed at Buildings B and S. | 84433 | GC | Capital Plan | 57000 | 17100 | 39900 |  | In Progress
The Ardent | 2025 | Gutters & downspouts | Clean and secure gutters and down spouts | 83439 | GC | Capital Plan | 37000 | 11100 | 25900 |  | In Progress
The Ardent | 2025 | Roofing - Flashing | Replace damaged drip edge on balconies | 84433 | GC | Capital Plan | 67400 | 20220 | 47180 |  | In Progress
The Ardent | 2025 | Roofing - Sealants & caulking | Roof Sealant & Caulking | 84433 | GC | Capital Plan | 49000 | 14700 | 34300 |  | In Progress
The Ardent | 2025 | Repair / replace wood siding | Replace rotted siding and scrape and paint Cedar siding Recommended to evaluate wall cavity conditions and prioritize bu | 84102 | GC | Capital Plan | 110000 | 33000 | 77000 |  | In Progress
The Ardent | 2025 | Masonry Repairs | Repair Exterior Masonry Walls | 84102 | GC | Capital Plan | 23500 | 7050 | 16450 |  | In Progress
The Ardent | 2025 | Dryer Vents | Dryer Vent Cleaning | 84106 | PMC | Capital Plan | 42750 | 16706 | 26044 |  | In Progress
The Ardent | 2025 | Breezeway soffit repairs | Add soffit vents at Phase 3 breezeways to improve attic ventilation and enhance moisture control; addresses incomplete v | 84113 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
The Ardent | 2025 | Exterior Painting | Paint community including peal stop on all delaminated cedar | 84101 | GC | Capital Plan | 916200 | 274860 | 641340 |  | In Progress
The Ardent | 2025 | Repair / replace wood trim | Replace all rotted trim throughout property | 84113 | GC | Capital Plan | 158000 | 47400 | 110600 |  | In Progress
The Ardent | 2025 | Water Heater Strapping | This item is for compliance with Section 507.2 of the Washington Plumbing Code. This item can be carried out as part of | 84209 | PMC | Capital Plan | 300 | 0 | 300 |  | Not Started
The Ardent | 2025 | Seismic Shutoff Valve | There is a natural gas line provided to Fitness Center B, and it is not provided with a seismic shutoff valve. Provide a | 84217 | PMC | Capital Plan | 1000 | 0 | 1000 |  | Not Started
The Ardent | 2025 | Fire Protection | Includes adding fire stops in all units | 84211 | PMC | Capital Plan | 42750 | 19836 | 22914 |  | In Progress
The Ardent | 2025 | Fitness Center Remodel (Gym 1 Phase II) | Turn yoga studio into pool lounge with Bay door | 84190 | GC | Capital Plan | 50000 | 15000 | 35000 |  | In Progress
The Ardent | 2025 | Fitness Center Remodel (Gym 2 Phase III) | Convert into golf simulator | 84190 | GC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
The Ardent | 2025 | Dog Park | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola | 84130 | GC | Capital Plan | 16000 | 0 | 16000 |  | Not Started
The Ardent | 2025 | Electrical Distribution | Repair electric to pole lights and photo cells | 84210 | GC | Capital Plan | 32000 | 9600 | 22400 |  | In Progress
The Ardent | 2025 | Lighting - Common area light fixtures | Replace walkway pole lights - change to wall pack lights? ($5k) | 84210 | GC | Capital Plan | 48000 | 14400 | 33600 |  | In Progress
The Ardent | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 133740 | 0 | 133740 |  | Reserve
The Ardent | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 140427 | 0 | 140427 |  | Reserve
The Ardent | 2025 | 82260 - Exterior Lighting | Increase lighting across the property - Defer | 82260 | GC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
The Fairways | 2025 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | 84300 | PMC | Capital Plan | 20000 | 27840 | -7840 |  | Completed
The Fairways | 2025 | Sanitary sewer piping | Add rocks around storm drains around property. Clean the area around the drain. | 84209 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
The Fairways | 2025 | Storm sewer piping | Improve current french drain towards the back right of the property. | 84385 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
The Fairways | 2025 | concrete pavement | Fill cracks and seal area next to dog park and sports court. | 84221 | GC | Capital Plan | 17500 | 17500 | 0 |  | Completed
The Fairways | 2025 | Asphalt Coating | Crack fill and double seal coat asphalt throughout property. Includes Lender PCR Item- Damaged pavement consisting of l | 84204 | GC | Capital Plan | 298500 | 298500 | 0 |  | Completed
The Fairways | 2025 | ADA parking & curb cuts | Include where needed in concrete/asphalt work | 84201 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
The Fairways | 2025 | Sidewalks | Repair cracked/broken sidewalks throughout property. | 84221 | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
The Fairways | 2025 | Landscaping | Tree trim and clean up throughout property. 1st Call getting bid in conjunction with Paddocks to improve cost | 84300 | GC | Capital Plan | 92800 | 92800 | 0 |  | Completed
The Fairways | 2025 | Resurface swimming pool | Resurface pool | 84095 | GC | Capital Plan | 40000 | 32200 | 7800 |  | In Progress
The Fairways | 2025 | Replace swimming pool coping | Deck-O-Seal coping around pool. And relocate pots off the new deck to avoid further damage | 84361 | GC | Capital Plan | 4500 | 4500 | 0 |  | Completed
The Fairways | 2025 | Repair swimming pool deck | Clean pool deck, crack fill and seal. Repair the deck attached to pool deck and repaint/stain. Reinforce and lvel suppor | 84361 | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
The Fairways | 2025 | Dog Park | Replace chainlink fencing around dog park and replace with aluminum fencing. Add enzyme injector to irrigation valve | 84130 | GC | Capital Plan | 26000 | 7800 | 18200 |  | In Progress
The Fairways | 2025 | Dumpster enclosures | Repair any damage on dumpster enclosure. | 84111 | GC | Capital Plan | 2150 | 2150 | 0 |  | Completed
The Fairways | 2025 | Retaining walls | Retaining wall needs repair by sport court - replace with stone wall | 84434 | GC | Capital Plan | 2000 | 2000 | 0 |  | Completed
The Fairways | 2025 | Repair exterior stair treads and stringers | Secure. | 84114 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
The Fairways | 2025 | Repair exterior stair railings | Secure. | 84121 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
The Fairways | 2025 | Repair balcony framing & decking | Half the properties balconies are showing signs of weathering due to moisture/rot. Replace any rotted wood and scrap, sa | 84101 | GC | Capital Plan | 95000 | 95000 | 0 |  | Completed
The Fairways | 2025 | Asphalt composite shingle roofing | Replace flashing around all chimneys throughout property as well as a minor roof tune up to each building. Any significa | 84433 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
The Fairways | 2025 | Repair / replace cement fiber siding | Repair/replace areas of failed hardie board and paint to match throughout property | 84206 | GC | Capital Plan | 41500 | 41500 | 0 |  | Completed
The Fairways | 2025 | Repair / replace wood trim | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. | 84113 | GC | Capital Plan | 38500 | 38500 | 0 |  | Completed
The Fairways | 2025 | Drier vents | Clean dryer vents throughout property. | 84106 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
The Fairways | 2025 | CO detectors | Install CO detectors in each unit. Lender PCA Item- Due to the presence of gas-fire water heaters at each unit, carbon m | 82131 | PMC | Capital Plan | 16800 | 0 | 16800 |  | Not Started
The Fairways | 2025 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods TV to verify with Dan H on ordering | 84239 | PMC | Capital Plan | 11723 | 0 | 11723 |  | Not Started
The Fairways | 2025 | Clubhouse / Office Remodel | Paint cabinets in kitchen with hardware, add backsplash, replace appliances, replace "snack shack" window to be function | 84208 | GC | Capital Plan | 15000 | 15000 | 0 |  | Completed
The Fairways | 2025 | Clubhouse / Office Furniture | Looks good, misc supplemental items - Add a TV. TAM to order and install. Move the leasing desktop to back work area, pu | 82140 | PMC | Capital Plan | 10000 | 10439 | -439 |  | Completed
The Fairways | 2025 | Pool Area Remodel | Games and placeholder budget - TV contacting Key Designs | 84361 | PMC | Capital Plan | 15000 | 65776 | -50776 |  | Completed
The Fairways | 2025 | Pool Furniture | Maybe budget for full replacement. Tables and chairs look ok, 24 chaises are ok but a cheaper style. Budget for new, a f | 84360 | PMC | Capital Plan | 50000 | 75016 | -25016 |  | Completed
The Fairways | 2025 | Picnic/Grill Area Remodel | Look at adding grills and outdoor kitchen, gazebo, landscaping or turf in planters, replace/fix lights | 84203 | GC | Capital Plan | 30000 | 27000 | 3000 |  | In Progress
The Fairways | 2025 | Picnic/Grill Furniture | Tables ok, possibly add games | 84195 | PMC | Capital Plan | 10000 | 24300 | -14300 |  | Completed
The Fairways | 2025 | Sports Courts | Resurface and add 2 pickleball courts along with tennis | 84390 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
The Fairways | 2025 | Dog Park | Looks good, misc budget - add enzyme injector | 84130 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
The Fairways | 2025 | Access Control System | Need for pool area and bathroom doors - just updating to keypad. Review for future FOB system for afterhours access on a | 84275 | PMC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
The Fairways | 2025 | Storage Shed | Look at adding storage shed for appliances next to maintenance - enclose area to left of maintenance shop | 84206 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
The Fairways | 2025 | HVAC inspection and maintenance | Clean foliage around condensors throughout property. Raise units with HVAC pad as needed. | 84218 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
The Fairways | 2025 | Electrical distribution | Electrical Distribution | 84210 | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
The Fairways | 2025 | Replace breezeway lights | Breezeway Lighting | 84210 | GC | Capital Plan | 37500 | 37500 | 0 |  | Completed
The Fairways | 2025 | Pool area lighting | Lights are all 110 and need to be rewired | 84361 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
The Fairways | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 178027 | 0 | 178027 |  | Reserve
The Fairways | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 66000 | 0 | 66000 |  | Reserve
The Lakes | 2025 | Landscape Cleanup and Enhancements | Lakes - Landscape Enhancements Revive - Landscape Enhancements | 84303 | PMC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
The Lakes | 2025 | Asphalt Coating | Lakes - Crack fill, seal and coating Revive - Crack fill, seal and coating | 84204 | GC | Capital Plan | 455000 | 136500 | 318500 |  | In Progress
The Lakes | 2025 | Fencing | Take down the chain-link fence separating properties. Add two paths for golf cart to travel between. Add walking path - | 84205 | GC | Capital Plan | 50000 | 15000 | 35000 |  | In Progress
The Lakes | 2025 | Stripe Parking Areas | Lakes - Stripe Parking Lot Revive - Stripe Parking Lot | 84201 | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
The Lakes | 2025 | ADA Parking & Curb Cuts | Lakes - Concrete Modifications Revive - Concrete Modifications | 83520 | GC | Capital Plan | 26000 | 7800 | 18200 |  | In Progress
The Lakes | 2025 | Sidewalks Trip Hazard | Lakes - Repair trip hazards Revive - Repair trip hazards. A limited sidewalk crack was also observed by Building 2335. | 84115 | GC | Capital Plan | 29000 | 8700 | 20300 |  | In Progress
The Lakes | 2025 | Storm Sewer Piping | Lakes - Clean Yard Basins of Debris Revive - Clean Yard Basins of Debris | 84432 | GC | Capital Plan | 23000 | 6900 | 16100 |  | In Progress
The Lakes | 2025 | Fences & Gates - Site Perimeter | Revive - Add ~200ft wall between Revive and comp with razor wire | 84205 | GC | Capital Plan | 15000 | 4500 | 10500 |  | In Progress
The Lakes | 2025 | Pavement | Lakes - R&R 2000 Sf of Potholes Revive - R&R 1500 sq ft pavement | 84204 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
The Lakes | 2025 | Landscaping | Lakes - Tree trim and raise canopy | 84303 | GC | Capital Plan | 64000 | 19200 | 44800 |  | In Progress
The Lakes | 2025 | ADA Modifications | Revive - Common area restroom sink is not insulated at clubhouse. LRR- ADA sink insulation | 83520 | PMC | Capital Plan | 350 | 0 | 350 |  | Not Started
The Lakes | 2025 | Fences & Gates - Swimming Pool | Lakes - Repair gate and paint fence Revive - Repair gate and paint fence | 84205 | GC | Capital Plan | 16200 | 4860 | 11340 |  | In Progress
The Lakes | 2025 | Pool Area | Lakes - Enhance pool area with turf and a fireplace | 84361 | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
The Lakes | 2025 | Dumpster Enclosures | Lakes - Replace fencing on all dumpster enclosures Revive - Replace fencing on all dumpster enclosures | 84111 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
The Lakes | 2025 | Concrete Deck / Floor Fill | Lakes - Seal cracks in landings Revive - Seal cracks in landings | 84430 | GC | Capital Plan | 41000 | 12300 | 28700 |  | In Progress
The Lakes | 2025 | Roof Deck | Revive - Roof Deck Repairs | 84433 | GC | Capital Plan | 13000 | 13000 | 0 |  | Completed
The Lakes | 2025 | Repair Exterior Stair Treads and Stringers | Lakes - Repair stair tread and stringers Revive - Repair stair tread and stringers | 84114 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
The Lakes | 2025 | Repair Exterior Stair Railings | Lakes - Repair and secure stair railings Revive - Repair and secure stair railings | 84121 | GC | Capital Plan | 24000 | 7200 | 16800 |  | In Progress
The Lakes | 2025 | Repair Balcony Framing & Decking | Lakes - Repair damaged patio framing Revive - Repair damaged patio framing | 84104 | GC | Capital Plan | 22000 | 6600 | 15400 |  | In Progress
The Lakes | 2025 | Repair Patio/Balcony Railings | Lakes - Secure all balcony railings Revive - Secure all balcony railings | 84121 | GC | Capital Plan | 22000 | 6600 | 15400 |  | In Progress
The Lakes | 2025 | Asphalt Composite Shingle Roofing | Lakes - Roof tune up on buildings 9 Revive - Replace Roofs | 84433 | GC | Capital Plan | 428000 | 428000 | 0 |  | Completed
The Lakes | 2025 | Gutters & Downspouts | Lakes - Clean and secure gutters and down spouts Revive - Clean and secure gutters and down spouts | 84202.0 | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
The Lakes | 2025 | Flashing | Lakes - Replace damaged drip edge on balconies. Revive - Replace damaged drip edge on balconies. LRR - Damaged balconi | 84433 | GC | Capital Plan | 22800 | 6840 | 15960 |  | In Progress
The Lakes | 2025 | Sealants & Caulking | Lakes - Roof Sealants & Caulking Revive - Roof Sealants & Caulking | 84102 | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
The Lakes | 2025 | Repair / Replace Wood Siding | Lakes - Replace rotted siding and scrape and paint Cedar siding Revive - Replace rotted siding and scrape and paint Ceda | 84102 | GC | Capital Plan | 40000 | 12000 | 28000 |  | In Progress
The Lakes | 2025 | Exterior Building Paint | Lakes - Paint community Revive - Paint community | 84101 | GC | Capital Plan | 348000 | 104400 | 243600 |  | In Progress
The Lakes | 2025 | Repair / Replace Wood Trim | Lakes - Replace all rotted trim throughout property Revive - Replace all rotted trim throughout property | 84113 | GC | Capital Plan | 40000 | 12000 | 28000 |  | In Progress
The Lakes | 2025 | Repair Microbial Growth | LRR - Limited areas of microbial growth was observed in the bedroom corner and closet wall of Unit 2347-1. Affected non- | 82460 | PMC | Capital Plan | 900 | 0 | 900 |  | Not Started
The Lakes | 2025 | Fire Stops | Add Fire Stops | 84211 | PMC | Capital Plan | 24696 | 18931 | 5765 |  | In Progress
The Lakes | 2025 | Leasing Golf Cart | Get Leasing Golf Cart | 83375 | PMC | Capital Plan | 15000 | 32400 | -17400 |  | Completed
The Lakes | 2025 | Fitness Center Remodel | Revive - Convert Leasing office into a Gym | 84190 | GC | Capital Plan | 100000 | 30000 | 70000 |  | In Progress
The Lakes | 2025 | Cyber Café upgrade at Lakes | Lakes - Open up the side wall and expand the leasing area | 84208 | GC | Capital Plan | 30000 | 9000 | 21000 |  | In Progress
The Lakes | 2025 | Security Camera System | Install new Security Cameras | 84450 | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
The Lakes | 2025 | Sanitary Sewer Piping | Lakes - Building C - Minor tree root intrusion. Recommended remediation: Dig approximately 4 feet and replace the affect | 84385 | PMC | Capital Plan | 6600 | 0 | 6600 |  | Not Started
The Lakes | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 104927 | 0 | 104927 |  | Reserve
The Lakes | 2025 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 119624 | 0 | 119624 |  | Reserve
The Vibe | 2025 | Landscape Cleanup and Enhancements | HPCA - Tree trimming/removal overhanging structures | 84300 | PMC | Capital Plan | 7500 | 4077 | 3423 |  | In Progress
The Vibe | 2025 | Asphalt Coating | PNA - contingent amount to work on parking lot as needed. LPCA - Linear/alligator cracking and pothole formation was obs | 84204 | GC | Capital Plan | 68000 | 40800 | 27200 |  | In Progress
The Vibe | 2025 | Stripe parking areas | PNA - stripe parking lot | 84090 | GC | Capital Plan | 32000 | 9600 | 22400 |  | In Progress
The Vibe | 2025 | Parking equipment | HPCA - Add ADA van stall at Carport | 84085 | GC | Capital Plan | 500 | 150 | 350 |  | In Progress
The Vibe | 2025 | ADA parking & curb cuts | Concrete Modifications | 84090 | GC | Capital Plan | 2250 | 675 | 1575 |  | In Progress
The Vibe | 2025 | Sidewalks | PNA - Repair trip hazards HPCA - Concrete Walks/Steps - Trip Hazards/ADA | 84080 | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
The Vibe | 2025 | Storm sewer piping | PNA - Clean yard basins of debree | 84470 | GC | Capital Plan | 12000 | 9600 | 2400 |  | In Progress
The Vibe | 2025 | Fences & gates - site perimeter | PNA - Pool fence is vinyl and post holding up the fence are rotting. Repair posts and repair fence | 84205 | GC | Capital Plan | 24000 | 19200 | 4800 |  | In Progress
The Vibe | 2025 | Move topsoil/mulch away from bldg. siding | HPCA - Backfill exposed/undercut concrete steps and foundations | 84080 | GC | Capital Plan | 7500 | 6000 | 1500 |  | In Progress
The Vibe | 2025 | Resurface swimming pool | PNA - contingent amount to work on pool resurface | 84095 | GC | Capital Plan | 70000 | 21000 | 49000 |  | In Progress
The Vibe | 2025 | Pool Lift | HPCA - Add ADA lift to 1 pool | 84095 | GC | Capital Plan | 9500 | 2850 | 6650 |  | In Progress
The Vibe | 2025 | Pool Pumps | HPCA - Install variable speed pool pumps with VFD control | 84095 | GC | Capital Plan | 8659 | 2598 | 6061 |  | In Progress
The Vibe | 2025 | Replace swimming pool deck | PNA - address existing cracking on pool decks and cosmetic enhacement | 84095 | GC | Capital Plan | 40000 | 12000 | 28000 |  | In Progress
The Vibe | 2025 | Playground area | HPCA - Add ADA path of travel to playground | 84122 | GC | Capital Plan | 3500 | 1050 | 2450 |  | In Progress
The Vibe | 2025 | Dumpster enclosures | PNA - Replace fencing on all dumpster enclosures | 84125 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
The Vibe | 2025 | Carports / Garages | PNA - Replace rotted facia on carports | 84085 | GC | Capital Plan | 17000 | 17000 | 0 |  | Completed
The Vibe | 2025 | Drainage correction | HPCA - Drainage corrections at carports | 84432 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
The Vibe | 2025 | Concrete deck / floor fill | PNA - seal cracks in landings | 84102 | GC | Capital Plan | 26000 | 18200 | 7800 |  | In Progress
The Vibe | 2025 | Unit Deck Resurfacing | HPCA - Bldg. M Unit 302 Deck resurfacing. Exposed painted plywood at unit deck surface | 84105 | GC | Capital Plan | 1200 | 360 | 840 |  | In Progress
The Vibe | 2025 | Repair exterior stair treads and stringers | PNA - repair stair tread and stringers | 84114 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
The Vibe | 2025 | Repair exterior stair railings | PNA - repair and secure stair railings | 84205 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
The Vibe | 2025 | Repair balcony framing & decking | PNA - repair damaged patio framing | 84104 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
The Vibe | 2025 | Repair patio/balcony railings | PNA - secure all balcony railings | 84205 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
The Vibe | 2025 | Asphalt composite shingle roofing | PNA - Roof tune up on 37 buildings | 84050 | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
The Vibe | 2025 | Gutters & downspouts | PNA - Clean and secure gutters and down spouts HPCA - Repair selective areas of damaged gutter; reconnect Downspouts to | 84050 | GC | Capital Plan | 32000 | 32000 | 0 |  | Completed
The Vibe | 2025 | Flashing | PNA - Replace damaged drip edge on balconies | 84050 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
The Vibe | 2025 | Sealants & caulking | Roof Sealant & Caulking | 84050 | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
The Vibe | 2025 | Repair / replace wood siding | PNA - Replace rotted siding and scrape and paint Cedar siding | 84105 | GC | Capital Plan | 18000 | 18000 | 0 |  | Completed
The Vibe | 2025 | Repair stucco | Exterior Stucco Repair | 84105 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
The Vibe | 2025 | Exterior building | PNA - Paint community including peal stop on all delaminated cedar LPCA - Faded paint finishes were observed at several | 84101 | GC | Capital Plan | 592200 | 532980 | 59220 |  | In Progress
The Vibe | 2025 | Repair / replace wood trim | PNA - Replace all rotted trim throughout property | 84105 | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
The Vibe | 2025 | Fire Protection | Fire Stops | 84239 | PMC | Capital Plan | 24675 | 2798 | 21877 |  | In Progress
The Vibe | 2025 | Unit Water Leak Repairs | HPCA - Unit P104 Bathroom Water Leak Repairs | 84470 | PMC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
The Vibe | 2025 | Bathroom cleaning/klitz/painting with organic growth | HPCA - Excessive damage repair and repainting | 84304 | PMC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
The Vibe | 2025 | Security Camera System | Adding 9 security cameras (inc. installation, labor, etc.) | 84450 | PMC | Capital Plan | 37000 | 0 | 37000 |  | Not Started
The Vibe | 2025 | Water Distribution and Domestic Hot Water | Discuss with maintenace manager | 84470 | PMC | Capital Plan | 2250 | 10580 | -8330 |  | Completed
The Vibe | 2025 | Inspect defective heaters | HPCA - Review Cadet Heaters and replace any Models installed between 1982 through 1999 Modles: FW, FX, LX, TK, ZA, Z, RA | 84218 | GC | Capital Plan | 5250 | 5250 | 0 |  | Completed
The Vibe | 2025 | Inspect defective ITE electrical panels | HPCA - Given the Bldg.'s were constructed between 1985 and 1986 there is the potential some of the Unit ITE Electrical P | 84210 | GC | Capital Plan | 5250 | 5250 | 0 |  | Completed
The Vibe | 2025 | Replace recalled heaters | HPCA - Replace 16 Recalled Heaters (Estimated Potential Recalled Heaters) | 842220 | GC | Capital Plan | 3200 | 960 | 2240 |  | In Progress
The Vibe | 2025 | Replace electrical panels | HPCA - Replace 8 Electrical Panels (Estimated Potential Recalled Heaters) | 84210 | GC | Capital Plan | 36000 | 10800 | 25200 |  | In Progress
The Vibe | 2025 | Electrical distribution | PNA - Repair electric to pole lights and photo cells | 84210 | GC | Capital Plan | 12000 | 12000 | 0 |  | Completed
The Vibe | 2025 | Common area light fixtures | PNA - Replace pole lights around pool | 84210 | GC | Capital Plan | 7500 | 7500 | 0 |  | Completed
The Vibe | 2025 | Outlets & Dryer Vents | Contingent as needed | 84210 | PMC | Capital Plan | 2000 | 3898 | -1898 |  | Completed
The Vibe | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 229733 | 0 | 229733 |  | Reserve
The Vibe | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 78333 | 0 | 78333 |  | Reserve
Valera Riverside | 2025 | Repair / replace swimming pool pumps | seal small cracks on pool deck | 84361.0 | GC | Capital Plan | 6500 | 0 | 6500 |  | Not Started
Valera Riverside | 2025 | Retaining walls | Paint mural on retaining wall outside pool | 84434.0 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Valera Riverside | 2025 | Pergola | repair and stain bar and deck | 84195.0 | GC | Capital Plan | 9500 | 0 | 9500 |  | Not Started
Valera Riverside | 2025 | Outdoor Kitchen | replace broken gas valve | 84203.0 | GC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Valera Riverside | 2025 | Fire Stops | Fire stops | 84239.0 | PMC | Capital Plan | 25480 | 3345 | 22135 |  | In Progress
Valera Riverside | 2025 | Signage - Building identification | *Per Kevin for Signage Change/Rebrand | 84103.0 | PMC | Capital Plan | 50000 | 3833 | 46167 |  | In Progress
Valera Riverside | 2025 | Fitness Center Remodel | additional equipment | 84190.0 | PMC | Capital Plan | 20000 | 1814 | 18186 |  | In Progress
Valera Riverside | 2025 | Security/ fire alarm systems | Yellow, Non-Compliance tags were observed affixed to the sprinkler risers, dated May 2025. | 84211.0 | PMC | Capital Plan | 5000 | 2000 | 3000 |  | In Progress
Valera Riverside | 2025 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 7224 | 0 | 7224 |  | Reserve
Valera Riverside | 2025 | Construction Management Fee | CM Fees | 84505.0 | GC | CM Fee | 7585 | 0 | 7585 |  | Reserve
Windward | 2025 | Landscape Cleanup and Enhancements | Tree trimming (Added in after PNA/Site Visit) | 84303 | PMC | Capital Plan | 50000 | 19200 | 30800 |  | In Progress
Windward | 2025 | Asphalt Coating | PNA: Seal Coat and Crack Fill (Decreased by $127380 and moved BTL in Yr 5) | 84204 | GC | Capital Plan | 144000 | 43200 | 100800 |  | In Progress
Windward | 2025 | Stripe parking areas | Stripe Parking Lot Decreased $34,115 and moved BTL in Yr 9 | 84201 | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
Windward | 2025 | Pavement Repairs | PNA: Repair potholes Lender PCA/Equity PCA: Damaged pavement consisting of linear cracking and alligator cracking, was o | 84204 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
Windward | 2025 | ADA parking & curb cuts | Equity PCA: No van-accessible parking space was present at the leasing office. Installation of one van-accessible space | 83520 | PMC | Capital Plan | 1000 | 0 | 1000 |  | Not Started
Windward | 2025 | Exterior Stairs - Repair exterior stair railings | Post: Adding in painting of exterior railings | 84121 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Windward | 2025 | Asphalt composite shingle roofing | PNA: Standard roof tune up on ridge, vallt and pipe jacks; Equity PCA: Roof replacement - asphalt shingles (Yr 10) (Decr | 84433 | GC | Capital Plan | 22000 | 6600 | 15400 |  | In Progress
Windward | 2025 | Gutters & downspouts | PNA: Clean and repitch gutters throughout property | 84202.0 | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
Windward | 2025 | Exterior building | Capitalized year 5 work: exterior painting, repairing stucco, replacing wood trim, replacing siding (Decreased by $38,01 | 84206 | PMC | Capital Plan | 359000 | 371 | 358629 |  | In Progress
Windward | 2025 | Appliances Package | Cost Reallocation from BTL Yr1: Adjusted amount to reflect appliance actuals on Cortland's past BTL | 84431.0 | PMC | Capital Plan | 29680 | 0 | 29680 |  | Not Started
Windward | 2025 | Flooring | Cost Reallocation from BTL Yr1: Adjusted amount to reflect replacing one unit's floors per month ($3k per turn) | 84431.0 | PMC | Capital Plan | 36000 | 0 | 36000 |  | Not Started
Windward | 2025 | Clean Dryer vents | Clean vents and replace missing covers (Added in after PNA/Site Visit) | 84106 | GC | Capital Plan | 16170 | 4851 | 11319 |  | In Progress
Windward | 2025 | Water Heaters | Cost Reallocation from BTL Yr1: Adjusted amount to reflect water heater actuals on Cortland's past BTL | 84476.0 | PMC | Capital Plan | 16000 | 0 | 16000 |  | Not Started
Windward | 2025 | HVAC inspection and maintenance | Cost Reallocation from BTL Yr1: Adjusted amount to reflect HVAC actuals on Cortland's past BTL | 84218.0 | PMC | Capital Plan | 16000 | 2531 | 13469 |  | In Progress
Windward | 2025 | Doors | Cost Reallocation from BTL Yr1: replace sliding doors at turnover (40% in Yr 1, 30% in Yr 2, 20% in Yr 3, and 10% in Yr | 84304.0 | PMC | Capital Plan | 180000 | 1022 | 178978 |  | In Progress
Windward | 2025 | Fire Stops | PNA: Fire stops | 84211 | PMC | Capital Plan | 28812 | 24990 | 3822 |  | In Progress
Windward | 2025 | Carbon Monoxide/Smoke Detectors | Lender PCA: Two smoke-only detectors were observed in Units 16014 and 2004. This appeared to be a rare exception, and th | 83236 | PMC | Capital Plan | 450 | 0 | 450 |  | Not Started
Windward | 2025 | Signage - Site | Post: Adding in signage to account for switching from Cortland signage | 84103 | PMC | Capital Plan | 50000 | 1032 | 48968 |  | In Progress
Windward | 2025 | Security Camera System | Vistria: address adding security cameras to mailbox area | 84450 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Windward | 2025 | Golf Cart | Post: Adding in new leasing golf cart | 83375 | PMC | Capital Plan | 15000 | 5814 | 9186 |  | In Progress
Windward | 2025 | Replace AC condenser | PNA: Add insulation to Condensing unit lines | 84218.0 | GC | Capital Plan | 26000 | 7800 | 18200 |  | In Progress
Windward | 2025 | Electrical Panel Disconnects & Meter Banks | Vistria: raise electrical panel replacements up front @ $2,300 a unit | 84330 | GC | Capital Plan | 676200 | 202860 | 473340 |  | In Progress
Windward | 2025 | Common area light fixtures | Vistria: address adding exterior lighting around mailbox area (includes other lighting enhancements) | 84210 | GC | Capital Plan | 35000 | 10500 | 24500 |  | In Progress
Windward | 2025 | Contingency | Contingency Amount | 84510 | GC | Contingency | 89516 | 0 | 89516 |  | Reserve
Windward | 2025 | Construction Management Fee | CM Fees | 84505 | GC | CM Fee | 93991 | 0 | 93991 |  | Reserve
Almaden 1930 | 2026 | Landscape Cleanup and Enhancements | Post: General curb appeal enhancement | 51045-00 | GC | Capital Plan | 35000 | 96250 | -61250 |  | Completed
Almaden 1930 | 2026 | Asphalt Coating | PNA: Repair asphalt, seal coat, and stripe. Lender PCA: The asphalt pavement has localized alligator cracking, and gener | 51051-00 | GC | Capital Plan | 32970 | 700 | 32270 |  | In Progress
Almaden 1930 | 2026 | Repair / replace swimming pool pumps | PNA: Anti entrapment devices | 51025-00 | GC | Capital Plan | 7140 | 63158 | -56018 |  | Completed
Almaden 1930 | 2026 | Fences & gates - swimming pool | PNA: Repair and paint pool fence | 51025-00 | GC | Capital Plan | 22050 | 0 | 22050 |  | Not Started
Almaden 1930 | 2026 | Carports / Garages | PNA: Repair car ports and paint posts and pearling | 51172-00 | GC | Capital Plan | 13650 | 0 | 13650 |  | Not Started
Almaden 1930 | 2026 | ADA parking & curb cuts | Lender PCA: One van accessible space should be added at the leasing office. The restroom at the leasing office has acces | 51091-00 | GC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Almaden 1930 | 2026 | Sidewalks | Lender PCA: A cracked walkway was observed. Immediate repairs are recommended to repair the walkway. | 51091-00 | GC | Capital Plan | 500 | 0 | 500 |  | Not Started
Almaden 1930 | 2026 | Landscape irrigation | PNA: Inspect and repair irrigation | 51045-00 | GC | Capital Plan | 29400 | 0 | 29400 |  | Not Started
Almaden 1930 | 2026 | Fences & gates - site perimeter | PNA: Overlay wood fence on back of community. Lender PCA: Some of the chain link has been bowed slightly where cars have | 51077-00 | GC | Capital Plan | 19950 | 0 | 19950 |  | Not Started
Almaden 1930 | 2026 | Retaining walls | PNA: Rebuild one section of retaining wall | 51085-00 | GC | Capital Plan | 16800 | 0 | 16800 |  | Not Started
Almaden 1930 | 2026 | Landscaping | PNA: Remove dead tree branches and trim trees. EPCA: Trees were observed impeding on the building rooftops and facades o | 51043-00 | GC | Capital Plan | 91350 | 0 | 91350 |  | Not Started
Almaden 1930 | 2026 | Resurface swimming pool | PNA: Repair to pool shell and resurface pool | 51025-00 | GC | Capital Plan | 68250 | 0 | 68250 |  | Not Started
Almaden 1930 | 2026 | Replace swimming pool coping | PNA: Replace decko seal | 51025-00 | GC | Capital Plan | 9975 | 0 | 9975 |  | Not Started
Almaden 1930 | 2026 | Replace swimming pool deck | PNA: Pressure wash and seal brick pool deck | 51025-00 | GC | Capital Plan | 18900 | 0 | 18900 |  | Not Started
Almaden 1930 | 2026 | Storm sewer piping | PNA: Clean storm drains. EPCA: Debris was observed clogging storm drains. Clearing the debris is recommended | 51130-00 | GC | Capital Plan | 18900 | 0 | 18900 |  | Not Started
Almaden 1930 | 2026 | Termite Remediation | EPCA: Partner engaged Terminix for a termite and fungus/dryrot inspection at the subject property. Based on their findin | 51992-00 | GC | Capital Plan | 35000 | 17500 | 17500 |  | In Progress
Almaden 1930 | 2026 | Water distribution piping | PNA: Install sewer covers | 51134-00 | GC | Capital Plan | 10500 | 14700 | -4200 |  | Completed
Almaden 1930 | 2026 | Concrete deck / floor fill | PNA: Rebuild 20% of balconies | 51072-00 | GC | Capital Plan | 124488 | 0 | 124488 |  | Not Started
Almaden 1930 | 2026 | Wall framing | PNA: Replace damaged framing in gable ends | 51070-00 | GC | Capital Plan | 14700 | 0 | 14700 |  | Not Started
Almaden 1930 | 2026 | Balcony inspection | Lender PCA: Based on exterior appurtenances, this Property is subject to the State of California Law. According to a rec | 51072-00 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Almaden 1930 | 2026 | Repair exterior stair treads and stringers | PNA: Repair stair treads and stringers | 51093-00 | GC | Capital Plan | 9975 | 0 | 9975 |  | Not Started
Almaden 1930 | 2026 | Repair exterior stair railings | PNA: Secure railings | 51077-00 | GC | Capital Plan | 10500 | 0 | 10500 |  | Not Started
Almaden 1930 | 2026 | Repair balcony framing & decking | PNA: Add joist hangers to balcony joists | 51072-00 | GC | Capital Plan | 30450 | 5000 | 25450 |  | In Progress
Almaden 1930 | 2026 | Repair balcony railings | PNA: Secure railings | 51077-00 | GC | Capital Plan | 9975 | 0 | 9975 |  | Not Started
Almaden 1930 | 2026 | Asphalt composite shingle roofing | PNA: Roof tune up and Roof replacements (Yr. 8): | 51061-00 | GC | Capital Plan | 40950 | 29675 | 11275 |  | In Progress
Almaden 1930 | 2026 | Gutters & downspouts | PNA: Secure and clean gutters. Lender PCA: Ac cracked concrete gutter was observed at the driveway entrance to the prope | 51071-00 | GC | Capital Plan | 10551 | 0 | 10551 |  | Not Started
Almaden 1930 | 2026 | Sealants & caulking | PNA: Seal between T-111 siding | 51062-00 | GC | Capital Plan | 37800 | 0 | 37800 |  | Not Started
Almaden 1930 | 2026 | Flashing | PNA: Add z flash to replacement siding | 51062-00 | GC | Capital Plan | 29400 | 0 | 29400 |  | Not Started
Almaden 1930 | 2026 | Repair / replace wood siding | PNA: Replace rotted siding. EPCA: Partner observed deteriorated siding located below and near dryer vents at the communa | 51070-00 | GC | Capital Plan | 69250 | 0 | 69250 |  | Not Started
Almaden 1930 | 2026 | Repair / replace wood trim | PNA: Replace rotted fascia and trim | 51070-00 | GC | Capital Plan | 58800 | 0 | 58800 |  | Not Started
Almaden 1930 | 2026 | Paint community | PNA: Paint community - LRR | 51080-00 | GC | Capital Plan | 239400 | 0 | 239400 |  | Not Started
Almaden 1930 | 2026 | Designer Fees | Post: Leasing office refresh | 51200-00 | GC | Capital Plan | 32500 | 16250 | 16250 |  | In Progress
Almaden 1930 | 2026 | Pool Furniture | Post: Pool furniture replacement | 51011-00 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Almaden 1930 | 2026 | Smoke/fire detection | Lender PCA: Smoke detectors were generally present where required, however several units were observed where the tenant | 51990-00 | GC | Capital Plan | 1000 | 1000 | 0 |  | Completed
Almaden 1930 | 2026 | Sanitary Sewer Piping | Jet main drain lines per scope | 51131-00 | GC | Capital Plan | 28896 | 11000 | 17896 |  | In Progress
Almaden 1930 | 2026 | Electrical Panel Disconnects & Meter Banks | Lender PCA: At unit electric panels, some panels did not have the breakers labeled. Immediate repairs are recommended fo | 51140-00 | PMC | Capital Plan | 150000 | 0 | 150000 |  | Not Started
Almaden 1930 | 2026 | Electrical IR Inspection | EPCA: Based on the age of the property and some of the electrical equipment, an IR survey is recommended. | 51140-00 | GC | Capital Plan | 6130 | 0 | 6130 |  | Not Started
Almaden 1930 | 2026 | Electrical distribution | PNA: Inspect and repair lighting controllers on all buildings | 51140-00 | GC | Capital Plan | 18900 | 0 | 18900 |  | Not Started
Almaden 1930 | 2026 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 87089 | 0 | 87089 |  | Reserve
Almaden 1930 | 2026 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 73654 | 0 | 73654 |  | Reserve
Ardmore Springs | 2026 | Asphalt Coating | PNA: Repair potholes. Lender PCA: One area with a failed asphalt patch was noted in front of Building 11. Priority repai | 84204.0 | GC | Capital Plan | 30000 | 9000 | 21000 |  | In Progress
Ardmore Springs | 2026 | ADA parking & curb cuts | Lender PCA: One ADA parking space at the leasing office has a post for an ADA sign, but the face is blank and missing th | 84221.0 | PMC | Capital Plan | 150 | 0 | 150 |  | Not Started
Ardmore Springs | 2026 | Sidewalks | PNA: Repair trip hazards | 84221.0 | GC | Capital Plan | 8500 | 2550 | 5950 |  | In Progress
Ardmore Springs | 2026 | Landscape irrigation | Lender PCA: A broken irrigation line was observed at Building 6. Priorty repairs are recommended to repair the broken ir | 84302.0 | PMC | Capital Plan | 500 | 0 | 500 |  | Not Started
Ardmore Springs | 2026 | Erosion control | PNA: Add rocks at downspout in eroded areas | 83517.0 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Ardmore Springs | 2026 | Fences & gates - site perimeter | Lender PCA: The site fencing near the pet wash station near the operable gate is damaged. Priority repairs are recommend | 84205.0 | PMC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Ardmore Springs | 2026 | Building entrance | Post: Signage replacements for rebranding | 84103.0 | PMC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Ardmore Springs | 2026 | Mold and water remediation | Lender PCA: Approximately 12 sf of suspect mold was observed at the fire sprinkler room of Building 8, possibly from tes | 83160.0 | PMC | Capital Plan | 2500 | 0 | 2500 |  | Not Started
Ardmore Springs | 2026 | Repair exterior stair railings | PNA: Secure stair rails | 84121.0 | GC | Capital Plan | 8500 | 2550 | 5950 |  | In Progress
Ardmore Springs | 2026 | Repair balcony framing & decking | PNA: Repair vinyl on balcony band board ($10,000) and secure all patio railings ($6,500) | 84104.0 | GC | Capital Plan | 16500 | 4950 | 11550 |  | In Progress
Ardmore Springs | 2026 | Expansion joints | Expansion Joints | 84206.0 | GC | Capital Plan | 8000 | 2400 | 5600 |  | In Progress
Ardmore Springs | 2026 | Asphalt composite shingle roofing | PNA: Roof inspection and tune up | 84433.0 | GC | Capital Plan | 22000 | 6600 | 15400 |  | In Progress
Ardmore Springs | 2026 | Gutters & downspouts | PNA: Replace damaged gutter and downspouts, clean, re-pitch remaining | 84202.0 | GC | Capital Plan | 11000 | 3300 | 7700 |  | In Progress
Ardmore Springs | 2026 | Sealants & caulking | Roof Sealants and Caulking | 84433.0 | GC | Capital Plan | 8500 | 2550 | 5950 |  | In Progress
Ardmore Springs | 2026 | Flashing | PNA: Replace damaged flashing on breezeway roofs | 84433.0 | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
Ardmore Springs | 2026 | Repair / replace cement fiber siding | PNA: Replace damaged siding and paint | 84206.0 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Ardmore Springs | 2026 | Repair / replace wood shingles | PNA: Replace rotted trim and paint to match | 84113.0 | GC | Capital Plan | 5000 | 1500 | 3500 |  | In Progress
Ardmore Springs | 2026 | Dryer Vents | Lender PCA: Three locations total, at Building 5 and 10, exhibit missing laundry vent covers which allows for moisture a | 83106.0 | PMC | Capital Plan | 225 | 0 | 225 |  | Not Started
Ardmore Springs | 2026 | Tuck-pointing | Lender PCA: One stairstep cracked area was observed in the central part of an entrance arch of brick masonry facade at b | 83212.0 | GC | Capital Plan | 1000 | 300 | 700 |  | In Progress
Ardmore Springs | 2026 | Breezeway soffit repairs | PNA: Repair breezeway soffit | 84120.0 | GC | Capital Plan | 9500 | 2850 | 6650 |  | In Progress
Ardmore Springs | 2026 | Exterior building | PNA: Paint community, iron will require special treatment | 84101.0 | GC | Capital Plan | 300000 | 90000 | 210000 |  | In Progress
Ardmore Springs | 2026 | Masonry Repairs | PNA: Pressure wash vinyl on posts and balcony head | 84102.0 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Ardmore Springs | 2026 | Appliances Package | Post: Washer/Dryer installs | 82200.0 | PMC | Capital Plan | 272400 | 38587 | 233813 |  | In Progress
Ardmore Springs | 2026 | Radon remediation | Per ESA: Radon remediation in 9 areas, ($3,500-$4,500 per location) EBI recommends completing pilot testing, building ch | 84250.0 | GC | Capital Plan | 47750 | 14325 | 33425 |  | In Progress
Ardmore Springs | 2026 | Leasing office floor/wall finishes, Replace Furniture | Post: Remodel leasing office (Paint - 1st Call & Furniture - PMC) | 84116.0 | GC | Capital Plan | 119850 | 0 | 119850 |  | Not Started
Ardmore Springs | 2026 | Leasing office | Lender PCA: The sinks at the leasing office bathroom do not appear to havescald/abrasion protection at the sink piping a | 84116.0 | GC | Capital Plan | 150 | 35955 | -35805 |  | Completed
Ardmore Springs | 2026 | Fitness Center Remodel | PNA: Repair sheetrock and paint fitness center and package room | 84190.0 | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
Ardmore Springs | 2026 | Gym Equipment | Post: Replace gym equipment | 84190.0 | PMC | Capital Plan | 50000 | 8571 | 41429 |  | In Progress
Ardmore Springs | 2026 | Unit Model Update | Post: Set up model unit | 84280.0 | PMC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Ardmore Springs | 2026 | Fire stops | PNA: Fire stops | 84239.0 | PMC | Capital Plan | 24696 | 41880 | -17184 |  | Completed
Ardmore Springs | 2026 | Stormwater Pipe Repair | PNA: Clean storm sewer basins | 84432.0 | GC | Capital Plan | 4000 | 1200 | 2800 |  | In Progress
Ardmore Springs | 2026 | Replace defective outlet | Lender PCA: One GFCI outlet at unit 4206 in the kitchen does not reset, and priorty repairs are recommended to replace t | 84210.0 | PMC | Capital Plan | 30 | 0 | 30 |  | Not Started
Ardmore Springs | 2026 | Replace electric baseboard heater | Lender PCA: One electric baseboard heater located within the sprinkler system closet in building 8 was noted to have dis | 83217.0 | PMC | Capital Plan | 500 | 624 | -124 |  | Completed
Ardmore Springs | 2026 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 56013 | 0 | 56013 |  | Reserve
Ardmore Springs | 2026 | Construction Management Fee | CM Fee | 84505.0 | GC | CM Fee | 58813 | 0 | 58813 |  | Reserve
Bentley Parke | 2026 | Storm sewer piping and drains | PNA - Clear drains on pool deck |  | GC | Capital Plan | 5000 | 1500 | 3500 |  | In Progress
Bentley Parke | 2026 | Sidewalks and curbs | PNA - Grind trip hazards |  | GC | Capital Plan | 13000 | 3900 | 9100 |  | In Progress
Bentley Parke | 2026 | Carports / Garages | PNA - Repair carports |  | GC | Capital Plan | 22000 | 6600 | 15400 |  | In Progress
Bentley Parke | 2026 | Dumpster enclosures | PNA - Repair dumpster enclosures |  | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
Bentley Parke | 2026 | WDIR | WDIR Treatment per Inspection |  | PMC | Capital Plan | 15900 | 0 | 15900 |  | Not Started
Bentley Parke | 2026 | Concrete deck / floor fill | PNA - Repair landings |  | GC | Capital Plan | 15000 | 4500 | 10500 |  | In Progress
Bentley Parke | 2026 | Exterior building | PNA - Paint community 100% paintable 3.2.4. Painting, Exterior. The paint finish on the apartment buildings was observe |  | GC | Capital Plan | 382800 | 114840 | 267960 |  | In Progress
Bentley Parke | 2026 | Repair exterior stair treads and stringers | PNA - Replace 40 broken stair treads |  | GC | Capital Plan | 18900 | 5670 | 13230 |  | In Progress
Bentley Parke | 2026 | Expansion joints | PNA - Seal expansion joints |  | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
Bentley Parke | 2026 | Asphalt composite shingle roofing | PNA - Roof tune up 3.2.8 - Asphalt Shingle (3-tab). The inboard parapet asphalt shingle installation date was not provid |  | GC | Capital Plan | 10260 | 3078 | 7182 |  | In Progress
Bentley Parke | 2026 | Modified bitumen membrane roof repairs | PNA - Repairs to flat roofing and repairs with modified bit 3.2.8. - Built-up roof / Modified Bitumen |  | GC | Capital Plan | 75000 | 22800 | 52200 |  | In Progress
Bentley Parke | 2026 | Gutters & downspouts | PNA - Clean and repatch gutters throughout property |  | GC | Capital Plan | 21000 | 6300 | 14700 |  | In Progress
Bentley Parke | 2026 | Flashing | PNA - Repair parapet wall flashing |  | GC | Capital Plan | 15600 | 4680 | 10920 |  | In Progress
Bentley Parke | 2026 | Sealants & caulking | PNA - Seal windows as part of paint |  | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
Bentley Parke | 2026 | Repair stucco | PNA - Repairs to stucco |  | GC | Capital Plan | 26000 | 7800 | 18200 |  | In Progress
Bentley Parke | 2026 | Domestic Hot Water Heater, Replace | 3.3.5 - Water Heater Sesimic Strapping. The water heaters lacked one or both seismic bracing straps at observed units 10 |  | PMC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Bentley Parke | 2026 | Electrical distribution | PNA - Replace lighting controlers |  | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
Bentley Parke | 2026 | Replace breezeway lights | PNA - R&R ceiling lights in breezeways with LED |  | GC | Capital Plan | 38600 | 11580 | 27020 |  | In Progress
Bentley Parke | 2026 | Interior Upgrades | Raising Y1 of Unit Interior Upgrades upfront |  | PMC | Capital Plan | 260680 | 38010 | 222670 |  | In Progress
Bentley Parke | 2026 | Drier vents | PNA - Remove vent covers, clean vent piping, and install new dryer vent covers |  | GC | Capital Plan | 38280 | 11484 | 26796 |  | In Progress
Bentley Parke | 2026 | Fire Stops | PNA - Fire stops |  | PMC | Capital Plan | 22736 | 1916 | 20820 |  | In Progress
Bentley Parke | 2026 | ADA - Leasing Office Restrooms | 5.4 - The plumbing under the lavatories within the publicly-accessible toilet rooms did not appear to be configured to p |  | PMC | Capital Plan | 300 | 25 | 275 |  | In Progress
Bentley Parke | 2026 | Unit Deferred Maintenance | Down Unit Refurbishment (Unit 1405) - Damaged bedroom ceiling ($8,000) Roof Leak Repair (Unit 1405) - Repair Roof above |  | GC | Capital Plan | 9000 | 2400 | 6600 |  | In Progress
Bentley Parke | 2026 | CA SB-721 Elevated Exterior Elements Inspection | 3.2.7 - According to a recent State of California Law (SB 721), subject properties that contain “exterior elevated eleme |  | GC | Capital Plan | 6500 | 1950 | 4550 |  | In Progress
Bentley Parke | 2026 | Clubhouse / Office remodel | Concept Walk - Convert staff room to a business center/cybercafe |  | PMC | Capital Plan | 25000 | 3750 | 21250 |  | In Progress
Bentley Parke | 2026 | Security/ fire alarm systems | Concept Walk - Add security cameras |  | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Bentley Parke | 2026 | Swimming pool deck | PNA - Presure wash pool deck |  | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
Bentley Parke | 2026 | Swimming Pool Shower | Concept Walk - Re-tile shower |  | GC | Capital Plan | 5000 | 1500 | 3500 |  | In Progress
Bentley Parke | 2026 | Swimming pool fencing / gates | PNA - Repair pool fence |  | GC | Capital Plan | 5600 | 1680 | 3920 |  | In Progress
Bentley Parke | 2026 | BBQ Grill Area | Concept Walk - Add BBQ/Grill Area outside swimming pool fence |  | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
Bentley Parke | 2026 | Contingency | Contingency Amount |  | GC | Contingency | 58758 | 0 | 58758 |  | Reserve
Bentley Parke | 2026 | Construction Management Fee | CM Fee |  | GC | CM Fee | 61696 | 0 | 61696 |  | Reserve
Cherry Creek | 2026 | Storm sewer piping and drains | PNA: clean storm drains | 51130-00 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Cherry Creek | 2026 | Asphalt seal coating | Lender PCA: Damaged pavement consisting of linear cracking was present at the drive aisles typical of the conditions not | 51053-00 | GC | Capital Plan | 81000 | 0 | 81000 |  | Not Started
Cherry Creek | 2026 | Stripe parking areas | Stripe Parking Lots | 51053-00 | GC | Capital Plan | 28000 | 0 | 28000 |  | Not Started
Cherry Creek | 2026 | Sidewalks and curbs | Lender PCA: A potential trip hazard consisting of vertical and horizontal separation was observed to the northeast of bu | 51091-00 | PMC | Capital Plan | 500 | 0 | 500 |  | Not Started
Cherry Creek | 2026 | Sidewalks and curbs | PNA: Trip Hazards | 51091-00 | GC | Capital Plan | 14000 | 0 | 14000 |  | Not Started
Cherry Creek | 2026 | Landscape Cleanup & Enhancements | Lender PCA: Trees were observed impeding on the building rooftop and facade between units 54 and 64. No portion of any t | 51045-00 | PMC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Cherry Creek | 2026 | Carports / Garages | PNA: Carport repairs and paint post and pearling | 51172-00 | GC | Capital Plan | 36000 | 0 | 36000 |  | Not Started
Cherry Creek | 2026 | Dumpster enclosures | Lender PCA: The threshold height at the accessible leasing office entrance does not appear to be ADA-compliant. Installa | 51163-00 | PMC | Capital Plan | 125 | 0 | 125 |  | Not Started
Cherry Creek | 2026 | Termite Remediation | Lender PCA: Termite remediation - Evidence of drywood termites for areas 2A, 2C, 2E, 2F, 2H, and 2I on the termite map. | 51992-00 | PMC | Capital Plan | 23250 | 1000 | 22250 |  | In Progress
Cherry Creek | 2026 | Termite damage repairs | Lender PCA: Termite Damage - Repair and replace damaged materials noted on the termite report. Lender PCA: Termite Damag | 51070-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Cherry Creek | 2026 | Repair exterior stair railings | PNA: secure and paint railings | 51077-00 | GC | Capital Plan | 26000 | 0 | 26000 |  | Not Started
Cherry Creek | 2026 | Repair patio/balcony railings/fences | Lender PCA: Deteriorated and damaged wood framing and trim were noted at balconies and upper landings including at build | 51077-00 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Cherry Creek | 2026 | Repair Catwalks | PNA: secure catwalk railings | 51072-00 | GC | Capital Plan | 28000 | 0 | 28000 |  | Not Started
Cherry Creek | 2026 | Expansion Joints | PNA: Stucco expansion joints | 51090-00 | GC | Capital Plan | 6000 | 0 | 6000 |  | Not Started
Cherry Creek | 2026 | Gutters & downspouts | Lender PCA: Leaf accumulation was noted in gutters across the site. Removal of the leaf debris is recommended. PNA: sec | 51071-00 | GC | Capital Plan | 19000 | 0 | 19000 |  | Not Started
Cherry Creek | 2026 | Sealants & caulking | PNA: seal and prep stucco | 51062-00 | GC | Capital Plan | 36000 | 0 | 36000 |  | Not Started
Cherry Creek | 2026 | Repair Roof Gambles | Lender PCA: Deteriorated and damaged roof gables were observed at buildings 6 and 7. Repair of the noted issues is recom | 84433.0 | GC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Cherry Creek | 2026 | Repair / replace wood shingles | PNA: Replace rotted fascia and trim | 51075-00 | GC | Capital Plan | 46000 | 0 | 46000 |  | Not Started
Cherry Creek | 2026 | Wall framing | PNA: damaged framing on stair supports | 51159-00 | GC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Cherry Creek | 2026 | Stucco repairs | PNA: Stucco repairs | 51075-00 | GC | Capital Plan | 40000 | 0 | 40000 |  | Not Started
Cherry Creek | 2026 | Exterior paint | Lender PCA: Peeling paint was observed on the exterior stairway wall of building 7. Reapplication of exterior paint is r | 51080-00 | GC | Capital Plan | 230000 | 0 | 230000 |  | Not Started
Cherry Creek | 2026 | Unit water heaters | PNA: replace two hot water heaters | 50050-00 | GC | Capital Plan | 42000 | 0 | 42000 |  | Not Started
Cherry Creek | 2026 | Electrical distribution - exterior | PNA: Place Holder for electric meter and load center replacement | 51140-00 | GC | Capital Plan | 80000 | 0 | 80000 |  | Not Started
Cherry Creek | 2026 | Pole lighting | Retrofit porch lights to LED - Concept Walk | 51141-00 | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Cherry Creek | 2026 | Breezeway and patio lights | Concept Walk: there are 13 breezeways (budgeting $750/unit) | 51141-00 | GC | Capital Plan | 9750 | 0 | 9750 |  | Not Started
Cherry Creek | 2026 | Fire monitoring system | Fire Stops: Expire 2031 but some maybe old - approx. 50% - Concept Walk | 51177-00 | PMC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Cherry Creek | 2026 | Security alarm systems | Lender PCA: An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recert | 51993-00 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Cherry Creek | 2026 | Elevators | Lender PCA: Current operation permits were not posted in each elevator cab. Property management should schedule reinspec | 51164-00 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Cherry Creek | 2026 | Swimming pool resurface | PNA: resurface pool | 51023-00 | GC | Capital Plan | 52000 | 0 | 52000 |  | Not Started
Cherry Creek | 2026 | Swimming pool deck | PNA: deck o seal on pool | 51022-00 | GC | Capital Plan | 14000 | 0 | 14000 |  | Not Started
Cherry Creek | 2026 | Swimming pool pumps repair / replace | PNA: anti entrapment devices | 51026-00 | GC | Capital Plan | 6800 | 0 | 6800 |  | Not Started
Cherry Creek | 2026 | Swimming pool fencing / gates | PNA: Repair fence and Paint | 51076-00 | GC | Capital Plan | 22000 | 0 | 22000 |  | Not Started
Cherry Creek | 2026 | Pool furniture | Pool Furniture Straps, BBQ Grill Upgrade - Concept Walk | 51011-00 | PMC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Cherry Creek | 2026 | Contingency | Contingency Amount | 51990-00 | GC | Contingency | 49171 | 0 | 49171 |  | Reserve
Cherry Creek | 2026 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 51630 | 0 | 51630 |  | Reserve
Clipper Cove | 2026 | Storm sewer piping and drains | PNA - Clean storm drains throughout property |  | GC | Capital Plan | 24000 | 7200 | 16800 |  | In Progress
Clipper Cove | 2026 | Parking lot repairs | PNA - Seal coat entire parking lot - add crack fill as needed |  | GC | Capital Plan | 430000 | 129000 | 301000 |  | In Progress
Clipper Cove | 2026 | Asphalt seal coating | PNA - Repair broken or failing asphalt LPCA - Asphalt pavement |  | GC | Capital Plan | 68000 | 20400 | 47600 |  | In Progress
Clipper Cove | 2026 | Stripe parking areas | PNA - Stripe parking areas |  | GC | Capital Plan | 24000 | 7200 | 16800 |  | In Progress
Clipper Cove | 2026 | ADA parking & ramps | PNA - Repairs to failing ADA ramps LPCA - ADA van-accessible parking |  | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
Clipper Cove | 2026 | Sidewalks and curbs | PNA - Replace failing areas of sidewalk LPCA - Trip hazards at concrete walkway |  | GC | Capital Plan | 42000 | 12600 | 29400 |  | In Progress
Clipper Cove | 2026 | Detention pond fountain | Concept Walk - Installation of 6 lake fountains |  | GC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Clipper Cove | 2026 | Erosion control and drainage | PNA - Erosion control around all buildings |  | GC | Capital Plan | 82500 | 24750 | 57750 |  | In Progress
Clipper Cove | 2026 | Landscape irrigation | Concept Walk - Irrigation LPCA - Irrigation |  | GC | Capital Plan | 40000 | 300 | 39700 |  | In Progress
Clipper Cove | 2026 | Landscape Cleanup & Enhancements | Concept Walk - Office landscape enhancements |  | GC | Capital Plan | 50000 | 8572 | 41428 |  | In Progress
Clipper Cove | 2026 | Tree Trimming | PNA - Tree trim, get overgrowth off buildings |  | GC | Capital Plan | 48000 | 14400 | 33600 |  | In Progress
Clipper Cove | 2026 | Dumpster enclosures | PNA - Repair dumpster enclosures |  | GC | Capital Plan | 42000 | 12600 | 29400 |  | In Progress
Clipper Cove | 2026 | Termite damage repairs | LPCA - WDO Repairs |  | GC | Capital Plan | 19500 | 5850 | 13650 |  | In Progress
Clipper Cove | 2026 | Repair balcony framing & decking | PNA - Repair failing lightweight concrete on catwalk |  | GC | Capital Plan | 49000 | 14700 | 34300 |  | In Progress
Clipper Cove | 2026 | Repair exterior stair treads and stringers | PNA - Replace twenty failing exterior stair cases LPCA - Exterior stairs, balconies, and breezeways (near units 104 and |  | GC | Capital Plan | 360000 | 108000 | 252000 |  | In Progress
Clipper Cove | 2026 | Repair exterior stair railings | PNA - Repair failing stair and catwalk railings |  | GC | Capital Plan | 86000 | 25800 | 60200 |  | In Progress
Clipper Cove | 2026 | Expansion Joints | PNA - Expansion joints |  | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
Clipper Cove | 2026 | Modified bitumen membrane repairs / replacement | PNA - Replace the modified bit roofing on racquetball structures |  | GC | Capital Plan | 16500 | 4950 | 11550 |  | In Progress
Clipper Cove | 2026 | Gutters & downspouts | PNA - Repair, clean, reattach replace gutters throughout the property |  | GC | Capital Plan | 62500 | 18750 | 43750 |  | In Progress
Clipper Cove | 2026 | Sealants & caulking | PNA - Sealants & caulking |  | GC | Capital Plan | 24000 | 7200 | 16800 |  | In Progress
Clipper Cove | 2026 | Repair / replace siding | PNA - Pressure wash to remove mildew. Repair/replace damaged or broken vinyl siding matching the existing color |  | GC | Capital Plan | 92000 | 27600 | 64400 |  | In Progress
Clipper Cove | 2026 | Wall framing | PNA - Repair structural framing in areas that indicate failures |  | GC | Capital Plan | 210000 | 63000 | 147000 |  | In Progress
Clipper Cove | 2026 | Stucco repairs | PNA - Failing and damaged stucco was observed throughout the property |  | GC | Capital Plan | 82000 | 24600 | 57400 |  | In Progress
Clipper Cove | 2026 | Exterior paint | PNA - Paint stucco, trim and wood rails |  | GC | Capital Plan | 428000 | 128400 | 299600 |  | In Progress
Clipper Cove | 2026 | Repair / replace wood trim | PNA - Rotted window trim and facia was observed, repairs would include paint to match |  | GC | Capital Plan | 52000 | 15600 | 36400 |  | In Progress
Clipper Cove | 2026 | HVAC pipe insulation | PNA - Install linset insulation |  | GC | Capital Plan | 24000 | 7200 | 16800 |  | In Progress
Clipper Cove | 2026 | Electrical distribution - exterior | PNA - Electrical distribution LPCA - Electrical (open electrical boxes were observed near irrigation piping) |  | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
Clipper Cove | 2026 | Pole lighting | PNA - Replace with LED fixture |  | GC | Capital Plan | 39000 | 11700 | 27300 |  | In Progress
Clipper Cove | 2026 | Lighing controller system | PNA - Common area light fixtures (building light LED retrofit) |  | GC | Capital Plan | 46000 | 13800 | 32200 |  | In Progress
Clipper Cove | 2026 | Interior Upgrades | Concept Walk - Renovate classic units |  | PMC | Capital Plan | 1000000 | 63780 | 936220 |  | In Progress
Clipper Cove | 2026 | Drier vents | PNA - Drier vents |  | PMC | Capital Plan | 28800 | 0 | 28800 |  | Not Started
Clipper Cove | 2026 | Stovetop fire suppression | PNA - Fire protection |  | PMC | Capital Plan | 37632 | 0 | 37632 |  | Not Started
Clipper Cove | 2026 | Interior microbial growth treatment | LPCA - Localized water staining was observed at the ceiling of Unit 103.The unit appears to currently be used for miscel |  | PMC | Capital Plan | 1000 | 0 | 1000 |  | Not Started
Clipper Cove | 2026 | Patio Fence Enclosure | Concept Walk - Screened in porches for all unit stacks |  | GC | Capital Plan | 270000 | 81000 | 189000 |  | In Progress
Clipper Cove | 2026 | Clubhouse / Office remodel | Concept Walk - Clubhouse repaint, kitchen remodel, & flooring |  | GC | Capital Plan | 95000 | 28500 | 66500 |  | In Progress
Clipper Cove | 2026 | Clubhouse / Office redecorate (FFE) | Concept Walk - Leasing office / clubhouse redec and furniture |  | PMC | Capital Plan | 105000 | 14962 | 90038 |  | In Progress
Clipper Cove | 2026 | Model Unit | Concept Walk - Update model to include appliances, cabinetry, flooring, & fixtures |  | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Clipper Cove | 2026 | Golf Cart | Concept Walk - 3 golf carts |  | PMC | Capital Plan | 45000 | 0 | 45000 |  | Not Started
Clipper Cove | 2026 | Swimming pool resurface | PNA - Resurface the pool and hot tub at the leasing office |  | GC | Capital Plan | 38000 | 11400 | 26600 |  | In Progress
Clipper Cove | 2026 | Swimming pool coping and tile | PNA - Replace swimming pool coping |  | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
Clipper Cove | 2026 | Swimming pool deck | PNA - Powerwash decking on both pools |  | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
Clipper Cove | 2026 | Swimming pool pumps repair / replace | PNA - Repair the hot tub that is currently not working Concept Walk - Fill in hot tub and make seating area |  | GC | Capital Plan | 50000 | 15000 | 35000 |  | In Progress
Clipper Cove | 2026 | Pool furniture | Concept Walk - 1st pool furniture + 2nd pool furniture |  | PMC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Clipper Cove | 2026 | Tennis / sports court | Concept Walk - Tennis court repurpose ($100k) + repurpose racquetball court to maintenance/storage ($50k) LPCA - Tennis |  | GC | Capital Plan | 134854 | 40456 | 94398 |  | In Progress
Clipper Cove | 2026 | Playground area and equipment | PNA - install fall zone borders and add fall zone material |  | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
Clipper Cove | 2026 | Pool Area Upgrades | Concept Walk - Turf installation, landscape cleanup, lighting replacement, palm tree cleanup, etc. |  | GC | Capital Plan | 250000 | 75000 | 175000 |  | In Progress
Clipper Cove | 2026 | Contingency | Contingency Amount |  | GC | Contingency | 237714 | 0 | 237714 |  | Reserve
Clipper Cove | 2026 | Construction Management Fee | CM Fee |  | GC | CM Fee | 249600 | 0 | 249600 |  | Reserve
Cypress Ridge | 2026 | Parking Lots | PNA - repair potholes |  | GC | Capital Plan | 22000 | 6600 | 15400 |  | In Progress
Cypress Ridge | 2026 | Asphalt Milling/Paving/SealCoat | PNA - Crack fill TCAC - Asphalt seal coat and striping |  | GC | Capital Plan | 27000 | 8100 | 18900 |  | In Progress
Cypress Ridge | 2026 | Stripe parking areas | PNA - Stripe parking lot |  | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
Cypress Ridge | 2026 | ADA parking & ramps | PNA - Repair concrete on ramp |  | GC | Capital Plan | 14000 | 4200 | 9800 |  | In Progress
Cypress Ridge | 2026 | Sidewalks and curbs | PNA - Grind trip hazards |  | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
Cypress Ridge | 2026 | Site perimeter fencing | LPCA - Minor fence board damage was noted at a single location near Unit 2154. Repair of the noted issue is recommended. |  | PMC | Capital Plan | 750 | 0 | 750 |  | Not Started
Cypress Ridge | 2026 | Landscape Cleanup & Enhancements | Concept Walk - landscape cleanup and ground cover |  | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Cypress Ridge | 2026 | Dumpster enclosures | PNA - Repair enclosures |  | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
Cypress Ridge | 2026 | Termite Remediation | LPCA - Partner was provided with a WDO report by Redwood Empire Termite and Pest Control, dated January 25, 2026. The re |  | PMC | Capital Plan | 920 | 0 | 920 |  | Not Started
Cypress Ridge | 2026 | Termite damage repairs | LPCA - The WDO report also stated fungus/dryrot was observed. Partner recomments repairs. |  | GC | Capital Plan | 5000 | 1500 | 3500 |  | In Progress
Cypress Ridge | 2026 | Repair exterior stair treads and stringers | LPCA - Subsequent to site inspection activities, Partner was notified that installation of EV charging station caused cr |  | GC | Capital Plan | 5000 | 1500 | 3500 |  | In Progress
Cypress Ridge | 2026 | Expansion Joints | PNA - Expansion joints |  | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
Cypress Ridge | 2026 | Asphalt composite shingle roofing | PNA - Tune up roofs (building replacements as needed) TCAC - Asphalt shingle |  | GC | Capital Plan | 50000 | 15000 | 35000 |  | In Progress
Cypress Ridge | 2026 | Gutters & downspouts | PNA - Repair downspouts and gutters |  | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
Cypress Ridge | 2026 | Flashing | PNA - Flashing |  | GC | Capital Plan | 12000 | 3600 | 8400 |  | In Progress
Cypress Ridge | 2026 | Sealants & caulking | PNA - Seal roof cracks LPCA (PR-90) - Evidence of discoloration was noted in the upper bedroom or bathroom ceilings at U |  | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
Cypress Ridge | 2026 | Roof treatment / cleaning | LPCA - Organic growth including moss was noted on main and secondary asphalt-shingle roofs. Over time the organic materi |  | GC | Capital Plan | 18900 | 5670 | 13230 |  | In Progress
Cypress Ridge | 2026 | Stucco repairs | PNA - Patch cracked stucco LPCA - Horizontal cracking was noted at multiple facades including Units 2129, 2159, 2209, an |  | GC | Capital Plan | 40000 | 12000 | 28000 |  | In Progress
Cypress Ridge | 2026 | Exterior paint | PNA - Paint community |  | GC | Capital Plan | 227400 | 68220 | 159180 |  | In Progress
Cypress Ridge | 2026 | Repair / replace wood trim | PNA - Repair / replace wood trim |  | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
Cypress Ridge | 2026 | Electrical distribution - exterior | PNA - Repair lighting controllers |  | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
Cypress Ridge | 2026 | Partial Renovation | Seller to address: LPCA - Units 65 and 103 are considered down units due to evictions that are currently in progress. Ma |  | PMC | Capital Plan | 17000 | 0 | 17000 |  | Not Started
Cypress Ridge | 2026 | Drier vents | PNA - Drier vents |  | PMC | Capital Plan | 11590 | 0 | 11590 |  | Not Started
Cypress Ridge | 2026 | Stovetop fire suppression | PNA - Fire stops |  | PMC | Capital Plan | 11956 | 0 | 11956 |  | Not Started
Cypress Ridge | 2026 | Interior microbial growth treatment | Seller to address: LPCA (PR-90) - Water damage was observed at ceiling areas in the bathroom and bedroom of Unit 2 and t |  | PMC | Capital Plan | 3000 | 0 | 3000 |  | Not Started
Cypress Ridge | 2026 | Signage - entry | Concept Walk - replace main ID and add directional signage |  | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Cypress Ridge | 2026 | Fire system - Code Violations | LPCA (PR-90) - There are open There are open fire code violations for expired fire extinguishers at 1815 Meda Ave. At th |  | PMC | Capital Plan | 500 | 0 | 500 |  | Not Started
Cypress Ridge | 2026 | Video systems | Concept Walk - replace inoperable cameras and add in dead zones |  | PMC | Capital Plan | 15000 | 47799 | -32799 |  | Completed
Cypress Ridge | 2026 | Outdoor kitchen, fire pits, and seating area | Concept Walk - outdoor grills and seating area |  | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Cypress Ridge | 2026 | Playground area and equipment | Concept Walk - playground and fall zone |  | GC | Capital Plan | 45000 | 13500 | 31500 |  | In Progress
Cypress Ridge | 2026 | Contingency | Contingency Amount |  | GC | Contingency | 38601 | 0 | 38601 |  | Reserve
Cypress Ridge | 2026 | Construction Management Fee | CM Fees |  | GC | CM Fee | 40531 | 0 | 40531 |  | Reserve
Oslo | 2026 | Dryer Vent Cleaning | Dryer Vent Cleaning - Contingency | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Oslo | 2026 | Gutter Cleaning | Gutter Cleaning - Contingency | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Oslo | 2026 | Plumbing | Plumbing Repairs - Contingency | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Oslo | 2026 | Windows/Doors | Window/Door Repairs - Contingency | REOCCURING COMMON AREA/EXTERIOR (DEFERRED MAINTENANCE) | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Oslo | 2026 | Capital Plan |  |  | Unmarked | Capital Plan | 95000 | 119427 | -24427 |  | Completed
Oslo | 2026 | Contingency Amount | Contingency | Contingency & Fees | GC | Contingency | 4750 | 0 | 4750 |  | Reserve
Oslo | 2026 | Construction Management Fees | CM Fees | Contingency & Fees | GC | CM Fee | 4988 | 0 | 4988 |  | Reserve
San Regis | 2026 | Storm sewer piping and drains | PNA - clear parking lot drains |  | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
San Regis | 2026 | Parking lot repairs | PNA - repair potholes |  | GC | Capital Plan | 28000 | 0 | 28000 |  | Not Started
San Regis | 2026 | Asphalt seal coating | PNA - crack fill |  | GC | Capital Plan | 19000 | 0 | 19000 |  | Not Started
San Regis | 2026 | Stripe parking areas | PNA - stripe parking lot |  | GC | Capital Plan | 27000 | 0 | 27000 |  | Not Started
San Regis | 2026 | ADA parking & ramps | PNA - repair concrete on ramp |  | GC | Capital Plan | 14000 | 0 | 14000 |  | Not Started
San Regis | 2026 | Sidewalks and curbs | PNA - grind trip hazards |  | GC | Capital Plan | 14000 | 0 | 14000 |  | Not Started
San Regis | 2026 | Landscape Cleanup & Enhancements | Concept Walk - tree trim + landscape cleanup |  | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
San Regis | 2026 | Dumpster enclosures | PNA - Prevent damage to hallway to parking lot |  | GC | Capital Plan | 18000 | 0 | 18000 |  | Not Started
San Regis | 2026 | Termite Remediation | WDIR - findings from WDIR (placeholder) |  | GC | Capital Plan | 31500 | 0 | 31500 |  | Not Started
San Regis | 2026 | Repair balcony framing & decking | PNA - repair and recoat exposed walkways |  | GC | Capital Plan | 39500 | 0 | 39500 |  | Not Started
San Regis | 2026 | Expansion Joints | PNA - seal joint |  | GC | Capital Plan | 8500 | 0 | 8500 |  | Not Started
San Regis | 2026 | Modified bitumen membrane repairs / replacement | PNA - was not able to get on roofs but based on age suspect damage on all roofs and replace roof on office building |  | GC | Capital Plan | 95000 | 0 | 95000 |  | Not Started
San Regis | 2026 | Gutters & downspouts | PNA - replace crushed down spouts |  | GC | Capital Plan | 21000 | 0 | 21000 |  | Not Started
San Regis | 2026 | Flashing | PNA - flashing |  | GC | Capital Plan | 19800 | 0 | 19800 |  | Not Started
San Regis | 2026 | Sealants & caulking | PNA - sealants & caulking |  | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
San Regis | 2026 | Stucco repairs | PNA - patch stucco and paint to match |  | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
San Regis | 2026 | Interior Hallway flooring / painting | PNA - paint hallways/breezeways |  | GC | Capital Plan | 156000 | 0 | 156000 |  | Not Started
San Regis | 2026 | Exterior paint | PNA - exterior building |  | GC | Capital Plan | 646000 | 0 | 646000 |  | Not Started
San Regis | 2026 | Domestic water piping | PNA - insulate hot water lines on office roofs |  | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
San Regis | 2026 | Common area water heaters / boilers | PNA - insulate boiler lines on office roof |  | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
San Regis | 2026 | Electrical distribution - exterior | PNA - provide and install can light adapters to catwalk lighting and inspect and replace lighting controllers |  | GC | Capital Plan | 19500 | 0 | 19500 |  | Not Started
San Regis | 2026 | Breezeway and patio lights | PNA - replace breezeway and catwalk lighting to LED |  | GC | Capital Plan | 59800 | 0 | 59800 |  | Not Started
San Regis | 2026 | Interior Upgrades | 2746679.999999999 |  | PMC | Capital Plan | 425380 | 0 | 425380 |  | Not Started
San Regis | 2026 | ADA Accessibility | ADA Upgrades (responsible for 25 of 43 total required) |  | PMC | Capital Plan | 2321300 | 0 | 2321300 |  | Not Started
San Regis | 2026 | Stovetop fire suppression | PNA - fire stops |  | PMC | Capital Plan | 38220 | 0 | 38220 |  | Not Started
San Regis | 2026 | ADA Relocation Costs | ADA Relocation Costs |  | PMC | Capital Plan | 125000 | 0 | 125000 |  | Not Started
San Regis | 2026 | Clubhouse / Office remodel | Concept Walk - fix water leaks and prevent any continued deterioration in leasing office (2nd and 3rd floor) |  | GC | Capital Plan | 100000 | 0 | 100000 |  | Not Started
San Regis | 2026 | Fire suppression system | LPCA - The annual inspection and 5-year inspection tags were not current. Partner recommends obtaining current inspectio |  | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
San Regis | 2026 | Elevators | LPCA - Current operation permits were not posted in each elevator cab. Partner recommends obtaining current inspection t |  | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
San Regis | 2026 | Swimming pool resurface | PNA - resurface pool and hot tub |  | GC | Capital Plan | 58000 | 0 | 58000 |  | Not Started
San Regis | 2026 | Swimming pool deck | PNA - repair cracks and seal |  | GC | Capital Plan | 38000 | 0 | 38000 |  | Not Started
San Regis | 2026 | Swimming pool fencing / gates | PNA - fences & gates - swimming pool |  | GC | Capital Plan | 14000 | 0 | 14000 |  | Not Started
San Regis | 2026 | Pool furniture | Concept Walk - pool furniture |  | PMC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
San Regis | 2026 | Tennis / sports court | Concept Walk - sports court furniture |  | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
San Regis | 2026 | Contingency | Contingency Amount |  | GC | Contingency | 227475 | 0 | 227475 |  | Reserve
San Regis | 2026 | Construction Management Fee | CM Fee |  | GC | CM Fee | 238849 | 0 | 238849 |  | Reserve
Tribute Verdae | 2026 | Asphalt Coating | Asphalt seal coat & striping | 84204.0 | GC | Capital Plan | 46000 | 13800 | 32200 |  | In Progress
Tribute Verdae | 2026 | Stripe parking areas | Restripe parking | 84201.0 | GC | Capital Plan | 14000 | 4200 | 9800 |  | In Progress
Tribute Verdae | 2026 | Accessibility Exterior accessible route | Please refer to the accessibility report | 84221.0 | GC | Capital Plan | 132850 | 39855 | 92995 |  | In Progress
Tribute Verdae | 2026 | Accessibility Parking and route from parking | Please refer to the accessibility report | 84201.0 | GC | Capital Plan | 32000 | 9600 | 22400 |  | In Progress
Tribute Verdae | 2026 | Accessibility Exterior door approaches | Please refer to the accessibility report | 84221.0 | GC | Capital Plan | 5250 | 1575 | 3675 |  | In Progress
Tribute Verdae | 2026 | Accessibility Interior access & access to amenities | Please refer to the accessibility report | 84221.0 | GC | Capital Plan | 750 | 225 | 525 |  | In Progress
Tribute Verdae | 2026 | Accessibility Public toilets /common area toilets | Please refer to the accessibility report | 84116.0 | GC | Capital Plan | 6700 | 2010 | 4690 |  | In Progress
Tribute Verdae | 2026 | Accessibility Access to other items | Please refer to the accessibility report | 84116.0 | GC | Capital Plan | 3650 | 1095 | 2555 |  | In Progress
Tribute Verdae | 2026 | Landscape irrigation | Inspect and repair irrigation prior to installing turf | 84300.0 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Tribute Verdae | 2026 | Erosion control | The grade around a few of the apartment buildings exhibited substantial runoff erosion and/or water ponding adjacent to | 84435.0 | GC | Capital Plan | 15000 | 4500 | 10500 |  | In Progress
Tribute Verdae | 2026 | Erosion control | Additional soil and regional turf to barren areas Barren turf was observed at isolated areas throughout, typical to sid | 84435.0 | PMC | Capital Plan | 100000 | 9153 | 90847 |  | In Progress
Tribute Verdae | 2026 | Retaining walls | Add additional retaining wall between building 8 and 9 | 84434.0 | GC | Capital Plan | 75000 | 22500 | 52500 |  | In Progress
Tribute Verdae | 2026 | Swimming pool deck | Pressure wash deck | 84361.0 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Tribute Verdae | 2026 | Swimming pool fencing / gates | Repair gate closers | 84361.0 | GC | Capital Plan | 4000 | 1200 | 2800 |  | In Progress
Tribute Verdae | 2026 | Storm sewer piping and drains | Add storm drains between bulding 8 and 9 | 84385.0 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Tribute Verdae | 2026 | Playground equipment | New Playground (Find Placement) | 84195.0 | GC | Capital Plan | 65000 | 19500 | 45500 |  | In Progress
Tribute Verdae | 2026 | Radon Long-Term Testing and Remediation | Post-Closing Radon Long-Term Testing and Remediation for 21 units | 84250.0 | PMC | Capital Plan | 150000 | 0 | 150000 |  | Not Started
Tribute Verdae | 2026 | Sustainability Improvements | Reserve for post-closing sustainability due diligence review and imrovements | 84905.0 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Tribute Verdae | 2026 | Jack & underpin foundations | Inspect all building cut post tension cables and seal | 84435.0 | GC | Capital Plan | 3000 | 900 | 2100 |  | In Progress
Tribute Verdae | 2026 | Concrete deck / floor fill | Inspect route and seal concrete cracks The concrete patio in the northwest corner contained exposed and improperly term | 84430.0 | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
Tribute Verdae | 2026 | Repair balcony framing & decking | Inspect & repair wood decking on breezeways. Some of the wood-framed upper floor balconies & breezeway landings were obs | 84104.0 | GC | Capital Plan | 50000 | 15000 | 35000 |  | In Progress
Tribute Verdae | 2026 | Pressure Wash | Pressure wash 1st floor of brick to remove clay spoils | 84206.0 | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
Tribute Verdae | 2026 | Repair brick pier damage | The brick pier adjacent to garage 2202 was observed with damage, likely resulting from mechanical impact. The observed d | 84102.0 | GC | Capital Plan | 2500 | 750 | 1750 |  | In Progress
Tribute Verdae | 2026 | Repair balcony support posts | The bases at some balcony support posts are overhanging the concrete patio slab edge and not fully bearing on the concre | 84104.0 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
Tribute Verdae | 2026 | Gutters & downspouts | Inspect and repair downspouts, splash blocks | 84202.0 | GC | Capital Plan | 45000 | 13500 | 31500 |  | In Progress
Tribute Verdae | 2026 | Dog Park | Purchasing new astroturf, benches, and shade | 84130.0 | GC | Capital Plan | 75000 | 22500 | 52500 |  | In Progress
Tribute Verdae | 2026 | Sanitary Sewer Piping | At sewer scope cleanouts numbers 9 and 2 joint separations were observed. It is recommended to replace or repair the joi | 84385.0 | PMC | Capital Plan | 29500 | 4481 | 25019 |  | In Progress
Tribute Verdae | 2026 | Refrigerant linesets insulation | Partner observed that the insulation on the exterior portion of the refrigerant linesets between the condensing units an | 84217.0 | GC | Capital Plan | 6500 | 1950 | 4550 |  | In Progress
Tribute Verdae | 2026 | Construction Management Fee | CM Fee | 84505.0 | GC | CM Fee | 51635 | 0 | 51635 |  | Reserve
Walnut Square | 2026 | Landscape Cleanup and Enhancements | Tree trim and landscape cleanup | 84303.0 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Walnut Square | 2026 | Water Distribution Piping | Two different water leaks from meter boxes Allowance to repair city water main leaks at the property based on observed c | 84470.0 | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Walnut Square | 2026 | Pavement | Remove and replace pothole areas on site | 84204.0 | GC | Capital Plan | 28000 | 0 | 28000 |  | Not Started
Walnut Square | 2026 | ADA parking & curb cuts | Remove and replace damaged curbs on community | 84221.0 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Walnut Square | 2026 | Sidewalks | Grind trip hazards | 84221.0 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Walnut Square | 2026 | Fences & gates - site perimeter | Rebuild 2500 lf of wood fence, repair 2000 lf of iron fence and paint both | 84205.0 | GC | Capital Plan | 192000 | 0 | 192000 |  | Not Started
Walnut Square | 2026 | Fences & gates - swimming pool | Repair and paint | 84205.0 | GC | Capital Plan | 5600 | 0 | 5600 |  | Not Started
Walnut Square | 2026 | Playground area | Turf around playground areas | 84195.0 | GC | Capital Plan | 45000 | 0 | 45000 |  | Not Started
Walnut Square | 2026 | Dumpster enclosures | Repair and paint | 84111.0 | GC | Capital Plan | 14000 | 0 | 14000 |  | Not Started
Walnut Square | 2026 | Repair exterior stair treads and stringers | Resurface stairs to office | 84114.0 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Walnut Square | 2026 | Repair patio/balcony railings | Secure balcony railings | 84121.0 | GC | Capital Plan | 8500 | 0 | 8500 |  | Not Started
Walnut Square | 2026 | Expansion joints | Exterior Expansion Joints | 84206.0 | GC | Capital Plan | 17000 | 0 | 17000 |  | Not Started
Walnut Square | 2026 | Gutters & downspouts | Clean and repitch gutters and repair down spouts throughout property | 84202.0 | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
Walnut Square | 2026 | Flashing | Roof Flashing | 84433.0 | GC | Capital Plan | 8500 | 2550 | 5950 |  | In Progress
Walnut Square | 2026 | Sealants & caulking | Roof Sealants & caulking | 84433.0 | GC | Capital Plan | 8500 | 2550 | 5950 |  | In Progress
Walnut Square | 2026 | Repair / replace cement fiber siding | Repair or replace damaged siding siding | 84105.0 | GC | Capital Plan | 19000 | 5700 | 13300 |  | In Progress
Walnut Square | 2026 | Exterior building Painting | Paint community | 84101.0 | GC | Capital Plan | 232000 | 69600 | 162400 |  | In Progress
Walnut Square | 2026 | Repair / replace wood trim | Repair / replace wood trim | 84105.0 | GC | Capital Plan | 16000 | 4800 | 11200 |  | In Progress
Walnut Square | 2026 | Drier vents | Drier vents | 84106.0 | GC | Capital Plan | 15675 | 0 | 15675 |  | Not Started
Walnut Square | 2026 | Leasing office floor/wall finishes, Replace | Reflooring / repaint in office | 84208 | GC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Walnut Square | 2026 | Leasing office FF&E, Replace | Leasing office FF&E, Replace | 84306 | GC | Capital Plan | 50000 | 4702 | 45298 |  | In Progress
Walnut Square | 2026 | Electrical distribution | Replace lightning controllers | 84210 | GC | Capital Plan | 6000 | 7200 | -1200 |  | Completed
Walnut Square | 2026 | Common area light fixtures | Replace 6 missing pole lights Allowance to repair/replace emergency light fixtures in common areas based on expired tags | 84112 | GC | Capital Plan | 8000 | 1800 | 6200 |  | In Progress
Walnut Square | 2026 | Replace breezeway lights | Replace front door lights with mini LED wallpacks | 84112 | GC | Capital Plan | 24000 | 2400 | 21600 |  | In Progress
Walnut Square | 2026 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 44389 | 0 | 44389 |  | Reserve
Walnut Square | 2026 | Construction Management Fee | CM Fee | 84505.0 | GC | CM Fee | 46608 | 0 | 46608 |  | Reserve
Waterford | 2026 | Parking lot repairs | PNA: repair potholes. Concept Walk - Replace speed bumps as needed | 84201 | GC | Capital Plan | 38000 | 12000 | 26000 |  | In Progress
Waterford | 2026 | Asphalt seal coating | PNA: Crack Fill | 84221 | GC | Capital Plan | 29000 | 8700 | 20300 |  | In Progress
Waterford | 2026 | Curbing Repairs | PNA: Curbing Repairs | MISSING | GC | Capital Plan | 24000 | 7200 | 16800 |  | In Progress
Waterford | 2026 | Sidewalks and curbs | PNA: grind trip hazards | 84221 | GC | Capital Plan | 14000 | 4200 | 9800 |  | In Progress
Waterford | 2026 | Site perimeter fencing | Concept Walk - Stain streetside perimeter fencing. Pressure wash interior perimeter fencing to remove moss buildup. | 84205 | GC | Capital Plan | 16480 | 4944 | 11536 |  | In Progress
Waterford | 2026 | Landscape Cleanup and Enhancements | Concept Walk - Tree trim and general curb appeal enhancement; Streetside cleanup around sign | 84303 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Waterford | 2026 | Carports / Garages | PNA: Repair carports | 84219 | GC | Capital Plan | 22000 | 6600 | 15400 |  | In Progress
Waterford | 2026 | Dumpster enclosures | PNA - Repair dumpster enclosures. | 84111 | GC | Capital Plan | 18000 | 5400 | 12600 |  | In Progress
Waterford | 2026 | Concrete deck / floor fill | PNA: Repair catwalks and install new outdoor carpet | 84221 | GC | Capital Plan | 81000 | 24300 | 56700 |  | In Progress
Waterford | 2026 | Repair exterior stair treads and stringers | PNA: inspect and secure railings on cat walks | 84114 | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
Waterford | 2026 | Asphalt composite shingle roofing | PNA: roof tune up | 84433 | GC | Capital Plan | 29000 | 8700 | 20300 |  | In Progress
Waterford | 2026 | Roof treatment / cleaning | PNA: Flashing | 84433 | GC | Capital Plan | 9800 | 2940 | 6860 |  | In Progress
Waterford | 2026 | Gutters & downspouts | PNA: Clean and repatch gutters throughout property | 84202 | GC | Capital Plan | 21000 | 6300 | 14700 |  | In Progress
Waterford | 2026 | Sealants & caulking | PNA: At band boards | 84433 | GC | Capital Plan | 20000 | 6000 | 14000 |  | In Progress
Waterford | 2026 | Repair / replace siding | PNA: Replace damaged Masonite and paint to match | 84206 | GC | Capital Plan | 30000 | 9000 | 21000 |  | In Progress
Waterford | 2026 | Breezeway soffit repairs | PNA: R&R ceiling lights in breezeways with LED | 84206 | GC | Capital Plan | 33200 | 9960 | 23240 |  | In Progress
Waterford | 2026 | Repair / replace wood trim | PNA: R&R rotted wood trim and paint to match | 84206 | GC | Capital Plan | 10000 | 3000 | 7000 |  | In Progress
Waterford | 2026 | Patio yard enclosures | Concept Walk - Installation of patior fencing where applicable | 84120 | GC | Capital Plan | 3600 | 0 | 3600 |  | Not Started
Waterford | 2026 | Electrical Panel Disconnects & Meter Banks | Electrical Panel Replacements | 84330 | GC | Capital Plan | 200000 | 0 | 200000 |  | Not Started
Waterford | 2026 | Breezeway Lighting | PNA - Wiring for pole lights | 84112 | GC | Capital Plan | 30000 | 9000 | 21000 |  | In Progress
Waterford | 2026 | Common Area Lighting | PNA: replace both pole light on existing post, straiten posts and add a concrete curb, replace wall packs with LED | 84112 | GC | Capital Plan | 73000 | 21900 | 51100 |  | In Progress
Waterford | 2026 | Breezeway Lighting | R&R ceiling lights in breezeway with LED | 84112 | GC | Capital Plan | 33200 | 9960 | 23240 |  | In Progress
Waterford | 2026 | Drier vents | PNA: Remove vent covers, clean vent piping, and install new dryer vent covers | 84106.0 | GC | Capital Plan | 33000 | 9900 | 23100 |  | In Progress
Waterford | 2026 | Fire Stops | Fire Stops | 84239 | PMC | Capital Plan | 19600 | 0 | 19600 |  | Not Started
Waterford | 2026 | Clubhouse / Office redecorate (FFE) | Concept Walk - Update clubhouse furniture and fixtures | 84208 | PMC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Waterford | 2026 | Security/ fire alarm systems | Lender PCA: Valid inspection certificates were affixed to the fire sprinklers dated September 2025. While the systems we | 84211 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Waterford | 2026 | Swimming pool resurface | PNA: Outdoor pool covered assume needing resurface hot tub needs resurface Indoor pool has been painted All Four nee | 84095 | GC | Capital Plan | 135000 | 40500 | 94500 |  | In Progress
Waterford | 2026 | Swimming pool coping and tile | Lender PCA: The pool and spa were down at the time of the site visit. Management reported the pool/spa area was closed d | 84095 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Waterford | 2026 | Swimming pool deck | PNA: Repair cracks | 84095 | GC | Capital Plan | 32000 | 9600 | 22400 |  | In Progress
Waterford | 2026 | Swimming pool fencing / gates | PNA - Repair pool fence and gate. | 84205 | GC | Capital Plan | 14000 | 4200 | 9800 |  | In Progress
Waterford | 2026 | Pool furniture | Concept Walk - Add pool furniture | 84360 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Waterford | 2026 | Pergola / shade covers | PNA: Repair, paint, and pressure was outdoor kitchen area | 84113.0 | GC | Capital Plan | 26000 | 7800 | 18200 |  | In Progress
Waterford | 2026 | Tennis / sports court | Concept Walk - Resurface basketball court / replace goals | 84390 | GC | Capital Plan | 25200 | 7560 | 17640 |  | In Progress
Waterford | 2026 | Outdoor kitchen, fire pits, and seating area | PNA: Replace grill with Charcoal Grill to fit in island (8K). Concept Walk: placeholder for outdoor kitchen and shade st | 84203.0 | GC | Capital Plan | 28000 | 8400 | 19600 |  | In Progress
Waterford | 2026 | Playground area and equipment | Concept Walk - Install new playground | 84340 | GC | Capital Plan | 40000 | 12000 | 28000 |  | In Progress
Waterford | 2026 | Pet park / pet washing station | Concept Walk: placeholder for adding gravel/turf | 84130 | GC | Capital Plan | 25000 | 7500 | 17500 |  | In Progress
Waterford | 2026 | Fitness Center Remodel | Concept Walk: placeholder for fitness room/flooring paint in the lobby | 84190 | GC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Waterford | 2026 | Model Unit | Concept Walk - Update model | 84280.0 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Waterford | 2026 | Golf Carts | Concept Walk: need to purchase two new golf carts | 83375.0 | PMC | Capital Plan | 12500 | 0 | 12500 |  | Not Started
Waterford | 2026 | Shed (Storage Space) | Concept Walk: The current shop is only 8x8 and lacks adequate storage space. | 84102.0 | PMC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Waterford | 2026 | Contingency | Contingency Amount | 84510 | GC | Contingency | 66979 | 0 | 66979 |  | Reserve
Waterford | 2026 | Construction Management Fee | CM Fee | 84505 | GC | CM Fee | 70328 | 0 | 70328 |  | Reserve
Willow Lakes | 2026 | Landscape Enhancements | Tree trim, Increasing by 50K for curb appeal based on concept walk LPCA - Tree branches were observed in contact at Bui | 84303.0 | PMC | Capital Plan | 95000 | 0 | 95000 |  | Not Started
Willow Lakes | 2026 | Pool Area Repairs & Equipment | Repair pool gates | 84361.0 | GC | Capital Plan | 19000 | 9500 | 9500 |  | In Progress
Willow Lakes | 2026 | Covered Parking & Misc. Parking Items | LPCA - Impact damage was observed at the garage door at the G-30 garage. Repairs are recommended. | 84219.0 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Willow Lakes | 2026 | Asphalt Milling/Paving/Sealcoat | Stripe Parking Areas | 84204.0 | GC | Capital Plan | 22000 | 22000 | 0 |  | Completed
Willow Lakes | 2026 | Concrete Curb/Sidewalk | Repair 2000 sq ft of concrete | 84221.0 | GC | Capital Plan | 70000 | 96000 | -26000 |  | Completed
Willow Lakes | 2026 | ADA Compliance Expense | ADA landings on apartment entrances are cracking up and failing | 83520.0 | GC | Capital Plan | 36000 | 36000 | 0 |  | Completed
Willow Lakes | 2026 | Sidewalks | repair trip hazards | 84115.0 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Pool Area Repairs & Equipment | LPCA - Excessive algae growth due to an inoperable aeration pump was observed at the south portion of the pond. | 84361.0 | GC | Capital Plan | 2500 | 16000 | -13500 |  | Completed
Willow Lakes | 2026 | Erosion control | Landscaping Erosion Control | 84517.0 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Fences & gates - site perimeter | repair iron and wood fence and paint | 84205.0 | GC | Capital Plan | 56000 | 66000 | -10000 |  | Completed
Willow Lakes | 2026 | Pool Area Repairs & Equipment | deck o seal | 84361.0 | GC | Capital Plan | 9500 | 0 | 9500 |  | Not Started
Willow Lakes | 2026 | Pool Area Repairs & Equipment | seal small cracks on pool deck and clean | 84361.0 | GC | Capital Plan | 16000 | 0 | 16000 |  | Not Started
Willow Lakes | 2026 | Fences & gates | Pedestrian and Front Gate Improvements | 84205.0 | GC | Capital Plan | 10000 | 19000 | -9000 |  | Completed
Willow Lakes | 2026 | Exterior Kitchen | replace grills | 84203.0 | GC | Capital Plan | 9500 | 9500 | 0 |  | Completed
Willow Lakes | 2026 | Dumpster enclosures | Build an enclosed area around roll off trash set up | 84111.0 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Willow Lakes | 2026 | Common Corridors Rehab | Grind and seal cracks in breezeways An isolated area of sectional cracking was noted on the main entrance drive and area | 84120.0 | GC | Capital Plan | 26000 | 0 | 26000 |  | Not Started
Willow Lakes | 2026 | Exterior Stairs | Repair exterior stair treads and stringers - Replace 90 stair treads | 84114.0 | GC | Capital Plan | 12500 | 12500 | 0 |  | Completed
Willow Lakes | 2026 | Handrail / Railings | Repair Exterior Railings | 84121.0 | GC | Capital Plan | 8500 | 8500 | 0 |  | Completed
Willow Lakes | 2026 | Balconies | Repair Balcony Decks | 84104.0 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Roof Replacements/Repairs | Roof tune up - Asphalt composite shingle roofing | 84433.0 | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Willow Lakes | 2026 | Roof/Gutters | Clean gutters and downspouts | 84202.0 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Willow Lakes | 2026 | Building - Exterior | replace siding that was caulked and painted over | 84206.0 | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Willow Lakes | 2026 | Building Repairs | Masonry Repairs - Repair areas of damaged stone | 84102.0 | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
Willow Lakes | 2026 | Dryer Vents | Annual Dryer Vent Cleaning | 84106.0 | GC | Capital Plan | 20460 | 20460 | 0 |  | Completed
Willow Lakes | 2026 | Exterior Paint, Carpentry, & Misc. Repairs | Repair / replace wood trim - replace rotted wood | 84113.0 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Equipment, baracades and staging | Equipment & Staging (Details of Scope?) | 84305.0 | GC | Capital Plan | 10000 | 10000 | 0 |  | Completed
Willow Lakes | 2026 | Fire Life Safety Work | Fire stops | 84239.0 | PMC | Capital Plan | 36456 | 0 | 36456 |  | Not Started
Willow Lakes | 2026 | Smoke Alarms | Completed by Seller - Move to Contingency? | 83236.0 | PMC | Capital Plan | 18600 | 0 | 18600 |  | Not Started
Willow Lakes | 2026 | Monument Sign | Enhance Signage (cordinate w/ church - add signage on their property) | 84290.0 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Willow Lakes | 2026 | Club House/Leasing Center Addition/Alteration | Leasing office floor/wall finishes - Light leasing office upgrade | 84116.0 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Willow Lakes | 2026 | Fitness Center | Moderate upgrades to the fitness center | 84190.0 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Willow Lakes | 2026 | Pool Area Remodel | Refresh area with color and furniture. Split between the two pools | 84360.0 | PMC | Capital Plan | 60000 | 49907 | 10093 |  | In Progress
Willow Lakes | 2026 | Dog Run | Add lighting, dog amenities, and repairs to fencing | 84130.0 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Willow Lakes | 2026 | Golf Cart | Add leasing cart | 83375.0 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Willow Lakes | 2026 | Stormwater Piping | Clean out basin | 84432.0 | GC | Capital Plan | 14000 | 14000 | 0 |  | Completed
Willow Lakes | 2026 | Replace AC condenser | align condensers and insulate suction lines | 84218.0 | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Willow Lakes | 2026 | Electrical/Lighting | Electrical distribution - repair lighting controlers | 84210.0 | GC | Capital Plan | 21000 | 21000 | 0 |  | Completed
Willow Lakes | 2026 | Exterior Lighting | Common area light fixtures - wall packs and pole light throughout | 84112.0 | GC | Capital Plan | 39000 | 39000 | 0 |  | Completed
Willow Lakes | 2026 | Exterior Lighting | Replace breezeway lights - wall sconce, ceiling and garage lights | 84112.0 | GC | Capital Plan | 59500 | 59500 | 0 |  | Completed
Willow Lakes | 2026 | Contingency | Contingency Amount | 84510.0 | GC | Contingency | 51163 | 0 | 51163 |  | Reserve
Willow Lakes | 2026 | Other CM Fees | Construction Management Fee Amount | 84505.0 | GC | CM Fee | 54509 | 0 | 54509 |  | Reserve
Colonnade | 2026 | Interior Hallway painting | Interior hallway repaint | 51160-00 | GC | Capital Plan | 158900 | 158900 | 0 |  | Completed
Colonnade | 2026 | Controlled access gates | Add controlled access to main entry, fitness center, pool, & any other main entry point | 51993-00 | GC | Capital Plan | 100000 | 100000 | 0 |  | Completed
Colonnade | 2026 | Trellis Repairs | Deteriorated beam framing at the wood beam framed trellis structure was noted. Repair is recommended. | 51070-00 | PMC | Capital Plan | 2500 | 0 | 2500 |  | Not Started
Colonnade | 2026 | Equipment, Baracades, & Staging | Baracades & Staging | 51180-00 | GC | Capital Plan | 45000 | 45000 | 0 |  | Completed
Colonnade | 2026 | Repair exterior stair railings | Paint interior stairwells and iron | 51077-00 | GC | Capital Plan | 38000 | 38000 | 0 |  | Completed
Colonnade | 2026 | Façade repairs | Stucco deterioration was noted on the northern upper facade locations and organic build-up was noted. Repairs are recomm | 51075-00 | GC | Capital Plan | 5000 | 5000 | 0 |  | Completed
Colonnade | 2026 | Full Property Repaint | Full property repaint | 51080-00 | GC | Capital Plan | 663000 | 663000 | 0 |  | Completed
Colonnade | 2026 | Gutters & downspouts | Clean scuppers and roof drains | 51071-00 | GC | Capital Plan | 24000 | 24000 | 0 |  | Completed
Colonnade | 2026 | Sealants & caulking | Roof Sealants & Caulking | 51062-00 | GC | Capital Plan | 25300 | 25300 | 0 |  | Completed
Colonnade | 2026 | Elevator Cabs | Full repairs of 3 elevator interiors. Wood panels, flooring, stainless doors | 51160-00 | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
Colonnade | 2026 | Fire Stops | Add fire stops to 50% of units missing | 51993-01 | PMC | Capital Plan | 10829 | 0 | 10829 |  | Not Started
Colonnade | 2026 | Fitness center renovation | Full redeck of flooring and full repaint | 51160-00 | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
Colonnade | 2026 | Stab-Lok Panels | Stab-Lok brand breaker panels manufactured by Federal Pacific Electric (FPE) were observed in the units. These panels ha | 51142-00 | GC | Capital Plan | 123200 | 123200 | 0 |  | Completed
Colonnade | 2026 | Security/ fire alarm systems | An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recertification of | 51993-00 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Colonnade | 2026 | Fire Sprinkler Certificaiton | The systems display lapsed certification. Recertification is required | 51993-01 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Colonnade | 2026 | Fire extinguisher certification | The extinguishers displayed lapsed certification. Recertification is required. | 51993-01 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Colonnade | 2026 | Elevator Inspection | A current cab certification permit was not provided and load test information was not displayed. Property management sho | 51993-01 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Colonnade | 2026 | Fountain Repairs | The water feature is reportedly leaking into the garage area and are not presently in use. Repair is recommended. | 51160-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Colonnade | 2026 | Startup Marketing | Rebrand of property signage | 51990-00 | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Colonnade | 2026 | Pest Control | Rat droppings were observed at the emergency generator room. Engaging a pest contractor and treatment for pest control o | 51992-00 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Colonnade | 2026 | Swimming pool coping and tile | Resurface pool ( pool is on 4th floor and will required extreme labor cost ) | 51021-00 | GC | Capital Plan | 50000 | 50000 | 0 |  | Completed
Colonnade | 2026 | Swimming pool deck | Seal small cracks on pool deck and clean | 51022-00 | GC | Capital Plan | 16000 | 16000 | 0 |  | Completed
Colonnade | 2026 | Pool furniture | Furniture Upgrades | 51011-00 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Colonnade | 2026 | Pergola / shade covers | Repair and recoat pergola | 51070-00 | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
Colonnade | 2026 | Outdoor kitchen, fire pits, and seating area | Kitchen and outdoor cooking area upgrades | 51160-04 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Colonnade | 2026 | Steam Sauna & Bathroom | FF&E facelift and upgrade | 51160-00 | PMC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Colonnade | 2026 | Fitness equipment | 7 pieces of new equipments | 51028-00 | PMC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Colonnade | 2026 | Contingency | Contingency Amount | 51175-00 | GC | Contingency | 78861 | 78861 | 0 |  | Reserve
Colonnade | 2026 | Construction Management Fee | CM Fee | 51190-00 | GC | CM Fee | 82805 | 82805 | 0 |  | Reserve
The Retreat | 2022 | Parking equipment | add 15 speed bumps | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
The Retreat | 2022 | Sidewalks | repair cracked concrete | 0200 - Site Utilities & Improvements | GC | Capital Plan | 20000 | 20000 | 0 |  | Completed
The Retreat | 2022 | Landscape irrigation | inspect and repair irrigation | 0200 - Site Utilities & Improvements | GC | Capital Plan | 26000 | 26000 | 0 |  | Completed
The Retreat | 2022 | Patio fencing | 20 Extended Dog yards @ $5k- Value add | 0200 - Site Utilities & Improvements | GC | Capital Plan | 100000 | 100000 | 0 |  | Completed
The Retreat | 2022 | Landscaping | New palms, bare land, dead bushes, etc.. | 0200 - Site Utilities & Improvements | GC | Capital Plan | 25000 | 25000 | 0 |  | Completed
The Retreat | 2022 | Fences & gates - swimming pool | Replace entire dog park fence | 0200 - Site Utilities & Improvements | GC | Capital Plan | 35000 | 35000 | 0 |  | Completed
The Retreat | 2022 | Pickleball court | Install pickleball court behind clubhouse | 0200 - Site Utilities & Improvements | GC | Capital Plan | 40000 | 40000 | 0 |  | Completed
The Retreat | 2022 | Playground equipment | New Playground | 0200 - Site Utilities & Improvements | GC | Capital Plan | 30000 | 30000 | 0 |  | Completed
The Retreat | 2022 | Dumpster enclosures | Repair Dumpsters and paint | 0200 - Site Utilities & Improvements | GC | Capital Plan | 6000 | 6000 | 0 |  | Completed
The Retreat | 2022 | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | 0700 - Roofing | GC | Capital Plan | 16500 | 16500 | 0 |  | Completed
The Retreat | 2022 | Dryer Vents | Clean all dryer vents | 0800 - Exterior Wall | GC | Capital Plan | 11340 | 11340 | 0 |  | Completed
The Retreat | 2022 | Appliances Package |  | 0900 - FF&E in Units | PMC | Capital Plan | 486000 | 0 | 486000 |  | Not Started
The Retreat | 2022 | Ceramic tile | 324 Backsplash @ $700 | 0900 - FF&E in Units | PMC | Capital Plan | 226800 | 0 | 226800 |  | Not Started
The Retreat | 2022 | Range Queen |  | 0900 - FF&E in Units | PMC | Capital Plan | 29160 | 0 | 29160 |  | Not Started
The Retreat | 2022 | Unit Model Update | New furniture in model unit | 0900 - FF&E in Units | PMC | Capital Plan | 13000 | 0 | 13000 |  | Not Started
The Retreat | 2022 | Signage - site |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 25000 | 3739 | 21261 |  | In Progress
The Retreat | 2022 | Clubhouse / Office Remodel | Wall and glass door between game/movie rooms | 1100- Specialties, Equipment & Furnishings | GC | Capital Plan | 6500 | 6500 | 0 |  | Completed
The Retreat | 2022 | Video Systems | Movie Room refresh | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
The Retreat | 2022 | Clubhouse / Office Redecorate (FFE) | Clubhouse furniture- quote #PS6143285 from Charter Furniture | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 92000 | 46776 | 45224 |  | In Progress
The Retreat | 2022 | Tech Package per unit | 162 units x $700 | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 113400 | 0 | 113400 |  | Not Started
The Retreat | 2022 | Audio systems | Audio systems - Game Room | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
The Retreat | 2022 | Pool furniture | Update pool furniture to include cabanas | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 40000 | 37994 | 2006 |  | In Progress
The Retreat | 2022 | Golf Cart |  | 1100- Specialties, Equipment & Furnishings | PMC | Capital Plan | 14000 | 24807 | -10807 |  | Completed
The Retreat | 2022 | Replace Fire Alarm Panel |  | 1600 - Electrical | GC | Capital Plan | 1500 | 1500 | 0 |  | Completed
Anthem Clearwater | 2026 | Exterior paint | Exterior paint | 84101 | GC | Capital Plan | 624000 | 0 | 624000 |  | Not Started
Anthem Clearwater | 2026 | Repair exterior stair treads and stringers | Repair exterior stair treads and stringers | 84114 | GC | Capital Plan | 520183 | 0 | 520183 |  | Not Started
Anthem Clearwater | 2026 | Modified bitumen membrane repairs / replacement | Modified bitumen membrane repairs / replacement | 84433 | GC | Capital Plan | 324000 | 0 | 324000 |  | Not Started
Anthem Clearwater | 2026 | Asphalt seal coating | Asphalt seal coating | 84201 | GC | Capital Plan | 272450 | 0 | 272450 |  | Not Started
Anthem Clearwater | 2026 | Swimming pool resurface | Swimming pool resurface | 84095 | GC | Capital Plan | 130000 | 0 | 130000 |  | Not Started
Anthem Clearwater | 2026 | Repair / replace wood trim | Repair / replace wood trim | 84206 | GC | Capital Plan | 126000 | 0 | 126000 |  | Not Started
Anthem Clearwater | 2026 | Repair exterior stair railings | Repair exterior stair railings | 84114 | GC | Capital Plan | 102520 | 0 | 102520 |  | Not Started
Anthem Clearwater | 2026 | Landscape Cleanup & Enhancements | Landscape Cleanup & Enhancements | 84303 | GC | Capital Plan | 82500 | 0 | 82500 |  | Not Started
Anthem Clearwater | 2026 | Pool furniture | Pool furniture | 84360 | PMC | Capital Plan | 55000 | 0 | 55000 |  | Not Started
Anthem Clearwater | 2026 | Gutters & downspouts | Gutters & downspouts | 84433 | GC | Capital Plan | 50220 | 0 | 50220 |  | Not Started
Anthem Clearwater | 2026 | Pole lighting | Pole lighting | 84112 | GC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Anthem Clearwater | 2026 | Landscape irrigation | Landscape irrigation | 84303 | GC | Capital Plan | 45000 | 0 | 45000 |  | Not Started
Anthem Clearwater | 2026 | Parking lot repairs | Parking lot repairs | 84201 | GC | Capital Plan | 42000 | 0 | 42000 |  | Not Started
Anthem Clearwater | 2026 | Fire suppression system | Fire suppression system | 84211 | PMC | Capital Plan | 40768 | 0 | 40768 |  | Not Started
Anthem Clearwater | 2026 | HVAC pipe insulation | HVAC pipe insulation | 84220 | GC | Capital Plan | 35360 | 0 | 35360 |  | Not Started
Anthem Clearwater | 2026 | HVAC replacement - exterior | HVAC replacement - exterior | 84220 | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Anthem Clearwater | 2026 | Clubhouse / Office remodel | Clubhouse / Office remodel | 84208 | GC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Anthem Clearwater | 2026 | Model Unit | Model Unit | 84280 | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Anthem Clearwater | 2026 | Swimming pool deck | Swimming pool deck | 84095 | GC | Capital Plan | 34562 | 0 | 34562 |  | Not Started
Anthem Clearwater | 2026 | Playground area and equipment | Playground area and equipment | 84340 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Anthem Clearwater | 2026 | Unit Smoke/Fire Detectors | Unit Smoke/Fire Detectors | 84211 | PMC | Capital Plan | 29550 | 0 | 29550 |  | Not Started
Anthem Clearwater | 2026 | Wall pack lighting | Wall pack lighting | 84112 | GC | Capital Plan | 28800 | 0 | 28800 |  | Not Started
Anthem Clearwater | 2026 | Stucco repairs | Stucco repairs | 84206 | GC | Capital Plan | 28500 | 0 | 28500 |  | Not Started
Anthem Clearwater | 2026 | Pet park / pet washing station | Pet park / pet washing station | 84130 | GC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Anthem Clearwater | 2026 | Stripe parking areas | Stripe parking areas | 84201 | GC | Capital Plan | 24100 | 0 | 24100 |  | Not Started
Anthem Clearwater | 2026 | Storm sewer piping and drains | Storm sewer piping and drains | 84432 | GC | Capital Plan | 24000 | 0 | 24000 |  | Not Started
Anthem Clearwater | 2026 | Asphalt composite shingle roofing | Asphalt composite shingle roofing | 84433 | GC | Capital Plan | 23200 | 0 | 23200 |  | Not Started
Anthem Clearwater | 2026 | Tree Trimming | Tree Trimming | 83307 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Anthem Clearwater | 2026 | Irrigaton well | Irrigaton well | 84385 | GC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Anthem Clearwater | 2026 | Outdoor kitchen, fire pits, and seating area | Outdoor kitchen, fire pits, and seating area | 84203 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Anthem Clearwater | 2026 | Fitness Center Remodel | Fitness Center Remodel | 84190 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Anthem Clearwater | 2026 | Interior Hallway flooring / painting | Interior Hallway flooring / painting | 84119 | GC | Capital Plan | 18720 | 0 | 18720 |  | Not Started
Anthem Clearwater | 2026 | Pipe jacks / exterior vents | Pipe jacks / exterior vents | 84433 | GC | Capital Plan | 17500 | 0 | 17500 |  | Not Started
Anthem Clearwater | 2026 | Pressure wash | Pressure wash | 84206 | GC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Anthem Clearwater | 2026 | Misc. Common Area Amenities | Misc. Common Area Amenities | 84195 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Anthem Clearwater | 2026 | Replace unit entry doors - exterior | Replace unit entry doors - exterior | 84215 | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Anthem Clearwater | 2026 | Site perimeter fencing | Site perimeter fencing | 84205 | GC | Capital Plan | 11560 | 0 | 11560 |  | Not Started
Anthem Clearwater | 2026 | Flashing | Flashing | 84433 | GC | Capital Plan | 10692 | 0 | 10692 |  | Not Started
Anthem Clearwater | 2026 | Sealants & caulking | Sealants & caulking | 84433 | GC | Capital Plan | 3850 | 0 | 3850 |  | Not Started
Anthem Clearwater | 2026 | Sidewalks and curbs | Sidewalks and curbs | 84221 | GC | Capital Plan | 3500 | 0 | 3500 |  | Not Started
Anthem Clearwater | 2026 | Test Fire Hydrants | Test Fire Hydrants | 84211 | PMC | Capital Plan | 1000 | 0 | 1000 |  | Not Started
Anthem Clearwater | 2026 | Fire Emergency Lights | Fire Emergency Lights | 84211 | PMC | Capital Plan | 250 | 0 | 250 |  | Not Started
Anthem Clearwater | 2026 | Contingency | Contingency | 84510 | GC | Contingency | 386303 | 0 | 386303 |  | Reserve
Anthem Clearwater | 2026 | Construction Management Fee | Construction Management Fee | 84505 | GC | CM Fee | 171404 | 0 | 171404 |  | Reserve
Forest View | 2026 | Exterior paint | PNA: Exterior Paint (property painted in 2024 Scheduled for Year3. Scrape / Paint Railing Year one) | 84101 | PMC | Capital Plan | 140400 | 0 | 140400 |  | Not Started
Forest View | 2026 | Swimming pool resurface | PNA: Resurface two pools & Spa (min 30% quartz) | 84095 | GC | Capital Plan | 130000 | 0 | 130000 |  | Not Started
Forest View | 2026 | Patio Fence Enclosure | Concept Walk: Placeholder (enclose patios with screen) | 84430 | GC | Capital Plan | 124800 | 0 | 124800 |  | Not Started
Forest View | 2026 | Tree Trimming | PNA: Tree Trimming / Cut back foilage throughout including Palms and Volleyball Court | 83307 | GC | Capital Plan | 100000 | 0 | 100000 |  | Not Started
Forest View | 2026 | Pool furniture | Concept Walk: 45K for Main Pool Upgrades (Furniture), 50K for Second Pool / Second Clubhouse Area Improvements | 84360 | PMC | Capital Plan | 95000 | 0 | 95000 |  | Not Started
Forest View | 2026 | Clubhouse / Office redecorate (FFE) | Concept Walk: $20K for furniture, $10K for updating the lighting, $10K for Movie Theatre improvements in the Clubhouse. | 84208 | PMC | Capital Plan | 68000 | 0 | 68000 |  | Not Started
Forest View | 2026 | Unit Water Heaters | PNA: Currently condensors are located within the minimum 3' from existing meter banks. Unknown if code enforcement will | 82209 | PMC | Capital Plan | 62500 | 0 | 62500 |  | Not Started
Forest View | 2026 | Swimming pool deck | PNA: Pressure Wash Main Pool Deck / Seal -Remove / Replace 2nd pool deck (appx.1500sf ) | 84095 | GC | Capital Plan | 60000 | 0 | 60000 |  | Not Started
Forest View | 2026 | Asphalt composite shingle roofing | PNA: Roof Tune Up Le | 84433 | GC | Capital Plan | 52000 | 0 | 52000 |  | Not Started
Forest View | 2026 | Down units (Units 1524 and 1534) - Fire Damage | Lender PCA: Two of the units were down due to fire damage (Units 1524 and 1534). Ms. Santos reported a fire occurred at | 84304 | PMC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Forest View | 2026 | Outdoor kitchen, fire pits, and seating area | PNA: Replace two grills / Install 2 Grills and Coutnertops at main pool / Add 50 LF 10 fencing w/ Logo at Rear of Volley | 84203 | GC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Forest View | 2026 | Parking lot repairs | PNA: Patch Asphalt Paving & Crackfill (appx. 3500 SF) | 84201 | GC | Capital Plan | 49000 | 0 | 49000 |  | Not Started
Forest View | 2026 | Pressure wash | PNA: Pressure Wash Buildings | 84206 | PMC | Capital Plan | 46800 | 0 | 46800 |  | Not Started
Forest View | 2026 | HVAC replacement - exterior | PNA: Clean Condensate Lines at 2nd / 3rd Floors | 84220 | GC | Capital Plan | 41600 | 0 | 41600 |  | Not Started
Forest View | 2026 | Gutters & downspouts | PNA: Repair / Clean Gutters Lender PCA: | 84433 | GC | Capital Plan | 39000 | 0 | 39000 |  | Not Started
Forest View | 2026 | Repair / replace siding | PNA: Remove / Replace Damaged Siding - Paint to match | 84206 | GC | Capital Plan | 39000 | 0 | 39000 |  | Not Started
Forest View | 2026 | Repair / replace wood trim | PNA: Trim Repair / Paint to Match Lender P | 84206 | GC | Capital Plan | 39000 | 0 | 39000 |  | Not Started
Forest View | 2026 | Drier vents | PNA: Clean Drier Vents | 83106 | GC | Capital Plan | 39000 | 0 | 39000 |  | Not Started
Forest View | 2026 | Stovetop fire suppression | PNA: Install Range Queens | 84211 | PMC | Capital Plan | 35880 | 0 | 35880 |  | Not Started
Forest View | 2026 | Landscape Cleanup & Enhancements | PNA: Clean up landscape | 84303 | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Forest View | 2026 | Termite Remediation | Concept Walk: WDIR Placeholder (Lexi requesting Quote - 5/18) | 83301 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Forest View | 2026 | Signage - building identification | Concept Walk: 25K for Building Signage | 84103 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Forest View | 2026 | Down units (Units 611,) - Current Suspect Microbial Gro | Lender PCA: Three of the units were down due to current suspect microbial growth (Units 611, 813, and 1221). The units w | 84304 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Forest View | 2026 | Down Unit 621 - Current Suspect Microbial Growth | Lender PCA: Unit 621 is down due to current suspect microbial growth. According to property management, the unit was dow | 84304 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Forest View | 2026 | Misc. Common Area Amenities | Concept Walk: 20K for the 4x4 unit that is off the rent roll in the clubhouse area, 5K for Exterior Amenity Improvements | 84195 | PMC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Forest View | 2026 | Wall pack lighting | PNA: Additional Wall Pack Lighting | 84112 | GC | Capital Plan | 17500 | 0 | 17500 |  | Not Started
Forest View | 2026 | Pet park / pet washing station | PNA: Clean Up Dog Park / Add Benches - (Foilage captured in tree trim budget) | 84130 | GC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Forest View | 2026 | Fitness Center Remodel | Concept Walk: $5K for Cardio Gym Improvement. $7.5K for Main Gym Upgrades | 84190 | PMC | Capital Plan | 12500 | 0 | 12500 |  | Not Started
Forest View | 2026 | Controlled access gates | PNA: Allowance for Access Gate Repair | 84275 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Forest View | 2026 | Pole lighting | PNA: Add Pole Light at Volley Ball Court / Repair Signage Lighting | 84112 | GC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Forest View | 2026 | Model Unit | Concept Walk: 10K for Model Refresh | 84280 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Forest View | 2026 | Fire monitoring system | Lender PCA: Per the February 16, 2026 Fire Inspection Report, there are numerous open fire code violations for fire alar | 84211 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Forest View | 2026 | Security alarm systems | Concept Walk: $10K placeholder budget to finish Ambient lock integration project (Currently 75% linked with Ambient for | 84275 | PMC | Capital Plan | 10000 | 0 | 10000 |  | Not Started
Forest View | 2026 | Clubhouse / Office remodel | PNA: Clean / Paint Front & Rear Decking | 84208 | GC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Forest View | 2026 | Tennis / sports court | PNA: Clean Repaint Two Basketball Courts | 84390 | GC | Capital Plan | 7000 | 0 | 7000 |  | Not Started
Forest View | 2026 | Flashing | PNA: Flashing | 84433 | GC | Capital Plan | 6500 | 0 | 6500 |  | Not Started
Forest View | 2026 | Pipe jacks / exterior vents | PNA: Replace / Boot jacks & Vents as required | 84433 | GC | Capital Plan | 6500 | 0 | 6500 |  | Not Started
Forest View | 2026 | Swimming pool coping and tile | PNA: Replace missing Tile on Pool 2 | 84095 | GC | Capital Plan | 5500 | 0 | 5500 |  | Not Started
Forest View | 2026 | Sealants & caulking | PNA: Sealants / Caulking | 84433 | GC | Capital Plan | 5200 | 0 | 5200 |  | Not Started
Forest View | 2026 | Flooring | Lender PCA: The living room subfloor in Down Unit 621 was observed to be flexible. According to property management, the | 84207 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Forest View | 2026 | Swimming pool fencing / gates | PNA: Repair Pool / Gate Fencing | 84095 | GC | Capital Plan | 4500 | 0 | 4500 |  | Not Started
Forest View | 2026 | Repair exterior stair treads and stringers | PNA: Remove / Replace Concerete Step Treads Lender PCA: A broken concrete step was observed at the exterior stairway of | 84114 | GC | Capital Plan | 3600 | 0 | 3600 |  | Not Started
Forest View | 2026 | Sidewalks and curbs | PNA: Repair Damaged / Broken Curbing Lender PCA: Linear cracking w | 84221 | GC | Capital Plan | 2500 | 0 | 2500 |  | Not Started
Forest View | 2026 | Swimming pool pumps repair / replace | Lender PCA: The south pool was reported and observed to be in a down condition. The pool water was observed to be murky | 84095 | PMC | Capital Plan | 2500 | 0 | 2500 |  | Not Started
Forest View | 2026 | Fire suppression system | Lender PCA: Expired certification tags present at the fire extinguishers in north clubhouse. Re-certification of the fir | 84211 | PMC | Capital Plan | 2000 | 0 | 2000 |  | Not Started
Forest View | 2026 | Water distribution piping | Lender PCA: A leaking water meter was observed at Building 7. Repair of the noted issue is recommended. | 84470 | PMC | Capital Plan | 1500 | 0 | 1500 |  | Not Started
Forest View | 2026 | Playground area and equipment | PNA: Pressure Wash Basketball Court | 84340 | GC | Capital Plan | 500 | 0 | 500 |  | Not Started
Forest View | 2026 | ADA parking & ramps | Lender PCA: ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at t | 84201 | PMC | Capital Plan | 300 | 0 | 300 |  | Not Started
Forest View | 2026 | Construction Management Fee | CM Fee | 85305 | GC | CM Fee | 82823 | 0 | 82823 |  | Reserve
Forest View | 2026 | Contingency | Contingency Amount | 84510 | GC | Contingency | 78879 | 0 | 78879 |  | Reserve
Almaden Terrace | 2026 | Seismic Retrofitting | Retrofit tuck under parking | 51070-00 | GC | Capital Plan | 1235000 | 0 | 1235000 |  | Not Started
Almaden Terrace | 2026 | Repair / replace siding | Replace siding with Hardie Areas of siding displaying deterioration were noted including but not limited to the southern | 51075-00 | GC | Capital Plan | 865000 | 0 | 865000 |  | Not Started
Almaden Terrace | 2026 | Exterior paint | The paint finish on the apartment buildings was chipping and worn. Survey and as needed reapplication of exterior paint | 51080-00 | GC | Capital Plan | 366000 | 0 | 366000 |  | Not Started
Almaden Terrace | 2026 | Gutters & downspouts | Replace gutters and downspouts on 30 buildings (830LF per building Avg.) | 51071-00 | GC | Capital Plan | 298800 | 0 | 298800 |  | Not Started
Almaden Terrace | 2026 | Electrical distribution - exterior | During site reconnaissance, the maintenance manager reported that combinations of copper and aluminum electrical wiring | 51140-00 | GC | Capital Plan | 262000 | 0 | 262000 |  | Not Started
Almaden Terrace | 2026 | Repair / replace wood trim | Replace wood trim | 51070-00 | GC | Capital Plan | 151960 | 0 | 151960 |  | Not Started
Almaden Terrace | 2026 | Hardware package | Add ceiling fans/lights to bathrooms to prevent mold issues | 51150-00 | GC | Capital Plan | 137400 | 0 | 137400 |  | Not Started
Almaden Terrace | 2026 | Repair balcony framing & decking | According to a review of municipal information, it appears that the SB721 Inspection was completed in 2024. A copy of th | 51072-00 | GC | Capital Plan | 116058 | 0 | 116058 |  | Not Started
Almaden Terrace | 2026 | Termite Remediation | Placeholder for full quote from Terminex | 51992-00 | GC | Capital Plan | 90000 | 0 | 90000 |  | Not Started
Almaden Terrace | 2026 | Playground area and equipment | Playground and BBQ upgrades | 51029-00 | GC | Capital Plan | 55000 | 0 | 55000 |  | Not Started
Almaden Terrace | 2026 | Swimming pool resurface | Resurface pool & hottub | 51023-00 | GC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Almaden Terrace | 2026 | Wall pack lighting | Replace random flood lighting with high lumin LED | 51141-00 | GC | Capital Plan | 49800 | 0 | 49800 |  | Not Started
Almaden Terrace | 2026 | Tile roofing | Tile roof repairs | 51062-00 | GC | Capital Plan | 45000 | 0 | 45000 |  | Not Started
Almaden Terrace | 2026 | Wall framing | Rplace structural damage | 51159-00 | GC | Capital Plan | 33000 | 0 | 33000 |  | Not Started
Almaden Terrace | 2026 | Sanitary sewer piping | Jet the sewer lines | 51130-00 | GC | Capital Plan | 27200 | 0 | 27200 |  | Not Started
Almaden Terrace | 2026 | Breezeway and patio lights | Replace CFL front door lights with LED | 51141-00 | GC | Capital Plan | 26200 | 0 | 26200 |  | Not Started
Almaden Terrace | 2026 | Sidewalks and curbs | Repair trip hazards Potential trip hazards consisting of vertical and horizontal separation were present throughout the | 51091-00 | GC | Capital Plan | 21000 | 0 | 21000 |  | Not Started
Almaden Terrace | 2026 | Pole lighting | Replace pole lights with LED | 51141-00 | GC | Capital Plan | 19600 | 0 | 19600 |  | Not Started
Almaden Terrace | 2026 | Repair patio/balcony railings/fences | Repairs to patio and balcony fencing | 51077-00 | GC | Capital Plan | 19000 | 0 | 19000 |  | Not Started
Almaden Terrace | 2026 | Carports / Garages | Repair & paint carports Impact damaged roof panels were noted north of building R. Repairs are recommended | 51172-00 | GC | Capital Plan | 18500 | 0 | 18500 |  | Not Started
Almaden Terrace | 2026 | Expansion Joints | Seal Landing expansion joins | 51090-00 | GC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Almaden Terrace | 2026 | Pipe jacks / exterior vents | Replace and seal damaged | 51062-00 | GC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Almaden Terrace | 2026 | Concrete deck / floor fill | Route and seal landings | 51090-00 | GC | Capital Plan | 14500 | 0 | 14500 |  | Not Started
Almaden Terrace | 2026 | Dumpster enclosures | Tuck Point and Paint | 51163-00 | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Almaden Terrace | 2026 | Flashing | Replace missing or damaged flashing | 51062-00 | GC | Capital Plan | 12000 | 0 | 12000 |  | Not Started
Almaden Terrace | 2026 | Sealants & caulking |  | 51062-00 | GC | Capital Plan | 9000 | 0 | 9000 |  | Not Started
Almaden Terrace | 2026 | Swimming pool coping and tile | Replace deck-o-seal | 51021-00 | GC | Capital Plan | 8500 | 0 | 8500 |  | Not Started
Almaden Terrace | 2026 | Swimming pool fencing / gates | Repair pool gates | 51076-00 | GC | Capital Plan | 7600 | 0 | 7600 |  | Not Started
Almaden Terrace | 2026 | Parking lot repairs | Damaged asphalt pavement consisting of pocketed map cracking was observed west of buildings U and V and north of buildin | 51050-00 | GC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Almaden Terrace | 2026 | ADA parking & ramps | Repair ADA Ramps (2) | 51091-00 | GC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Almaden Terrace | 2026 | Domestic water piping | During site reconnaissance, management disclosed a variety of plumbing problems relating to sewer and supply piping. Whi | 51130-00 | GC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Almaden Terrace | 2026 | Lighing controller system | Inspect & Replace | 51140-00 | GC | Capital Plan | 6800 | 0 | 6800 |  | Not Started
Almaden Terrace | 2026 | Storm sewer piping and drains | Clear yard drains | 51130-00 | GC | Capital Plan | 6500 | 0 | 6500 |  | Not Started
Almaden Terrace | 2026 | Landscape Cleanup & Enhancements | Volunteer tree landscaping was noted in close proximity to buildings within patio enclosures. Locations included but wer | 51045-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Almaden Terrace | 2026 | Patio Fence Enclosure | Settlement and impact damage was noted at various patio enclosures throughout the site. Repairs are recommended. | 51076-00 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Almaden Terrace | 2026 | Storage room doors | Replace 10 storage doors | 51073-00 | GC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Almaden Terrace | 2026 | Tools | Various Tools for Maintenance Workshop | 51995-00 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Almaden Terrace | 2026 | Swimming pool pumps repair / replace | Add vacume release device | 51026-00 | GC | Capital Plan | 4800 | 0 | 4800 |  | Not Started
Almaden Terrace | 2026 | Repair exterior stair treads and stringers | Replace 10 damaged stair treads and repair landings | 51070-00 | GC | Capital Plan | 3800 | 0 | 3800 |  | Not Started
Almaden Terrace | 2026 | Common Area Accessibility | ADA-compliant parking spaces are required to have an adjacent access aisle. Access aisles were not observed at the acces | 51160-00 | PMC | Capital Plan | 500 | 0 | 500 |  | Not Started
Almaden Terrace | 2026 | Contingency |  | 51990-00 | GC | Contingency | 427584 | 0 | 427584 |  | Reserve
Almaden Terrace | 2026 | Construction Management Fee |  | 51190-00 | GC | CM Fee | 158628 | 0 | 158628 |  | Reserve
Sunterra | 2026 | Modified bitumen membrane repairs / replacement | Modified bitumen membrane repairs / replacement | 84433 | GC | Capital Plan | 650000 | 0 | 650000 |  | Not Started
Sunterra | 2026 | Retaining walls | Retaining walls | 84434 | GC | Capital Plan | 615000 | 0 | 615000 |  | Not Started
Sunterra | 2026 | Asphalt seal coating | Asphalt seal coating | 84204 | GC | Capital Plan | 426300 | 0 | 426300 |  | Not Started
Sunterra | 2026 | Exterior paint | Exterior paint | 84101 | GC | Capital Plan | 360000 | 0 | 360000 |  | Not Started
Sunterra | 2026 | ADA parking & ramps | ADA parking & ramps | 84201 | GC | Capital Plan | 160000 | 0 | 160000 |  | Not Started
Sunterra | 2026 | Stucco repairs | Stucco repairs | 84206 | GC | Capital Plan | 135500 | 0 | 135500 |  | Not Started
Sunterra | 2026 | Plumbing, kitchen and baths | Plumbing, kitchen and baths | 84304 | PMC | Capital Plan | 124800 | 0 | 124800 |  | Not Started
Sunterra | 2026 | Erosion control and drainage | Erosion control and drainage | 84435 | GC | Capital Plan | 118500 | 0 | 118500 |  | Not Started
Sunterra | 2026 | Termite Remediation | Termite Remediation | 83170 | Unmarked | Capital Plan | 114500 | 0 | 114500 |  | Not Started
Sunterra | 2026 | Pet park / pet washing station | Pet park / pet washing station | 84130 | GC | Capital Plan | 110000 | 0 | 110000 |  | Not Started
Sunterra | 2026 | Repair exterior stair treads and stringers | Repair exterior stair treads and stringers | 84114 | GC | Capital Plan | 102000 | 0 | 102000 |  | Not Started
Sunterra | 2026 | Sidewalks and curbs | Sidewalks and curbs | 84221 | GC | Capital Plan | 85500 | 0 | 85500 |  | Not Started
Sunterra | 2026 | Tree Trimming | Tree Trimming | 84300 | PMC | Capital Plan | 75000 | 0 | 75000 |  | Not Started
Sunterra | 2026 | Wall pack lighting | Wall pack lighting | 84112 | GC | Capital Plan | 72500 | 0 | 72500 |  | Not Started
Sunterra | 2026 | Stripe Parking | Stripe Parking | 84201 | GC | Capital Plan | 51450 | 0 | 51450 |  | Not Started
Sunterra | 2026 | Landscape Cleanup & Enhancements | Landscape Cleanup & Enhancements | 84303 | GC | Capital Plan | 50000 | 0 | 50000 |  | Not Started
Sunterra | 2026 | Repair exterior stair railings | Repair exterior stair railings | 84121 | GC | Capital Plan | 48500 | 0 | 48500 |  | Not Started
Sunterra | 2026 | Swimming pool resurface | Swimming pool resurface | 84095 | GC | Capital Plan | 46000 | 0 | 46000 |  | Not Started
Sunterra | 2026 | Sewer Systems | Sewer Systems | 84385 | GC | Capital Plan | 45000 | 0 | 45000 |  | Not Started
Sunterra | 2026 | Swimming pool fencing / gates | Swimming pool fencing / gates | 84095 | GC | Capital Plan | 42800 | 0 | 42800 |  | Not Started
Sunterra | 2026 | Sealants & caulking | Sealants & caulking | 84202 | GC | Capital Plan | 37500 | 0 | 37500 |  | Not Started
Sunterra | 2026 | Site perimeter fencing | Site perimeter fencing | 84205 | GC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Sunterra | 2026 | Landscape irrigation | Landscape irrigation | 84302 | PMC | Capital Plan | 35000 | 0 | 35000 |  | Not Started
Sunterra | 2026 | Expansion Joints | Expansion Joints | 84102 | GC | Capital Plan | 32500 | 0 | 32500 |  | Not Started
Sunterra | 2026 | Grills | Grills | 84203 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Sunterra | 2026 | Playground area and equipment | Playground area and equipment | 84340 | GC | Capital Plan | 30000 | 0 | 30000 |  | Not Started
Sunterra | 2026 | Concrete deck / floor fill | Concrete deck / floor fill | 84104 | GC | Capital Plan | 25000 | 0 | 25000 |  | Not Started
Sunterra | 2026 | Gutters & downspouts | Gutters & downspouts | 84202 | GC | Capital Plan | 18500 | 0 | 18500 |  | Not Started
Sunterra | 2026 | Controlled access gates | Controlled access gates | 84275 | GC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Sunterra | 2026 | Pool furniture | Pool furniture | 84360 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Sunterra | 2026 | Dumpster enclosures | Dumpster enclosures | 84111 | GC | Capital Plan | 13500 | 0 | 13500 |  | Not Started
Sunterra | 2026 | Swimming pool deck | Swimming pool deck | 84095 | GC | Capital Plan | 13500 | 0 | 13500 |  | Not Started
Sunterra | 2026 | Electrical distribution - exterior | Electrical distribution - exterior | 84210 | GC | Capital Plan | 13000 | 0 | 13000 |  | Not Started
Sunterra | 2026 | Replace unit entry doors - exterior | Replace unit entry doors - exterior | 84215 | PMC | Capital Plan | 5000 | 0 | 5000 |  | Not Started
Sunterra | 2026 | Construction Management | Construction Management | 85305 | GC | CM Fee | 188630 | 0 | 188630 |  | Reserve
Santa Lucia | 2026 | Exterior paint | PNA - Paint Exteriors | 51080-00 | GC | Capital Plan | 357000 | 0 | 357000 |  | Not Started
Santa Lucia | 2026 | Asphalt seal coating | PNA - Seal / Crack Fill | 51053-00 | GC | Capital Plan | 266800 | 0 | 266800 |  | Not Started
Santa Lucia | 2026 | Install Wheel Stops at All Parking | PNA - Install Wheel Stops (6' Concrete) | 51050-00 | GC | Capital Plan | 62800 | 0 | 62800 |  | Not Started
Santa Lucia | 2026 | Pressure wash | PNA - Pressure Wash Exteriors | 51990-00 | GC | Capital Plan | 61200 | 0 | 61200 |  | Not Started
Santa Lucia | 2026 | Termite Remediation | PNA - Termite Remediation | 51992-00 | PMC | Capital Plan | 58800 | 0 | 58800 |  | Not Started
Santa Lucia | 2026 | Tree Trimming | PNA - Tree Trimming | 51045-00 | PMC | Capital Plan | 43200 | 0 | 43200 |  | Not Started
Santa Lucia | 2026 | Wall pack lighting | PNA - Replace Wall Pack / Carport Lighting w/ LED | 51141-00 | GC | Capital Plan | 39900 | 0 | 39900 |  | Not Started
Santa Lucia | 2026 | Landscape Cleanup & Enhancements | PNA - Landscape Enhancements & Repair | 51045-00 | PMC | Capital Plan | 20000 | 0 | 20000 |  | Not Started
Santa Lucia | 2026 | Erosion control and drainage | PNA - Erosion Control and Drainage Repair | 51086-00 | PMC | Capital Plan | 15000 | 0 | 15000 |  | Not Started
Santa Lucia | 2026 | Parking lot repairs | PNA - Asphalt Patch (Up to 500 SF) | 51050-00 | GC | Capital Plan | 14000 | 0 | 14000 |  | Not Started
Santa Lucia | 2026 | Repair / replace wood trim | PNA - Remove / Replace Wood Trim (paint to match) | 51070-00 | GC | Capital Plan | 11200 | 0 | 11200 |  | Not Started
Santa Lucia | 2026 | Carports / Garages | PNA - Repair Carports | 51172-00 | GC | Capital Plan | 10500 | 0 | 10500 |  | Not Started
Santa Lucia | 2026 | Dumpster enclosures | PNA - Repair Dumpster Enclosures | 51163-00 | GC | Capital Plan | 7500 | 0 | 7500 |  | Not Started
Santa Lucia | 2026 | Stripe parking areas | PNA - Re-Stripe Parking | 51053-00 | GC | Capital Plan | 5723 | 0 | 5723 |  | Not Started
Santa Lucia | 2026 | Site perimeter fencing | PNA - Repair CMU Block Fencing (Hollow Cells) | 51076-00 | GC | Capital Plan | 3750 | 0 | 3750 |  | Not Started
Santa Lucia | 2026 | Sidewalks and curbs | PNA - Repair Sidewalks / Curbs (Up to 100 SF) | 51091-00 | GC | Capital Plan | 3500 | 0 | 3500 |  | Not Started
Santa Lucia | 2026 | Storage room doors | PNA - Replace Storage Room Doors (3068 HCWD) | 51073-00 | GC | Capital Plan | 1100 | 0 | 1100 |  | Not Started
Santa Lucia | 2026 | Construction Management Fee | CM Fees | 51190-00 | GC | CM Fee | 51554 | 0 | 51554 |  | Reserve
Santa Lucia | 2026 | Contingency | Contingency Amount | 51990-00 | GC | Contingency | 49099 | 0 | 49099 |  | Reserve

## Summary
Post Capital Plans — Alternative Approach (All Properties)
GC by cohort: 2024 & earlier assumed 100% @ budget; 2025 from pay app (else GL); 2026 pay app only. PMC/Unmarked from GL (cohort window). '% Projects' EXCLUDES Contingency & CM Fee. 'Net vs Total Budget' = Total Budget − Project Spent: positive = contingency/CM reserve covers any base overage; red/negative = genuinely over total budget.
Property | Acquired | Method | Project Budget | Total Spend | Capital Plan | Contingency | CM Fee | Total Budget | Remaining Balance | Capital Plan | GC Contract | Recent Pay App | GL Detail | Banner Report | First Call A/R | Scope Split GC/PMC/Unmarked
Allora Bella Terra | 2024 | GC @ budget | 1420738 | 1420738 |  | 802262 | 111150 | 2334150 |  | ✓ |  | ✓ app 004 | Entrata GL | ✓ | ✓ | 47 GC / 0 PMC
Almaden 1930 | 2026 | GC pay app | 1386000 | 255233 |  | 87089 | 73654 | 1546744 |  | ✓ | ✓ | ✓ app 001 | Aperto GL | ✓ |  | 38 GC / 2 PMC
Amalfi at Tuscan Lakes | 2023 | GC @ budget | 3314095 | 3231255 |  | 279443 | 0 | 3593538 |  | ✓ |  | ✓ app 005 | Entrata GL | ✓ | ✓ | 48 GC / 0 PMC / 11 unmarked
Ardmore Springs | 2026 | GC pay app | 1120251 | 288292 |  | 56013 | 58813 | 1235077 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ |  | 23 GC / 12 PMC
Avenues of Kennesaw | 2025 | GC pay app | 4667854 | 3940881 |  | 258304 | 271220 | 5197378 |  | ✓ | ✓ | ✓ app 006 | Entrata GL | ✓ | ✓ | 56 GC / 14 PMC
Avila | 2023 | GC @ budget | 1578975 | 1578975 |  | 0 | 0 | 1578975 |  | ✓ |  | ✓ app 005 | Entrata GL | ✓ |  | 42 GC / 0 PMC
Avonmora | 2024 | GC @ budget | 3700650 | 2514650 |  | 20000 | 0 | 3720650 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ | ✓ | 32 GC / 4 PMC
Azur Aparments | 2025 | GC pay app | 1227998 | 384860 |  | 329680 | 77884 | 1635562 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 55 GC / 1 PMC
Bentley Parke | 2026 | GC pay app | 1175156 | 287463 |  | 58758 | 61696 | 1295609 |  | ✓ | ✓ | ✓ app 001 | Aperto GL | ✓ |  | 25 GC / 7 PMC
Bridgepoint | 2024 | GC @ budget | 3389015 | 3395678 |  | 90985 | 174000 | 3654000 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ | ✓ | 71 GC / 1 PMC
Cambridge Square | 2025 | GC pay app | 2315365 | 723573 |  | 115768 | 121557 | 2552690 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ |  | 35 GC / 5 PMC
Candlewood | 2025 | GC pay app | 1325788 | 508005 |  | 132579 | 72918 | 1531285 |  | ✓ | ✓ | ✓ app 002 | Aperto GL | ✓ |  | 22 GC / 8 PMC
Canyon Villa | 2025 | GC GL fallback | 1262654 | 148445 |  | 33781 | 64822 | 1361257 |  | ✓ | ✓ | Project not started | ConAM GL | ✓ | ✓ | 30 GC / 7 PMC
Chaparral | 2025 | GC pay app | 2241450 | 1791338 |  | 87488 | 116447 | 2445384 |  | ✓ | ✓ | ✓ app 003 | Aperto GL | ✓ | ✓ | 30 GC / 6 PMC
Cherry Creek | 2026 | GC none ($0) | 983425 | 1000 |  | 49171 | 51630 | 1084226 |  | ✓ | ✓ | Project not started | Aperto GL | ✓ |  | 26 GC / 9 PMC
Cityscape | 2024 | GC @ budget | 171634 | 187122 |  | 17163 | 9440 | 198238 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ | ✓ | 7 GC / 1 PMC
Clipper Cove | 2026 | GC pay app | 4754286 | 1078170 |  | 237714 | 249600 | 5241600 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ |  | 40 GC / 8 PMC
Collin Creek | 2023 | GC @ budget | 2763458 | 2168870 |  | 1004542 | 0 | 3768000 |  | ✓ |  | ✓ app 004 | Entrata GL | ✓ |  | 46 GC / 11 PMC / 2 unmarked
Colonnade | 2026 | GC @ budget | 1577229 | 1329400 |  | 78861 | 82805 | 1738895 |  | ✓ |  | Project not started | None |  |  | 16 GC / 13 PMC
Crescent Village 1 & 2 | 2017 | GC @ budget | 648850 | 648850 |  | 0 | 0 | 648850 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 19 GC / 1 PMC
Crestmark | 2025 | GC pay app | 1755200 | 542139 |  | 87760 | 92148 | 1935108 |  | ✓ | ✓ | ✓ app 002 | Entrata GL | ✓ | ✓ | 19 GC / 25 PMC
Cypress Bend | 2025 | GC pay app | 623390 | 459041 |  | 77339 | 42724 | 743453 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 22 GC / 13 PMC
Cypress Bend Village | 2025 | GC pay app | 932415 | 736833 |  | 103516 | 57309 | 1093241 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ | ✓ | 30 GC / 10 PMC
Cypress Ridge | 2026 | GC pay app | 772016 | 241689 |  | 38601 | 40531 | 851148 |  | ✓ | ✓ | ✓ app 003 | CapEX GL | ✓ |  | 22 GC / 10 PMC
David Ave | 2025 | GC pay app | 864956 | 530429 |  | 45096 | 47350 | 957402 |  | ✓ | ✓ | ✓ app 002 | Aperto GL | ✓ | ✓ | 30 GC / 10 PMC
Discovery Park | 2024 | GC @ budget | 784444 | 788231 |  | 20000 | 40222 | 844666 |  | ✓ |  | ✓ app 002 | Entrata GL | ✓ | ✓ | 49 GC / 1 PMC
Elliot Baymeadows | 2025 | GC pay app | 2868800 | 1348085 |  | 0 | 143440 | 3012240 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 27 GC / 16 PMC
Emerald Pointe | 2015 | GC @ budget | 1356304 | 1321427 |  | 64432 | 0 | 2709387 |  | ✓ |  | ✓ app 003 | Aperto GL | ✓ |  | 19 GC / 4 PMC / 1 unmarked
Encore Crossing | 2022 | GC @ budget | 2244350 | 1283909 |  | 0 | 0 | 2244350 |  | ✓ |  | ✓ app 004 | Entrata GL | ✓ |  | 39 GC / 9 PMC
Foster Creek | 2025 | GC pay app | 1118497 | 550622 |  | 48067 | 50470 | 1217034 |  | ✓ | ✓ | ✓ app 2 | Entrata GL | ✓ | ✓ | 23 GC / 13 PMC
Foxdale Village | 2025 | GC pay app | 3326446 | 2588390 |  | 351235 | 183884 | 3861564 |  | ✓ | ✓ | ✓ app 004 | Aperto GL | ✓ | ✓ | 44 GC / 5 PMC
Hampton Courts | 2024 | GC @ budget | 1990358 | 1150400 |  | 100000 | 104518 | 2194875 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 44 GC / 15 PMC
Harbor Terrace | 2024 | GC @ budget | 31500 | 31500 |  | 0 | 0 | 31500 |  | ✓ | ✓ | ✓ app 002 | Aperto GL | ✓ | ✓ | 4 GC / 0 PMC
Island Villas | 2022 | GC @ budget | 2101360 | 1838026 |  | 0 | 0 | 2101360 |  | ✓ |  | ✓ app 004 | Entrata GL | ✓ | ✓ | 35 GC / 8 PMC
Las Colinas Heights | 2023 | GC @ budget | 5539442 | 3979908 |  | 162465 | 0 | 5701907 |  | ✓ |  | ✓ app 006 | Entrata GL | ✓ |  | 56 GC / 13 PMC / 1 unmarked
Latitude at the Commons | 2025 | GC pay app | 735739 | 239238 |  | 271880 | 50381 | 1058000 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ |  | 22 GC / 13 PMC
Marquee | 2024 | GC @ budget | 1232147 | 718065 |  | 61607 | 61607 | 1355362 |  | ✓ | ✓ | ✓ app 003 | Aperto GL | ✓ | ✓ | 22 GC / 18 PMC
Navigator Villas | 2024 | GC @ budget | 864061 | 310259 |  | 20000 | 44203 | 928264 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ |  | 16 GC / 18 PMC
Oak Forest | 2023 | GC @ budget | 2613720 | 2198268 |  | 4346280 | 0 | 6960000 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ |  | 40 GC / 8 PMC / 4 unmarked
Oak Park | 2023 | GC @ budget | 7843534 | 6119761 |  | 572778 | 534592 | 8950904 |  | ✓ |  |  | Entrata GL | ✓ |  | 0 GC / 0 PMC / 70 unmarked
Oak Park Monrovia | 2025 | GC pay app | 1297450 | 352080 |  | 90693 | 69407 | 1457550 |  | ✓ | ✓ | ✓ app 001 | Aperto GL | ✓ | ✓ | 18 GC / 8 PMC
Orchard Glen | 2025 | GC pay app | 3179250 | 2583879 |  | 166381 | 174700 | 3520331 |  | ✓ | ✓ | ✓ app 003 | Aperto GL | ✓ | ✓ | 33 GC / 13 PMC
Oslo | 2026 | GC none ($0) | 115000 | 119427 |  | 4750 | 4988 | 124738 |  | ✓ |  | Project not started | Entrata GL | ✓ |  | 2 GC / 4 PMC / 1 unmarked
Paddock Club | 2025 | GC pay app | 1565089 | 1658198 |  | 282911 | 92400 | 1940400 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ |  | 26 GC / 18 PMC
Presidium Edgestone | 2024 | GC @ budget | 365506 | 361506 |  | 36551 | 20103 | 422160 |  | ✓ |  | ✓ app 003 | CapEX GL | ✓ |  | 22 GC / 2 PMC
Rancho Cordova | 2025 | GC pay app | 622145 | 576066 |  | 31107 | 32663 | 685915 |  | ✓ | ✓ | ✓ app 002 | Aperto GL | ✓ | ✓ | 24 GC / 5 PMC
Regency & Lexington | 2025 | GC pay app | 1996796 | 1430810 |  | 215411 | 118476 | 2330684 |  | ✓ | ✓ | ✓ app 003 | Aperto GL | ✓ | ✓ | 68 GC / 23 PMC
Renaissance | 2025 | GC GL fallback | 1909884 | 21302 |  | 95494 | 100269 | 2105647 |  | ✓ | ✓ | Project not started | CapEX GL | ✓ |  | 18 GC / 10 PMC
Rosemont | 2025 | GC pay app | 2757064 | 1874580 |  | 137853 | 144746 | 3039663 |  | ✓ | ✓ | ✓ app 007 | CapEX GL |  |  | 40 GC / 21 PMC
San Regis | 2026 | GC none ($0) | 4549500 | 0 |  | 227475 | 238849 | 5015824 |  | ✓ | ✓ | Project not started | Aperto GL | ✓ |  | 28 GC / 8 PMC
Sorrento at Tuscan Lakes | 2023 | GC @ budget | 2479733 | 2438420 |  | 77226 | 127848 | 2684807 |  | ✓ |  | ✓ app 005 | Entrata GL | ✓ |  | 44 GC / 0 PMC / 12 unmarked
Swiss Gables | 2025 | GC pay app | 1065004 | 678115 |  | 0 | 53250 | 1118254 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 24 GC / 13 PMC
The Arbors | 2024 | GC @ budget | 2269256 | 2221801 |  | 70064 | 116966 | 2456286 |  | ✓ | ✓ | ✓ app 004 | Aperto GL | ✓ |  | 48 GC / 11 PMC
The Ardent | 2025 | GC pay app | 2699800 | 763142 |  | 133740 | 140427 | 2973967 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ |  | 44 GC / 4 PMC
The Fairways | 2025 | GC pay app | 1141973 | 1164821 |  | 178027 | 66000 | 1386000 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 30 GC / 9 PMC
The Grand at Hill Street | 2023 | GC @ budget | 454050 | 506463 |  | 0 | 0 | 454050 |  | ✓ |  | ✓ app 003 | Entrata GL | ✓ |  | 14 GC / 3 PMC
The Hightone (Allora Denton) | 2023 | GC @ budget | 509500 | 610504 |  | 0 | 0 | 509500 |  | ✓ |  | ✓ app 002 | Entrata GL | ✓ | ✓ | 11 GC / 3 PMC
The Lakes | 2025 | GC pay app | 2098546 | 983631 |  | 104927 | 119624 | 2323097 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ |  | 29 GC / 7 PMC
The Retreat | 2022 | GC @ budget | 1402200 | 451156 |  | 0 | 0 | 1402200 |  | ✓ |  | ✓ app 003 | Entrata GL |  |  | 13 GC / 11 PMC
The Vibe | 2025 | GC pay app | 1336934 | 1009575 |  | 229733 | 78333 | 1645000 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ | ✓ | 38 GC / 7 PMC
Tribute Verdae | 2026 | GC pay app | 1032700 | 218594 |  | 0 | 51635 | 1084335 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ |  | 24 GC / 5 PMC
Valera Riverside | 2025 | GC GL fallback | 144480 | 10992 |  | 7224 | 7585 | 159289 |  | ✓ | ✓ | Project not started | Entrata GL | ✓ |  | 5 GC / 5 PMC
Viewcrest Village | 2021 | GC @ budget | 1098375 | 1036958 |  | 0 | 0 | 1098375 |  | ✓ |  | ✓ app 2 | None | ✓ |  | 9 GC / 10 PMC
Village at Broadstone | 2024 | GC @ budget | 3729334 | 3728984 |  | 0 | 186467 | 3915800 |  | ✓ | ✓ | ✓ app 001 | None | ✓ |  | 52 GC / 2 PMC
Walnut Square | 2026 | GC pay app | 887775 | 109702 |  | 44389 | 46608 | 978772 |  | ✓ | ✓ | ✓ app 001 | CapEX GL | ✓ |  | 25 GC / 1 PMC
Waterford | 2026 | GC pay app | 1339580 | 273564 |  | 66979 | 70328 | 1476887 |  | ✓ | ✓ | ✓ app 001 | Entrata GL | ✓ |  | 34 GC / 8 PMC
Willow Lakes | 2026 | GC pay app | 1039016 | 814867 |  | 51163 | 54509 | 1144688 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ |  | 32 GC / 9 PMC
Windward | 2025 | GC pay app | 1790312 | 354472 |  | 89516 | 93991 | 1973819 |  | ✓ | ✓ | ✓ app 003 | Entrata GL | ✓ |  | 12 GC / 13 PMC
Anthem Clearwater | 2026 | GC none ($0) | 3041785 | 0 |  | 386303 | 171404 | 3599492 |  | ✓ |  | Project not started |  |  |  | 32 GC / 10 PMC
Forest View | 2026 | GC none ($0) | 1577580 | 0 |  | 78879 | 82823 | 1739282 |  | ✓ |  | Project not started |  |  |  | 25 GC / 23 PMC
Almaden Terrace | 2026 | GC none ($0) | 4045018 | 0 |  | 427584 | 158628 | 4631230 |  | ✓ |  | Project not started |  |  |  | 37 GC / 3 PMC
Sunterra | 2026 | GC none ($0) | 3751850 | 0 |  | 0 | 188630 | 3940480 |  | ✓ |  | Project not started |  |  |  | 28 GC / 5 PMC / 1 unmarked
Santa Lucia | 2026 | GC none ($0) | 981973 | 0 |  | 49099 | 51554 | 1082625 |  | ✓ |  | Project not started |  |  |  | 13 GC / 4 PMC
TOTAL

## Emerald Pointe
Emerald Pointe — 2015 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requiring | Lender Due Date | Reserve Used
84 | 51140-00 | Electrical Replacement | Replace Zinsco Electrical Subpanels ($525,000) Zinsco breakers were observed in the electrical subpanels inside all the residential units which is 250 panels. Per Fannie Mae, these breakers have been recalled and should be replaced at this time. ($212,500) - $525,000 Replace Zinsco Unit Main Breakers/Panels ($62,000) Zinsco breakers were observed in the main switchboards, which contain approximately 31 panels in the main switchboards that contain the unit main breakers. Per Fannie Mae, these breakers have been recalled and should be replaced at this time. | GC | Year 1 | 587000 | 587000 |  |  | 0 |  | Replace Zinsco Electrical Subpanels ($525,000) Zinsco breakers were observed in the electrical subpanels inside all the residential units which is 250 panels. Per Fannie Mae, these breakers have been | [5 empty] | 2026-06-05
117 | 51992-00 | Termite/Pest Control | Termite Remediation ($249,500) WDI infestation noted at rafter tail, water heater closet door jam, and water heater closet trim. ($5,820) Address dryrot/fungus identified throughout the site in the WDI report.($67,700) - $124,500 Facia Repairs as noted in the WDI report. ($7,900) - $119,180 | GC | Year 1 | 249500 | 249500 |  |  | 0 |  | Termite Remediation ($249,500) WDI infestation noted at rafter tail, water heater closet door jam, and water heater closet trim. ($5,820) Address dryrot/fungus identified throughout the site in the W | [5 empty] | 2026-12-05
87 | 51143-00 | Wiring | Repair Aluminum Wiring - Allowance ($225,000) Aluminum wiring was observed in the residential units. To mitigate aluminum wires, it is required that an allowance be made for the installation of COPALUM and/or AlumiConn connectors at receptacles and devices at this time. ($150,000) - $225,000 | GC | Year 1 | 225000 | 225000 |  |  | 0 |  | Repair Aluminum Wiring - Allowance ($225,000) Aluminum wiring was observed in the residential units. To mitigate aluminum wires, it is required that an allowance be made for the installation of COPALU | [5 empty] | 2026-06-05
58 | 51084-00 | Railings & Fences | Replace Landing Railings ($60,000) | GC | Year 1 | 60000 | 60000 |  |  | 0 |  | Replace Landing Railings ($60,000)
21 | 51023-00 | Pool Resurfacing | Resurface Pool Decks ($42,500) | GC | Year 1 | 42500 | 42500 |  |  | 0 |  | Resurface Pool Decks ($42,500)
32 | 51043-00 | Tree Trimming/Pruning & Removal | Tree Trimming ($25,000) | Capex | Year 1 | 25000 | 59 |  |  | N/A |  | Tree Trimming ($25,000)
34 | 51046-00 | Irrigation System | Irrigation Repairs ($25,000) | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Irrigation Repairs ($25,000)
42 | 51062-00 | Roof Repairs | Roof Repairs ($15,000) | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Roof Repairs ($15,000)
52 | 51076-00 | Fence Repair/Replacement | Remove Pergolas ($15,000) | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Remove Pergolas ($15,000)
57 | 51083-00 | Decks/Balconies/Patio Repairs | Repair Deteriorating Wood on Patios ($15,000) | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Repair Deteriorating Wood on Patios ($15,000)
43 | 51063-00 | Roof Cleaning | Roof Inspection & Cleaning ($10,000) | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Roof Inspection & Cleaning ($10,000)
33 | 51045-00 | Landscape Upgrades | Repair/Improve Landscape ($7,500) Many of the landscaping sprinkler systems are broken in multiple areas of theProperty. These areas were specifically observed by Building 7 with broken sprinkler pipes, and with bare ground/no grass observed by Buildings 12,14, 20-23, north pool, and by the playground. Repairing and improving the damaged landscaping areas is required. | PMC | Year 1 | 7500 | 18 |  |  | N/A |  | Repair/Improve Landscape ($7,500) Many of the landscaping sprinkler systems are broken in multiple areas of theProperty. These areas were specifically observed by Building 7 with broken sprinkler pipe | [5 empty] | 2026-12-05
15 | 51010-00 | Pool Furniture Replacement | New Pool Furniture ($5,000) | PMC | Year 1 | 5000 | 12 |  |  | N/A |  | New Pool Furniture ($5,000)
62 | 51091-00 | Sidewalk/Curb Repair/Replacement | Repair Sidewalk Tripping Hazards ($2,500) | GC | Year 1 | 2500 | 2500 |  |  | 0 |  | Repair Sidewalk Tripping Hazards ($2,500)
92 | 51159-00 | Carpentry/Sheetrock | Repair Damaged Breezeway Ceiling ($1,000) A limited damaged of exterior breezeway ceiling finishes located by Building 2 was observed. Repairing the damaged ceiling breezeway is required. | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | Repair Damaged Breezeway Ceiling ($1,000) A limited damaged of exterior breezeway ceiling finishes located by Building 2 was observed. Repairing the damaged ceiling breezeway is required. | [5 empty] | 2026-06-05
56 | 51082-00 | Trim/Doors | Repair Damaged Door ($750) The maintenance room door located near the north pool was observed to bedamaged. Repairing the damaged door is required | GC | Year 1 | 750 | 750 |  |  | 0 |  | Repair Damaged Door ($750) The maintenance room door located near the north pool was observed to bedamaged. Repairing the damaged door is required | [5 empty] | 2026-12-05
19 | 51021-00 | Pool Deck Repair | Seal Cracks Pool Deck ($700) Cracks were observed on the clubhouse pool deck. It appeared that there were attempts of resealing the cracks. However, the cracks are still visible and not sealed. CBRE requires resealing cracks with a non-shrinking grout. | GC | Year 1 | 700 | 700 |  |  | 0 |  | Seal Cracks Pool Deck ($700) Cracks were observed on the clubhouse pool deck. It appeared that there were attempts of resealing the cracks. However, the cracks are still visible and not sealed. CBRE r | [5 empty] | 2026-12-05
63 | 51091-00 | Sidewalk/Curb Repair/Replacement | Repair Sidewalk Cracks ($700) A couple of the Subject's concrete sidewalk sections exhibit cracks. These conditions were specifically observed by Units 129 and 217. CBRE requires resealing cracks with a non-shrinking grout. | GC | Year 1 | 700 | 700 |  |  | 0 |  | Repair Sidewalk Cracks ($700) A couple of the Subject's concrete sidewalk sections exhibit cracks. These conditions were specifically observed by Units 129 and 217. CBRE requires resealing cracks with | [5 empty] | 2026-12-05
25 | 51027-00 | Court Resurfacing | Repair Basketball Court Cracks ($500) Asphalt pavement cracks was observed throughout the basketball court. Resealing cracks is required. | GC | Year 1 | 500 | 500 |  |  | 0 |  | Repair Basketball Court Cracks ($500) Asphalt pavement cracks was observed throughout the basketball court. Resealing cracks is required. | [5 empty] | 2026-12-05
61 | 51090-00 | Concrete/Foundation | Repair Concrete Pavement Cracks ($500) Concrete cracks were observed at the concrete pavement located adjacent to the basketball court. Resealing cracks is required. | GC | Year 1 | 500 | 500 |  |  | 0 |  | Repair Concrete Pavement Cracks ($500) Concrete cracks were observed at the concrete pavement located adjacent to the basketball court. Resealing cracks is required. | [5 empty] | 2026-12-05
69 | 51110-00 | Boiler Replacement | Repair Water Heater Leaks - Building 3 ($500) The water heater was leaking in Building 3 at the time of the assessment. Repairing water leaks is required. | PMC | Year 1 | 500 | 1 |  |  | N/A |  | Repair Water Heater Leaks - Building 3 ($500) The water heater was leaking in Building 3 at the time of the assessment. Repairing water leaks is required. | [5 empty] | 2026-12-05
|  | PROJECTS subtotal (excl. contingency/CM fee) |  |  | Year 1
132 | 51190-00 | Construction Supervision Expense | CM Fees | CMF | Year 1 | 67654 | 67654 | 0 |  | N/A |  | CM Fees
131 | 51180-00 | Contingency Amount | Contingency | CON | Year 1 | 64432 | 64432 | 0 |  | N/A |  | Contingency

## Crescent Village 1 & 2
Crescent Village 1 & 2 — 2017 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
15 | 84204 | Asphalt & Pavement | Mill cement stabilize and repave asphalt part of drive esles and repair concrete potholes on phase two Repair concrete parking lot/pavement areas - The concrete paving was observed to be in fair condition with numerous cracks and uneven edges. CBRE recommends crack sealing and sectional replacement for the damaged concrete and uneven edge areas. | GC | Year 1 | 400000 | 400000 |  |  | 0 |  | Mill cement stabilize and repave asphalt part of drive esles and repair concrete potholes on phase two Repair concrete parking lot/pavement areas - The concrete paving was observed to be in fair cond
19 | 84205 | Fences & gates - site perimeter | Replace perimater fence on three sides of community Repair perimeter fencing - Collapsed fence panels were observed along the perimeter of the site. In addition, parts of the chain link fencing at the perimeter were noted as damaged and leaning. CBRE recommends replacing the damaged fence panels to match the existing ones. | GC | Year 1 | 95000 | 95000 |  |  | 0 |  | Replace perimater fence on three sides of community Repair perimeter fencing - Collapsed fence panels were observed along the perimeter of the site. In addition, parts of the chain link fencing at the
53 | 84210 | Common area light fixtures | repair /replace leaning or broken poles and pole lights throughout the community | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | repair /replace leaning or broken poles and pole lights throughout the community
20 | 84303 | Tree Trimming - Landscaping | Tree trim | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Tree trim
16 | 84201 | Stripe parking areas | Stripe Parking | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Stripe Parking
17 | 84115 | Sidewalks | Repair trip Hazards | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Repair trip Hazards
26 | 84111 | Dumpster enclosures | repair and paint | GC | Year 1 | 9800 | 9800 |  |  | 0 |  | repair and paint
36 | 84202 | Gutters & downspouts | Replace damaged gutter and downspouts, Clean, re-pitch remaining | GC | Year 1 | 9800 | 9800 |  |  | 0 |  | Replace damaged gutter and downspouts, Clean, re-pitch remaining
50 | 84220 | Replace AC condenser | Install installation and separate condensing units | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | Install installation and separate condensing units
24 | 84095 | Fences & gates - swimming pool | Rerair and paint pool fence | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | Rerair and paint pool fence
25 | 84105 | Pergola court | Repair and paint purgola in culdasac | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Repair and paint purgola in culdasac
33 | 84206 | Expansion Joints | Building Expansion Joints | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Building Expansion Joints
32 | 84121 | Repair patio/balcony railings | secure all patio railings Repair exterior railings on east side of the property - Peeling and flaking paint was specifically observed on the exterior railings of Units 3301 and 3002. This condition appears to be prevalent in the units along the east side of the property. Remove all peeling and flaking paint, prime, and re-paint the ratings with rust-inhibitive paint. An allowance is included to accommodate repairs in these areas. | GC | Year 1 | 6500 | 6500 |  |  | 0 |  | secure all patio railings Repair exterior railings on east side of the property - Peeling and flaking paint was specifically observed on the exterior railings of Units 3301 and 3002. This condition a
38 | 84433 | Roof - Sealants & caulking | Roof Sealants | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Roof Sealants
52 | 84210 | Electrical distribution | repair lighting control system | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | repair lighting control system
37 | 84433 | Roof Flashing | replace damaged flashing | GC | Year 1 | 4000 | 4000 |  |  | 0 |  | replace damaged flashing
14 | 84432 | Storm sewer piping | Clean storm sewer basins | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Clean storm sewer basins
28 | 84221 | Repair ADA accessway and wheel stop | Repair ADA accessway and wheel stop - the accessway from the ADA parking lot, between Crescent Village 1 and 2 on the northwest access road, was damaged and, causing a tripping hazard. In addition, a wheel stop adjacent to the area was observed damaged and dislodged. The accessway should be repaired to align with adjacent surfaces to allow ADA access, and the wheelstop should be replaced with a new one to match the existing. | GC | Year 1 | 1800 | 1800 |  |  | 0 |  | Repair ADA accessway and wheel stop - the accessway from the ADA parking lot, between Crescent Village 1 and 2 on the northwest access road, was damaged and, causing a tripping hazard. In addition, a
18 | 84517 | Erosion control | Add soil to eroded areas Repair erosion at drainage channel - Minor erosion was observed in the drainage channel at the northeast section of the property. These areas should be regraded and filled in, compacted, an reseeded with grass. | GC | Year 1 | 1200 | 1200 |  |  | 0 |  | Add soil to eroded areas Repair erosion at drainage channel - Minor erosion was observed in the drainage channel at the northeast section of the property. These areas should be regraded and filled in,
27 | 84221 | Concrete Repairs - Repair washed out walkway at unit | Repair wash out walkway at unit 2301 - The front entry concrete walkway to unit 2301 was noted as damaged from flooding and separated from the stoop. Remove the damaged section, regrade it, and install a new section to match the existing one. | PMC | Year 1 | 750 | 750 |  |  | N/A |  | Repair wash out walkway at unit 2301 - The front entry concrete walkway to unit 2301 was noted as damaged from flooding and separated from the stoop. Remove the damaged section, regrade it, and instal
PROJECTS subtotal (excl. contingency/CM fee)

## Viewcrest Village
Viewcrest Village — 2021 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
31 | 84101.0 | Exterior painting | Community Paint | GC | Year 1 | 375000 | 375000 |  |  | 0 |  | Community Paint
25 | 84433.0 | Roof Replacement | Replace 12 roofs | GC | Year 1 | 372000 | 372000 |  |  | 0 |  | Replace 12 roofs
37 | 84330.0 | Electrical Panels - Replace FPE Stab-Lok Panels | It was reported that approximately 20% of the units still have FPE stab-lok panels. | GC | Year 1 | 126000 | 126000 |  |  | 0 |  | It was reported that approximately 20% of the units still have FPE stab-lok panels. | [5 empty] | 2027-02-06
38 | 84210.0 | Electrical Meters - Electrical audit and grounding r | Audit meters for proper housing, mounting and grounding and repair/replace as needed | GC | Year 1 | 51000 | 51000 |  |  | 0 |  | Audit meters for proper housing, mounting and grounding and repair/replace as needed
17 | 84116.0 | Leasing office | Spot reno (new FF&E) | Capex | Year 1 | 35000 | 8746 |  |  | N/A |  | Spot reno (new FF&E)
23 | 84210.0 | Meter Boxes - Repair/replace meter/cable housing | Replace on all buildings | Capex | Year 1 | 25000 | 6247 |  |  | N/A |  | Replace on all buildings
26 | 84202.0 | Gutters & downspouts | Repair and replace damaged or missing gutters | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Repair and replace damaged or missing gutters
30 | 84206.0 | Repair / replace vinyl siding | Replace failing siding as needed | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Replace failing siding as needed
32 | 84105.0 | Repair / replace wood trim | Replace bad areas of Fascia | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Replace bad areas of Fascia
27 | 84433.0 | Flashing | Replace flashing on 12 remaining roofs | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Replace flashing on 12 remaining roofs
28 | 84433.0 | Roof Repairs - Repair/replace sofits | Repair/replace missing or poorly maintained sofits to improve airflow | GC | Year 1 | 12500 | 12500 |  |  | 0 |  | Repair/replace missing or poorly maintained sofits to improve airflow
40 | 82480.0 | Appliances - Repair Washer/Dryer Hookups | Approximately 10-15 units have improperly installed hookups. | PMC | Year 1 | 9375 | 2343 |  |  | N/A |  | Approximately 10-15 units have improperly installed hookups. | [5 empty] | 2027-02-06
34 | 84217.0 | HVAC Repair - Heating System | Cadet wall heaters were observed in 3-BR units. | PMC | Year 1 | 3188 | 796 |  |  | N/A |  | Cadet wall heaters were observed in 3-BR units. | [5 empty] | 2027-02-06
14 | 84221.0 | Grind Sidewalk Trip Hazard | Trip hazards were specifically observed by Buildings 3342, 3423, 3412, 3413, 3430, 1542, 3427. | PMC | Year 1 | 3062 | 765 |  |  | N/A |  | Trip hazards were specifically observed by Buildings 3342, 3423, 3412, 3413, 3430, 1542, 3427. | [5 empty] | 2026-05-06
41 | 83160.0 | Interior Other - Bathroom tub mold | Mold at the bottom of the tub surround was observed at Unit 3412, 1512, 1538B, 1579, 4 out of 30 units that were inspected. | PMC | Year 1 | 2500 | 625 |  |  | N/A |  | Mold at the bottom of the tub surround was observed at Unit 3412, 1512, 1538B, 1579, 4 out of 30 units that were inspected. | [5 empty] | 2026-05-06
42 | 83170.0 | Pest Control - Interior pest control | Two vacant units, 3419B and 1512B have been found to have fleas throughout. Pest control treatment has been scheduled for both units. | PMC | Year 1 | 2000 | 500 |  |  | N/A |  | Two vacant units, 3419B and 1512B have been found to have fleas throughout. Pest control treatment has been scheduled for both units. | [5 empty] | 2026-05-06
15 | 84221.0 | Sidewalk - Seal Concrete Cracks | Limited areas of concrete sidewalk were observed with cracks. These area were specifically were observed by Units 3472C (2 locations) and 3442. | PMC | Year 1 | 750 | 187 |  |  | N/A |  | Limited areas of concrete sidewalk were observed with cracks. These area were specifically were observed by Units 3472C (2 locations) and 3442. | [5 empty] | 2027-02-06
16 | 84221.0 | Concrete Crack - Building 8 | Sidewalk exhibiting crack in concrete | PMC | Year 1 | 625 | 156 |  |  | N/A |  | Sidewalk exhibiting crack in concrete | [5 empty] | 2027-02-06
36 | 84211.0 | Fire System Work - Clear Fire Department Violations | The fire inspection report dated March 27, 2023, cited violations, including extension cords hanging from the ceiling and fire extinguishers with expired tags. | PMC | Year 1 | 375 | 94 |  |  | N/A |  | The fire inspection report dated March 27, 2023, cited violations, including extension cords hanging from the ceiling and fire extinguishers with expired tags. | [5 empty] | 2027-02-06
PROJECTS subtotal (excl. contingency/CM fee)

## Encore Crossing
Encore Crossing — 2022 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
90 | 0900 - FF&E in Units | Interior Update Placeholder | Interior Unit Renovation | Capex | Year 1 | 960000 | 332 |  |  | N/A
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Per Mark, placeholder for office redecoration x 2 (Includes adding sliding glass doors out to pool and opening up wall to expand gym area in phase 1 and update kitchen area in phase 1). | GC | Year 1 | 125000 | 125000 |  |  | 0 |  | Per Mark, placeholder for office redecoration x 2 (Includes adding sliding glass doors out to pool and opening up wall to expand gym area in phase 1 and update kitchen area in phase 1).
24 | 0200 - Site Utilities & Improvements | Landscaping | remove dead shrubs and change entrance island shrubs. DD $60k placeholder for landscape enhancement | GC | Year 1 | 110000 | 110000 |  |  | 0 |  | remove dead shrubs and change entrance island shrubs. DD $60k placeholder for landscape enhancement
22 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | $40k = Repair wood fence and paint, $40k = Repair (3) entrance gates. $15k iron fence repairs Phase 1 | GC | Year 1 | 95000 | 95000 |  |  | 0 |  | $40k = Repair wood fence and paint, $40k = Repair (3) entrance gates. $15k iron fence repairs Phase 1
121 | 1100- Specialties, Equipment & Furnishings | Video systems | Installation of new system (placeholder) | Capex | Year 1 | 75000 | 0 |  |  | N/A |  | Installation of new system (placeholder)
123 | 1100- Specialties, Equipment & Furnishings | Pool furniture | New pool furniture (2 pools) | Capex | Year 1 | 60000 | 206 |  |  | N/A |  | New pool furniture (2 pools)
32 | 0200 - Site Utilities & Improvements | Pool Area Enhancement | Value-add enhancement to pool area, to inlcude turf installation, outdoor kitchen, fire pit area | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Value-add enhancement to pool area, to inlcude turf installation, outdoor kitchen, fire pit area
116 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | Office redecoration placeholder | Capex | Year 1 | 50000 | 131158 |  |  | N/A |  | Office redecoration placeholder
122 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | New fitness equipment | Capex | Year 1 | 50000 | 67319 |  |  | N/A |  | New fitness equipment
39 | 0200 - Site Utilities & Improvements | Carports / Garages | Replace 10 garage doors | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | Replace 10 garage doors
38 | 0200 - Site Utilities & Improvements | Building entrance | Entrance upgrade | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Entrance upgrade
108 | 0900 - FF&E in Units | Range Queen | Stove Replacements | Capex | Year 1 | 32040 | 0 |  |  | N/A
145 | 1600 - Electrical | Replace breezeway lights | Replace breezeway fixtures with led | GC | Year 1 | 28600 | 28600 |  |  | 0 |  | Replace breezeway fixtures with led
25 | 0200 - Site Utilities & Improvements | Resurface swimming pool | Resurface Phase I | GC | Year 1 | 28000 | 28000 |  |  | 0 |  | Resurface Phase I
82 | 0800 - Exterior Wall | Repair / replace wood trim | Added $8000 for paint to match | GC | Year 1 | 26900 | 26900 |  |  | 0 |  | Added $8000 for paint to match
16 | 0200 - Site Utilities & Improvements | Parking equipment | add 10 speed bumps | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | add 10 speed bumps
20 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | inspect and repair irrigation
72 | 0800 - Exterior Wall | Repair / replace wood siding | Added $8000 for paint to match | GC | Year 1 | 25200 | 25200 |  |  | 0 |  | Added $8000 for paint to match
12 | 0200 - Site Utilities & Improvements | Storm sewer piping | Storm Jetting - Site Wide | GC | Year 1 | 25000 | 25000 |  |  | 0
113 | 1100- Specialties, Equipment & Furnishings | Signage - site | Front monument sign & lighting | Capex | Year 1 | 25000 | 29319 |  |  | N/A |  | Front monument sign & lighting
120 | 1100- Specialties, Equipment & Furnishings | Audio systems | Audio system for 2 pool areas | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Audio system for 2 pool areas
144 | 1600 - Electrical | Common area light fixtures | replace garage light fixtures | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | replace garage light fixtures
14 | 0200 - Site Utilities & Improvements | Concrete pavement | Repair | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Repair
19 | 0200 - Site Utilities & Improvements | Sidewalks | repair cracked concrete | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | repair cracked concrete
61 | 0700 - Roofing | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | inspect and replace missing or damaged shingles
114 | 1100- Specialties, Equipment & Furnishings | Signage - building identification | New signage throughout, includes logo design and all new collateral | Capex | Year 1 | 20000 | 23455 |  |  | N/A |  | New signage throughout, includes logo design and all new collateral
27 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | Pressure wash and coat pool deck in phase two | GC | Year 1 | 18900 | 18900 |  |  | 0 |  | Pressure wash and coat pool deck in phase two
55 | 0400 - Structure | Repair balcony framing & decking | Balcony Repairs | GC | Year 1 | 18500 | 18500 |  |  | 0
30 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | repair dog park and Pool fences and paint | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | repair dog park and Pool fences and paint
124 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | Install new gym floor phase 2 and paint | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Install new gym floor phase 2 and paint
76 | 0800 - Exterior Wall | Dryer Vents | Clean 256 dryer vents ($35 per) and replace (100) dryer vents | GC | Year 1 | 13960 | 13960 |  |  | 0 |  | Clean 256 dryer vents ($35 per) and replace (100) dryer vents
40 | 0200 - Site Utilities & Improvements | Carports / Garages | Repair/replace 15 garage door openers/ placeholder for purchase of openers | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Repair/replace 15 garage door openers/ placeholder for purchase of openers
83 | 0800 - Exterior Wall | Shutters | Replace missing shutters and paint to match | GC | Year 1 | 10200 | 10200 |  |  | 0 |  | Replace missing shutters and paint to match
41 | 0200 - Site Utilities & Improvements | Dog Park | Placeholder for upgrade of equipment in dog park | GC | Year 1 | 10000 | 10000 |  |  | 0% |  | Placeholder for upgrade of equipment in dog park
66 | 0700 - Roofing | Gutters & downspouts | clean and repin | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | clean and repin
125 | 1100- Specialties, Equipment & Furnishings | Golf Cart | Repair (2) golf carts- changed to 3 new golf carts | Capex | Year 1 | 10000 | 69808 |  |  | N/A |  | Repair (2) golf carts- changed to 3 new golf carts
26 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | replace deck-o-seal in both pools | GC | Year 1 | 9200 | 9200 |  |  | 0% |  | replace deck-o-seal in both pools
49 | 0400 - Structure | Wall framing | Exterior Carpentry | GC | Year 1 | 8200 | 8200 |  |  | 0
15 | 0200 - Site Utilities & Improvements | Stripe parking areas | Parking Lot Striping | GC | Year 1 | 8000 | 8000 |  |  | 0
37 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair Dumpsters and paint | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Repair Dumpsters and paint
54 | 0400 - Structure | Repair exterior stair railings | Railing Repairs | GC | Year 1 | 7000 | 7000 |  |  | 0
56 | 0400 - Structure | Repair patio/balcony railings | Patio & Balcony Railings | GC | Year 1 | 7000 | 7000 |  |  | 0
141 | 1600 - Electrical | Electrical distribution | Electrical Repairs | GC | Year 1 | 6600 | 6600 |  |  | 0
67 | 0700 - Roofing | Flashing | Roof Flashing | GC | Year 1 | 5600 | 5600 |  |  | 0
68 | 0700 - Roofing | Sealants & caulking and paint | Roof Sealants & Caulking | GC | Year 1 | 5600 | 5600 |  |  | 0
28 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | Phase 2 pool fountain repair | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Phase 2 pool fountain repair
17 | 0200 - Site Utilities & Improvements | Parking Lot | Install 27 car stops in front of iron fencing Phase 1 | GC | Year 1 | 4050 | 4050 |  |  | 0 |  | Install 27 car stops in front of iron fencing Phase 1
77 | 0800 - Exterior Wall | Tuck-pointing | Property Tuck Point Repairs | GC | Year 1 | 3800 | 3800 |  |  | 0
PROJECTS subtotal (excl. contingency/CM fee)

## Island Villas
Island Villas — 2022 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
88 | 0900 - FF&E in Units | Interior Update Placeholder | Interior Upgrades | Capex | Year 1 | 749760 | 592172 |  |  | N/A
21 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Replace wood fence and paint | GC | Year 1 | 154000 | 154000 |  |  | 0 |  | Replace wood fence and paint
23 | 0200 - Site Utilities & Improvements | Landscaping | remove dead shrubs and change entrance island shrubs, landscaping around pool and planters for 2nd pool. Installation of shrubs along perimeter fence | GC | Year 1 | 100000 | 100000 |  |  | 0 |  | remove dead shrubs and change entrance island shrubs, landscaping around pool and planters for 2nd pool. Installation of shrubs along perimeter fence
27 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | Replace pool deck w/ stamp stain concrete (main pool) and repairs to 2nd pool deck | GC | Year 1 | 80000 | 80000 |  |  | 0 |  | Replace pool deck w/ stamp stain concrete (main pool) and repairs to 2nd pool deck
66 | 0700 - Roofing | Sealants & caulking and paint | Seal all face nails in siding | GC | Year 1 | 67200 | 67200 |  |  | 0 |  | Seal all face nails in siding
22 | 0200 - Site Utilities & Improvements | Retaining walls | build retaining wall at site exit | GC | Year 1 | 60000 | 60000 |  |  | 0 |  | build retaining wall at site exit
61 | 0700 - Roofing | Cleaning Blue Algae | Treating/cleaning blue algae on roofs ($4k per building) | GC | Year 1 | 60000 | 60000 |  |  | 0 |  | Treating/cleaning blue algae on roofs ($4k per building)
117 | 1100- Specialties, Equipment & Furnishings | Security/ fire alarm systems | Placeholder for installation of cameras | Capex | Year 1 | 60000 | 30339 |  |  | N/A |  | Placeholder for installation of cameras
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Re-paint / new flooring for office | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Re-paint / new flooring for office
20 | 0200 - Site Utilities & Improvements | Erosion control | replace dirt missing due to erosion | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | replace dirt missing due to erosion
31 | 0200 - Site Utilities & Improvements | Pool Area | Install (2) pool cabanas, turf in outdoor kitchen area | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | Install (2) pool cabanas, turf in outdoor kitchen area
24 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface pool by office | GC | Year 1 | 41000 | 41000 |  |  | 0 |  | resurface pool by office
143 | 1600 - Electrical | Common area light fixtures | replace garage light fixtures and wall packs | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | replace garage light fixtures and wall packs
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | Clubhouse Upgrades | Capex | Year 1 | 35000 | 53745 |  |  | N/A
106 | 0900 - FF&E in Units | Range Queen | Firestops | Capex | Year 1 | 30240 | 0 |  |  | N/A
120 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | New gym equipment | Capex | Year 1 | 30000 | 19034 |  |  | N/A |  | New gym equipment
122 | 1100- Specialties, Equipment & Furnishings | Pool furniture | Include additional tables/sitting areas | Capex | Year 1 | 30000 | 4650 |  |  | N/A |  | Include additional tables/sitting areas
16 | 0200 - Site Utilities & Improvements | Parking equipment | add 10 speed bumps | GC | Year 1 | 28000 | 28000 |  |  | 0 |  | add 10 speed bumps
38 | 0200 - Site Utilities & Improvements | Carports / Garages | Replace 6 garage doors and paint garages | GC | Year 1 | 28000 | 28000 |  |  | 0 |  | Replace 6 garage doors and paint garages
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | inspect and repair irrigation
110 | 1100- Specialties, Equipment & Furnishings | Signage - entry | New Monument Sign at corner | Capex | Year 1 | 25000 | 7329 |  |  | N/A |  | New Monument Sign at corner
123 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | Remove wall to enlarge gym area & install flooring/paint | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Remove wall to enlarge gym area & install flooring/paint
70 | 0800 - Exterior Wall | Repair / replace wood siding | Added $8000 for paint to match | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Added $8000 for paint to match
80 | 0800 - Exterior Wall | Repair / replace wood trim | Added $7500 for paint to match | GC | Year 1 | 22500 | 22500 |  |  | 0 |  | Added $7500 for paint to match
18 | 0200 - Site Utilities & Improvements | Sidewalks | repair cracked concrete | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | repair cracked concrete
59 | 0700 - Roofing | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | inspect and replace missing or damaged shingles
53 | 0400 - Structure | Repair balcony framing & decking | Fill cracks in decking | GC | Year 1 | 18500 | 18500 |  |  | 0 |  | Fill cracks in decking
14 | 0200 - Site Utilities & Improvements | Concrete pavement | Repair | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Repair
29 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | repair dog park and Pool fences and paint | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | repair dog park and Pool fences and paint
12 | 0200 - Site Utilities & Improvements | Storm sewer piping | Sewer Pipe Repairs | GC | Year 1 | 16000 | 16000 |  |  | 0
140 | 1600 - Electrical | Electrical distribution | repair outside GFCI'S | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | repair outside GFCI'S
111 | 1100- Specialties, Equipment & Furnishings | Signage - site | Bldg ID signs, common area signage | Capex | Year 1 | 15000 | 4397 |  |  | N/A |  | Bldg ID signs, common area signage
118 | 1100- Specialties, Equipment & Furnishings | Audio systems | Speaker system for main pool area | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Speaker system for main pool area
15 | 0200 - Site Utilities & Improvements | Stripe parking areas | Includes $5k for painting curbs at closing | GC | Year 1 | 13000 | 13000 |  |  | 0% |  | Includes $5k for painting curbs at closing
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair Dumpsters and paint | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Repair Dumpsters and paint
64 | 0700 - Roofing | Gutters & downspouts | replace missing elbows and splash blocks | GC | Year 1 | 12000 | 12000 |  |  | 0% |  | replace missing elbows and splash blocks
74 | 0800 - Exterior Wall | Dryer Vents | clean all dryer vents | GC | Year 1 | 11760 | 11760 |  |  | 0% |  | clean all dryer vents
81 | 0800 - Exterior Wall | Shutters | Added $3000 for paint to match | GC | Year 1 | 10200 | 10200 |  |  | 0 |  | Added $3000 for paint to match
25 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | replace deck-o-seal in both pools | GC | Year 1 | 9600 | 9600 |  |  | 0 |  | replace deck-o-seal in both pools
52 | 0400 - Structure | Repair exterior stair railings | Minor repairs to balconies | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | Minor repairs to balconies
54 | 0400 - Structure | Repair patio/balcony railings | resecure | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | resecure
65 | 0700 - Roofing | Flashing | Roof Flashing Repairs | GC | Year 1 | 5600 | 5600 |  |  | 0
47 | 0400 - Structure | Wall framing | Exterior Carpentry | GC | Year 1 | 5000 | 5000 |  |  | 0
PROJECTS subtotal (excl. contingency/CM fee)

## Amalfi at Tuscan Lakes
Amalfi at Tuscan Lakes — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
88 | 84207 | Unit Upgrades - Unit type 1, 2 & 3 Beds | 773sqft, 1BR 1BA | GC | Year 1 | 1679634 | 1540512 |  |  | 1 |  | 773sqft, 1BR 1BA
77 |  | Exterior building | Paint community | GC | Year 1 | 328000 | 328000 |  |  | 0 |  | Paint community
23 | 83303 | Landscaping | Landscaping for curb and pool (place Holder) | GC | Year 1 | 150000 | 150000 |  |  | 0 |  | Landscaping for curb and pool (place Holder)
131 |  | Pool Remodel | New vertical tile on side of pool wall to replace aged blue Fire pit in raised area if feasible New grill area with counters and pergola above the fountain pool Repair existing pergola, add fully covered section Add big ass fan under covered area Add 1-2 corn hole sets | GC | Year 1 | 100000 | 100000 |  |  | 0 |  | New vertical tile on side of pool wall to replace aged blue Fire pit in raised area if feasible New grill area with counters and pergola above the fountain pool Repair existing pergola, add fully cov
100 |  | Ceiling Fans | Add to all living rooms | GC | Year 1 | 90200 | 90200 |  |  | 0 |  | Add to all living rooms
124 |  | Clubhouse / Office Redecorate (FFE) | Clubhouse upgrades | Capex | Year 1 | 80000 | 63309 |  |  | N/A
21 | 83205 | Fences & gates - site perimeter | Remove vines, repair fence and paint fence | GC | Year 1 | 60000 | 60000 |  |  | 0 |  | Remove vines, repair fence and paint fence
24 | 83100 | Resurface swimming pool | Resurface pool, Replace tile | GC | Year 1 | 58000 | 58000 |  |  | 0 |  | Resurface pool, Replace tile
123 |  | Clubhouse / Office Remodel | Replace carpet tile, some paint and finish refresh | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Replace carpet tile, some paint and finish refresh
154 |  | Replace breezeway lights | Replace breezeway, Garage and landscaping lights | GC | Year 1 | 49860 | 49860 |  |  | 0 |  | Replace breezeway, Garage and landscaping lights
26 | 83100 | Replace swimming pool deck | Clean and recoat pool deck | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | Clean and recoat pool deck
133 |  | Pool furniture | New furniture for pool, repurpose and re-sling existing and move to Sorrento | Capex | Year 1 | 45000 | 28892 |  |  | N/A |  | New furniture for pool, repurpose and re-sling existing and move to Sorrento
153 |  | Common area light fixtures | Replace all wall packs | GC | Year 1 | 38640 | 38640 |  |  | 0 |  | Replace all wall packs
19 | 83300 | Landscape irrigation | inspect and repair irrigation | GC | Year 1 | 34000 | 34000 |  |  | 0 |  | inspect and repair irrigation
34 | 83219 | Carport and garage | Repair carport damage and paint | GC | Year 1 | 29000 | 29000 |  |  | 0 |  | Repair carport damage and paint
79 |  | Shutters | Replace bad shutters | GC | Year 1 | 28000 | 28000 |  |  | 0 |  | Replace bad shutters
149 |  | Dryer Vent cleaning | Dryer Vent Cleaning | GC | Year 1 | 24600 | 24600 |  |  | 0
58 | 83202 | Asphalt composite shingle roofing | minor roof repairs | GC | Year 1 | 23000 | 23000 |  |  | 0 |  | minor roof repairs
63 | 83439 | Gutters & downspouts | Clean down spouts and gutters | GC | Year 1 | 23000 | 23000 |  |  | 0 |  | Clean down spouts and gutters
76 |  | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | GC | Year 1 | 23000 | 23000 |  |  | 0 |  | Repair soffit on breezeways patios and balconies
78 |  | Repair / replace wood trim | Wood Trim Repairs | GC | Year 1 | 23000 | 23000 |  |  | 0
25 | 83100 | Replace swimming pool coping | Replace deck-o-seal on pool and repair coping | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | Replace deck-o-seal on pool and repair coping
75 |  | Repair stucco | Stucco Repairs | GC | Year 1 | 20000 | 20000 |  |  | 0
127 |  | Mailboxes | Package locker or Fetch system needed | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Package locker or Fetch system needed
129 |  | Security Camera System | Need at least for entry drive, clubhouse, and amenity coverage | Capex | Year 1 | 20000 | 7426 |  |  | N/A |  | Need at least for entry drive, clubhouse, and amenity coverage
152 |  | Fire and Sprinklers | replace emergency lights | GC | Year 1 | 18560 | 18560 |  |  | 0 |  | replace emergency lights
14 | 83221 | Concrete pavement | Concrete Repairs | GC | Year 1 | 18000 | 18000 |  |  | 0
30 | 83206 | Pergola | repair and stain all pergola | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | repair and stain all pergola
53 | 83104 | Repair balcony framing & decking | repair balcony band boards | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | repair balcony band boards
65 | 83206 | Sealants & caulking | Roof Sealants & Caulking | GC | Year 1 | 18000 | 18000 |  |  | 0
132 |  | Fitness Equipment | 2 Ellipticals, other allowance for repairs and new equipment | Capex | Year 1 | 18000 | 11961 |  |  | N/A |  | 2 Ellipticals, other allowance for repairs and new equipment
15 | 83201 | Stripe parking areas | Parking Lot Striping | GC | Year 1 | 16000 | 16000 |  |  | 0
35 | 83111 | Dumpster enclosures | Repair dumpster enclosures | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Repair dumpster enclosures
55 | 83206 | Expansion Joints | clean and seal expansion joints | GC | Year 1 | 15000 | 15000 |  |  | 0% |  | clean and seal expansion joints
128 |  | Fountain area Remodel | Address planter- either fill with rocks or fix irrigation Look at cabanas or shade over benches by reflecting pond Lock breaker panel under cabana | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Address planter- either fill with rocks or fix irrigation Look at cabanas or shade over benches by reflecting pond Lock breaker panel under cabana
70 |  | Repair / replace cement fiber siding | repair damaged siding | GC | Year 1 | 10000 | 10000 |  |  | 0% |  | repair damaged siding
134 |  | Fitness center renovation | Add mirrors, 1-2 TVs | GC | Year 1 | 10000 | 10000 |  |  | 0% |  | Add mirrors, 1-2 TVs
29 | 83205 | Fences & gates - swimming pool | Repair and paint pool fence | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | Repair and paint pool fence
151 |  | Electrical distribution | Electrical Repairs | GC | Year 1 | 8500 | 8500 |  |  | 0
52 | 83114 | Repair exterior stair railings | secure railings | GC | Year 1 | 8300 | 8300 |  |  | 0 |  | secure railings
54 | 83114 | Repair patio/balcony railings | secure railings | GC | Year 1 | 8300 | 8300 |  |  | 0 |  | secure railings
130 |  | EV Chargers | Likely will be no-cost to property, but providing allowance | PMC | Year 1 | 8000 | 0 |  |  | N/A |  | Likely will be no-cost to property, but providing allowance
135 |  | Golf Cart | Utility/Maintenance Cart | PMC | Year 1 | 8000 | 0 |  |  | N/A |  | Utility/Maintenance Cart
17 | 83520 | ADA parking & curb cuts | ADA Parking Repairs | GC | Year 1 | 6500 | 6500 |  |  | 0
125 |  | Model Unit | Allowance for small additions/refresh | PMC | Year 1 | 4000 | 8256 |  |  | N/A |  | Allowance for small additions/refresh
126 |  | Computers | Not needed, allowance for 1 | PMC | Year 1 | 1500 | 1817 |  |  | N/A |  | Not needed, allowance for 1
PROJECTS subtotal (excl. contingency/CM fee)
158 |  | Construction Management Fee |  | CMF | Contingency | 171121 | 0 | 171121 |  | N/A
157 |  | Contingency |  | CON | Contingency | 108322 | 0 | 108322 |  | N/A

## Avila
Avila — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
67 | 0800 - Exterior Wall | Exterior building | changed to Paint the total community 100% paintable | GC | Year 1 | 400000 | 400000 |  |  | 0
12 | 0200 - Site Utilities & Improvements | Pavement | Large areas of asphalt paving, speed bump repair Includes $2,500 in lender mandates- The asphalt pavement has localized potholes, and deterioration. These asphalt potholes were observed by the clubhouse, maintenance shop, ingress, and egress on the northeast side, and buildings #14, #15, #16, #17, #22, and #3. | GC | Year 1 | 150000 | 150000 |  |  | 0
76 | 1100- Specialties, Equipment & Furnishings | Picnic Area Renovation | Add turf soccer field with goals and playground structure on one side. Add pavilion near picnic area, resurface remaining old tennis court area with pavers (where there are fire pits or eating areas and turf (where the activity areas are). Move both corn hole sets to turf area. Relocate fire pit from future soccer area to be near other fire pit, remove benches around fire pits, add chairs. | GC | Year 1 | 150000 | 150000 |  |  | 0
14 | 0200 - Site Utilities & Improvements | Asphalt coating | Seal coat lot | GC | Year 1 | 98000 | 98000 |  |  | 0
37 | 0300 - Excavation & Foundations | Jack & underpin foundations | Foundation in three buildings | GC | Year 1 | 72000 | 72000 |  |  | 0
58 | 0800 - Exterior Wall | Repair / replace wood siding | Replace damaged t 11 siding Increase cost by 30000 in lower window walls and hip walls | GC | Year 1 | 66000 | 66000 |  |  | 0
17 | 0200 - Site Utilities & Improvements | Landscape irrigation | Inspect and repair irrigation Increased by 20000 due to amount of issues with Irrigation | GC | Year 1 | 49000 | 49000 |  |  | 0
10 | 0200 - Site Utilities & Improvements | Storm sewer piping | Clear drainage lines increase by 15,000 due to areas of bad water flow ( water infiltration into ground floor units ) | GC | Year 1 | 38800 | 38800 |  |  | 0
87 | 1600 - Electrical | Common area light fixtures | Replace building Wall Packs with LED | GC | Year 1 | 32400 | 32400 |  |  | 0
33 | 0200 - Site Utilities & Improvements | Carport and garage | repair and paint | GC | Year 1 | 31000 | 31000 |  |  | 0
18 | 0200 - Site Utilities & Improvements | Erosion control |  | GC | Year 1 | 30000 | 30000 |  |  | 0
44 | 0400 - Structure | Repair exterior stair treads and stringers | replace bad stair treads | GC | Year 1 | 30000 | 30000 |  |  | 0
45 | 0400 - Structure | Repair exterior stair railings | Repair and Paint | GC | Year 1 | 30000 | 30000 |  |  | 0
78 | 1100- Specialties, Equipment & Furnishings | Old Pool House by Pool 1 (West) | Convert pool house to rentable party space, new sliding doors | GC | Year 1 | 30000 | 30000 |  |  | 0
68 | 0800 - Exterior Wall | Repair / replace wood trim |  | GC | Year 1 | 28000 | 28000 |  |  | 0
72 | 0900 - FF&E in Units | Fire protection | Clean drier vents | GC | Year 1 | 24525 | 24525 |  |  | 0 |  | 327
49 | 0700 - Roofing | Asphalt composite shingle roofing | Minor roof repairs | GC | Year 1 | 23000 | 23000 |  |  | 0
54 | 0700 - Roofing | Gutters & downspouts | Clean gutters | GC | Year 1 | 23000 | 23000 |  |  | 0
63 | 0800 - Exterior Wall | Tuck-pointing | Tuck point and caulk | GC | Year 1 | 23000 | 23000 |  |  | 0
86 | 1600 - Electrical | Electrical distribution | Repair lighting Electric and anchor weather heads increase weather head repairs by 10,000 due to more locations | GC | Year 1 | 22800 | 22800 |  |  | 0
34 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair dumpster enclosures | GC | Year 1 | 21000 | 21000 |  |  | 0
46 | 0400 - Structure | Repair balcony framing & decking |  | GC | Year 1 | 20000 | 20000 |  |  | 0
69 | 0800 - Exterior Wall | storage room doors - exterior | Replace damaged storage room doors | GC | Year 1 | 20000 | 20000 |  |  | 0
80 | 1100- Specialties, Equipment & Furnishings | Dog Park | Add dog park fencing (no jumps), signage, & wash station | GC | Year 1 | 20000 | 20000 |  |  | 0
39 | 0400 - Structure | Concrete deck / floor fill | entrance landings | GC | Year 1 | 18000 | 18000 |  |  | 0
75 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) |  | GC | Year 1 | 15000 | 15000 |  |  | 0
20 | 0200 - Site Utilities & Improvements | Retaining walls | Repair cracks in retaining walls Includes $3,000 in lender mandates- The railroad tie retaining wall located on the west side exhibits rot and deterioration. | GC | Year 1 | 14000 | 14000 |  |  | 0
13 | 0200 - Site Utilities & Improvements | Stripe parking areas | Restripe lot, repaint curbs and fire lanes | GC | Year 1 | 13000 | 13000 |  |  | 0
55 | 0700 - Roofing | Flashing | Increase by 10,000 for Kickout flashing at hip walls | GC | Year 1 | 11000 | 11000 |  |  | 0
77 | 1100- Specialties, Equipment & Furnishings | Pool 1 (West) Renovation | Turf grass areas | GC | Year 1 | 10000 | 10000 |  |  | 0
27 | 0200 - Site Utilities & Improvements | Fences & gates | repair and paint Includes $2,000 in lender mandates- The metal panels fencing on the west side of the property was observed to be damaged. | GC | Year 1 | 9600 | 9600 |  |  | 0
23 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Deck o seal | GC | Year 1 | 8600 | 8600 |  |  | 0
16 | 0200 - Site Utilities & Improvements | Sidewalks | Lender Mandate- Several of the Subject's concrete sidewalk sections have settled or heaved over the years causing tripping hazards. Such sections were observed by the swimming pool, clubhouse, and buildings #17, #10, #1, #16, #2, #15, #19, #20, #14, and #23. | GC | Year 1 | 8400 | 8400 |  |  | 0
56 | 0700 - Roofing | Sealants & caulking and paint |  | GC | Year 1 | 7500 | 7500 |  |  | 0%
15 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts | Replace ADA signage | GC | Year 1 | 6800 | 6800 |  |  | 0
25 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | anti entrapment devices | GC | Year 1 | 6800 | 6800 |  |  | 0%
47 | 0400 - Structure | Repair patio/balcony railings | secure railings | GC | Year 1 | 6500 | 6500 |  |  | 0%
79 | 1100- Specialties, Equipment & Furnishings | Pool 2 (East) Renovation | Repair wood fence at pump house, Remove rock and art in red brick planter, replace with turf, Repair grill counter, Repaint black grill face | GC | Year 1 | 5000 | 5000 |  |  | 0
35 | 0200 - Site Utilities & Improvements | Maintenance Structure | Lender Mandate- The batt insulation of the maintenance shop was observed to be damaged and in poor condition. | GC | Year 1 | 2500 | 2500 |  |  | 0
40 | 0400 - Structure | Wall framing |  | GC | Year 1 | 1500 | 1500 |  |  | 0
71 | 0900 - FF&E in Units | Unit Repair | Lender Mandate- The ceiling tiles of units #111 and #2211 were observed to be stained. Replacing the stained ceiling tiles is recommended at this time. Also, the ceiling drywall of unit #212 was observed to be damaged. Replacing the damaged ceiling is recommended at this time. | GC | Year 1 | 1500 | 1500 |  |  | 0
11 | 0200 - Site Utilities & Improvements | Parking Equipment- wheel stops | Lender Mandate- At the time of the site visit, some concrete wheel stops were observed to be damaged. Such damaged wheel stops were observed next to buildings #16 and #10. | GC | Year 1 | 750 | 750 |  |  | 0
PROJECTS subtotal (excl. contingency/CM fee)

## Collin Creek
Collin Creek — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
90 | 0900 - FF&E in Units | Interior Update- Classic to Gold | Test smaller initial qty | Capex | Year 1 | 500000 | 255167 |  |  | N/A |  | Test smaller initial qty |  | Completed
91 | 0900 - FF&E in Units | Interior Update- Silver to Gold | Test smaller initial qty | Capex | Year 1 | 450000 | 229651 |  |  | N/A |  | Test smaller initial qty |  | Completed
80 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Year 1 | 320000 | 320000 |  |  | 0 |  | Paint community
42 | 0300 - Excavation & Foundations | Foundations | Additional scope identified by TAM | GC | Year 1 | 172728 | 172728 |  |  | 0 |  | Additional scope identified by TAM
41 | 0300 - Excavation & Foundations | Jack & underpin foundations | Place holder for 5 building that show signs of foundation movement | GC | Year 1 | 150000 | 150000 |  |  | 0 |  | Place holder for 5 building that show signs of foundation movement
22 | 0200 - Site Utilities & Improvements | Retaining walls | Replace railroad tie retaining walls | GC | Year 1 | 120000 | 120000 |  |  | 0 |  | Replace railroad tie retaining walls
23 | 0200 - Site Utilities & Improvements | Landscaping | Trim Trees and sod building with erosion | GC | Year 1 | 72000 | 72000 |  |  | 0 |  | Trim Trees and sod building with erosion
28 | 0200 - Site Utilities & Improvements | Replace swimming pool deck- Primary pool | New decking to replace aggregate | GC | Year 1 | 70000 | 70000 |  |  | 0 |  | New decking to replace aggregate
135 | 1100- Specialties, Equipment & Furnishings | Package lockers | Luxer one- from Texas Package Solutions | Capex | Year 1 | 70000 | 0 |  |  | N/A |  | Luxer one- from Texas Package Solutions
81 | 0800 - Exterior Wall | Repair / replace wood trim | Exterior Carpentry | GC | Year 1 | 51000 | 51000 |  |  | 0
48 | 0400 - Structure | Wall framing | Replace damaged gable vents and balcony structure | GC | Year 1 | 43000 | 43000 |  |  | 0 |  | Replace damaged gable vents and balcony structure
130 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | New exterior windows New flooring-rubber tiles Paint Ventilation/fans Electrical to doors for key Relocate TV above aerobic units Hide TV cables | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | New exterior windows New flooring-rubber tiles Paint Ventilation/fans Electrical to doors for key Relocate TV above aerobic units Hide TV cables
14 | 0200 - Site Utilities & Improvements | Concrete pavement | repair pot holes and broken sidewalks | GC | Year 1 | 39000 | 39000 |  |  | 0 |  | repair pot holes and broken sidewalks
60 | 0700 - Roofing | Asphalt composite shingle roofing | minor roof repairs | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | minor roof repairs
127 | 1100- Specialties, Equipment & Furnishings | Pool enhancements- Primary Pool | 110 & 55 sqft of turf 2 corn hole boards w/custom logo chess/checkers shade structure Budget | Capex | Year 1 | 36000 | 2899 |  |  | N/A |  | 110 & 55 sqft of turf 2 corn hole boards w/custom logo chess/checkers shade structure Budget |  | Not Started
123 | 1100- Specialties, Equipment & Furnishings | Gym Fitness Equipment | Upgraded package from Comm FIT, Basic also available fo $20k | Capex | Year 1 | 34000 | 13734 |  |  | N/A |  | Upgraded package from Comm FIT, Basic also available fo $20k |  | Completed
20 | 0200 - Site Utilities & Improvements | Erosion control | Site Wide Erosion Control | GC | Year 1 | 31000 | 31000 |  |  | 0
26 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface pool | GC | Year 1 | 31000 | 31000 |  |  | 0 |  | resurface pool
128 | 1100- Specialties, Equipment & Furnishings | Pool enhancements- Secondary Pool | New grill New fire pit Convert planters next to pool to turf or pavers | Capex | Year 1 | 30000 | 2415 |  |  | N/A |  | New grill New fire pit Convert planters next to pool to turf or pavers |  | Not Started
110 | 0900 - FF&E in Units | Range Queen | Stove Replacements | GC | Year 1 | 29830 | 29830 |  |  | 0
155 | 1600 - Electrical | Common area light fixtures | Lighting Upgrades | GC | Year 1 | 29000 | 29000 |  |  | 0
18 | 0200 - Site Utilities & Improvements | Sidewalks | Sidewalk Trip Hazards | GC | Year 1 | 26000 | 26000 |  |  | 0
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | inspect and repair irrigation
156 | 1600 - Electrical | Replace breezeway lights | Replace Breezeway Lights | GC | Year 1 | 26000 | 26000 |  |  | 0
51 | 0400 - Structure | Roof deck | replace bad decking on roofs | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | replace bad decking on roofs
125 | 1100- Specialties, Equipment & Furnishings | Pool furniture- Primary Pool | Pool Furniture | Capex | Year 1 | 25000 | 27009 |  |  | N/A
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Dumpster enclosures are scrubs replace with fencing and repair gates | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | Dumpster enclosures are scrubs replace with fencing and repair gates
24 | 0200 - Site Utilities & Improvements | Landscaping- Primary pool area | Turf or other plants instead of brown mulch and boxwood hedges in planters | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Turf or other plants instead of brown mulch and boxwood hedges in planters
65 | 0700 - Roofing | Gutters & downspouts | Clean down spouts and gutters | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Clean down spouts and gutters
134 | 1100- Specialties, Equipment & Furnishings | Dog Park entrance area | Convert entry area to concrete. Adjust entry level to avoid erosion/wash out and raise gate to avoid contact with ground | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | Convert entry area to concrete. Adjust entry level to avoid erosion/wash out and raise gate to avoid contact with ground
76 | 0800 - Exterior Wall | Tuck-pointing |  | GC | Year 1 | 14000 | 14000 |  |  | 0
57 | 0400 - Structure | Expansion joints | clean and seal expansion joints | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | clean and seal expansion joints
72 | 0800 - Exterior Wall | Repair / replace cement fiber siding | repair damaged siding | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | repair damaged siding
124 | 1100- Specialties, Equipment & Furnishings | Gym Flooring | Fitdek 8mm roll with install- Quotation # S07142 from Comm FIT | Capex | Year 1 | 11000 | 1957 |  |  | N/A |  | Fitdek 8mm roll with install- Quotation # S07142 from Comm FIT |  | Not Started
136 | 1100- Specialties, Equipment & Furnishings | Sport court surfacing |  | GC | Year 1 | 11000 | 11000 |  |  | 0
25 | 0200 - Site Utilities & Improvements | Landscaping- Secondary pool area | Areas by pool- new sod | GC | Year 1 | 10000 | 10000 |  |  | 0% |  | Areas by pool- new sod
39 | 0200 - Site Utilities & Improvements | Radon Remediation from lender report | Radon mitigation should be completed by a Texas-licensed contractor. When radon remains elevated over the EPA Action Level, the ground floor units within that particular building (#s 3, 9, 18 and 19) with radon concerns would require mitigation. This is usually accomplished by installing one or more sub-slab depressurization systems at that building to vent the radon gas to the outside (rather than letting it build up inside the apartment building). This engineered system is rather simple in construction. The industry cost is estimated at $2,000 per unit. Typically, the contractor will conduct testing to determine if the entire building should be addressed or just the elevated unit. They will also conduct a walk-through of the units to be able to provide a cost estimate for services. Oftentimes a good mitigation company can design a system that will address more than one apartment unit. | Capex | Year 1 | 10000 | 40580 |  |  | N/A |  | Radon mitigation should be completed by a Texas-licensed contractor. When radon remains elevated over the EPA Action Level, the ground floor units within that particular building (#s 3, 9, 18 and 19)
34 | 0200 - Site Utilities & Improvements | Playground equipment | Replace Fall zone in play ground | GC | Year 1 | 9800 | 9800 |  |  | 0 |  | Replace Fall zone in play ground
54 | 0400 - Structure | Repair balcony framing & decking | repair balcony band boards | GC | Year 1 | 9700 | 9700 |  |  | 0 |  | repair balcony band boards
15 | 0200 - Site Utilities & Improvements | Stripe parking areas | Parking Lot Striping | GC | Year 1 | 9500 | 9500 |  |  | 0
67 | 0700 - Roofing | Sealants & caulking and paint | Roofing Sealants & Caulking | GC | Year 1 | 9000 | 9000 |  |  | 0
35 | 0200 - Site Utilities & Improvements | Picnic areas | replace 2 grills | GC | Year 1 | 8800 | 8800 |  |  | 0 |  | replace 2 grills
12 | 0200 - Site Utilities & Improvements | Storm sewer piping | clean out storm drain boxes | GC | Year 1 | 8600 | 8600 |  |  | 0 |  | clean out storm drain boxes
27 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Replace deck-o-seal on pool | GC | Year 1 | 8600 | 8600 |  |  | 0 |  | Replace deck-o-seal on pool
137 | 1100- Specialties, Equipment & Furnishings | Gym hallway & Restrooms | Paint Toilets/fixtures New cove base Base | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Paint Toilets/fixtures New cove base Base
78 | 0800 - Exterior Wall | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | GC | Year 1 | 6800 | 6800 |  |  | 0 |  | Repair soffit on breezeways patios and balconies
17 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts |  | GC | Year 1 | 6500 | 6500 |  |  | 0
129 | 1100- Specialties, Equipment & Furnishings | Pool area lighting fixtures | Update pole lighting- new fixtures on top and straighten poles | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Update pole lighting- new fixtures on top and straighten poles
153 | 1600 - Electrical | Electrical distribution |  | GC | Year 1 | 6000 | 6000 |  |  | 0
31 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair and paint pool fences | GC | Year 1 | 5600 | 5600 |  |  | 0 |  | Repair and paint pool fences
133 | 1100- Specialties, Equipment & Furnishings | Dog Park upgrades | Move square dog jump paint jumps Wash station for dogs | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Move square dog jump paint jumps Wash station for dogs
53 | 0400 - Structure | Repair exterior stair railings | secure railings | GC | Year 1 | 4200 | 4200 |  |  | 0 |  | secure railings
55 | 0400 - Structure | Repair patio/balcony railings | secure railings | GC | Year 1 | 4200 | 4200 |  |  | 0 |  | secure railings
32 | 0200 - Site Utilities & Improvements | Pergola | repair and stain all pergola | GC | Year 1 | 3100 | 3100 |  |  | 0 |  | repair and stain all pergola
132 | 1100- Specialties, Equipment & Furnishings | Laundry room furniture | Furniture in waiting area | PMC | Year 1 | 2000 | 0 |  |  | N/A |  | Furniture in waiting area
131 | 1100- Specialties, Equipment & Furnishings | Laundry room | Built in table instead of floating tables Replace broken window | GC | Year 1 | 1500 | 1500 |  |  | 0 |  | Built in table instead of floating tables Replace broken window
PROJECTS subtotal (excl. contingency/CM fee)
161 | Contingency | Contingency- Unit Upgrades |  | CON | Contingency | 610000 | 0 | 610000 |  | N/A
159 | Contingency | Contingency- Deferred Maintenance |  | CON | Contingency | 290000 | 0 | 290000 |  | N/A
160 | Contingency | Contingency- Amenities |  | CON | Contingency | 104542 | 0 | 104542 |  | N/A

## Las Colinas Heights
Las Colinas Heights — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
109 | 0900 - FF&E in Units | PFC Units | Unit Upgrades | Capex | Year 1 | 1600000 | 0 |  |  | N/A
93 | 0900 - FF&E in Units | Platinum upgrades | Unit Upgrades | Capex | Year 1 | 650000 | 886629 |  |  | N/A
83 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Year 1 | 595000 | 595000 |  |  | 0 |  | Paint community
42 | 0200 - Site Utilities & Improvements | Las Colinas Association Estoppel Repairs | See list on separate tab | GC | Year 1 | 330550 | 330550 |  |  | 0 |  | See list on separate tab
12 | 0200 - Site Utilities & Improvements | Storm sewer piping | clear storm drains, repair drains around pool two, clean and service lift pumps, install drainage is sub-terrain units | GC | Year 1 | 225000 | 225000 |  |  | 0 |  | clear storm drains, repair drains around pool two, clean and service lift pumps, install drainage is sub-terrain units
45 | 0300 - Excavation & Foundations | Jack & underpin foundations | Buildings 5,11,14,21,19,36,24,6,9,13,19,26 From PCA- $5,000- The foundation exhibits settlement/step cracking in the exterior walls of building #13. | GC | Year 1 | 199985 | 199985 |  |  | 0 |  | Buildings 5,11,14,21,19,36,24,6,9,13,19,26 From PCA- $5,000- The foundation exhibits settlement/step cracking in the exterior walls of building #13. | [5 empty] | 2024-03-30
29 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | Remove and replace pool deck on two of four pools add missing expansion boards on remaining two pools | GC | Year 1 | 160000 | 160000 |  |  | 0 |  | Remove and replace pool deck on two of four pools add missing expansion boards on remaining two pools
43 | 0200 - Site Utilities & Improvements | Creek | Clean, and service fountain's in creek | GC | Year 1 | 100000 | 100000 |  |  | 0 |  | Clean, and service fountain's in creek
145 | 1100- Specialties, Equipment & Furnishings | Pool area amenities- 2 pools | Pool Upgrades | Capex | Year 1 | 100000 | 4808 |  |  | N/A
14 | 0200 - Site Utilities & Improvements | Concrete pavement | Repair concrete drive From PCA- $3,750- Isolated sections of the concrete pavement were observed to be cracked, settled, or spalled. The damaged concrete sections were observed at ingress and egress, the property entrance, by buildings #2, #7, #8, #10, #14, and #20. | GC | Year 1 | 94000 | 94000 |  |  | 0 |  | Repair concrete drive From PCA- $3,750- Isolated sections of the concrete pavement were observed to be cracked, settled, or spalled. The damaged concrete sections were observed at ingress and egress, | [5 empty] | 2024-03-30
19 | 0200 - Site Utilities & Improvements | Sidewalks | replace missing expansion boards in sidewalks From PCA- $7,000- Several of the Subject's concrete sidewalk sections have settled or heaved over the years causing tripping hazards. These damaged sections were observed by laundry rooms, swimming pools, unit #666, buildings #6, #9, #14, #19, #20, #23, #24, and #28. | GC | Year 1 | 75000 | 75000 |  |  | 0 |  | replace missing expansion boards in sidewalks From PCA- $7,000- Several of the Subject's concrete sidewalk sections have settled or heaved over the years causing tripping hazards. These damaged secti | [5 empty] | 2023-06-29
65 | 0700 - Roofing | Tile roofing | remove and reset or replace clay tiles on 30 buildings | GC | Year 1 | 65000 | 65000 |  |  | 0 |  | remove and reset or replace clay tiles on 30 buildings
27 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface two of four pools | GC | Year 1 | 61000 | 61000 |  |  | 0 |  | resurface two of four pools
21 | 0200 - Site Utilities & Improvements | Erosion control | add dirt around each building | GC | Year 1 | 60000 | 60000 |  |  | 0 |  | add dirt around each building
22 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Repair fence, columns and paint From PCA- $1,000- The concrete fencing on the southwest side was observed to be damaged. | GC | Year 1 | 51300 | 51300 |  |  | 0 |  | Repair fence, columns and paint From PCA- $1,000- The concrete fencing on the southwest side was observed to be damaged. | [5 empty] | 2024-03-30
36 | 0200 - Site Utilities & Improvements | WDO Treatment | From PCA- Subsequent to the Site Visit a WDO inspection was conducted by Terminix Commercial on 2/3/23. Evidence of active and previous subterranean termite activity was found. at various locations throughout the site. A proposal was submitted for treatment. | Capex | Year 1 | 51112 | 15586 |  |  | N/A |  | From PCA- Subsequent to the Site Visit a WDO inspection was conducted by Terminix Commercial on 2/3/23. Evidence of active and previous subterranean termite activity was found. at various locations th | [5 empty] | 2024-03-30
129 | 0900 - FF&E in Units | Range Queen | Fire stops | GC | Year 1 | 50985 | 50985 |  |  | 0 |  | Fire stops
143 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Fitness Upgrades | Capex | Year 1 | 50000 | 50321 |  |  | N/A
20 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | inspect and repair irrigation
80 | 0800 - Exterior Wall | Repair stucco | repair cracked stucco | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | repair cracked stucco
84 | 0800 - Exterior Wall | Repair / replace wood trim | From PCA- $1,000- The wood siding at buildings #10 and #12 was observed to be damaged. | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | From PCA- $1,000- The wood siding at buildings #10 and #12 was observed to be damaged. | [5 empty] | 2024-03-30
26 | 0200 - Site Utilities & Improvements | Landscaping | Tree trim | GC | Year 1 | 42000 | 42000 |  |  | 0 |  | Tree trim
170 | 1600 - Electrical | Replace breezeway lights | change breezeway lights to LED | GC | Year 1 | 42000 | 42000 |  |  | 0 |  | change breezeway lights to LED
137 | 1100- Specialties, Equipment & Furnishings | Clubhouse Furniture | Clubhouse Furniture Upgrades | Capex | Year 1 | 40000 | 2946 |  |  | N/A
144 | 1100- Specialties, Equipment & Furnishings | Pool furniture | To include installation of cabanas | Capex | Year 1 | 40000 | 0 |  |  | N/A |  | To include installation of cabanas
41 | 0200 - Site Utilities & Improvements | Carports / Garages | repair Car ports From PCA- $750- The metal carport by building #12 was observed to be damaged. | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | repair Car ports From PCA- $750- The metal carport by building #12 was observed to be damaged. | [5 empty] | 2024-03-30
169 | 1600 - Electrical | Common area light fixtures | Change all 8 ft pole lights to LED | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | Change all 8 ft pole lights to LED
25 | 0200 - Site Utilities & Improvements | Retaining walls | repair cracks in retaining walls From PCA- $1,000- The retaining walls are in generally good condition, but there are sections by buildings #10 and #4 that appear to be failing. In order to prevent further deterioration | GC | Year 1 | 35600 | 35600 |  |  | 0 |  | repair cracks in retaining walls From PCA- $1,000- The retaining walls are in generally good condition, but there are sections by buildings #10 and #4 that appear to be failing. In order to prevent fu | [5 empty] | 2024-03-30
141 | 1100- Specialties, Equipment & Furnishings | Audio systems | Audio Visual Upgrades | Capex | Year 1 | 30000 | 0 |  |  | N/A
155 | 1400 - Plumbing | Plumbing- General | 6 buildings with leaks | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | 6 buildings with leaks
50 | 0400 - Structure | Concrete deck / floor fill | fill cracks in breezeways | GC | Year 1 | 29000 | 29000 |  |  | 0 |  | fill cracks in breezeways
55 | 0400 - Structure | Repair exterior stair treads and stringers | Stair Repairs | GC | Year 1 | 29000 | 29000 |  |  | 0
68 | 0700 - Roofing | Gutters & downspouts | clean and repin From PCA- $2,000- some of the metal gutters and the metal leaders of building #26 were observed to be damaged. | GC | Year 1 | 29000 | 29000 |  |  | 0 |  | clean and repin From PCA- $2,000- some of the metal gutters and the metal leaders of building #26 were observed to be damaged. | [5 empty] | 2024-03-30
77 | 0800 - Exterior Wall | Soffit repairs | repair damaged soffits | GC | Year 1 | 29000 | 29000 |  |  | 0% |  | repair damaged soffits
28 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | replace deck-o-seal on four pools | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | replace deck-o-seal on four pools
136 | 1100- Specialties, Equipment & Furnishings | Clubhouse Renovation | Hide cabling Look at replacing hexagonal mirrored tile on walls Kitchen upgrades? | Capex | Year 1 | 25000 | 1720 |  |  | N/A |  | Hide cabling Look at replacing hexagonal mirrored tile on walls Kitchen upgrades?
32 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair Pool fence and paint | GC | Year 1 | 24000 | 24000 |  |  | 0% |  | Repair Pool fence and paint
167 | 1600 - Electrical | Install CO Detector | From PCA- $12,950- Carbon Monoxide detectors were not observed as required. | GC | Year 1 | 23310 | 23310 |  |  | 0 |  | From PCA- $12,950- Carbon Monoxide detectors were not observed as required. | [5 empty] | 2023-06-29
128 | 0900 - FF&E in Units | Dryer Vents | Clean dryer vents | GC | Year 1 | 23175 | 23175 |  |  | 0 |  | Clean dryer vents
16 | 0200 - Site Utilities & Improvements | Parking equipment | add parking stops by fencing | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | add parking stops by fencing
23 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Fix Entrance Gates & Access Control | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Fix Entrance Gates & Access Control
51 | 0400 - Structure | Roof pad | Roof Repairs | GC | Year 1 | 20000 | 20000 |  |  | 0
146 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | New flooring- rubber or epoxy | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | New flooring- rubber or epoxy
39 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair Dumpsters and paint | GC | Year 1 | 19800 | 19800 |  |  | 0 |  | Repair Dumpsters and paint
130 | 0900 - FF&E in Units | Install GFCI outlet in wet areas | From PCA- $11,750- 50% of the bathrooms of 2-bedroom units had Non-GFCI outlets. | GC | Year 1 | 17625 | 17625 |  |  | 0 |  | From PCA- $11,750- 50% of the bathrooms of 2-bedroom units had Non-GFCI outlets. | [5 empty] | 2023-06-29
54 | 0400 - Structure | Roof deck | replace decking and underlayment on roofs | GC | Year 1 | 17500 | 17500 |  |  | 0 |  | replace decking and underlayment on roofs
30 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | inspect and repair/replace pool pumps | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | inspect and repair/replace pool pumps
56 | 0400 - Structure | Repair exterior stair railings | Stair Repairs | GC | Year 1 | 15000 | 15000 |  |  | 0
57 | 0400 - Structure | Repair balcony framing & decking | repair 5 balconies | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | repair 5 balconies
58 | 0400 - Structure | Repair patio/balcony railings | secure all railings | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | secure all railings
69 | 0700 - Roofing | Flashing | replace rotted flashing on doghouse meter rooms | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | replace rotted flashing on doghouse meter rooms
70 | 0700 - Roofing | Sealants & caulking and paint | Roof Sealants | GC | Year 1 | 15000 | 15000 |  |  | 0
15 | 0200 - Site Utilities & Improvements | Stripe parking areas | Parking Lot Striping | GC | Year 1 | 14000 | 14000 |  |  | 0
52 | 0400 - Structure | Roof framing | Roof Framing Repairs | GC | Year 1 | 12000 | 12000 |  |  | 0
135 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | repair and stain office catwalk balcony | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | repair and stain office catwalk balcony
127 | 0900 - FF&E in Units | Down Units | From PCA- $10,000- At the time of the site visit, 1 down unit (unit #4335) was observed due to subflooring damage according to the property manager. | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | From PCA- $10,000- At the time of the site visit, 1 down unit (unit #4335) was observed due to subflooring damage according to the property manager. | [5 empty] | 2024-03-30
123 | 0900 - FF&E in Units | Repair Leaking at Unit Interiors | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 676 - evidence of a major leak in the ceiling of the living room. Unit 4097 - Tenant reported a leak in the pantry, a previous leak in the hallway caused by tub overflow, and the ceiling has not been repaired. The tub appears to still be leaking in the upstairs bathroom and the patio door seal is missing and the door is unstable. CBRE recommends sources for the leaks be isolated, and repaired and that all affected areas be replaced/repaired at this time. | PMC | Year 1 | 8500 | 56593 |  |  | N/A |  | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 676 - evidence of a major leak in the ceiling of the living room. Unit 4097 - Tenant reported a leak in the p | [5 empty] | 2024-03-30
34 | 0200 - Site Utilities & Improvements | Pool Area repairs | From PCA- $7,000- The walls and ceilings of the swimming pool equipment rooms were observed to be damaged. The restrooms in the swimming pool building were observed to be in bad condition. | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | From PCA- $7,000- The walls and ceilings of the swimming pool equipment rooms were observed to be damaged. The restrooms in the swimming pool building were observed to be in bad condition. | [5 empty] | 2024-03-30
17 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts | add proper signage | GC | Year 1 | 5600 | 5600 |  |  | 0 |  | add proper signage
163 | 1600 - Electrical | Electrical distribution | From PCA- $1,000- The Electrical Panel in the swimming pool equipment by the leasing office was observed to be without cover and exposed wiring. | GC | Year 1 | 5200 | 5200 |  |  | 0 |  | From PCA- $1,000- The Electrical Panel in the swimming pool equipment by the leasing office was observed to be without cover and exposed wiring. | [5 empty] | 2023-06-29
24 | 0200 - Site Utilities & Improvements | Access Control | Need more fobs, repair hardware & need software to program | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Need more fobs, repair hardware & need software to program
168 | 1600 - Electrical | Fire suppression | From PCA- $2,000- No fire extinguishers were observed in any visited units. | GC | Year 1 | 2500 | 2500 |  |  | 0 |  | From PCA- $2,000- No fire extinguishers were observed in any visited units. | [5 empty] | 2023-06-29
125 | 0900 - FF&E in Units | Remove interior mold | From PCA- $2,000- CBRE observed conspicuous mold growth in the areas identified as walls and ceiling of the living room of Unit #4275. walls of the storage area on the balcony of unit #528. | PMC | Year 1 | 2000 | 13316 |  |  | N/A |  | From PCA- $2,000- CBRE observed conspicuous mold growth in the areas identified as walls and ceiling of the living room of Unit #4275. walls of the storage area on the balcony of unit #528. | [5 empty] | 2023-06-29
165 | 1600 - Electrical | Fix/ test the fire riser | From PCA- $2,000- The fire sprinkler riser in building #10 has a red inspection tag. | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | From PCA- $2,000- The fire sprinkler riser in building #10 has a red inspection tag. | [5 empty] | 2023-06-29
18 | 0200 - Site Utilities & Improvements | Curbs & gutters | Sections of the concrete curbing were noted to be chipped, spalled, and damaged. Such sections were noted by the maintenance shop, buildings #13, #14, and #20. | GC | Year 1 | 1500 | 1500 |  |  | 0 |  | Sections of the concrete curbing were noted to be chipped, spalled, and damaged. Such sections were noted by the maintenance shop, buildings #13, #14, and #20. | [5 empty] | 2024-03-30
126 | 0900 - FF&E in Units | Remove Interior Mold in Unit 3951 | From PCA- $1,000- Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 3951 - major leak with mold was observed. CBRE recommends sources for the leaks be isolated, and repaired and that all affected areas be replaced/repaired at this time. Costs for this work are included in the cost table and documentation is included in the appendices. | PMC | Year 1 | 1000 | 6658 |  |  | N/A |  | From PCA- $1,000- Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 3951 - major leak with mold was observed. CBRE recommends sources for the leaks be isolated | [5 empty] | 2023-06-29
166 | 1600 - Electrical | Fix the fire alarm panel | From PCA- $1,000- A trouble indicator light was noted at the fire alarm panel of building #5. | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | From PCA- $1,000- A trouble indicator light was noted at the fire alarm panel of building #5. | [5 empty] | 2023-06-29
164 | 1600 - Electrical | Switchgear/metering | From PCA- $700- The Electrical Panels in the swimming pool equipment by the leasing office and in the electrical room of building #3 were observed to be without cover and exposed wiring. | GC | Year 1 | 700 | 700 |  |  | 0 |  | From PCA- $700- The Electrical Panels in the swimming pool equipment by the leasing office and in the electrical room of building #3 were observed to be without cover and exposed wiring. | [5 empty] | 2023-06-29
124 | 0900 - FF&E in Units | Fix Broken handrail in Unit 4425 | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 4425 - Handrail is broken and should be repaired at this time. Costs for this work are included in the cost table and documentation is included in the appendices. | PMC | Year 1 | 500 | 0 |  |  | N/A |  | Subsequent to the site visit CBRE was informed of additional areas of repairs needed. Unit 4425 - Handrail is broken and should be repaired at this time. Costs for this work are included in the cost t |  | Completed |  |  |  | 2024-03-30
PROJECTS subtotal (excl. contingency/CM fee)
176 | Contingency | Contingency- Other |  | CON | Contingency | 162465 | 0 | 162465 |  | N/A

## Oak Forest
Oak Forest — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
79 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Year 1 | 686000 | 686000 |  |  | 0 |  | Paint community
119 | 1100- Specialties, Equipment & Furnishings | Video systems |  | Capex | Year 1 | 250000 | 40715 |  |  | N/A
21 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Repair and paint wooden fence and replace sections of damaged metal fence, Repair gate operators and ped gate closers | GC | Year 1 | 185000 | 185000 |  |  | 0 |  | Repair and paint wooden fence and replace sections of damaged metal fence, Repair gate operators and ped gate closers
108 | 0900 - FF&E in Units | Washer/dryer |  | Capex | Year 1 | 130000 | 0 |  |  | N/A
23 | 0200 - Site Utilities & Improvements | Landscaping | Trim Trees and remove dead bushes | GC | Year 1 | 85000 | 85000 |  |  | 0 |  | Trim Trees and remove dead bushes
24 | 0200 - Site Utilities & Improvements | Resurface swimming pool | Resurface three pools with pebble tech plaster | GC | Year 1 | 81000 | 81000 |  |  | 0 |  | Resurface three pools with pebble tech plaster
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | New clubhouse furniture | Capex | Year 1 | 80000 | 59297 |  |  | N/A |  | New clubhouse furniture
122 | 1100- Specialties, Equipment & Furnishings | Pool area enhancements | Address pool inspection items, upgraded pool deck | Capex | Year 1 | 80000 | 23295 |  |  | N/A |  | Address pool inspection items, upgraded pool deck
143 | 1600 - Electrical | Fire and Sprinklers | replace painted heads in units From PCA- $68,000- The fire and life safety system appeared to be in overall fair to average condition. The AFSS risers were last inspected by FPI LLC in December 2022, and the fire alarm panels were last inspected by ACT Low Voltage LLC in December 2022. All of the building AFSS were yellow tagged for painted fire sprinkler heads, and most fire alarm panels observed had supervisory/ trouble statuses or were actively alarming. Management did not provide a copy of the most recent fire inspection report or a bid to complete repairs. Blackstone recommends that a fire safety contractor evaluate the AFSS and fire alarm panels and complete necessary repairs to correct these conditions as a priority repair (PR-90) need. The costs included for these repairs are for budgetary purposes only; the fire safety contractor will need to provide an accurate count of painted fire sprinkler heads and provide more accurate costs for repairs. | GC | Year 1 | 68000 | 68000 |  |  | 0 |  | replace painted heads in units From PCA- $68,000- The fire and life safety system appeared to be in overall fair to average condition. The AFSS risers were last inspected by FPI LLC in December 2022, | [5 empty] | 2023-06-13
107 | 0900 - FF&E in Units | Range Queen | Fire stops | GC | Year 1 | 66120 | 66120 |  |  | 0 |  | Fire stops
14 | 0200 - Site Utilities & Improvements | Concrete pavement | repair pot holes and broken sidewalks | GC | Year 1 | 62000 | 62000 |  |  | 0 |  | repair pot holes and broken sidewalks
47 | 0400 - Structure | Wall framing | Replace damaged gable vents and balcony structure | GC | Year 1 | 62000 | 62000 |  |  | 0 |  | Replace damaged gable vents and balcony structure
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Paint accent walls Create built in desk/counter Add glass wall and door to back right office for tenant discussions | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Paint accent walls Create built in desk/counter Add glass wall and door to back right office for tenant discussions
80 | 0800 - Exterior Wall | Repair / replace wood trim |  | GC | Year 1 | 48000 | 48000 |  |  | 0
35 | 0200 - Site Utilities & Improvements | Carport and garage | Repair carport damage | GC | Year 1 | 39000 | 39000 |  |  | 0 |  | Repair carport damage
59 | 0700 - Roofing | Asphalt composite shingle roofing | minor roof repairs | GC | Year 1 | 38000 | 38000 |  |  | 0 |  | minor roof repairs
64 | 0700 - Roofing | Gutters & downspouts | Clean down spouts and gutters | GC | Year 1 | 38000 | 38000 |  |  | 0 |  | Clean down spouts and gutters
76 | 0800 - Exterior Wall | Repair stucco |  | GC | Year 1 | 38000 | 38000 |  |  | 0
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | Inspect and repair irrigation. From PCA- $34,000- The landscaping and irrigation systems appeared to be in fair to average condition. Blackstone observed overgrown shrubs, bushes, and tree branches in contact or in close proximity to exterior walls and roofs at buildings throughout the property. In addition, damaged and/or dead bushes and bare soil were observed at multiple areas. Blackstone recommends installing suitable groundcover and/or resodding areas of bare soil, removing dead/damaged bushes and trimming overgrown shrubs, bushes, and tree branches throughout the property as a priority repair need. | GC | Year 1 | 34000 | 34000 |  |  | 0 |  | Inspect and repair irrigation. From PCA- $34,000- The landscaping and irrigation systems appeared to be in fair to average condition. Blackstone observed overgrown shrubs, bushes, and tree branches | [5 empty] | 2024-03-14
74 | 0800 - Exterior Wall | Dryer Vents | Clean dryer vents ($45@) & Vent cover replacements as needed ($3000) | GC | Year 1 | 34000 | 34000 |  |  | 0 |  | Clean dryer vents ($45@) & Vent cover replacements as needed ($3000)
77 | 0800 - Exterior Wall | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | Repair soffit on breezeways patios and balconies
20 | 0200 - Site Utilities & Improvements | Erosion control | From PCA- $25,500- Management reported erosion repairs in 2022, and Blackstone observed new rock groundcover at several locations. However, these repairs were only completed at some locations and did not appear to be sufficient. Blackstone observed areas of erosion throughout the site including some areas where the new rock groundcover had been installed. Based on conditions observed, we recommend drainage improvements as needed (regrading, French drains, installing downspout extensions, etc.), and landscaping improvements (new plantings, rock or mulch ground cover) at areas of erosion to stabilize the soils as a priority repair need. | GC | Year 1 | 31000 | 31000 |  |  | 0 |  | From PCA- $25,500- Management reported erosion repairs in 2022, and Blackstone observed new rock groundcover at several locations. However, these repairs were only completed at some locations and did | [5 empty] | 2024-03-14
33 | 0200 - Site Utilities & Improvements | Picnic areas | replace 8 grills | GC | Year 1 | 31000 | 31000 |  |  | 0 |  | replace 8 grills
120 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment |  | Capex | Year 1 | 30000 | 42136 |  |  | N/A
121 | 1100- Specialties, Equipment & Furnishings | Pool furniture- Office Pool | New furniture for office pool area only, repurpose existing good furniture to other 2 pools | Capex | Year 1 | 30000 | 49605 |  |  | N/A |  | New furniture for office pool area only, repurpose existing good furniture to other 2 pools
18 | 0200 - Site Utilities & Improvements | Sidewalks | From PCA- $5,000- The concrete sidewalks and flatwork were observed to be in overall fair to good condition. Blackstone observed damaged, cracked and uplifted sections (trip hazards) of concrete sidewalks at several locations near Buildings 5, 7, 10, 11, 18, 19, and 26. Due to the widespread nature of these conditions, we recommend that management survey all sidewalks and flatwork and repair or replace damaged sections as needed as a priority repair need. $3,000- Blackstone observed concrete steps with four or more risers and no handrails at Buildings 9 and 14. Blackstone recommends installing handrails at these locations as a priority repair need. | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | From PCA- $5,000- The concrete sidewalks and flatwork were observed to be in overall fair to good condition. Blackstone observed damaged, cracked and uplifted sections (trip hazards) of concrete sidew | [5 empty] | 2024-03-14
25 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Replace deck-o-seal on pools | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | Replace deck-o-seal on pools
22 | 0200 - Site Utilities & Improvements | Retaining walls | Tuck Point retaining walls From PCA- $5,000- Blackstone observed cracking and/or missing stone components at retaining walls near Buildings 10, 11, 30 and 31. Blackstone recommends repairing the stone retaining wall as a priority repair need. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Tuck Point retaining walls From PCA- $5,000- Blackstone observed cracking and/or missing stone components at retaining walls near Buildings 10, 11, 30 and 31. Blackstone recommends repairing the stone | [5 empty] | 2024-03-14
123 | 1100- Specialties, Equipment & Furnishings | Pool area enhancements | Activities, turf, etc | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Activities, turf, etc
30 | 0200 - Site Utilities & Improvements | Pergola | repair and stain all pergolas | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | repair and stain all pergolas
53 | 0400 - Structure | Repair balcony framing & decking | repair balcony band boards | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | repair balcony band boards
66 | 0700 - Roofing | Sealants & caulking and paint |  | GC | Year 1 | 18000 | 18000 |  |  | 0
29 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair and paint pool fences | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Repair and paint pool fences
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair dumpster enclosures | GC | Year 1 | 15000 | 15000 |  |  | 0% |  | Repair dumpster enclosures
12 | 0200 - Site Utilities & Improvements | Storm sewer piping | clean out storm drain boxes | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | clean out storm drain boxes
15 | 0200 - Site Utilities & Improvements | Stripe parking areas |  | GC | Year 1 | 14000 | 14000 |  |  | 0%
32 | 0200 - Site Utilities & Improvements | Playground equipment | Replace Fall zone in play ground | GC | Year 1 | 14000 | 14000 |  |  | 0% |  | Replace Fall zone in play ground
55 | 0400 - Structure | Repair catwalks | clean and seal expansion joints | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | clean and seal expansion joints
70 | 0800 - Exterior Wall | Repair / replace wood siding | repair damaged siding | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | repair damaged siding
75 | 0800 - Exterior Wall | Tuck-pointing |  | GC | Year 1 | 12000 | 12000 |  |  | 0
106 | 0900 - FF&E in Units | Radon Mitigation Systems: | Lender Mandate- In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the subject property to measure radon gas concentrations. The screening program included the deployment of short-term (48-96 hour) radon scintillation screening devices. Radon gas concentrations above the USEPA 4.0 pCi/L guidance limit were identified in Building 1, Unit 111 (5.0 pCi/L), Building 23, Unit 2314 (8.4 pCi/L), and Building 32 Unit 3214 (4.8 pCi/L) during the short-term screenings, and long-term testing is currently in progress. Based upon the results of the initial screening, Blackstone recommends budgeting for the potential installation of radon mitigation systems at Building 1, Unit 111, Building 23, Unit 2314, and Building 32 Unit 3214 as a priority repair need. | Capex | Year 1 | 10500 | 0 |  |  | N/A |  | Lender Mandate- In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the subject property to measure radon gas concentrations. The screening program inc | [5 empty] | 2024-03-14
50 | 0400 - Structure | Roof deck | replace bad decking on roofs | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | replace bad decking on roofs
52 | 0400 - Structure | Repair exterior stair railings | secure railings | GC | Year 1 | 8300 | 8300 |  |  | 0 |  | secure railings
54 | 0400 - Structure | Repair patio/balcony railings | secure railings | GC | Year 1 | 8300 | 8300 |  |  | 0 |  | secure railings
17 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts |  | GC | Year 1 | 6500 | 6500 |  |  | 0
124 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | Close 2-3 wall openings between gym and bathroom hallway | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Close 2-3 wall openings between gym and bathroom hallway
125 | 1100- Specialties, Equipment & Furnishings | Fitness center adjacent restroom upgrades | Repair/replace partitions, touch up paint and base | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Repair/replace partitions, touch up paint and base
105 | 0900 - FF&E in Units | Mold remediation | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan coil unit. Blackstone recommends identifying and repairing the source of water intrusion, replacing water damaged materials, and remediating all AMG in accordance with USEPA guidelines as a priority repair need. | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan coil unit. Blackstone recommends identifying and repairing the source of water in | [5 empty] | 2024-03-14
PROJECTS subtotal (excl. contingency/CM fee)
151 | Contingency | Contingency- Unit Upgrades |  | CON | Contingency | 2784000 | 0 | 2784000 |  | N/A
152 | Contingency | Contingency- Other |  | CON | Contingency | 996280 | 0 | 996280 |  | N/A
149 | Contingency | Contingency- Deferred Maintenance |  | CON | Contingency | 466000 | 0 | 466000 |  | N/A
150 | Contingency | Contingency- Amenities |  | CON | Contingency | 100000 | 0 | 100000 |  | N/A

## Oak Park
Oak Park — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
37 | Exterior Building & Site Work | Exterior Paint, Carpentry & Misc Repairs | Bldg. paint looks to be in good shape. Last painted 2017. Need to paint all metal except doors yr1 $201k. Pick and pull carpenty, patch paint reapirs corner to corner $69k. Ph1&2 rebuild 25 leaning chimneys $110k pre Crest bid. Ph3 wrap and reside all chimneys $63.5k Tune up wood patio fences if not replaced $8k. most pricing listed per Norman bids. | Unmarked | Year 1 | 1059500 | 938581 |  |  | N/A |  | Bldg. paint looks to be in good shape. Last painted 2017. Need to paint all metal except doors yr1 $201k. Pick and pull carpenty, patch paint reapirs corner to corner $69k. Ph1&2 rebuild 25 leaning ch |  | Completed
69 | MEP | HVAC Equipment (HVAC FULL NEW REPLACEMENT) | Based on eval from SRT there are 368 R22/Mixed refrigerant systems. Researching run rates for MT and AW I came up with a 36% replacement rate here of R22/mixed sytems $596k over the first 5yrs. Per system cost is now $4.5k with new epa regulation on seer requirements. The goal here is to only spend as needed and to PM all units to try to reduce the number of replacements. | Unmarked | Year 1 | 646160 | 639431 |  |  | N/A |  | Based on eval from SRT there are 368 R22/Mixed refrigerant systems. Researching run rates for MT and AW I came up with a 36% replacement rate here of R22/mixed sytems $596k over the first 5yrs. Per sy |  | Completed
58 | Interior Units | Vacant Unit Deferred Maintenance |  | Unmarked | Year 1 | 500000 | 117730 |  |  | N/A
76 | MEP | Water Piping & Plumbing | Replace (27 pairs) building valves that are barried, rusted, and don’t work $46k. unit 516 had an external repipe that needs corrected 5k. Ph1 and 2 have schedule m copper Ph1 is susceptible to pin hole leaks and under ground leaks due to being on a boiler system. Researched run rates on AW,MT,MB. 50k for as needed domestic pipe replacments | Unmarked | Year 1 | 401000 | 198926 |  |  | N/A |  | Replace (27 pairs) building valves that are barried, rusted, and don’t work $46k. unit 516 had an external repipe that needs corrected 5k. Ph1 and 2 have schedule m copper Ph1 is susceptible to pin ho |  | Completed
71 | MEP | Panel Replacement/GFCI | PH2 has Zinsco panels in all units. Need to replace breakers $346k. Per bid from Shields Electrical Services. 296 units in Ph2 | Unmarked | Year 1 | 346005 | 383245 |  |  | N/A |  | PH2 has Zinsco panels in all units. Need to replace breakers $346k. Per bid from Shields Electrical Services. 296 units in Ph2
22 | Common Area | Pool Area Repairs & Equipment | Replaster both pools at leasing offfice pool, refresh grill/pergola area, and repair expansion joints on deck replace grills 70k. Pool near gym, replaster pool, resurface pool deck, refresh grill/pergola area 62k. Back pool at bldg 14, Replatster both pools Fix tile and raise skimmers repair leak, repair expansion joints on deck85.5k. pool lost power and froze solid 2021.Code and filter repairs23k. Bids from H2O. Need to add Poolsure at all pools and should be budgeted in operations | Unmarked | Year 1 | 342164 | 454979 |  |  | N/A |  | Replaster both pools at leasing offfice pool, refresh grill/pergola area, and repair expansion joints on deck replace grills 70k. Pool near gym, replaster pool, resurface pool deck, refresh grill/perg
70 | MEP | HVAC PM | Dryer vent cleaning 75/unit $45k. Replace dryer vents 65 ea. PM all a/c units $120k this include pm service and some part replacements. | Unmarked | Year 1 | 341470 | 110179 |  |  | N/A |  | Dryer vent cleaning 75/unit $45k. Replace dryer vents 65 ea. PM all a/c units $120k this include pm service and some part replacements. |  | Completed
74 | MEP | Sewer Systems | Repairs sewer blockages and breaks. bldgs1,2,4,5,6,7,10,12,13,14,15,16,21,26 Bid from SRT. Also researched run rates on AW,MT,MB | Unmarked | Year 1 | 253000 | 2334 |  |  | N/A |  | Repairs sewer blockages and breaks. bldgs1,2,4,5,6,7,10,12,13,14,15,16,21,26 Bid from SRT. Also researched run rates on AW,MT,MB |  | Completed
27 | Exterior Building & Site Work | Balconies | Rebuild 12 balconies called out by gc $68k. Pick and pull other balcony and land structural members including replacement of rotted joist, fascia, cracked/twisted/bowed/rotten posts, missing hangers 117k. Replace Ph 2 SWB roof Post with Steel post qty 33 $45k. Ph1 cantilevered balconies, ph2 ledger board anchored with post outer supports with open sturctures. Will need to hold monnies for misc post failures over hold. | Unmarked | Year 1 | 243600 | 148350 |  |  | N/A |  | Rebuild 12 balconies called out by gc $68k. Pick and pull other balcony and land structural members including replacement of rotted joist, fascia, cracked/twisted/bowed/rotten posts, missing hangers |  | Completed
26 | Exterior Building & Site Work | Asphalt Milling/Paving/Sealcoat | Restripe some areas in Y1. Y2 fix major potholes and restripe after | Unmarked | Year 1 | 243500 | 105364 |  |  | N/A |  | Restripe some areas in Y1. Y2 fix major potholes and restripe after |  | Completed
52 | Exterior Building & Site Work | Sports Court | See sports court taband add $25K for iron fence between soccer field and social area | Unmarked | Year 1 | 227000 | 514328 |  |  | N/A |  | See sports court taband add $25K for iron fence between soccer field and social area
80 | Miscellaneous | Environmental - Asbestos Abatement | For as needed abatement Ph1 only | Unmarked | Year 1 | 210000 | 122414 |  |  | N/A |  | For as needed abatement Ph1 only
54 | Exterior Building & Site Work | Tree/Plant Removal | Cut life safety trees for $60K. All trees removed are bid to be replaced w/ sod. Class B trim and removal of dead limbs $40k. Removal of dead shrubs replaced with hollies $33k. Deage living shrubs $23k. | Unmarked | Year 1 | 202000 | 223962 |  |  | N/A |  | Cut life safety trees for $60K. All trees removed are bid to be replaced w/ sod. Class B trim and removal of dead limbs $40k. Removal of dead shrubs replaced with hollies $33k. Deage living shrubs $23
36 | Exterior Building & Site Work | Exterior Lighting | Replace all metal halo building lights and fix 25% of carport lights | Unmarked | Year 1 | 198710 | 143010 |  |  | N/A |  | Replace all metal halo building lights and fix 25% of carport lights |  | Completed
39 | Exterior Building & Site Work | Fireplace & Flue | 95/ unit, need to confirm FP count 608 budgeted | Unmarked | Year 1 | 173280 | 34688 |  |  | N/A |  | 95/ unit, need to confirm FP count 608 budgeted |  | Completed
51 | Exterior Building & Site Work | Roof Replacements/Repairs | Roof PM needed on all bldgs- PM also includes fix dryer vent termination on roof, repair busted roof trust in attics- PH1 $42.5 PH2 $51K PH3 $7.5k Decking Repairs 20k per bid from Centex | Unmarked | Year 1 | 156000 | 231180 |  |  | N/A |  | Roof PM needed on all bldgs- PM also includes fix dryer vent termination on roof, repair busted roof trust in attics- PH1 $42.5 PH2 $51K PH3 $7.5k Decking Repairs 20k per bid from Centex
59 | Interior Units | Washers/Dryers |  | Unmarked | Year 1 | 123000 | 0 |  |  | N/A |  |  |  | In Progress
64 | MEP | Domestic Water Heaters | As needed replacements on PH2&3 review unit walks | Unmarked | Year 1 | 105000 | 4620 |  |  | N/A |  | As needed replacements on PH2&3 review unit walks
29 | Exterior Building & Site Work | Concrete Curb/Sidewalk | Sidewalk repairs and grinding 49k per bid from Sunland. Per Post PNA -ADA acess to common areas 16k. Includes $5k in lender mandates- The concrete sidewalks and flatwork were observed to be in overall fair to good condition. Blackstone observed damaged, cracked and uplifted sections (trip hazards) of concrete sidewalks at several locations near Buildings 5, 7, 10, 11, 18, 19, and 26. Due to the widespread nature of these conditions, we recommend that management survey all sidewalks and flatwork and repair or replace damaged sections as needed as a priority repair need. | Unmarked | Year 1 | 95000 | 750 |  |  | N/A |  | Sidewalk repairs and grinding 49k per bid from Sunland. Per Post PNA -ADA acess to common areas 16k. Includes $5k in lender mandates- The concrete sidewalks and flatwork were observed to be in overal |  | Completed |  |  |  | 2024-03-14
40 | Exterior Building & Site Work | Foundations & Site Grading | Install Exterior peirs buildings 1,8,6.24 Watch list 2,13,15,26,31 | Unmarked | Year 1 | 92000 | 0 |  |  | N/A |  | Install Exterior peirs buildings 1,8,6.24 Watch list 2,13,15,26,31 |  | Not Started
30 | Exterior Building & Site Work | Controlled Access Systems | Site uses Gate Wise Need to check Mo. Operating cost Call box is Linear and does not work and needs replaced. Also several of the motors and safety loops need work, PM PED Gates and all wiring. 60k | Unmarked | Year 1 | 90000 | 20147 |  |  | N/A |  | Site uses Gate Wise Need to check Mo. Operating cost Call box is Linear and does not work and needs replaced. Also several of the motors and safety loops need work, PM PED Gates and all wiring. 60k |  | Completed
34 | Exterior Building & Site Work | Erosion Control/Drainage | Repair drainage and add swell back side bldgs. 11-13 $11k. Clean out and test all french drains through out property $15k. Add new drains at 5 buildings $33k. Fill in LS pot hole listed on line 94. Add soil in out yrs to fill in holes as new soil settles. Per bids from Superior. Includes $25,500 in Lender Mandates- Management reported erosion repairs in 2022, and Blackstone observed new rock groundcover at several locations. However, these repairs were only completed at some locations and did not appear to be sufficient. Blackstone observed areas of erosion throughout the site including some areas where the new rock groundcover had been installed. Based on conditions observed, we recommend drainage improvements as needed (regrading, French drains, installing downspout extensions, etc.), and landscaping improvements (new plantings, rock or mulch ground cover) at areas of erosion to stabilize the soils as a priority repair need. | Unmarked | Year 1 | 89000 | 101269 |  |  | N/A |  | Repair drainage and add swell back side bldgs. 11-13 $11k. Clean out and test all french drains through out property $15k. Add new drains at 5 buildings $33k. Fill in LS pot hole listed on line 94. A | [5 empty] | 2024-03-14
63 | MEP | Domestic Water Boilers/Heat Exchangers & Related Wor | Replace boiler 1 near building 14, 48.3k PM other 2 boilers 7k Bid from SRT | Unmarked | Year 1 | 85300 | 93981 |  |  | N/A |  | Replace boiler 1 near building 14, 48.3k PM other 2 boilers 7k Bid from SRT
15 | Admin/Marketing | Office Furniture/Finishes | Refresh on furnitre per Post | Unmarked | Year 1 | 85000 | 6260 |  |  | N/A |  | Refresh on furnitre per Post |  | Completed
48 | Exterior Building & Site Work | Patio Doors/Sliders | replace 5 sliders per yr | Unmarked | Year 1 | 77000 | 85 |  |  | N/A |  | replace 5 sliders per yr
44 | Exterior Building & Site Work | Handrail/Railings | Fixing balcony handrails and misc metal fencing repairs | Unmarked | Year 1 | 76000 | 55360 |  |  | N/A |  | Fixing balcony handrails and misc metal fencing repairs
75 | MEP | Sprinkler Systems | Ph 3 dry heads due for10yr UL testing next yr. if replacement needed after testing 800 ea including SRR @64k waiting metro report. Spoke to FPI who did last insp. System was all white tagged and in good shape. | Unmarked | Year 1 | 76000 | 0 |  |  | N/A |  | Ph 3 dry heads due for10yr UL testing next yr. if replacement needed after testing 800 ea including SRR @64k waiting metro report. Spoke to FPI who did last insp. System was all white tagged and in go |  | Completed
41 | Exterior Building & Site Work | General Site Fencing | Repair wood perim fencing. Replace middle pool fencing for $24.5K | Unmarked | Year 1 | 74500 | 124690 |  |  | N/A |  | Repair wood perim fencing. Replace middle pool fencing for $24.5K
82 | Miscellaneous | Lead Paint/Radon Remediation | To maintain paint on all ph1 balcony handrails. Yr 1 plan is to paint all railings in the exterior scope. | Unmarked | Year 1 | 70000 | 0 |  |  | N/A |  | To maintain paint on all ph1 balcony handrails. Yr 1 plan is to paint all railings in the exterior scope.
68 | MEP | Fire Safety Systems | The fire and life safety system appeared to be in overall fair to average condition. The AFSS risers were last inspected by FPI LLC in December 2022, and the fire alarm panels were last inspected by ACT Low Voltage LLC in December 2022. All of the building AFSS were yellow tagged for painted fire sprinkler heads, and most fire alarm panels observed had supervisory/trouble statuses or were actively alarming. Management did not provide a copy of the most recent fire inspection report or a bid to complete repairs. Blackstone recommends that a fire safety contractor evaluate the AFSS and fire alarm panels and complete necessary repairs to correct these conditions as a priority repair (PR-90) need. The costs included for these repairs are for budgetary purposes only; the fire safety contractor will need to provide an accurate count of painted fire sprinkler heads and provide more accurate costs for repairs. | Unmarked | Year 1 | 68000 | 5711 |  |  | N/A |  | The fire and life safety system appeared to be in overall fair to average condition. The AFSS risers were last inspected by FPI LLC in December 2022, and the fire alarm panels were last inspected by A |  | Completed |  |  |  | 2023-06-13
65 | MEP | Drain Clean/Jet Lines/Video | Scrape and clean cast iron sewers in ph1&2 19k. Hyrdo jet all of Ph3 2k | Unmarked | Year 1 | 67000 | 42606 |  |  | N/A |  | Scrape and clean cast iron sewers in ph1&2 19k. Hyrdo jet all of Ph3 2k |  | Completed
43 | Exterior Building & Site Work | Gutters & Downspouts | Gutter tune up($23k) and add Raindrop gutter guard($131k)to prevent future damage or maintance needs | Unmarked | Year 1 | 63000 | 35600 |  |  | N/A |  | Gutter tune up($23k) and add Raindrop gutter guard($131k)to prevent future damage or maintance needs |  | Completed
38 | Exterior Building & Site Work | Exterior Stairs | ~20% of switch backs on ph2 were replaced. Additional needing replacement. Rebuild 6 SWB landing 60k per Crest. 10k for stair treads | Unmarked | Year 1 | 60000 | 49795 |  |  | N/A |  | ~20% of switch backs on ph2 were replaced. Additional needing replacement. Rebuild 6 SWB landing 60k per Crest. 10k for stair treads |  | Completed
31 | Exterior Building & Site Work | Covered Parking & Misc Parking Items | Repair handful of carports in Y1, and then 1 or 2 a year in outyears. | Unmarked | Year 1 | 55000 | 57741 |  |  | N/A |  | Repair handful of carports in Y1, and then 1 or 2 a year in outyears.
50 | Exterior Building & Site Work | Retaining Walls | general tuck point repairs to retaining walls Includes $5k in lender mandates- Blackstone observed cracking and/or missing stone components at retaining walls near Buildings 10, 11, 30 and 31. Blackstone recommends repairing the stone retaining wall as a priority repair need. | Unmarked | Year 1 | 52000 | 41380 |  |  | N/A |  | general tuck point repairs to retaining walls Includes $5k in lender mandates- Blackstone observed cracking and/or missing stone components at retaining walls near Buildings 10, 11, 30 and 31. Blacks |  | Completed |  |  |  | 2024-03-14
19 | Common Area | Common Corridors Rehab | Power wash breezeways - has valet waste | Unmarked | Year 1 | 50000 | 0 |  |  | N/A |  | Power wash breezeways - has valet waste |  | Completed
21 | Common Area | Mailboxes | Wish list item from PM, new mail boxes there are 7 mail rooms, Budgteing for 2 replacements 55k. And some in out yrs. Add Package lockers near building 24 79k | Unmarked | Year 1 | 50000 | 0 |  |  | N/A |  | Wish list item from PM, new mail boxes there are 7 mail rooms, Budgteing for 2 replacements 55k. And some in out yrs. Add Package lockers near building 24 79k
47 | Exterior Building & Site Work | Landscape Enhancements | Updgrade front curb appeal, office, pools, and entry drive fence line | Unmarked | Year 1 | 50000 | 143923 |  |  | N/A |  | Updgrade front curb appeal, office, pools, and entry drive fence line
16 | Admin/Marketing | Vehicles/Carts | Have 3 working maint, 1 leasing, budgeting for 2 gators, 1 leasing and 1 maintenance (used) | Unmarked | Year 1 | 48000 | 125664 |  |  | N/A |  | Have 3 working maint, 1 leasing, budgeting for 2 gators, 1 leasing and 1 maintenance (used)
85 | Miscellaneous | Structural Repairs | LS Repairs- Fill in potholes in yards 16k.TM to sure up LS balconies includes labor/super/estimated material needed $30k. Remove gazebo Remove 30 LS trees 60k (See line 55) . | Unmarked | Year 1 | 46000 | 0 |  |  | N/A |  | LS Repairs- Fill in potholes in yards 16k.TM to sure up LS balconies includes labor/super/estimated material needed $30k. Remove gazebo Remove 30 LS trees 60k (See line 55) . |  | Completed
23 | Common Area | Pool Furniture/Finishes | Pool furniture needed at leasing pool- space holder 25k | Unmarked | Year 1 | 45000 | 58118 |  |  | N/A |  | Pool furniture needed at leasing pool- space holder 25k
42 | Exterior Building & Site Work | Grill Station | Refresh of pool grilling areas including replacement of grills included line 24. Removal of gazebo on line 94.This is the cost to replace gazebo with a pergola and replace 4 charcoal grills30k. Add DG at grill stations ($10K) | Unmarked | Year 1 | 40000 | 109552 |  |  | N/A |  | Refresh of pool grilling areas including replacement of grills included line 24. Removal of gazebo on line 94.This is the cost to replace gazebo with a pergola and replace 4 charcoal grills30k. Add
53 | Exterior Building & Site Work | Storm Water Management/Retention Ponds | Maintain storm drains | Unmarked | Year 1 | 40000 | 17205 |  |  | N/A |  | Maintain storm drains |  | Completed
87 | Miscellaneous | Video Surveillance System | 19 new cameras replacing NVR and reusing some of existing 35k. 25 cameras and NRV per Post PNA | Unmarked | Year 1 | 35150 | 84704 |  |  | N/A |  | 19 new cameras replacing NVR and reusing some of existing 35k. 25 cameras and NRV per Post PNA
10 | Admin/Marketing | Club House/Leasing Center Addition/Alteration | Need to replace front door to meet ADA 10k. 20k per post PNA to replace some other doors and update bathroom | Unmarked | Year 1 | 35000 | 38925 |  |  | N/A |  | Need to replace front door to meet ADA 10k. 20k per post PNA to replace some other doors and update bathroom
55 | Exterior Building & Site Work | Windows | As needed replacements. Single pain windows | Unmarked | Year 1 | 35000 | 14100 |  |  | N/A |  | As needed replacements. Single pain windows
73 | MEP | PM/Clean Meter Stack | Repalced main meter panels as needed through out hold | Unmarked | Year 1 | 35000 | 0 |  |  | N/A |  | Repalced main meter panels as needed through out hold |  | Completed
33 | Exterior Building & Site Work | Dumpster Enclosures | Per bid from Norman. Repair and stain dumpster enclosures | Unmarked | Year 1 | 32000 | 7966 |  |  | N/A |  | Per bid from Norman. Repair and stain dumpster enclosures |  | Completed
12 | Admin/Marketing | Fitness Center & Equipment | Site has new equipment and new floors room has repair needs and still needs paint,Add TVs lights/fans water despenser 15k. 3k for peaton. | Unmarked | Year 1 | 28000 | 8979 |  |  | N/A |  | Site has new equipment and new floors room has repair needs and still needs paint,Add TVs lights/fans water despenser 15k. 3k for peaton. |  | Completed
81 | Miscellaneous | Environmental - Pest Control Extermination | Waiting on bid for treatment. 35/unit space holder and 15k spaceholder for termite | Unmarked | Year 1 | 21295 | 48447 |  |  | N/A |  | Waiting on bid for treatment. 35/unit space holder and 15k spaceholder for termite
13 | Admin/Marketing | Model Furniture/Finishes | model furniture discussed 15k spaceholder | Unmarked | Year 1 | 20000 | 7163 |  |  | N/A |  | model furniture discussed 15k spaceholder |  | Completed
32 | Exterior Building & Site Work | Dog Park | Ali numbers are high ($9K for refresh + $35K for new dogpark). FCP believes they can do add new park for $15K and refresh for $5K | Unmarked | Year 1 | 20000 | 34842 |  |  | N/A |  | Ali numbers are high ($9K for refresh + $35K for new dogpark). FCP believes they can do add new park for $15K and refresh for $5K
77 | MEP | Wiring | Wiring PM/Cleanup throughout property includes securing meter banks | Unmarked | Year 1 | 20000 | 21812 |  |  | N/A |  | Wiring PM/Cleanup throughout property includes securing meter banks
66 | MEP | Fire Extinguishers | missing or dischaged 5lb fire extinguisher. | Unmarked | Year 1 | 16650 | 233339 |  |  | N/A |  | missing or dischaged 5lb fire extinguisher.
62 | MEP | CO/Smoke Detectors | Verify if we need CO detectors for code. 471 have smoke detectors. $35 / unit | Unmarked | Year 1 | 16450 | 21264 |  |  | N/A |  | Verify if we need CO detectors for code. 471 have smoke detectors. $35 / unit
28 | Exterior Building & Site Work | Brick Repair/Point-Up | Per bid from Norman. | Unmarked | Year 1 | 15000 | 310 |  |  | N/A |  | Per bid from Norman. |  | Completed
84 | Miscellaneous | Maintenance Shop | Clean up maintence shop and storages | Unmarked | Year 1 | 15000 | 0 |  |  | N/A |  | Clean up maintence shop and storages |  | Completed
83 | Miscellaneous | Radon Mitigation Systems | In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the subject property to measure radon gas concentrations. The screening program included the deployment of short-term (48-96 hour) radon scintillation screening devices. Radon gas concentrations above the USEPA 4.0 pCi/L guidance limit were identified in Building 1, Unit 111 (5.0 pCi/L), Building 23, Unit 2314 (8.4 pCi/L), and Building 32 Unit 3214 (4.8 pCi/L) during the short-term screenings, and long-term testing is currently in progress. Based upon the results of the initial screening, Blackstone recommends budgeting for the potential installation of radon mitigation systems at Building 1, Unit 111, Building 23, Unit 2314, and Building 32 Unit 3214 as a priority repair need. | Unmarked | Year 1 | 10500 | 0 |  |  | N/A |  | In accordance with the Freddie Mac Phase I ESA Guidelines, Blackstone conducted a radon screening at the subject property to measure radon gas concentrations. The screening program included the deploy |  | Completed |  |  |  | 2024-03-14
11 | Admin/Marketing | Computers | do we need computer? | Unmarked | Year 1 | 10000 | 1985 |  |  | N/A |  | do we need computer?
20 | Common Area | Laundry Center | Has two laundry center need to refresh both 5k ea. | Unmarked | Year 1 | 10000 | 5620 |  |  | N/A |  | Has two laundry center need to refresh both 5k ea. |  | Completed
46 | Exterior Building & Site Work | Irrigation | Per Superior Edge evaluated system and found 10k in repairs. Per bid. Includes $34k in lender mandates- The landscaping and irrigation systems appeared to be in fair to average condition. Blackstone observed overgrown shrubs, bushes, and tree branches in contact or in close proximity to exterior walls and roofs at buildings throughout the property. In addition, damaged and/or dead bushes and bare soil were observed at multiple areas. Blackstone recommends installing suitable groundcover and/or resodding areas of bare soil, removing dead/damaged bushes and trimming overgrown shrubs, bushes, and tree branches throughout the property as a priority repair need. | Unmarked | Year 1 | 10000 | 29287 |  |  | N/A |  | Per Superior Edge evaluated system and found 10k in repairs. Per bid. Includes $34k in lender mandates- The landscaping and irrigation systems appeared to be in fair to average condition. Blackstone | [5 empty] | 2024-03-14
67 | MEP | Fire Life Safety Work | Ph3 only PM Riser closets 5k. Panels are still using pots lines to communicate, recommend canceling these to save money and install cellular communicators 5k | Unmarked | Year 1 | 10000 | 41243 |  |  | N/A |  | Ph3 only PM Riser closets 5k. Panels are still using pots lines to communicate, recommend canceling these to save money and install cellular communicators 5k
86 | Miscellaneous | Tools/Miscellaneous Equipment | Misc tools | Unmarked | Year 1 | 10000 | 37248 |  |  | N/A |  | Misc tools
14 | Admin/Marketing | Monument Sign | Monument looked good. All building signage looks old and drab. Space holder 15k to replace bldg signs at $85ea | Unmarked | Year 1 | 8300 | 2042 |  |  | N/A |  | Monument looked good. All building signage looks old and drab. Space holder 15k to replace bldg signs at $85ea |  | Completed
35 | Exterior Building & Site Work | Exterior Doors (Other) | Replace Misc mech rm doors | Unmarked | Year 1 | 5000 | 10036 |  |  | N/A |  | Replace Misc mech rm doors
49 | Exterior Building & Site Work | Playground & Site Furniture | Top off existing playground. 5k. See line 53 for new playground on Sport court. | Unmarked | Year 1 | 5000 | 7250 |  |  | N/A |  | Top off existing playground. 5k. See line 53 for new playground on Sport court.
45 | Exterior Building & Site Work | Concrete Steps - Handrails | Lender mandate- Blackstone observed concrete steps with four or more risers and no handrails at Buildings 9 and 14. Blackstone recommends installing handrails at these locations as a priority repair need. | Unmarked | Year 1 | 3000 | 0 |  |  | N/A |  | Lender mandate- Blackstone observed concrete steps with four or more risers and no handrails at Buildings 9 and 14. Blackstone recommends installing handrails at these locations as a priority repair n |  | Completed |  |  |  | 2024-03-14
60 | Interior Units | Apparent Mold Growth - Unit 110 | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan coil unit. Blackstone recommends identifying and repairing the source of water intrusion, replacing water damaged materials, and remediating all AMG in accordance with USEPA guidelines as a priority repair need. | Unmarked | Year 1 | 2000 | 38 |  |  | N/A |  | Blackstone observed apparent mold growth (AMG) at the Unit 110 bathroom ceiling, likely due to condensate from the fan coil unit. Blackstone recommends identifying and repairing the source of water in |  | Completed |  |  |  | 2024-03-14
PROJECTS subtotal (excl. contingency/CM fee)
90 | Contingency and Fees | Contingency |  | CON | Contingency | 572778 | 0 | 572778 |  | N/A
91 | Contingency and Fees | FCP CM Fees |  | CMF | CM Fee | 534592 | 245052 | 289541 |  | N/A

## Sorrento at Tuscan Lakes
Sorrento at Tuscan Lakes — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
124 | 0900 - FF&E in Units | Unit Upgrade Program | 1 Bedroom & 2 Bedroom Unit Upgrades | GC | Year 1 | 1231044 | 1231044 |  |  | 0 |  | 1117sqft, 2BR 2BA
76 | 0800 - Exterior Wall | Exterior building | Paint community | GC | Year 1 | 210000 | 210000 |  |  | 0 |  | Paint community
23 | 0200 - Site Utilities & Improvements | Landscaping | Curb appeal is bad and dated (place Holder) | GC | Year 1 | 150000 | 150000 |  |  | 0 |  | Curb appeal is bad and dated (place Holder)
186 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | New flooring at a minimum, preferably new paint as well Remove window curtains Convert business center counter to booth style or other seating | GC | Year 1 | 90000 | 90000 |  |  | 0 |  | New flooring at a minimum, preferably new paint as well Remove window curtains Convert business center counter to booth style or other seating
187 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | Most or all furniture will need to be replaced, it is very dated | Capex | Year 1 | 90000 | 108179 |  |  | N/A |  | Most or all furniture will need to be replaced, it is very dated
178 | 0900 - FF&E in Units | Ceiling Fans | Add to all living rooms | GC | Year 1 | 56100 | 56100 |  |  | 0 |  | Add to all living rooms
21 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Remove vegitation from fence repair and Paint | GC | Year 1 | 51000 | 51000 |  |  | 0 |  | Remove vegitation from fence repair and Paint
34 | 0200 - Site Utilities & Improvements | Carport and garage | Repair carport damage and paint | GC | Year 1 | 39000 | 39000 |  |  | 0 |  | Repair carport damage and paint
24 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface pool | GC | Year 1 | 38000 | 38000 |  |  | 0 |  | resurface pool
77 | 0800 - Exterior Wall | Repair / replace wood trim | Wood Trim Repairs throughout as needed | GC | Year 1 | 36000 | 36000 |  |  | 0
217 | 1600 - Electrical | Replace breezeway lights | Change breezeway lights, landscape lights | GC | Year 1 | 32570 | 32570 |  |  | 0 |  | Change breezeway lights, landscape lights
196 | 1100- Specialties, Equipment & Furnishings | Pool furniture | Move furniture from Amalfi, supplement with bistro tables/chairs, sectionals, other seating, cabanas | Capex | Year 1 | 30000 | 12636 |  |  | N/A |  | Move furniture from Amalfi, supplement with bistro tables/chairs, sectionals, other seating, cabanas
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | inspect and repair irrigation
14 | 0200 - Site Utilities & Improvements | Concrete pavement | repair pot holes and broken sidewalks | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | repair pot holes and broken sidewalks
192 | 1100- Specialties, Equipment & Furnishings | Security Camera System | Need at least for entry drive, clubhouse, and amenity coverage | Capex | Year 1 | 20000 | 7426 |  |  | N/A |  | Need at least for entry drive, clubhouse, and amenity coverage
194 | 1100- Specialties, Equipment & Furnishings | Pool Remodel | Allowance, the pool area was in decent shape | Capex | Year 1 | 20000 | 10113 |  |  | N/A |  | Allowance, the pool area was in decent shape
216 | 1600 - Electrical | Common area light fixtures | Change wall Packs | GC | Year 1 | 18720 | 18720 |  |  | 0 |  | Change wall Packs
30 | 0200 - Site Utilities & Improvements | Pergola | repair and stain all pergolas | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | repair and stain all pergolas
65 | 0700 - Roofing | Sealants & caulking | Seal where windows meet stucco | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Seal where windows meet stucco
72 | 0800 - Exterior Wall | Masonry repairs | Presure wash Stone walls | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Presure wash Stone walls
75 | 0800 - Exterior Wall | Breezeway soffit repairs | Repair soffit on breezeways patios and balconies | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Repair soffit on breezeways patios and balconies
212 | 1500- HVAC | Dryer Vent cleaning | Dryer Vent Cleaning - Per capital Budget | GC | Year 1 | 15300 | 15300 |  |  | 0
35 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair dumpster enclosures and paint | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Repair dumpster enclosures and paint
58 | 0700 - Roofing | Asphalt composite shingle roofing | minor roof repairs | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | minor roof repairs
190 | 1100- Specialties, Equipment & Furnishings | Mailboxes | Package locker or Fetch system needed | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Package locker or Fetch system needed
63 | 0700 - Roofing | Gutters & downspouts | Clean down spouts and gutters | GC | Year 1 | 13000 | 13000 |  |  | 0 |  | Clean down spouts and gutters
26 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | Crack Fill and clean | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Crack Fill and clean
53 | 0400 - Structure | Repair balcony framing & decking | repair balcony band boards | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | repair balcony band boards
55 | 0400 - Structure | Expansion Joints | clean and seal expansion joints | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | clean and seal expansion joints
69 | 0800 - Exterior Wall | Repair / replace cement fiber siding | repair damaged siding | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | repair damaged siding
74 | 0800 - Exterior Wall | Repair stucco | Stucco Repairs As Needed | GC | Year 1 | 12000 | 12000 |  |  | 0
78 | 0800 - Exterior Wall | Shutters | Replace bad shutters | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Replace bad shutters
15 | 0200 - Site Utilities & Improvements | Stripe parking areas | Parking Lot Striping | GC | Year 1 | 10500 | 10500 |  |  | 0
50 | 0400 - Structure | Roof deck | replace bad decking on roofs | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | replace bad decking on roofs
195 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | In good shape, allowance for minor equipment repairs & replacements | PMC | Year 1 | 10000 | 4664 |  |  | N/A |  | In good shape, allowance for minor equipment repairs & replacements
197 | 1100- Specialties, Equipment & Furnishings | Fitness center renovation | Allowance, not much needed | PMC | Year 1 | 10000 | 4664 |  |  | N/A |  | Allowance, not much needed
215 | 1600 - Electrical | Fire and Sprinklers | replace emergency lights | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | replace emergency lights
29 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair and paint pool fence | GC | Year 1 | 8900 | 8900 |  |  | 0 |  | Repair and paint pool fence
52 | 0400 - Structure | Repair exterior stair railings | secure railings | GC | Year 1 | 8300 | 8300 |  |  | 0 |  | secure railings
54 | 0400 - Structure | Repair patio/balcony railings | secure railings | GC | Year 1 | 8300 | 8300 |  |  | 0 |  | secure railings
25 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Replace deck-o-seal on pools | GC | Year 1 | 8200 | 8200 |  |  | 0 |  | Replace deck-o-seal on pools
214 | 1600 - Electrical | Electrical distribution | repair electric issues with lights | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | repair electric issues with lights
17 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts | Curb Cuts | GC | Year 1 | 4800 | 4800 |  |  | 0
188 | 1100- Specialties, Equipment & Furnishings | Model Unit | Allowance for small additions/refresh | PMC | Year 1 | 4000 | 8799 |  |  | N/A |  | Allowance for small additions/refresh
198 | 1100- Specialties, Equipment & Furnishings | Golf Cart | Repair & replace battery in old leasing cart from Amalfi | PMC | Year 1 | 2000 | 1793 |  |  | N/A |  | Repair & replace battery in old leasing cart from Amalfi
189 | 1100- Specialties, Equipment & Furnishings | Computers | Not needed, allowance for 1 | PMC | Year 1 | 1500 | 2913 |  |  | N/A |  | Not needed, allowance for 1
PROJECTS subtotal (excl. contingency/CM fee)
221 | Contingency & Fees | Construction Management Fee | CM Fee | CMF | CM Fee | 127848 | 0 | 127848 |  | N/A
220 | Contingency & Fees | Contingency | Contingency Amount | CON | Contingency | 77226 | 0 | 77226 |  | N/A
1231044

## The Grand at Hill Street
The Grand at Hill Street — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
17 | 0200 - Site Utilities & Improvements | Parking Lot | Extend the parking lot at the northern end of the property for $5k/parking spot to create potentially 26 new spaces | GC | Year 1 | 130000 | 130000 |  |  | 0 |  | 26
108 | 0900 - FF&E in Units | Turf back yards of first floor units that have crush |  | GC | Year 1 | 80000 | 80000 |  |  | 0
116 | 1100- Specialties, Equipment & Furnishings | Convert Conference room to package room | Includes $15k for renovation expense & $50k for lockers | GC | Year 1 | 65000 | 65000 |  |  | 0
110 | 1100- Specialties, Equipment & Furnishings | Signage - entry | New monument and building sign for rebrand | Capex | Year 1 | 40000 | 74976 |  |  | N/A
114 | 1100- Specialties, Equipment & Furnishings | Add ceiling fans at ground floor and 2nd floor aroun |  | GC | Year 1 | 40000 | 40000 |  |  | 0
106 | 0900 - FF&E in Units | Fire protection | Fire stops | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | 200
111 | 1100- Specialties, Equipment & Furnishings | Signage - site | New property signage throughout for rebrand | Capex | Year 1 | 20000 | 37488 |  |  | N/A
14 | 0200 - Site Utilities & Improvements | Pavement | Replace Pavers with Stamped stained concrete | GC | Year 1 | 18000 | 18000 |  |  | 0
86 | 0800 - Exterior Wall | Look at sealing cedar/wood wall partitions |  | GC | Year 1 | 10000 | 10000 |  |  | 0
117 | 1100- Specialties, Equipment & Furnishings | Convert current package room to convenience market |  | GC | Year 1 | 10000 | 10000 |  |  | 0
80 | 0800 - Exterior Wall | Repair / replace wood trim | Remove and replace damaged wood on garage buildings and paint to match | GC | Year 1 | 5000 | 5000 |  |  | 0
118 | 1100- Specialties, Equipment & Furnishings | Dog Park | Add Pergola /Bench | GC | Year 1 | 5000 | 5000 |  |  | 0
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Install motorized door opener on garage style door/window | GC | Year 1 | 3000 | 3000 |  |  | 0
140 | 1600 - Electrical | Fire Sprinklers | Current inspection tags were not observed on the riser as they were showing their initial installation/inspection stickers from construction of the subject property. Servicing and recertification of the fire suppression systems is recommended. | GC | Year 1 | 3000 | 3000 |  |  | 0 | [7 empty] | 2024-04-24
142 | 1600 - Electrical | Fire alarms | Current inspection tags were not observed on the main control panel as they were showing their initial installation/inspection stickers from construction of the subject property. Servicing and recertification of the fire alarm system is recommended. | GC | Year 1 | 3000 | 3000 |  |  | 0 | [7 empty] | 2024-04-24
141 | 1600 - Electrical | Fire extinguishers | Current inspection tags were not observed on the fire extinguishers. Servicing and recertification of the fire extinguishers is recommended. | GC | Year 1 | 1000 | 1000 |  |  | 0 | [7 empty] | 2024-04-24
115 | 1100- Specialties, Equipment & Furnishings | ADA compliance | The accessible designated parking spaces in front of the leasing office were not configured with signage indicating they were van accessible; however, both stalls appeared to have the required spacing for the stall and access aisle. Installation of a van placard for one of the stalls is recommended. | PMC | Year 1 | 50 | 0 |  |  | N/A | [7 empty] | 2024-04-24
PROJECTS subtotal (excl. contingency/CM fee)

## The Hightone (Allora Denton)
The Hightone (Allora Denton) — 2023 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
120 | Radon | Retest and Mitigate as needed | Radon & Mitigation | GC | Year 1 | 123000 | 123000 |  |  | 0
123 | Roofing Systems | Downspout repairs and gutter installations | Rout downspouts away from the building and onto grass landscaping or concrete sidewalks / pavements to prevent erosion of sandy soils and expansion / contraction of clay soils. Install gutters and downspouts as needed | GC | Year 1 | 68500 | 68500 |  |  | 0 |  | Rout downspouts away from the building and onto grass landscaping or concrete sidewalks / pavements to prevent erosion of sandy soils and expansion / contraction of clay soils. Install gutters and dow
119 | 1100- Specialties, Equipment & Furnishings | Carports (Determine Upon Stabilization) | Tenants have requested covered parking, consider as value add | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Tenants have requested covered parking, consider as value add
114 | 1100- Specialties, Equipment & Furnishings | Trash Compactor (Determine Upon Stabilization) | Look at adding to reduce trash collection fees | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Look at adding to reduce trash collection fees
118 | 1100- Specialties, Equipment & Furnishings | Pool furniture (Determine Upon Stabilization) | Budget for new chaises since all are wicker, Cabanas, umbrellas | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Budget for new chaises since all are wicker, Cabanas, umbrellas
104 | 0900 - FF&E in Units | Fire Stops |  | GC | Year 1 | 37000 | 37000 |  |  | 0
108 | 1100- Specialties, Equipment & Furnishings | Signage - entry | Monument Sign | Capex | Year 1 | 30000 | 46414 |  |  | N/A |  | Monument Sign
21 | 0200 - Site Utilities & Improvements | Landscaping | the new shrubs look to be struggling to take root, some will need to be replace this summer | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | the new shrubs look to be struggling to take root, some will need to be replace this summer
17 | 0200 - Site Utilities & Improvements | Landscape irrigation | Irrigation drip line look to be questionable in multiple areas test and repair lines | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | Irrigation drip line look to be questionable in multiple areas test and repair lines
109 | 1100- Specialties, Equipment & Furnishings | Signage - site | Rebrand signage | Capex | Year 1 | 20000 | 108353 |  |  | N/A |  | Rebrand signage
18 | 0200 - Site Utilities & Improvements | Erosion control | down spouts empty onto river rock drainage, some are short others are long storm water has already caused erosion in some areas | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | down spouts empty onto river rock drainage, some are short others are long storm water has already caused erosion in some areas
124 | Fair Housing | Dumpster Enclosures | Reconfigure the walkway accessing the western and southwestern dumpster enclosures to provide a 60-inch turning radius Provide disabled accessible parking spaces, reconfigure curb cut ramp on building 5 Reconfigure sinks in disabled accessible units to orient garbage disposals | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | Reconfigure the walkway accessing the western and southwestern dumpster enclosures to provide a 60-inch turning radius Provide disabled accessible parking spaces, reconfigure curb cut ramp on building
125 | 1100- Specialties, Equipment & Furnishings | Dog Park | Dog Park refresh- sail shades, benches, water station | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Dog Park refresh- sail shades, benches, water station
117 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment (Determine Upon Stabilization) | Add rowing machine | PMC | Year 1 | 4000 | 237 |  |  | N/A |  | Add rowing machine
PROJECTS subtotal (excl. contingency/CM fee)

## Allora Bella Terra
Allora Bella Terra — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
77 | 0800 - Exterior Wall | Exterior building | Paint community | Capex | Year 1 | 345000 | 0 |  |  | N/A |  | Paint community
90 | 0900 - FF&E in Units | Flooring | Replace carpet throughout with LVP | Capex | Year 1 | 272700 | 6037.18 |  |  | N/A |  | Replace carpet throughout with LVP
119 | 1100- Specialties, Equipment & Furnishings | Pool Furniture & Games | Need 4-6 new in pool loungers, lounge seating, games, lounge seating needed by fire place | Capex | Year 1 | 60000 | 0 |  |  | N/A |  | Need 4-6 new in pool loungers, lounge seating, games, lounge seating needed by fire place
92 | 0900 - FF&E in Units | Pet yard enclosures | About 10 units we could add yards to | GC | Year 1 | 58000 | 58000 | 0 |  | 0 |  | About 10 units we could add yards to
21 | 0200 - Site Utilities & Improvements | Landscaping | Add landscaping in planters around pool. Look at hardier fan palms, can be smaller to reduce cost. | Capex | Year 1 | 50000 | 15834.57 |  |  | N/A |  | Add landscaping in planters around pool. Look at hardier fan palms, can be smaller to reduce cost.
76 | 0800 - Exterior Wall | Interior Hallway painting | Breezeway paint | Capex | Year 1 | 45000 | 0 |  |  | N/A |  | Breezeway paint
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Iif we are ok with the tuscan, somewhat dated look, there is minimal scope ($10k). | Capex | Year 1 | 40000 | 0 |  |  | N/A |  | Iif we are ok with the tuscan, somewhat dated look, there is minimal scope ($10k).
126 | 1100- Specialties, Equipment & Furnishings | Package Lockers | No need, have fetch, but can look at adding package lockers outside of mail area | Capex | Year 1 | 40000 | 26287 |  |  | N/A |  | No need, have fetch, but can look at adding package lockers outside of mail area
105 | 0900 - FF&E in Units | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | Capex | Year 1 | 36338 | 38947 |  |  | N/A |  | LowPro (Pair covers 4 burner range)- For range top microwaves
22 | 0200 - Site Utilities & Improvements | Landscaping- entry & in front of office | PCA- $19,500- Address bare areas throughout property Add seasonal color, add turf where needed | GC | Year 1 | 35000 | 35000 | 0 |  | 0 |  | PCA- $19,500- Address bare areas throughout property Add seasonal color, add turf where needed
152 | 1600 - Electrical | Common area light fixtures | Replace pole lights with LED | GC | Year 1 | 31000 | 31000 | 0 |  | 0 |  | Replace pole lights with LED
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | Same as the renovation scope, this can either be minimal (need to reupholster some items) if we keep the theme, or it will be substantial if we change it. | Capex | Year 1 | 30000 | 10173 |  |  | N/A |  | Same as the renovation scope, this can either be minimal (need to reupholster some items) if we keep the theme, or it will be substantial if we change it.
118 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Pool speaker needs repair, add lights in 6 planters. Turf around perimeter, bigger TV under gazebo | Capex | Year 1 | 30000 | 7776.27 |  |  | N/A |  | Pool speaker needs repair, add lights in 6 planters. Turf around perimeter, bigger TV under gazebo
129 | 1100- Specialties, Equipment & Furnishings | Repair or Repalce the Fire Extinguisher Cabinets | From MEP Report- The fire extinguisher cabinets throughout the residentail building breezeways are corroding. | Capex | Year 1 | 30000 | 35550 |  |  | N/A |  | From MEP Report- The fire extinguisher cabinets throughout the residentail building breezeways are corroding.
19 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Paint perimeter fence | GC | Year 1 | 26500 | 26500 | 0 |  | 0 |  | Paint perimeter fence
17 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair Irrigation | GC | Year 1 | 22600 | 22600 | 0 |  | 0 |  | inspect and repair Irrigation
32 | 0200 - Site Utilities & Improvements | Carports / Garages | Repair and paint Garages | GC | Year 1 | 22000 | 22000 | 0 |  | 0 |  | Repair and paint Garages
121 | 1100- Specialties, Equipment & Furnishings | Dog Park | Rubber matting for dog wash room, water station, shade structure, benches | Capex | Year 1 | 20000 | 13057 |  |  | N/A |  | Rubber matting for dog wash room, water station, shade structure, benches
122 | 1100- Specialties, Equipment & Furnishings | Unit Model Update | Add model furniture in 1 br unit, outside stepping stones in yard? | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Add model furniture in 1 br unit, outside stepping stones in yard?
128 | 1100- Specialties, Equipment & Furnishings | EV Chargers | Look at level 1 chargers for garages, manager feels they can upcharge | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Look at level 1 chargers for garages, manager feels they can upcharge
34 | 0200 - Site Utilities & Improvements | Pet yards | paint pet yard fencing | GC | Year 1 | 15000 | 15000 | 0 |  | 0 |  | paint pet yard fencing
59 | 0700 - Roofing | Asphalt composite shingle roofing | Roof inspection and minor repairs | GC | Year 1 | 15000 | 15000 | 0 |  | 0 |  | Roof inspection and minor repairs
106 | 0900 - FF&E in Units | Unit deferred maintenance | Painted sprinkler heads (82 total sprinklers observed in 42 units) | Capex | Year 1 | 15000 | 2783 |  |  | N/A |  | Painted sprinkler heads (82 total sprinklers observed in 42 units)
117 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Good equipment currently, request for cross fit equipment | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Good equipment currently, request for cross fit equipment
150 | 1600 - Electrical | Perform Infrared (IR) Scanning | The facility staff was not aware of IR scanning having been performed at the property. | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | From MEP Report- The facility staff was not aware of IR scanning having been performed at the property.
25 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | anti entrapment devices | GC | Year 1 | 12800 | 12800 | 0 |  | 0 |  | anti entrapment devices
46 | 0400 - Structure | Repair exterior stair railings | Secure railings | GC | Year 1 | 7500 | 7500 | 0 |  | 0 |  | Secure railings
47 | 0400 - Structure | Expansion Joints | Seal expansion joints | GC | Year 1 | 7500 | 7500 | 0 |  | 0 |  | Seal expansion joints
70 | 0800 - Exterior Wall | Repair / replace cement fiber siding |  | GC | Year 1 | 7500 | 7500 | 0 |  | 0
78 | 0800 - Exterior Wall | Repair / replace wood trim | minor trim replacement | GC | Year 1 | 7500 | 7500 | 0 |  | 0 |  | minor trim replacement
27 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Paint pool fence | GC | Year 1 | 6800 | 6800 | 0 |  | 0 |  | Paint pool fence
33 | 0200 - Site Utilities & Improvements | Dumpster enclosures | PCA- $1,500- Repair/replace gate as required Paint enclosure | GC | Year 1 | 6500 | 6500 | 0 |  | 0 |  | PCA- $1,500- Repair/replace gate as required Paint enclosure
149 | 1600 - Electrical | Electrical distribution | inspect and repair electric to pole lights | GC | Year 1 | 6500 | 6500 | 0 |  | 0 |  | inspect and repair electric to pole lights
10 | 0200 - Site Utilities & Improvements | Storm sewer piping | add stone around storm drains | GC | Year 1 | 6000 | 6000 | 0 |  | 0 |  | add stone around storm drains
31 | 0200 - Site Utilities & Improvements | Outdoor Fireplaces | Repair 2 outdoor fireplaces | GC | Year 1 | 5000 | 5000 | 0 |  | 0 |  | Repair 2 outdoor fireplaces
113 | 1100- Specialties, Equipment & Furnishings | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas
136 | 1400 - Plumbing | Scope and Clear the Sewer Lines | From MEP Report- Maintenance records were not provided before the report delvery date | PMC | Year 1 | 5000 | 374 |  |  | N/A |  | From MEP Report- Maintenance records were not provided before the report delvery date
144 | 1500- HVAC | Replace the Refrigerant Line Insulation | From MEP Report- The insulation on the refrigerant lines at nearly all of the condensing units is deteriorated and at one condenser the suction line had ice build up | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | From MEP Report- The insulation on the refrigerant lines at nearly all of the condensing units is deteriorated and at one condenser the suction line had ice build up
61 | 0700 - Roofing | Tile roofing | Repairs to clay tile roofs | GC | Year 1 | 4500 | 4500 | 0 |  | 0 |  | Repairs to clay tile roofs
65 | 0700 - Roofing | Flashing | Repair flashing over clay tile | GC | Year 1 | 4500 | 4500 | 0 |  | 0 |  | Repair flashing over clay tile
135 | 1400 - Plumbing | Water pressure regulator / back-flow preventer | Inspect and repair PVB's | GC | Year 1 | 3500 | 3500 | 0 |  | 0 |  | Inspect and repair PVB's
137 | 1400 - Plumbing | Inspect and Clean Oil-Water Separator | From MEP Report- Maintenance records were not supplied prior to the report delivery date. Therefore, Partner recommends that the oil- water separator go through a full service. | PMC | Year 1 | 3500 | 0 |  |  | N/A |  | From MEP Report- Maintenance records were not supplied prior to the report delivery date. Therefore, Partner recommends that the oil- water separator go through a full service.
116 | 1100- Specialties, Equipment & Furnishings | Fitness Center Remodel | Misc needs, fitness center looked good | PMC | Year 1 | 3000 | 810 |  |  | N/A |  | Misc needs, fitness center looked good
127 | 1100- Specialties, Equipment & Furnishings | Car wash area equipment | Hose or vacuum replacement, misc items | PMC | Year 1 | 2000 | 495 |  |  | N/A |  | Hose or vacuum replacement, misc items
143 | 1500- HVAC | Inspect and Repair Condenser Electrical Connection | From MEP Report- There were multiple electrical connections observed at condensing units where the weather tight flexible conduit had pull away from its connector. | PMC | Year 1 | 2000 | 0 |  |  | N/A |  | From MEP Report- There were multiple electrical connections observed at condensing units where the weather tight flexible conduit had pull away from its connector.
PROJECTS subtotal (excl. contingency/CM fee)
156 | Contingency & Fees | Contingency |  | CON | Contingency | 802262 | 0 | 0 |  | N/A
157 | Contingency & Fees | Construction Management Fee |  | CMF | CM Fee | 111150 | 0 | 0 |  | N/A

## Avonmora
Avonmora — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
52 | 84433 | Asphalt composite shingle roofing | Replace all roofs. Metal, flash, vents, and ridge | GC | Year 1 | 1344500 | 1344500 |  |  | 0 |  | Replace all roofs. Metal, flash, vents, and ridge
70 | 84207 | Interior Update Placeholder | Paint cabinets and new hardware, Flooring, resurface counters Appliances if possible | Capex | Year 1 | 1140000 | 207258 |  |  | N/A |  | Paint cabinets and new hardware, Flooring, resurface counters Appliances if possible
60 | 84101 | Exterior painting | repaint buildings 100% paintable | GC | Year 1 | 260000 | 260000 |  |  | 0 |  | repaint buildings 100% paintable
22 | 84303 | Perimeter fencing access control | Add thorny Pyracantha hedges alongside the fence which will grow into a natural barrier Shrubs are $80-$165 each installed, placed every 6’ for a quicker hedge formation, 3,000 linear feet= $82,500 $150k total is safe including irrigation, contingency, etc. | GC | Year 1 | 160000 | 160000 |  |  | 0 |  | Add thorny Pyracantha hedges alongside the fence which will grow into a natural barrier Shrubs are $80-$165 each installed, placed every 6’ for a quicker hedge formation, 3,000 linear feet= $82,500 $1
34 | 84435 | Jack & underpin foundations | Foundations on 3 buildings | GC | Year 1 | 93000 | 93000 |  |  | 0 |  | Foundations on 3 buildings
23 | 84303 | Landscaping | Landscape enhancements in office area and front entrances and 13-8 buildings on Wickersham Zeroscape | GC | Year 1 | 85000 | 85000 |  |  | 0 |  | Landscape enhancements in office area and front entrances and 13-8 buildings on Wickersham Zeroscape
26 | 84361 | Pool Deck | Replace pool deck with new stamped stained concrete | GC | Year 1 | 85000 | 85000 |  |  | 0 |  | Replace pool deck with new stamped stained concrete
27 | 84219 | Maintenance Shop Structure | Add Shop for golf carts | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Add Shop for golf carts
41 | 84104 | Repair balcony framing & decking | rebuild three balcony towers | GC | Year 1 | 46000 | 46000 |  |  | 0 |  | rebuild three balcony towers
134 | 84112 | Common area light fixtures | exterior building security lighting are pole lights and need new fixtures | GC | Year 1 | 38000 | 38000 |  |  | 0 |  | exterior building security lighting are pole lights and need new fixtures
24 | 84361 | Repair / replace swimming pool pumps | remove splash pad and fill, add turf for sitting area | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | remove splash pad and fill, add turf for sitting area
102 | 84360 | Pool Furniture | All new pool furniture and games | Capex | Year 1 | 35000 | 0 |  |  | N/A |  | All new pool furniture and games
19 | 84517 | Erosion | Backfill areas of erosion in Dog park, and throughout property | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Backfill areas of erosion in Dog park, and throughout property
25 | 84361 | Fences & gates - swimming pool | Pool fence replacement | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Pool fence replacement
101 | 84361 | Pool Area Remodel | Add plants or metal art in planters Landscape enhancements | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Add plants or metal art in planters Landscape enhancements
15 | 84385 | Storm sewer piping | Regrade area for proper drainage south west of creek | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Regrade area for proper drainage south west of creek
17 | 84221 | Sidewalks | repair trip hazards | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | repair trip hazards
96 | 84116 | Clubhouse / Office Remodel | Sitting area by leasing- New lounge furniture, replace shelving with art and TVs. Doors out to pool, pergola outside, seating Lounge area- speak with designer about ideas- games, more TVs, content sticks for TVs, furniture | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Sitting area by leasing- New lounge furniture, replace shelving with art and TVs. Doors out to pool, pergola outside, seating Lounge area- speak with designer about ideas- games, more TVs, content st
135 | 84112 | exterior lights | replace pool lights and correct electric for pool lights | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | replace pool lights and correct electric for pool lights
58 | 84105 | Repair / replace wood siding | repair loose siding | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | repair loose siding
18 | 84434 | Retaining walls | Repair three retaining walls | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Repair three retaining walls
28 | 84219 | Carports / Garages | repair car ports | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | repair car ports
61 | 84113 | Repair / replace soffits | repair stairwell soffit | GC | Year 1 | 14500 | 14500 |  |  | 0 |  | repair stairwell soffit
29 | 84111 | Dumpster enclosures | dumpster repairs | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | dumpster repairs
59 | 84206 | Repair stucco | repair damaged stucco | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | repair damaged stucco
62 | 84105 | Repair / replace wood trim | wood replacement | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | wood replacement
87 | 84304 | Sub Floor Repairs | Sub Floors | Capex | Year 1 | 10000 | 6100 |  |  | N/A |  | Sub Floors
39 | 84114 | Repair exterior stair treads and stringers | replace 80 stair treads | GC | Year 1 | 9250 | 9250 |  |  | 0 |  | replace 80 stair treads
63 | 84206 | Shutters | replace 50 pairs of shutters | GC | Year 1 | 9000 | 9000 |  |  | 0 |  | replace 50 pairs of shutters
53 | 84202 | Gutters & downspouts | Repair and replace damaged or missing gutters | GC | Year 1 | 8300 | 8300 |  |  | 0 |  | Repair and replace damaged or missing gutters
16 | 84201 | ADA parking & curb cuts | strip and repaint ADA ramps | GC | Year 1 | 7800 | 7800 |  |  | 0 |  | strip and repaint ADA ramps
54 | 84433 | Sealants & caulking and paint | sealant for stucco expansion joints | GC | Year 1 | 5300 | 5300 |  |  | 0 |  | sealant for stucco expansion joints
40 | 84121 | Repair exterior stair railings | repair and secure stair rails | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | repair and secure stair rails
106 | 84130 | Dog Park | Add benches and table | GC | Year 1 | 4000 | 4000 |  |  | 0 |  | Add benches and table
95 | 84905 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | PMC | Year 1 | 1000 | 750 |  |  | N/A |  | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas
PROJECTS subtotal (excl. contingency/CM fee)
141 | 84510 | Contingency | Contingency Amount | CON | Contingency | 20000 | 0 |  |  | N/A |  | Contingency Amount

## Bridgepoint
Bridgepoint — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
93 | 0900 - FF&E in Units | Unit Upgrades | See unit upgrade calc for detail | Capex | Year 1 | 1786097 | 606700 |  |  | N/A |  | See unit upgrade calc for detail |  | Completed
146 | 1500- HVAC | Replace AC condenser | Air conditioners at 40% conversion to 410-a, but not all replaced inside and out. Contingency for replacement of R-22 units MEP Item- Split system units - Older units are in poor condition with some non-functioning units observed. Replacement of non-functional units is recommended. | GC | Year 1 | 210000 | 27150 |  |  | 0 |  | Air conditioners at 40% conversion to 410-a, but not all replaced inside and out. Contingency for replacement of R-22 units MEP Item- Split system units - Older units are in poor condition with some |  | Completed
79 | 0800 - Exterior Wall | Exterior building | paint community | GC | Year 1 | 209000 | 209000 |  |  | 0 |  | 1st Call will paint entire building
103 | 0900 - FF&E in Units | Washers & Dryers- Basic front load | From Grid report 28 have connections, 115 have full size W/D, 45 don’t have connections | Capex | Year 1 | 109250 | 4132 |  |  | N/A |  | From Grid report 28 have connections, 115 have full size W/D, 45 don’t have connections |  | Completed
12 | 0200 - Site Utilities & Improvements | concrete pavement | Patch and repair damaged areas, replace existing speed bumps with monolithic speed bumps PCA Item- Linear cracking was observed near the office and near Buildings 1, 2, 5, and 8. Routing and sealing is recommended. | GC | Year 1 | 70000 | 70000 |  |  | 0 |  | Patch and repair damaged areas, replace existing speed bumps with monolithic speed bumps PCA Item- Linear cracking was observed near the office and near Buildings 1, 2, 5, and 8. Routing and sealing i
42 | 0300 - Excavation & Foundations | Jack & underpin foundations | Placeholder for foundation repairs on "2 buildings" | Capex | Year 1 | 70000 | 61600 |  |  | N/A |  | Placeholder for foundation repairs on "2 buildings" |  | Completed
22 | 0200 - Site Utilities & Improvements | Landscaping | Add river rock in high visibility bare areas Add french drains to address areas with flooding, particularly flooded unit patios | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Add river rock in high visibility bare areas Add french drains to address areas with flooding, particularly flooded unit patios
145 | 1500- HVAC | HVAC | Install AC pads on all units sitting on dirt, secure all unit access control panels MEP Item- Split system units - Condensing units at the apartment buildings were mounted in close proximity to the adjacent units in several locations. This condition limits heat rejection capacity and performance and could cause overheating at the units. Electrical connections at condensing units were in need of minor repairs. Insulation at the refrigerant line sets has deteriorated. Partner recommends the units be relocated, insulation be repaired and electrical connections repaired. Modification to the refrigerant lines and support pads are likely required. Several units were observed lacking supporting pads or mounted atop unstable or inadequate supports. Installation of adequate supports is recommended. | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Install AC pads on all units sitting on dirt, secure all unit access control panels MEP Item- Split system units - Condensing units at the apartment buildings were mounted in close proximity to the a
23 | 0200 - Site Utilities & Improvements | Resurface swimming pool | resurface | GC | Year 1 | 38000 | 38000 |  |  | 0 |  | Resurface 1 pool
16 | 0200 - Site Utilities & Improvements | Sidewalks | Mortar expansion joints between curb and sidewalk PCA Item- Differential settlement between the curb and the sidewalk was observed at select areas of the subject property; some examples are near Buildings 2, 4, 11, 13, and 15. Additionally, worn, rough, and degraded sidewalk was observed near Buildings 1, 2, 4, 5, and 11. Repair of the noted areas is recommended. | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | Mortar expansion joints between curb and sidewalk PCA Item- Differential settlement between the curb and the sidewalk was observed at select areas of the subject property; some examples are near Buil
19 | 0200 - Site Utilities & Improvements | Fences & gates - site perimeter | Straighten and add additional side to wooden privacy fence between communities | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Straighten and add additional side to wooden privacy fence between communities
119 | 1100- Specialties, Equipment & Furnishings | Pool Furniture | All new furniture, move current tables and chairs to other areas at property | Capex | Year 1 | 35000 | 0 |  |  | N/A |  | All new furniture, move current tables and chairs to other areas at property
82 | 0800 - Exterior Wall | Replace unit entry doors - exterior | Placeholder to replace up to 50 doors throughout property | Capex | Year 1 | 31500 | 0 |  |  | N/A |  | Placeholder to replace up to 50 doors throughout property
153 | 1600 - Electrical | Common area light fixtures | Replace wall packs on buildings | GC | Year 1 | 31000 | 31000 |  |  | 0 |  | Replace wall packs on buildings
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Work with designer on options for Repaint Other finishes including backsplash and counters New art on walls New TV above fireplace Possible Cabinet refacing and different hardware Need to fix roof leak | Capex | Year 1 | 30000 | 20424 |  |  | N/A |  | Work with designer on options for Repaint Other finishes including backsplash and counters New art on walls New TV above fireplace Possible Cabinet refacing and different hardware Need to fix roof lea |  | Completed
120 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Area Remodel | Grill by pool- turf under entire grill area, add gazebo, convert pergola over grill to gazebo | Capex | Year 1 | 30000 | 18900 |  |  | N/A |  | Grill by pool- turf under entire grill area, add gazebo, convert pergola over grill to gazebo |  | Completed
154 | 1600 - Electrical | Replace additional lights | Replace pole light fixtures | GC | Year 1 | 28000 | 28000 |  |  | 0 |  | Replace pole light fixtures
18 | 0200 - Site Utilities & Improvements | Erosion control | Property Erosion Control | GC | Year 1 | 25500 | 25500 |  |  | 0
109 | 1100- Specialties, Equipment & Furnishings | Signage - Entry Monument | Explore adding monument sign | Capex | Year 1 | 25000 | 6510 |  |  | N/A |  | Explore adding monument sign |  | Not Started | Will add to 2027 budget for office sign
106 | 0900 - FF&E in Units | Pet Yards | Test 4 per yards on tour path- turf with vinyl or iron fence and privacy screen | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Test 4 per yards on tour path- turf with vinyl or iron fence and privacy screen
10 | 0200 - Site Utilities & Improvements | Storm sewer piping | Clean out yard drains PCA Item- It was reported that storm water ponds around Building 2 and 6. Partner observed sandbags around some of the perimeters of these buildings. Unit 204 was noted to contain damage from water intrusion; approximately six square feet of drywall was missing near the floor in the living room. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Clean out yard drains PCA Item- It was reported that storm water ponds around Building 2 and 6. Partner observed sandbags around some of the perimeters of these buildings. Unit 204 was noted to contai
123 | 1100- Specialties, Equipment & Furnishings | Dog Park | Water/Wash Station with concrete pad ($6k) Add gazebo or shade sail Furniture next to laundry area | Capex | Year 1 | 20000 | 15888 |  |  | N/A |  | Water/Wash Station with concrete pad ($6k) Add gazebo or shade sail Furniture next to laundry area |  | Completed
151 | 1600 - Electrical | Electrical distribution | Inspect and repair lighting controllers on all buildings "additional wiring requirements are not included" MEP Item- Electrical Repairs - Electrical systems at the site appeared to be in fair to poor overall condition. Several exterior junction boxes and disconnects were observed missing cover plates. Melted wire insulation was observed at connection points at mainbreaker boxes and within apartment breaker panels, Rust was observed at ground busses at main breaker boxes. Evidence of electrical failure, including burn marks at the breaker buss was observed. Site repairs of the electrical systems is recommended. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Inspect and repair lighting controllers on all buildings "additional wiring requirements are not included" MEP Item- Electrical Repairs - Electrical systems at the site appeared to be in fair to poor
52 | 0400 - Structure | Repair exterior stair treads and stringers | replace 140 stair treads across property | GC | Year 1 | 18900 | 18900 |  |  | 0 |  | replace 140 stair treads across property
13 | 0200 - Site Utilities & Improvements | Stripe parking areas | Entire property | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Entire property
17 | 0200 - Site Utilities & Improvements | Landscape irrigation | Inspect and repair Irrigation | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Inspect and repair Irrigation
33 | 0200 - Site Utilities & Improvements | Carports / Garages | Repair and paint | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Repair and paint
30 | 0200 - Site Utilities & Improvements | Dog Park | Replace 225 ft of fencing, replace bench with moveable bench | GC | Year 1 | 17400 | 17400 |  |  | 0 |  | Replace 225 ft of fencing, replace bench with moveable bench
47 | 0400 - Structure | Concrete deck / floor fill |  | GC | Year 1 | 17000 | 17000 |  |  | 0
65 | 0700 - Roofing | Gutters & downspouts | repitch and clean | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | repitch and clean
66 | 0700 - Roofing | Flashing | siding flashing | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | siding flashing
80 | 0800 - Exterior Wall | Repair / replace wood trim | replace rotted trim/fascia/band boards | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | replace rotted trim/fascia/band boards
117 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Add more equipment along walkway, add storage | Capex | Year 1 | 16000 | 22538 |  |  | N/A |  | Add more equipment along walkway, add storage
111 | 1100- Specialties, Equipment & Furnishings | Signage - Building identification | New to match paint | Capex | Year 1 | 15000 | 104 |  |  | N/A |  | New to match paint |  | Completed
116 | 1100- Specialties, Equipment & Furnishings | Fitness Center Remodel | Paint, add lighting, add water fountain, add 2 TVs, look at adding fans | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Paint, add lighting, add water fountain, add 2 TVs, look at adding fans
122 | 1100- Specialties, Equipment & Furnishings | Sports Courts | Convert old tennis court to pickleball- need to resurface and stripe, and add nets, bring surrounding soil back up to slab | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Convert old tennis court to pickleball- need to resurface and stripe, and add nets, bring surrounding soil back up to slab
25 | 0200 - Site Utilities & Improvements | Replace swimming pool deck | pressure wash, replace expansion joint materials and deck o seal | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | pressure wash, replace expansion joint materials and deck o seal
29 | 0200 - Site Utilities & Improvements | Pergola court | repair, stain and seal pergolas over grill areas | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | repair, stain and seal pergolas over grill areas
21 | 0200 - Site Utilities & Improvements | Landscaping | remove dead tree stumps on site | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | remove dead tree stumps on site
131 | 1100- Specialties, Equipment & Furnishings | Security Camera System | No urgent need, would be nice to have for monitoring | Capex | Year 1 | 10000 | 326 |  |  | N/A |  | No urgent need, would be nice to have for monitoring |  | Not Started
141 | 1400 - Plumbing | Sanitary sewer piping | MEP Item- Industry best practices typically include clearing sanitary waste lines every 18- to 24-months. Partner recommends that the sewer lines be cleared in the immediate term. Sewer scope report found 1 section of the line that is 80% collapsed, need to repair | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | MEP Item- Industry best practices typically include clearing sanitary waste lines every 18- to 24-months. Partner recommends that the sewer lines be cleared in the immediate term. Sewer scope report f
104 | 0900 - FF&E in Units | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | PMC | Year 1 | 9570 | 7663 |  |  | N/A |  | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods |  | Completed
24 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | retile pool | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | retile pool
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair door and paint | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | Repair door and paint
15 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts | Repair damaged curbs | GC | Year 1 | 9300 | 9300 |  |  | 0 |  | Repair damaged curbs
28 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | paint and repair | GC | Year 1 | 9300 | 9300 |  |  | 0 |  | paint and repair
67 | 0700 - Roofing | Sealants & caulking |  | GC | Year 1 | 8000 | 8000 |  |  | 0
107 | 0900 - FF&E in Units | Down Unit | PCA Item- Unit 514 was observed to be down due to a recent fire that was started by a candle in the bathroom of the unit. Smoke and fire damage was observed within the unit. According to property management, approximately $5,000 worth of repairs are needed. Partner recommends performing repairs to the unit. | PMC | Year 1 | 8000 | 12627 |  |  | N/A |  | PCA Item- Unit 514 was observed to be down due to a recent fire that was started by a candle in the bathroom of the unit. Smoke and fire damage was observed within the unit. According to property mana
135 | 1100- Specialties, Equipment & Furnishings | Golf Cart | Need maintenance cart | PMC | Year 1 | 8000 | 8669 |  |  | N/A |  | Need maintenance cart
53 | 0400 - Structure | Repair exterior stair railings | secure stair railings | GC | Year 1 | 5100 | 5100 |  |  | 0 |  | secure stair railings
113 | 1100- Specialties, Equipment & Furnishings | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas Office chairs and other miscellaneous Items Add picnic tables, chairs, games Look at adding storage, other misc landscaping and needs | Capex | Year 1 | 43000 | 38328 |  |  | N/A |  | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas |  | Completed
71 | 0800 - Exterior Wall | Repair / replace cement fiber siding |  | GC | Year 1 | 3400 | 3400 |  |  | 0
74 | 0800 - Exterior Wall | Dryer Vents | Just cleaned, no cleaning needed. Need to replace some flappers | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Just cleaned, no cleaning needed. Need to replace some flappers
127 | 1100- Specialties, Equipment & Furnishings | Computers | 2 new comupters for clubhouse resident use | PMC | Year 1 | 2000 | 7742 |  |  | N/A |  | 2 new comupters for clubhouse resident use
48 | 0400 - Structure | Wall framing | seal penetrations in landings | GC | Year 1 | 1700 | 1700 |  |  | 0 |  | seal penetrations in landings
37 | 0200 - Site Utilities & Improvements | Compactor door out of place | TAM team has bid to repair | GC | Year 1 | 1500 | 1500 |  |  | 0 |  | TAM team has bid to repair
133 | 1100- Specialties, Equipment & Furnishings | Fire Extinguishers | PCA Item- Expired certification tags were present at the fire extinguishers in common area breezeways. Servicing and re-certification of the fire extinguishers is recommended. | PMC | Year 1 | 1000 | 500 |  |  | N/A |  | PCA Item- Expired certification tags were present at the fire extinguishers in common area breezeways. Servicing and re-certification of the fire extinguishers is recommended. |  | Completed
126 | 1100- Specialties, Equipment & Furnishings | Access Control System | Replace keypad on fitness center door | GC | Year 1 | 500 | 500 |  |  | 0 |  | Replace keypad on fitness center door
PROJECTS subtotal (excl. contingency/CM fee)
159 | Contingency & Fees | Construction Management Fee |  | CMF | CM Fee | 174000 | 0 | 0 |  | N/A
158 | Contingency & Fees | Contingency |  | CON | Contingency | 90985 | 0 | 0 |  | N/A

## Cityscape
Cityscape — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
141 | 83515 | Green Initiatives | Green Program | GC | Year 1 | 100000 | 100000 |  |  | 0 |  | Green Program
112 | 84239 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | Capex | Year 1 | 28634 | 44122 |  |  | N/A |  | LowPro (Pair covers 4 burner range)- For range top microwaves
21 | 84102 | Concrete pavement | Remove and replace 10,000 LF of failing expansion joint material | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Remove and replace 10,000 LF of failing expansion joint material
16 | 84303 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
120 | 84116 | Clubhouse / Office Remodel | Add controlled access for clubhouse for rentals | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Add controlled access for clubhouse for rentals
122 | 84190 | Fitness Center Remodel | Add lighting around perimeter soffit | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Add lighting around perimeter soffit
PROJECTS subtotal (excl. contingency/CM fee)
164 | 84510 | Contingency | Contingency Amount | CON | Contingency | 17164 | 0 | 0 |  | N/A |  | Contingency Amount
165 | 84505 | Construction Management Fee | CM Fee | CMF | Contingency | 9440 | 9440 | 0 |  | N/A |  | CM Fee

## Discovery Park
Discovery Park — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
22 | 0200 - Site Utilities & Improvements | Carports | Look at adding, garages are sold out so there is a need | GC | Year 1 | 152000 | 152000 |  |  | 0 |  | Look at adding, garages are sold out so there is a need
11 | 0200 - Site Utilities & Improvements | Concrete Pavement | From PCA- Replace the large area of prior-repaired concrete pavement near the southwest corner of Building 1 due to significant overt cracking throughout | GC | Year 1 | 43750 | 43750 |  |  | 0 |  | From PCA- Replace the large area of prior-repaired concrete pavement near the southwest corner of Building 1 due to significant overt cracking throughout
129 | 1100- Specialties, Equipment & Furnishings | Pool Furniture | New side tables, new lounge seating or at least replace cushions on existing wicker seating. 1-2 new cabanas or more chaise lounges to replace 3 pyramid daybeds Cornhole & ping pong | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | New side tables, new lounge seating or at least replace cushions on existing wicker seating. 1-2 new cabanas or more chaise lounges to replace 3 pyramid daybeds Cornhole & ping pong
161 | 1600 - Electrical | Fire and Sprinklers | Add anti freeze to hallway and patio sprinkler systems | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Add anti freeze to hallway and patio sprinkler systems
20 | 0200 - Site Utilities & Improvements | Resurface swimming pool | Resurface Pool | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Resurface Pool
112 | 0900 - FF&E in Units | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | GC | Year 1 | 30069 | 30069 |  |  | 0 |  | LowPro (Pair covers 4 burner range)- For range top microwaves
127 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Allowance for supplemental equipment and replacements for cycling room and gym | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Allowance for supplemental equipment and replacements for cycling room and gym
140 | 1100- Specialties, Equipment & Furnishings | Rubber Mats for Breezeway transitions for Non-Slip S |  | GC | Year 1 | 25000 | 25000 |  |  | 0
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair Irrigation | GC | Year 1 | 22600 | 22600 |  |  | 0 |  | inspect and repair Irrigation
13 | 0200 - Site Utilities & Improvements | Concrete Pavement | From PCA- Allowance to replace the deteriorated sealant in the concrete pavement joints | GC | Year 1 | 21700 | 21700 |  |  | 0 |  | From PCA- Allowance to replace the deteriorated sealant in the concrete pavement joints
45 | 0200 - Site Utilities & Improvements | Dryer Vents | Clean, fix any flapper valves | GC | Year 1 | 21225 | 21225 |  |  | 0 |  | Clean, fix any flapper valves
44 | 0200 - Site Utilities & Improvements | Soffit beam supports appear to be separating in some |  | GC | Year 1 | 20000 | 20000 |  |  | 0
121 | 1100- Specialties, Equipment & Furnishings | Signage- Monument | Look at adding monument sign | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Look at adding monument sign
154 | 1500- HVAC | Repair HVAC in fitness center |  | GC | Year 1 | 20000 | 20000 |  |  | 0
160 | 1600 - Electrical | Electrical distribution | Electric for car ports- Remove if we don’t add car ports | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Electric for car ports- Remove if we don’t add car ports
123 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | Misc items, new pool table? | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Misc items, new pool table?
24 | 0200 - Site Utilities & Improvements | Pet yards | paint pet yard fencing | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | paint pet yard fencing
54 | 0400 - Structure | Roof deck | Secure Decking while doing roof tune-up | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Secure Decking while doing roof tune-up
67 | 0700 - Roofing | Asphalt composite shingle roofing | Roof inspection and minor repairs | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Roof inspection and minor repairs
119 | 1100- Specialties, Equipment & Furnishings | Signage - Building identification | Need better signage at leasing office, new garage number signs to replace current faded ones, new window shade branded decals on exterior of basketball gym to replace current peeling ones | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Need better signage at leasing office, new garage number signs to replace current faded ones, new window shade branded decals on exterior of basketball gym to replace current peeling ones
133 | 1100- Specialties, Equipment & Furnishings | Dog Park | Water/Wash Station with concrete pad ($6k) Shade sail or pergola Look at adding additional Dog Park across road | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Water/Wash Station with concrete pad ($6k) Shade sail or pergola Look at adding additional Dog Park across road
162 | 1600 - Electrical | Common area light fixtures | Lighting for carports | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Lighting for carports
113 | 0900 - FF&E in Units | Fire protection | Fix heads with overspray- allowance | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Fix heads with overspray- allowance
122 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Placeholder for minor items | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Placeholder for minor items
37 | 0200 - Site Utilities & Improvements | Dog Park Fence | Repair and repaint fence, replace or fix broken gate hinge and bring latches down to FHAA compliant height | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | Repair and repaint fence, replace or fix broken gate hinge and bring latches down to FHAA compliant height
46 | 0200 - Site Utilities & Improvements | Garages | Replace at least 6 dented garage doors (G115 is the worst) | GC | Year 1 | 8800 | 8800 |  |  | 0 |  | Replace at least 6 dented garage doors (G115 is the worst)
80 | 0800 - Exterior Wall | Repair / replace wood trim | minor trim replacement | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | minor trim replacement
124 | 1100- Specialties, Equipment & Furnishings | Indoor Basketball Area Repairs | Restripe basketball court Fix leak in roof and repair damage at ceiling Repair wall chips behind hoop Fix chipped paint above door and throughout Replaceme motor/winch for raising basketball hoop | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Restripe basketball court Fix leak in roof and repair damage at ceiling Repair wall chips behind hoop Fix chipped paint above door and throughout Replaceme motor/winch for raising basketball hoop
10 | 0200 - Site Utilities & Improvements | Storm sewer piping | add stone around storm drains | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | add stone around storm drains
78 | 0800 - Exterior Wall | Repair / replace cement fiber siding |  | GC | Year 1 | 7500 | 7500 |  |  | 0
21 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | anti entrapment devices | GC | Year 1 | 6800 | 6800 |  |  | 0 |  | anti entrapment devices
136 | 1100- Specialties, Equipment & Furnishings | Access Control System | Need to add access control at 2 doors from pool to business center and to restrooms | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Need to add access control at 2 doors from pool to business center and to restrooms
18 | 0200 - Site Utilities & Improvements | Accessibility | From PCA- Ramps are provided on the first floor of the buildings to address changes in the slab elevations. Handrails are placed to the sides of each ramp; however, in most instances, the handrails do not have the required extensions beyond the ramps and in one instance at Building 3, the handrail does not continue to the end of the ramp. Also at Building 3, one of the stairs adjacent to a ramp does not have the proper handrail extension at the top of the flight. An allowance is included to review each common path breezeway and appropriately modify the handrails for FHAA compliance. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | From PCA- Ramps are provided on the first floor of the buildings to address changes in the slab elevations. Handrails are placed to the sides of each ramp; however, in most instances, the handrails do
75 | 0700 - Roofing | Articulating Lift Rental |  | GC | Year 1 | 5000 | 5000 |  |  | 0
114 | 0900 - FF&E in Units | Unit deferred maintenance | Sub floor repairs | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Sub floor repairs
128 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Replace bamboo screen around pool equipment room with better screen, misc repairs and pool equipment | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Replace bamboo screen around pool equipment room with better screen, misc repairs and pool equipment
12 | 0200 - Site Utilities & Improvements | Concrete Pavement | From PCA- Allowance to repair all areas of random pavement cracks scattered throughout the parking areas | GC | Year 1 | 4500 | 4500 |  |  | 0 |  | From PCA- Allowance to repair all areas of random pavement cracks scattered throughout the parking areas
23 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Paint enclosure | GC | Year 1 | 4500 | 4500 |  |  | 0 |  | Paint enclosure
146 | 1400 - Plumbing | Water pressure regulator / back-flow preventer | inspect and repair PVB's | GC | Year 1 | 3500 | 3500 |  |  | 0 |  | inspect and repair PVB's
15 | 0200 - Site Utilities & Improvements | Sidewalk Railing | From PCA- Install a guardrail along the east edge of the wide sidewalk leading to the maintenance garage where the adjacent grade within 36" of the sidewalk drops more than 30" | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | From PCA- Install a guardrail along the east edge of the wide sidewalk leading to the maintenance garage where the adjacent grade within 36" of the sidewalk drops more than 30"
16 | 0200 - Site Utilities & Improvements | Concrete Stairs | From PCA- Due to the muddy, deteriorated landscape conditions at the fire sprinkler riser room of Building 1 discussed in Section 3.2.4 and the significant transition from grade to the floor of the room, it is recommended that property ownership consider constructing stairs to access this room as part of future property enhancements. A similar elevation change is also at Building 3 which should also be considered for future installation of access stairs | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | From PCA- Due to the muddy, deteriorated landscape conditions at the fire sprinkler riser room of Building 1 discussed in Section 3.2.4 and the significant transition from grade to the floor of the ro
17 | 0200 - Site Utilities & Improvements | Accessibility | From PCA- Install edge protection at the base of the guardrail along the west side of the pool deck for FHAA compliance | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | From PCA- Install edge protection at the base of the guardrail along the west side of the pool deck for FHAA compliance
49 | 0300 - Excavation & Foundations | Foundation Repair | Review all exposed areas and appropriately repair any foundation cracking such as the ones noted near garage G505 on Building 5, the linear cracks in the common area corridor/breezeway of Building 1 and the deteriorated joint sealant at the breezeway of Building 4 | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Review all exposed areas and appropriately repair any foundation cracking such as the ones noted near garage G505 on Building 5, the linear cracks in the common area corridor/breezeway of Building 1 a
126 | 1100- Specialties, Equipment & Furnishings | Fitness Center Remodel | Allowance for minor repairs | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Allowance for minor repairs
125 | 1100- Specialties, Equipment & Furnishings | Indoor Basketball Area Furniture | Replace 2 long benches | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | Replace 2 long benches
132 | 1100- Specialties, Equipment & Furnishings | Business Center & Office Computers | 1 computer is cracked and needs to be replaced. | PMC | Year 1 | 1500 | 5287 |  |  | N/A |  | 1 computer is cracked and needs to be replaced.
14 | 0200 - Site Utilities & Improvements | Sidewalk Repair | From PCA- Area of heaving adjacent to the pavement curb near the southwest corner of Building 4 and deteriorated sealant in the joint between this same stretch of sidewalk and the adjacent curb. | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | From PCA- Area of heaving adjacent to the pavement curb near the southwest corner of Building 4 and deteriorated sealant in the joint between this same stretch of sidewalk and the adjacent curb.
142 | 1100- Specialties, Equipment & Furnishings | Cigarette Urns | Per Shelly, look at adding smoking urns where needed to reduce cigarette butts throughout property | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | Per Shelly, look at adding smoking urns where needed to reduce cigarette butts throughout property
PROJECTS subtotal (excl. contingency/CM fee)
168 | Contingency & Fees | Construction Management Fee |  | CMF | CM Fee | 40222 | 0 | 0 |  | N/A
167 | Contingency & Fees | Contingency |  | CON | Contingency | 20000 | 0 | 0 |  | N/A

## Hampton Courts
Hampton Courts — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
71 | 7200-0013 | Paint community - working with Keys | Paint community - working with Keys | GC | Year 1 | 340000 | 408000 |  |  | 0 |  | Paint community - working with Keys
101 | 7400-0041 | 170 units we could add washer dryers - Team to orde | 170 units we could add washer dryers - Team to order stock and install on turn, reno, WO, PM | Capex | Year 1 | 221000 | 49850 |  |  | N/A |  | 170 units we could add washer dryers - Team to order stock and install on turn, reno, WO, PM
147 | 7200-0033 | PCA Item- $690,000- The maintenance supervisor repor | PCA Item- $690,000- The maintenance supervisor reported that roughly 50% of the heat pump condensers are from the original 1986 construction, and roughly 50% of the FCUs are from the original 1986 construction. The equipment is typically given an EUL between 15- and 20-years. Spend as needed | Capex | Year 1 | 200000 | 115052 |  |  | N/A |  | PCA Item- $690,000- The maintenance supervisor reported that roughly 50% of the heat pump condensers are from the original 1986 construction, and roughly 50% of the FCUs are from the original 1986 con
17 | 7200-0064 | Seal Coat asphalt PCA Item- $1,725- Limited surface | Seal Coat asphalt PCA Item- $1,725- Limited surface linear cracking and “map” or “alligator” cracking were noted along the drive aisle to the south of Building O. Repair of the noted area is recommended. | GC | Year 1 | 81000 | 81000 |  |  | 0 |  | Seal Coat asphalt PCA Item- $1,725- Limited surface linear cracking and “map” or “alligator” cracking were noted along the drive aisle to the south of Building O. Repair of the noted area is recommend | [5 empty] | 2025-09-10
140 | 7200-0007 | PCA Item- $276,000- The maintenance supervisor repor | PCA Item- $276,000- The maintenance supervisor reported that roughly 50% of the domestic water heaters are from the original 1986 construction. Electric, storage-type water heaters of this type have an estimated end of useful life (EUL) of 15-years. Spend as needed | Capex | Year 1 | 80000 | 14127 |  |  | N/A |  | PCA Item- $276,000- The maintenance supervisor reported that roughly 50% of the domestic water heaters are from the original 1986 construction. Electric, storage-type water heaters of this type have a
117 | 7200-0027 | New furniture - Keys | New furniture - Keys | Capex | Year 1 | 75000 | 44320 |  |  | N/A |  | New furniture - Keys
116 | 7200-0032 | New carpeting in corridor and on stairs, lots of dry | New carpeting in corridor and on stairs, lots of drywall repairs | GC | Year 1 | 60000 | 60000 |  |  | 0 |  | New carpeting in corridor and on stairs, lots of drywall repairs
121 | 7200-0061 | Supplement or replace furniture, add games - Keys | Supplement or replace furniture, add games - Keys | Capex | Year 1 | 60000 | 75025 |  |  | N/A |  | Supplement or replace furniture, add games - Keys
63 | 7200-0002 | Clubhouse needs new roof, property received bid for | Clubhouse needs new roof, property received bid for $40-$50k to replace | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Clubhouse needs new roof, property received bid for $40-$50k to replace
130 | 7200-0055 | Needed, would need to find space outside or repurpos | Needed, would need to find space outside or repurpose laundry room if possible - explore options | Capex | Year 1 | 50000 | 3840 |  |  | N/A |  | Needed, would need to find space outside or repurpose laundry room if possible - explore options
19 | 7200-0045 | Initial property tree trim around buildings, landsca | Initial property tree trim around buildings, landscape cleanup, entry and tour path enhancements, etc. PCA Item- $5,000- Vegetation was noted to be heavily overgrown at most areas adjacent to buildings, particularly surrounding the HVAC pad-mounted condensing units. Trimming/removal of overgrown vegetation is required at this time. | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Initial property tree trim around buildings, landscape cleanup, entry and tour path enhancements, etc. PCA Item- $5,000- Vegetation was noted to be heavily overgrown at most areas adjacent to building
119 | 7200-0074 | New equipment to supplement existing - Keys | New equipment to supplement existing - Keys | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | New equipment to supplement existing - Keys
124 | 7200-0059 | Pickleball courts in decent shape, budget for resurf | Pickleball courts in decent shape, budget for resurfacing and concrete repair since blue surface is loose in places with water coming up through cracks. Lights not functional, paint poles | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Pickleball courts in decent shape, budget for resurfacing and concrete repair since blue surface is loose in places with water coming up through cracks. Lights not functional, paint poles
62 | 7200-0012 | Seal edges of delaminated cedar | Seal edges of delaminated cedar | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | Seal edges of delaminated cedar
154 | 7200-0040 | Replace wall packs | Replace wall packs | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | Replace wall packs
59 | 7200-0002 | Roof tune up include chimney | Roof tune up include chimney | GC | Year 1 | 34000 | 34000 |  |  | 0 |  | Roof tune up include chimney
105 | 7400-0038 | LowPro (Pair covers 4 burner range)- For range top m | LowPro (Pair covers 4 burner range)- For range top microwaves (assuming current hoods are replaced with OTR microwaves) | Capex | Year 1 | 32258 | 32130 |  |  | N/A |  | LowPro (Pair covers 4 burner range)- For range top microwaves (assuming current hoods are replaced with OTR microwaves)
15 | 7200-0064 | Repair pot holes | Repair pot holes | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Repair pot holes
100 | 7400-0040 | 99 units with missing GFCIs in the kitchen across di | 99 units with missing GFCIs in the kitchen across different buildings and renovation levels - Team to order stock and install on turn, reno, WO, PM | Capex | Year 1 | 29700 | 55200 |  |  | N/A |  | 99 units with missing GFCIs in the kitchen across different buildings and renovation levels - Team to order stock and install on turn, reno, WO, PM
70 | 7200-0012 | Replace rotted cedar siding | Replace rotted cedar siding | GC | Year 1 | 27000 | 27000 |  |  | 0 |  | Replace rotted cedar siding
122 | 7200-0060 | Look at adding a picnic area or enhance existing gri | Look at adding a picnic area or enhance existing grill, add gazebo - Keys | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Look at adding a picnic area or enhance existing grill, add gazebo - Keys
72 | 7200-0012 | Replace rotted fascia and trim - work in conjunctio | Replace rotted fascia and trim - work in conjunction with bat removal | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Replace rotted fascia and trim - work in conjunction with bat removal
153 | 7200-0040 | inspect and repair electric for exposed electrical l | inspect and repair electric for exposed electrical lines in lighting systems . PCA Item- $3,000- Repair electrical distribution trough - One exterior electrical distribution trough was observed to be in poor condition at the clubhouse. The enclosure was detached from the building structure, and the cover no-longer closes properly. | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | inspect and repair electric for exposed electrical lines in lighting systems . PCA Item- $3,000- Repair electrical distribution trough - One exterior electrical distribution trough was observed to be
103 | 7200-0041 | Done every fall, budget for cleaning after takeover | Done every fall, budget for cleaning after takeover | GC | Year 1 | 20700 | 20700 |  |  | 0 |  | Done every fall, budget for cleaning after takeover
16 | 7200-0064 | Stripe Parking | Stripe Parking | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Stripe Parking | [5 empty] | 2025-09-10
109 | 7400-0032 | Evidence of water infiltration observed (20)- Units | Evidence of water infiltration observed (20)- Units - COMPLETE BEFORE TAKEOVER | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Evidence of water infiltration observed (20)- Units - COMPLETE BEFORE TAKEOVER
18 | 7200-0064 | Repair trip hazards PCA Item- $3,000- A significant | Repair trip hazards PCA Item- $3,000- A significant area of heaved concrete was observed in the sidewalk at the south of Building B. | GC | Year 1 | 18500 | 18500 |  |  | 0 |  | Repair trip hazards PCA Item- $3,000- A significant area of heaved concrete was observed in the sidewalk at the south of Building B.
61 | 7200-0017 | secure and clean gutters | secure and clean gutters | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | secure and clean gutters
126 | 7200-0037 | New furniture in model unit - Keys | New furniture in model unit - Keys | Capex | Year 1 | 18000 | 0 |  |  | N/A |  | New furniture in model unit - Keys
73 | 7200-0023 | Replace damaged storage doors | Replace damaged storage doors | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | Replace damaged storage doors
112 | 7400-0053 | Allowance | Allowance | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Allowance
118 | 7200-0032 | Paint, lighting, flooring is ok - frost the glass an | Paint, lighting, flooring is ok - frost the glass and possibly add sound dampening panels to upper walls | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Paint, lighting, flooring is ok - frost the glass and possibly add sound dampening panels to upper walls
125 | 7200-0048 | Allowance for Dog Park enhancements - adding enzyme | Allowance for Dog Park enhancements - adding enzyme injector | Capex | Year 1 | 15000 | 8876 |  |  | N/A |  | Allowance for Dog Park enhancements - adding enzyme injector
133 |  | Have 10 cameras and good coverage, allowance for som | Have 10 cameras and good coverage, allowance for some additional cameras | Capex | Year 1 | 15000 | 1116 |  |  | N/A |  | Have 10 cameras and good coverage, allowance for some additional cameras
134 | 7200-0066 | Need storage for maintenance and inventory - mainten | Need storage for maintenance and inventory - maintenance shop clean up first. If still not enough space, add used Conex - site team to find locations | Capex | Year 1 | 15000 | 1760 |  |  | N/A |  | Need storage for maintenance and inventory - maintenance shop clean up first. If still not enough space, add used Conex - site team to find locations
48 | 7200-0016 | Repair loose pickets | Repair loose pickets | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Repair loose pickets
60 | 7200-0002 | Seal flat roof on club building - option to replace | Seal flat roof on club building - option to replace soon to fail skylight. Pushes cost to $30k | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Seal flat roof on club building - option to replace soon to fail skylight. Pushes cost to $30k
20 | 7200-0057 | Anti entrapment devices | Anti entrapment devices | GC | Year 1 | 12800 | 12800 |  |  | 0 |  | Anti entrapment devices
155 | 7200-0040 | Replace pole lights around pool | Replace pole lights around pool | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Replace pole lights around pool
150 | 7200-0033 | HVAC lines are under sized, need to replace. - As ne | HVAC lines are under sized, need to replace. - As needed | Capex | Year 1 | 10000 | 3770 |  |  | N/A |  | HVAC lines are under sized, need to replace. - As needed
49 | 7400-0015 | Repair Balconies | Repair Balconies | GC | Year 1 | 9000 | 9000 |  |  | 0 |  | Repair Balconies
50 | 7200-0016 | secure railings | secure railings | GC | Year 1 | 8600 | 8600 |  |  | 0 |  | secure railings
23 | 7200-0081 | Repair and paint compactor enclosure | Repair and paint compactor enclosure | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | Repair and paint compactor enclosure
46 | 7200-0012 | replace damaged framing in gable ends | replace damaged framing in gable ends | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | replace damaged framing in gable ends
148 | 7200-0033 | PCA Item- $8,500- Insulation at the refrigerant line | PCA Item- $8,500- Insulation at the refrigerant lines for a majority of the outdoor condensing units were observed to be deteriorated.Insufficient insulation at the refrigerant lines decreases system efficiency, Repair or replacement of the insulation is recommended to maintain system efficiency. | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | PCA Item- $8,500- Insulation at the refrigerant lines for a majority of the outdoor condensing units were observed to be deteriorated.Insufficient insulation at the refrigerant lines decreases system
24 | 7200-0064 | PCA Item- $6,000- Provide accessible path of travel | PCA Item- $6,000- Provide accessible path of travel from municipal sidewalk to leasing office entrance. | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | PCA Item- $6,000- Provide accessible path of travel from municipal sidewalk to leasing office entrance.
47 | 7200-0016 | secure railings | secure railings | GC | Year 1 | 6800 | 6800 |  |  | 0 |  | secure railings
21 | 7200-0069 | Adjust closers on pool gates | Adjust closers on pool gates | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Adjust closers on pool gates
141 | 7200-0007 | PCA Item- $5,000- The clubhouse domestic water heate | PCA Item- $5,000- The clubhouse domestic water heater is origional; to the 1986 construction. Electric, storage-type water heaters of this type have an estimated end of useful life (EUL) of 15-years. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | PCA Item- $5,000- The clubhouse domestic water heater is origional; to the 1986 construction. Electric, storage-type water heaters of this type have an estimated end of useful life (EUL) of 15-years.
22 | 7200-0061 | Replace grill | Replace grill | GC | Year 1 | 4000 | 4000 |  |  | 0 |  | Replace grill
131 | 7200-0029 | 4 new computers needed | 4 new computers needed | PMC | Year 1 | 4000 | 0 |  |  | N/A |  | 4 new computers needed
149 | 7200-0033 | PCA Item- $4,000- The ductwork within the clubhouse | PCA Item- $4,000- The ductwork within the clubhouse displayed evident signs of dust accumulation, observable upon visible inspection. | GC | Year 1 | 4000 | 4000 |  |  | 0 |  | PCA Item- $4,000- The ductwork within the clubhouse displayed evident signs of dust accumulation, observable upon visible inspection.
51 | 7200-0015 | PCA Item- $2,500- At Building A, two exterior stair | PCA Item- $2,500- At Building A, two exterior stair conditions requiring repair were noted. At the uppermost landing of the west stair, the concrete floor edge where the guardrail is anchored was cracked in two places, possibly compromising the rail stability. At the uppermost landing of the south stair, the nosing (edge angle) was damaged and appeared to be a trip hazard. | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | PCA Item- $2,500- At Building A, two exterior stair conditions requiring repair were noted. At the uppermost landing of the west stair, the concrete floor edge where the guardrail is anchored was crac
108 | 7400-0028 | PCA Item- $2,000- Complete flooring/appliance replac | PCA Item- $2,000- Complete flooring/appliance replacement at Unit F102.- COMPLETE BEFORE TAKEOVER | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | PCA Item- $2,000- Complete flooring/appliance replacement at Unit F102.- COMPLETE BEFORE TAKEOVER
139 | 7200-0047 | PCA Item- $2,000- At the front of Building M, the ad | PCA Item- $2,000- At the front of Building M, the adjacent asphalt parking lot and drive aisle were observed to be saturated and to have noticeable algae growth - COMPLETE BEFORE TAKEOVER | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | PCA Item- $2,000- At the front of Building M, the adjacent asphalt parking lot and drive aisle were observed to be saturated and to have noticeable algae growth - COMPLETE BEFORE TAKEOVER
107 | 7400-0032 | PCA Item- $1,000- Remove and replace suspect microbi | PCA Item- $1,000- Remove and replace suspect microbial growth-damaged ceiling at Unit A107 bathroom - COMPLETE BEFORE TAKEOVER | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | PCA Item- $1,000- Remove and replace suspect microbial growth-damaged ceiling at Unit A107 bathroom - COMPLETE BEFORE TAKEOVER
106 | 7400-0034 | PCA Item- $500- At vacant Unit E105, standing water | PCA Item- $500- At vacant Unit E105, standing water was observed on the floor - COMPLETE BEFORE TAKEOVER | GC | Year 1 | 500 | 500 |  |  | 0 |  | PCA Item- $500- At vacant Unit E105, standing water was observed on the floor - COMPLETE BEFORE TAKEOVER
PROJECTS subtotal (excl. contingency/CM fee)
161 | 7200-0084 | CM Fee | CM Fee | CMF | CM Fee | 104518 | 104518 | 0 |  | N/A |  | CM Fee
160 | 7200-0083 | Contingency Amount | Contingency Amount | CON | Contingency | 100000 | 0 | 0 |  | N/A |  | Contingency Amount

## Harbor Terrace
Harbor Terrace — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
16 | 51045-00 | Initial property tree trim, landscape cleanup, entry | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | GC | Year 1 | 15000 | 14708 |  |  | 1 |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
18 | 51053-00 | Restripe parking garage | Restripe parking garage | GC | Year 1 | 9700 | 9700 |  |  | 0 |  | Restripe parking garage
17 | 51130-00 | All floor drains have been painted over and should h | All floor drains have been painted over and should have the covers cleaned or replaced | GC | Year 1 | 6500 | 6500 |  |  | 0 |  | All floor drains have been painted over and should have the covers cleaned or replaced
19 | 51032-00 | Equity PCR Item 7.0- ADA-compliant parking spaces ar | Equity PCR Item 7.0- ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at the head of each space. It did not appear that ADA-compliant signage was provided at ADA parking spaces. Installation of compliant van-accessible signage is recommended. | GC | Year 1 | 300 | 300 |  |  | 0 |  | Equity PCR Item 7.0- ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at the head of each space. It did not appear that ADA-compliant signage was
| 51072-00 | Balcony/Deck Repair/Replacement | Replace areas of soft decking | GC | Year 1 | 7500 | 7500 |  |  | 0
| 51072-00 | Balcony/Deck Repair/Replacement | There are two balconies that appear to have had repairs done to them and could be questionable. Includes Equity PCR Item 4.5- The balcony system at Unit 217 was noted to have deteriorated elastomer and rotted wood decking. Immediate repair of the balcony flooring is recommended. | GC | Year 1 | 30000 | 30000 |  |  | 0
| 51993-01 | Safety Inspection | Request copy of completed inspection, or plan for new inspection | PMC | Year 1 | 5000 | 5000 |  |  | N/A
| 51061-00 | Roof Replacement | Repair areas of roofs that hold water and recoat roof Includes Equity PCR Item 4.4.1- Roof coatings are typically applied to to aged roofing systems in an attempt to extend the useful service life of the roofing system. Based on the observed condition, estimated useful life of roof coatings, and tt;ie assumed age of the underlying membrane, Partner recommends replacement of the low-slope roofing system in the short term. | GC | Year 1 | 48000 | 38350 |  |  | 2
| 51062-00 | Roof Repairs | Seal parapet wall flashing | GC | Year 1 | 4500 | 0 |  |  | 4
| 51150-00 | Approved Unit Upgrades | See Unit Renovation Calculator for details by unit | Capex | Year 1 | 400000 | 173571 |  |  | N/A
| 52111-00 | Down Unit Repairs | Equity PCR Item 8.0- Water damaged ceiling materials were observed in Unit 109. These appear to be due to a historic roof leak. Replacement of the water damaged wall and ceiling materials is recommended | PMC | Year 1 | 1500 | 1500 |  |  | N/A
| 51180-00 | Other Extraordinary Expense | LowPro (Pair covers 4 burner range)- For range top microwaves | Capex | Year 1 | 11103.125 | 11103 |  |  | N/A
| 51160-00 | Approved Common Area Upgrades | Miscellaneous needs | Capex | Year 1 | 10000 | 10000 |  |  | N/A
| 51160-00 | Approved Common Area Upgrades | Patio Level Enhancements | Capex | Year 1 | 30000 | 8530 |  |  | N/A
| 51993-01 | Safety Inspection | PCA Item- Expired certification tags were present at the fire extinguishers in corridors. Servicing and re-certification of the fire extinguishers is recommended. | PMC | Year 1 | 750 | 375 |  |  | N/A
| 51993-01 | Safety Inspection | PCA Item- Current operation permits expired in 2023 and were posted in elevator cab. Property management should schedule re-inspection with the local authority. | PMC | Year 1 | 1500 | 1907 |  |  | N/A
| 51158-00 | Plumbing Upgrades | Numerous copper water lines have been repaired without insulation being installed | GC | Year 1 | 15000 | 15000 |  |  | 0
| 51130-00 | Plumbing Replacement | Curent boiler is a 2002 Raypax boilet while it is curently operating and appears to be in good condition it is 22 years old and is reached it normal life span | Capex | Year 1 | 45000 | 45000 |  |  | N/A
| 51141-00 | Ext Lighting Fixtures Repair/Replacement | Replace garage lighting with LED | GC | Year 1 | 22500 | 22500 |  |  | 0
| 51993-01 | Safety Inspection | PCA Item- Based on prelimuinary load calculations, some of the one or two bedroom units have a calculated demand exceeding 30-amps. Retaining a qualified electrical contractor or engineer to perform load calculations per the NEC is recommended. | PMC | Year 1 | 5000 | 4400 |  |  | N/A
PROJECTS subtotal (excl. contingency/CM fee)
| 51175-00 | Construction/Rehab - Contingency | Contingency Amount | CON | Year 1 | 393147 | 0 |  |  | N/A
| 51190-00 | Construction Supervision Expense | CM Fee | CMF | Year 1 | 53100.0063 | 19327 |  |  | N/A

## Marquee
Marquee — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
78 | 51080-00 | Exterior building | Paint community Using Elastomaric paint Equity PCA Item 4.3.1- Exterior paint appeared to be in fair condition. The recent stucco repairs have not been painted to-date. According to property management, the exterior walls are planned to be painted in October 2024; however, no budget was provided for reference. Based on the observed condition and recent stucco repairs, Partner recommends reapplication of the exterior wall paint at this time. | GC | Year 1 | 250000 | 250000 |  |  | 0 |  | Paint community Using Elastomaric paint Equity PCA Item 4.3.1- Exterior paint appeared to be in fair condition. The recent stucco repairs have not been painted to-date. According to property manageme | [5 empty] | 2025-07-31
113 | 51158-00 | Water Savings Project | Echelon proposal for water savings devices | Capex | Year 1 | 138000 | 21858 |  |  | N/A |  | Echelon proposal for water savings devices
157 | 51140-00 | Electrical distribution | Equity PCA Item 5.3- Stab-Lok brand breaker panels manufactured by Federal Pacific Electric (FPE) were observed in approximately 25% of units accessed at the time of the assessment. Stab-Lok breaker panels lack UL labeling, are considered to be noncode compliant, and are a latent fire hazard. Retaining a licensed electrician to replace the panels is recommended. | Capex | Year 1 | 118000 | 8547 |  |  | N/A |  | Equity PCA Item 5.3- Stab-Lok brand breaker panels manufactured by Federal Pacific Electric (FPE) were observed in approximately 25% of units accessed at the time of the assessment. Stab-Lok breaker p
94 | 51150-00 | Interior Update Placeholder | Match renovated units with upcoming available classic units | Capex | Year 1 | 112000 | 26889 |  |  | N/A |  | Match renovated units with upcoming available classic units
77 | 51080-00 | Interior Hallway painting | Paint interior hallways and staircases | GC | Year 1 | 89000 | 89000 |  |  | 0 |  | Paint interior hallways and staircases
79 | 51073-00 | Replace unit entry doors - exterior | Replace 28 back doors | GC | Year 1 | 70800 | 70800 |  |  | 0 |  | Replace 28 back doors
146 | 51110-00 | Common area water heaters / boilers | Replace two ray pak boilers and one upright 199,000 but heater | Capex | Year 1 | 65000 | 33557 |  |  | N/A |  | Replace two ray pak boilers and one upright 199,000 but heater
21 | 51050-00 | Parking Pavement & Seal Coat | Equity PCA Item 3.2.2- Linear cracking was noted at the drive aisle on the eastern side of the subject property, adjacent to the swimming pool area. The noted cracking was at a low point in the asphalt pavement and was likely caused to standing water. Repair of the noted area is recommended. Equity PCA Item 3.2.2- Asphalt seal coat and pavement markings and striping appear to be in fair condition. Faded striping was noted throughout the parking areas. Based on the noted condition and estimated useful life (EUL), Partner recommends reapplication of the seal coat and striping in the short term, subsequent to the aforementioned pavement repairs. | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | Equity PCA Item 3.2.2- Linear cracking was noted at the drive aisle on the eastern side of the subject property, adjacent to the swimming pool area. The noted cracking was at a low point in the asphal | [5 empty] | 2025-07-31
76 | 51075-00 | Repair stucco | repair remaining areas of delaminated stucco and cracked stucco | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | repair remaining areas of delaminated stucco and cracked stucco
18 | 51026-00 | Repair / replace swimming pool heaters | replace hot tub heater | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | replace hot tub heater
128 | 51992-00 | Termite treatment & Repairs | Refer to Orkin WDIR dated 9/25/24 for details | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | Refer to Orkin WDIR dated 9/25/24 for details
125 | 51011-00 | Pool & Spa Area Furniture & Games | Match furniture style in main pool area, possibly move some irems from pool to spa area | Capex | Year 1 | 20000 | 20000 |  |  | N/A |  | Match furniture style in main pool area, possibly move some irems from pool to spa area
130 | 51160-05 | Unit Model Update | New furniture in model unit, definitely enhance lighting in model | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | New furniture in model unit, definitely enhance lighting in model
137 | 51993-00 | Security Camera System | Needed, especially at pedestrian gates | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Needed, especially at pedestrian gates
65 | 51071-00 | Gutters & downspouts | secure and clean gutters | GC | Year 1 | 19000 | 19000 |  |  | 0 |  | secure and clean gutters
15 | 51053-00 | Stripe parking areas | Restripe parking lot | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Restripe parking lot
16 | 51043-00 | Landscaping | Tree trim away from buildings | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Tree trim away from buildings
67 | 51062-00 | Sealants & caulking | Seal seams windows prior to paint | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Seal seams windows prior to paint
66 | 51062-00 | Flashing | Seal seams on parapet walls | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Seal seams on parapet walls
105 | 51993-01 | Smoke & CO detectors | Per LADBS Declaration- Required complaince with Section 91.8603 LAMC Either confirm they are already installed or plan for install | Capex | Year 1 | 11800 | 9550 |  |  | N/A |  | Per LADBS Declaration- Required complaince with Section 91.8603 LAMC Either confirm they are already installed or plan for install
110 | 51993-01 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | Capex | Year 1 | 11797 | 12000 |  |  | N/A |  | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods
23 | 51045-00 | Landscape Enhancements | Add turf or better landscaping in bare areas | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Add turf or better landscaping in bare areas
124 | 51160-00 | Pool & Spa Area Remodel | Add shade screens to each area along parking lot fence, possibly add turf in planter areas. | Capex | Year 1 | 10000 | 10000 |  |  | N/A |  | Add shade screens to each area along parking lot fence, possibly add turf in planter areas.
52 | 51090-00 | Concrete deck / floor fill | Repair cracked areas on catwalks | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | Repair cracked areas on catwalks
54 | 51077-00 | Repair patio/balcony railings | Repair catwalk railings | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | Repair catwalk railings
20 | 51163-00 | Dumpster enclosures | repair and paint compacter enclosure | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | repair and paint compacter enclosure
123 | 51028-00 | Fitness Equipment | Replace treadmill, supplemental items | PMC | Year 1 | 8000 | 8000 |  |  | N/A |  | Replace treadmill, supplemental items
141 | 51994-00 | Golf Cart | Maintenance Cart | PMC | Year 1 | 7500 | 7713 |  |  | N/A |  | Maintenance Cart
53 | 51072-00 | Repair exterior stair treads and stringers | secure railings | GC | Year 1 | 6800 | 6800 |  |  | 0 |  | secure railings
19 | 51076-00 | Fences & gates - swimming pool | adjust closers on pool gates amd paint pool fence | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | adjust closers on pool gates amd paint pool fence
106 | 51073-00 | Impact Glazing/Film for Sliding Glass Doors | Per LADBS Declaration- Required complaince with Section 96.302 LAMC Contingency for roughly 15-20 sliding doors in Building C that could need film | PMC | Year 1 | 5000 | 4800 |  |  | N/A |  | Per LADBS Declaration- Required complaince with Section 96.302 LAMC Contingency for roughly 15-20 sliding doors in Building C that could need film
121 | 51169-00 | Clubhouse / Office Furniture | Allowance for supplemental items | PMC | Year 1 | 5000 | 5000 |  |  | N/A |  | Allowance for supplemental items
17 | 51026-00 | Repair / replace swimming pool pumps | Install anti entrapment divise on pool pumps | GC | Year 1 | 4300 | 4300 |  |  | 0 |  | Install anti entrapment divise on pool pumps
119 | 51180-00 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | PMC | Year 1 | 2000 | 2000 |  |  | N/A |  | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas
120 | 51169-00 | Clubhouse / Office Remodel | No needs, flooring ok, misc amount for repairs and paint if needed | PMC | Year 1 | 2000 | 2000 |  |  | N/A |  | No needs, flooring ok, misc amount for repairs and paint if needed
122 | 51160-00 | Fitness Center Remodel | No needs, flooring ok, misc amount for repairs and paint if needed | PMC | Year 1 | 2000 | 2000 |  |  | N/A |  | No needs, flooring ok, misc amount for repairs and paint if needed
135 | 51168-00 | Mailbox Repairs | Repair broken mailbox doors | GC | Year 1 | 1500 | 1500 |  |  | 0 |  | Repair broken mailbox doors
22 | 51032-00 | ADA Signage | Equity PCA Item 7.0- A lack of signage identifying the van-accessible parking space at the leasing office was observed | GC | Year 1 | 150 | 150 |  |  | 0 |  | Equity PCA Item 7.0- A lack of signage identifying the van-accessible parking space at the leasing office was observed
PROJECTS subtotal (excl. contingency/CM fee)
164 | 51175-00 | Contingency | Contingency Amount | CON | Contingency | 61607 | 0 | 0 |  | N/A |  | Contingency Amount
165 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 61607 | 61607 | 49363 |  | N/A |  | CM Fee

## Navigator Villas
Navigator Villas — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
98 | 84207 | Unit Renovations | See Unit Renovation Calculator for detail | Capex | Year 1 | 565942 | 0 |  |  | N/A |  | See Unit Renovation Calculator for detail
39 | 84219 | Carports / Garages | Repair and paint 15 Garage doors | GC | Year 1 | 33000 | 33000 |  |  | 0 |  | Repair and paint 15 Garage doors
154 | 84210 | Common area light fixtures | Wall Pack replacement | GC | Year 1 | 31000 | 31000 |  |  | 0 |  | Wall Pack replacement
64 | 84433 | Asphalt composite shingle roofing | Roof inspection and minor repairs | GC | Year 1 | 29000 | 29000 |  |  | 0 |  | Roof inspection and minor repairs
28 | 84300 | Landscaping | Add landscaping in planters around pool | Capex | Year 1 | 26000 | 14820 |  |  | N/A |  | Add landscaping in planters around pool
24 | 84300 | Landscape irrigation | Inspect and repair Irrigation | Capex | Year 1 | 22000 | 4763 |  |  | N/A |  | Inspect and repair Irrigation
104 | 84239 | Fire Stops | LowPro - For range top microwaves | Capex | Year 1 | 20570 | 48953 |  |  | N/A |  | LowPro - For range top microwaves
146 | 84220 | Replace AC condenser | AC Condenser | Capex | Year 1 | 20000 | 20968 |  |  | N/A |  | AC Condenser
31 | 84095 | Replace swimming pool deck | Presure wash pool deck (reduced to $6,000) | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Presure wash pool deck (reduced to $6,000)
103 | 84106 | Clean Dryer Vents | Dryer Vent Cleaning | GC | Year 1 | 13200 | 13200 |  |  | 0 |  | Dryer Vent Cleaning
32 | 84095 | Repair / replace swimming pool pumps | Anti entrapment devices | GC | Year 1 | 12800 | 12800 |  |  | 0 |  | Anti entrapment devices
34 | 84095 | Fences & gates - swimming pool | Paint pool fence | GC | Year 1 | 8400 | 8400 |  |  | 0 |  | Paint pool fence
57 | 84121 | Repair exterior stair railings | Secure railings | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Secure railings
61 | 84102 | Expansion Joints | Seal expansion joints | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Seal expansion joints
76 | 84105 | Repair / replace cement fiber siding | replace bad siding and paint to match | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | replace bad siding and paint to match
85 | 84105 | Repair / replace wood trim | Minor trim replacement | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Minor trim replacement
151 | 84210 | Electrical distribution | Inspect and repair electric pole lights | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Inspect and repair electric pole lights
70 | 84433 | Flashing | repair flashing over clay tile | GC | Year 1 | 6500 | 6500 |  |  | 0 |  | repair flashing over clay tile
19 | 84221 | concrete pavement | replace broken curbs | GC | Year 1 | 6250 | 6250 |  |  | 0 |  | replace broken curbs
36 | 84340 | Playground equipment | Add mulch to playground | PMC | Year 1 | 6200 | 3537 |  |  | N/A |  | Add mulch to playground
131 | 84450 | Security Camera System | Only cameras on the leasing office and gym, no expressed need for additional cameras, maybe add for package lockers | PMC | Year 1 | 5000 | 2359 |  |  | N/A |  | Only cameras on the leasing office and gym, no expressed need for additional cameras, maybe add for package lockers
113 | 84208 | Clubhouse / Office Remodel | No clubhouse, office in good shape. Misc allowance for paint, etc | PMC | Year 1 | 2000 | 28000 |  |  | N/A |  | No clubhouse, office in good shape. Misc allowance for paint, etc
114 | 84208 | Clubhouse / Office Furniture | Placeholder for misc items. | PMC | Year 1 | 2000 | 4274 |  |  | N/A |  | Placeholder for misc items.
22 | 84201 | Add Accessible Van Parking Space | The accessible parking space in front of the leasing office is not van-accessible; | PMC | Year 1 | 450 | 13308 |  |  | N/A |  | The accessible parking space in front of the leasing office is not van-accessible; | [5 empty] | 2025-01-01
116 | 84209 | Install sink drain insulation in the fitness area ba | There is no sink drain insulation provided in the fitness area bathroom. | PMC | Year 1 | 250 | 1918 |  |  | N/A |  | There is no sink drain insulation provided in the fitness area bathroom. | [5 empty] | 2025-01-01
PROJECTS subtotal (excl. contingency/CM fee)
159 | 84505 | Construction Management Fee | CM Fee | CMF | CM Fee | 44203 | 44203 | 0 |  | N/A |  | CM Fee
158 | 85305 | Contingency | Contingency Amount | CON | Contingency | 20000 | 20000 | 0 |  | N/A |  | Contingency Amount

## Presidium Edgestone
Presidium Edgestone — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
139 | 83515 | Green Initiatives | Green Program | GC | Year 1 | 100000 | 100000 |  |  | 0 |  | Green Program
14 | 84115 | Sidewalks | Replace crushed granite path with concrete on front of community 600 LF 4 ft wide | GC | Year 1 | 41200 | 41200 |  |  | 0 |  | Replace crushed granite path with concrete on front of community 600 LF 4 ft wide
17 | 84303 | Landscaping | Add turf and tree rings with rock to tree lines by rec area and parking lot side outside of pool to prevent erosion | GC | Year 1 | 37300 | 37300 |  |  | 0 |  | Add turf and tree rings with rock to tree lines by rec area and parking lot side outside of pool to prevent erosion
107 | 83520 | Add Shower/Tub ADA compliant grab bars | Seller has completed half of the units, budget for 94 remaining units. All units are 1 bath | GC | Year 1 | 32900 | 32900 |  |  | 0 |  | Seller has completed half of the units, budget for 94 remaining units. All units are 1 bath
42 | 84219 | Add Carports | Add 8 carports to test | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Add 8 carports to test
16 | 84205 | Fences & gates - site perimeter | Scrape and Paint perimeter fence. 3700 LF of fence PCA Item- A portion of the perimeter fencing on the south section of the subject property, near the parking garage, was observed to exhibit evidence of corrosion. | GC | Year 1 | 29600 | 29600 |  |  | 0 |  | Scrape and Paint perimeter fence. 3700 LF of fence PCA Item- A portion of the perimeter fencing on the south section of the subject property, near the parking garage, was observed to exhibit evidence
109 | 84211 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | GC | Year 1 | 22206 | 22206 |  |  | 0 |  | LowPro (Pair covers 4 burner range)- For range top microwaves
15 | 84302 | Landscape irrigation | Adjust irrigation to not cause erosion to A/C pads | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Adjust irrigation to not cause erosion to A/C pads
19 | 84105 | Pergola court | Pressure wash and seal pavers in seating area | GC | Year 1 | 8700 | 8700 |  |  | 0 |  | Pressure wash and seal pavers in seating area
23 | 84517 | Drainage | PCA Item- Ponding was observed along the exterior walls the parking garages M and L, south of Building 8. Regrading of the landscaping near these parking garages to alleviate ponding is recommended. | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | PCA Item- Ponding was observed along the exterior walls the parking garages M and L, south of Building 8. Regrading of the landscaping near these parking garages to alleviate ponding is recommended.
18 | 84205 | Fences & gates - swimming pool | Repair and paint | GC | Year 1 | 6800 | 6800 |  |  | 0 |  | Repair and paint
20 | 84340 | Playground equipment | Repair, scrape and paint pet park fence | GC | Year 1 | 6800 | 6800 |  |  | 0 |  | Repair, scrape and paint pet park fence
50 | 84120 | Repair Corridor Walls | PCA Item- Cracking was observed in several areas of the corridor walls and ceilings throughout Building 1. This appears to be a result of normal building movement/settle after construction. Repair of the damaged finishes are recommended. | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | PCA Item- Cracking was observed in several areas of the corridor walls and ceilings throughout Building 1. This appears to be a result of normal building movement/settle after construction. Repair of
70 | 84113 | Sealants & caulking and paint | Cut out and reseal lintels' on garage doors with elastomeric caulk 60 garages | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Cut out and reseal lintels' on garage doors with elastomeric caulk 60 garages
29 | 84361 | Repair swimming pool coping | Section of pool coping has separated from the deck, either repair with new sealant or re-set section of coping | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Section of pool coping has separated from the deck, either repair with new sealant or re-set section of coping
133 | 84239 | Fire Lane Gates - Regulatory Compliance | PCA Item- All opticom sensors must work, or gates must remain open. On new and existing buildings, the address must be legible from the street, rear access or fire lane and of a color contrasting the background, number should be at least 12" tall. The location of all fir hydrants shall be identified with a blue reflective road marker placed near the center of the roadway in front of the hydrant. | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | PCA Item- All opticom sensors must work, or gates must remain open. On new and existing buildings, the address must be legible from the street, rear access or fire lane and of a color contrasting the
134 | 84905 | Elevator Permits | PCA Item- Current operation permits were not posted in each elevator cab. Property management should schedule re-inspection with the local authority. | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | PCA Item- Current operation permits were not posted in each elevator cab. Property management should schedule re-inspection with the local authority.
135 | 84239 | Fire Riser Inspection | PCA Item- A yellow inspection tag was observed at the fire riser at Building 1 for a defective flow switch. Expired tags were also observed on the fire riser. According to the provided fire report, yellow tags were observed for deficient sprinklers at Building 1 and 8 and expired gauges. Repair of the noted deficiencies is recommended followed by reinspection and recertification of the fire riser. | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | PCA Item- A yellow inspection tag was observed at the fire riser at Building 1 for a defective flow switch. Expired tags were also observed on the fire riser. According to the provided fire report, ye
137 | 84239 | Fire Alarm Certification | PCA Item - A current annual fire alarm certification tag was not present at the fire alarm control panel. According to the provided fire system report, yellow tags were observed at Buildings 2, 5, 7, and 8 due to non-compliance. Repair, servicing, and recertification of the fire alarm system is recommended. | PMC | Year 1 | 2500 | 0 |  |  | N/A |  | PCA Item - A current annual fire alarm certification tag was not present at the fire alarm control panel. According to the provided fire system report, yellow tags were observed at Buildings 2, 5, 7,
22 | 84115 | Sidewalks | PCA Item- Potential trip hazards consisting of vertical separation were noted at the walkway southwest of the main building. Sectional replacement or grinding is recommended as necessary. | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | PCA Item- Potential trip hazards consisting of vertical separation were noted at the walkway southwest of the main building. Sectional replacement or grinding is recommended as necessary.
136 | 84239 | Fire Extinguisher Inspection | PCA Item- Expired certification tags were present at the fire extinguishers Servicing and re-certification of the fire extinguishers is recommended. | PMC | Year 1 | 1500 | 1115 |  |  | N/A |  | PCA Item- Expired certification tags were present at the fire extinguishers Servicing and re-certification of the fire extinguishers is recommended.
24 | 84103 | ADA Parking Signage | PCA Item - ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at the head of each space. It did not appear that ADA-compliant signage was provided at ADA parking spaces. Installation of compliant signage is recommended. | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | PCA Item - ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at the head of each space. It did not appear that ADA-compliant signage was provided
PROJECTS subtotal (excl. contingency/CM fee)
162 | 84510 | Contingency | Contingency Amount | CON | Contingency | 36551 | 0 |  |  | N/A |  | Contingency Amount
163 | 84505 | Construction Management Fee | CM Fee | CMF | Contingency | 20103 | 0 |  |  | N/A |  | CM Fee

## The Arbors
The Arbors — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
29 | 51169-00 | ADA Accessibility | From PCA- 7.0- Parking areas that provide self-parking for employees and visitors must provide ADA-compliant parking spaces. No accessible spaces are provided at the leasing office. Partner recommends installation of a complaint van-accessible parking space nearest to the leasing office entrance. From PCA- 7.0- The leasing office restroom did not appear to be generally accessible. The lavatory is provided with a full vanity. Replacement of the vanity with a wall-mounted lavatory is recommended. | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | From PCA- 7.0- Parking areas that provide self-parking for employees and visitors must provide ADA-compliant parking spaces. No accessible spaces are provided at the leasing office. Partner recommends
102 | 51995-00 | Leasing Office Furniture | Ok, small allowance | PMC | Year 1 | 2000 | 1243 |  |  | N/A |  | Ok, small allowance
100 | 51990-00 | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | PMC | Year 1 | 3000 | 10357 |  |  | N/A |  | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas
103 | 51995-00 | Computers | Allowance for new office computers and software, printer, office supplies | PMC | Year 1 | 4000 | 4000 |  |  | N/A |  | Allowance for new office computers and software, printer, office supplies
113 | 51180-00 | Property Photo Shoot | Professional photos and vdeo of remodeled exterior areas, unit interiors when applicable | PMC | Year 1 | 4000 | 5102 |  |  | N/A |  | Professional photos and vdeo of remodeled exterior areas, unit interiors when applicable
42 | 51077-00 | Repair patio/balcony railings | Secure rails | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Secure rails
120 | 51998-00 | Tools & Equipment | Maintenance tools, equipment, & inventory | PMC | Year 1 | 7000 | 6121 |  |  | N/A |  | Maintenance tools, equipment, & inventory
90 | 51993-01 | C02 Dectors | Install CO2 detectors | PMC | Year 1 | 7200 | 0 |  |  | N/A |  | Install CO2 detectors
91 | 51993-01 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | PMC | Year 1 | 7656 | 0 |  |  | N/A |  | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods
40 | 51077-00 | Repair exterior stair railings | Secure rails | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Secure rails
43 | 51070-00 | Expansion Joints | Re-seal expansions | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Re-seal expansions
55 | 51062-00 | Flashing | replace damaged z bar on siding replacement | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | replace damaged z bar on siding replacement
56 | 51062-00 | Sealants & caulking | caulk and seal | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | caulk and seal
111 | 51029-00 | Dog Park | Water/Wash Station with concrete pad | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Water/Wash Station with concrete pad
28 | 51163-00 | Dumpster enclosures | Repair and Paint | GC | Year 1 | 9000 | 9000 |  |  | 0 |  | Repair and Paint
97 | 51032-00 | Signage - Site | Refresh | Capex | Year 1 | 10000 | 47044 |  |  | N/A |  | Refresh
105 | 51028-00 | Fitness Equipment | Refresh equipment, add stair stepper | Capex | Year 1 | 10000 | 8000 |  |  | N/A |  | Refresh equipment, add stair stepper
110 | 51027-00 | Sports Courts | Resurface, look at pickleball, replace basketball system if that stays | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Resurface, look at pickleball, replace basketball system if that stays
89 | 51090-00 | Unit Patio Concrete | From PCA- 3.2.3- Uplifting concrete patio slabs was observed at Units 136, 139, and 107. The upheaval appears to be due, in part, to shallow tree root growth. Repair of the damaged patios is recommended. Consultation with an arborist may be warranted due to the shallow tree roots | GC | Year 1 | 10500 | 10500 |  |  | 0 |  | From PCA- 3.2.3- Uplifting concrete patio slabs was observed at Units 136, 139, and 107. The upheaval appears to be due, in part, to shallow tree root growth. Repair of the damaged patios is recommend
25 | 51026-00 | Repair / replace swimming pool pumps | Anti entrapment devices | GC | Year 1 | 12900 | 12900 |  |  | 0 |  | Anti entrapment devices
54 | 51071-00 | Gutters & downspouts | Clean, re-pitch and resecure gutters | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Clean, re-pitch and resecure gutters
60 | 51075-00 | Repair / replace wood siding | Replace rotted siding | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Replace rotted siding
17 | 51053-00 | Stripe parking areas | Re-stripe From PCA- 3.2.2- The seal coat and stall striping appeared to be in fair condition. Based on the observed condition and EUL, reapplication of the seal coat and parking stall striping is recommended in the short term. | GC | Year 1 | 14500 | 14500 |  |  | 0 |  | Re-stripe From PCA- 3.2.2- The seal coat and stall striping appeared to be in fair condition. Based on the observed condition and EUL, reapplication of the seal coat and parking stall striping is reco
23 | 51021-00 | Replace swimming pool coping | Deck o seal both pools | GC | Year 1 | 14500 | 14500 |  |  | 0 |  | Deck o seal both pools
96 | 51031-00 | Signage - Entry Monument | Refresh 1 sign, replace the other, replace wall banner facing Fairhaven | Capex | Year 1 | 15000 | 29576 |  |  | N/A |  | Refresh 1 sign, replace the other, replace wall banner facing Fairhaven
101 | 51169-00 | Leasing Office Remodel | Refresh paint on accent wall to brighten space, flooring, add lighting | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Refresh paint on accent wall to brighten space, flooring, add lighting
109 | 51160-04 | Picnic/Grill Furniture | Allowance for new grills, furniture & misc items, move concrete furniture from pool to picnic area | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Allowance for new grills, furniture & misc items, move concrete furniture from pool to picnic area
114 | 51993-00 | Access Control System | Add at entry gates and fitness center | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Add at entry gates and fitness center
117 | 51166-00 | Laundry rooms- one on each side | Paint refresh, replace track lighting, resurface or replace counter, look at adding equipment From PCA- 4.3.3- Worn doors were observed at the laundry building at 1200 Fairhaven side of the property. Based on the observed condition, replacement of the doors is recommended. | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Paint refresh, replace track lighting, resurface or replace counter, look at adding equipment From PCA- 4.3.3- Worn doors were observed at the laundry building at 1200 Fairhaven side of the property.
127 | 51134-00 | Sanitary sewer piping | Sewer Pipe Jetting | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Sewer Pipe Jetting
26 | 51076-00 | Fences & gates - swimming pool | Repair gates and paint At gym pool- fix exit gate eye level hinge so it doesn't protrude | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Repair gates and paint At gym pool- fix exit gate eye level hinge so it doesn't protrude
61 | 51075-00 | Repair stucco |  | GC | Year 1 | 16000 | 16000 |  |  | 0
104 | 51160-00 | Fitness Center Remodel | Fix front door, add lighting, replace fan with something more commercial, add mini split HVAC, new larger TV, add rubber matting under equipment | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Fix front door, add lighting, replace fan with something more commercial, add mini split HVAC, new larger TV, add rubber matting under equipment
106 | 51011-00 | Pool Area Remodel- 2 pools | Allowance for lighting, other enhancements | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Allowance for lighting, other enhancements
20 | 51046-00 | Landscape irrigation | Inspect and repair | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | Inspect and repair
21 | 51076-00 | Fences & gates - site perimeter | Paint Iron fencing on perimeter of community | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Paint Iron fencing on perimeter of community
64 | 51082-00 | Repair / replace wood trim | Replace rotted trim and fascia | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | Replace rotted trim and fascia
137 | 51141-00 | Replace breezeway lights | Replace ceiling lights in breezeways | GC | Year 1 | 28000 | 28000 |  |  | 0 |  | Replace ceiling lights in breezeways
19 | 51043-00 | Landscaping | Tree trim and landscape maintenance throughout From PCA- 3.2.4- Overgrown trees were observed to be in contact with the building facades along the perimeters of the buildings. Landscaping materials should not be in contact with the buildings or rooflines. Trimming all overgrown trees is recommended. | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Tree trim and landscape maintenance throughout From PCA- 3.2.4- Overgrown trees were observed to be in contact with the building facades along the perimeters of the buildings. Landscaping materials sh | [5 empty] | 2024-11-06
22 | 51023-00 | Resurface swimming pool | Resurface two hot tubs | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | Resurface two hot tubs
62 | 51160-00 | Interior Hallway painting | Paint hallways and front doors, Stripe stair treads in breezeways to address trip hazards | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | Paint hallways and front doors, Stripe stair treads in breezeways to address trip hazards
53 | 51061-00 | Asphalt composite shingle roofing | Reportedly roofs were replaced on unit building 4 years ago however the ancillary buildings were not done. Allowance for car port roof repairs & replacements | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Reportedly roofs were replaced on unit building 4 years ago however the ancillary buildings were not done. Allowance for car port roof repairs & replacements
30 | 51992-00 | Termite Treatment & Repairs | WDIR treatment and repairs will be required by lender within 60-90 days of closing. Reference Terminix report and quote. | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | WDIR treatment and repairs will be required by lender within 60-90 days of closing. Reference Terminix report and quote. | [5 empty] | 2024-11-06
119 | 51998-00 | New storage units by leasing office pool | Add 8 new units against car port wall, behind existing storage units | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Add 8 new units against car port wall, behind existing storage units
18 | 51053-00 | Asphalt Coating | West side of community needs to be seal coated and crack fill From PCA- 3.2.2- Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present at the drive aisles at both sides of the property. Sectional full-depth replacement and crack routing/sealing is recommended. | GC | Year 1 | 49000 | 49000 |  |  | 0 |  | West side of community needs to be seal coated and crack fill From PCA- 3.2.2- Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present at the dri
24 | 51022-00 | Replace swimming pool deck | Both pool decks need to be cleaned, etched and coated. Replacing decks add $60k totalAt Leasing pool- look at changing entry for adjacent maintenance shed to back side, or relocate current maintenance shop From PCA- 3.2.9- Cracking was observed at the concrete decking surrounding the swimming pool at 1100 Fairhaven. Repair of the cracked concrete pool deck is recommended. | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Both pool decks need to be cleaned, etched and coated. Replacing decks add $60k totalAt Leasing pool- look at changing entry for adjacent maintenance shed to back side, or relocate current maintenance
116 | 51168-00 | Package Lockers | Add package locker system | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | Add package locker system
123 | 51110-00 | Common area water heaters / boilers | 3 Boilers are reported to be original, contingency for replacement. 1 goes out frequently and they have a bid for $21k to replace | GC | Year 1 | 63000 | 63000 |  |  | 0 |  | 3 Boilers are reported to be original, contingency for replacement. 1 goes out frequently and they have a bid for $21k to replace
107 | 51011-00 | Pool Furniture- 2 pools | New furniture & games | GC | Year 1 | 70000 | 70000 |  |  | 0 |  | New furniture & games
131 | 51120-00 | HVAC | Contingency for HVAC replacements From PCA- 5.2- While generally reported to be functional, approximately 80% of the units appear to be in service past the end of useful life. As such, replacement of these units is recommended in the short term. | GC | Year 1 | 75000 | 75000 |  |  | 0 |  | Contingency for HVAC replacements From PCA- 5.2- While generally reported to be functional, approximately 80% of the units appear to be in service past the end of useful life. As such, replacement of
27 | 51172-00 | Carports / Garages | Replace rotted wood and paint parking buildings Exterior only | GC | Year 1 | 95000 | 95000 |  |  | 0 |  | Replace rotted wood and paint parking buildings Exterior only
15 | 51200-00 | Gas Submeter Replacements | Need to replace old submeters, 10% will be inspected each year by Orange County Weights & Measures. Summary from property:This property is sub-metered. We own the meters (not the gas company) and that is why we get the proceeds from water, trash, gas and electric from all the bills(RUBS). Real page is the servicing company. We did have our maintenance crew install the electric meters, so I would assume that we would just have our maintenance personnel install the gas meters. We just paid our maintenance crew hourly wage and it was a couple of days. You may confirm with Real Page, Reina Laymus 972-810-2274, reina.layumas@realpage.com. All meters MUST be checked by OC Weights and Measures (registration is receipt is in the Dropbox)Permit #EG-00921 and it is a requirement to have a ten-year maintenance check. I have included the explanation in the Dropbox, please refer to it or confirm with Reina Laymus Direct Line 972-810-2274 | GC | Year 1 | 96000 | 96000 |  |  | 0 |  | Need to replace old submeters, 10% will be inspected each year by Orange County Weights & Measures. Summary from property:This property is sub-metered. We own the meters (not the gas company) and that
16 | 51050-00 | Pavement | East side of community has deteriorated drives that need to be milled and overlayed From PCA- 3.2.1- The concrete drainage swales appeared to be in good to fair condition. Isolated areas of damage swales were observed throughout the property, primarily near heavy alligator cracking of the asphalt pavement. Replacement of the damaged concrete swales is recommended in conjunction with the asphalt pavement repairs discussed below.From PCA- 3.2.2- Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present at the drive aisles at both sides of the property. Sectional full-depth replacement and crack routing/sealing is recommended. | GC | Year 1 | 108000 | 108000 |  |  | 0 |  | East side of community has deteriorated drives that need to be milled and overlayed From PCA- 3.2.1- The concrete drainage swales appeared to be in good to fair condition. Isolated areas of damage swa
41 | 51072-00 | Repair balcony framing & decking | Place Holder to have all balconies inspected and repaired | GC | Year 1 | 160000 | 160000 |  |  | 0 |  | Place Holder to have all balconies inspected and repaired
14 | 51132-00 | Gas, Water, Sanitary Sewer Piping | Active leak on East side of community with temp line to the boilers this will have to be repaired and the gas lines will have to be pressure testedMay not be needed, the property team is replacing the gas and water lines currently, and is likely to be complete before takeover.Contingency for additional gas and water line replacement.From PCA- 5.1- Based on age and observed condition, phased replacement of the domestic water and sanitary drain systems is anticipated later in the evaluation period. An opinion of cost for this work is included in Table 2. Routine maintenance is anticipated throughout the evaluation period. From PCA- 5.3- The natural gas services to each building did not appear to be equipped with automatic seismic shut-off devices to prevent dangerous gas leaks in the event of a line break during a significant seismic event. Installation of automatic seismic shut-off devices at each building is recommended. | GC | Year 1 | 200000 | 200000 |  |  | 0 |  | Active leak on East side of community with temp line to the boilers this will have to be repaired and the gas lines will have to be pressure testedMay not be needed, the property team is replacing the
63 | 51080-00 | Exterior building | Paint exterior From PCA- 4.3.1- The paint finish on the apartment buildings was noted to be chipping and worn. Based on the observed condition, reapplication of exterior paint is recommended in the short term, which should include repair/replacement of deteriorated wood trim components. | GC | Year 1 | 200000 | 200000 |  |  | 0 |  | Paint exterior From PCA- 4.3.1- The paint finish on the apartment buildings was noted to be chipping and worn. Based on the observed condition, reapplication of exterior paint is recommended in the s
136 | 51140-00 | Electrical distribution | Place holder to replace Zinsco Load center in each unit ( Zinsco breakers have not been formally recalled however are considered to be a safety hazard) this number will not include any code upgrades that could be required by the electric inspector From PCA- 5.3- Zinsco circuit breaker panels were reported and observed at the units. Zinsco breaker panels lack UL labeling, are considered to be non-code compliant, and are a latent fire hazard. Retaining a licensed electrician to replace the panels is recommended. From PCA- 5.3- The electrical systems appeared to be in fair to poor condition. The electrical systems were typically from the original construction and aged. Updates were not observed. Based on observed condition and EUL, replacement of the electrical service equipment is recommended in the short term. | GC | Year 1 | 380000 | 380000 |  |  | 0 |  | Place holder to replace Zinsco Load center in each unit ( Zinsco breakers have not been formally recalled however are considered to be a safety hazard) this number will not include any code upgrades t
PROJECTS subtotal (excl. contingency/CM fee)
143 | 51175-00 | Contingency | Contingency Amount | CON | Contingency | 70064 | 0 |  |  | N/A |  | Contingency Amount
144 | 51190-00 | Construction Management Fee | CM Fees | CMF | CM Fee | 116966 | 42153 |  |  | N/A |  | CM Fees

## Village at Broadstone
Village at Broadstone — 2024 acq · GC @ budget |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
89 | 0900 - FF&E in Units | Unit Renovations | Classic, Partial & Premium (A, B & C Units) | GC | Year 1 | 2586304 | 2586304 |  |  | 0 |  | Classic
78 | 0800 - Exterior Wall | Exterior Paint | Paint one coat of SW Superpaint on the siding, trim, shutters, doors, railings and ammenities. | GC | Year 1 | 270000 | 270000 |  |  | 0 |  | Paint one coat of SW Superpaint on the siding, trim, shutters, doors, railings and ammenities.
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | New flooring, paint in the clubhouse to modernize it, using Bell Apex clubhouse as a target finish level. | GC | Year 1 | 130000 | 130000 |  |  | 0 |  | New flooring, paint in the clubhouse to modernize it, using Bell Apex clubhouse as a target finish level.
18 | 0200 - Site Utilities & Improvements | Landscape Irrigation & Drainage | Repair, replace and troubleshoot exhisting irrigation system. | GC | Year 1 | 81000 | 81000 |  |  | 0 |  | Repair, replace and troubleshoot exhisting irrigation system.
114 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | New FF&E | GC | Year 1 | 70000 | 70000 |  |  | 0 |  | New FF&E
58 | 0700 - Roofing | Roof Repairs | Remove rusted nails on pipe boots across the community. Install new rain collars, screws, and seal bottom flanges. Remove rusted nails on (all) flashing, install new screws and seal. Remove rusted nails on static vents, install new screws and seal. Remove and replace damaged pipe boots, install new ice and water shields, and new shingles. Replace missing/damaged shingles. Repair exposed nails. Reattach the corner of the metal fascia. Install elbows on the downspouts. Replace damaged downspouts and reattach downspouts to gutters. Remove rusted nails on (all) flashing, install new screws and seal. Remove rusted nails on static vents, install new screws, and seal clean gutters. | GC | Year 1 | 57000 | 57000 |  |  | 0 |  | Remove rusted nails on pipe boots across the community. Install new rain collars, screws, and seal bottom flanges. Remove rusted nails on (all) flashing, install new screws and seal. Remove rusted nai
118 | 1100- Specialties, Equipment & Furnishings | Pool Furniture | New furniture to replace existing strap, new lounge seating, bar stools, cornhole, other games | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | New furniture to replace existing strap, new lounge seating, bar stools, cornhole, other games
138 | 1400 - Plumbing | Fire Sprinklers | PCA Item- $40,818- Replace deficient sprinkler heads, per inspection report. | GC | Year 1 | 40818 | 40818 |  |  | 0 |  | PCA Item- $40,818- Replace deficient sprinkler heads, per inspection report. | [5 empty] | 2024-08-29
22 | 0200 - Site Utilities & Improvements | Landscaping Enhancements | Remove, add plants. | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Remove, add plants.
104 | 0900 - FF&E in Units | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | GC | Year 1 | 35063 | 35063 |  |  | 0 |  | LowPro (Pair covers 4 burner range)- For range top microwaves
116 | 1100- Specialties, Equipment & Furnishings | Fitness Equipment | Need new equipment, stairstepper, have rack, need more weights | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Need new equipment, stairstepper, have rack, need more weights
21 | 0200 - Site Utilities & Improvements | Tree Trim & Shrub Cutback | Trim trees & reduce shrubs where appropriate. Remove dead tree throughout all 3 phases to prevent any future damage to buildings and to limit life safety liability. | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Trim trees & reduce shrubs where appropriate. Remove dead tree throughout all 3 phases to prevent any future damage to buildings and to limit life safety liability.
11 | 0200 - Site Utilities & Improvements | Stripe parking areas | Clean parking lot of debris and oil, crack fill 3000lf. Apply one coat of latex sealer and stripe to existing layout. Includes PCA Item- $24,000- Seal coat and stripe asphalt pavement | GC | Year 1 | 29000 | 29000 |  |  | 0 |  | Clean parking lot of debris and oil, crack fill 3000lf. Apply one coat of latex sealer and stripe to existing layout. Includes PCA Item- $24,000- Seal coat and stripe asphalt pavement | [5 empty] | 2025-05-31
149 | 1600 - Electrical | Replace all balcony ceiling lights & breezeway light | Replace dated fixtures | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Replace dated fixtures
106 | 0900 - FF&E in Units | Drier vents | Clean drier vents | GC | Year 1 | 22500 | 22500 |  |  | 0 |  | Clean drier vents
84 | 0800 - Exterior Wall | Window screens | Contingency to remove and replace some of the 1/2 screens on the windows of the residential units and clubhouse. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Contingency to remove and replace some of the 1/2 screens on the windows of the residential units and clubhouse.
122 | 1100- Specialties, Equipment & Furnishings | Unit Model Update | New furniture in model unit | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | New furniture in model unit
29 | 0200 - Site Utilities & Improvements | Grill stations | Upgrade grill stations with new Bull Outlaw grill heads, granite countertops and gas timers. Repair and paint pergolas. | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Upgrade grill stations with new Bull Outlaw grill heads, granite countertops and gas timers. Repair and paint pergolas.
80 | 0800 - Exterior Wall | Shutters | Paint or replace faded shutters | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Paint or replace faded shutters
119 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Area Remodel | For 2 grill areas outside of pool-Add full covered pergola over grill | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | For 2 grill areas outside of pool-Add full covered pergola over grill
121 | 1100- Specialties, Equipment & Furnishings | Dog Park | Water/Wash Station with concrete pad Shade sail or pergola | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Water/Wash Station with concrete pad Shade sail or pergola
77 | 0800 - Exterior Wall | Bldg. Exterior Cladding | Repair damaged fiber cement siding and trim. Secure shutters. Repair damaged metal fascia, metal row lock flashing and vinyl soffit. | GC | Year 1 | 14500 | 14500 |  |  | 0 |  | Repair damaged fiber cement siding and trim. Secure shutters. Repair damaged metal fascia, metal row lock flashing and vinyl soffit.
17 | 0200 - Site Utilities & Improvements | Sidewalks | Remove and replace approx 375sf of concrete sidewalk. Perform approx. 40EA grinds at lifted sidewalk seams. | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Remove and replace approx 375sf of concrete sidewalk. Perform approx. 40EA grinds at lifted sidewalk seams.
143 | 1500- HVAC | HVAC Replacements | Cost to replace two units at $5,200/unit | GC | Year 1 | 10400 | 10400 |  |  | 0 |  | Cost to replace two units at $5,200/unit
14 | 0200 - Site Utilities & Improvements | Compactor Ramp | Build an ADA ramp at the compactor. | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Build an ADA ramp at the compactor.
69 | 0800 - Exterior Wall | Soffit/roof fascia repair | Repair where failing, building 5 & others | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Repair where failing, building 5 & others
117 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Move gate/fencing in so that the grill area can be used when the pool is closed, add TV above sink under pool grill pergola | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Move gate/fencing in so that the grill area can be used when the pool is closed, add TV above sink under pool grill pergola
150 | 1600 - Electrical | Fire and Life Safety | Repair pull stations throughout the property. Install a riser room sign where missing, install fire extinguishers and repair extinguisher boxes, repair emergency lights, and horn strobe repairs | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Repair pull stations throughout the property. Install a riser room sign where missing, install fire extinguishers and repair extinguisher boxes, repair emergency lights, and horn strobe repairs
152 | 1600 - Electrical | Common area light fixtures | Possibly replace remaining halogen parking lot pole lights with LED | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Possibly replace remaining halogen parking lot pole lights with LED
28 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Add fence between pool and grill area, repair broken pool gate latch | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | Add fence between pool and grill area, repair broken pool gate latch
31 | 0200 - Site Utilities & Improvements | Playground equipment | Add mulch and plastic coat damaged landings | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Add mulch and plastic coat damaged landings
144 | 1500- HVAC | Replace Refrigerant Line Insulation | From MEPFLS Report- Insulation at the refrigerant lines at the outdoor condensing units were observed to be deteriorated. Insufficient insulation at the refrigerant lines decreases system efficiency. Repair or replacement of the insulation is recommended to maintain system efficiency. | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | From MEPFLS Report- Insulation at the refrigerant lines at the outdoor condensing units were observed to be deteriorated. Insufficient insulation at the refrigerant lines decreases system efficiency.
139 | 1400 - Plumbing | Provide Drain Pans for Domestic Hot Water Heaters | From MEPFLS Report- Several domestic water heaters in residential units were observed to be missing drain pans. Partner recommends thatall residential domestic hot water heaters are provided a drain pan to reduce the risk of damage should a leak occur. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | From MEPFLS Report- Several domestic water heaters in residential units were observed to be missing drain pans. Partner recommends thatall residential domestic hot water heaters are provided a drain p
140 | 1400 - Plumbing | Scope and Clear Sewer Lines | From MEPFLS Report- Recent scoping and clearing of the sanitary drain lines was not reported; therefore, Partner recommends that a contractor scope all of the sanitary sewer lines and clear and blockages. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | From MEPFLS Report- Recent scoping and clearing of the sanitary drain lines was not reported; therefore, Partner recommends that a contractor scope all of the sanitary sewer lines and clear and blocka
19 | 0200 - Site Utilities & Improvements | Irrigation Repairs | 4 Rain bird 5000, 15 Rain bird 1806, 6 MP Rotator Nozzles, 33 Rain bird Nozzles, 2 Wireless Rain sensors, 7 zones not running. A diagnostic is needed for the controller wire adjustment to run uniformly with property. Replace 8 valve box lids. Controller 1 for 27 zones and Controller 2 for 25 zones. | GC | Year 1 | 4400 | 4400 |  |  | 0 |  | 4 Rain bird 5000, 15 Rain bird 1806, 6 MP Rotator Nozzles, 33 Rain bird Nozzles, 2 Wireless Rain sensors, 7 zones not running. A diagnostic is needed for the controller wire adjustment to run uniforml
115 | 1100- Specialties, Equipment & Furnishings | Fitness Center Remodel | Add conduit for power and data cables to TVs | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Add conduit for power and data cables to TVs
120 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Furniture | Add benches by cornhole, misc furniture | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Add benches by cornhole, misc furniture
109 | 1100- Specialties, Equipment & Furnishings | Signage - Site | Change signage for leasing hours since they are not open Sundays, add hanging clock for Sunday hours | PMC | Year 1 | 250 | 0 |  |  | N/A |  | Change signage for leasing hours since they are not open Sundays, add hanging clock for Sunday hours
127 | 1100- Specialties, Equipment & Furnishings | Correct and Close OpenViolation | PCA Item- $100- Open code violation report by building department (expired permit) should be corrected and closed. | PMC | Year 1 | 100 | 0 |  |  | N/A |  | PCA Item- $100- Open code violation report by building department (expired permit) should be corrected and closed. | [5 empty] | 2025-05-31
PROJECTS subtotal (excl. contingency/CM fee)
157 | Contingency & Fees | Construction Management Fee |  | CMF | CM Fee | 186467 | 186467 | 0 |  | N/A

## Avenues of Kennesaw
Avenues of Kennesaw — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
77 | 84101 | Exterior building | Repaint community, west side will need special process in order to seal Masonite to prevent future delamination | GC | Year 1 | 733600 | 733600 |  |  | 0 |  | Repaint community, west side will need special process in order to seal Masonite to prevent future delamination
107 | 82480 | Washer & Dryer in Unit | Washer & Dryer Modifications | Capex | Year 1 | 493324 | 261797 | 493324 |  | N/A |  | Washer & Dryer Modifications
92 | 84207 | Interior Unit Upgrades | Interior Unit Upgrades | Capex | Year 1 | 300585 | 41806 | 300585 |  | N/A |  | Interior Unit Upgrades
75 | 84206 | Repair / replace cement fiber siding | Replace rotted Masonite siding with Hardie on west side Equity PCA Item- 4.3.1- Replacement of deteriorated and damaged pressboard siding at the West Campus Equity PCA Item- 4.3.1- Refurbishment of missing and damaged stone veneer to the East Campus Equity PCA Item- 4.3.1- Allowance to refasten the vinyl lap panels of the balcony and patio ceilings around the property Lender PCA (Pressboard Siding Replacement): Deteriorated and damaged pressboard siding was observed in sporadic locations throughout, but most frequently at the West side of the property. Partner recommends replacement of all deteriorated and damaged pressboard siding. Lender PCA (Exterior Wall Cleaning/Repairs): Algae was observed throughout the property, partial and minimal cleaning efforts were reported to have been performed. Partner recommends cleaning of the algae. Sections of stone veneer were observed to have isolated areas of missing stone throughout the east campus of the property. | GC | Year 1 | 220000 | 220000 | 0 |  | 0 |  | Replace rotted Masonite siding with Hardie on west side Equity PCA Item- 4.3.1- Replacement of deteriorated and damaged pressboard siding at the West Campus Equity PCA Item- 4.3.1- Refurbishment of | [5 empty] | 2026-03-26
80 | 83436 | Windows | Equity PCA Item- 4.3.2- Phased Replacement of dwelling window units from wood framed to aluminum framed - West Campus Equity PCA Item- 4.3.2- Phased Replacement of dwelling window units from wood framed to aluminum framed - East Campus Replace broken seals on windows, contingency for repairing 100/yr @ $250 each Lender PCA (Window Replacements):Window units throughout the subject property appeared fogged with condensation, indicative of broken window seals. Partner recommends all fogged and broken windows be replaced at this time. | GC | Year 1 | 215740 | 203240 | 12500 |  | 1 |  | Equity PCA Item- 4.3.2- Phased Replacement of dwelling window units from wood framed to aluminum framed - West Campus Equity PCA Item- 4.3.2- Phased Replacement of dwelling window units from wood fram | [5 empty] | 2026-03-26
151 | 84905 | Water Intrusion Remediation | The SOW will include replacing bathroom vent fans and cleaning dirty AC coils, removing dry water staining and repainting, and combining the bathroom light switch with the vent fan to prevent future SVMG and water staining in bathrooms. The existing capital plan includes various exterior repairs that will address/mitigate against future water leaks, if any (see attached email). | GC | Year 1 | 200000 | 200000 | 0 |  | 0 |  | The SOW will include replacing bathroom vent fans and cleaning dirty AC coils, removing dry water staining and repainting, and combining the bathroom light switch with the vent fan to prevent future S
64 | 84433 | Asphalt composite shingle roofing | Roof repairs Equity PCA Item- 4.4.1- Allowance for replacement of shingles and possible decking Equity PCA Item- 4.4.1- Allowance for replacement of shingles and possible decking of Building 200 - West Campus Equity PCA Item- 4.4.1-Allowance for replacement of shingles and possible decking of Building 300 - West Equity PCA Item- 4.4.1-Allowance for replacement of shingles and possible decking of Building 200 - East Campus Equity PCA Item- 4.4.1-Allowance for replacement of shingles and possible decking of Building 300 - East Campus Equity PCA Item- 4.4.1-Allowance for replacement of shingles and possible decking of Building 500 - East Campus Equity PCA Item- 4.4.1-Allowance for replacement of shingles and possible decking of Building 600 - East Campus Lender PCA (Roof Repairs): Though most of the roofs appeared to have no missing or ridge damage shingles, buildings with wind alleys were noted to have missing tabs and damaged shingles.Sporadic areas of soft decking and cracking was observed during the site visit which could indicate either moisture damaged decking or lateral cracking between rafters. Due to the buildings being constructed around trees, excessive debris accumulation was observed. This presents an increased risk in the EUL rapidly decreasing due to storm water being restricted from easy runoff and increase of moisture and bacteria build up. A proposal from 1st Call Services was provided for inspection and as needed repair of the roof, including repair and sealing of roof penetrations as needed. The proposal indicated a cost of $67,780 for this work. Completion of work as noted within the proposal is recommended. | GC | Year 1 | 190919 | 190919 | 0 |  | 0 |  | Roof repairs Equity PCA Item- 4.4.1- Allowance for replacement of shingles and possible decking | [5 empty] | 2026-03-26
127 | 84390 | Sports Courts | Resurface 3 courts, fix net and stripe for pickleball as well, add pergola, seating, etc. | GC | Year 1 | 175000 | 175000 | 0 |  | 0 |  | Resurface 3 courts, fix net and stripe for pickleball as well, add pergola, seating, etc.
55 | 84104 | Repair balcony framing & decking | Repair balconies Equity PCA Item- 4.1- Rout and seal all cracks in the concrete patios. Periodically monitor for further repairs. Equity PCA Item- 4.2- The elevated concrete slabs at the West Apartment balconies were observed with unsealed cracks, and the majority of the observed balcony slabs were not protected by a waterproofing membrane. Immediate repairs should include routing and sealing all balcony cracks to prevent water intrusion with subsequent application of a waterproofing membrane to the balcony slabs that are not currently protected. Lender PCA (Patio Crack Sealing): cracks should be routed and sealed to reduce water infiltration. Lender PCA (Balcony Slab Repairs): The elevated concrete slabs at the West Apartment balconies were observed with unsealed cracks, and the majority of the observed balcony slabs were not protected by a waterproofing membrane. Immediate repairs should include routing and sealing all balcony cracks to prevent water intrusion with subsequent application of a waterproofing membrane to the balcony slabs that are not currently protected. Lender PCA (Balcony Repairs): Deck boards, posts, handrails, stairs, and trim were observed to be rotted, deteriorated, and damaged throughout the property. Partner recommends rotted and deteriorated deck boards, posts, handrails, stairs, and trim be removed, replaced, and repainted/stained at this time. Partner also recommends refastening of vinyl ceiling panels throughout the subject property. | GC | Year 1 | 150000 | 150000 | 0 |  | 0 |  | Repair balconies Equity PCA Item- 4.1- Rout and seal all cracks in the concrete patios. Periodically monitor for further repairs. Equity PCA Item- 4.2- The elevated concrete slabs at the West Apartme | [5 empty] | 2026-03-26
78 | 84105 | Repair / replace wood trim | Replace damaged trim Equity PCA Item- 4.5- Allowance to refurbish wood trim and balconies around subject property where damaged from moisture intrusion and pestilence | GC | Year 1 | 124000 | 124000 | 0 |  | 0 |  | Replace damaged trim Equity PCA Item- 4.5- Allowance to refurbish wood trim and balconies around subject property where damaged from moisture intrusion and pestilence
53 | 84114 | Repair exterior stair treads and stringers | Replace 90 wood and concrete stair treads. Replace damaged railing on stair cases. Equity PCA Item- 4.2- The wood-framed breezeways and stairs at both the East and West Apartments were observed to contain rotted and/or damaged framing (base of wood stringers, wood treads, wood handrails, precast concrete treads, steel seat angles for stair treads, metal column bases, base of wood columns, wood decking at landings, loose stair treads, etc.). All rotted or damaged wood framing and damaged metal connectors or seat angles should be replaced in kind or strengthened where required in order to restore the structural integrity of the breezeway framing. Lender PCA (Breezeway Repairs): The wood-framed breezeways at both the East and West Apartments were observed to contain rotted and/or damaged framing (base of wood stringers, wood treads, wood handrails, precast concrete treads, steel seat angles for stair treads, metal column bases, base of wood columns, wood decking at landings, loose stair treads, etc.). All rotted or damaged wood framing and damaged metal connectors or seat angles should be replaced in kind or strengthened where required in order to restore the structural integrity of the breezeway framing. | GC | Year 1 | 94000 | 94000 | 0 |  | 0 |  | Replace 90 wood and concrete stair treads. Replace damaged railing on stair cases. Equity PCA Item- 4.2- The wood-framed breezeways and stairs at both the East and West Apartments were observed to con | [5 empty] | 2026-03-26
18 | 84204 | Pavement | Repair potholes on both sides of community Equity PCA Item- 3.2.2- Linear cracking, "map", or "alligator" cracking, and pothole formation were noted at the drive aisle and parking areas throughout the subject property. Three areas of pavement failure were noted, caused by shallow tree root heaving, these areas were generally located in front of West Buildings 1100 and 1200, between West Buildings 1700 and 1900, and in front of Building 600. Repairs to the noted areas, repaving and subgrade stabilization, including removal of tree roots and trees is recommended. Lender PCA (Asphalt Pavement Repair): Linear cracking, "map", or "alligator" cracking, and pothole formation were noted at the drive aisle and parking areas throughout the subject property. Three areas of pavement failure were noted, caused by shallow tree root heaving, these areas were generally located in front of West Buildings 1100 and 1200, between West Buildings 1700 and 1900, and in front of Building 600. Repairs to the noted areas, repaving and subgrade stabilization, including removal of tree roots and trees is recommended. | GC | Year 1 | 80000 | 80000 | 0 |  | 0 |  | Repair potholes on both sides of community Equity PCA Item- 3.2.2- Linear cracking, "map", or "alligator" cracking, and pothole formation were noted at the drive aisle and parking area | [5 empty] | 2026-03-26
14 | 84303 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | Capex | Year 1 | 75000 | 165469 | -90469 |  | N/A |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
24 | 84517 | Erosion control | Fill eroded areas around buildings Equity PCA Item- 3.2.4-Significant areas of missing or lost ground cover were noted throughout the subject property and around each building area. The limited ground cover has resulted in erosion with siltation of pavement and parking area, erosion and undermining of concrete walkways and steps, and exposing tree and shrubbery roots. Reestablishing ground cover throughout the landscaped areas of the subject property is recommended. Lender PCA (Erosion Control): Significant areas of missing or lost ground cover were noted throughout the subject property and around each building area. The limited ground cover has resulted in erosion with siltation of pavement and parking area, erosion and undermining of concrete walkways and steps, and exposing tree and shrubbery roots. Reestablishing ground cover throughout the landscaped areas of the subject property is recommended. | GC | Year 1 | 70000 | 70000 | 0 |  | 0 |  | Fill eroded areas around buildings Equity PCA Item- 3.2.4-Significant areas of missing or lost ground cover were noted throughout the subject property and around each building area. The limited grou | [5 empty] | 2026-03-26
124 | 84360 | Pool Furniture | New furniture at 2 pools | Capex | Year 1 | 70000 | 9000 | 61000 |  | N/A |  | New furniture at 2 pools
56 | 84121 | Repair patio/balcony railings | Repair balcony railings | GC | Year 1 | 68000 | 68000 | 0 |  | 0 |  | Repair balcony railings
65 | 83439 | Gutters & downspouts | Clean, repitch, and secure gutters. Ongoing gutter cleanout. Equity PCA Item- 4.4.2- Allowance for replacement of gutter and downspouts lot wide Lender PCA (Gutter Replacement): Gutters were observed to be extremely clogged with leaf debris preventing easy water runoff from roof system. Gutters were also observed to have inadequate spacing of gutter fasteners which has caused gutters to have a drastically shortened EUL and causing sagging. The gutters and downspouts were reported and observed to be from original construction. Partner recommends replacement of all gutter and downspout assemblies. | GC | Year 1 | 66000 | 66000 | 0 |  | 0 |  | Clean, repitch, and secure gutters. Ongoing gutter cleanout. Equity PCA Item- 4.4.2- Allowance for replacement of gutter and downspouts lot wide | [5 empty] | 2026-03-26
109 | 84239 | Fire Stops | Mix of Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods and LowPro (Pair covers 4 burner range)- For range top microwaves | Capex | Year 1 | 61944 | 47962 | 13982 |  | N/A |  | Mix of Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods and LowPro (Pair covers 4 burner range)- For range top microwaves
27 | 84095 | Resurface swimming pool | Resurface both pools, Replace missing pool tile at water line | GC | Year 1 | 60000 | 60000 | 0 |  | 0 |  | Resurface both pools, Replace missing pool tile at water line
135 | 84275 | Entry gates | None, can look at adding but there are 4 access drives | Capex | Year 1 | 60000 | 29350 | 60000 |  | N/A |  | None, can look at adding but there are 4 access drives
143 | 84209 | Water pressure regulator / back-flow preventer | Equity PCA Item- 5.1- Observed water heaters were often not provided with drain pans and lacked discharge piping from the temperature & pressure relief valve (T&P valve) or the installed piping was routed upwards. Partner recommends that the water heaters be installed atop a pedestal and provided with an approved drain pan and piping from the T&P valve routed to the drain pan. Lender PCA (Water Heater T&P): Observed water heaters were often not provided with drain pans, which are required where a storage tank-type water heater is installed in a location where water leakage from the tank will cause damage. Additionally, water heaters observed often also lacked discharge piping from the temperature & pressure relief valve (T&P valve) or the installed piping was routed upwards which would not allow proper drainage. Partner recommends that the water heaters be installed atop a pedestal and provided with an approved drain pan.The drain pan should be provided with a drain line routed to a hub drain connected to the sanitary drain piping or routed to the building exterior. Piping from the T&P valve would then be routed to the drain pan. | GC | Year 1 | 52500 | 52500 | 0 |  | 0 |  | Equity PCA Item- 5.1- Observed water heaters were often not provided with drain pans and lacked discharge piping from the temperature & pressure relief valve (T&P valve) or the installed piping was ro | [5 empty] | 2026-03-26
20 | 84204 | Asphalt Coating | Crack fill cracks over 1/2 inch | GC | Year 1 | 50000 | 50000 | 0 |  | 0 |  | Crack fill cracks over 1/2 inch
66 | 84433 | Flashing | Repair damaged flashing | GC | Year 1 | 50000 | 50000 | 0 |  | 0 |  | Repair damaged flashing
137 | 84450 | Security Camera System | Security Cameras | Capex | Year 1 | 50000 | 0 | 50000 |  | N/A |  | Security Cameras
22 | 84115 | Sidewalks | Remove and replace areas of trip hazards Lender PCA (Walkway Repairs): Cracking and heaving/settling of walkways was noted throughout the subject property. Repairs are recommended | GC | Year 1 | 46000 | 46000 | 0 |  | 0 |  | Remove and replace areas of trip hazards Lender PCA (Walkway Repairs): Cracking and heaving/settling of walkways was noted throughout the | [5 empty] | 2025-06-26
153 | 83515 | Green Program - Echelon Water Savings | Installation of aerators on faucets and shower heads | GC | Year 1 | 42312 | 42312 | 0 |  | 0 |  | Installation of aerators on faucets and shower heads
97 | 84106 | Clean Dryer vents | Dryer Vent Cleaning | GC | Year 1 | 39300 | 39300 | 0 |  | 0 |  | Dryer Vent Cleaning
68 | 84433 | Repair/Replace roof pipe vents | Equity PCA Item- 4.4.1- Allowance for replacement of all pipe penetrations lot wide | GC | Year 1 | 38750 | 38750 | 0 |  | 0 |  | Equity PCA Item- 4.4.1- Allowance for replacement of all pipe penetrations lot wide
31 | 84361 | Swimming pool lighting | Replace pool lights | GC | Year 1 | 36000 | 36000 | 0 |  | 0 |  | Replace pool lights
163 | 84210 | Common area light fixtures | Replace wall pack lights | GC | Year 1 | 36000 | 36000 | 0 |  | 0 |  | Replace wall pack lights
162 | 84210 | Electrical distribution | inspect, repair or replace lighting controllers | GC | Year 1 | 33000 | 33000 | 0 |  | 0 |  | inspect, repair or replace lighting controllers
57 | 84102 | Expansion Joints | Property Expansion Joints | GC | Year 1 | 32000 | 32000 | 0 |  | 0 |  | Property Expansion Joints
76 | 84120 | Breezeways - Interior Coordiors | Repair soffits | GC | Year 1 | 32000 | 32000 | 0 |  | 0 |  | Repair soffits
29 | 84361 | Replace swimming pool deck | Pressure wash pool decks, , level paver trip hazards | GC | Year 1 | 30000 | 30000 | 0 |  | 0 |  | Pressure wash pool decks, , level paver trip hazards
34 | 84219 | Carports / Garages | Repair garage siding and trim Equity PCA Item- 4.2- Garage 12 at the East Apartments exhibited damage from vehicle impact. The wood stud wall, interior finishes and exterior cladding should be repaired to restore the structural integrity and watertightness of the structure. Lender PCA (Garage Repairs): The interior finishes and exterior cladding of Garage 12 at the East Apartments exhibited damage from vehicle impact. It is likely that the wood-framed wall has also experienced damage from the impact. The wood stud wall, interior finishes and exterior cladding should be repaired to restore the structural integrity and watertightness of the structure. | GC | Year 1 | 30000 | 30000 | 0 |  | 0 |  | Repair garage siding and trim Equity PCA Item- 4.2- Garage 12 at the East Apartments exhibited damage from vehicle | [5 empty] | 2026-03-26
35 | 84111 | Dumpster enclosures | Repair compactor areas Lender PCA (Refuse Enclosure Repairs):The West development dumpster enclosure appeared to be in generally good condition. A minor area of brick finish mortar cracking was observed. Repointing and mortar repairs are recommended. The East development dumpster enclosure appeared to be in generally good condition. Isolated areas of broken and warped slats at the perimeter and gate were noted. Replacing damaged and warped slats is recommended. | GC | Year 1 | 30000 | 30000 | 0 |  | 0 |  | Repair compactor areas Lender PCA (Refuse Enclosure Repairs):The West developm | [5 empty] | 2026-03-26
79 | 84206 | Shutters | Replace damaged shutters | GC | Year 1 | 30000 | 30000 | 0 |  | 0 |  | Replace damaged shutters
123 | 84361 | Pool Area Remodel | Turf areas around pool | GC | Year 1 | 30000 | 30000 | 0 |  | 0 |  | Turf areas around pool
148 | 84400 | Fire Sprinkler Risers | Equity PCA Item- 5.5.1- The following risers were observed to have missing 5-year riser inspection tags: 500E, 600E, 300W, 400W, 700W, 1000W, 1100W, 1200W, 1400W, and 1500W. Inspection and certification of the risers is recommended | Capex | Year 1 | 30000 | 28487 | 30000 |  | N/A |  | Equity PCA Item- 5.5.1- The following risers were observed to have missing 5-year riser inspection tags: 500E, 600E, 300W, 400W, 700W, 1000W, 1100W, 1200W, 1400W, and 1500W. Inspection and certificati
19 | 84201 | Stripe parking areas | Stripe Parking Areas | GC | Year 1 | 28000 | 28000 | 0 |  | 0 |  | Stripe Parking Areas
51 | 84430 | Concrete deck / floor fill | Grind and seal cracks in light weight concrete landings | GC | Year 1 | 27000 | 27000 | 0 |  | 0 |  | Grind and seal cracks in light weight concrete landings
155 | 83225 | Condensate drain overflow sensors | Equity PCA Item- 5.2- The fan coil units were not fitted with condensate drain overflow sensors. As installed, clogged drain lines overflow onto the surrounding floor until the leak is discovered. Partner recommends installation of overflow sensors | GC | Year 1 | 26200 | 26200 | 0 |  | 0 |  | Equity PCA Item- 5.2- The fan coil units were not fitted with condensate drain overflow sensors. As installed, clogged drain lines overflow onto the surrounding floor until the leak is discovered. Par
164 | 84210 | Electrical Repairs | Equity PCA Item- 5.3- General electrical deficiencies were observed including GFCI outlets , exit lighting, receptacle covers, switch covers, exposed wiring, missing breaker fillers, and damaged lighting. Partner recommends budgeting for a review of these and similar areas with repairs made as needed. Equity PCA Item- 5.3- Poor low voltage workmanship was observed in the building-500 east exterior cabling. Based on the current condition, Partner recommends budgeting for immediate corrections Equity PCA Item- 5.3- The site contact did not report any recent ground fault system test, infrared (IR) scan, or arc-flash test. It did not appear that IR scans have been completed at the property. IR scans are often regularly performed on electrical distribution equipment as preventative maintenance. IR scans can identify loose connections, load balance issues, defective breakers, and excessive circuit loads. Partner recommends that IR scans of the electrical equipment be completed in the immediate term Lender PCA (Electrical Repairs): General electrical deficiencies were observed. Based on the current condition, Partner recommends budgeting for a review of these and similar areas with repairs made as needed. | GC | Year 1 | 26000 | 26000 | 0 |  | 0 |  | Equity PCA Item- 5.3- General electrical deficiencies were observed including GFCI outlets , exit lighting, receptacle covers, switch covers, exposed wiring, missing breaker fillers, and damaged light | [5 empty] | 2025-06-26
17 | 84385 | Storm sewer piping | Clear drains around buildings | GC | Year 1 | 25000 | 25000 | 0 |  | 0 |  | Clear drains around buildings
26 | 84434 | Retaining walls | Repair fences on retaining walls Equity PCA Item- 4.1- The segmental retaining walls at the East Aparments contained loose, damaged, or displaced guardrail sections along with displaced blocks in some limited locations. Immediate repairs should include re-installing the displace blocks and sectionally replacing the damaged or displaced wood guardrails. Equity PCA Item- 4.2- The brick veneer at the retaining walls at the West Apartments were noted with detached and deteriorated brick sections. Immediate repairs should include restoration of all damaged sections of the brick veneer to improve watertightness. Lender PCA (Retaining Wall Repair): The segmental retaining walls at the East Apartments contained loose, damaged, or displaced guardrail sections along with displaced blocks in some limited locations. Immediate repairs should include re- installing the displaced blocks and sectionally replacing the damaged or displaced wood guardrails. | GC | Year 1 | 25000 | 25000 | 0 |  | 0 |  | Repair fences on retaining walls Equity PCA Item- 4.1- The segmental retaining walls at the East Aparments contained loose, damaged, or displaced guardrail sections along with displaced blocks in some | [5 empty] | 2026-03-26
113 | 84290 | Signage - Entry Monument | Reface or possibly enlarge 2 monument signs | Capex | Year 1 | 25000 | 25101 | -62 |  | N/A |  | Reface or possibly enlarge 2 monument signs
145 | 84470 | Plumbing Repairs | Plumbing Fixture Leaks, Ongoing repairs due to high number of work orders. Plumbing Repairs: Ongoing repair of water leaks behind sheetrock due to high number of work orders | Capex | Year 1 | 23000 | 15546 | 8359 |  | N/A |  | Plumbing Fixture Leaks, Ongoing repairs due to high number of work orders. Plumbing Repairs: Ongoing repair of water leaks behind sheetrock due to high number of work orders
118 | 84208 | Clubhouse / Office Remodel | Minor refresh & repairs | GC | Year 1 | 20000 | 20000 | 0 |  | 0 |  | Minor refresh & repairs
119 | 84208 | Clubhouse / Office Furniture | Misc furniture items | Capex | Year 1 | 20000 | 106226 | -86226 |  | N/A |  | Misc furniture items
32 | 84205 | Fences & gates - swimming pool | Adjust gates and repair gate latches | GC | Year 1 | 18000 | 18000 | 0 |  | 0 |  | Adjust gates and repair gate latches
67 | 84433 | Sealants & caulking | Roof Sealants & Caulking | GC | Year 1 | 18000 | 18000 | 0 |  | 0 |  | Roof Sealants & Caulking
149 | 84400 | Fire Sprinklers | Equity PCA Item- 5.5.1- General fire sprinkler deficiencies were observed. The observed general deficiencies included damaged riser access doors and insulation, improperly mounted sprinkler heads, missing wrench in spare sprinkler head box and damaged swtiches. Repair of fire sprinkler deficiencies is recommended | Capex | Year 1 | 16030 | 15600 | 15430 |  | N/A |  | Equity PCA Item- 5.5.1- General fire sprinkler deficiencies were observed. The observed general deficiencies included damaged riser access doors and insulation, improperly mounted sprinkler heads, mis
158 | 83225 | HVAC Preventative Maintenance | Equity PCA Item- 5.2- The fan coil units were observed with dirty coils and filters at Units 318E, 1017W, 303E. Partner recommends budgeting for review of all units with cleaning the fan coil units and replacement of the filters as needed | GC | Year 1 | 15750 | 15750 | 0 |  | 0 |  | Equity PCA Item- 5.2- The fan coil units were observed with dirty coils and filters at Units 318E, 1017W, 303E. Partner recommends budgeting for review of all units with cleaning the fan coil units an
122 | 84190 | Fitness Equipment | Equipment repairs and some new equipment | Capex | Year 1 | 15000 | 3712 | 11288 |  | N/A |  | Equipment repairs and some new equipment
159 | 83225 | HVAC Preventative Maintenance | Equity PCA Item- 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the units. This condition reduces unit efficiency and decrease the useful life of the equipment. Repair of deteriorated insulation at the refrigeration linesets is recommended. The HVAC units often have labels that do not meet durability requirements, which can fade, detach in adverse weather, or get misplaced during replacements. Partner recommends replacing all labels with engraved tags directly on the body of each disconnect, as covers are frequently switched or lost Lender PCA (Refrigerant Line Insulation): Insulation at the refrigerant lines from the condensing units were deteriorated at many of the units. This condition reduces unit efficiency and decrease the useful life of the equipment. Repair of deteriorated insulation at the refrigeration linesets is recommended. Lender PCA (Fan Coil Cleaning): The fan coil units were observed with dirty coils and filters at Units 318E, 1017W, 303E. Partner recommends budgeting for review of all units with cleaning the fan coil units and replacement of the filters as needed. | GC | Year 1 | 13100 | 13100 | 0 |  | 0 |  | Equity PCA Item- 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the units. This condition reduces unit efficiency and decrease the useful life of the e | [5 empty] | 2026-03-26
52 | 84433 | Roof deck | Roof Deck Repairs | GC | Year 1 | 12000 | 12000 | 0 |  | 0 |  | Roof Deck Repairs
165 | 84239 | Emergency Lighting | Equity PCA Item- 5.3- Emergency lights were not installed at any West buildings. Installation of emergency lighting is recommended as an immediate action Equity PCA Item- 5.3- Emergency lighting was damaged or missing at 30% of location on the East Buildings. Based on the current condition, Partner recommends budgeting for immediate corrections | GC | Year 1 | 10800 | 10800 | 0 |  | 0 |  | Equity PCA Item- 5.3- Emergency lights were not installed at any West buildings. Installation of emergency lighting is recommended as an immediate action Equity PCA Item- 5.3- Emergency lighting wa
33 | 84203 | Outdoor Kitchen | Pressure wash area and allowance for grill repairs or replacement with charcoal | GC | Year 1 | 10000 | 10000 | 0 |  | 0 |  | Pressure wash area and allowance for grill repairs or replacement with charcoal
121 | 84190 | Fitness Center Remodel | Paint and misc repairs | GC | Year 1 | 10000 | 10000 | 0 |  | 0 |  | Paint and misc repairs
132 | 84208 | Veritas After School Care | Housing Authority Program (Veritas) - Additional School Room | Capex | Year 1 | 10000 | 53113 | -43113 |  | N/A |  | Housing Authority Program (Veritas) - Additional School Room
150 | 84905 | Radon Remediation | Radon Mitigation | GC | Year 1 | 10000 | 10000 | 0 |  | 0 |  | Radon Mitigation
147 | 84211 | Fire Alarm Deficiencies | Equity PCA Item- 5.5.1- The fire alarm annual inspection report was not provided. Reports often include recommendations and issues not noted on the tags. We recommend acquiring the full inspection report. Partner recommends budgeting a contingency for corrections that may be required by the report. Equity PCA Item- 5.5.1- A portion of fire alarm control panels are in poor condition. The systems were observed with trouble alarms at buildings 500E and 600E. Immediate correction is recommended. | PMC | Year 1 | 9000 | 35000 | -69487 |  | N/A |  | Equity PCA Item- 5.5.1- The fire alarm annual inspection report was not provided. Reports often include recommendations and issues not noted on the tags. We recommend acquiring the full inspection re
152 | 84209 | Office Faucet | Office Faucet Replacement | GC | Year 1 | 8000 | 8000 | 0 |  | 0 |  | Office Faucet Replacement
110 | 82460 | Unit deferred maintenance | Equity PCA Item- 8.0- Address potential water intrusion, Unit 403 East. Equity PCA Item- 8.0- Address potential microbial growth, HVAC ducts, and vents Unit 314 West Lender PCA (Moisture/Mold Repairs): Evidence of water damage and/or suspect microbial growth was observed during the survey. Partner observed a blower and area of water intrusion in the bedroom of East Unit 403, partial removal of the rug in this area indicated potential suspect microbial growth on subflooring and carpet tack-board and on the wood baseboard and door framing. Partner observed suspect microbial growth on the HVAC vents in West Unit 314. (Also Pest treatment at unit $1,500) | GC | Year 1 | 6500 | 6500 | 0 |  | 0 |  | Equity PCA Item- 8.0- Address potential water intrusion, Unit 403 East. Equity PCA Item- 8.0- Address potential microbial growth, HVAC ducts, and vents Unit 314 West | [5 empty] | 2026-03-26
28 | 84361 | Replace swimming pool coping | Repair or replace broken coping Lender PCA (Pool Coping/Tile Repair): Throughout the West development pool area, as well as minor spalling of the pool coping. Replacing missing water line tile and coping repairs are warranted. | GC | Year 1 | 5000 | 5000 | 0 |  | 0 |  | Repair or replace broken coping Lender PCA (Pool Coping/Tile Repair): Throughout the West development pool area, as we | [5 empty] | 2026-03-26
37 | 83520 | ADA Compliance | Equity PCA Item- 7.0- Reconfigure leasing office restroom for ADA compliance | GC | Year 1 | 4500 | 4500 | 0 |  | 0 |  | Equity PCA Item- 7.0- Reconfigure leasing office restroom for ADA compliance
146 | 84211 | Fire Protection Deficiencies | Equity PCA Item- 5.5.1- General fire protection deficiencies were observed. The observed general deficiencies included damaged fire- and life safety devices at 316E, and 611E, lack of combo smoke detectors at Units 1507W and 1812W, inner cover is missing at the fire alarm control panels at 700E, 800E, 900E, 1000E, and 1100E, and aged batteries at buildings East 100 to 300 and 500 to 1100. Expired fire extinguisher tags at limited areas and yellow tagged fire extinguisher at building 500.Partner recommends budgeting for a review of these and similar areas with repairs made as needed. | PMC | Year 1 | 4500 | 39243 | -34743 |  | N/A |  | Equity PCA Item- 5.5.1- General fire protection deficiencies were observed. The observed general deficiencies included damaged fire- and life safety devices at 316E, and 611E, lack of combo smoke det
133 | 84260 | Mailboxes | Lender PCA (Mailbox Repair): Several mailboxes were noted to contain damaged or missing doors. Repair of the mailboxes is recommended. | PMC | Year 1 | 500 | 5894 | -5394 |  | N/A |  | Lender PCA (Mailbox Repair): Several mailboxes were noted to contain damaged or missing doors. Repair of the mailboxes is recommended. | [5 empty] | 2026-03-26
PROJECTS subtotal (excl. contingency/CM fee)
170 | 84505 | Construction Management Fee | CM Fees | CMF | CM Fee | 271220 | 0 | 271220 |  | N/A |  | CM Fees
169 | 84510 | Contingency | Contingency Amount | CON | Contingency | 258304 | 0 | 258304 |  | N/A |  | Contingency Amount

## Azur Aparments
Azur Aparments — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
73 | 0800 - Exterior Wall | Exterior building | Paint Community Lender PCR Item- $62,400- The exterior walls appeared to be in generally good to fair condition. Isolated areas of wood deterioration and damaged trim were noted throughout. Additionally, the painted surfaces appeared to be faded. Repair of the damaged siding/trim components and full exterior painting is recommended. | GC | Year 1 | 208000 | 208000 |  |  | 0 |  | Paint Community Lender PCR Item- $62,400- The exterior walls appeared to be in generally good to fair condition. Isolated areas of wood deterioration and damaged trim were noted throughout. Additiona | [5 empty] | 1900-06-28
12 | 0200 - Site Utilities & Improvements | Pavement | Large areas of asphalt paving Lender PCR Item- $6,000- Several pot holes and areas of “alligatoring”and general deterioration were noted to be scattered throughout the subject property. The seal coating appeared to be generally worn with several areas of loose gravel present. | GC | Year 1 | 91000 | 91000 |  |  | 0 |  | Large areas of asphalt paving Lender PCR Item- $6,000- Several pot holes and areas of “alligatoring”and general deterioration were noted to be scattered throughout the subject property. The seal coati | [5 empty] | 1900-12-30
104 | 0900 - FF&E in Units | Turf private yards | Approximately 96 units with yards that we can turf | GC | Year 1 | 86400 | 86400 |  |  | 0 |  | Approximately 96 units with yards that we can turf
14 | 0200 - Site Utilities & Improvements | Asphalt Coating | Seal coat lot Equity PCA Item 3.2.2- $42,000- The seal coating appeared to be generally worn with several areas of loose gravel present. Additionally, the striping in several areas was faded or deteriorated. Partner recommends reapplication of the seal coat and striping subsequent to completion of pavement repairs. | GC | Year 1 | 80000 | 80000 |  |  | 0 |  | Seal coat lot Equity PCA Item 3.2.2- $42,000- The seal coating appeared to be generally worn with several areas of loose gravel present. Additionally, the striping in several areas was faded or deter
147 | 1500- HVAC | Separate AC condenser | Separate Condensers to achieve 12 inches between units, add equiptment pads as needed | GC | Year 1 | 41600 | 41600 |  |  | 0 |  | Separate Condensers to achieve 12 inches between units, add equiptment pads as needed
116 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Furniture | New furniture in clubhouse, supplement furniture in office | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | New furniture in clubhouse, supplement furniture in office
120 | 1100- Specialties, Equipment & Furnishings | Pool Furniture & Games |  | GC | Year 1 | 40000 | 40000 |  |  | 0
19 | 0200 - Site Utilities & Improvements | Resurface swimming pool |  | GC | Year 1 | 30000 | 30000 |  |  | 0
50 | 0400 - Structure | Repair exterior stair railings | Repair and Paint | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Repair and Paint
107 | 0900 - FF&E in Units | Unit deferred maintenance | There are 8 down units- all of Building #16 is down due to fire Appx. 57 units noted to have prior water stains on the dropped ceiling tiles in the bathrooms | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | There are 8 down units- all of Building #16 is down due to fire Appx. 57 units noted to have prior water stains on the dropped ceiling tiles in the bathrooms
16 | 0200 - Site Utilities & Improvements | Landscape irrigation | Inspect and repair irrigation | GC | Year 1 | 29000 | 29000 |  |  | 0 |  | Inspect and repair irrigation
74 | 0800 - Exterior Wall | Repair / replace wood trim |  | GC | Year 1 | 28000 | 28000 |  |  | 0
17 | 0200 - Site Utilities & Improvements | Erosion control |  | GC | Year 1 | 26000 | 26000 |  |  | 0
49 | 0400 - Structure | Repair exterior stair treads and stringers | Replace bad stair treads | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | Replace bad stair treads
11 | 0200 - Site Utilities & Improvements | Storm sewer piping | Replace drainage on pool deck with larger channel drains and connect to proper drain | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Replace drainage on pool deck with larger channel drains and connect to proper drain
10 | 0200 - Site Utilities & Improvements | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
51 | 0400 - Structure | Repair balcony framing & decking |  | GC | Year 1 | 20000 | 20000 |  |  | 0
75 | 0800 - Exterior Wall | storage room doors - exterior | Replace damaged storage room doors | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Replace damaged storage room doors
119 | 1100- Specialties, Equipment & Furnishings | Pool Area Remodel | Look at adding shade areas over pool and grill | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Look at adding shade areas over pool and grill
121 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Area Remodel | Add grill area with gazebo and furniture by mail area | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Add grill area with gazebo and furniture by mail area
47 | 0400 - Structure | Concrete deck / floor fill | Entrance landings | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Entrance landings
60 | 0700 - Roofing | Asphalt composite shingle roofing | Minor roof repairs | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | Minor roof repairs
61 | 0700 - Roofing | Gutters & downspouts | Clean gutters | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | Clean gutters
71 | 0800 - Exterior Wall | Repair / replace cement fiber siding | Replace damaged siding in breezeways | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | Replace damaged siding in breezeways
23 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair dumpster enclosures | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Repair dumpster enclosures
94 | 0900 - FF&E in Units | Clean Drier vents |  | GC | Year 1 | 15600 | 15600 |  |  | 0
124 | 1100- Specialties, Equipment & Furnishings | Dog Park | Look at adding more furniture, jumps, shade | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Look at adding more furniture, jumps, shade
18 | 0200 - Site Utilities & Improvements | Retaining walls | Replace damaged railroad tie wall | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Replace damaged railroad tie wall
72 | 0800 - Exterior Wall | Tuck-pointing | Tuck point and caulk | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Tuck point and caulk
13 | 0200 - Site Utilities & Improvements | Stripe parking areas |  | GC | Year 1 | 11000 | 11000 |  |  | 0
139 | 1400 - Plumbing | Domestic water piping | Insulate main water lines going into buildings Equity PCA Item 5.1- $5,000-The domestic water piping at the central domestic hot water boilers is not insulated. Material is stacked around the boilers making them difficult to access and to maintain. Partner recommends that the domestic hot water piping be insulated and materials that block access to the boilers be removed | GC | Year 1 | 11000 | 11000 |  |  | 0 |  | Insulate main water lines going into buildings Equity PCA Item 5.1- $5,000-The domestic water piping at the central domestic hot water boilers is not insulated. Material is stacked around the boilers
155 | 1600 - Electrical | CO Detectors | Residential units were not provided with CO detectors. Residential units had wood burning fireplaces. Partner recommends that hard-wired, battery-backup combination smoke/CO detectors be installed in each of the residential units with wood burning fire places. | Capex | Year 1 | 10400 | 4110 |  |  | N/A |  | Residential units were not provided with CO detectors. Residential units had wood burning fireplaces. Partner recommends that hard-wired, battery-backup combination smoke/CO detectors be installed in |  | Completed
105 | 0900 - FF&E in Units | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | GC | Year 1 | 10048 | 10049 |  |  | 0 |  | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods
39 | 0200 - Site Utilities & Improvements | Arbor Realty Trust Deferred Maintenance Items | Items noted from lender inspection, items due 11/11/24 & 4/9/25. Property owner only completing November items | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Items noted from lender inspection, items due 11/11/24 & 4/9/25. Property owner only completing November items
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Flooring & paint ok, look at additional HVAC or insulation in roof since it gets very hot in clubhouse. Misc repairs and other items | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Flooring & paint ok, look at additional HVAC or insulation in roof since it gets very hot in clubhouse. Misc repairs and other items
122 | 1100- Specialties, Equipment & Furnishings | Picnic/Grill Furniture |  | GC | Year 1 | 10000 | 10000 |  |  | 0
127 | 1100- Specialties, Equipment & Furnishings | Access Control System | Office alarm and restore night drop box for keys needed | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Office alarm and restore night drop box for keys needed
22 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Repair and paint Equity PCA Item 3.2.7- $7,500- Partner observed some areas of damaged fencing along the northwest perimeter as well as a portion of the southeast perimeter that was broken off to allow for fire truck equipment access next to Building 16. Several areas of patio fencing were observed with broken or detached slats and at least one dumpster enclosure wall was noted to be leaning. Repair of the damaged areas of fencing is recommended. | GC | Year 1 | 9600 | 9600 |  |  | 0 |  | Repair and paint Equity PCA Item 3.2.7- $7,500- Partner observed some areas of damaged fencing along the northwest perimeter as well as a portion of the southeast perimeter that was broken off to all
136 | 1100- Specialties, Equipment & Furnishings | Golf Cart | Need leasing cart | GC | Year 1 | 9000 | 9000 |  |  | 0 |  | Need leasing cart
20 | 0200 - Site Utilities & Improvements | Replace swimming pool coping | Deck o seal | GC | Year 1 | 8600 | 8600 |  |  | 0 |  | Deck o seal
152 | 1600 - Electrical | Electrical distribution | Repair house panels issues | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | Repair house panels issues
25 | 0200 - Site Utilities & Improvements | Fences & Gates - Site Perimeter | Lender PCR Item- $7,500- Partner observed some areas of damaged fencing along the northwest perimeter as well as a portion of the southeast perimeter that was broken off to allow for fire truck equipment access next to Building 16. Several areas of patio fencing were observed with broken or detached slats and at least one dumpster enclosure wall was noted to be leaning. Repair of the damaged areas of fencing is recommended. | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Lender PCR Item- $7,500- Partner observed some areas of damaged fencing along the northwest perimeter as well as a portion of the southeast perimeter that was broken off to allow for fire truck equipm | [5 empty] | 1900-06-28
148 | 1500- HVAC | HVAC Condensing Refrigerant Line Insulation | Equity PCA Item 5.2- $7,500- Many of the ground mounted AC condensing units were found to have insulation missing from their exterior refrigerant lines. The missing insulation makes the unit run less efficiently and therefore to have longer run times and a shorter useful life. Partner recommends that all units to be inspected and the missing insulation re-installed. | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Equity PCA Item 5.2- $7,500- Many of the ground mounted AC condensing units were found to have insulation missing from their exterior refrigerant lines. The missing insulation makes the unit run less
154 | 1600 - Electrical | Fire Extinguishers | Lender PCR Item- $1,500- The common fire extinguisher at the resident postal boxes structure had an expired tag from 2015. Partner recommends an annual inspection of the fire extinguishers. Equity PCA Item 5.5.1- $100- A cabinet mounted fire extinguisher at the mail kiosk near the Leasing Office/Clubhouse Building had an expired tag from January of 2015. Inspection and certification of the extinguisher is recommended. | GC | Year 1 | 7100 | 7100 |  |  | 0 |  | Lender PCR Item- $1,500- The common fire extinguisher at the resident postal boxes structure had an expired tag from 2015. Partner recommends an annual inspection of the fire extinguishers. Equity PCA | [5 empty] | 1900-01-29
15 | 0200 - Site Utilities & Improvements | ADA parking & curb cuts | Replace ADA signage | GC | Year 1 | 6800 | 6800 |  |  | 0 |  | Replace ADA signage
21 | 0200 - Site Utilities & Improvements | Repair / replace swimming pool pumps | Anti entrapment devices | GC | Year 1 | 6800 | 6800 |  |  | 0 |  | Anti entrapment devices
63 | 0700 - Roofing | Sealants & caulking |  | GC | Year 1 | 6800 | 6800 |  |  | 0
153 | 1600 - Electrical | Unit Electrical Panel Repairs | Equity PCA Item 5.3- $5,200- During the inspection it was noted that many of the electrical panels within the apartments were painted shut and could not be opened. This makes it difficult to reset a breaker if one trips in the apartment. Partner recommends that all apartment electrical panels be inspected to assure that the breakers are accessible. This might include replacing the panel covers. | GC | Year 1 | 5200 | 5200 |  |  | 0 |  | Equity PCA Item 5.3- $5,200- During the inspection it was noted that many of the electrical panels within the apartments were painted shut and could not be opened. This makes it difficult to reset a b
62 | 0700 - Roofing | Flashing |  | GC | Year 1 | 3400 | 3400 |  |  | 0
114 | 1100- Specialties, Equipment & Furnishings | Designer Fees | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas | GC | Year 1 | 2500 | 2500 |  |  | 0 |  | Exterior Paint, Unit Interiors, Clubhouse/Amenity areas
130 | 1100- Specialties, Equipment & Furnishings | Grills | Misc repairs | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | Misc repairs
24 | 0200 - Site Utilities & Improvements | Accessibility | Lender PCR Item- $1,350- Lack of accessible toilet room at the leasing office including lack of lever hardware, toilet grab bars, and accessible vanity. Based on the observed conditions, installation of signage noting for employee use only is recommended. Consideration for ADA accessibility at the time of remodel is recommended. | GC | Year 1 | 1650 | 1650 |  |  | 0 |  | Lender PCR Item- $1,350- Lack of accessible toilet room at the leasing office including lack of lever hardware, toilet grab bars, and accessible vanity. Based on the observed conditions, installation | [5 empty] | 1900-06-28
48 | 0400 - Structure | Wall framing |  | GC | Year 1 | 1500 | 1500 |  |  | 0
103 | 0900 - FF&E in Units | Unit Exhaust Fan | Equity PCA Item 5.2- $500- Apartment 502 was noted to have a missing exhaust fan in one of its bathrooms that did not have a window. Property management reported the exhaust fan was not provided due to an electrical problem. Partner recommends that the electrical service for the exhaust fan be repaired and the bathroom exhaust fan be replaced | GC | Year 1 | 500 | 500 |  |  | 0 |  | Equity PCA Item 5.2- $500- Apartment 502 was noted to have a missing exhaust fan in one of its bathrooms that did not have a window. Property management reported the exhaust fan was not provided due t
PROJECTS subtotal (excl. contingency/CM fee)
159 | Contingency & Fees | Contingency |  | CON | Contingency | 329680 | 0 |  |  | N/A
160 | Contingency & Fees | Construction Management Fee |  | CMF | CM Fee | 77884 | 0 |  |  | N/A

## Cambridge Square
Cambridge Square — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
100 | 83301.0 | WDO | Wood Destroying Organisms- LPCA - Select areas of building exteriors were observed to have dryrot damage in locations throughout the subject property. Partner recommends that a complete survey of the subject property be performed by a certified pest control inspector independent of the currently contracted pest control service. | PMC | Year 1 | 2500 | 0 |  |  | N/A |  | Wood Destroying Organisms- LPCA - Select areas of building exteriors were observed to have dryrot damage in locations throughout the subject property. Partner recommends that a complete survey of the | [5 empty] | 2026-12-01
24 | 83520.0 | ADA parking & curb cuts | LPCA - Add van accessible parking stall near leasing office | GC | Year 1 | 6000 | 0 |  |  | 4 |  | LPCA - Add van accessible parking stall near leasing office | [5 empty] | 2026-12-01
66 | 84114.0 | Repair exterior stair treads and stringers | Scrap and paint, secure stair treads | GC | Year 1 | 8500 | 0 |  |  | 4 |  | Scrap and paint, secure stair treads
119 | 83236.0 | CO Detectors | Install CO Detectors | Capex | Year 1 | 12060 | 0 |  |  | N/A |  | Install CO Detectors
67 | 84121.0 | Repair exterior stair railings | Scrap and paint, secure stair railings | GC | Year 1 | 12500 | 0 |  |  | 4 |  | Scrap and paint, secure stair railings
70 | 84102.0 | Expansion joints | Seal expansion joints | GC | Year 1 | 14000 | 0 |  |  | 4 |  | Seal expansion joints
25 | 84115.0 | Sidewalks | LPCA (PR-90) - Potential trip hazards consisting of vertical and horizontal separation and significantly cracked and damaged concrete were present throughout the property. The trip hazards were specifically observed at two locations near Building 1 and at the west pool. LPCA - Additional areas of cracked concrete walkways were present throughout the property. Sectional replacement or grinding is recommended as necessary. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | LPCA (PR-90) - Potential trip hazards consisting of vertical and horizontal separation and significantly cracked and damaged concrete were present throughout the property. The trip hazards were specif | [5 empty] | 2026-03-01
90 | 84102.0 | Repair stucco | Repair Exterior Stucco - Keep existing look of property. | GC | Year 1 | 20000 | 0 |  |  | 4 |  | Repair Exterior Stucco - Keep existing look of property.
144 | 84275.0 | Security/ fire alarm systems | Install controlled access system for common areas | GC | Year 1 | 20000 | 0 |  |  | 4 |  | Install controlled access system for common areas
156 | 84209.0 | Seismic Strapping | Seismic Strapping - LPCA - The water heaters lacked seismic bracing straps. Provision of adequate seismic bracing is recommended. | GC | Year 1 | 20100 | 20100 |  |  | 0 |  | Seismic Strapping - LPCA - The water heaters lacked seismic bracing straps. Provision of adequate seismic bracing is recommended. | [5 empty] | 2026-12-01
118 | 84239.0 | Fire Stops | Install Fire Stops | Capex | Year 1 | 21105 | 16619.8 |  |  | N/A |  | Install Fire Stops
23 | 84201.0 | Stripe parking areas | Stripe Parking Area | GC | Year 1 | 22000 | 0 |  |  | 4 |  | Stripe Parking Area
26 | 84300.0 | Landscape irrigation | Inspect and repair irrigation | Capex | Year 1 | 22500 | 0 |  |  | N/A |  | Inspect and repair irrigation
80 | 84433.0 | Sealants & caulking | Roof Sealants and Caulking | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Roof Sealants and Caulking
127 | 84208.0 | Office Clubhouse | Clubhouse upgrades - Move office to pool clubhouse room. | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | Clubhouse upgrades - Move office to pool clubhouse room.
165 | 84210.0 | Electrical distribution | Inspect and repair lighting controllers on all buildings | GC | Year 1 | 26000 | 0 |  |  | 4 |  | Inspect and repair lighting controllers on all buildings
166 | 84210.0 | Common area light fixtures | Replace pole lights with LED | GC | Year 1 | 28000 | 0 |  |  | 4 |  | Replace pole lights with LED
68 | 84104.0 | Repair balcony framing & decking | SB 721 needed, minor repairs included. Anything more extensive will need a change order. Catwalk railing potentially too short. | GC | Year 1 | 30000 | 0 |  |  | 4 |  | SB 721 needed, minor repairs included. Anything more extensive will need a change order. Catwalk railing potentially too short.
167 | 84210.0 | Replace breezeway lights | Replace doorway sconces | GC | Year 1 | 32100 | 0 |  |  | 4 |  | Replace doorway sconces
79 | 84433.0 | Flashing | Flashing around chimneys to be replaced as needed | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Flashing around chimneys to be replaced as needed
22 | 84204.0 | Pavement | Replace areas of potholes | GC | Year 1 | 36000 | 0 |  |  | 4 |  | Replace areas of potholes
69 | 84121.0 | Repair patio/balcony railings | Scrap and paint, secure | GC | Year 1 | 36000 | 0 |  |  | 4 |  | Scrap and paint, secure
78 | 84202.0 | Gutters & downspouts | Secure and clean gutters | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | Secure and clean gutters
16 | 83307.0 | Landscape Cleanup and Enhancements | Tree trim | Capex | Year 1 | 42500 | 17654 |  |  | N/A |  | Tree trim
40 | 84111.0 | Dumpster enclosures | Replace exisiting dumpster enclosures with new structures throughout property | GC | Year 1 | 45000 | 0 |  |  | 4 |  | Replace exisiting dumpster enclosures with new structures throughout property
95 | 84105.0 | Shutters | Repair/replacement of damaged shutters throughout | GC | Year 1 | 45000 | 0 |  |  | 4 |  | Repair/replacement of damaged shutters throughout
141 | 84260.0 | Mailboxes | Current boxes are damaged | GC | Year 1 | 46500 | 0 |  |  | 4 |  | Current boxes are damaged
17 | 84204.0 | Asphalt Coating | Fill asphalt cracks, seal coat | GC | Year 1 | 47500 | 0 |  |  | 4 |  | Fill asphalt cracks, seal coat
18 | 84095.0 | Resurface swimming pool | Two pools - resurface 2 pools | GC | Year 1 | 50000 | 15000 |  |  | 3 |  | Two pools - resurface 2 pools
19 | 84361.0 | Pool maintenance | Deck cleaning & Equipment repair/replacement | GC | Year 1 | 50000 | 15000 |  |  | 3 |  | Deck cleaning & Equipment repair/replacement
28 | 84205.0 | Fences & gates - site perimeter | Replace fences between units | GC | Year 1 | 75000 | 0 |  |  | 4 |  | Replace fences between units
130 | 84190.0 | Fitness Center Remodel | Convert other clubhouse (high ceiling) into a fitness center | Capex | Year 1 | 75000 | 0 |  |  | N/A |  | Convert other clubhouse (high ceiling) into a fitness center
86 | 84206.0 | Repair / replace wood shingles | Replace any damage faux cedar shake | GC | Year 1 | 85000 | 0 |  |  | 4 |  | Replace any damage faux cedar shake
85 | 84206.0 | Repair / replace cement fiber siding | Replace damaged horizontal siding where needed | GC | Year 1 | 88500 | 0 |  |  | 4 |  | Replace damaged horizontal siding where needed
94 | 84105.0 | Repair / replace wood trim | Replace rotted fascia and trim | GC | Year 1 | 185000 | 0 |  |  | 4 |  | Replace rotted fascia and trim
102 | 84207.0 | Interior Update Placeholder | Contingency for interiors | Capex | Year 1 | 225000 | 0 |  |  | N/A |  | Contingency for interiors
93 | 84101.0 | Exterior building | Paint community LPCA - Select areas of building exteriors were observed to have dryrot damage in locations throughout the subject property. Dryrot damage repair is recommended. Additionally, the paint finish on the apartment buildings was chipping and worn. Repainting is recommended. | GC | Year 1 | 250000 | 0 |  |  | 4 |  | Paint community LPCA - Select areas of building exteriors were observed to have dryrot damage in locations throughout the subject property. Dryrot damage repair is recommended. Additionally, the paint | [5 empty] | 2026-12-01
73 | 84433.0 | Asphalt composite shingle roofing | Half of the roofs have been redone recently. Still need to replace 9 roofs throughout property | GC | Year 1 | 495000 | 495000 |  |  | 0 |  | Half of the roofs have been redone recently. Still need to replace 9 roofs throughout property
PROJECTS subtotal (excl. contingency/CM fee)
171 | 84510.0 | Contingency | Construction Contingency | CON | Contingency | 115768 | 0 |  |  | N/A |  | Construction Contingency
172 | 84505.0 | Construction Management Fee | CM Fee | CMF | CM Fee | 121557 | 23853 |  |  | N/A |  | CM Fee

## Candlewood
Candlewood — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
43 | 51172-00 | Carports / Garages | Significant wood rotting at stand alone carports. Need to replace all rotted wood and fix all damaged stucco on all 3 stand alone carports. Item No. 14: Allowance for carport miscellaneous repairs due to vehicular impact or dry rot damage at fascia board and damaged plywood. Repeat every 5 years. | GC | Year 1 | 340000 | 0 |  |  | 4 |  | Significant wood rotting at stand alone carports. Need to replace all rotted wood and fix all damaged stucco on all 3 stand alone carports. Item No. 14: Allowance for carport miscellaneous repairs due
104 | 51080-00 | Exterior Paint | Item No. 11: Budget for pressure washing, preparation, caulking, stucco wall repairs, and painting of building exteriors on a 7-year cycle to prevent water infiltration and maintain the appearance of the buildings. Repair minor cracks between the patio walls and the building exterior walls. It was reported that the buildings were repainted 5 to 6 years ago. Item No. 12: Using a rust-inhibiting primer, prepare and paint with marine paint all exterior ferrous metal building and site components including handrails and guardrails; and fencing and gates. Preparation work should include rust removal where necessary. Perform on a 7-year cycle. | GC | Year 1 | 283500 | 283500 |  |  | 0 |  | Item No. 11: Budget for pressure washing, preparation, caulking, stucco wall repairs, and painting of building exteriors on a 7-year cycle to prevent water infiltration and maintain the appearance of
16 | 51053-00 | Asphalt Coating | Fill, seal and coat of parking area at back of property. Mix of asphalt and concrete repairs needed (approx 80% asphalt). Item No. 2: The asphalt pavement at the rear of the property was observed to be in fair condition. Cracks in the asphalt paving and cracks in the concrete aprons at the entrance of the parking area along Kinzie Street were noted. An allowance for limited depth repairs, crack seal, seal coat, and restriping of parking spaces and driveways on a 3-5-year cycle is recommended throughout the term to prolong the life of the asphalt surfacing. | GC | Year 1 | 173000 | 0 |  |  | 4 |  | Fill, seal and coat of parking area at back of property. Mix of asphalt and concrete repairs needed (approx 80% asphalt). Item No. 2: The asphalt pavement at the rear of the property was observed to b
97 | 51080-00 | Exterior building repairs | Due to extensive repairs at the 3 stand alone carports need to repaint entire structures to match exisiting color scheme. | GC | Year 1 | 135000 | 0 |  |  | 4 |  | Due to extensive repairs at the 3 stand alone carports need to repaint entire structures to match exisiting color scheme.
141 | 51160-00 | Pool Area Remodel | Building A: replace umbrellas and furniture Building B: repurpose middle space and replace plants. | Capex | Year 1 | 75000 | 0 |  |  | N/A |  | Building A: replace umbrellas and furniture Building B: repurpose middle space and replace plants.
15 | 51043-00 | Landscape Cleanup and Enhancements | Item No. 1: Trim trees along the perimeter throughout the site to prevent the accumulation of debris and tree leaves over the three residential buildings. Numerous palm trees are planted on site and project over the roofs, touching the exterior walls and leaving debris on the roofs, blocking roof drains. Untrimmed trees located all along the perimeter of the site and between the buildings.Tree trimming should occur every year with a higher cost as an immediate need. | Capex | Year 1 | 50000 | 10850 |  |  | N/A |  | Item No. 1: Trim trees along the perimeter throughout the site to prevent the accumulation of debris and tree leaves over the three residential buildings. Numerous palm trees are planted on site and p
30 | 51023-00 | Resurface swimming pool | Item No. 6: Allowance to resurface both pools and one spa, including repairing any cracks around the pool decks and replacing any missing sealants. It is unknown when the pools were resurfaced. | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Item No. 6: Allowance to resurface both pools and one spa, including repairing any cracks around the pool decks and replacing any missing sealants. It is unknown when the pools were resurfaced.
64 | 51062-00 | Roof framing | Replace/repair any wood rotting on carport roof decking on all 3 stand alone carports. | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Replace/repair any wood rotting on carport roof decking on all 3 stand alone carports.
179 | 51141-00 | Common Area Light Fixtures | Change all patio/balcony lights to LED flush mounted lights | GC | Year 1 | 28350 | 28350 |  |  | 0 |  | Change all patio/balcony lights to LED flush mounted lights
44 | 51134-00 | Storm Sewer Piping | 50% of storm water drains on balconies need to be repaired/replaced due to paint/damage. | GC | Year 1 | 25988 | 25988 |  |  | 0 |  | 50% of storm water drains on balconies need to be repaired/replaced due to paint/damage.
82 | 51071-00 | Gutters & downspouts | Replace gutters at the 3 stand alone carports | GC | Year 1 | 22500 | 0 |  |  | 4 |  | Replace gutters at the 3 stand alone carports
128 | 51180-00 | Radon Mitigation | 1.1.5 - Elevated levels of radon were detected in Building 9830 - Unit 123 and Building 9850 - Unit 118. The sponsor has elected to forgot additional testing and mitigate the units. Mitigation is expected to cost $7,000 per unit | Capex | Year 1 | 20000 | 20600 |  |  | N/A |  | 1.1.5 - Elevated levels of radon were detected in Building 9830 - Unit 123 and Building 9850 - Unit 118. The sponsor has elected to forgot additional testing and mitigate the units. Mitigation is expe | [5 empty] | 2026-05-29
21 | 51053-00 | Stripe parking areas | Restripe Parking Area including carports. | GC | Year 1 | 19000 | 0 |  |  | 4 |  | Restripe Parking Area including carports.
178 | 51140-00 | Electrical - Load Centers | Item No. 23: Ensure that all apartment load centers have the proper index identifying circuit number and devices served. | GC | Year 1 | 9450 | 8505 |  |  | 1 |  | Item No. 23: Ensure that all apartment load centers have the proper index identifying circuit number and devices served.
66 | 51062-00 | Roof deck | Roof Deck Repairs | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Roof Deck Repairs
176 | 51140-00 | Electrical distribution systems Electrical Load Tests | Item No. 21: Allowance to provide periodic maintenance of the electrical distribution systems including infrared scans, cleaning of all contacts, and tightening of all connections as well as infrared scans of multimeter assemblies. Item No. 29: Perform the required 5-year load test. Posted placard expired 6/11/2018. | Capex | Year 1 | 13200 | 0 |  |  | N/A |  | Item No. 21: Allowance to provide periodic maintenance of the electrical distribution systems including infrared scans, cleaning of all contacts, and tightening of all connections as well as infrared
27 | 51076-00 | Fences & gates - site perimeter | Item No. 4: Allowance for periodic fencing repairs, including property perimeter wood slat fencing and CMU fencing along the east property line. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Item No. 4: Allowance for periodic fencing repairs, including property perimeter wood slat fencing and CMU fencing along the east property line.
86 | 51062-00 | Roof Maintenance | Item No. 15: Allowance for annual roof maintenance on all roof areas including inspection and repair of flashing, sealants, roof cleaning, minor repair of roof assemblies, as well as gutter and downspout cleaning, repairs, and replacements, throughout the term. The roofs were observed the day after heavy rain and numerous areas of ponding, especially at Building C were noted. | GC | Year 1 | 5000 | 0 |  |  | 4 |  | Item No. 15: Allowance for annual roof maintenance on all roof areas including inspection and repair of flashing, sealants, roof cleaning, minor repair of roof assemblies, as well as gutter and downsp
105 | 51993-01 | Balconies | Item No. 13: Engage a specialty consultant to survey 100% of apartment balconies associated with observed deterioration of balcony drains, poor slope and blocked balcony drains. Most of the balcony drains observed were blocked not allowing proper drainage and most balconies did not slope to drain, creating ponding. Unit C315 had a damaged drain.Signs of ongoing balcony repairs were noted along the Reseda elevation. | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Item No. 13: Engage a specialty consultant to survey 100% of apartment balconies associated with observed deterioration of balcony drains, poor slope and blocked balcony drains. Most of the balcony dr
126 | 52111-00 | Unit deferred maintenance (cont.) - 1 | Item No. 17: Allowance for repairs in bathrooms showing evidence of minor ceiling damage. Seen in Units C311 with tape in bathroom ceiling, Unit C315 bathroom ceiling, Unit C319 wall and ceiling, Unit C201 ceiling, Unit C202 ceiling, and Unit C205 ceiling. Repeat every 5 years based on age. | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Item No. 17: Allowance for repairs in bathrooms showing evidence of minor ceiling damage. Seen in Units C311 with tape in bathroom ceiling, Unit C315 bathroom ceiling, Unit C319 wall and ceiling, Unit
127 | 52111-00 | Unit deferred maintenance (cont.) -2 | Item No. 18: Allowance for remediation of organic growth in isolated areas, especially in bathrooms where exhaust fans are not functioning properly. Seen in Units C315 bathroom ceiling, | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Item No. 18: Allowance for remediation of organic growth in isolated areas, especially in bathrooms where exhaust fans are not functioning properly. Seen in Units C315 bathroom ceiling,
157 | 51164-00 | Elevator Tests | Item No. 28: Perform the annual elevator tests and post the most recent certificates. Cab certificates expired 6/29/2024. | PMC | Year 1 | 4800 | 28842 |  |  | N/A |  | Item No. 28: Perform the annual elevator tests and post the most recent certificates. Cab certificates expired 6/29/2024.
177 | 51140-00 | Meter Banks - Rust and Corrosion | Item No. 22: Remove rust and corrosion from the multi-meter assemblies and paint with a matching rust inhibitive paint. | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | Item No. 22: Remove rust and corrosion from the multi-meter assemblies and paint with a matching rust inhibitive paint.
125 | 52111-00 | Unit deferred maintenance | Item No. 3: Repair cracked concrete at Unit A119 patio. | GC | Year 1 | 2500 | 2500 |  |  | 0 |  | Item No. 3: Repair cracked concrete at Unit A119 patio.
69 | 51072-00 | Repair balcony framing & decking | 3.2.7 - The balcony deck surface at unit A303 was buckled and standing water observed. The deck surface should be repaired and water tight coating reapplied. | GC | Year 1 | 2250 | 2250 |  |  | 0 |  | 3.2.7 - The balcony deck surface at unit A303 was buckled and standing water observed. The deck surface should be repaired and water tight coating reapplied. | [5 empty] | 2026-05-29
70 | 51062-00 | Roof Drainage | 3.2.9 - Areas of roof ponding were noted on all roofs. Although ponding may decrease the useful life of the roof, decking and insulation repairs are not practical or recommended. Cleaning of the roof membrane surface is recommended to prevent deterioration. | GC | Year 1 | 2250 | 2250 |  |  | 0 |  | 3.2.9 - Areas of roof ponding were noted on all roofs. Although ponding may decrease the useful life of the roof, decking and insulation repairs are not practical or recommended. Cleaning of the roof | [5 empty] | 2026-05-29
17 | 51050-00 | Asphalt Pavement | 3.1.6 - Isolated asphalt cracking was observed in the rear drive aisles and areas near the entrance gates. Repair is recommended | GC | Year 1 | 2000 | 0 |  |  | 4 |  | 3.1.6 - Isolated asphalt cracking was observed in the rear drive aisles and areas near the entrance gates. Repair is recommended | [5 empty] | 2026-05-29
PROJECTS subtotal (excl. contingency/CM fee)
182 | 51175-00 | Contingency | Contingency Amount | CON | Contingency | 132579 | 0 | 132579 |  | N/A |  | Contingency Amount
183 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 72918 | 17016 | 72918 |  | N/A |  | CM Fee

## Canyon Villa
Canyon Villa — 2025 acq · GC GL fallback |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
42 | 83000-3400 | Exterior building Paint | Paint Community EPCA - Perform maintenance needs on the exterior elevated elements as recommended in the EEE Report prepared by Partner and dated June 20, 2024. The recommendations include the balconies, landings, stairways, and walkway sections. | GC | Year 1 | 354000 | 45646 |  |  | 4 |  | Paint Community EPCA - Perform maintenance needs on the exterior elevated elements as recommended in the EEE Report prepared by Partner and dated June 20, 2024. The recommendations include the balconi
32 | 83000-7600 | SB721 Repairs | Various SB721 repairs | GC | Year 1 | 100000 | 12894 |  |  | 4 |  | Various SB721 repairs
37 | 83000-6100 | Roof Cleanup and treatment | Roof Cleaning & Moss Treatment | GC | Year 1 | 72000 | 9284 |  |  | 4 |  | Roof Cleaning & Moss Treatment
23 | 80000-6800 | Termite treatment | Includes inspection/treatment of Drywood, Subterranean and Dampwood termites) LPCA - According to provided information, Nixtermite, Inc. has submitted a bid of $54,900.00 to provide a Wood Destroying Organism (WDO) inspection at the subject property and perform any necessary localized treatments as necessary. | GC | Year 1 | 54900 | 7079 |  |  | 4 |  | Includes inspection/treatment of Drywood, Subterranean and Dampwood termites) LPCA - According to provided information, Nixtermite, Inc. has submitted a bid of $54,900.00 to provide a Wood Destroyin | [5 empty] | 2026-09-01
61 | 80000-4800 | Replace transformer | EPCA - Contact the local utility to replace one utility transformer exhibiting significant corrosion. The unit is nearest the clubhouse. Assume 100-kVA. | GC | Year 1 | 50000 | 6447 |  |  | 4 |  | EPCA - Contact the local utility to replace one utility transformer exhibiting significant corrosion. The unit is nearest the clubhouse. Assume 100-kVA.
16 | 83000-2000 | Asphalt Coating | R&R 1500 SF of potholes in concrete pavement LPCA - Cracking in the concrete driving lanes and parking areas was observed throughout the property grounds, most notably adjacent to carport parking spaces 1, 11, 14, 38, 39, 42, 46, and 51, and adjacent to parking garages 15, 36, and 53. Repair of the affected areas is recommended. | GC | Year 1 | 45000 | 5802 |  |  | 4 |  | R&R 1500 SF of potholes in concrete pavement LPCA - Cracking in the concrete driving lanes and parking areas was observed throughout the property grounds, most notably adjacent to carport parking spac | [5 empty] | 2026-09-01
28 | 83000-2400 | Repair balcony framing & decking | Repair damaged patio framing | GC | Year 1 | 38000 | 4900 |  |  | 4 |  | Repair damaged patio framing
62 | 80000-4800 | Install GFCI protection | EPCA - Install GFCI protection on the counter-height kitchen power outlets. Only 1 protected outlet was observed in each kitchen. Assume two per apartment. | Capex | Year 1 | 36600 | 0 |  |  | N/A |  | EPCA - Install GFCI protection on the counter-height kitchen power outlets. Only 1 protected outlet was observed in each kitchen. Assume two per apartment.
35 | 83000-6100 | Modified bitumen membrane roof Repairs | Roof repairs on 35 roofs | GC | Year 1 | 35000 | 4513 |  |  | 4 |  | Roof repairs on 35 roofs
25 | 83000-2800 | Concrete deck / floor fill | Seal cracks in landing | GC | Year 1 | 32000 | 4126 |  |  | 4 |  | Seal cracks in landing
26 | 83000-7100 | Repair exterior stair treads and stringers | Repair stair tread and stringers | GC | Year 1 | 32000 | 4126 |  |  | 4 |  | Repair stair tread and stringers
38 | 800 | Gutters & downspouts | Clean and secure gutters and down spouts | GC | Year 1 | 32000 | 4126 |  |  | 4 |  | Clean and secure gutters and down spouts
60 | 83000-3200 | Common area light fixtures | replace exterior building lights and post lights | GC | Year 1 | 32000 | 4126 |  |  | 4 |  | replace exterior building lights and post lights
19 | 83000-3900 | Fences & gates - site perimeter | Repair Iron fence and paint | GC | Year 1 | 25000 | 3224 |  |  | 4 |  | Repair Iron fence and paint
34 | 83000-6100 | Roofing | Tune up clay tile and repair flashing LPCA - Organic materials were observed on the clay/concrete mission tiles. Cleaning of the clay/concrete mission tiles is recommended | GC | Year 1 | 25000 | 3224 |  |  | 4 |  | Tune up clay tile and repair flashing LPCA - Organic materials were observed on the clay/concrete mission tiles. Cleaning of the clay/concrete mission tiles is recommended | [5 empty] | 2026-09-01
39 | 83000-6100 | Sealants & caulking | Seal & Caulk Roofing Areas | GC | Year 1 | 25000 | 3224 |  |  | 4 |  | Seal & Caulk Roofing Areas
43 | 83000-3700 | Repair / replace wood trim | Replace all rotted fascia throughout property | GC | Year 1 | 25000 | 3224 |  |  | 4 |  | Replace all rotted fascia throughout property
17 | 83000-2000 | Stripe parking areas | Stripe parking lot LPCA - Pavement markings and striping appeared to be in fair condition. Reapplication of pavement markings and striping is recommended upon completion of pavement repairs. | GC | Year 1 | 22000 | 2837 |  |  | 4 |  | Stripe parking lot LPCA - Pavement markings and striping appeared to be in fair condition. Reapplication of pavement markings and striping is recommended upon completion of pavement repairs. | [5 empty] | 2026-09-01
49 | 80000-1700 | Fire/Life Safety System - Smoke/CO alarm | EPCA - Budget to replace the existing combination smoke/CO alarms based on age and useful life. The NFPA requires that smoke alarms not remain in service longer than 10 years from the date of manufacture. There are approximately 518 smoke alarms at the property based on the unit mix. | Capex | Year 1 | 20720 | 15725 |  |  | N/A |  | EPCA - Budget to replace the existing combination smoke/CO alarms based on age and useful life. The NFPA requires that smoke alarms not remain in service longer than 10 years from the date of manufact
48 | 80000-1700 | Security/ fire alarm systems | LPCA (PR-90) - An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recertification of the fire alarm system is recommended. EPCA - There are three fire alarm systems installed in the buildings equipped with elevators. One of the fire alarm control panels is almost 30 years old and in need of replacement. The other panels are expected to require replacement at the end of the term. | GC | Year 1 | 20000 | 2579 |  |  | 4 |  | LPCA (PR-90) - An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recertification of the fire alarm system is recommended. EPCA - There are three fir
52 | 80000-5200 | Galvanized Pipe Replacement | EPCA - Allowance for periodic domestic and sanitary piping repairs or replacements based on age and EUL (year 1 upfront, BTL thereafter) | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | EPCA - Allowance for periodic domestic and sanitary piping repairs or replacements based on age and EUL (year 1 upfront, BTL thereafter)
59 | 80000-4800 | Electrical distribution | Repair electric to pole lights and photo cells | GC | Year 1 | 20000 | 2579 |  |  | 4 |  | Repair electric to pole lights and photo cells
63 | 80000-4800 | Preventative Maintenance - Breaker Panels | EPCA - Perform preventative maintenance on the electrical systems throughout the site, including opening breaker panels, cleaning and checking connections, and correcting any deficiencies identified. | Capex | Year 1 | 18300 | 1227 |  |  | N/A |  | EPCA - Perform preventative maintenance on the electrical systems throughout the site, including opening breaker panels, cleaning and checking connections, and correcting any deficiencies identified.
45 | 80000-6400 | Fire Protection | Fire Stops | Capex | Year 1 | 17934 | 509 |  |  | N/A |  | Fire Stops
27 | 83000-7100 | Repair exterior stair railings | repair and secure stair railings | GC | Year 1 | 16000 | 2063 |  |  | 4 |  | repair and secure stair railings
29 | 83000-2400 | Repair patio/balcony railings | Secure all balcony railings LPCA - Paint along the balcony railing was observed to be chipping and peeling. Additionally, deteriorating elastomeric coating was observed adjacent to Unit 357. Repair of the affected areas is recommended | GC | Year 1 | 16000 | 2063 |  |  | 4 |  | Secure all balcony railings LPCA - Paint along the balcony railing was observed to be chipping and peeling. Additionally, deteriorating elastomeric coating was observed adjacent to Unit 357. Repair of | [5 empty] | 2026-09-01
36 | 83000-6100 | Flashing | Replace damaged drip edge on balconies. | GC | Year 1 | 16000 | 2063 |  |  | 4 |  | Replace damaged drip edge on balconies.
18 | 83000-2800 | Sidewalks | Repair Trip Hazards LPCA - Cracking in the concrete walkways was observed adjacent to Units 121, 140, 167, and 288. Repair of the affected areas is recommended. | GC | Year 1 | 15000 | 1934 |  |  | 4 |  | Repair Trip Hazards LPCA - Cracking in the concrete walkways was observed adjacent to Units 121, 140, 167, and 288. Repair of the affected areas is recommended. | [5 empty] | 2026-09-01
21 | 83000-2600 | Carports / Garages | Repair carports | GC | Year 1 | 15000 | 1934 |  |  | 4 |  | Repair carports
41 | 83000-3700 | Repair stucco | Repairs to damaged stucco | GC | Year 1 | 14000 | 1805 |  |  | 4 |  | Repairs to damaged stucco
20 | 83000-5300 | Fences & gates - swimming pool | Repair and paint | GC | Year 1 | 12000 | 1547 |  |  | 4 |  | Repair and paint
30 | 83000-7500 | Retaining Wall repairs | ESCA - Repair chips and broken sections of concrete on top of the concrete retaining wall. Repair to consist of placing concrete epoxy paste at chipped section or forming and placing new concrete corners as needed. Add a cap flashing on top of the concrete retaining wall. | GC | Year 1 | 4000 | 516 |  |  | 4 |  | ESCA - Repair chips and broken sections of concrete on top of the concrete retaining wall. Repair to consist of placing concrete epoxy paste at chipped section or forming and placing new concrete corn
51 | 80000-5100 | Back-flow preventer | EPCA - The three irrigation backflow preventer assemblies were last inspected in February 2024 and are now past due for reinspection. | PMC | Year 1 | 1500 | 0 |  |  | N/A |  | EPCA - The three irrigation backflow preventer assemblies were last inspected in February 2024 and are now past due for reinspection.
31 | 83000-7500 | Retaining Wall repairs | ESCA - Implement a protocol for regular maintenance and cleaning of the drainage system including removal of plants | GC | Year 1 | 400 | 52 |  |  | 4 |  | ESCA - Implement a protocol for regular maintenance and cleaning of the drainage system including removal of plants
47 | 83000-4300 | Signage - Entry Monument | EPCA - Provide signage directing individuals from the accessible parking spaces to the leasing office entrance doors. | PMC | Year 1 | 300 | 0 |  |  | N/A |  | EPCA - Provide signage directing individuals from the accessible parking spaces to the leasing office entrance doors.
PROJECTS subtotal (excl. contingency/CM fee)
66 | 80000-7200 | Construction Management Fee | CM Fees | CMF | CM Fee | 64822 | 0 |  |  | N/A |  | CM Fees
65 | 80000-7700 | Contingency | Contingency Amount | CON | Contingency | 33781 | 0 |  |  | N/A |  | Contingency Amount

## Chaparral
Chaparral — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
19 | 51050-00 | Asphalt pavement | Mill and overlay asphalt throughout entire property Includes Equity PCA Item 3.2.2- Asphalt Pavment; Mill and overlay approximately 25% of the damaged pavement in year 1 | GC | Year 1 | 740000 | 740000 |  |  | 0 |  | Mill and overlay asphalt throughout entire property Includes Equity PCA Item 3.2.2- Asphalt Pavment; Mill and overlay approximately 25% of the damaged pavement in year 1 | [5 empty] | 2026-02-28
21 | 51053-00 | Asphalt Coating | Double seal coat entire pavement throughout property | GC | Year 1 | 525000 | 525000 |  |  | 0 |  | Double seal coat entire pavement throughout property
97 | 51150-00 | Interior Update Placeholder | Placeholder Expense | Capex | Year 1 | 296000 | 1780 |  |  | N/A |  | Placeholder Expense
157 | 51158-00 | Natural Gas Seismic Shutoff Devices | Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices to prevent dangerous gas leaks in the event of a line break during a significant seismic event. Installation of automatic seismic shut-off devices at the services is recommended | GC | Year 1 | 148000 | 148000 |  |  | 0 |  | Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices to prevent dangerous gas leaks in the event of a line break during a significant seismic event.
24 | 51023-00 | Resurface swimming pool | Resurface both pools, not including spas (completed recently) | GC | Year 1 | 67500 | 67500 |  |  | 0 |  | Resurface both pools, not including spas (completed recently)
161 | 51141-00 | Common area light fixtures | Replace all pole lights with LED and change tennis court lights with LED | GC | Year 1 | 55750 | 55750 |  |  | 0 |  | Replace all pole lights with LED and change tennis court lights with LED
27 | 51027-00 | Sport Court | Resurface and stripe for tennis & pickleball. Fencing and lighting repairs. Includes Equity PCA Item 3.2.9- Tennis Courts; Repair cracks and deteriorated topcoat | GC | Year 1 | 55000 | 55000 |  |  | 0 |  | Resurface and stripe for tennis & pickleball. Fencing and lighting repairs. Includes Equity PCA Item 3.2.9- Tennis Courts; Repair cracks and deteriorated topcoat | [5 empty] | 2026-02-28
41 | 51020-00 | Playground equipment | Playground Addition | Capex | Year 1 | 40000 | 5950 |  |  | N/A |  | Playground Addition
163 | 51993-00 | Fire Alarm Panels | Equity PCA Item- 5.5.2- Fire alarm control panels (FACP) at Buildings L and N were observed to with active trouble alarms. Property management indicated the panels were faulty and scheduled to be replaced in early December 2024. Replacement of the panels is recommended | Capex | Year 1 | 40000 | 31766 |  |  | N/A |  | Equity PCA Item- 5.5.2- Fire alarm control panels (FACP) at Buildings L and N were observed to with active trouble alarms. Property management indicated the panels were faulty and scheduled to be repl
26 | 51076-00 | Fences & gates - swimming pool | Scrap, prime and paint both pool fences. Add metal fence topper to extend height on gates and improve gate security. Property is having trouble with unauthorized people entering pools. | GC | Year 1 | 37600 | 37600 |  |  | 0 |  | Scrap, prime and paint both pool fences. Add metal fence topper to extend height on gates and improve gate security. Property is having trouble with unauthorized people entering pools.
20 | 51053-00 | Stripe parking areas | Stripe throughout property | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Stripe throughout property
137 | 51168-00 | Package Lockers (Defer Costs) | Accept small packages at office, otherwise deliver to door. Look at adding package lockers in enclosed room by 2nd pool. Budget 1 locker per 4-5 units @$400/locker ($29,600) | Capex | Year 1 | 29600 | 0 |  |  | N/A |  | Accept small packages at office, otherwise deliver to door. Look at adding package lockers in enclosed room by 2nd pool. Budget 1 locker per 4-5 units @$400/locker ($29,600)
160 | 51140-00 | Electrical distribution | Electrical Panels | GC | Year 1 | 27000 | 27000 |  |  | 0 |  | Electrical Panels
22 | 51091-00 | ADA parking & curb cuts | Restripe all handicap parking spots | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Restripe all handicap parking spots
120 | 51033-00 | Signage - Building identification | Unit number signage needed at doors | Capex | Year 1 | 22200 | 0 |  |  | N/A |  | Unit number signage needed at doors
18 | 51043-00 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | Capex | Year 1 | 20000 | 7570 |  |  | N/A |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
162 | 51141-00 | Replace breezeway lights | Replace all breezeway lights in stairwells with LED | GC | Year 1 | 16500 | 16500 |  |  | 0 |  | Replace all breezeway lights in stairwells with LED
42 | 51160-04 | Picnic areas | Tables & Seating | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | Tables & Seating
129 | 51160-04 | Picnic/Grill Area Remodel | Remove and install new stand alone grils throughout property | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | Remove and install new stand alone grils throughout property
144 | 51994-00 | Golf Cart | Have leasing cart but could use new one | PMC | Year 1 | 8000 | 16562 |  |  | N/A |  | Have leasing cart but could use new one
25 | 51021-00 | Replace swimming pool coping | Deck-o-seal coping around both pools | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Deck-o-seal coping around both pools
125 | 51160-00 | Fitness Center Remodel (Defer Costs) | Paint & Reupholster ($5,000) | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Paint & Reupholster ($5,000)
140 | 51993-00 | Security Camera System | Have 23 cameras, need 2-4 more cameras to cover side views | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Have 23 cameras, need 2-4 more cameras to cover side views
23 | 51091-00 | Sidewalks | Replace cracked sidewalks throughout property | GC | Year 1 | 4500 | 4500 |  |  | 0 |  | Replace cracked sidewalks throughout property
156 | 51122-00 | HVAC Exterior Condensing Unit Refrigerant Line Insul | Equity PCA Item- 5.1- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the units. This condition reduces unit efficiency and decrease the useful life of the equipment. Repair of deteriorated insulation at the refrigeration linesets is recommended | GC | Year 1 | 3700 | 3700 |  |  | 0 |  | Equity PCA Item- 5.1- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the units. This condition reduces unit efficiency and decrease the useful life of the e
38 | 51076-00 | Fences & gates - swimming pool | Reinforce or increase size of pool gate gate posts at both pools | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Reinforce or increase size of pool gate gate posts at both pools
31 | 51085-00 | Retaining walls | Equity PCA Item 3.2.5- Install weepholes on southern perimeter concrete masonry retaining walls | GC | Year 1 | 2400 | 2400 |  |  | 0 |  | Equity PCA Item 3.2.5- Install weepholes on southern perimeter concrete masonry retaining walls | [5 empty] | 2026-02-28
146 | 51158-00 | Domestic Water Service Main | Equity PCA Item- 5.1- The east domestic water service backflow prevention device was observed with an active drip leak. Repair of the backflow prevention device is recommended | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | Equity PCA Item- 5.1- The east domestic water service backflow prevention device was observed with an active drip leak. Repair of the backflow prevention device is recommended | [5 empty] | 2026-02-28
34 | 51021-00 | West Poolhouse | Equity PCA Item 3.2.9- Eliminate step between pool surround and poolhouse interior to provide wheelchair accessible route | GC | Year 1 | 1250 | 1250 |  |  | 0 |  | Equity PCA Item 3.2.9- Eliminate step between pool surround and poolhouse interior to provide wheelchair accessible route
154 | 51120-00 | HVAC inspection and maintenance | Add HVAC pads to 3 units at the leasing office. Currently sitting on ground with debris around. | GC | Year 1 | 750 | 750 |  |  | 0 |  | Add HVAC pads to 3 units at the leasing office. Currently sitting on ground with debris around.
147 | 51158-00 | Domestic Water Hose Bibs | Equity PCA Item- 5.1- Hose bibs were observed with active drip leaks on the exterior risers of apartment buildings E and K. Repair of the leaking hose bibs is recommended | GC | Year 1 | 500 | 500 |  |  | 0 |  | Equity PCA Item- 5.1- Hose bibs were observed with active drip leaks on the exterior risers of apartment buildings E and K. Repair of the leaking hose bibs is recommended | [5 empty] | 2026-02-28
36 | 51026-00 | Pool Equipment | Includes Equity PCA Item 3.2.9- Repair active leaks observed at East and West pool heater PVC distribution piping | GC | Year 1 | 300 | 300 |  |  | 0 |  | Includes Equity PCA Item 3.2.9- Repair active leaks observed at East and West pool heater PVC distribution piping | [5 empty] | 2026-02-28
45 | 51158-00 | ADA Accessibility | Equity PCA Item- 7.1- Provide compliant scald-protection underneath leasing office men's restroom sink | GC | Year 1 | 200 | 200 |  |  | 0 |  | Equity PCA Item- 7.1- Provide compliant scald-protection underneath leasing office men's restroom sink
148 | 51158-00 | Water Heater T&P Valve Discharge | Equity PCA Item- 5.1- The water heater at unit A9 was observed lacking piping from the T&P valve to the building exterior. Installation of discharge piping at this water heater is recommended | GC | Year 1 | 200 | 200 |  |  | 0 |  | Equity PCA Item- 5.1- The water heater at unit A9 was observed lacking piping from the T&P valve to the building exterior. Installation of discharge piping at this water heater is recommended | [5 empty] | 2026-02-28
PROJECTS subtotal (excl. contingency/CM fee)
168 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 116447 | 0 | 116447 |  | N/A |  | CM Fee
167 | 51175-00 | Contingency | Contingency Amount | CON | Contingency | 87488 | 85765 | 87488 |  | N/A |  | Contingency Amount

## Crestmark
Crestmark — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
90 | 84101 | Paint/finish | Repaint full site | Capex | Year 1 | 334000 | 90000 |  |  | N/A |  | Repaint full site
85 | 84113 | Siding- Water Intrusion | Address water intrusion near bay windows - 32 units | GC | Year 1 | 160000 | 80000 |  |  | 3 |  | Address water intrusion near bay windows - 32 units
16 | 84204 | Asphalt Coating | Seal Coat and Crack Fill | Capex | Year 1 | 144000 | 6391 |  |  | N/A |  | Seal Coat and Crack Fill
88 | 84105 | Repair / replace vinyl siding | Repair Vinyl siding / trim / flashing | Capex | Year 1 | 85000 | 0 |  |  | N/A |  | Repair Vinyl siding / trim / flashing
95 | 84105 | Repair / replace wood trim | Replace rotten wood throughout | Capex | Year 1 | 83500 | 0 |  |  | N/A |  | Replace rotten wood throughout
17 | 84095 | Resurface swimming pool | Resurface both pools | GC | Year 1 | 79000 | 79000 |  |  | 0 |  | Resurface both pools
29 | 84303 | Landscaping | Curb Appeal | Capex | Year 1 | 75000 | 88873 |  |  | N/A |  | Curb Appeal
136 | 84390 | Sports Courts | Convert tennis court to pickle ball court | GC | Year 1 | 75000 | 22500 |  |  | 3 |  | Convert tennis court to pickle ball court
141 | 84005 | Mailboxes | New Mailboxes | Capex | Year 1 | 65000 | 5191 |  |  | N/A |  | New Mailboxes
132 | 84360 | Pool Area Furniture | Split between the two pools | Capex | Year 1 | 60000 | 49000 |  |  | N/A |  | Split between the two pools
134 | 84203 | Picnic/Grill Area Remodel | Pool 1: $25K & Pool 2: $15K | Capex | Year 1 | 40000 | 55778 |  |  | N/A |  | Pool 1: $25K & Pool 2: $15K
119 | 84239 | Fire Stops | Fire stops | Capex | Year 1 | 36740 | 15411 |  |  | N/A |  | Fire stops
74 | 84433 | Asphalt composite shingle roofing | Standard roof tune up on ridge, vault and pipe jacks | GC | Year 1 | 32000 | 9600 |  |  | 3 |  | Standard roof tune up on ridge, vault and pipe jacks | [5 empty] | 2026-10-09
18 | 84361 | Replace swimming pool deck | Level pavers and presure wash | GC | Year 1 | 31000 | 31000 |  |  | 0 |  | Level pavers and presure wash
42 | 84195 | Playground | Replace/repair playground equipment next to blacktop courts | Capex | Year 1 | 30000 | 2300 |  |  | N/A |  | Replace/repair playground equipment next to blacktop courts
69 | 84104 | Repair balcony framing & decking | Repair 3 landing with structural issues | GC | Year 1 | 30000 | 15000 |  |  | 3 |  | Repair 3 landing with structural issues
127 | 84116 | Clubhouse | Update color scheme and game room | Capex | Year 1 | 30000 | 3425 |  |  | N/A |  | Update color scheme and game room
149 | 83375 | Golf Cart | Maintenace carts; property has 2 maintenance carts & 1 6-seat leasing | Capex | Year 1 | 30000 | 12840 |  |  | N/A |  | Maintenace carts; property has 2 maintenance carts & 1 6-seat leasing
21 | 84201 | Stripe parking areas | Restripe of parking lot | Capex | Year 1 | 28000 | 0 |  |  | N/A |  | Restripe of parking lot
20 | 84219 | Carports / Garages | Repairs to garage door - The garage door at 14C was observed damaged and should be repaired or replaced at this time. | Capex | Year 1 | 26000 | 19190 |  |  | N/A |  | Repairs to garage door - The garage door at 14C was observed damaged and should be repaired or replaced at this time. | [5 empty] | 2026-04-09
15 | 84201 | Pavement | Repair potholes | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | Repair potholes
37 | 84361 | Pool Area | Pool bathroom upgrades - 1st Call to verify scope | Capex | Year 1 | 25000 | 39730 |  |  | N/A |  | Pool bathroom upgrades - 1st Call to verify scope
103 | 83236 | Install CO Detectors | CO detectors were not observed in the units. The fireplaces are reportedly gas-fired units and require a CO detector. Install CO detectors in all units. | Capex | Year 1 | 20040 | 35518 |  |  | N/A |  | CO detectors were not observed in the units. The fireplaces are reportedly gas-fired units and require a CO detector. Install CO detectors in all units. | [5 empty] | 2026-01-09
120 | 84304 | Unit deferred maintenance | Repair mechanical closet subfloors | GC | Year 1 | 20000 | 6000 |  |  | 3 |  | Repair mechanical closet subfloors
130 | 84190 | Fitness Center: New Equipment | Supplement existing equipment & redo bathrooms | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Supplement existing equipment & redo bathrooms
167 | 84210 | Replace breezeway lights | Inspect and replace emergency lighting | GC | Year 1 | 19000 | 19000 |  |  | 0 |  | Inspect and replace emergency lighting
19 | 84361 | Fences & gates - swimming pool | Repair fence and gates | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Repair fence and gates
79 | 84202 | Gutters & downspouts | Clean and repitch gutters throughout property | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | Clean and repitch gutters throughout property
108 | 84106 | Clean Drier vents | clean dryer vents and replace damaged covers | GC | Year 1 | 16700 | 16700 |  |  | 0 |  | clean dryer vents and replace damaged covers
53 | 84102 | Concrete deck / floor fill | Rout and seal landings | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Rout and seal landings
161 | 84217 | Replace AC condenser | Add insulation to Condensing unit lines | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Add insulation to Condensing unit lines
112 | 83330 | Install GCI Outlets | Non-GFCI outlets were observed in the pool restrooms and some secondary bathrooms of the apartment units, including 8-813,9-931, 10-1022, 16-1603, and 14-1425. GFCI outlets were present in the primary bathrooms; however, property personnel did not report whether the outlets in the secondary bathrooms were on the same circuit as the GFCI outlets in the primary bathrooms. | Capex | Year 1 | 10020 | 13300 |  |  | N/A |  | Non-GFCI outlets were observed in the pool restrooms and some secondary bathrooms of the apartment units, including 8-813,9-931, 10-1022, 16-1603, and 14-1425. GFCI outlets were present in the primary | [5 empty] | 2026-01-09
30 | 84206 | Pressure wash Breezeways | Pressure Washing - Breezeways | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Pressure Washing - Breezeways
123 | 84290 | Signage - Entry Monument | Noted during concept walk | Capex | Year 1 | 10000 | 2061 |  |  | N/A |  | Noted during concept walk
28 | 84205 | Fences & gates - site perimeter | The motor for automated gates at Crestmark Drive were reported to be inoperable. Repairs are recommended at this time. | PMC | Year 1 | 7000 | 1823 |  |  | N/A |  | The motor for automated gates at Crestmark Drive were reported to be inoperable. Repairs are recommended at this time. | [5 empty] | 2026-04-09
68 | 84121 | Repair exterior stair railings | Secure railings | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | Secure railings
70 | 84121 | Repair patio/balcony railings | Secure railings | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | Secure railings
24 | 84115 | Sidewalks | PNA - Sidewalk Cracks LPCA - Sidewalks were observed to be in good to fair condition with cracks noted in isolated areas including at building 1 breezeway, 4 and the mail center. Uneven edges are also present at multiple walkways including near buildings 5, 9, and 12. Repairs are recommended at this time to eliminate any potential trip hazard. | PMC | Year 1 | 5000 | 1650 |  |  | N/A |  | PNA - Sidewalk Cracks LPCA - Sidewalks were observed to be in good to fair condition with cracks noted in isolated areas including at building 1 breezeway, 4 and the mail center. Uneven edges are als | [5 empty] | 2026-01-09
27 | 84111 | Fences & gates - compactor | The gates on the trash compactor enclosures are either damaged or missing. Repairs are recommended at this time. | PMC | Year 1 | 5000 | 1302 |  |  | N/A |  | The gates on the trash compactor enclosures are either damaged or missing. Repairs are recommended at this time. | [5 empty] | 2026-04-09
124 | 84103 | Signage - Site | Added based on Kevin DD email feedback | PMC | Year 1 | 5000 | 2062 |  |  | N/A |  | Added based on Kevin DD email feedback
25 | 84300 | Landscape irrigation | A leak from the irrigation system was observed at the site stairs between building 5 and the leasing office/clubhouse building. | PMC | Year 1 | 1500 | 877 |  |  | N/A |  | A leak from the irrigation system was observed at the site stairs between building 5 and the leasing office/clubhouse building. | [5 empty] | 2026-04-09
87 | 84105 | Flashing/Siding | A section of metal flashing is missing on the west side of the clock tower. Repairs are recommended. | PMC | Year 1 | 700 | 0 |  |  | N/A |  | A section of metal flashing is missing on the west side of the clock tower. Repairs are recommended. | [5 empty] | 2026-04-09
PROJECTS subtotal (excl. contingency/CM fee)
172 | 84505 | Construction Management Fee | CM Fees | CMF | CM Fee | 92148 | 0 | 92148 |  | N/A |  | CM Fees
171 | 84510 | Contingency | Contingency Amount | CON | Contingency | 87760 | 0 | 87760 |  | N/A |  | Contingency Amount

## Cypress Bend
Cypress Bend — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
80 | 84101 | Exterior building | PNA - Exterior painting. PCA 4.3.1- Exterior cleaning, painting, sealing | GC | Year 1 | 195000 | 167100 |  |  | 2 |  | PNA - Exterior painting. PCA 4.3.1- Exterior cleaning, painting, sealing
20 | 84205 | Fences & gates - site perimeter | PNA - Repair perimater fencing | GC | Year 1 | 43000 | 43000 |  |  | 0 |  | PNA - Repair perimater fencing
55 | 84121 | Repair exterior stair railings | PNA - Replace damaged railing on staircases. PCA 4.5 - Rust and corrosion was observed on the metal stringers, handrails, and guardrails on the steps at Buildings 11, 12, 10, 9, 7, 5, and 2. In addition, the paint was observed to be chipping of the metal components of the staircases throughout the property. Repair/replacement of the damaged stairs followed by painting of the metal components is recommended. | GC | Year 1 | 39000 | 39000 |  |  | 0 |  | PNA - Replace damaged railing on staircases. PCA 4.5 - Rust and corrosion was observed on the metal stringers, handrails, and guardrails on the steps at Buildings 11, 12, 10, 9, 7, 5, and 2. In addi
19 | 84517 | Erosion control | PNA - Fill in erosion areas around buildings. | GC | Year 1 | 29000 | 29000 |  |  | 0 |  | PNA - Fill in erosion areas around buildings.
112 | 84239 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | Capex | Year 1 | 22440 | 22848 |  |  | N/A |  | LowPro (Pair covers 4 burner range)- For range top microwaves
17 | 84204 | Pavement | PNA - Repair Potholes PCA 3.2.2 - Areas of linear cracking and isolated spalling around linear cracks was observed at the concrete pavement between Buildings 9 and 10, in the north drive aisle, west and north adjacent to Building 6, east adjacent to Building 5, in the southeast drive aisle, and adjacent to the leasing office. Crack routing / sealing of the noted areas is recommended. | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | PNA - Repair Potholes PCA 3.2.2 - Areas of linear cracking and isolated spalling around linear cracks was observed at the concrete pavement between Buildings 9 and 10, in the north drive aisle, west
113 | 84304 | Unit deferred maintenance | Major Repairs Floors 18 Bedrooms 13 Living Rooms 3 Kitchens 2 Kitchen Countertop Resurface 2 Interior Door Replacement Estimated Total Repair Cost: $20,191 | Capex | Year 1 | 21000 | 7527 |  |  | N/A |  | Major Repairs Floors 18 Bedrooms 13 Living Rooms 3 Kitchens 2 Kitchen Countertop Resurface 2 Interior Door Replacement Estimated Total Repair Cost: $20,191
155 | 84220 | AC condenser | PNA - Reposistion A/C condensers to achive 12" between units | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | PNA - Reposistion A/C condensers to achive 12" between units
133 | 84280 | Unit Model Update | New furniture in model unit | Capex | Year 1 | 18000 | 0 |  |  | N/A |  | New furniture in model unit
21 | 84111 | Dumpster enclosures | PNA - Repair dumpster enclosures PCA 3.2.7 - Areas of damaged wood fencing was observed east adjacent to Building 12, north adjacent to Building 9, and south adjacent to Building 11. Additionally, missing or damaged slats were noted at refuse enclosures. Repair of the noted areas is recommended at this time. Repair dumpster enclosures. | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | PNA - Repair dumpster enclosures PCA 3.2.7 - Areas of damaged wood fencing was observed east adjacent to Building 12, north adjacent to Building 9, and south adjacent to Building 11. Additionally, mi
159 | 84217 | HVAC Preventative Maintenance | PCA - 5.2 Supply and return air vents were observed with buildup of debris and need cleaning in buildings 10 and 12 due to the exterior algae and mildew growth. | Capex | Year 1 | 15600 | 14000 |  |  | N/A |  | PCA - 5.2 Supply and return air vents were observed with buildup of debris and need cleaning in buildings 10 and 12 due to the exterior algae and mildew growth.
16 | 84303 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
22 | 84201 | Stripe parking areas | Stripe Parking | GC | Year 1 | 15000 | 4500 |  |  | 3 |  | Stripe Parking
54 | 84110 | Concrete deck / floor fill | Grind and seal cracks in light weight concrete landings | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Grind and seal cracks in light weight concrete landings
82 | 84106 | Drier vents | PNA - Clean all dryer vents. PCA 5.2 Some of the dryer vents appeared to be damaged and full of debris. Cracked or vents that are missing louvres may allow pests and debris to enter the ventilation system. Numerous vents and related ducts were filled with lint and debris. This can cause the dryers to overheat and ignite the lint causing a fire hazard. Repair and cleaning of the vents is recommended. | GC | Year 1 | 14400 | 14400 |  |  | 0 |  | PNA - Clean all dryer vents. PCA 5.2 Some of the dryer vents appeared to be damaged and full of debris. Cracked or vents that are missing louvres may allow pests and debris to enter the ventilation sy
18 | 84115 | Sidewalks | PNA - Remove and replace areas of trip hazards. PCA 3.2.3 -Areas of linear cracking was observed in the concrete walkways on the south elevation of Building 11, east adjacent to Building 10 and 12, east and southeast adjacent to Building 9, east adjacent to Buildings 7 and 9, and northwest adjacent to Building 6. In addition, a trip hazard comprised of a heaved concrete walkway section was observed north adjacent to Building 10. Crack sealing of the noted area and repair/grinding of the noted heaved concrete section is recommended. Remove and replace areas of trip hazards | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | PNA - Remove and replace areas of trip hazards. PCA 3.2.3 -Areas of linear cracking was observed in the concrete walkways on the south elevation of Building 11, east adjacent to Building 10 and 12, e
67 | 84433 | Asphalt composite shingle roofing | PNA - Roof tune up. PCA 4.4.1 - Unit 606 was observed to have water staining on the ceiling indicative of a roof leak. Partner recommends retaining a licensed roofing contractor to locate to source of the water infiltration and perform necessary repairs (yr1). Roof replacement - asphalt shingles | GC | Year 1 | 13000 | 13000 |  |  | 0 |  | PNA - Roof tune up. PCA 4.4.1 - Unit 606 was observed to have water staining on the ceiling indicative of a roof leak. Partner recommends retaining a licensed roofing contractor to locate to source o
131 | 84195 | Playground | PCA 3.2.9 - Partner observed that the ground cover beneath the play equipment consisted of grass. According to the Consumer Product Safety Commission (CPSC), grass is considered an inappropriate surfacing type for playgrounds. Grass does not provide as much impact absorption compared to other surfaces. As a safety precaution, Partner recommends removal and replacement with a CPSC approved uncompressed ground cover. | Capex | Year 1 | 11250 | 12048 |  |  | N/A |  | PCA 3.2.9 - Partner observed that the ground cover beneath the play equipment consisted of grass. According to the Consumer Product Safety Commission (CPSC), grass is considered an inappropriate surfa
116 | 84103 | Signage | Budget for wall signage, current is dated. | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | Budget for wall signage, current is dated.
143 | 83440 | Tools & Equipment | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools | Capex | Year 1 | 10000 | 866 |  |  | N/A |  | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools
81 | 84105 | Repair / replace wood trim | PNA - Replace damaged trim | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | PNA - Replace damaged trim
144 | 83375 | Golf Cart | Don't have any carts, nowhere to park them. Could budget for one | PMC | Year 1 | 8000 | 0 |  |  | N/A |  | Don't have any carts, nowhere to park them. Could budget for one
68 | 84202 | Gutters & downspouts | PNA - Clean, repitch, and secure gutters. PCA 4.4.2 - Building 1 was observed to have a missing gutter system on the south elevation. Replacement of the missing gutter system is recommended to maintain proper roof drainage. | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | PNA - Clean, repitch, and secure gutters. PCA 4.4.2 - Building 1 was observed to have a missing gutter system on the south elevation. Replacement of the missing gutter system is recommended to mainta
78 | 84206 | Repair / replace cement fiber siding | PNA - Siding repairs. PCA 4.3.1 - Damaged fiber cement lap board siding was observed on the east elevation of Building 12 and 9. Wood trim located adjacent to the fire riser rooms on Buildings 5, and 9, the northeast corner of Building 9, and adjacent to Unit 601 was observed to be damaged. In addition, areas of damaged fascia was located at the soffit areas was observed on the west elevation of Buildings 9, 8, and 7, and on the east elevation of Building 5. Repair / replacement of the damaged exterior components is warranted | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | PNA - Siding repairs. PCA 4.3.1 - Damaged fiber cement lap board siding was observed on the east elevation of Building 12 and 9. Wood trim located adjacent to the fire riser rooms on Buildings 5, an
110 | 82206 | Garabage Disposals | Interior Replacements | PMC | Project | 7500 | 0 |  |  | N/A |  | Interior Replacements
70 | 84433 | Sealants & caulking | Roof Sealants | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Roof Sealants
79 | 84120 | Breezeways | PNA - Repair soffits | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | PNA - Repair soffits
69 | 84433 | Flashing | Repair damaged flashing | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Repair damaged flashing
122 | 84306 | Clubhouse / Office Furniture | No clubhouse, allowance for office furniture | PMC | Project | 5000 | 0 |  |  | N/A |  | No clubhouse, allowance for office furniture
123 | 82140 | Computers | Budget for 2 replacement | PMC | Project | 4000 | 9877 |  |  | N/A |  | Budget for 2 replacement
121 | 84208 | Clubhouse / Office Remodel | PCA 7.1 - Installation of grab bars adjacent to the commode in the leasing office | PMC | Project | 500 | 0 |  |  | N/A |  | PCA 7.1 - Installation of grab bars adjacent to the commode in the leasing office
117 | 84103 | Signage - Site | PCA 7.1 - Installation of ADA vertical identification parking signage | PMC | Project | 450 | 0 |  |  | N/A |  | PCA 7.1 - Installation of ADA vertical identification parking signage
24 | 84221 | ADA parking & curb cuts | PCA 7.1 - Installation of an access aisle adjacent to the accessible parking stall north adjacent to Building 10 | GC | Year 1 | 250 | 250 |  |  | 0 |  | PCA 7.1 - Installation of an access aisle adjacent to the accessible parking stall north adjacent to Building 10
PROJECTS subtotal (excl. contingency/CM fee)
169 | 84510 | Contingency | Contingency Amount | CON | Contingency | 77339 | 0 | 77339 |  | N/A |  | Contingency Amount
170 | 84505 | Construction Management Fee | CM Fees | CMF | CM Fee | 42724 | 14348 | 42724 |  | N/A |  | CM Fees

## Cypress Bend Village
Cypress Bend Village — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
69 | 84101 | Exterior building | PNA - Repaint community PCA 4.3.1 - Areas of damaged siding were observed on the east and south elevations of Building 3, the north elevation of Building 3, a soffit area on the west elevation of Building 8, adjacent to the fire riser closet at Building 13, and the northeast corner and south elevation of Building 9. Repair/replacement of the damaged materials is recommended. The exterior walls on Building 7, 9, 10, 12, and 13 were observed to be excessively dirty/stained and exhibit mildew. PCA-4.3.1The exteriors were reportedly last cleaned and painted in 2019. Based on the noted condition and EUL of paint | GC | Year 1 | 198000 | 185750 |  |  | 1 |  | PNA - Repaint community PCA 4.3.1 - Areas of damaged siding were observed on the east and south elevations of Building 3, the north elevation of Building 3, a soffit area on the west elevation of Bui
145 | 84220 | Replace forced air unit | PCA 5.2 - Split-system furnace/fan coil, Replace | GC | Year 1 | 78000 | 23400 |  |  | 3 |  | PCA 5.2 - Split-system furnace/fan coil, Replace
15 | 84385 | Storm sewer piping | PNA - Add drainage behing 4 building and connect to downspouts | GC | Year 1 | 75000 | 75000 |  |  | 0 |  | PNA - Add drainage behing 4 building and connect to downspouts
131 | 84450 | Security Camera System | Manager says system is ok, maybe add license plate reader and a few cameras | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | Manager says system is ok, maybe add license plate reader and a few cameras
21 | 84095 | Resurface swimming pool | Swimming Pool | GC | Year 1 | 42000 | 18600 |  |  | 3 |  | Swimming Pool
47 | 84114 | Repair exterior stair treads, stringers, and railing | PNA - Replace damaged railing on stair cases PCA 4.5 - Areas of rust and corrosion was observed on the steel stingers and base of the landings at Buildings 2, 4, and 6. In addition, the paint was observed to be chipping of the steel components throughout the subject property. Repair of the noted staircases followed by painting of the steel components is recommended. | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | PNA - Replace damaged railing on stair cases PCA 4.5 - Areas of rust and corrosion was observed on the steel stingers and base of the landings at Buildings 2, 4, and 6. In addition, the paint was obse
117 | 84361 | Pool Area Remodel | Add gazebo, turf next to clubhouse | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Add gazebo, turf next to clubhouse
104 | 84304 | Unit Deferred Maintenance | 2 Units have mold: (1-601, 1-610) 97% of water heaters > 10 years old Major Repairs Flooring repair: 17 Bedrooms 18 Living Areas Estimated total repair cost: $25,909 | Capex | Year 1 | 26000 | 0 |  |  | N/A |  | 2 Units have mold: (1-601, 1-610) 97% of water heaters > 10 years old Major Repairs Flooring repair: 17 Bedrooms 18 Living Areas Estimated total repair cost: $25,909
116 | 84190 | Fitness Equipment | Add equipment | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | Add equipment
17 | 84204 | Stripe parking areas | Stripe Parking | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Stripe Parking
20 | 83517 | Erosion control / Tree trimming | PNA - Fill eroded areas around buildings; PCA - 3.2.4- Areas of soil erosion were observed on the northeast corner ad east elevations of Building 7, the east elevation of Building 9, and adjacent to the fire riser room at Building 10. Repair of the noted areas followed by implementation of soil erosion control measures is recommended. PCA 3.2.4 - Areas of barren soil was observed east adjacent to Building 7, south adjacent to Building 6, and north adjacent to Building 7. Replacement / resodding of the noted areas is recommended. PCA - 3.2.4 Vegetative overhand was observed on the west elevations of Bldgs. 1, 12, and 13. No portion of any trees should be in contact wi the bldg. exterior. It is recommended that the trees be trimmed back. | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | PNA - Fill eroded areas around buildings; PCA - 3.2.4- Areas of soil erosion were observed on the northeast corner ad east elevations of Building 7, the east elevation of Building 9, and adjacent to
103 | 84239 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | Capex | Year 1 | 23375 | 0 |  |  | N/A |  | LowPro (Pair covers 4 burner range)- For range top microwaves
16 | 84204 | Pavement | PNA - Repair Potholes PCA 3.2.2 - Linear cracking was observed in the drive aisles and parking spaces at the entrance drive, between Buildings 2 and 3, north adjacent to Building 3 and 5, west adjacent to Building 8, south adjacent to Building 10, and west adjacent to the leasing office. Repair of the noted areas is recommended. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | PNA - Repair Potholes PCA 3.2.2 - Linear cracking was observed in the drive aisles and parking spaces at the entrance drive, between Buildings 2 and 3, north adjacent to Building 3 and 5, west adjace
124 | 84280 | Model Unit Update | New furniture in model unit | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | New furniture in model unit
146 | 84218 | Replace AC condenser | PCA 5.2 -Many of the condensing units were installed in an improper manner. Limited units were observed set on pads that were not protected from a rain gutter. These types of poor installation practices can lead to premature failure. Partner recommends that units be repaired and protected as necessary. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | PCA 5.2 -Many of the condensing units were installed in an improper manner. Limited units were observed set on pads that were not protected from a rain gutter. These types of poor installation practic
48 | 84121 | Repair patio/balcony railings | PNA - Repair balcony railings | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | PNA - Repair balcony railings
57 | 84433 | Asphalt composite shingle roofing | PNA - Roof tune up | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | PNA - Roof tune up
91 | 84106 | Drier vents | PNA - Clean drier vents and repair as needed. PCA 5.2 - Some of the dryer vents appeared to be damaged and full of debris. Cracked or vents that are missing louvres may allow pests and debris to enter the ventilation system. Numerous vents and related ducts were filled with lint and debris. This can cause the dryers to overheat and ignite the lint causing a fire hazard. Repair and cleaning of the vents is recommended. | GC | Year 1 | 16660 | 24500 |  |  | 0 |  | PNA - Clean drier vents and repair as needed. PCA 5.2 - Some of the dryer vents appeared to be damaged and full of debris. Cracked or vents that are missing louvres may allow pests and debris to enter
25 | 84111 | Dumpster enclosures | PNA - Repair compactor areas | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | PNA - Repair compactor areas
118 | 84360 | Pool Furniture | New furniture | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | New furniture
123 | 84130 | Dog Park | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola
19 | 84221 | Sidewalks | PNA - remove and replace areas of trip hazards PCA 3.2.3 - Potential tripping hazards due to heaved concrete sections were observed southeast adjacent to Building 5, the southeast corner of Building 3, and northwest adjacent to Building 2. In addition, linear cracking was observed in the concrete walkways north adjacent to Building 1 and 2, in the building entrance flatwork on the north and south elevations of Building 3, north adjacent to Building 4, south and east adjacent to Building 5, southwest adjacent to Building 7, west adjacent to Building 8, and east adjacent to Building 13. Repair/sectional replacement of the noted areas is recommended. | GC | Year 1 | 14400 | 14400 |  |  | 0 |  | PNA - remove and replace areas of trip hazards PCA 3.2.3 - Potential tripping hazards due to heaved concrete sections were observed southeast adjacent to Building 5, the southeast corner of Building
18 | 84204 | ADA parking & curb cuts | PNA - Add rail around ADA Ramp to units PCA - Installation of vertical identification signage at parking space | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | PNA - Add rail around ADA Ramp to units PCA - Installation of vertical identification signage at parking space
23 | 84361 | Replace swimming pool deck | PNA - Pressure wash pool decks | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | PNA - Pressure wash pool decks
46 | 84206 | Concrete deck / floor fill | PNA - Grind and seal cracks in light weight concrete landings | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | PNA - Grind and seal cracks in light weight concrete landings
134 | 84905 | Restoration & Remediation | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools | Capex | Project | 10000 | 2400 |  |  | N/A |  | Water Restoration Equipment- Dehumidifier, 2 blowers, Wet vac Miscellaneous tools
135 | 83375 | Golf Cart | Budget for maintenance cart. Don't have leasing cart, budget for one in case it is needed | Capex | Project | 10000 | 0 |  |  | N/A |  | Budget for maintenance cart. Don't have leasing cart, budget for one in case it is needed
58 | 84202 | Gutters & downspouts | PNA - Clean, repitch, and secure gutters | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | PNA - Clean, repitch, and secure gutters
49 | 84102 | Expansion Joints | Building Expansion Joints | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Building Expansion Joints
70 | 84105 | Repair / replace wood trim | Replace damaged trim | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Replace damaged trim
112 | 84208 | Clubhouse / Office Remodel | No clubhouse, allowance for office | PMC | Project | 7500 | 3871 |  |  | N/A |  | No clubhouse, allowance for office
22 | 84361 | Replace swimming pool coping | PNA - Replace deck-o-seal | GC | Year 1 | 6500 | 6500 |  |  | 0 |  | PNA - Replace deck-o-seal
24 | 84361 | Fences & gates - swimming pool | PNA - Adjust gates and repair gate latches | GC | Year 1 | 6500 | 6500 |  |  | 0 |  | PNA - Adjust gates and repair gate latches
59 | 84433 | Flashing | PNA - Repair damaged flashing | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | PNA - Repair damaged flashing
60 | 84433 | Sealants & caulking | Roof Sealants | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Roof Sealants
68 | 84120 | Breezeways | Repair soffits | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Repair soffits
114 | 83265 | Computers | Budget for 3 replacement | PMC | Project | 6000 | 75832 |  |  | N/A |  | Budget for 3 replacement
26 | 84205 | Fences & gates - site perimeter | PCA 3.2.7 - Isolated areas of damaged fencing was observed north adjacent to Building 12, south adjacent to Building 4, and at the refuse enclosure located northeast adjacent to Building 5. Repair of the noted areas of damage is recommended. | GC | Year 1 | 980 | 980 |  |  | 0 |  | PCA 3.2.7 - Isolated areas of damaged fencing was observed north adjacent to Building 12, south adjacent to Building 4, and at the refuse enclosure located northeast adjacent to Building 5. Repair of
PROJECTS subtotal (excl. contingency/CM fee)
158 | 84510 | Contingency | Contingency | CON | Contingency | 103516 | 0 | 103516 |  | N/A |  | Contingency
159 | 84505 | Construction Management Fee | CM Fee | CMF | CM Fee | 57309 | 32690 | 57309 |  | N/A |  | CM Fee

## David Ave
David Ave — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
172 | 51140-00 | Electrical Panel Disconnects & Meter Banks | Phased replacement of 2 main meter banks Equity PCA Item- 5.3- The main disconnects and meter banks were manufactured by Wadsworth Electrical Mfg., a company that is no longer in business and no longer supported. Extensive surface rust was observed on the meter walls at each building. Based on the age, observed condition and obsolescence of the disconnects and meter banks, Partner recommends these be replaced | GC | Year 1 | 120000 | 36000 |  |  | 3 |  | Phased replacement of 2 main meter banks Equity PCA Item- 5.3- The main disconnects and meter banks were manufactured by Wadsworth Electrical Mfg., a company that is no longer in business and no longe
70 | 51077-00 | Increase rail height | Raise catwalk rail height to 42" per SB 721 report | GC | Year 1 | 100000 | 30000 |  |  | 3 |  | Raise catwalk rail height to 42" per SB 721 report
101 | 51080-00 | Exterior building Paint | Paint community | GC | Year 1 | 98000 | 123667 |  |  | 0 |  | Paint community
18 | 51023-00 | Resurface swimming pool | Resurface two pools | GC | Year 1 | 92000 | 27600 |  |  | 3 |  | Resurface two pools
17 | 51053-00 | Asphalt Coating | Seal asphalt Includes Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in fair condition. Reapplication of the seal coat and markings/striping is recommended in the short term. | GC | Year 1 | 61000 | 61000 |  |  | 0 |  | Seal asphalt Includes Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in fair condition. Reapplication of the seal coat and markings/striping is recommended in t
69 | 51072-00 | Repair balcony framing & decking | Repairs for 2 walkways and stairwells per SB721 report from Medro, contingency for additional repairs PCA 4.5- As no documentation was provided with regard to the SB 721 inspections, Partner recommends performing the SB 721 inspections at this time | GC | Year 1 | 55000 | 49862 |  |  | 1 |  | Repairs for 2 walkways and stairwells per SB721 report from Medro, contingency for additional repairs PCA 4.5- As no documentation was provided with regard to the SB 721 inspections, Partner recommend
102 | 51082-00 | Repair / replace wood trim Repair or replace damaged | Replace rotted fascia and trim PCA 4.2. - Repair or replace damaged wood trim and stucco at elevated walkways and soffits. Allowance for in-kind replacement of any damaged wood framing. | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | Replace rotted fascia and trim PCA 4.2. - Repair or replace damaged wood trim and stucco at elevated walkways and soffits. Allowance for in-kind replacement of any damaged wood framing.
164 | 51990-00 | Green Program - Energy Retrofit | Echelon upfront costs | Capex | Year 1 | 35760 | 2436 |  |  | N/A |  | Echelon upfront costs
94 | 51075-00 | Repair / replace wood shingles | Replace window walls with Hardie Horizontal | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Replace window walls with Hardie Horizontal
159 | 51130-00 | Galvanized Pipe Replacement | Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone to developing pinhole leaks and is susceptible to corrosion inside the pipe, restricting water flow. Based on age and condition of the piping, Partner recommends that the galvanized steel pipe be replaced throughout each building, starting with the service entrances and water heaters | Capex | Year 1 | 30000 | 30740 |  |  | N/A |  | Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone to developing pinhole leaks and is susceptible to corrosion inside the pipe, restricting water flow.
56 | 51092-00 | Install metal hardware connections at post-to-beam a | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces. | GC | Year 1 | 22500 | 22500 |  |  | 0 |  | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces.
58 | 51070-00 | 3040 David – Engineered repair design to remediate d | PCA 4.2. -3040 David – Engineered repair design to remediate damaged beam at TUP. | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | PCA 4.2. -3040 David – Engineered repair design to remediate damaged beam at TUP.
68 | 51077-00 | Repair exterior stair railings | Secure railings on all catwalks | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Secure railings on all catwalks
82 | 51062-00 | Sealants & caulking | Prep and seal exterior | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Prep and seal exterior
140 | 51011-00 | Pool Furniture | No furniture, need to add for 2 pools | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | No furniture, need to add for 2 pools
20 | 51076-00 | Fences & gates - swimming pool | Adjust closers on pool gates | GC | Year 1 | 12800 | 12800 |  |  | 0 |  | Adjust closers on pool gates
19 | 51026-00 | Repair / replace swimming pool pumps | Anti entrapment devices | GC | Year 1 | 12600 | 3780 |  |  | 3 |  | Anti entrapment devices
21 | 51172-00 | Carports / Garages | Repair and paint carport supports | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Repair and paint carport supports
59 | 51070-00 | Remediation of exposed wood beams exhibiting deterio | PCA 4.2 - Remediation of exposed wood beams exhibiting deterioration at TUP regions. | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | PCA 4.2 - Remediation of exposed wood beams exhibiting deterioration at TUP regions.
60 | 51070-00 | Replace edge beams in-kind at TUP areas, where neede | PCA 4.2. Replace edge beams in-kind at TUP areas, where needed. | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | PCA 4.2. Replace edge beams in-kind at TUP areas, where needed.
81 | 51071-00 | Gutters & downspouts Replace missing or crushed down | Secure and clean gutters PCA 4.4.1. -Replace missing or crushed downspouts. | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Secure and clean gutters PCA 4.4.1. -Replace missing or crushed downspouts.
160 | 51130-00 | Stormwater Pipe Repair | Number based on actual bid; $285 per cleanout, est. 10 cleanouts. $402 per storm drain, 4 cleanouts. $129 per flow test, 12 tests. $185 per clean out plug removal, 4 removals Equity PCA Item- 5.1- The site contact reported a stormwater pipe located in parking lot area near the southeast corner of the property appeared to be broken as the system did not drain properly. The property was in the process of engaging a contractor to repair the system. Based on this information, Partner recommends a qualified contractor be engaged to repair the sanitary drain | PMC | Year 1 | 6746 | 4296 |  |  | N/A |  | Number based on actual bid; $285 per cleanout, est. 10 cleanouts. $402 per storm drain, 4 cleanouts. $129 per flow test, 12 tests. $185 per clean out plug removal, 4 removals Equity PCA Item- 5.1- The
47 | 51992-00 | Termite Remediation | Drywood termites treatment | PMC | Year 1 | 6000 | 6000 |  |  | N/A |  | Drywood termites treatment
141 | 51160-04 | Picnic/Grill Area Remodel | Allowance for grill/outdoor kitchen upgrades | PMC | Year 1 | 6000 | 0 |  |  | N/A |  | Allowance for grill/outdoor kitchen upgrades
162 | 51130-00 | Natural Gas Seismic Shutoff | Will confirm with Gas utility company if needed Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices to prevent dangerous gas leaks in the event of a line break during a significant seismic event. Installation of automatic seismic shut-off devices at the services is recommended | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Will confirm with Gas utility company if needed Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices to prevent dangerous gas leaks in the event of
61 | 51090-00 | Repair or replace damaged concrete treads at stairs. | PCA 4.2.- Repair or replace damaged concrete treads at stairs. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | PCA 4.2.- Repair or replace damaged concrete treads at stairs.
139 | 51160-00 | Pool Area Remodel | Allowance | PMC | Year 1 | 5000 | 2400 |  |  | N/A |  | Allowance
174 | 51140-00 | Electrical service and distribution, Ongoing Repalce | Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B (Recommended Practice for Electrical Equipment Maintenance) recommends that IR scans be performed on an annual basis in order to identify malfunctioning electrical equipment before the condition can cause a life-safety concern. Partner recommends that IR scans of the electrical equipment be completed in the immediate term. | GC | Year 1 | 5000 | 1500 |  |  | 3 |  | Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B (Recommended Practice for Electrical Equipment Maintenance) recommends that IR scans be
161 | 51134-00 | Sanitary Sewer Piping | Equity PCA Item- 5.1- The sanitary waste system was original to construction. Typically, sections were replaced as needed. Based on the apparent age of the system and EUL of cast iron piping, a sewer scope is recommended to visualize any potential damaging, and aging of the sewer piping | PMC | Year 1 | 4000 | 7211 |  |  | N/A |  | Equity PCA Item- 5.1- The sanitary waste system was original to construction. Typically, sections were replaced as needed. Based on the apparent age of the system and EUL of cast iron piping, a sewer
57 | 51090-00 | Rout and seal cracks in concrete slab-on-grade. | PCA 4.1 Rout and seal cracks in concrete slab-on-grade. | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | PCA 4.1 Rout and seal cracks in concrete slab-on-grade.
62 | 51077-00 | Clean and repaint steel stair frame with surface cor | PCA 4.2. -Clean and repaint steel stair frame with surface corrosion. | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | PCA 4.2. -Clean and repaint steel stair frame with surface corrosion.
158 | 51130-00 | Back-flow preventer | Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. Municipalities typically require annual inspections of backflow preventers and require the tag to be displayed on the device. Inspection and certification of the backflow preventers by a qualified contractor is recommend. | PMC | Year 1 | 3000 | 2184 |  |  | N/A |  | Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. Municipalities typically require annual inspections of backflow preventers and require the tag to be displ
136 | 51160-06 | Common area FF&E, Replace | FF& E - Common Areas | PMC | Year 1 | 2000 | 1200 |  |  | N/A |  | FF& E - Common Areas
142 | 51160-04 | Picnic/Grill Furniture | Allowance for furniture | PMC | Year 1 | 2000 | 1200 |  |  | N/A |  | Allowance for furniture
138 | 51169-00 | Leasing Office Restroom Accessibility | Equity PCA Item- 7.1- The leasing office restroom is provided with a full vanity at the lavatory. Replacement of the vanity with a wall mounted lavatory is recommended. The leasing office restroom toilet lacks grab bars. Installation of grab bars is recommended. Accessible signage for the leasing office restroom was observed to be mounted directly on the entry door. This signage should be relocated to the wall adjacent to the entrance for compliance. | PMC | Year 1 | 1550 | 0 |  |  | N/A |  | Equity PCA Item- 7.1- The leasing office restroom is provided with a full vanity at the lavatory. Replacement of the vanity with a wall mounted lavatory is recommended. The leasing office restroom to
171 | 51993-01 | Fire Department Violations - Engage expeditor to cle | Lender PCA Item- There are outstanding fire department violations. CBRE recommends engaging an expeditor to clear all outstanding violatons. | PMC | Year 1 | 1500 | 548 |  |  | N/A |  | Lender PCA Item- There are outstanding fire department violations. CBRE recommends engaging an expeditor to clear all outstanding violatons. | [5 empty] | 2025-06-30
63 | 51062-00 | Replace missing vent tops. | PCA4.4.1 - Replace missing vent tops. | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | PCA4.4.1 - Replace missing vent tops.
173 | 51140-00 | Replace Electrical Meter Panel at Building 3 | Equity PCA Item- 5.3- A metal panel was missing on the wiring trough at the meter enclosure at Building 3. The missing plate exposed the electrical wiring to the outside elements, creating a safety issue. Partner recommends installing a metal cover plate | PMC | Year 1 | 500 | 156 |  |  | N/A |  | Equity PCA Item- 5.3- A metal panel was missing on the wiring trough at the meter enclosure at Building 3. The missing plate exposed the electrical wiring to the outside elements, creating a safety is
PROJECTS subtotal (excl. contingency/CM fee)
179 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 47350 | 22198 | 47350 |  | N/A |  | CM Fee
178 | 51175-00 | Contingency | Contingency Amount | CON | Contingency | 45096 | 0 | 45096 |  | N/A |  | Contingency Amount

## Elliot Baymeadows
Elliot Baymeadows — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
95 | 84101 | Exterior Building Painting | Heavy pressure wash and prep for mildew and paint community | GC | Year 1 | 675000 | 405000 |  |  | 2 |  | Heavy pressure wash and prep for mildew and paint community
105 | 84207 | Unit Interior Replacements | Classic & Partial Units | Capex | Year 1 | 880000 | 43095 |  |  | N/A |  | Classic Units
75 | 84433 | Asphalt composite shingle roofing | Roof tune up | GC | Year 1 | 160000 | 161000 |  |  | 0 |  | Roof tune up
15 | 84303 | Landscape Cleanup and Enhancements | Tree trim, foliage cut back throughout | GC | Year 1 | 100000 | 90000 |  |  | 1 |  | Tree trim, foliage cut back throughout
44 | 84390 | Sports Courts PCA 3.2.9 - Repair tennis and sports c | Placeholder for repurposing of sports court area. Could include turf installation for soccer Tennis/sports court were observed to contain cracked playing surfaces and water ponding on the surface. Resurfacing is recommended. | GC | Year 1 | 75000 | 75000 |  |  | 0 |  | Placeholder for repurposing of sports court area. Could include turf installation for soccer Tennis/sports court were observed to contain cracked playing surfaces and water ponding on the surface. Res
166 | 84210 | Common area light fixtures | Pole lights, buildings lights, and amenities courts | GC | Year 1 | 72000 | 72000 |  |  | 0 |  | Pole lights, buildings lights, and amenities courts
29 | 84095 | Resurface swimming pool | Two pools - Resurface | GC | Year 1 | 70000 | 21056 |  |  | 3 |  | Two pools - Resurface
162 | 84220 | Replace AC condenser | Contingent HVAC replacement - projections taken from EPCA | GC | Year 1 | 69490 | 53704 |  |  | 2 |  | Contingent HVAC replacement - projections taken from EPCA
135 | 84361 | Pool Area Remodel | Allocation for two pools | Capex | Year 1 | 50000 | 19703 |  |  | N/A |  | Allocation for two pools
67 | 84114 | Repair exterior stair treads and stringers | Repair failing wood stair cases | GC | Year 1 | 43000 | 80000 |  |  | 0 |  | Repair failing wood stair cases
100 | 84102 | Chimney Cap Covers | Fabricate and replace rusted out and failing chimney covers | GC | Year 1 | 43000 | 40000 |  |  | 1 |  | Fabricate and replace rusted out and failing chimney covers
77 | 84433 | Flashing | Roof Flashing | GC | Year 1 | 40000 | 35000 |  |  | 2 |  | Roof Flashing
133 | 84195 | Fitness Center Remodel | New equipment, refurbishment of existing equipment | Capex | Year 1 | 40000 | 49616 |  |  | N/A |  | New equipment, refurbishment of existing equipment
86 | 84102 | Repair / replace wood siding | Replace failing siding | GC | Year 1 | 38000 | 30400 |  |  | 2 |  | Replace failing siding
161 | 84218 | Replace forced air unit | Level and replace AC pads | GC | Year 1 | 35200 | 0 |  |  | 4 |  | Level and replace AC pads
136 | 84360 | Pool Furniture | Allocation for two pools | Capex | Year 1 | 35000 | 537 |  |  | N/A |  | Allocation for two pools
167 | 84210 | Replace breezeway lights | Entry lights | GC | Year 1 | 32100 | 32100 |  |  | 0 |  | Entry lights
21 | 84219 | Parking equipment | Need more info from Mark | GC | Year 1 | 32000 | 0 |  |  | 4 |  | Need more info from Mark
24 | 84302 | Landscape irrigation PCA 3.2.11 - Evaluate system, r | Irrigation in fair to poor condition. Electrical wiring in the control panel appeared to be cut and maintenance personnel did not know how the system worked. | Capex | Year 1 | 32000 | 22824 |  |  | N/A |  | Irrigation in fair to poor condition. Electrical wiring in the control panel appeared to be cut and maintenance personnel did not know how the system worked.
115 | 84239 | Fire Stops | Fire Stops | Capex | Year 1 | 29920 | 29920 |  |  | N/A |  | Fire Stops
23 | 84115 | Sidewalks | Sidewalk Repairs | GC | Year 1 | 28000 | 21000 |  |  | 2 |  | Sidewalk Repairs
96 | 84113 | Repair / replace wood trim | Wood Trim Repairs | GC | Year 1 | 28000 | 22400 |  |  | 2 |  | Wood Trim Repairs
22 | 84204 | Parking pavement PCA 3.2.2 - Repair pothole formatio | Linear cracking, "map" or "alligator" cracking, and pothole formation were noted throughout the drive aisles adjacent to the storm drains. | GC | Year 1 | 26500 | 26500 |  |  | 0 |  | Linear cracking, "map" or "alligator" cracking, and pothole formation were noted throughout the drive aisles adjacent to the storm drains.
106 | 84106 | Dryer Vents | Clean dryer vents | GC | Year 1 | 26400 | 27300 |  |  | 0 |  | Clean dryer vents
169 | 84210 | Electrical service and distribution, Ongoing Repalce | CBRE recommends verifying that the non-GFCI outlets in the secondary bathrooms are on the same circuit as the GFCI outlets in the primary bathrooms. | GC | Year 1 | 23000 | 12600 |  |  | 3 |  | CBRE recommends verifying that the non-GFCI outlets in the secondary bathrooms are on the same circuit as the GFCI outlets in the primary bathrooms. | [5 empty] | 2025-10-09
20 | 84201 | Stripe parking areas PCA 7.0 - install proper access | Parking Lot Striping | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | Parking Lot Striping
25 | 84517 | Erosion control | Site Erosion Control | GC | Year 1 | 22000 | 11412 |  |  | 3 |  | Site Erosion Control
82 | 84433 | Sealants & caulking and paint | Roof Sealants & Caulking | GC | Year 1 | 20000 | 16000 |  |  | 2 |  | Roof Sealants & Caulking
134 | 84230 | Package lockers | Add Lockers | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Add Lockers
141 | 84280 | Unit Model Update | New furniture in model unit | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | New furniture in model unit
170 | 83236 | Smoke detectors PCA 5.5.2 - Replace all smoke detect | In dwelling units observed, smoke detectors were only mounted in the hallways or living room areas, not in the sleeping rooms and in many of the units only the bracket was observed. Partner recommends replacement of all smoke detectors in all dwelling units | Capex | Year 1 | 17600 | 5535 |  |  | N/A |  | In dwelling units observed, smoke detectors were only mounted in the hallways or living room areas, not in the sleeping rooms and in many of the units only the bracket was observed. Partner recommends
168 | 84330 | Electrical Panel Disconnects & Meter Banks PCA 5.3 - | Electrical systems are approaching 40-years-old and are exposed to the weather. IR scans can identify loose connections, load balance issues, defective breakers, and excessive circuit loads | GC | Year 1 | 14000 | 12600 |  |  | 1 |  | Electrical systems are approaching 40-years-old and are exposed to the weather. IR scans can identify loose connections, load balance issues, defective breakers, and excessive circuit loads
49 | 83301 | WDO Repairs PCR - WDO Repairs - WDO report | Subsequent to the site visit, a WDO inspection was conducted by Busy Bee Termite, and their findings indicate evidence of wood rot and damage, and wood/stucco contact with the ground. CBRE recommends that repairs to the areas indicated in the report be completed. | Capex | Year 1 | 12000 | 356 |  |  | N/A |  | Subsequent to the site visit, a WDO inspection was conducted by Busy Bee Termite, and their findings indicate evidence of wood rot and damage, and wood/stucco contact with the ground. CBRE recommends | [5 empty] | 2026-07-09
157 | 84385 | Sanitary Sewer Piping PCA 5.1 - Sewer scoping | Due to the age of the site, Partner recommends a sewer scoping of all waste lines. This scoping can tell if there are breaks or separations in the sanitary lines | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Due to the age of the site, Partner recommends a sewer scoping of all waste lines. This scoping can tell if there are breaks or separations in the sanitary lines
171 | 83236 | CO Detectors PCR (PR-90) - Provide CO detectors PCA | Carbon Monoxide detectors were not observed as required. A recommendation has been included to install CO detectors in all units immediately as a life safety issue. | PMC | Year 1 | 8800 | 2767 |  |  | N/A |  | Carbon Monoxide detectors were not observed as required. A recommendation has been included to install CO detectors in all units immediately as a life safety issue. | [5 empty] | 2025-10-09
48 | 83301 | Termite treatment PCR - Termite damage repairs | Subsequent to the site visit, a WDO inspection wasconducted by Busy Bee Termite, and their findings indicate visible signs of live subterranean termites. CBRE recommends that treatment as described in the report. | PMC | Year 1 | 7500 | 223 |  |  | N/A |  | Subsequent to the site visit, a WDO inspection wasconducted by Busy Bee Termite, and their findings indicate visible signs of live subterranean termites. CBRE recommends that treatment as described in | [5 empty] | 2026-07-09
158 | 84476 | Domestic Hot Water Heater Replacement | Contingent hot water heater replacement | PMC | Year 1 | 7040 | 4600 |  |  | N/A |  | Contingent hot water heater replacement
26 | 84205 | Fences & gates - site perimeter PCR - Repair inopera | The motor for the automated gates were reported and observed to be inoperable. Repairs are recommended at this time. | PMC | Year 1 | 2500 | 1600 |  |  | N/A |  | The motor for the automated gates were reported and observed to be inoperable. Repairs are recommended at this time. | [5 empty] | 2026-07-09
47 | 83301 | Termite Repairs PCR - Termite Damage Repairs | Evidence of termite damage was observed on the door frame of the poop pump room, near the fitness center building. All damaged wood should be replaced and the area treated as needed. | PMC | Year 1 | 700 | 600 |  |  | N/A |  | Evidence of termite damage was observed on the door frame of the poop pump room, near the fitness center building. All damaged wood should be replaced and the area treated as needed. | [5 empty] | 2026-07-09
159 | 84218 | PCR - Water heater repairs | Minor damage was observed at the water heater pan in units 609 and 1709. A cover plate for the control panel is also missing at the water heater in unit 602. | PMC | Year 1 | 700 | 633 |  |  | N/A |  | Minor damage was observed at the water heater pan in units 609 and 1709. A cover plate for the control panel is also missing at the water heater in unit 602. | [5 empty] | 2026-07-09
34 | 83270 | Maintenance Shop PCR - Overhead door repair (Mainten | Minor damage was observed on the overhead door trim at the maintenance shop. Repairs are recommended | PMC | Year 1 | 350 | 299.89 |  |  | N/A |  | Minor damage was observed on the overhead door trim at the maintenance shop. Repairs are recommended | [5 empty] | 2026-07-09
PROJECTS subtotal (excl. contingency/CM fee)
174 | 84505 | Construction Management Fee | CM Fees | CMF | CM Fee | 143440 | 49924 | 143440 |  | N/A |  | CM Fees

## Foster Creek
Foster Creek — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
94 | 84101 | Exterior building Paint | Repaint Community | GC | Year 1 | 320000 | 96000 |  |  | 3 |  | Repaint Community
93 | 84113 | Breezeway soffit repairs | Repair soffits - Could be changed to $120k | GC | Year 1 | 160000 | 48000 |  |  | 3 |  | Repair soffits - Could be changed to $120k
200 | 83210 | 83210 - Electrical | Outlets and switches replacement program | Capex | Year 1 | 102000 | 81929 |  |  | N/A |  | Outlets and switches replacement program
46 | 84450 | Security Camreas System | Add additional security camreas systems to the property | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | Add additional security camreas systems to the property
70 | 84121 | Repair patio/balcony railings Equty PCA 3.3.5 | Repair balconies railings Balcony Repairs | GC | Year 1 | 40000 | 12000 |  |  | 3 |  | Repair balconies railings Balcony Repairs
72 | 84121 | Repair exterior stair railings | Repair wooden railings on stairs | GC | Year 1 | 35000 | 10500 |  |  | 3 |  | Repair wooden railings on stairs
196 | 84130 | Dog Park & Grilling Area | Dog Park & Grilling Area | Capex | Year 1 | 35000 | 0 |  |  | N/A |  | Dog Park & Grilling Area
87 | 84102 | Repair / replace wood siding Lender PCA 3.2.4 Equity | Replace damaged T 1-11 siding on mansards Damaged T1-11 siding was present at Building G (Phase II). Repair is recommended. An opinion of cost for this work is included as an immediate repair. Replace deteriorated T1-11 wood siding | GC | Year 1 | 34000 | 10200 |  |  | 3 |  | Replace damaged T 1-11 siding on mansards Damaged T1-11 siding was present at Building G (Phase II). Repair is recommended. An opinion of cost for this work is included as an immediate repair. Replac | [5 empty] | 2025-06-01
164 | 84210 | General Electrical Services Equity PCA 3.4.4 | Replace wall packs | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | Replace wall packs
24 | 84115 | Sidewalks Lender PCA 3.1.7 Equity PCA 3.2.4 | Remove and replace areas of trip hazards. Cracked concrete was observed adjacent to the entrance to Building C. Repair is recommended. Repair trip hazards - concrete sidewalks | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Remove and replace areas of trip hazards. Cracked concrete was observed adjacent to the entrance to Building C. Repair is recommended. Repair trip hazards - concrete sidewalks | [5 empty] | 2025-09-01
79 | 84433 | Modified bitumen membrane roof Repairs | Repairs to flat roofs. Equity PCA did not mention roof as an immediate need, but did mention as a replacement in YR 1 | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Repairs to flat roofs. Equity PCA did not mention roof as an immediate need, but did mention as a replacement in YR 1
25 | 84204 | Asphalt Pavement Lender PCA 3.1.6 Equity PCA 3.2.4 | Lender PCA 3.1.6 Damaged asphalt pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was typically present throughout the drive aisles. Repairs are recommended. Localized Full depth asphalt repairs (>1K SF) | GC | Year 1 | 24250 | 24250 |  |  | 0 |  | Lender PCA 3.1.6 Damaged asphalt pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was typically present throughout the drive aisles. Repairs are recommended. | [5 empty] | 2025-06-01
71 | 84430 | Concrete deck / floor fill | np1 sealant to cracks in landing | GC | Year 1 | 19000 | 19000 |  |  | 0 |  | np1 sealant to cracks in landing
81 | 83439 | Gutters & downspouts | Clear scuppers and roof drains | GC | Year 1 | 19000 | 19000 |  |  | 0 |  | Clear scuppers and roof drains
42 | 84111 | Dumpster enclosures Equity PCA 3.2.2 | Repair dumpster inclosures. Replaced Damaged Dumpster Gates | GC | Year 1 | 16000 | 4800 |  |  | 3 |  | Repair dumpster inclosures. Replaced Damaged Dumpster Gates
95 | 84113 | Repair / replace wood trim Equity PCA 3.3.3 | Replace damaged trim | GC | Year 1 | 16000 | 4800 |  |  | 3 |  | Replace damaged trim
103 | 84905 | Moisture and Microbial Growth Equity PCA 4.6 | Proactive rewire bathroom fan to light switch. Mold & Moisture Removal | GC | Year 1 | 15215 | 15215 |  |  | 0 |  | Proactive rewire bathroom fan to light switch. Mold & Moisture Removal
114 | 84211 | Fire Stops | Install Fire Stops | Capex | Year 1 | 15215 | 105065 |  |  | N/A |  | Install Fire Stops
27 | 84517 | Storm Water Management Equity PCA 3.2.1 | Erosion Repairs | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Erosion Repairs
194 | 83103 | Signage | Building Signage | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Building Signage
168 | 84330 | GFCI Receptacles Equity PCA 3.4.4 | Missing GFCI receptacles | Capex | Year 1 | 13500 | 0 |  |  | N/A |  | Missing GFCI receptacles
76 | 84433 | Asphalt composite shingle roofing | Roof Tune Up | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Roof Tune Up
120 | 82460 | Down Unit Renovation (C-309) Lender PCA 3.4.2 | Unit C-309 was observed in poor condition and is considered ‘down’. A notice affixed to the door by the King County Sheriff’s office indicated that the previous tenants were evicted. Multiple water leaks were observed and reported; an electrical outlet was exposed in the bedroom, and cabinet doors and drawers were damaged or missing. Renovation and repair is recommended. | Capex | Year 1 | 10800 | 10800 |  |  | N/A |  | Unit C-309 was observed in poor condition and is considered ‘down’. A notice affixed to the door by the King County Sheriff’s office indicated that the previous tenants were evicted. Multiple water le | [5 empty] | 2025-06-01
15 | 84303 | Landscape Cleanup and Enhancements Equity PCA 3.2.2 | Install Landscaping and Mulch - North of Building 15042 | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | Install Landscaping and Mulch - North of Building 15042
89 | 84102 | Repair / replace vinyl siding Lender PCA 3.2.4 | Isolated areas of warped vinyl lap siding were observed at the leasing office and Buildings B and C of Phase I. Repairs and/or replacement as necessary of the damaged siding and any damaged materials behind the siding is recommended. | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Isolated areas of warped vinyl lap siding were observed at the leasing office and Buildings B and C of Phase I. Repairs and/or replacement as necessary of the damaged siding and any damaged materials | [5 empty] | 2025-06-01
82 | 84433 | Flashing | Repair damaged flashing | GC | Year 1 | 8500 | 2550 |  |  | 3 |  | Repair damaged flashing
83 | 84433 | Sealants & caulking and paint | Roof Sealants & Caulking | GC | Year 1 | 8500 | 2550 |  |  | 3 |  | Roof Sealants & Caulking
47 | 84275 | Key Pad and Auto Locking Door | Add to gym door | PMC | Year 1 | 7500 | 0 |  |  | N/A |  | Add to gym door
121 | 82460 | Damaged Unit Repair (C-209) Lender PCA 3.4.2 Equity | Additionally, Unit C-209 was observed in fair condition. The unit has water damage to finishes from the unit above (C-309). It is recommended that all affected finishes are removed, underlying substrates cleaned and dried and affected finishes repaired. Return Down Unit C-309 Back to Rentable Condition | PMC | Year 1 | 5000 | 3411 |  |  | N/A |  | Additionally, Unit C-209 was observed in fair condition. The unit has water damage to finishes from the unit above (C-309). It is recommended that all affected finishes are removed, underlying substra | [5 empty] | 2025-06-01
198 | 83209 | 83209 - Plumbing | Plumbing Work Orders | PMC | Year 1 | 3500 | 29571 |  |  | N/A |  | Plumbing Work Orders
108 | 84106 | Clean Dryer vents | Clean dryer vents. Get a unit count of units with W/D | PMC | Year 1 | 2250 | 2750 |  |  | N/A |  | Clean dryer vents. Get a unit count of units with W/D
199 | 83209 | 83209 - Plumbing | Water Leaks Behind Sheetrock | PMC | Year 1 | 1667 | 14084 |  |  | N/A |  | Water Leaks Behind Sheetrock
23 | 83520 | ADA parking & curb cuts Lender PCA 5.4 Equity PCA | The subject property does not provide van-accessible parking spaces at the Leasing Office. Installation of one van-accessible parking space with appropriate pole signage, markings, and access aisle at the leasing office is recommended. Access to the leasing office requires the navigation of steps at the building entrance and knobbed entrance door hardware. Installation of a communication device between the building entrance and the leasing office entrance is recommended. Parking - Provide van-accessible parking spaces adjacent to areas of leasing office.Exterior Accessible Route - Install compliant curb cuts/ramps on accessible route to leasing office. | GC | Year 1 | 1600 | 1600 |  |  | 0 |  | The subject property does not provide van-accessible parking spaces at the Leasing Office. Installation of one van-accessible parking space with appropriate pole signage, markings, and access aisle at | [5 empty] | 2025-09-01
165 | 84330 | Improperly supported meter bank Equity PCA 3.4.4 | Meter bank supports | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | Meter bank supports
PROJECTS subtotal (excl. contingency/CM fee)
172 | 85305 | Construction Management Fee | CM Fee | CMF | CM Fee | 50470 | 14882.75 | 50470 |  | N/A |  | CM Fee
171 | 84510 | Contingency | Contingency Amount | CON | Contingency | 48067 | 0 | 48067 |  | N/A |  | Contingency Amount

## Foxdale Village
Foxdale Village — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
91 | 51075-00 | Repair / replace wood shingles | Replace T-111 siding with Hardie. Equity PCA Item 4.3.1- $19,800- Damaged and deteriorated T1-11 siding was present at numerous areas throughout the site. Replacement of the damaged siding and any damaged materials behind the siding is recommended. Equity PCA Item 4.3.1- $80,000- Areas of deteriorated fascia board was observed. Replacement of the damaged fascia boards is recommended in conjunction with the T1-11 repairs. Lender required termite treatment will be covered within this scope. Will be completed within 6 months from closing. | GC | Year 1 | 1033200 | 1033200 |  |  | 0 |  | Replace T-111 siding with Hardie. Equity PCA Item 4.3.1- $19,800- Damaged and deteriorated T1-11 siding was present at numerous areas throughout the site. Replacement of the damaged siding and any dam | [5 empty] | 2025-06-19
93 | 51080-00 | Exterior building paint | Paint community Equity PCA Item 3.2.7- $15,000- The paint finish on the wood fencing throughout the site was observed to be worn. Based on the noted condition, repainting of the wood fencing is recommended in the short term. Equity PCA Item 4.3.1- $550,000- The paint finish on the apartment buildings was observed to be deteriorated, chipping and worn. Based on the observed condition | GC | Year 1 | 401800 | 401800 |  |  | 0 |  | Paint community Equity PCA Item 3.2.7- $15,000- The paint finish on the wood fencing throughout the site was observed to be worn. Based on the noted condition, repainting of the wood fencing is recom
20 | 51050-00 | Asphalt Coating | Fill asphalt cracks and seal coat parking lot Equity PCA Item 3.2.2- $110,500- Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present at the drive aisles. Sectional full-depth replacement and crack routing/sealing is recommended. Equity PCA Item 3.2.2- $92,125- The seal coat and striping appeared to be largely faded throughout the site. Partner recommends reapplication of the slurry coat and striping subsequent to completion of pavement repairs discussed above. | GC | Year 1 | 182000 | 182000 |  |  | 0 |  | Fill asphalt cracks and seal coat parking lot Equity PCA Item 3.2.2- $110,500- Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present at the dri
94 | 51082-00 | Repair / replace wood trim | Replace trim and damaged fascia | GC | Year 1 | 179500 | 179500 |  |  | 0 |  | Replace trim and damaged fascia
133 | 51169-00 | Clubhouse / Office Remodel | Paint, Repair, and replace carpet in office, explore repurposing community center for fitness center or other use | GC | Year 1 | 150000 | 33150 |  |  | 4 |  | Paint, Repair, and replace carpet in office, explore repurposing community center for fitness center or other use
121 | 51160-00 | Green Program - Echelon Energy Retrofit | Energy Retrofit | Capex | Year 1 | 116000 | 0 |  |  | N/A |  | Energy Retrofit
21 | 51050-00 | Add Parking Spaces | Parking is an issue at the property, explore adding lot area or gaining spaced via restriping | GC | Year 1 | 100000 | 0 |  |  | 4 |  | Parking is an issue at the property, explore adding lot area or gaining spaced via restriping
79 | 51061-00 | Roofing | 19 roofs appear to be TPO- replace one roof and repair 19 roofs yr2 A, C, D, E, F, G, H, I, J, K, M, N, P, R, T, V, X, Y, 1, 3, 4, & 5. Yr7 B, L, O, Q, S, U, W, Z, 2 & 6 Contingency to replace 1 roof/yr starting year 4 Equity PCA Item 4.3.1- $97,500- The majority of the low slope roofs were in good condition, however, the modified bitumen cap sheet roofing on the south side of building 1340 and the built-up roofing with asphalt flood coat embedded aggregate surface at 1310 was worn/aged and in fair condition. | GC | Year 1 | 97500 | 97500 |  |  | 0 |  | 19 roofs appear to be TPO- replace one roof and repair 19 roofs yr2 A, C, D, E, F, G, H, I, J, K, M, N, P, R, T, V, X, Y, 1, 3, 4, & 5. Yr7 B, L, O, Q, S, U, W, Z, 2 & 6 Contingency to replace 1 roo
53 | 51072-00 | Concrete deck / floor fill | 25 Balcony or landing replacements | GC | Year 1 | 90000 | 90000 |  |  | 0 |  | 25 Balcony or landing replacements
125 | 51157-00 | Unit deferred maintenance | Flooring replacement needed: kitchen (26), living room (13), bedroom (31), and bathroom (7) Equity PCA Item 6.5.2- $341,600- Stained carpet was observed in approximately half of the units observed. The carpeting in these units appear to have reached the end of their useful lives. New carpeting is recommended. | Capex | Year 1 | 85400 | 76942 |  |  | N/A |  | Flooring replacement needed: kitchen (26), living room (13), bedroom (31), and bathroom (7) Equity PCA Item 6.5.2- $341,600- Stained carpet was observed in approximately half of the units observed. Th
92 | 51075-00 | Repair stucco | Repair damaged stucco | GC | Year 1 | 75000 | 75000 |  |  | 0 |  | Repair damaged stucco
163 | 51140-00 | Electrical distribution | Electrical service and distribution equipment, Phased replacement | GC | Year 1 | 57400 | 51351 |  |  | 2 |  | Electrical service and distribution equipment, Phased replacement
25 | 51993-00 | Replace camera / security equipment | Replace camera and security equipment | Capex | Year 1 | 51000 | 50000 |  |  | N/A |  | Replace camera and security equipment
54 | 51070-00 | Wall framing | Replace damaged framing in gable ends | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Replace damaged framing in gable ends
69 | 51077-00 | Repair patio/balcony railings | Patio fence repairs | GC | Year 1 | 48000 | 48000 |  |  | 0 |  | Patio fence repairs
71 | 51075-00 | Expansion Joints | Replace stucco expansion joints | GC | Year 1 | 48000 | 48000 |  |  | 0 |  | Replace stucco expansion joints
24 | 51043-00 | Landscaping | Tree trim Equity PCA Item 3.2.4- $5,000- Overgrown tress were observed throughout the subject property. Many of the overgrown trees have extended over the roofline, which has resulted in accumulation of tree leaf debris on the roofing systems. No portion of any trees should be in contact with the building exterior or roof line. It is recommended that the trees be trimmed back. | GC | Year 1 | 42000 | 42000 |  |  | 0 |  | Tree trim Equity PCA Item 3.2.4- $5,000- Overgrown tress were observed throughout the subject property. Many of the overgrown trees have extended over the roofline, which has resulted in accumulation
22 | 51091-00 | Sidewalks | Replace trip hazards Lender PCR Item- $3,000- Sidewalks were observed to have uneven edges, resulting in trip hazards. These conditions were specifically observed by Units: 1320-215, 1310-126, 1310-124, 1310-118, and by Buildings 1360 and 1350. Equity PCA Item 3.2.3- $25,000- Potential trip hazards consisting of vertical and horizontal separation were present throughout the site. Sectional replacement or grinding is recommended as necessary. | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | Replace trip hazards Lender PCR Item- $3,000- Sidewalks were observed to have uneven edges, resulting in trip hazards. These conditions were specifically observed by Units: 1320-215, 1310-126, 1310-12 | [5 empty] | 2025-04-19
68 | 51070-00 | Replace equipment screen | PCA 4.4.1 - Replace equipment screen | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | PCA 4.4.1 - Replace equipment screen
23 | 51046-00 | Landscape irrigation | Inspect and repair irrigation | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | Inspect and repair irrigation
40 | 51029-00 | Playground | Fall zone on 4 playgrounds, misc equipment repairs and replacements | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Fall zone on 4 playgrounds, misc equipment repairs and replacements
134 | 51160-06 | Clubhouse / Office Furniture | Clubhouse Furniture | Capex | Year 1 | 30000 | 0 |  |  | N/A |  | Clubhouse Furniture
81 | 51071-00 | Gutters & downspouts | Clean and repair gutters | GC | Year 1 | 29274 | 29274 |  |  | 0 |  | Clean and repair gutters
162 | 51140-00 | Electrical distribution | Inspect and repair lighting controllers on all buildings Contingency for electrical panel upgrades/replacements starting yr 4 - $25,000 Equity PCA Item 5.3- $2,500- Several electrical boxes were observed missing cover plates. Due to the life safety nature of this condition, installation of cover plates at all electrical boxes is recommended. $27,500 total | GC | Year 1 | 27500 | 25000 |  |  | 1 |  | Inspect and repair lighting controllers on all buildings Contingency for electrical panel upgrades/replacements starting yr 4 - $25,000 Equity PCA Item 5.3- $2,500- Several electrical boxes were obser
80 | 51062-00 | Roofing Maintenance | PCA 4.4.1 All roof sections: Annual maintenance | GC | Year 1 | 25243 | 24840 |  |  | 1 |  | PCA 4.4.1 All roof sections: Annual maintenance
55 | 51072-00 | Repair exterior stair treads and stringers | Secure railings | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Secure railings
56 | 51072-00 | Repair balcony framing & decking | Balcony Decking | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Balcony Decking
82 | 51062-00 | Flashing | Replace damaged flashing | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Replace damaged flashing
83 | 51062-00 | Sealants & caulking | Seal transition to stucco from siding | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Seal transition to stucco from siding
18 | 51130-00 | Storm sewer piping | Clean storm drains | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | Clean storm drains
19 | 51053-00 | Stripe parking areas | Restripe parking lot | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | Restripe parking lot
60 | 51076-00 | Repair masonary fence | PCA 4.2 - Remediation and/or sectional replacement of masonry perimeter fence. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | PCA 4.2 - Remediation and/or sectional replacement of masonry perimeter fence.
61 | 51090-00 | Repair concrete stairs | PCA 4.2 - Repair or replace damaged concrete treads at stairs. | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | PCA 4.2 - Repair or replace damaged concrete treads at stairs.
63 | 51070-00 | Repair exposed wood beams | PCA 4.2 -Remediate wood deterioration of exterior exposed wood beams and vertical braces | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | PCA 4.2 -Remediate wood deterioration of exterior exposed wood beams and vertical braces
123 | 51993-00 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | Capex | Year 1 | 14129 | 14102 |  |  | N/A |  | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods
59 | 51070-00 | Replace damaged wood | PCA 4.2 -Allowance for replacement of damaged wood framing during exterior cladding replacement. | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | PCA 4.2 -Allowance for replacement of damaged wood framing during exterior cladding replacement.
65 | 51075-00 | Replace deteriorated roof-lines | PCA 4.4.1 - Replace deteriorated wood siding at roof-lines | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | PCA 4.4.1 - Replace deteriorated wood siding at roof-lines
66 | 51062-00 | Replace roof hatch | PCA 4.4.1 - Replace roof hatch and install safety railing | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | PCA 4.4.1 - Replace roof hatch and install safety railing
122 | 52111-00 | Deferred Maintenance - Remove Mold | Lender PCR Item- $6,000- Mold was observed in the bathrooms of many units. The units include the following: Unit 1350-521 bathtub areas; Unit 1360-630 bathtub areas; Unit 1395-724 bathtub areas and wall; Unit 1425-754 bathtub areas; Unit 1330-327 bathtub areas, walls, and ceiling; Unit 1350-540 bathtub areas; Unit 2525-903 bathtub areas; Unit 1410-804 bathtub areas. | PMC | Year 1 | 6000 | 6133 |  |  | N/A |  | Lender PCR Item- $6,000- Mold was observed in the bathrooms of many units. The units include the following: Unit 1350-521 bathtub areas; Unit 1360-630 bathtub areas; Unit 1395-724 bathtub areas and wa | [5 empty] | 2025-04-19
166 | 51993-01 | Infrared Scan of Electrical Equipment | Equity PCA Item 5.3- $6,000- An infrared (IR) scan tag was observed at an electrical service entrance, the date on the tag indicated the last inspection was performed in August of 2023. IR scans can identify loose connections, load balance issues, defective breakers, and excessive circuit loads. NFPA 70B | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Equity PCA Item 5.3- $6,000- An infrared (IR) scan tag was observed at an electrical service entrance, the date on the tag indicated the last inspection was performed in August of 2023. IR scans can i
126 | 52111-00 | Down Units | Lender PCR Item- $5,500- At the time of the site visit, one (1) down unit (Unit 1350-513) was observed due to fire damage. | GC | Year 1 | 5500 | 5500 |  |  | 0 |  | Lender PCR Item- $5,500- At the time of the site visit, one (1) down unit (Unit 1350-513) was observed due to fire damage. | [5 empty] | 2025-04-19
57 | 51045-00 | Landscaping -Leasing office | PCA 4.1 -Leasing Office – Allowance for landscaping remediation at ledge extension | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | PCA 4.1 -Leasing Office – Allowance for landscaping remediation at ledge extension
58 | 51090-00 | Repair cracks in leasing office | PCA -4.1 - Leasing Office – Allowance for spalling and crack repairs at concrete slab ledge extension, and potential sectional replacement. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | PCA -4.1 - Leasing Office – Allowance for spalling and crack repairs at concrete slab ledge extension, and potential sectional replacement.
62 | 51070-00 | Inspect stair landing | PCA 4.2- Evaluate stair landing framing with borescope and replace any damaged framing, soffit material and rim joist as required. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | PCA 4.2- Evaluate stair landing framing with borescope and replace any damaged framing, soffit material and rim joist as required.
64 | 51074-00 | Replace skylight lens | PCA 4.4.1 -Replace deteriorated or capped skylight lens | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | PCA 4.4.1 -Replace deteriorated or capped skylight lens
67 | 51062-00 | Replace missing vent tops | PCA 4.4.1 - Replace missing vent tops | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | PCA 4.4.1 - Replace missing vent tops
164 | 51993-00 | Fire Alarm System | Lender PCR Item- $2,000- Repair the main fire alarm system which indicates "trouble" and perform the expired annual inspection on the main fire alarm panel. Equity PCA Item 5.5.2- $1,000- Current inspection tags were not observed at the main fire panel. Inspection and certification of the system by a qualified contractor is recommended. | PMC | Year 1 | 1000 | 4284 |  |  | N/A |  | Lender PCR Item- $2,000- Repair the main fire alarm system which indicates "trouble" and perform the expired annual inspection on the main fire alarm panel. Equity PCA Item 5.5.2- $1,000- Current insp | [5 empty] | 2025-04-19
PROJECTS subtotal (excl. contingency/CM fee)
170 | 51175-00 | Contingency | Contingency Amount | CON | Contingency | 351235 | 0 | 351235 |  | N/A |  | Contingency Amount
171 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 183884 | 123572 | 183884 |  | N/A |  | CM Fee

## Latitude at the Commons
Latitude at the Commons — 2025 acq · GC pay app |  |  |  | Repair Reserve | Lender Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requiring | Lender Due Date | Reserve Used | Costs Basis
18 | 84204 | Asphalt Coating | Seal Coat parking lot | GC | Year 1 | 89000 | 26700 |  |  | 3 | 100% | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
34 | 84114 | Repair exterior stair treads and stringers | Stairs, Treads, and stringers are bare wood they are in good shape - need sealant | GC | Year 1 | 72000 | 21600 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
35 | 84104 | Repair balcony framing & decking | Landings and balconies are bare wood - need sealant | GC | Year 1 | 60000 | 18000 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
42 | 84101 | Exterior building | Corner to corner point of repaired areas. | GC | Year 1 | 54000 | 16200 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
17 | 84303 | Landscape Cleanup and Enhancements | Concept Walk - Tree trimming | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | No Spend Shown |  |  | Bidding Currently |  |  |  |  | GL PMC
40 | 84206 | Repair / replace cement fiber siding | Remove and replace buckling siding on 5 gable ends of buildings | GC | Year 1 | 46000 | 13800 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
25 | 84095 | Resurface swimming pool | Resurface Pool | GC | Year 1 | 45000 | 13500 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
54 | 83375 | Golf Cart | Concept Walk - not included in personal property list. Currently have 4 carts on site | Capex | Year 1 | 40000 | 0 |  |  | N/A |  | No Spend Shown | [7 empty] | GL PMC
46 | 83236 | Replace old smoke detectors | H - Majority of units. These devices have an EUL of 7-10. The majority of smoke detectors were of original installation. Replacement with combined CO/Smoke devices is okay if the existing central alarm system is compatible. | Capex | Year 1 | 32400 | 0 |  |  | N/A |  | H - Majority of units. These devices have an EUL of 7-10. The majority of smoke detectors were of original installation. Replacement with combined CO/Smoke devices is okay if the existing central alar | [7 empty] | GL PMC
31758 | 84211 | Fire Stops | Install fire stops in every unit | Capex | Year 1 | 28224 | 31758 |  |  | N/A | [9 empty] | GL PMC
48 | 84106 | Clean Dryer vents | Dryer Vent Cleaning | GC | Year 1 | 21600 | 6480 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
45 | 83304 | Flooring Repairs | H - Repair carpets with trip hazards in units 115, 118, 121, 123, 127, 128, 133, 212, 234, 432, 613, 625, 827, 914, 922, 1112, 1227. All of these are deemed to be tripping hazards. Stretch (temporary fix) or replace. | Capex | Year 1 | 20736 | 7314 |  |  | N/A |  | H - Repair carpets with trip hazards in units 115, 118, 121, 123, 127, 128, 133, 212, 234, 432, 613, 625, 827, 914, 922, 1112, 1227. All of these are deemed to be tripping hazards. Stretch (temporary | [7 empty] | GL PMC
51 | 84215 | Patio screening on remaining units | Concept Walk - Add patio screen doors | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Concept Walk - Add patio screen doors | [7 empty] | GL PMC
65 | 84210 | Add lighting | Concept Walk - exterior lighting is lacking, should supplement the existing lighting to ensure it's well lit at night | GC | Year 1 | 20000 | 6000 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
37 | 83439 | Gutters & downspouts | Clean and repitch gutters throughout property H - The roof and gutters at Garage G is damaged. | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
38 | 84102 | Sealants & caulking | Seal all seams on face nailed siding | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
19 | 84201 | Stripe parking areas | Stripe Parking Lots | GC | Year 1 | 12000 | 3600 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
22 | 84204 | Pavement | Crack fill large crack running in the center of the drive aisle LPCA - Localized cracking was observed in the center of the drive aisles. Repairs are recommended | GC | Year 1 | 12000 | 3600 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  | 2026-12-20 |  | GC (pay app)
43 | 84105 | Repair / replace wood trim | Replace rotted wood | GC | Year 1 | 12000 | 3600 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
24 | 84517 | Erosion control | Concept Walk - Required in two separate locations per management. They are currently digging a trench to release, however, a more permanent solution would rip/rap or concrete flume | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
26 | 84360 | Swimming pool furniture | Concept Walk - Pool umbrellas | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | Concept Walk - Pool umbrellas | [7 empty] | GL PMC
21 | 83520 | ADA parking & curb cuts | Need ADA signage and poles LPCA - ADA compliant parking spaces are required to have a sign with the International Symbol of Accessibility at the head of each space. It did not appear that ADA-compliant signage was provided at ADA parking spaces. Installation of compliant signage is recommended. Also, ADA compliant parking spaces are required to have an adjacent access aisle. Access aisles were not observed at the accessible parking spaces. | PMC | Year 1 | 9000 | 3600 |  |  | N/A |  | Need ADA signage and poles LPCA - ADA compliant parking spaces are required to have a sign with the International Symbol of Accessibility at the head of each space. It did not appear that ADA-complia | [5 empty] | 2026-12-20 |  | GL PMC
63 | 84210 | Electrical Distribution | Repair timers or photo cells | GC | Year 1 | 9000 | 2700 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
27 | 84111 | Dumpster enclosures | Paint Enclosures | GC | Year 1 | 7500 | 2250 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
20 | 84115 | Sidewalks | Sidewalk Repairs Sunken and uplifted sidewalks at the front of buildings | GC | Year 1 | 5200 | 1560 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
66 | 84210 | LED Upgrade - Exterior Common Area Lighting | Hillmann Green Energy Audit - EEM No. 7 | PMC | Year 1 | 4546 | 2222 |  |  | N/A |  | Hillmann Green Energy Audit - EEM No. 7 | [7 empty] | GL PMC
56 | 84476 | Domestic Hot Water Heater | Rust damage on the DHW heater for units 522, 925, and 1217 | GC | Year 1 | 4485 | 1346 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
49 | 84304 | Window Repairs | H - Windows in units 137, 213, and 417 are in need of repair. | PMC | Year 1 | 2097 | 646 |  |  | N/A |  | H - Windows in units 137, 213, and 417 are in need of repair. | [7 empty] | GL PMC
23 | 84115 | Flatwork Repairs | LPCA (PR-90) - Two vertical-separation trip hazards were observed. One was at the north entrance to the breezeway of Building 2175, and another was at the curb cut by Building 2184. Repairs are recommended. | PMC | Year 1 | 1000 | 503 |  |  | N/A |  | LPCA (PR-90) - Two vertical-separation trip hazards were observed. One was at the north entrance to the breezeway of Building 2175, and another was at the curb cut by Building 2184. Repairs are recomm | [5 empty] | 2026-03-20 |  | GL PMC
41 | 84120 | Breezeway Missing/Exposed Nails | Breezeway at building missing/exposed nails on the stairway for building 2184 and 2210 | GC | Year 1 | 1000 | 300 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
64 | 84239 | Exit Sign | Exit sign is damaged at 2210 and 2175 buildings | GC | Year 1 | 376 | 113 |  |  | 3 |  | Mobilization Paid |  |  | CM needs to verify final |  |  |  |  | GC (pay app)
47 | 83236 | Replace Smoke Detectors in observed units | H - Smoke detectors missing in units: 212, 234, 726, 1021, 1114 | PMC | Year 1 | 375 | 150 |  |  | N/A |  | H - Smoke detectors missing in units: 212, 234, 726, 1021, 1114 | [7 empty] | GL PMC
50 | 83212 | Missing Kitchen cabinet drawer front | H - Unit 117 has missing drawer front in kitchen | PMC | Year 1 | 200 | 150 |  |  | N/A |  | H - Unit 117 has missing drawer front in kitchen |  |  | PMC had maintenance execute |  |  |  |  | GL PMC
PROJECTS subtotal (excl. contingency/CM fee)
68 | 84510 | Contingency | Contingency Amount | CON | Contingency | 271880 | 0 | 271880 |  | N/A |  | Contingency Amount
69 | 85305 | Construction Management Fee | CM Fees | CMF | CM Fee | 50381 | 0 | 50381 |  | N/A |  | CM Fees

## Oak Park Monrovia
Oak Park Monrovia — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
175 | 51140-00 | Electrical Distribution Center and Unit Electrical P | PCA 3.3.3 Exterior electrical service and distribution equipment was generally from the original construction and approximately 48 years old. Main service and branch service equipment have an EUL ranging from 40 to 50-years. Unit amperage was 40-amps, which is below the typical required amperage per unit of 60-amps. Additionally, the original equipment was manufactured by Federal Pacific Electric (FPE). This manufacturer is no longer in business and replacement parts are unavailable. Additionally, equipment from the manufacturer has a problematic history with various safety issues noted, such as circuit breakers failing to trip under overload conditions, poor connections leading to overheating, and susceptibility to corrosion. Based on EUL and the known problematic history of the equipment, replacement of the FPE electrical service and distribution equipment and breaker panels is recommended. | GC | Year 1 | 360000 | 108000 |  |  | 3 |  | PCA 3.3.3 Exterior electrical service and distribution equipment was generally from the original construction and approximately 48 years old. Main service and branch service equipment have an EUL rang | [5 empty] | 2026-07-31
96 | 51080-00 | Exterior building | Paint Exterior of Property (incl. Parking Garages) | GC | Year 1 | 234000 | 70200 |  |  | 3 |  | Paint Exterior of Property (incl. Parking Garages) | [5 empty] | 2026-08-08
70 | 51072-00 | Repair balcony framing & decking | DPCA 3.2.7 / EPCA 4.5 Select balconies at the buildings were observed to have deteriorated wood members at the balcony decking, railing and ornamental trellis throughout the property. Structural distress was observed at the balcony beam of Unit 119 at the North Building, which appeared to result in cracking of the interior wall within the bedroom of the unit. Property management report the balconies have been in the process of being repaired/rebuilt since 2022. According to property management, balcony repairs at nine units (North: 219, 224, 315, 319, and 324; South: 204, 216, 219, and 324) in 2022. Additional repairs/rebuilds were reportedly performed prior to this. A total list of the repaired balconies has been requested; however, as of the date this report was prepared, documentation was not provided. It was also reported that select balconies were planned to be repaired/rebuilt; however, specific details regarding this work were not provided. Survey and as needed repair of a portion of balconies is recommended. | GC | Year 1 | 140000 | 42000 |  |  | 3 |  | DPCA 3.2.7 / EPCA 4.5 Select balconies at the buildings were observed to have deteriorated wood members at the balcony decking, railing and ornamental trellis throughout the property. Structural distr | [5 empty] | 2026-08-08
95 | 51160-00 | Interior Hallway painting | Repair drywall and paint all interior hallways & Common Areas | GC | Year 1 | 94000 | 28200 |  |  | 3 |  | Repair drywall and paint all interior hallways & Common Areas
69 | 51077-00 | Repair patio/balcony railings | Repair/replace areas of rotted/failing wood railings on balconies. | GC | Year 1 | 75000 | 22500 |  |  | 3 |  | Repair/replace areas of rotted/failing wood railings on balconies.
46 | 51992-00 | Termite Remediation | Termite Remediation - tent and local treatment (per Ecola remediation proposal) | Capex | Year 1 | 57400 | 6685 |  |  | N/A |  | Termite Remediation - tent and local treatment (per Ecola remediation proposal) | [5 empty] | 2025-11-08
65 | 51070-00 | Roof framing | Inspect all mansard roofs and repair any damage to coping/façade of building to ensure areas are secure to prevent leaking. Will need to remove loose material from metal mansards and recoat. | GC | Year 1 | 47500 | 14250 |  |  | 3 |  | Inspect all mansard roofs and repair any damage to coping/façade of building to ensure areas are secure to prevent leaking. Will need to remove loose material from metal mansards and recoat.
93 | 51075-00 | Repair stucco | Repairs throughout property, also repair cement plaster at northeaster corner of western wing of parking garage. | GC | Year 1 | 40000 | 12000 |  |  | 3 |  | Repairs throughout property, also repair cement plaster at northeaster corner of western wing of parking garage.
168 | 51990-00 | Seismic shut off valve - install | DPCA 3.3.6 / EPCA 5.3 -The observed natural gas services lacked seismic shutoff valves to prevent dangerous gas leaks in the event of a line break during a significant seismic event. Installation of an automatic seismic shut-off device is recommended | GC | Year 1 | 39000 | 11700 |  |  | 3 |  | DPCA 3.3.6 / EPCA 5.3 -The observed natural gas services lacked seismic shutoff valves to prevent dangerous gas leaks in the event of a line break during a significant seismic event. Installation of a | [5 empty] | 2026-08-08
169 | 51120-00 | MAUs - Ventilation System | DPCA 3.3.1 / EPCA 5.2 The MAUs at each building were in poor overall condition. The unit at the North Building unit was inoperable. Replacement of both units is recommended | GC | Year 1 | 32000 | 9600 |  |  | 3 |  | DPCA 3.3.1 / EPCA 5.2 The MAUs at each building were in poor overall condition. The unit at the North Building unit was inoperable. Replacement of both units is recommended | [5 empty] | 2026-08-08
29 | 51043-00 | Landscaping | Tree trim - building clearance throughout property | Capex | Year 1 | 28500 | 13430 |  |  | N/A |  | Tree trim - building clearance throughout property
139 | 51160-00 | Common Area Greenspace Enhancements | Placeholder for greenspace improvements (e.g. dog park, bocce ball, etc.) | Capex | Year 1 | 24000 | 5162 |  |  | N/A |  | Placeholder for greenspace improvements (e.g. dog park, bocce ball, etc.)
177 | 51141-00 | Common area light fixtures | Replace all patio lighting with new LED lighting. | GC | Year 1 | 23500 | 7050 |  |  | 3 |  | Replace all patio lighting with new LED lighting.
76 | 51060-00 | Asphalt composite shingle roofing | Repair and add proper flashing to the roofing of the ganged mains and meter bank closets. | GC | Year 1 | 21500 | 6450 |  |  | 3 |  | Repair and add proper flashing to the roofing of the ganged mains and meter bank closets.
26 | 51086-00 | Erosion control | Fill areas of erosion around buildings and flower beds throughout property. Specifically areas that have exposed PVC irrigation lines. Regrade soil at east side of south side building to prevent moisture/termite infestation. | GC | Year 1 | 17500 | 5250 |  |  | 3 |  | Fill areas of erosion around buildings and flower beds throughout property. Specifically areas that have exposed PVC irrigation lines. Regrade soil at east side of south side building to prevent moist
178 | 51141-00 | Replace garage lighting | Replace existing garage lighting with LED. | GC | Year 1 | 15000 | 4500 |  |  | 3 |  | Replace existing garage lighting with LED.
15 | 51045-00 | Landscape Cleanup and Enhancements | DPCA 3.1.4 / EPCA 3.2.4 - Landscape areas were observed to be eroded with exposed irrigation lines at significant areas surrounding the buildings. Proper top cover should be installed to prevent erosion and protect the exposed PVC lines to prevent damage. | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | DPCA 3.1.4 / EPCA 3.2.4 - Landscape areas were observed to be eroded with exposed irrigation lines at significant areas surrounding the buildings. Proper top cover should be installed to prevent erosi | [5 empty] | 2026-08-08
157 | 51134-00 | Hydro-jetting & Camera inspection | PCA 5.1 -It appears that no hydro-jetting and camera inspection has been performed at the property. Industry best practices typically clearing sanitary waste lines every 18- to 24-months. | Capex | Year 1 | 10000 | 7424 |  |  | N/A |  | PCA 5.1 -It appears that no hydro-jetting and camera inspection has been performed at the property. Industry best practices typically clearing sanitary waste lines every 18- to 24-months.
155 | 51130-00 | Stormwater sump pump system, replace | PCA 3.3.4. It was observed that the South Building parking garage had failed, and control panel could not be energized after some effort from the maintenance supervisor. One system in the South Garage has failed. Replacement is recommended. PCA 5.1 - The stormwater sump pump system at the South Building parking garage had failed, and control panel could not be energized after some effort from the maintenance supervisor. Repair or replacement of the stormwater sump pump system is recommended | GC | Year 1 | 8800 | 2640 |  |  | 3 |  | PCA 3.3.4. It was observed that the South Building parking garage had failed, and control panel could not be energized after some effort from the maintenance supervisor. One system in the South Garage | [5 empty] | 2026-08-08
45 | 51180-00 | Mold Remediation | Mold Remediation | PMC | Year 1 | 6000 | 8355 |  |  | N/A |  | Mold Remediation
44 | 51172-00 | Carports / Garages | Repair damaged coating in parking structure at spots 65, 66 and 68. Also, extend routed and repair expansion joint at ramp. PCA 3.2.9 -Garage Traffic Coating, Reapply | GC | Year 1 | 5250 | 1575 |  |  | 3 |  | Repair damaged coating in parking structure at spots 65, 66 and 68. Also, extend routed and repair expansion joint at ramp. PCA 3.2.9 -Garage Traffic Coating, Reapply
126 | 51030-00 | Signage - Building identification | Adding signage to locate the leasing office - specifically on the North Building to guide tenants to the South Building more easily | PMC | Year 1 | 5000 | 1100 |  |  | N/A |  | Adding signage to locate the leasing office - specifically on the North Building to guide tenants to the South Building more easily
154 | 51130-00 | Water pressure regulator / back-flow preventer | Install backflow prevention device at north building. Currently leaking. | GC | Year 1 | 2000 | 600 |  |  | 3 |  | Install backflow prevention device at north building. Currently leaking.
147 | 51140-00 | Smoke and Fire Detection System, central panel | PCA 3.3.10: Current inspection tags were not observed on the main control panel, building panels or elevator panels. Inspection and certification of the fire alarm system by a qualified contractor is recommended. | PMC | Year 1 | 1500 | 403 |  |  | N/A |  | PCA 3.3.10: Current inspection tags were not observed on the main control panel, building panels or elevator panels. Inspection and certification of the fire alarm system by a qualified contractor is | [5 empty] | 2026-02-08
PROJECTS subtotal (excl. contingency/CM fee)
184 | 51175-00 | Contingency | Construction Contingency | CON | Contingency | 90693 | 0 | 90693 |  | N/A |  | Construction Contingency
185 | 51190-00 | Construction Management Fee | CM Fees | CMF | CM Fee | 69407 | 17691 | 69407 |  | N/A |  | CM Fees

## Orchard Glen
Orchard Glen — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
52 | 51075-00 | Repair / replace wall shake shingles | Post cost is inclusive of dry rot repair Replace shake siding, T111 and window wall siding and repair textured siding | GC | Year 1 | 921600 | 921600 |  |  | 0 |  | Post cost is inclusive of dry rot repair Replace shake siding, T111 and window wall siding and repair textured siding
53 | 51080-00 | Exterior building paint | Exterior Painting | GC | Year 1 | 433550 | 496173 |  |  | 0 |  | Exterior Painting
48 | 51071-00 | Gutters & downspouts | Gutters & Downspout Repairs | GC | Year 1 | 244800 | 244800 |  |  | 0 |  | Gutters & Downspout Repairs
95 | 51990-00 | Green Up Program | Domestic Hot Water - Gas Tank Heater - Large, (0.95 TE), Qty 12, Apartments | Capex | Year 1 | 187200 | 187200 |  |  | N/A |  | Domestic Hot Water - Gas Tank Heater - Large, (0.95 TE), Qty 12, Apartments
35 | 51992-00 | WDO Treatment/Repairs | LPCA - Subsequent to thesite visit,managementprovided a WDOinspection reportconducted on 4/29/25 by TerminixInternational.Their findingsindicate thepresence of drywood termites andfungus/dry rot,and further investigation isneeded. These onditions werefound throughoutthe property, andtreatment andremoval, andreplacement ofdamagedmaterials arerecommended. | Capex | Year 1 | 160000 | 34150 |  |  | N/A |  | LPCA - Subsequent to thesite visit,managementprovided a WDOinspection reportconducted on 4/29/25 by TerminixInternational.Their findingsindicate thepresence of drywood termites andfungus/dry rot,and f | [5 empty] | 2025-06-20
54 | 51082-00 | Repair / replace wood trim | EPCA 4.4.1 - Contingency for replacement of damaged wood decking and fascia during the first phase of roof replacements; estimated at 20% of total roof area.Contingency for replacement of damaged wood decking and fascia during the second phase of roof replacements; estimated at 20% of total roof area. EPCA 4.2 - The exposed ends of some of the exterior wood beam extensions were noted with deterioration associated with water damage from roof drainage. Remediation of exposed wood beams exhibiting deterioration LPCA - many of the buildings' exterior finishes are showing signs of deterioration, such as dry rot in the plywood exterior siding, missing or damaged wood shingles, limited dry rot windor wood trims, and most of the door wood trims to the water heater room have dry rot. Remove all damaged materials and replace them with new ones to match. | GC | Year 1 | 151200 | 151200 |  |  | 0 |  | EPCA 4.4.1 - Contingency for replacement of damaged wood decking and fascia during the first phase of roof replacements; estimated at 20% of total roof area.Contingency for replacement of damaged wood | [5 empty] | 2025-06-20
18 | 51053-00 | Asphalt Coating | EPCA 3.2.2 - The asphalt seal coat and pavement markings and striping appeared to be in fair to poor condition. The seal coat and striping appeared to be largely faded throughout the site. Partner recommends application of the seal coat and striping with localized repairs at this time. | GC | Year 1 | 121000 | 43650 |  |  | 3 |  | EPCA 3.2.2 - The asphalt seal coat and pavement markings and striping appeared to be in fair to poor condition. The seal coat and striping appeared to be largely faded throughout the site. Partner rec
99 | 51990-00 | Green Up Program | Water Fixture - WaterSense Certified Toilets, (0.8 gpf), Qty 240, 75% of Total Toilets | Capex | Year 1 | 108960 | 108960 |  |  | N/A |  | Water Fixture - WaterSense Certified Toilets, (0.8 gpf), Qty 240, 75% of Total Toilets
17 | 51045-00 | Landscape Cleanup and Enhancements | EPCA 4.4.1 - Cut back trees in contact with roofs. Initial tree trim, landscape cleanup, entry and tour path enhancements, etc | GC | Year 1 | 100000 | 6720 |  |  | 4 |  | EPCA 4.4.1 - Cut back trees in contact with roofs. Initial tree trim, landscape cleanup, entry and tour path enhancements, etc
46 | 51061-00 | Asphalt composite shingle roofing | EPCA 4.4.1 - Replacement of half of the shingled roofs within the next year. EPCA 4.4.1 - Replacement of half of the shingled roofs within the next two years. Roof Tune Up Only | GC | Year 1 | 80000 | 54500 |  |  | 2 |  | EPCA 4.4.1 - Replacement of half of the shingled roofs within the next year. EPCA 4.4.1 - Replacement of half of the shingled roofs within the next two years. Roof Tune Up Only
28 | 51085-00 | Retaining walls | The retaining walls appeared to be in fair condition. The walls appeared to exhibit lateral movement (leaning) and separation along the length of the wall. Based on the observed condition, replacement of the leaning retaining wall appears warranted and is recommended at this time. | GC | Year 1 | 62900 | 62900 |  |  | 0 |  | The retaining walls appeared to be in fair condition. The walls appeared to exhibit lateral movement (leaning) and separation along the length of the wall. Based on the observed condition, replacement
29 | 51023-00 | Resurface swimming pool | Pool Resurfacing | GC | Year 1 | 51000 | 30600 |  |  | 2 |  | Pool Resurfacing
39 | 51070-00 | Wall framing | replace damaged framing in chimney | GC | Year 1 | 48000 | 48000 |  |  | 0 |  | replace damaged framing in chimney
47 | 51062-00 | Repairs to roof systems | EPCA 4.4.1 - Immediate repairs to roof system to maintain water-tightness leading up to replacement. Immediate Repairs to Roof System during overall building tune up. | GC | Year 1 | 45000 | 45000 |  |  | 0 |  | EPCA 4.4.1 - Immediate repairs to roof system to maintain water-tightness leading up to replacement. Immediate Repairs to Roof System during overall building tune up.
38 | 51072-00 | Concrete deck / floor fill | repair and paint balconies | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | repair and paint balconies
30 | 51076-00 | Fences & gates - swimming pool | Swimming Pool Gate Repairs | GC | Year 1 | 38000 | 38000 |  |  | 0 |  | Swimming Pool Gate Repairs
50 | 51062-00 | Flashing | Flashing Repairs | GC | Year 1 | 38000 | 38000 |  |  | 0 |  | Flashing Repairs
25 | 51091-00 | Sidewalks | LPCA - limited sidewalk cracks were observed by the west playground equipment LPCA (PR-90) - a limited concrete sidewalk section was observed by Unit 3959-277 that is heaved and cracked causing a trip hazard | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | LPCA - limited sidewalk cracks were observed by the west playground equipment LPCA (PR-90) - a limited concrete sidewalk section was observed by Unit 3959-277 that is heaved and cracked causing a trip | [5 empty] | 2025-09-20
22 | 51172-00 | Carports / Garages | Repair carports and paint post and pearling EPCA 4.4.1 - Repair of impact damage to metal carport canopies. EPCA 3.2.9 - Damaged roof panels and carport support beams/posts from suspected vehicular impact were noted in several locations. Repair or replacement of the damaged components is recommended, as required | GC | Year 1 | 28000 | 16800 |  |  | 2 |  | Repair carports and paint post and pearling EPCA 4.4.1 - Repair of impact damage to metal carport canopies. EPCA 3.2.9 - Damaged roof panels and carport support beams/posts from suspected vehicular im
91 | 51131-00 | Stormwater Pipe Repair | Clean storm drains | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Clean storm drains
44 | 51070-00 | Expansion joints | Repair exterior expansion joints | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Repair exterior expansion joints
49 | 51062-00 | Sealants & caulking | Sealants and Caulking for Roof | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Sealants and Caulking for Roof
90 | 51120-00 | Split HVAC System (Move to HVAC) | EPCA 5.2 - The split heat pump system serving the clubhouse is more than 20 years old. Based on age and EUL, replacement of this system is anticipated. Both the indoor and outdoor unit should be replaced. | Capex | Year 1 | 24000 | 3786 |  |  | N/A |  | EPCA 5.2 - The split heat pump system serving the clubhouse is more than 20 years old. Based on age and EUL, replacement of this system is anticipated. Both the indoor and outdoor unit should be repla
23 | 51053-00 | Stripe parking areas | Striping of Parking Lots | GC | Year 1 | 23000 | 6900 |  |  | 3 |  | Striping of Parking Lots
93 | 51130-00 | Natural Gas Seismic Shutoff | EPCA 5.3 - Seismic shut-off valves were not installed on the natural gas services. The property is located in a seismic zone and installation of shut-off valves is recommended. | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | EPCA 5.3 - Seismic shut-off valves were not installed on the natural gas services. The property is located in a seismic zone and installation of shut-off valves is recommended.
57 | 52111-00 | Down Units | EPCA 6.5.2 - At the time of the site assessment, one residential unit (Unit 142) was identified to be in an un-rentable/down condition. According to property management, the entire unit suffered severe smoke damage associated with a fire. Some portions of the unit also suffered physical damage associated with the flames. Per property management, the entire unit was gutted down to the studs for a complete refurbishment. At the time of the site assessment, drywall had been added and bathroom fixtures had also been added. Property management indicated that the subject property was awaiting the finalization of permits to complete the unit refurbishment. Renovation of the unit to a rentable status is warranted. LPCA (PR-90) - Unit 142 is the only down unit. A resident caused a fire in Sep. 2024 | Capex | Year 1 | 20000 | 35021 |  |  | N/A |  | EPCA 6.5.2 - At the time of the site assessment, one residential unit (Unit 142) was identified to be in an un-rentable/down condition. According to property management, the entire unit suffered sever | [5 empty] | 2025-09-20
98 | 51990-00 | Green Up Program | Water Fixture - WaterSense Certified Showerheads, (1.25 gpm), Qty 294, 92% of Total Showerheads | Capex | Year 1 | 19110 | 19110 |  |  | N/A |  | Water Fixture - WaterSense Certified Showerheads, (1.25 gpm), Qty 294, 92% of Total Showerheads
42 | 51077-00 | Balconies/handrails/guardrails | Patio fence repairs and paint EPCA 4.2 - Elevated balconies and walkways are provided with wood guardrails, where posts are connected to the rim boards with bolted anchorage. Some connection locations were noted with unconventional repairs, and others were noted to be failing. Allowance for replacement/repair of failed wood guardrail post connections LPCA - Dry rot was observed in balcony areas and elevated walkways. These conditions were observed throughout the balconies and elevated walkways. Remove all damaged materials and replace them with new ones to match. | GC | Year 1 | 18000 | 72000 |  |  | 0 |  | Patio fence repairs and paint EPCA 4.2 - Elevated balconies and walkways are provided with wood guardrails, where posts are connected to the rim boards with bolted anchorage. Some connection locations | [5 empty] | 2025-06-20
34 | 51090-00 | Replacement of damaged concrete treads at stairs | EPCA 4.2 - The concrete stair treads were noted with cracks (varying degrees) and spalling areas with exposed steel reinforcement. | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | EPCA 4.2 - The concrete stair treads were noted with cracks (varying degrees) and spalling areas with exposed steel reinforcement.
40 | 51072-00 | Balcony framing & decking | Repair balcony framing & decking | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Repair balcony framing & decking
89 | 51130-00 | Back-flow preventer | EPCA 5.1 - The two 6" reduced pressure backflow prevention devices appear to be original and should be replaced. Annual inspections are recommended as part of routine maintenance thereafter. | Capex | Year 1 | 16000 | 25479 |  |  | N/A |  | EPCA 5.1 - The two 6" reduced pressure backflow prevention devices appear to be original and should be replaced. Annual inspections are recommended as part of routine maintenance thereafter.
107 | 51140-00 | Electrical service and distribution, Ongoing Repalce | inspect and repair lighting controllers on all buildings | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | inspect and repair lighting controllers on all buildings
20 | 51026-00 | Repair / replace swimming pool pumps | Pool Pumps | GC | Year 1 | 6800 | 4080 |  |  | 2 |  | Pool Pumps
27 | 51076-00 | Fences & gates - site perimeter | EPCA 3.2.7 - Damage/deterioration of the metal security perimeter fencing and the welded steel pool fencing was noted in several locations as well. The deterioration/damage appeared to primarily consist of corrosion and was generally observed along the base of the metal fencing. Additional damage/deterioration was noted on several chain-link panels at the trash dumpster enclosures. Cracked and missing concrete was observed in several areas along the concrete perimeter wall causing the exposure of the underlying metal structural rebar. Repair of the fencing and concrete wall is recommended. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | EPCA 3.2.7 - Damage/deterioration of the metal security perimeter fencing and the welded steel pool fencing was noted in several locations as well. The deterioration/damage appeared to primarily consi
97 | 51990-00 | Green Up Program | Water Fixture - Bathroom Aerators, (0.5 gpm 100% Aerator Replacement), Qty 320, Apartments | PMC | Year 1 | 3200 | 3200 |  |  | N/A |  | Water Fixture - Bathroom Aerators, (0.5 gpm 100% Aerator Replacement), Qty 320, Apartments
96 | 51990-00 | Green Up Program | Water Fixture - Kitchen Aerators, (1.2 gpm 100% Aerator Replacement), Qty 288, Apartments | PMC | Year 1 | 2880 | 2880 |  |  | N/A |  | Water Fixture - Kitchen Aerators, (1.2 gpm 100% Aerator Replacement), Qty 288, Apartments
36 | 51992-00 | WDO Inspection | LPCA - Subsequent to the site visit, management provided a WDO inspection report conducted on 4/29/25 by Terminix International. Their findings indicate the presence of dry wood termites and fungus/dry rot, and further investigation is needed. These conditions were found throughout the property, and treatment and removal, and replacement of damaged materials are recommended. | PMC | Year 1 | 2000 | 2000 |  |  | N/A |  | LPCA - Subsequent to the site visit, management provided a WDO inspection report conducted on 4/29/25 by Terminix International. Their findings indicate the presence of dry wood termites and fungus/dr | [5 empty] | 2025-06-20
24 | 51091-00 | Repair ADA deficiencies | LPCA - No ADA access aisles were observed in three ADA parking spaces. No insulation under the common area restroom sink at the Leasing Office | GC | Year 1 | 1500 | 450 |  |  | 3 |  | LPCA - No ADA access aisles were observed in three ADA parking spaces. No insulation under the common area restroom sink at the Leasing Office | [5 empty] | 2025-09-20
56 | 52111-00 | Remove Microbial Growth | LPCA (PR-90) - CBRE observed microbial growth. Specifically, these conditions were observed at the bathtub of Unit 3873-1 and the bathroom of Unit 5-100. Affected, damaged porous materials should be removed and replaced to match existing finishes, and nonporous surfaces should be cleaned. | PMC | Year 1 | 1100 | 1100 |  |  | N/A |  | LPCA (PR-90) - CBRE observed microbial growth. Specifically, these conditions were observed at the bathtub of Unit 3873-1 and the bathroom of Unit 5-100. Affected, damaged porous materials should be r | [5 empty] | 2025-09-20
21 | 51076-00 | Fences & gates - patios | EPCA 3.2.3 - The ground floor patio fence (wood guardrail) located between Units 85 and 87 was noted to be leaning outward with connection failure. The fence was noted with separation at the median connection point between the perimeter fence and the perpendicular demising wall. Prior attempted repairs were | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | EPCA 3.2.3 - The ground floor patio fence (wood guardrail) located between Units 85 and 87 was noted to be leaning outward with connection failure. The fence was noted with separation at the median co
33 | 51070-00 | Replacement of metal standoff post bases | EPCA 4.2 - The metal standoff bases at the wood walkway and stair posts near Unit 169 were exhibiting corrosion and potential steel connection failure. | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | EPCA 4.2 - The metal standoff bases at the wood walkway and stair posts near Unit 169 were exhibiting corrosion and potential steel connection failure.
58 | 52111-00 | Damaged Ceiling | LPCA (PR-90) - During an additional inspection conducted by the Lender, ceiling damage and possible water intrusion were observed in the bathroom ceiling at Unit 9-204. CBRE recommends that management verify that the water intrusion, if caused by leaking from above, has been repaired. In addition, the damaged ceiling drywall should be removed and replaced with new materials and match existing finishes. | PMC | Year 1 | 700 | 700 |  |  | N/A |  | LPCA (PR-90) - During an additional inspection conducted by the Lender, ceiling damage and possible water intrusion were observed in the bathroom ceiling at Unit 9-204. CBRE recommends that management | [5 empty] | 2025-09-20
19 | 51091-00 | Accessibility | EPCA 7.1 - The leasing office restroom lacked scald protection at the exposed lavatory piping. Installation is recommended. EPCA 7.1 - The leasing office restroom lacked a rear grab bar. Installation of a rear grab bar is recommended. | GC | Year 1 | 400 | 400 |  |  | 0 |  | EPCA 7.1 - The leasing office restroom lacked scald protection at the exposed lavatory piping. Installation is recommended. EPCA 7.1 - The leasing office restroom lacked a rear grab bar. Installation
59 | 51992-00 | Roach Treatment | LPCA (PR-90) - During an additional inspection conducted by the Lender, evidence of roaches was observed in Unit 1-10. CBRE recommends that treatment for roaches be completed and the area cleaned at this time. | PMC | Year 1 | 350 | 120 |  |  | N/A |  | LPCA (PR-90) - During an additional inspection conducted by the Lender, evidence of roaches was observed in Unit 1-10. CBRE recommends that treatment for roaches be completed and the area cleaned at t | [5 empty] | 2025-09-20
PROJECTS subtotal (excl. contingency/CM fee)
111 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 174700 | 119663 | 174700 |  | N/A |  | CM Fee
110 | 51180-00 | Contingency | Contingency Amount | CON | Contingency | 166381 | 0 | 166381 |  | N/A |  | Contingency Amount

## Paddock Club
Paddock Club — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
18 | 84204 | Asphalt Coating | Crack fill and double seal coat asphalt throughout property. Lender PCA Item- Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present at the drive aisles in isolated locations throughout the subject property typical of the conditions noted near Building 21. Repairs are recommended. | GC | Year 1 | 425000 | 425000 |  |  | 0 |  | Crack fill and double seal coat asphalt throughout property. Lender PCA Item- Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present at the driv | [5 empty] | 1900-12-30
23 | 84303 | Landscaping | Tree trim around property, especially around the lake. Clean up of brush foliage around lakes, as well. 1st call bidding in conjunction with Fairways for better pricing | GC | Year 1 | 125000 | 125000 |  |  | 0 |  | Tree trim around property, especially around the lake. Clean up of brush foliage around lakes, as well. 1st call bidding in conjunction with Fairways for better pricing
77 | 84105 | Repair / replace wood trim | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. Include ALL buildings throughout property. | GC | Year 1 | 95000 | 95000 |  |  | 0 |  | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. Include ALL buildings throughout property.
64 | 84433 | Asphalt composite shingle roofing | Moderate Roof Tune up on every building. This would include securing shingles, flashing, etc. Repairs of moderate water damange and patching leaks. If the damage is more extensive or needs full replacement, will need to do a change order. | GC | Year 1 | 75000 | 75000 |  |  | 0 |  | Moderate Roof Tune up on every building. This would include securing shingles, flashing, etc. Repairs of moderate water damange and patching leaks. If the damage is more extensive or needs full replac
75 | 84206 | Repair / replace cement fiber siding | Repair/replace areas of failed hardie board and paint to match throughout property | GC | Year 1 | 68500 | 68500 |  |  | 0 |  | Repair/replace areas of failed hardie board and paint to match throughout property
76 | 84206 | Repair / replace vinyl siding | Repair areas of damaged vinyl siding and clean vinyl covered in mold and grime throughout property. Also, secure vinyl soffit throughout property. | GC | Year 1 | 68500 | 68500 |  |  | 0 |  | Repair areas of damaged vinyl siding and clean vinyl covered in mold and grime throughout property. Also, secure vinyl soffit throughout property.
21 | 84205 | Fences & gates - site perimeter | Repair deck walkways/fencing throughout property. Some areas have broken stairs and missing areas of pickets. Railing repairs at walkway bridges to units- 3 buildings, 6 walkways with railing on each side | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Repair deck walkways/fencing throughout property. Some areas have broken stairs and missing areas of pickets. Railing repairs at walkway bridges to units- 3 buildings, 6 walkways with railing on each
120 | 84306 | Clubhouse / Office Furniture | Clubhouse Furniture | Capex | Year 1 | 50000 | 50000 |  |  | N/A |  | Clubhouse Furniture
124 | 84360 | Pool Furniture | New furniture and games needed | Capex | Year 1 | 50000 | 57216 |  |  | N/A |  | New furniture and games needed
159 | 84112 | Replace breezeway lights | Install LED pole lights on pre-existing posts throughout the propety | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Install LED pole lights on pre-existing posts throughout the propety
24 | 84095 | Resurface swimming pool | Resurface main pool at clubhouse. | GC | Year 1 | 42750 | 42750 |  |  | 0 |  | Resurface main pool at clubhouse.
20 | 84115 | Sidewalks | Repair cracked/broken sidewalks throughout property. | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Repair cracked/broken sidewalks throughout property.
133 | 84305 | Package Lockers | Look at adding to laundry room. Budget 1 locker per 4-5 units @$400/locker | Capex | Year 1 | 33600 | 13600 |  |  | N/A |  | Look at adding to laundry room. Budget 1 locker per 4-5 units @$400/locker
154 | 84217 | HVAC inspection and maintenance | Clean foliage around condensors and raise AC units with HVAC pads where needed. | GC | Year 1 | 33600 | 33600 |  |  | 0 |  | Clean foliage around condensors and raise AC units with HVAC pads where needed.
158 | 84112 | Common area light fixtures | Replace wallpacks on all buildings | GC | Year 1 | 28000 | 28000 |  |  | 0 |  | Replace wallpacks on all buildings
27 | 84105 | Pergola Court | Replace any damaged/rotted decking around the clubhouse and pool area. | GC | Year 1 | 26500 | 26500 |  |  | 0 |  | Replace any damaged/rotted decking around the clubhouse and pool area.
157 | 84210 | Electrical distribution | Electrical Distribution | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | Electrical Distribution
98 | 84106 | Clean Drier vents | Clean dryer vents throughout property. | GC | Year 1 | 25200 | 25200 |  |  | 0 |  | Clean dryer vents throughout property.
17 | 84201 | Stripe parking areas | Stripe Parking Lots | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Stripe Parking Lots
108 | 82131 | Co 2 detectors | Install Co2 detectors in each unit. Lender PCR Item- Due to the presence of gas-fire water heaters at each unit, carbon monoxide detectors are required. Installation of carbon monoxide detectors recommended. TAM to order and install on turn, PM inspections and WOs | Capex | Year 1 | 23520 | 0 |  |  | N/A |  | Install Co2 detectors in each unit. Lender PCR Item- Due to the presence of gas-fire water heaters at each unit, carbon monoxide detectors are required. Installation of carbon monoxide detectors recom | [5 empty] | 1900-12-30
26 | 84361 | Repair swimming pool deck | Clean pool deck, fill cracks and seal. Also, clean and resurface concreted steps going down to pool from clubhouse. | GC | Year 1 | 22500 | 22500 |  |  | 0 |  | Clean pool deck, fill cracks and seal. Also, clean and resurface concreted steps going down to pool from clubhouse.
16 | 84303 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | Capex | Year 1 | 20000 | 37500 |  |  | N/A |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
119 | 84208 | Clubhouse / Office Remodel | Placeholder budget, paint the blue framed wall areas - possibly use 1st call to renovate kitchen if budget permits | GC | Year 1 | 20000 | 16212 |  |  | 2 | 100% | Placeholder budget, paint the blue framed wall areas - possibly use 1st call to renovate kitchen if budget permits |  | Completed
122 | 84190 | Fitness Equipment | Replace broken items, add equipment- functional trainer, stair stepper | Capex | Year 1 | 18000 | 19675 |  |  | N/A |  | Replace broken items, add equipment- functional trainer, stair stepper
109 | 84239 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods | Capex | Year 1 | 16269 | 0 |  |  | N/A |  | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods
19 | 84221 | ADA parking & curb cuts | Lender PCA Item- Inadequate number of accessible parking and van accessible parking spaces at the leasing office. Installation of a van-accessible space is recommended at the leasing office. | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Lender PCA Item- Inadequate number of accessible parking and van accessible parking spaces at the leasing office. Installation of a van-accessible space is recommended at the leasing office. | [5 empty] | 1900-12-30
22 | 84434 | Retaining walls | Repair retaining walls where railroad ties are rotted out. Lender PCA Item- Damage was observed at a section of retaining wall along the north property perimeter. Repairs are recommended. 480 linear feet @ $100/ft = $48k | GC | Year 1 | 12500 | 48000 |  |  | 0 |  | Repair retaining walls where railroad ties are rotted out. Lender PCA Item- Damage was observed at a section of retaining wall along the north property perimeter. Repairs are recommended. 480 linear | [5 empty] | 1900-12-30
111 | 84431 | Hard turn/ renovation units | Lender PCA Item- Partner recommends completing the hard turn/ renovation in Units 130 and 281, which includes repair of any damaged finishes subsequent to the plumbing repairs discussed above. | Capex | Year 1 | 10000 | 17250 |  |  | N/A |  | Lender PCA Item- Partner recommends completing the hard turn/ renovation in Units 130 and 281, which includes repair of any damaged finishes subsequent to the plumbing repairs discussed above. | [5 empty] | 1900-12-30
123 | 84361 | Pool Area Remodel | Placeholder budget | Capex | Year 1 | 10000 | 5620 |  |  | N/A |  | Placeholder budget
137 | 84240 | Laundry Room Renovation | Replace fluorescent lights, clean fans and paint ceiling where needed, add TV - TAM to negotiate laundry contract to include laundry room refresh (flooring, paint, lights) | Capex | Year 1 | 10000 | 10000 |  |  | N/A |  | Replace fluorescent lights, clean fans and paint ceiling where needed, add TV - TAM to negotiate laundry contract to include laundry room refresh (flooring, paint, lights)
131 | 84275 | Access Control System | Add at maintenance shop. Fix system so that it can track which residents enter and leave, the manager said the system cannot track residents now | PMC | Year 1 | 8000 | 0 |  |  | N/A |  | Add at maintenance shop. Fix system so that it can track which residents enter and leave, the manager said the system cannot track residents now |  |  | Spend in other GL
29 | 84517 | Drainage | Add drainage in areas where water accumulates at base of retaining walls at building 17 | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Add drainage in areas where water accumulates at base of retaining walls at building 17
25 | 84361 | Replace swimming pool coping | Deck-O-Seal coping around pool. | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Deck-O-Seal coping around pool.
121 | 84190 | Fitness Center Remodel | Flooring and walls ok, misc allowance - update lighting in boxing closet to match main gym and add Tonal or equivalent with Yoga mats and replace speed bag. Organize main fitness area, add TRX and all in one. Remove old and damaged | PMC | Year 1 | 5000 | 5465 |  |  | N/A |  | Flooring and walls ok, misc allowance - update lighting in boxing closet to match main gym and add Tonal or equivalent with Yoga mats and replace speed bag. Organize main fitness area, add TRX and all
125 | 84203 | Picnic/Grill Area Remodel | Placeholder budget | PMC | Year 1 | 5000 | 8550 |  |  | N/A |  | Placeholder budget
126 | 84340 | Picnic/Grill Furniture | Placeholder budget | PMC | Year 1 | 5000 | 7950 |  |  | N/A |  | Placeholder budget
143 | 84209 | Plumbing Repairs | Lender PCR Item- Evidence of leaks and faulty piping was observed. According to the site escort, the piping leaks are repaired with PEX piping as needed. Ceiling leaks were observed in Units 1, 130, 146, and 281. Piping repairs and replacements are recommended. | PMC | Year 1 | 4800 | 76513 |  |  | N/A |  | Lender PCR Item- Evidence of leaks and faulty piping was observed. According to the site escort, the piping leaks are repaired with PEX piping as needed. Ceiling leaks were observed in Units 1, 130, 1 | [5 empty] | 2026-02-01
138 | 84240 | Laundry Room Furniture | Add seating | PMC | Year 1 | 4000 | 0 |  |  | N/A |  | Add seating
107 | 83465 | Water Damage in Units | Lender PCA Item- Partner recommends repair of any damaged finishes subsequent to the plumbing repairs in Units 1 and 146. | PMC | Year 1 | 3000 | 24082 |  |  | N/A |  | Lender PCA Item- Partner recommends repair of any damaged finishes subsequent to the plumbing repairs in Units 1 and 146. | [5 empty] | 1900-12-30
132 | 84260 | Mailboxes | Misc repairs - add concrete pad and USPS parcel boxes. | GC | Year 1 | 2000 | 4900 |  |  | 0 |  | Misc repairs - add concrete pad and USPS parcel boxes.
139 | 83265 | Office Computers | Have 2 new ones, budget for 1 new | PMC | Year 1 | 2000 | 13592 |  |  | N/A |  | Have 2 new ones, budget for 1 new
28 | 84103 | ADA Signage | Add ADA signage at clubhouse for wheelchair lift. | GC | Year 1 | 850 | 850 |  |  | 0 |  | Add ADA signage at clubhouse for wheelchair lift.
PROJECTS subtotal (excl. contingency/CM fee)
164 | 84510 | Contingency | Contingency Amount | CON | Contingency | 282911 | 0 | 282911 |  | N/A |  | Contingency Amount
165 | 84505 | Construction Management Fee | CM Fee | CMF | CM Fee | 92400 | 104484 | 92400 |  | N/A |  | CM Fee

## Rancho Cordova
Rancho Cordova — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
41 | 51080-00 | Exterior building | PNA - Repaint community EPCA - Budget to power wash and repaint the entire property. Property Management reported that touch-up painting has been performed as needed. Repeat every 7 years. Include the replacement of wood siding. The exterior walls were observed to be in fair-to-poor condition. LPCA - Repaint exterior walls, re-caulk, and minor repairs | GC | Year 1 | 188000 | 188000 |  |  | 0 |  | PNA - Repaint community EPCA - Budget to power wash and repaint the entire property. Property Manag
17 | 51050-00 | Asphalt Coating | Slurry Coat & Seal | GC | Year 1 | 64000 | 64000 |  |  | 0 |  | Slurry Coat & Seal
51 | 51140-00 | Replace electric panels | EPCA - Budget for phased replacement of the apartment Zinsco electrical distribution panels based on age and a recall due to a possible design flaw. | GC | Year 1 | 47500 | 47500 |  |  | 0 |  | EPCA - Budget for phased replacement of the apartment Zinsco electrical distribution panels based on age and a recall due to a possible design flaw.
25 | 51045-00 | Landscaping | PNA - Tree trim and branch removal EPCA - Trim trees throughout the site to prevent the accumulation of debris and tree leaves over the residential buildings. Numerous large trees are planted on site and projected over the roofs, touching the exteriors walls and leaving debris on the roofs. Tree trimming should occur every year. | Capex | Year 1 | 32000 | 0 |  |  | N/A |  | PNA - Tree trim and branch removal EPCA - Trim trees throughout the site to prevent the accumula
24 | 51076-00 | Patio and Fencing | EPCA - Repair areas of leaning wood patio enclosures as needed. Clean and restrain the fence with visible signs of deteriorated stain. LPCA - Patio and Fencing - Repair areas of leaning wood patio enclosures as needed. Clean and restrain the fence with visible signs of deteriorated stain. | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | EPCA - Repair areas of leaning wood patio enclosures as needed. Clean and restrain the fence with visible signs of deteriorated stain. LPCA - Patio and Fencing - Repair areas of leaning wood patio enc | [5 empty] | 2026-08-22
50 | 51141-00 | Replace Pole light fixtures | PNA - Pole lights throughout the parking lot LPCA - Replacement of pole lights throughout the parking area. | GC | Year 1 | 28500 | 28500 |  |  | 0 |  | PNA - Pole lights throughout the parking lot LPCA - Replacement of pole lights throughout the parking area. | [5 empty] | 2026-08-22
34 | 51062-00 | Modified bitumen membrane Roof Repairs | PNA - Clean flat roofs and repair minor areas of potential water intrusion | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | PNA - Clean flat roofs and repair minor areas of potential water intrusion
49 | 51141-00 | Common area light fixtures | PNA - Building wall packs LPCA - Budget for installation of building wall packs throughout the site. | GC | Year 1 | 18500 | 18500 |  |  | 0 |  | PNA - Building wall packs LPCA - Budget for installation of building wall packs throughout the site. | [5 empty] | 2026-08-22
21 | 51050-00 | Asphalt pavement | PNA - Remove and replace failing asphalt EPCA - Allowance to mill and overlay the driveway with heavy alligatoring. Observed on 40% of the asphalt pavement. LPCA - Driveways - Allowance to mill and overlay the driveway. | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | PNA - Remove and replace failing asphalt EPCA - Allowance to mill and overlay the driveway with heavy alligatoring. Observed on 40% | [5 empty] | 2026-08-22
32 | 51062-00 | Asphalt composite shingle roofing | PNA - Shingle roof tune up, loose and hanging shingles were observed EPCA - Budget for the replacement of the asphalt shingle roof systems on the various roof areas as they reach the end of their useful life during the term. The roofs were observed to be in fair to poor condition. | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | PNA - Shingle roof tune up, loose and hanging shingles were observed EPCA - Budget for the
39 | 51075-00 | Repair / replace wood siding | PNA - Replace rotted T1-11 ECPA - Survey the wood siding and soffits for dry rot damage and replace as necessary. Dry rot damage is visible at approximately 50% of the elevations with siding and soffits. LPCA - Address wood rot throughout the site identified in the WDI report. | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | PNA - Replace rotted T1-11 ECPA - Survey the wood siding and soffits for dry rot damage and replace as | [5 empty] | 2026-08-22
40 | 51075-00 | Repair stucco | PNA - Repair stucco, mansard/hip wall | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | PNA - Repair stucco, mansard/hip wall
47 | 52111-00 | Unit deferred maintenance | EPCA - Remediate select bathrooms with signs of organic growth observed in Units 16, 25, 35, 45, 61 & 70 LPCA - Unit 70 - Repairs dust/dirt on bathroom wall/ceiling. | Capex | Year 1 | 12500 | 11546 |  |  | N/A |  | EPCA - Remediate select bathrooms with signs of organic growth observed in Units 16, 25, 35, 45, 61 & 70 LPCA - Unit 70 - Repairs dust/dirt on bathroom wall/ceiling. | [5 empty] | 2026-02-22
18 | 51053-00 | Stripe parking areas | PNA - Stripe parking areas EPCA - Crack-fill linear cracks, slurry seal, and restripe asphaltic concrete paving throughout the site. To be completed on a 3 to 5 year cycle LPCA - Asphalt Pavement Sealcoat, Stripe and Minor Repairs, asphalt budgeted in future years | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | PNA - Stripe parking areas EPCA - Crack-fill linear cracks, slurry seal, and restripe asphaltic concret
29 | 51070-00 | Exterior Wall framing | Building Framing repairs | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Building Framing repairs
45 | 51993-00 | Smoke Alarm | EPCA - Budget to replace the existing smoke alarms based on age and useful life. The NFPA requires that smoke alarms not remain in service longer than 10 years from the date of manufacture. There are approximately 312 smoke alarms at the property based on the unit mix. | Capex | Year 1 | 10920 | 6568 |  |  | N/A |  | EPCA - Budget to replace the existing smoke alarms based on age and useful life. The NFPA requires that smoke alarms not remain in service longer than 10 years from the date of manufacture. There are
20 | 51091-00 | Sidewalks | PNA - Repair failing sidewalks EPCA - Budget to grind down the concrete walkways with any vertical displacement over 1/2" that presents a trip hazard as needed | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | PNA - Repair failing sidewalks EPCA - Budget to grind down the concrete walkways with
26 | 51029-00 | Playground equipment | PNA - Fall Zone Material | GC | Year 1 | 9800 | 9800 |  |  | 0 |  | PNA - Fall Zone Material
23 | 51076-00 | Fences & gates - site perimeter | PNA - Rough iron repairs EPCA - Budget for periodic painting of exterior ferrous metal components. Repeat every 3 to 5 years. | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | PNA - Rough iron repairs EPCA - Budget for periodic painting of exterior ferro
30 | 51090-00 | Expansion joints | Foundation Expansion Joint Repairs | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | Foundation Expansion Joint Repairs
36 | 51071-00 | Gutters & downspouts | PNA - Cleanout gutters and scuppers | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | PNA - Cleanout gutters and scuppers
42 | 51082-00 | Repair / replace wood trim | PNA - Repair/replace rotted trim | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | PNA - Repair/replace rotted trim
46 | 51993-00 | Fire Stops | Install Fire Stops | PMC | Year 1 | 8075 | 6119 |  |  | N/A |  | Install Fire Stops
27 | 51130-00 | Storm sewer piping | PNA - Clean out storm sewer catch basin | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | PNA - Clean out storm sewer catch basin
43 | 51075-00 | Repair/Replace Soffit | EPCA - Allowance to repair and replace all dry-rotted wood siding and soffits of the two-story residential buildings | GC | Year 1 | 6500 | 6500 |  |  | 0 |  | EPCA - Allowance to repair and replace all dry-rotted wood siding and soffits of the two-story residential buildings
37 | 51062-00 | Sealants & caulking | Roofing Sealants & Caulking Repairs | GC | Year 1 | 4500 | 4500 |  |  | 0 |  | Roofing Sealants & Caulking Repairs
19 | 51091-00 | ADA parking & curb cuts | Lender PCA - There is a van accessible parking space near the leasing office that is missing a pole-mounted sign. EPCA - Provide a compliant van-accessible parking space with compliant signage | PMC | Year 1 | 350 | 101 |  |  | N/A |  | Lender PCA - There is a van accessible parking space near the leasing office that is missing a pole-mounted sign. | [5 empty] | 2025-11-22
PROJECTS subtotal (excl. contingency/CM fee)
54 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 32663 | 4946 | 32663 |  | N/A |  | CM Fee
53 | 51180-00 | Contingency | Contingency | CON | Contingency | 31107 | 0 | 31107 |  | N/A |  | Contingency

## Regency & Lexington
Regency & Lexington — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
41 | 51080-00 | Exterior building | Paint community | GC | Year 1 | 239143 | 297600 |  |  | 0 |  | Paint community
34 | 51072-00 | Repair balcony framing & decking | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail PCA 4.2 - Repair waterproof coating at top of stair interface, and replace deteriorated fascia board. Any damaged rim joist should be sectionally replaced. | GC | Year 1 | 189643 | 236000 |  |  | 0 |  | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail PCA 4.2 - Repair waterproof coating at top of stair interface, and replace deteriorated fascia board.
100 | 51080-00 | Exterior building Paint | Paint community | GC | Year 1 | 132857 | 113732 |  |  | 2 |  | Paint community
90 | 51072-00 | Repair balcony framing & decking | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail | GC | Year 1 | 105357 | 134350 |  |  | 0 |  | SB 721 reports identified 1 required repair and other recommended repairs. See reports for detail
16 | 51053-00 | Asphalt Coating | Fill asphalt cracks Regency Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in good to fair condition. | GC | Year 1 | 91929 | 42900 |  |  | 3 |  | Fill asphalt cracks Regency Equity PCA Item- 3.2.2- Asphalt seal coat and pavement markings/striping appear to be in good to fair condition.
29 | 51092-00 | Install metal hardware | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces | GC | Year 1 | 67500 | 107500 |  |  | 0 |  | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces
69 | 51053-00 | Asphalt Coating | Filll asphalt cracks | GC | Year 1 | 51071 | 0 |  |  | 4 |  | Filll asphalt cracks
20 | 51023-00 | Resurface swimming pool | Resurface two pools | GC | Year 1 | 44500 | 71200 |  |  | 0 |  | Resurface two pools
73 | 51023-00 | Resurface swimming pool | Resurface two pools | GC | Year 1 | 44500 | 0 |  |  | 4 |  | Resurface two pools
83 | 51092-00 | Install metal hardware | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces | GC | Year 1 | 40000 | 0 |  |  | 4 |  | PCA 4.1 - Install metal hardware connections at post-to-beam and post-to-foundation locations in crawlspaces
110 | 51130-00 | Galvanized Pipe Replacement | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone to developing pinhole leaks and is susceptible to corrosion inside the pipe, restricting water flow. | GC | Year 1 | 40000 | 0 |  |  | 4 |  | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. Galvanized pipe is prone to developing pinhole leaks and is susceptible to corrosion inside the pipe, res
58 | 51160-00 | Energy Retrofit | Echelon upfront costs | Capex | Year 1 | 38441 | 0 |  |  | N/A |  | Echelon upfront costs
42 | 51082-00 | Repair / replace wood trim | Replace rotted fascia and trim | GC | Year 1 | 36000 | 57600 |  |  | 0 |  | Replace rotted fascia and trim
101 | 51082-00 | Repair / replace wood trim Repair exposed lumber and | Replace rotted fascia and trim PCA 4.4.1 - Repair exposed lumber and elevation changes. | GC | Year 1 | 36000 | 0 |  |  | 4 |  | Replace rotted fascia and trim PCA 4.4.1 - Repair exposed lumber and elevation changes.
54 | 51130-00 | Galvanized Pipe Replacement | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings. | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Regency & Lexington Equity PCA Item- 5.1- Galvanized steel pipe was observed at the buildings.
86 | 51082-00 | Allowance to replace deteriorated wood trim, fascia, | PCA 4.2-Allowance to replace deteriorated wood trim, fascia, rim joists and sheathing at elevated walkways and landings. | GC | Year 1 | 30000 | 24000 |  |  | 2 |  | PCA 4.2-Allowance to replace deteriorated wood trim, fascia, rim joists and sheathing at elevated walkways and landings.
60 | 51140-00 | Electrical distribution | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B | GC | Year 1 | 28143 | 13800 |  |  | 3 |  | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B
114 | 51160-00 | Energy Retrofit | Echelon upfront costs | Capex | Year 1 | 27121 | 0 |  |  | N/A |  | Echelon upfront costs
36 | 51062-00 | Asphalt composite shingle roofing Repair loose grave | Roof tune-up to include gravel. Reseal and secure gravel stop and drip edge. PCA 4.4.1 - Repair loose gravel stop and open perimeter flashing. PCA 4.4.1- Repair membrane and deck buckles | GC | Year 1 | 27000 | 125000 |  |  | 0 |  | Roof tune-up to include gravel. Reseal and secure gravel stop and drip edge. PCA 4.4.1 - Repair loose gravel stop and open perimeter flashing. PCA 4.4.1- Repair membrane and deck buckles
47 | 51011-00 | Pool Furniture | No furniture currently, need chaises and other furniture for main pool. Tables/chairs and armcharis only for 2nd pool due to lack of space | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | No furniture currently, need chaises and other furniture for main pool. Tables/chairs and armcharis only for 2nd pool due to lack of space
52 | 51993-00 | Security Camera System | Don't have anything, budget for a new system | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | Don't have anything, budget for a new system
107 | 51993-00 | Security Camera System | Don't have anything, budget for a new system | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | Don't have anything, budget for a new system
17 | 51091-00 | ADA parking & curb cuts | Repair trip hazards | GC | Year 1 | 24429 | 38000 |  |  | 0 |  | Repair trip hazards
40 | 51075-00 | Repair / replace wood siding | Replace rotted t-111 siding | GC | Year 1 | 24000 | 48000 |  |  | 0 |  | Replace rotted t-111 siding
99 | 51075-00 | Repair / replace wood siding | Replace rotted t-111 siding | GC | Year 1 | 24000 | 25000 |  |  | 0 |  | Replace rotted t-111 siding
79 | 51992-00 | Termite Remediation | Lexington - Drywood termite local treatments | Capex | Year 1 | 22000 | 20854 |  |  | N/A |  | Lexington - Drywood termite local treatments
18 | 51046-00 | Landscape irrigation | Inspect and repair Irrigation | GC | Year 1 | 20571 | 32000 |  |  | 0 |  | Inspect and repair Irrigation
93 | 51062-00 | Asphalt composite shingle roofing Repair loose grave | Roll roofing on roofs inspect and repair PCA 4.4.1 - Repair loose gravel stop and open perimeter flashing and membrane splits | GC | Year 1 | 20000 | 0 |  |  | 4 |  | Roll roofing on roofs inspect and repair PCA 4.4.1 - Repair loose gravel stop and open perimeter flashing and membrane splits
25 | 51992-00 | Termite Remediation | Regency - Drywood termite local treatments | Capex | Year 1 | 19000 | 18010 |  |  | N/A |  | Regency - Drywood termite local treatments
39 | 51062-00 | Sealants & caulking | Seal joints in t-111 | GC | Year 1 | 18000 | 36000 |  |  | 0 |  | Seal joints in t-111
97 | 51062-00 | Sealants & caulking | Seal joints in t-111 | GC | Year 1 | 18000 | 0 |  |  | 4 |  | Seal joints in t-111
119 | 51140-00 | Electrical distribution | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B | GC | Year 1 | 17857 | 0 |  |  | 4 |  | Inspect and repair lighting controllers on all buildings, Equity PCA Item- 5.3- The site contact reported no recent Infrared (IR) scans of electrical equipment. NFPA 70B
15 | 51130-00 | Storm sewer piping | Storm water drainage repairs in courtyards | GC | Year 1 | 16714 | 0 |  |  | 4 |  | Storm water drainage repairs in courtyards
26 | 51992-00 | Termite Remediation | Regency - Subterranean termite treatment and baiting | Capex | Year 1 | 15400 | 14598 |  |  | N/A |  | Regency - Subterranean termite treatment and baiting
46 | 51160-00 | Pool Area Remodel | Expand pool fenced area to make space for furniture | GC | Year 1 | 15000 | 0 |  |  | 4 |  | Expand pool fenced area to make space for furniture
70 | 51091-00 | ADA parking & curb cuts | Repair trip hazards | GC | Year 1 | 13571 | 0 |  |  | 4 |  | Repair trip hazards
19 | 51043-00 | Landscaping | Tree trim | Capex | Year 1 | 13000 | 300 |  |  | N/A |  | Tree trim
72 | 51043-00 | Landscaping | Tree trim | Capex | Year 1 | 13000 | 300 |  |  | N/A |  | Tree trim
33 | 51077-00 | Repair exterior stair railings | Secure railings | GC | Year 1 | 12000 | 24000 |  |  | 0 |  | Secure railings
37 | 51071-00 | Gutters & downspouts Reconnect loose downspout. | Secure and clean gutters PCA 4.4.1 - Reconnect loose downspout. | GC | Year 1 | 12000 | 24000 |  |  | 0 |  | Secure and clean gutters PCA 4.4.1 - Reconnect loose downspout.
57 | 51130-00 | Natural Gas Seismic Shutoff | Will confirm with Gas utiliity company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices | GC | Year 1 | 12000 | 6000 |  |  | 3 |  | Will confirm with Gas utiliity company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices
89 | 51077-00 | Repair exterior stair railings | Secure railings | GC | Year 1 | 12000 | 12500 |  |  | 0 |  | Secure railings
94 | 51071-00 | Gutters & downspouts | Secure and clean gutters | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Secure and clean gutters
71 | 51046-00 | Landscape irrigation | Inspect and repair Irrigation | GC | Year 1 | 11429 | 0 |  |  | 4 |  | Inspect and repair Irrigation
80 | 51992-00 | Termite Remediation | Lexington - Subterranean termite treatment and baiting | Capex | Year 1 | 10800 | 10237 |  |  | N/A |  | Lexington - Subterranean termite treatment and baiting
14 | 51045-00 | Initial Lanscape Cleanup | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | Capex | Year 1 | 10000 | 602 |  |  | N/A |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
23 | 51050-00 | Parking Lot Cleaning | Power wash garage/parking walls and asphalt | GC | Year 1 | 10000 | 20000 |  |  | 0 |  | Power wash garage/parking walls and asphalt
38 | 51062-00 | Flashing | Repair flashing between stucco and t-111 | GC | Year 1 | 10000 | 20000 |  |  | 0 |  | Repair flashing between stucco and t-111
67 | 51045-00 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | Capex | Year 1 | 10000 | 602 |  |  | N/A |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
76 | 51050-00 | Parking Lot Cleaning | Power wash garage/parking walls and asphalt | GC | Year 1 | 10000 | 0 |  |  | 4 |  | Power wash garage/parking walls and asphalt
82 | 51072-00 | Allowance to epoxy inject concrete topping slabs and | PCA 4.2- Allowance to epoxy inject concrete topping slabs and apply elastomeric coating at elevated walkways. | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | PCA 4.2- Allowance to epoxy inject concrete topping slabs and apply elastomeric coating at elevated walkways.
88 | 51075-00 | Allowance for exterior cladding replacement and repl | PCA 4.2 -Allowance for exterior cladding replacement and replacement of any damaged wood framing. | GC | Year 1 | 10000 | 8000 |  |  | 2 |  | PCA 4.2 -Allowance for exterior cladding replacement and replacement of any damaged wood framing.
96 | 51062-00 | Flashing | Repair flashing between stucco and t-111 | GC | Year 1 | 10000 | 0 |  |  | 4 |  | Repair flashing between stucco and t-111
68 | 51130-00 | Storm sewer piping | Storm water drainage repairs in courtyards | GC | Year 1 | 9286 | 0 |  |  | 4 |  | Storm water drainage repairs in courtyards
48 | 51160-04 | Picnic/Grill Area Remodel | Small grill area by pool, look at adding outdoor counter | PMC | Year 1 | 8000 | 0 |  |  | N/A |  | Small grill area by pool, look at adding outdoor counter
113 | 51130-00 | Natural Gas Seismic Shutoff | Will confirm with Gas utility company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices | GC | Year 1 | 8000 | 0 |  |  | 4 |  | Will confirm with Gas utility company if needed Regency Equity PCA Item- 5.1- The natural gas services were not equipped with automatic seismic shut-off devices
55 | 51134-00 | Sanitary Sewer Piping | Number based on actual bid; $285 per cleanout, est. 12 cleanouts. $402 per storm drain, 11 cleanouts. Regency & Lexington Equity PCA Item- 5.1- The sanitary waste system was original to construction. | PMC | Year 1 | 7842 | 26166 |  |  | N/A |  | Number based on actual bid; $285 per cleanout, est. 12 cleanouts. $402 per storm drain, 11 cleanouts. Regency & Lexington Equity PCA Item- 5.1- The sanitary waste system was original to construction.
24 | 51046-00 | Landscape irrigation | Irrigation repairs & upgrades | PMC | Year 1 | 7500 | 2007 |  |  | N/A |  | Irrigation repairs & upgrades
31 | 51070-00 | Replace sheathing | PCA 4.2 - Replace deteriorated sheathing and joists at roof eaves, as required. | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | PCA 4.2 - Replace deteriorated sheathing and joists at roof eaves, as required.
21 | 51026-00 | Repair / replace swimming pool pumps | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool did not appear to be compliant with the Virginia Graeme Baker Pool & Spa Safety Act | GC | Year 1 | 7000 | 11200 |  |  | 0 |  | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool did not appear to be compliant with the Virginia Graeme Baker Pool & Spa Safety A
22 | 51076-00 | Fences & gates - swimming pool | Adjust closers on pool gates | GC | Year 1 | 7000 | 14000 |  |  | 0 |  | Adjust closers on pool gates
74 | 51026-00 | Repair / replace swimming pool pumps | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool did not appear to be compliant with the Virginia Graeme Baker Pool & Spa Safety Act (P&SS Act). | GC | Year 1 | 7000 | 0 |  |  | 4 |  | Anti entrapment devices Regency & Lexington Equity PCA Item- 3.2.9- Based on Partner’s observations, the swimming pool did not appear to be compliant with the Virginia Graeme Baker Pool & Spa Safety A
75 | 51076-00 | Fences & gates - swimming pool | Adjust closers on pool gates | GC | Year 1 | 7000 | 7000 |  |  | 0 |  | Adjust closers on pool gates
30 | 51998-00 | Shore Maintenance Shed | PCA 4.2- Maintenance Shed - Immediately temporarily shore the unsupported double top plate. Engage licensed engineer to design a header or support beam with adequate bearing supports. | GC | Year 1 | 6000 | 0 |  |  | 4 |  | PCA 4.2- Maintenance Shed - Immediately temporarily shore the unsupported double top plate. Engage licensed engineer to design a header or support beam with adequate bearing supports.
35 | 51075-00 | Expansion Joints | Expansion Joints | GC | Year 1 | 6000 | 12000 |  |  | 0 |  | Expansion Joints
50 | 51029-00 | Playground equipment | Add seating and/or picnic tables year 1, budget for equipment replacement in year 4. | GC | Year 1 | 6000 | 10000 |  |  | 0 |  | Add seating and/or picnic tables year 1, budget for equipment replacement in year 4.
91 | 51075-00 | Expansion Joints | Expansion Joints | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Expansion Joints
32 | 51172-00 | Allowance for sectional replacement of damaged sheat | PCA 4.2 - Allowance for sectional replacement of damaged sheathing and joists at carports. | GC | Year 1 | 5000 | 2500 |  |  | 3 |  | PCA 4.2 - Allowance for sectional replacement of damaged sheathing and joists at carports.
44 | 51169-00 | Clubhouse / Office Remodel | No clubhouse, allowance for office | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | No clubhouse, allowance for office
111 | 51134-00 | Sanitary Sewer Piping | Number based on actual bid; $285 per cleanout, 8 cleanouts. $402 per storm drain, 6 cleanouts. Regency & Lexington Equity PCA Item- 5.1- The sanitary waste system was original to construction. | PMC | Year 1 | 4692 | 15655 |  |  | N/A |  | Number based on actual bid; $285 per cleanout, 8 cleanouts. $402 per storm drain, 6 cleanouts. Regency & Lexington Equity PCA Item- 5.1- The sanitary waste system was original to construction.
27 | 51070-00 | Wall framing | Replace damaged framing in gable ends | GC | Year 1 | 4500 | 9000 |  |  | 0 |  | Replace damaged framing in gable ends
59 | 51120-00 | HVAC Replacement | Large Rheem HVAC unit outside office looks very old and may need to be replaced | GC | Year 1 | 4500 | 0 |  |  | 4 |  | Large Rheem HVAC unit outside office looks very old and may need to be replaced
81 | 51070-00 | Wall framing | Replace damaged framing in gable ends | GC | Year 1 | 4500 | 4500 |  |  | 0 |  | Replace damaged framing in gable ends
87 | 51072-00 | Building G Balcony – sectional replacement of deteri | PCA 4.2 -Building G Balcony – sectional replacement of deteriorated framing. | GC | Year 1 | 4500 | 3600 |  |  | 2 |  | PCA 4.2 -Building G Balcony – sectional replacement of deteriorated framing.
116 | 51120-00 | HVAC Replacement | Large Rheem HVAC unit outside office looks very old and may need to be replaced | GC | Year 1 | 4500 | 0 |  |  | 4 |  | Large Rheem HVAC unit outside office looks very old and may need to be replaced
45 | 51160-06 | Clubhouse / Office Furniture | Need seating for reception area in leasing office. | PMC | Year 1 | 4000 | 0 |  |  | N/A |  | Need seating for reception area in leasing office.
51 | 51990-02 | Need key trak for office | Key Track | PMC | Year 1 | 3500 | 0 |  |  | N/A |  | Key Track
43 | 51075-00 | Repair stucco | Some walls next to windows need patching and paint | GC | Year 1 | 3000 | 6000 |  |  | 0 |  | Some walls next to windows need patching and paint
49 | 51160-04 | Picnic/Grill Furniture | Picnic tables or tables/chairs needed | PMC | Year 1 | 3000 | 0 |  |  | N/A |  | Picnic tables or tables/chairs needed
102 | 51075-00 | Repair stucco | Some walls next to windows need patching and paint | GC | Year 1 | 3000 | 3000 |  |  | 0 |  | Some walls next to windows need patching and paint
109 | 51130-00 | Back-flow preventer | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. | PMC | Year 1 | 3000 | 2474 |  |  | N/A |  | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed.
112 | 51130-00 | Pipe Repair at Building 1 Boiler | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could potentially affect the integrity of the pipe and lead to a leak. | GC | Year 1 | 3000 | 0 |  |  | 4 |  | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could potentially affect the integrity of the pipe and lead to a leak.
53 | 51130-00 | Back-flow preventer | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed. | PMC | Year 1 | 2250 | 1856 |  |  | N/A |  | Regency & Lexington Equity PCA Item- 5.1- The backflow preventers did not have current inspection tags displayed.
85 | 51141-00 | Fill pitch pockets and flash parking lot light bases | PCA 4.4.1 - Fill pitch pockets and flash parking lot light bases. | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | PCA 4.4.1 - Fill pitch pockets and flash parking lot light bases.
56 | 51130-00 | Pipe Repair at Building 1 Boiler | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could potentially affect the integrity of the pipe and lead to a leak. | GC | Year 1 | 750 | 3750 |  |  | 0 |  | Regency & Lexington Equity PCA Item- 5.1- Corrosion was observed on the pipe connected to Building 1 boiler that could potentially affect the integrity of the pipe and lead to a leak.
28 | 51156-00 | Replace hardware | PCA 4.2 - Building C, Unit 37 – Immediately replace the existing bolts with adequately sized bolts and washers. | GC | Year 1 | 500 | 500 |  |  | 0 |  | PCA 4.2 - Building C, Unit 37 – Immediately replace the existing bolts with adequately sized bolts and washers.
84 | 51070-00 | Repair checked wood beams by epoxy injection. | PCA 4.2- Repair checked wood beams by epoxy injection. | GC | Year 1 | 500 | 500 |  |  | 0 |  | PCA 4.2- Repair checked wood beams by epoxy injection.
PROJECTS subtotal (excl. contingency/CM fee)
61 | 51175-00 | Contingency | Contingency Amount - Regency | CON | Contingency | 127553 | 0 | 127553 |  | N/A |  | Contingency Amount
121 | 51175-00 | Contingency | Contingency Amount - Lexington | CON | Contingency | 87858 | 0 | 87858 |  | N/A |  | Contingency Amount
62 | 51190-00 | Construction Management Fee | CM Fee - Regency | CMF | CM Fee | 70154 | 0 | 70154 |  | N/A |  | CM Fee
122 | 51190-00 | Construction Management Fee | CM Fee - Lexington | CMF | CM Fee | 48322 | 0 | 48322 |  | N/A |  | CM Fee

## Renaissance
Renaissance — 2025 acq · GC GL fallback |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
97 | 83000-3400 | Exterior building painting | Including estimate from WDIR , to be in Yr 2 (Q4 of'27) | Capex | Year 1 | 556000 | 0 |  |  | N/A |  | Including estimate from WDIR , to be in Yr 2 (Q4 of'27)
18 | 83000-2200 | Asphalt Coating | PNA - Fill all alligator cracks, potholes and then seal coat throughout property. Also, speed bump repairs throughout property. | GC | Year 1 | 271120 | 0 |  |  | 4 |  | PNA - Fill all alligator cracks, potholes and then seal coat throughout property. Also, speed bump repairs throughout property.
104 | 80000-6800 | Exterior repair for WDIR | Remediation of active termites | Capex | Year 1 | 250000 | 0 |  |  | N/A |  | Remediation of active termites
34 | 83000-5100 | Replace swimming pool deck | PNA: Repairs to pool deck cracks and resurface. Bring depth markers, tile, and coping up to code | GC | Year 1 | 100000 | 0 |  |  | 4 |  | PNA: Repairs to pool deck cracks and resurface. Bring depth markers, tile, and coping up to code
48 | 83000-6700 | Sports Court | PNA: Complete resurface of sports court and new lines for basketball court. Lender PCA: Repair cracks at sports court paving | Capex | Year 1 | 98250 | 2510 |  |  | N/A |  | PNA: Complete resurface of sports court and new lines for basketball court. | [5 empty] | 2026-12-19
43 | 83000-2600 | Carport and garage | PNA: Repair any damaged carports throughtout property. Replace 31 garage doors throughout property - significant damage. | GC | Year 1 | 92400 | 2595 |  |  | 4 |  | PNA: Repair any damaged carports throughtout property. Replace 31 garage doors throughout property - significant damage.
17 | 83000-8300 | Landscape Cleanup and Enhancements | PNA: Building clearance tree trim and cleanup. | Capex | Year 1 | 84500 | 1923.5 |  |  | N/A |  | PNA: Building clearance tree trim and cleanup.
169 | 83000-3200 | Common area light fixtures | PNA: Replace all pole lights, wall packs throughout property. | GC | Year 1 | 44600 | 0 |  |  | 4 |  | PNA: Replace all pole lights, wall packs throughout property.
81 | 83000-6100 | Tile roofing | PNA: Clay tile roofing - inspect and minor repairs | GC | Year 1 | 39860 | 0 |  |  | 4 |  | PNA: Clay tile roofing - inspect and minor repairs
71 | 83000-7100 | Repair exterior stair railings | PNA: Secure railings and paint all metal stair railings. Currently significantly chipped. | GC | Year 1 | 37800 | 0 |  |  | 4 |  | PNA: Secure railings and paint all metal stair railings. Currently significantly chipped.
22 | 83000-2800 | Concrete pavement | PNA: Repair damaged/ cracked swales throughtout property Lender PCA: At the time of the assessment, several concrete trip hazards were observed throughout the site. The main areas of damage are near the office entrance, between the northwest buildings near 5669 uni 159, near the south side of the pool near the apartment buildings, and the townhomes on the east side at building units 5675 121-124. The cracked and damaged pavement should be repaired or sectionally replaced. | Capex | Year 1 | 36500 | 6500 |  |  | N/A |  | PNA: Repair damaged/ cracked swales throughtout property Lender PCA: At the time of the assessment, several concrete trip hazards were observed throughout the site. The main areas of damage are near t | [5 empty] | 2026-03-19
82 | 83000-6100 | Gutters & downspouts | PNA: Secure and clean downspouts. Confirm this includes gutters and repinning | GC | Year 1 | 36200 | 0 |  |  | 4 |  | PNA: Secure and clean downspouts. Confirm this includes gutters and repinning
26 | 83000-7100 | Sidewalks | Sidewalk Repairs | GC | Year 1 | 33350 | 0 |  |  | 4 |  | Sidewalk Repairs
27 | 83000-6900 | Landscape irrigation | PNA: Inspect and repair irrigation Lender PCA: At the time of the assessment, standing water was observed in various areas throughout the site due to recent heavy rainfall. The storm water does not appear to property drain due to debris. Additionally, some of the drain covered were observed to be damaged or missing in multiple areas of the site. The drain covers should be replaced and the debris should be removed from the lines. | Capex | Year 1 | 31200 | 0 |  |  | N/A |  | PNA: Inspect and repair irrigation Lender PCA: At the time of the assessment, standing water was observed in various areas throughout the site due to recent heavy rainfall. The storm water does not a | [5 empty] | 2026-12-19
23 | 83000-2200 | Stripe parking areas | PNA: Stripe parking lot throughout property. | GC | Year 1 | 30000 | 0 |  |  | 4 |  | PNA: Stripe parking lot throughout property.
46 | 83000-2200 | Parking Lot Concersion | Potential to convert unused parking lot, will evaluate further into hold | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Potential to convert unused parking lot, will evaluate further into hold
170 | 83000-3200 | Replace breezeway lights | PNA: Replace all breezeway sconces to LED throughout property. | GC | Year 1 | 27800 | 0 |  |  | 4 |  | PNA: Replace all breezeway sconces to LED throughout property.
122 | 80000-6400 | Fire Stops | PNA: Fire stops | Capex | Year 1 | 27244 | 9697 |  |  | N/A |  | PNA: Fire stops
44 | 83000-3700 | Dumpster enclosures | PNA: Damage cinderblocks at dumpster enclosures to be repaired. Lender PCA: Two of the refuse enclosures were observed with cracking and damaged CMU. Repairs are recommended. | Capex | Year 1 | 18500 | 0 |  |  | N/A |  | PNA: Damage cinderblocks at dumpster enclosures to be repaired. Lender PCA: Two of the refuse enclosures were observed with cracking and damaged CMU. Repairs are recommended. | [5 empty] | 2026-12-19
89 | 83000-6500 | Repair / replace cement fiber siding | PNA: Maintenance shed needs to new siding replacment and paint. | GC | Year 1 | 18500 | 0 |  |  | 4 |  | PNA: Maintenance shed needs to new siding replacment and paint.
40 | 83000-1700 | Playground equipment | PNA: Current playground extremely faded, if wanting replacement will need to add more funds. Number given is for adding mulch to fall zone. | GC | Year 1 | 12600 | 0 |  |  | 4 |  | PNA: Current playground extremely faded, if wanting replacement will need to add more funds. Number given is for adding mulch to fall zone.
70 | 83000-7100 | Repair exterior stair treads and stringers | PNA: Secure Stair Treads & Stringers | GC | Year 1 | 12200 | 0 |  |  | 4 |  | PNA: Secure Stair Treads & Stringers
25 | 83000-2800 | ADA parking & curb cuts | PNA: Repair of any damaged curbs. | GC | Year 1 | 10660 | 10850 |  |  | 0 |  | PNA: Repair of any damaged curbs.
79 | 83000-6100 | Moss Treatment | Moss treatment and pine needle cleaning | GC | Year 1 | 10000 | 0 |  |  | 4 |  | Moss treatment and pine needle cleaning
62 | 83000-7000 | Repair or replace damaged concrete treads at stairs. | Lender PCA: At the time of the assessment, a damaged concrete thread was observed at the stairs to the upper floor apartment units at the southwest side of the site near building 5665 units 233-240. The damaged thread should be repaired. | PMC | Year 1 | 500 | 0 |  |  | N/A |  | Lender PCA: At the time of the assessment, a damaged concrete thread was observed at the stairs to the upper floor apartment units at the southwest side of the site near building 5665 units 233-240. T | [5 empty] | 2026-03-19
147 | 80000-1700 | Security/ fire alarm systems | Lender PCA: At the time of the assessment, unit 143 was observed to have missing smoke detectors in the hallways and bedrooms. AEI recommends that property management surveys all units and installs missing smoke detectors where missing. | PMC | Year 1 | 100 | 0 |  |  | N/A |  | Lender PCA: At the time of the assessment, unit 143 was observed to have missing smoke detectors in the hallways and bedrooms. AEI recommends that property management surveys all units and installs mi | [5 empty] | 2026-03-19
PROJECTS subtotal (excl. contingency/CM fee)
175 | 80000-7200 | Construction Management Fee | CM Fee | CMF | CM Fee | 100269 | 0 | 100269 |  | N/A |  | CM Fee
174 | 80000-7200 | Contingency | Contingency Amount | CON | Contingency | 95494 | 0 | 95494 |  | N/A |  | Contingency Amount

## Rosemont
Rosemont — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
17 | 84204 | Asphalt Repairs | Mill, cement stabilize and overlay all drive aisles throughout property. Includes Equity PCR Item 3.3.2- Mill and overlay with restriping throughout are recommended in the short term. | GC | Year 1 | 750000 | 750000 |  |  | 0 |  | Mill, cement stabilize and overlay all drive aisles throughout property. Includes Equity PCR Item 3.3.2- Mill and overlay with restriping throughout are recommended in the short term.
147 | 84476 | Unit water heaters | Equity PCR Item- 5.1- Observed water heaters were not provided with drain pans. Additionally, most water heaters observed also either lacked discharge piping from the temperature & pressure relief valve (T&P valve) or the installed piping was routed upwards which would not allow proper drainage. Partner recommends that the water heaters be installed atop a pedestal and provided with an approved drain pan. The drain pan should be provided with a drain line routed to a hub drain connected to the sanitary drain piping or routed to the building exterior. Piping from the T&P valve would then be routed to the drain pan | GC | Year 1 | 211000 | 211000 |  |  | 0 |  | Equity PCR Item- 5.1- Observed water heaters were not provided with drain pans. Additionally, most water heaters observed also either lacked discharge piping from the temperature & pressure relief val | [5 empty] | 2026-01-20
68 | 84202 | Gutters & downspouts | Equity PCR Item 4.4.2- Gutters and downspouts should be installed at the roof eaves where not currently installed to help direct storm water away from building foundations. | GC | Year 1 | 130000 | 130000 |  |  | 0 |  | Equity PCR Item 4.4.2- Gutters and downspouts should be installed at the roof eaves where not currently installed to help direct storm water away from building foundations.
51 | 84121 | Repair exterior stair railings | Secure and paint | GC | Year 1 | 110000 | 110000 |  |  | 0 |  | Secure and paint
50 | 84114 | Repair exterior stair treads and stringers | Grind any rusted toe kick plates and red oxide prior to repaint. Replace damaged metal toe plates, as needed. Secure, as well. Includes Lender PCR Item- Repair corroded exterior steel framed stairs in Buildings 3621, 3625, 3822, 3843, 3777, 3611 and 3639 Includes Equity PCR Item 4.5- Steel stair and balcony components were noted to contain peeling paint, corrosion, and some moderate deterioration. These components should be repaired as needed, properly prepped, and painted in the short term. | GC | Year 1 | 100000 | 100000 |  |  | 0 |  | Grind any rusted toe kick plates and red oxide prior to repaint. Replace damaged metal toe plates, as needed. Secure, as well. Includes Lender PCR Item- Repair corroded exterior steel framed stairs | [5 empty] | 2026-01-20
75 | 84101 | Exterior building | Paint all metal throughout property | GC | Year 1 | 90000 | 90000 |  |  | 0 |  | Paint all metal throughout property
65 | 84433 | Underlayment | Roof Underlayment | GC | Year 1 | 88000 | 88000 |  |  | 0 |  | Roof Underlayment
23 | 84434 | Retaining walls | Replace missing or rotted timbers within existing retaining walls, replace some walls. Includes Lender PCR Item- Wood timber retaining walls located by Buildings 3740, 3760, and 3843 exhibits rot, deterioration or damage. Equity PCR Item 3.2.5- The wooden railroad tie retaining walls appeared to exhibit moderate to extensive deterioration as these types of walls are known for rotting from the soil side outward. Based on the observed condition and EUL, replacement of the noted retaining walls is recommended in the short term. | GC | Year 1 | 80000 | 80000 |  |  | 0 |  | Replace missing or rotted timbers within existing retaining walls, replace some walls. Includes Lender PCR Item- Wood timber retaining walls located by Buildings 3740, 3760, and 3843 exhibits rot, det | [5 empty] | 2025-04-20
64 | 84433 | Flashing | Roof Flashing | GC | Year 1 | 79200 | 79200 |  |  | 0 |  | Roof Flashing
24 | 84303 | Landscaping | Tree trim clearance of all buildings. Includes Equity PCR Item 3.2.4- Many trees were overhanging buildings and depositing tree leaf debris onto roofing systems. The overgrown trees need to be pruned at this time. Annual mulch/groundcover in yrs 2-10 | GC | Year 1 | 60000 | 60000 |  |  | 0 |  | Tree trim clearance of all buildings. Includes Equity PCR Item 3.2.4- Many trees were overhanging buildings and depositing tree leaf debris onto roofing systems. The overgrown trees need to be pruned
127 | 84203 | Picnic/Grill Area Remodel | Add 1-2 outdoor grill/kitchen areas at the property with gazebo | GC | Year 1 | 60000 | 60000 |  |  | 0 |  | Add 1-2 outdoor grill/kitchen areas at the property with gazebo
52 | 84121 | Repair patio/balcony railings | Replace all bottom level patio fencing on each building | GC | Year 1 | 55000 | 55000 |  |  | 0 |  | Replace all bottom level patio fencing on each building
108 | 84239 | Fire Stops | LowPro (Pair covers 4 burner range)- For range top microwaves | Capex | Year 1 | 52009 | 54600 |  |  | N/A |  | LowPro (Pair covers 4 burner range)- For range top microwaves
74 | 84206 | Repair / replace vinyl siding | Repair/replace damaged vinyl siding throughout property Includes Lender PCR Item- Dry rot was observed by the siding at the leasing office building. | GC | Year 1 | 52000 | 52000 |  |  | 0 |  | Repair/replace damaged vinyl siding throughout property Includes Lender PCR Item- Dry rot was observed by the siding at the leasing office building. | [5 empty] | 2025-04-20
35 | 84120 | Re-apply Coating on Walkways & Breezeways | Budget for initial repairs and contingency for ongoing replacements | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Budget for initial repairs and contingency for ongoing replacements
63 | 84433 | Asphalt composite shingle roofing | Roofs were replaced in 2019- Initial and ongoing repairs, and contingency for phased replacements in yrs 9-10 | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Roofs were replaced in 2019- Initial and ongoing repairs, and contingency for phased replacements in yrs 9-10
86 | 84215 | Metal Entry Door Replacement and Repairs | Contingency for replacements and repairs | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Contingency for replacements and repairs
137 | 84275 | New access gate at back entrance | Look at adding gate ro restrict access to dumpster area and prevent dumping | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Look at adding gate ro restrict access to dumpster area and prevent dumping
141 | 84219 | Carports | Look at adding carports for additional income | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Look at adding carports for additional income
149 | 84385 | Sanitary sewer Repairs | Contingency to remove roots and blockages at several locations, per the sewer scoping. See final report in diligence folder for detail. Preliminary findings from the scope are: CO18: Blocked. Serves Bldg. 3781, 3785 CO22: Blocked. Serves Bldg. 3945, 3949 CO31: Blocked. Serves Bldg. 3749 CO32: Blocked. Serves Bldg. 3741 CO35: Blocked. Serves Bldg. 3625, 3621 | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Contingency to remove roots and blockages at several locations, per the sewer scoping. See final report in diligence folder for detail. Preliminary findings from the scope are: CO18: Blocked. Serves
122 | 84360 | Leasing Pool Furniture | Supplement current furniture, add freestanding umbrellas, cornhole & ping pong, 2 cabanas, move some furniture to secondary pool | Capex | Year 1 | 45000 | 1416 |  |  | N/A |  | Supplement current furniture, add freestanding umbrellas, cornhole & ping pong, 2 cabanas, move some furniture to secondary pool
22 | 84205 | Fences & gates - site perimeter | Repair any damaged wooden fencing around property | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Repair any damaged wooden fencing around property
16 |  | Storm sewer piping | Address 7 areas of water intrusion throughout property | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | Address 7 areas of water intrusion throughout property
129 | 84390 | Sports Court | Resurface, add 2 Pickleball nets. Keep running track, stripe for Pickleball courts Includes Equity PCR Item 3.2.9- The sports courts were noted in poor condition. The surfaces were observed to be heavily deteriorated and not in a playable condition. Based on the observed condition, resurfacing the sports courts is recommended in the short term. | GC | Year 1 | 35000 | 66800 |  |  | 0 |  | Resurface, add 2 Pickleball nets. Keep running track, stripe for Pickleball courts Includes Equity PCR Item 3.2.9- The sports courts were noted in poor condition. The surfaces were observed to be hea
18 | 84201 | Stripe parking areas | Layout and stripe throughout property | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Layout and stripe throughout property
85 | 84206 | Window Replacement and Repairs, including frames | Contingency for replacements and repairs | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Contingency for replacements and repairs
87 | 84215 | Sliding Balcony Door Replacement and Repairs | Contingency for replacements and repairs | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Contingency for replacements and repairs
119 | 84190 | Fitness Center Remodel | Need to replace lights, repair damaged walls, paint, repair flooring that is lifting, repair men's bathroom items | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Need to replace lights, repair damaged walls, paint, repair flooring that is lifting, repair men's bathroom items
106 | 82131 | Co 2 detectors | Install Co2 detectors in every unit | Capex | Year 1 | 22000 | 607 |  |  | N/A |  | Install Co2 detectors in every unit
15 | 84303 | Landscape Cleanup and Enhancements | Initial property landscape entry and tour path enhancements, etc | Capex | Year 1 | 20000 | 17564 |  |  | N/A |  | Initial property landscape entry and tour path enhancements, etc
163 | 82131 | Smoke Detectors | Equity PCR Item 5.5.2- Smoke detectors not observed in bedrooms, Install | Capex | Year 1 | 20000 | 2860 |  |  | N/A |  | Equity PCR Item 5.5.2- Smoke detectors not observed in bedrooms, Install
25 | 84111 | Dumpster enclosures | Replace fencing around dumpster/compactor enclosures | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Replace fencing around dumpster/compactor enclosures
154 | 84217 | Install P trap on HVAC condensate piping | Equity PCR Item 5.3- The interior fan coil units (FCUs) observed at the residential units lacked p-traps at the condensate drain piping. P- traps are required to prevent air from entering or escaping the drain line and ensure proper draining of the condensate. Installation of a p-trap on the condensate drain lines at the fan coil units is recommended | GC | Year 1 | 16880 | 16880 |  |  | 0 |  | Equity PCR Item 5.3- The interior fan coil units (FCUs) observed at the residential units lacked p-traps at the condensate drain piping. P- traps are required to prevent air from entering or escaping
143 | 83375 | Golf Cart | Need 1-2 leasing carts, have 2 maintenance carts | Capex | Year 1 | 16000 | 19840 |  |  | N/A |  | Need 1-2 leasing carts, have 2 maintenance carts
128 | 84340 | Picnic/Grill Furniture | Furniture for new grill areas | Capex | Year 1 | 15000 | 15000 |  |  | N/A |  | Furniture for new grill areas
132 | 84280 | Unit Model Update | Change out carpet, misc supplemental furniture, remove screen door since it is broken and obscures visibility in the model | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Change out carpet, misc supplemental furniture, remove screen door since it is broken and obscures visibility in the model
125 | 84195 | Playground Remodel | Replace swing sets, border and mulch as well as replacing grills with new stand alone ones at secondary park area | GC | Year 1 | 13000 | 13000 |  |  | 0 |  | Replace swing sets, border and mulch as well as replacing grills with new stand alone ones at secondary park area
19 | 84221 | ADA parking & curb cuts | ADA Parking & Curb Cuts | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | ADA Parking & Curb Cuts
26 | 84302 | Irrigation | Equity PCR Item 3.2.4- Although operation of the sprinkler system was not directly tested, property management reported that the irrigation system is not currently working. Repair of the irrigation system is recommended. | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Equity PCR Item 3.2.4- Although operation of the sprinkler system was not directly tested, property management reported that the irrigation system is not currently working. Repair of the irrigation sy
120 | 84190 | Fitness Equipment | Stair Stepper, other misc items | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | Stair Stepper, other misc items
121 | 84361 | Leasing Pool Area Remodel | Replace wood/cable fence section in raised area with metal rail to match other fencing, other misc repairs | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Replace wood/cable fence section in raised area with metal rail to match other fencing, other misc repairs
20 | 84115 | Sidewalks | Secure, scrape, sand & paint deck walkway from office area to sports complex. | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | Secure, scrape, sand & paint deck walkway from office area to sports complex.
156 | 84217 | HVAC inspection and maintenance | Clean debris/foliage from around condensors as well as leveling with condensor pads. Includes Equity PCR Item 5.2- Many of the outdoor HVAC condensing units were observed mounted improperly on their housekeeping pads. Several units were observed in areas where trees and bushes were overgrown and potentially interfering with condensing fans and impeding proper ventilation. Additionally, leaves were piled around or atop many of the units, which can interfere with operation and impede proper ventilation. Trimming of trees and bushes surrounding the units, clearing of leaves and debris and re-aligning the units on their respective housekeeping pads is recommended | PMC | Year 1 | 8500 | 0 |  |  | N/A |  | Clean debris/foliage from around condensors as well as leveling with condensor pads. Includes Equity PCR Item 5.2- Many of the outdoor HVAC condensing units were observed mounted improperly on their h
126 | 84340 | Playground Furniture | Picnic tables and misc items | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Picnic tables and misc items
130 | 84390 | Sports Court- Soccer | Replace shade sails | GC | Year 1 | 8000 | 8000 |  |  | 0 |  | Replace shade sails
155 | 84217 | Insulate HVAC lines | Equity PCR Item 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the units. This condition reduces unit efficiency and decrease the useful life of the equipment. Repair of deteriorated insulation at the refrigeration line sets is recommended. | GC | Year 1 | 5375 | 5375 |  |  | 0 |  | Equity PCR Item 5.2- Insulation at the refrigerant lines from the condensing units were deteriorated at many of the units. This condition reduces unit efficiency and decrease the useful life of the e
114 | 84103 | Signage - Building identification | Misc replacement signage | PMC | Year 1 | 5000 | 1185 |  |  | N/A |  | Misc replacement signage
117 | 84208 | Clubhouse / Office Remodel | Not needed, misc allowance | PMC | Year 1 | 5000 | 5000 |  |  | N/A |  | Not needed, misc allowance
118 | 84306 | Clubhouse / Office Furniture | Not needed, misc allowance | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Not needed, misc allowance
123 | 84361 | Secondary Pool Area Remodel | Need to fix cosmetic issues or possibly resurface | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Need to fix cosmetic issues or possibly resurface
124 | 84360 | Secondary Pool Furniture | Misc items & move items from main pool | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Misc items & move items from main pool
139 | 84450 | Security Camera System | Add cameras by mailboxes | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Add cameras by mailboxes
134 | 84275 | Access Control System | Need to add access control for package lockers in fitness center | PMC | Year 1 | 3000 | 1792 |  |  | N/A |  | Need to add access control for package lockers in fitness center
116 | 84310 | Designer Fees | TBD scope | PMC | Year 1 | 2500 | 0 |  |  | N/A |  | TBD scope
21 | 84115 | Grind Sidewalk Trip Hazard | Lender PCR Item- Limited trip hazards were observed by Buildings 3825-A, 3777, and the Fitness Center Building. | GC | Year 1 | 2100 | 1025 |  |  | 3 |  | Lender PCR Item- Limited trip hazards were observed by Buildings 3825-A, 3777, and the Fitness Center Building. | [5 empty] | 2025-04-20
135 | 84260 | Mailboxes | Misc repairs | PMC | Year 1 | 2000 | 0 |  |  | N/A |  | Misc repairs
160 | 84239 | Inspect Fire Extinguishers | Lender PCR Item- Fire extinguishers are expired. | PMC | Year 1 | 2000 | 2000 |  |  | N/A |  | Lender PCR Item- Fire extinguishers are expired. | [5 empty] | 2025-04-20
161 | 84211 | Fire Suppression System Inspection | Equity PCR Item 5.5.1- Annual Fire suppression system inspection for Building 3971-3975 | PMC | Year 1 | 1000 | 1000 |  |  | N/A |  | Equity PCR Item 5.5.1- Annual Fire suppression system inspection for Building 3971-3975
162 | 84211 | Fire Alarm System Inspection | Equity PCR Item 5.5.2- Annual fire alarm system inspection for Building 3971-3975. | PMC | Year 1 | 1000 | 1000 |  |  | N/A |  | Equity PCR Item 5.5.2- Annual fire alarm system inspection for Building 3971-3975.
167 |  | PROJECTS subtotal (excl. contingency/CM fee)
166
| 85305 | Construction Management Fee | CM Fees | CMF | CM Fee | 144746 | 113028 |  |  | N/A
| 84510 | Contingency | Contingency Amount | CON | Contingency | 137853 | 0 |  |  | N/A
v

## Swiss Gables
Swiss Gables — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
95 | 84101 | Exterior building Painting | Paint community including peal stop on all delaminated cedar Paint chipping was observed at the columns and posts of the exterior walkways at Building E, on the second-floor north access stair railing of Building F and at the east elevation of Building D. Repairs are recommended. | GC | Year 1 | 189000 | 151200 |  |  | 2 |  | Paint community including peal stop on all delaminated cedar Paint chipping was observed at the columns and posts of the exterior walkways at Building E, on the second-floor north access stair railing | [5 empty] | 2026-08-29
72 | 84104 | Repair balcony framing & decking | Repair damaged patio and Catwalk framing Balcony repair allowance Deteriorating wood was present at the underside of the balcony observed from C-202. Replacement is recommended | GC | Year 1 | 109000 | 81750 |  |  | 2 |  | Repair damaged patio and Catwalk framing Balcony repair allowance Deteriorating wood was present at the underside of the balcony observed from C-202. Replacement is recommended | [5 empty] | 2026-08-29
55 | 84120 | Concrete deck / floor fill | Seal cracks in landings and cat walks | GC | Year 1 | 70000 | 56000 |  |  | 2 |  | Seal cracks in landings and cat walks
132 | 84211 | Seal Penetrations in Fire Walls and Smoke Barriers | Penetrations in the fire and smoke barriers are in poor condition. Penetrations in the fire rated walls were observed as not sealed in the attics of all the buildings. Based on the current condition, we recommend budgeting for a review of these and similar areas with repairs made as needed. | GC | Year 1 | 70000 | 21000 |  |  | 3 |  | Penetrations in the fire and smoke barriers are in poor condition. Penetrations in the fire rated walls were observed as not sealed in the attics of all the buildings. Based on the current condition,
48 | 84219 | Carports / Garages | Repair damaged sheet rock and paint 1st floor parking garages | GC | Year 1 | 66000 | 52800 |  |  | 2 |  | Repair damaged sheet rock and paint 1st floor parking garages
17 | 84204 | Asphalt Coating | Crack fill alligatored asphalt Damaged pavement consisting of linear cracking and alligator cracking was observed east of the northwest entrance, west of Building C, between Buildings B and C, and east of Building D. Centerline cracking was observed north of Building G and a pothole was present west of Building B. Repairs are recommended. | GC | Year 1 | 65000 | 19500 |  |  | 3 |  | Crack fill alligatored asphalt Damaged pavement consisting of linear cracking and alligator cracking was observed east of the northwest entrance, west of Building C, between Buildings B and C, and eas | [5 empty] | 2026-08-29
96 | 84105 | Repair / replace wood trim | Replace all rotted trim throughout property All Facia is Custom Scalloped Facia | GC | Year 1 | 45000 | 36000 |  |  | 2 |  | Replace all rotted trim throughout property All Facia is Custom Scalloped Facia
22 | 84204 | Stripe parking areas | Stripe parking lot and garages | GC | Year 1 | 36000 | 10800 |  |  | 3 |  | Stripe parking lot and garages
73 | 84121 | Repair patio/balcony railings | Secure all balcony and catwalk railings (custom pickets) | GC | Year 1 | 35000 | 28000 |  |  | 2 |  | Secure all balcony and catwalk railings (custom pickets)
87 | 84206 | Repair / replace wood siding | Replace rotted T-111 siding Damaged soffits were observed along the elevated walkway at Building A, isolated areas at the second-floor walkway soffit at Building F, and at the third-floor walkway soffit at Building D. Damaged T-111 siding near the ground surface was present at the north elevation of Building C, and paint chipping and bubbling was present at the ceiling of the tuck under parking at Building D. Repairs or replacement of damaged soffit locations, siding and tuck-under ceiling, and any damaged substructure materials is recommended. Conduct an invasive inspection of the elevated walkway at Building A | GC | Year 1 | 35000 | 28000 |  |  | 2 |  | Replace rotted T-111 siding Damaged soffits were observed along the elevated walkway at Building A, isolated areas at the second-floor walkway soffit at Building F, and at the third-floor walkway soff | [5 empty] | 2026-08-29
162 | 84210 | Common Area Light Fixtures | Replace parking garage and parking lot lights to LED | GC | Year 1 | 32000 | 25600 |  |  | 2 |  | Replace parking garage and parking lot lights to LED
42 | 84340 | Playground equipment | Enhance playground equipment | Capex | Year 1 | 30000 | 0 |  |  | N/A |  | Enhance playground equipment
124 | 84103 | Signage - Building identification | Site Rebrand - New Building Signage/New Door Numbers | Capex | Year 1 | 30000 | 0 |  |  | N/A |  | Site Rebrand - New Building Signage/New Door Numbers
122 | 84290 | Signage - Entry Monument | Site Rebrand - New Monument Sign | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | Site Rebrand - New Monument Sign
161 | 84210 | Electrical Distribution | Repair electric to pole lights and photo cells General electrical deficiencies were observed. The general deficiencies noted are: 1) The bollard lights (4 units) are not functioning, 2) The apartment entry light is damaged at building-C 301C, 3) The breaker filler is missing at the electrical panel located on the exterior wall of Building-C, 4) A data outlet in B103 is missing a plate, and 5) Ground Fault Circuit Interrupters (GFCIs) need to be added in the kitchens of classic units and the first-phase renovated kitchens to enhance electrical safety and ensure compliance with modern electrical codes. Based on the current condition, we recommend budgeting for a review of these and similar areas with repairs made as needed. | GC | Year 1 | 24400 | 19520 |  |  | 2 |  | Repair electric to pole lights and photo cells General electrical deficiencies were observed. The general deficiencies noted are: 1) The bollard lights (4 units) are not functioning, 2) The apartment
153 | 84385 | Sanitary Sewer Piping | Cleanout replacement; Hydrojet as needed | Capex | Year 1 | 24150 | 3967 |  |  | N/A |  | Cleanout replacement; Hydrojet as needed
28 | 84205 | Fences & gates - site perimeter | Repair and paint fence | GC | Year 1 | 21000 | 10500 |  |  | 3 |  | Repair and paint fence
77 | 84433 | Asphalt composite shingle roofing | Roof tune up on 7 buildings | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | Roof tune up on 7 buildings
83 | 84433 | Flashing | Replace damaged drip edge on cat walks | GC | Year 1 | 21000 | 16800 |  |  | 2 |  | Replace damaged drip edge on cat walks
25 | 84115 | Sidewalks | Repair trip Hazards Damaged concrete sidewalk was present at the walkway south of Building G. Repairs are recommended. Repair areas of deteriorated/damaged concrete sidewalk | GC | Year 1 | 18000 | 10800 |  |  | 2 |  | Repair trip Hazards Damaged concrete sidewalk was present at the walkway south of Building G. Repairs are recommended. Repair areas of deteriorated/damaged concrete sidewalk
133 | 84211 | General Fire Alarm Deficiencies | General fire alarm deficiencies were observed. The general deficiency noted is: expired smoke detectors throughout the buildings need to be replaced to ensure the safety of residents and compliance with fire safety regulations. Based on the current condition, we recommend budgeting for a review of these with replacements that include combination carbon monoxide and smoke combination detectors in areas above garages. | Capex | Year 1 | 16100 | 8112 |  |  | N/A |  | General fire alarm deficiencies were observed. The general deficiency noted is: expired smoke detectors throughout the buildings need to be replaced to ensure the safety of residents and compliance wi
46 | 84111 | Dumpster enclosures | Replace fencing on all dumpster enclosures Custom Pickets | GC | Year 1 | 15000 | 12000 |  |  | 2 |  | Replace fencing on all dumpster enclosures Custom Pickets
82 | 83439 | Gutters & downspouts | Clean and secure gutters and down spouts | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Clean and secure gutters and down spouts
84 | 84433 | Sealants & caulking | Sealants & caulking | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Sealants & caulking
71 | 84121 | Repair exterior stair railings | Repair and secure stair railings | GC | Year 1 | 12000 | 9600 |  |  | 2 |  | Repair and secure stair railings
119 | 84211 | Fire protection | Fire protection - Fire Stops | Capex | Year 1 | 10584 | 10381 |  |  | N/A |  | Fire protection - Fire Stops
16 | 84303 | Landscape Cleanup and Enhancements | Isolated locations of tree overgrowth at building elevations were observed. Tree trimming is recommended | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Isolated locations of tree overgrowth at building elevations were observed. Tree trimming is recommended | [5 empty] | 2026-08-29
164 | 84210 | Organize Electrical Wiring | The surface raceway in Building-C, unit C303, requires repair to ensure the proper protection and organization of electrical wiring. Based on the current condition, we recommend budgeting for review of all locations with repairs made as needed | GC | Year 1 | 5000 | 4000 |  |  | 2 |  | The surface raceway in Building-C, unit C303, requires repair to ensure the proper protection and organization of electrical wiring. Based on the current condition, we recommend budgeting for review o
24 | 84115 | Curbing Repairs | Damaged curbing was present southeast of Building C and at the east entrance to Building E. Repairs are recommended. | GC | Year 1 | 1500 | 2000 |  |  | 0 |  | Damaged curbing was present southeast of Building C and at the east entrance to Building E. Repairs are recommended. | [5 empty] | 2026-08-29
38 | 83520 | Install ADA-Compliant Curb Cut Ramps | ADA-compliant curb cut ramps are not present on accessible route at the subject property. Inclusion of ADA-compliant curb cut ramps is recommended. Install compliant curb cuts/ramps on accessible route | PMC | Year 1 | 1200 | 9265 |  |  | N/A |  | ADA-compliant curb cut ramps are not present on accessible route at the subject property. Inclusion of ADA-compliant curb cut ramps is recommended. Install compliant curb cuts/ramps on accessible rout | [5 empty] | 2025-11-29
39 | 83520 | Install ADA-Compliant Handrailing at Ramp | The ramps within the accessible route do not appear to have ADA-compliant handrails. Reconfiguration of the handrails is recommended. | PMC | Year 1 | 1200 | 9265 |  |  | N/A |  | The ramps within the accessible route do not appear to have ADA-compliant handrails. Reconfiguration of the handrails is recommended. | [5 empty] | 2025-11-29
165 | 84210 | Electrical Buzzing Sound | An electrical buzzing sound coming from the underground vault adjacent to the main roadside transformer indicates a potential issue with the electrical equipment housed within the vault. Based on the current condition, we recommend budgeting for immediate corrections | GC | Year 1 | 1000 | 2000 |  |  | 0 |  | An electrical buzzing sound coming from the underground vault adjacent to the main roadside transformer indicates a potential issue with the electrical equipment housed within the vault. Based on the
108 | 83236 | Install CO Detectors | Carbon monoxide detectors are not provided in dwelling units, and wood burning fireplaces were provided in the third floor units at Buildings D, E, F, and G. Because carbon monoxide is a colorless, odorless, poisonous gas that can be produced by the incomplete burning of fossil fuels (including natural gas), installation of carbon monoxide detectors is recommended where natural gas-fueled equipment is in use. | PMC | Year 1 | 770 | 1000 |  |  | N/A |  | Carbon monoxide detectors are not provided in dwelling units, and wood burning fireplaces were provided in the third floor units at Buildings D, E, F, and G. Because carbon monoxide is a colorless, od | [5 empty] | 2025-10-29
40 | 83520 | Install ADA-Compliant Door Hardware | The door at the designated accessible entrance does not appear to have ADA compliant hardware. Installation of ADA compliant hardware is recommended. Provide accessible door threshold < 1/2-inch at doorway. Replace non-compliant door hardware with lever/push type hardware. | PMC | Year 1 | 450 | 3474 |  |  | N/A |  | The door at the designated accessible entrance does not appear to have ADA compliant hardware. Installation of ADA compliant hardware is recommended. Provide accessible door threshold < 1/2-inch at do | [5 empty] | 2025-11-29
37 | 83520 | Install ADA Van-Accessible Space | The accessible parking spaces did not appear to be generally correctly configured. The installation of one van-accessible ADA accessible space for the leasing office is recommended. Provide van-accessible parking spaces adjacent to areas of public accommodation. | PMC | Year 1 | 400 | 3088 |  |  | N/A |  | The accessible parking spaces did not appear to be generally correctly configured. The installation of one van-accessible ADA accessible space for the leasing office is recommended. Provide van-access | [5 empty] | 2025-11-29
154 | 84476 | Install Seismic Strapping | The water heater at the employee restroom in Building C lacked seismic bracing straps. Provision of adequate seismic bracing is recommended. | PMC | Year 1 | 250 | 500 |  |  | N/A |  | The water heater at the employee restroom in Building C lacked seismic bracing straps. Provision of adequate seismic bracing is recommended. | [5 empty] | 2025-10-29
PROJECTS subtotal (excl. contingency/CM fee)
168 | 84505 | Construction Management Fee | CM Fees | CMF | CM Fee | 53250 | 744 | 53250 |  | N/A |  | CM Fees

## The Ardent
The Ardent — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
97 | 84101 | Exterior Painting | Paint community including peal stop on all delaminated cedar | GC | Year 1 | 916200 | 641340 |  |  | 2 |  | Paint community including peal stop on all delaminated cedar
17 | 84204 | Asphalt Coating | Crack fill, seal, and coat Damaged pavement consisting of pothole formation and alligator cracking was observed primarily along drive aisles. Localized repair of the damaged asphalt pavement is recommended. | GC | Year 1 | 260000 | 182000 |  |  | 2 |  | Crack fill, seal, and coat Damaged pavement consisting of pothole formation and alligator cracking was observed primarily along drive aisles. Localized repair of the damaged asphalt pavement is recomm
98 | 84113 | Repair / replace wood trim | Replace all rotted trim throughout property | GC | Year 1 | 158000 | 110600 |  |  | 2 |  | Replace all rotted trim throughout property
89 | 84102 | Repair / replace wood siding | Replace rotted siding and scrape and paint Cedar siding Recommended to evaluate wall cavity conditions and prioritize buildings for phased siding replacement; costs exclude preparation of repair documents. | GC | Year 1 | 110000 | 77000 |  |  | 2 |  | Replace rotted siding and scrape and paint Cedar siding Recommended to evaluate wall cavity conditions and prioritize buildings for phased siding replacement; costs exclude preparation of repair docum
30 | 84303 | Landscaping | Trees were observed impeding on the building envelope at apartment buildings and also at the roofs of the carports. It is recommended that trees be trimmed back from the apartment buildings and carports. | GC | Year 1 | 80000 | 0 |  |  | 4 |  | Trees were observed impeding on the building envelope at apartment buildings and also at the roofs of the carports. It is recommended that trees be trimmed back from the apartment buildings and carpor
85 | 84433 | Roofing - Flashing | Replace damaged drip edge on balconies | GC | Year 1 | 67400 | 47180 |  |  | 2 |  | Replace damaged drip edge on balconies
46 | 84204 | Pavement | R&R 6000 SF of Potholes and the worst alligatored pavement | GC | Year 1 | 60000 | 42000 |  |  | 2 |  | R&R 6000 SF of Potholes and the worst alligatored pavement
79 | 84433 | Asphalt composite shingle roofing | Roof tune up on 37 buildings Isolated areas of damaged and lifted asphalt shingles were observed at Buildings B and S. Repair of the affected shingles is recommended. | GC | Year 1 | 57000 | 39900 |  |  | 2 |  | Roof tune up on 37 buildings Isolated areas of damaged and lifted asphalt shingles were observed at Buildings B and S. Repair of the affected shingles is recommended.
42 | 84219 | Carports | Replace rotted facia on carports Isolated posts show significant deterioration and should be replaced immediately. Recommend phased replacement of remaining posts based on annual inspections. Carports throughout the parking area were observed with localized areas of dryrot conditions at the fascia boards and along the base of the posts. Repair of the damaged wood components is recommended. | GC | Year 1 | 52000 | 36400 |  |  | 2 |  | Replace rotted facia on carports Isolated posts show significant deterioration and should be replaced immediately. Recommend phased replacement of remaining posts based on annual inspections. Carports
44 | 84390 | Sport Court Renovation: Tennis | Repair chain link fence around tennis court. Turn into pickleball | GC | Year 1 | 50000 | 35000 |  |  | 2 |  | Repair chain link fence around tennis court. Turn into pickleball
133 | 84190 | Fitness Center Remodel (Gym 1 Phase II) | Turn yoga studio into pool lounge with Bay door | GC | Year 1 | 50000 | 35000 |  |  | 2 |  | Turn yoga studio into pool lounge with Bay door
86 | 84433 | Roofing - Sealants & caulking | Roof Sealant & Caulking | GC | Year 1 | 49000 | 34300 |  |  | 2 |  | Roof Sealant & Caulking
163 | 84210 | Lighting - Common area light fixtures | Replace walkway pole lights - change to wall pack lights? ($5k) | GC | Year 1 | 48000 | 34600 |  |  | 2 |  | Replace walkway pole lights - change to wall pack lights? ($5k)
71 | 84104 | Repair balcony framing & decking | Repair damaged patio framing | GC | Year 1 | 45000 | 31500 |  |  | 2 |  | Repair damaged patio framing
93 | 84106 | Dryer Vents | Dryer Vent Cleaning | Capex | Year 1 | 42750 | 26044 |  |  | N/A |  | Dryer Vent Cleaning
122 | 84211 | Fire Protection | Includes adding fire stops in all units | Capex | Year 1 | 42750 | 22914 |  |  | N/A |  | Includes adding fire stops in all units
69 | 84114 | Repair exterior stair treads and stringers | Repair stair tread and stringers | GC | Year 1 | 37000 | 25300 |  |  | 2 |  | Repair stair tread and stringers
84 | 83439 | Gutters & downspouts | Clean and secure gutters and down spouts | GC | Year 1 | 37000 | 25900 |  |  | 2 |  | Clean and secure gutters and down spouts
34 | 84361 | Swimming Pool 1 (Phase I: Leasing Office) | Repair cracked conrete & Update Pool Furniture | GC | Year 1 | 35000 | 24500 |  |  | 2 |  | Repair cracked conrete & Update Pool Furniture
35 | 84361 | Swimming Pool 2 (Phase I: Tennis Court) | Repair cracked conrete & Update Pool Furniture (Removed) | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Repair cracked conrete & Update Pool Furniture (Removed)
36 | 84361 | Swimming Pool 3 (Phase II) | Repair gate and paint fence Mark had $7.6K. Repair cracked concrete & Update Pool Furniture | GC | Year 1 | 35000 | 27500 |  |  | 2 |  | Repair gate and paint fence Mark had $7.6K. Repair cracked concrete & Update Pool Furniture
22 | 84204 | Seal & Stripe parking areas | Stripe Parking Lot | GC | Year 1 | 32000 | 22400 |  |  | 2 |  | Stripe Parking Lot
25 | 84115 | Sidewalks | Repair trip hazards Potential trip hazards consisting of damaged concrete and vertical and horizontal separation were present throughout the site including near Buildings B, M, N, P, and Q. Additionally, damaged concrete steps were observed near Building P resulting in a potential trip hazard. Repair of the potential trip hazards is recommended. | GC | Year 1 | 32000 | 22400 |  |  | 2 |  | Repair trip hazards Potential trip hazards consisting of damaged concrete and vertical and horizontal separation were present throughout the site including near Buildings B, M, N, P, and Q. Additional
161 | 84210 | Electrical Distribution | Repair electric to pole lights and photo cells | GC | Year 1 | 32000 | 22400 |  |  | 2 |  | Repair electric to pole lights and photo cells
54 | 84430 | Concrete deck / floor fill | Seal cracks in landings | GC | Year 1 | 28000 | 19600 |  |  | 2 |  | Seal cracks in landings
43 | 84111 | Dumpster enclosures | Replace fencing on all dumpster enclosures | GC | Year 1 | 27000 | 18900 |  |  | 2 |  | Replace fencing on all dumpster enclosures
31 | 84095 | Resurface swimming pool | Resurface Swimming Pool | GC | Year 1 | 25000 | 17500 |  |  | 2 |  | Resurface Swimming Pool
45 | 84390 | Sport Court Renovation: Basketball | Restripe & Add New Hoop | GC | Year 1 | 25000 | 17500 |  |  | 2 |  | Restripe & Add New Hoop
134 | 84190 | Fitness Center Remodel (Gym 2 Phase III) | Convert into golf simulator | GC | Year 1 | 25000 | 0 |  |  | 4 |  | Convert into golf simulator
182 | 82260 | 82260 - Exterior Lighting | Increase lighting across the property - Defer | GC | Year 1 | 25000 | 23993 |  |  | 1 |  | Increase lighting across the property - Defer
90 | 84102 | Masonry Repairs | Repair Exterior Masonry Walls | GC | Year 1 | 23500 | 16450 |  |  | 2 |  | Repair Exterior Masonry Walls
24 | 83520 | Curb cuts | Damaged concrete curbs were observed consisting of displacement and linear cracking were observed at the parking area perimeters. Repair of the damaged curbing is recommended. | GC | Year 1 | 20000 | 14000 |  |  | 2 |  | Damaged concrete curbs were observed consisting of displacement and linear cracking were observed at the parking area perimeters. Repair of the damaged curbing is recommended.
32 | 84361 | Replace swimming pool coping | Replace Pool Coping | GC | Year 1 | 17500 | 12250 |  |  | 2 |  | Replace Pool Coping
72 | 84121 | Repair patio/balcony railings | Secure all balcony railings | GC | Year 1 | 16000 | 11200 |  |  | 2 |  | Secure all balcony railings
140 | 84130 | Dog Park | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | Water/Wash Station with concrete pad ($6k) Dog turf ($10/sqft) Shade sail or pergola
37 | 84432 | Storm Sewer Piping | Clean Yard Basin | GC | Year 1 | 14000 | 9800 |  |  | 2 |  | Clean Yard Basin
51 | 84430 | Foundation - Seal pier and beam area | Replace damaged foundation vents | GC | Year 1 | 12000 | 8400 |  |  | 2 |  | Replace damaged foundation vents
70 | 84121 | Repair exterior stair railings | Repair and secure stair railings | GC | Year 1 | 12000 | 8400 |  |  | 2 |  | Repair and secure stair railings
73 | 83426 | Exterior Doors - replacement doors at patio and balc | Patio & Balcony Storage Doors | GC | Year 1 | 12000 | 8400 |  |  | 2 |  | Patio & Balcony Storage Doors
67 | 84211 | Fire - Draft Stops | Allowance to seal small penetrations in attic draft stops - Small openings were observed within the demising draft stop wall assembly, within attic spaces. Per the Fire Code, draft stops are required to be maintained, where provided. Sealing these penetrations will mitigate smoke and heat transfer during a fire event. | GC | Year 1 | 10000 | 19836 |  |  | 0 |  | Allowance to seal small penetrations in attic draft stops - Small openings were observed within the demising draft stop wall assembly, within attic spaces. Per the Fire Code, draft stops are required
74 | 84102 | Building Repairs & Exterior Walls | The exterior walls were observed with vegetative staining, peeling paint, and areas of damaged siding at the exterior walls, outboard sides of breezeways, and at balcony walls throughout the subject property including at Buildings B, C, E, G, and H. Localized cleaning, repainting, and repair of the affected areas is recommended. | GC | Year 1 | 10000 | 7000 |  |  | 2 |  | The exterior walls were observed with vegetative staining, peeling paint, and areas of damaged siding at the exterior walls, outboard sides of breezeways, and at balcony walls throughout the subject p
95 | 84113 | Breezeway soffit repairs | Add soffit vents at Phase 3 breezeways to improve attic ventilation and enhance moisture control; addresses incomplete ventilation currently relying on gable vents only.(Removed) | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Add soffit vents at Phase 3 breezeways to improve attic ventilation and enhance moisture control; addresses incomplete ventilation currently relying on gable vents only.(Removed)
39 | 84340 | Playground equipment | Replace fall zone mulch | GC | Year 1 | 5400 | 3780 |  |  | 2 |  | Replace fall zone mulch
61 | 84110 | Stairs - Repair or replace damaged concrete treads a | Replace sill plate supporting stair landing post outside of Unit 24 at Building 03C - Still plate has signficant rot | GC | Year 1 | 2000 | 1400 |  |  | 2 |  | Replace sill plate supporting stair landing post outside of Unit 24 at Building 03C - Still plate has signficant rot
107 | 84217 | Seismic Shutoff Valve | There is a natural gas line provided to Fitness Center B, and it is not provided with a seismic shutoff valve. Provide a seismic shutoff valve on the natural gas service. Seismic shutoff valves stop the flow of gas following a seismic event and are a recommended upgrade for buildings in seismically active zones. | PMC | Year 1 | 1000 | 1000 |  |  | N/A |  | There is a natural gas line provided to Fitness Center B, and it is not provided with a seismic shutoff valve. Provide a seismic shutoff valve on the natural gas service. Seismic shutoff valves stop t
106 | 84209 | Water Heater Strapping | This item is for compliance with Section 507.2 of the Washington Plumbing Code. This item can be carried out as part of standard building maintenance, The water heaters in the leasing office, one fitness center, and one of the residential units were not provided with seismic straps. All water heaters throughout the property should be strapped within the upper third and lower third of its vertical dimensions. | PMC | Year 1 | 300 | 300 |  |  | N/A |  | This item is for compliance with Section 507.2 of the Washington Plumbing Code. This item can be carried out as part of standard building maintenance, The water heaters in the leasing office, one fitn
PROJECTS subtotal (excl. contingency/CM fee)
169 | 84505 | Construction Management Fee | CM Fee | CMF | CM Fee | 140427 | 2951 | 140427 |  | N/A |  | CM Fee
168 | 84510 | Contingency | Contingency Amount | CON | Contingency | 133740 | 0 | 133740 |  | N/A |  | Contingency Amount

## The Fairways
The Fairways — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
18 | 84204 | Asphalt Coating | Crack fill and double seal coat asphalt throughout property. Includes Lender PCR Item- Damaged pavement consisting of linear cracking, alligator cracking, and surface raveling was present at the drive aisles typical of the conditions noted near Building 8. Repair is recommended. | GC | Year 1 | 298500 | 298500 |  |  | 0 |  | Crack fill and double seal coat asphalt throughout property. Includes Lender PCR Item- Damaged pavement consisting of linear cracking, alligator cracking, and surface raveling was present at the driv | [5 empty] | 2026-02-01
53 | 84101 | Repair balcony framing & decking | Half the properties balconies are showing signs of weathering due to moisture/rot. Replace any rotted wood and scrap, sand salvagable areas. Paint to match. | GC | Year 1 | 95000 | 95000 |  |  | 0 |  | Half the properties balconies are showing signs of weathering due to moisture/rot. Replace any rotted wood and scrap, sand salvagable areas. Paint to match.
21 | 84300 | Landscaping | Tree trim and clean up throughout property. 1st Call getting bid in conjunction with Paddocks to improve cost | GC | Year 1 | 92800 | 92800 |  |  | 0 |  | Tree trim and clean up throughout property. 1st Call getting bid in conjunction with Paddocks to improve cost
64 | 84433 | Asphalt composite shingle roofing | Replace flashing around all chimneys throughout property as well as a minor roof tune up to each building. Any significant water damage or other damage we will need to consider a change order. | GC | Year 1 | 50000 | 50000 |  |  | 0 |  | Replace flashing around all chimneys throughout property as well as a minor roof tune up to each building. Any significant water damage or other damage we will need to consider a change order.
124 | 84360 | Pool Furniture | Maybe budget for full replacement. Tables and chairs look ok, 24 chaises are ok but a cheaper style. Budget for new, a few new trash cans - TV contacting Key Designs | Capex | Year 1 | 50000 | 75016 |  |  | N/A |  | Maybe budget for full replacement. Tables and chairs look ok, 24 chaises are ok but a cheaper style. Budget for new, a few new trash cans - TV contacting Key Designs
75 | 84206 | Repair / replace cement fiber siding | Repair/replace areas of failed hardie board and paint to match throughout property | GC | Year 1 | 41500 | 41500 |  |  | 0 |  | Repair/replace areas of failed hardie board and paint to match throughout property
22 | 84095 | Resurface swimming pool | Resurface pool | GC | Year 1 | 40000 | 32200 |  |  | 2 |  | Resurface pool
76 | 84113 | Repair / replace wood trim | Repair/replace rotted trim, fascia throughout peroperty. Paint to match. | GC | Year 1 | 38500 | 38500 |  |  | 0 |  | Repair/replace rotted trim, fascia throughout peroperty. Paint to match.
157 | 84210 | Replace breezeway lights | Breezeway Lighting | GC | Year 1 | 37500 | 37500 |  |  | 0 |  | Breezeway Lighting
24 | 84361 | Repair swimming pool deck | Clean pool deck, crack fill and seal. Repair the deck attached to pool deck and repaint/stain. Reinforce and lvel support structure under decking. Composite planking is currently there. | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Clean pool deck, crack fill and seal. Repair the deck attached to pool deck and repaint/stain. Reinforce and lvel support structure under decking. Composite planking is currently there.
125 | 84203 | Picnic/Grill Area Remodel | Look at adding grills and outdoor kitchen, gazebo, landscaping or turf in planters, replace/fix lights | GC | Year 1 | 30000 | 27000 |  |  | 1 |  | Look at adding grills and outdoor kitchen, gazebo, landscaping or turf in planters, replace/fix lights
25 | 84130 | Dog Park | Replace chainlink fencing around dog park and replace with aluminum fencing. Add enzyme injector to irrigation valve | GC | Year 1 | 26000 | 7800 |  |  | 3 |  | Replace chainlink fencing around dog park and replace with aluminum fencing. Add enzyme injector to irrigation valve
127 | 84390 | Sports Courts | Resurface and add 2 pickleball courts along with tennis | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Resurface and add 2 pickleball courts along with tennis
153 | 84218 | HVAC inspection and maintenance | Clean foliage around condensors throughout property. Raise units with HVAC pad as needed. | GC | Year 1 | 24000 | 24000 |  |  | 0 |  | Clean foliage around condensors throughout property. Raise units with HVAC pad as needed.
20 | 84221 | Sidewalks | Repair cracked/broken sidewalks throughout property. | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | Repair cracked/broken sidewalks throughout property.
156 | 84210 | Electrical distribution | Electrical Distribution | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | Electrical Distribution
14 | 84300 | Landscape Cleanup and Enhancements | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc | Capex | Year 1 | 20000 | 27840 |  |  | N/A |  | Initial property tree trim, landscape cleanup, entry and tour path enhancements, etc
98 | 84106 | Drier vents | Clean dryer vents throughout property. | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | Clean dryer vents throughout property.
17 | 84221 | concrete pavement | Fill cracks and seal area next to dog park and sports court. | GC | Year 1 | 17500 | 17500 |  |  | 0 |  | Fill cracks and seal area next to dog park and sports court.
108 | 82131 | CO detectors | Install CO detectors in each unit. Lender PCA Item- Due to the presence of gas-fire water heaters at each unit, carbon monoxide detectors are required. Installation of carbon monoxide detectors recommended. TV - team to order and install on turns/PM inspections/work orders | Capex | Year 1 | 16800 | 0 |  |  | N/A |  | Install CO detectors in each unit. Lender PCA Item- Due to the presence of gas-fire water heaters at each unit, carbon monoxide detectors are required. Installation of carbon monoxide detectors recomm | [5 empty] | 2026-02-01
119 | 84208 | Clubhouse / Office Remodel | Paint cabinets in kitchen with hardware, add backsplash, replace appliances, replace "snack shack" window to be functional, replace counter top to allow a pass through from the clubhouse without going through the workspace | GC | Year 1 | 15000 | 15000 |  |  | 0 |  | Paint cabinets in kitchen with hardware, add backsplash, replace appliances, replace "snack shack" window to be functional, replace counter top to allow a pass through from the clubhouse without going
123 | 84361 | Pool Area Remodel | Games and placeholder budget - TV contacting Key Designs | Capex | Year 1 | 15000 | 65776 |  |  | N/A |  | Games and placeholder budget - TV contacting Key Designs
15 | 84209 | Sanitary sewer piping | Add rocks around storm drains around property. Clean the area around the drain. | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | Add rocks around storm drains around property. Clean the area around the drain.
109 | 84239 | Fire Stops | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods TV to verify with Dan H on ordering | Capex | Year 1 | 11723 | 0 |  |  | N/A |  | Basic Fire Stop (Pair covers 4 burner range)- For range vent hoods TV to verify with Dan H on ordering
19 | 84201 | ADA parking & curb cuts | Include where needed in concrete/asphalt work | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Include where needed in concrete/asphalt work
120 | 82140 | Clubhouse / Office Furniture | Looks good, misc supplemental items - Add a TV. TAM to order and install. Move the leasing desktop to back work area, purchase a laptop for touring and selling and lock the workspace to allow for office closure while renting the clubhouse | Capex | Year 1 | 10000 | 10439 |  |  | N/A |  | Looks good, misc supplemental items - Add a TV. TAM to order and install. Move the leasing desktop to back work area, purchase a laptop for touring and selling and lock the workspace to allow for offi
126 | 84195 | Picnic/Grill Furniture | Tables ok, possibly add games | Capex | Year 1 | 10000 | 24300 |  |  | N/A |  | Tables ok, possibly add games
134 | 84206 | Storage Shed | Look at adding storage shed for appliances next to maintenance - enclose area to left of maintenance shop | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Look at adding storage shed for appliances next to maintenance - enclose area to left of maintenance shop
16 | 84385 | Storm sewer piping | Improve current french drain towards the back right of the property. | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | Improve current french drain towards the back right of the property.
51 | 84114 | Repair exterior stair treads and stringers | Secure. | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Secure.
52 | 84121 | Repair exterior stair railings | Secure. | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | Secure.
131 | 84275 | Access Control System | Need for pool area and bathroom doors - just updating to keypad. Review for future FOB system for afterhours access on amenity rental | PMC | Year 1 | 6000 | 0 |  |  | N/A |  | Need for pool area and bathroom doors - just updating to keypad. Review for future FOB system for afterhours access on amenity rental
128 | 84130 | Dog Park | Looks good, misc budget - add enzyme injector | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Looks good, misc budget - add enzyme injector
158 | 84361 | Pool area lighting | Lights are all 110 and need to be rewired | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Lights are all 110 and need to be rewired
23 | 84361 | Replace swimming pool coping | Deck-O-Seal coping around pool. And relocate pots off the new deck to avoid further damage | GC | Year 1 | 4500 | 4500 |  |  | 0 |  | Deck-O-Seal coping around pool. And relocate pots off the new deck to avoid further damage
26 | 84111 | Dumpster enclosures | Repair any damage on dumpster enclosure. | GC | Year 1 | 2150 | 2150 |  |  | 0 |  | Repair any damage on dumpster enclosure.
27 | 84434 | Retaining walls | Retaining wall needs repair by sport court - replace with stone wall | GC | Year 1 | 2000 | 2000 |  |  | 0 |  | Retaining wall needs repair by sport court - replace with stone wall
PROJECTS subtotal (excl. contingency/CM fee)
163 | 84510 | Contingency | Contingency Amount | CON | Contingency | 178027 | 0 | 178027 |  | N/A |  | Contingency Amount
164 | 84505 | Construction Management Fee | CM Fee | CMF | CM Fee | 66000 | 65889 | 66000 |  | N/A |  | CM Fee

## The Lakes
The Lakes — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
18 | 84204 | Asphalt Coating | Lakes - Crack fill, seal and coating Revive - Crack fill, seal and coating | GC | Year 1 | 455000 | 136500 |  |  | 3 |  | Lakes - Crack fill, seal and coating Revive - Crack fill, seal and coating
76 | 84433 | Asphalt Composite Shingle Roofing | Lakes - Roof tune up on buildings 9 Revive - Replace Roofs | GC | Year 1 | 428000 | 428000 |  |  | 0 |  | Lakes - Roof tune up on buildings 9 Revive - Replace Roofs
96 | 84101 | Exterior Building Paint | Lakes - Paint community Revive - Paint community | GC | Year 1 | 348000 | 104400 |  |  | 3 |  | Lakes - Paint community Revive - Paint community
132 | 84190 | Fitness Center Remodel | Revive - Convert Leasing office into a Gym | GC | Year 1 | 100000 | 30000 |  |  | 3 |  | Revive - Convert Leasing office into a Gym
30 | 84303 | Landscaping | Lakes - Tree trim and raise canopy | GC | Year 1 | 64000 | 19200 |  |  | 3 |  | Lakes - Tree trim and raise canopy
22 | 84205 | Fencing | Take down the chain-link fence separating properties. Add two paths for golf cart to travel between. Add walking path - gravel or stone | GC | Year 1 | 50000 | 15000 |  |  | 3 |  | Take down the chain-link fence separating properties. Add two paths for golf cart to travel between. Add walking path - gravel or stone
54 | 84430 | Concrete Deck / Floor Fill | Lakes - Seal cracks in landings Revive - Seal cracks in landings | GC | Year 1 | 41000 | 12300 |  |  | 3 |  | Lakes - Seal cracks in landings Revive - Seal cracks in landings
17 | 84303 | Landscape Cleanup and Enhancements | Lakes - Landscape Enhancements Revive - Landscape Enhancements | Capex | Year 1 | 40000 | 0 |  |  | N/A |  | Lakes - Landscape Enhancements Revive - Landscape Enhancements
87 | 84102 | Repair / Replace Wood Siding | Lakes - Replace rotted siding and scrape and paint Cedar siding Revive - Replace rotted siding and scrape and paint Cedar siding LRR - Limited damaged wood siding was observed at Revive Building 2349. | GC | Year 1 | 40000 | 12000 |  |  | 3 |  | Lakes - Replace rotted siding and scrape and paint Cedar siding Revive - Replace rotted siding and scrape and paint Cedar siding LRR - Limited damaged wood siding was observed at Revive Building 2349 | [5 empty] | 2025-12-30
97 | 84113 | Repair / Replace Wood Trim | Lakes - Replace all rotted trim throughout property Revive - Replace all rotted trim throughout property | GC | Year 1 | 40000 | 12000 |  |  | 3 |  | Lakes - Replace all rotted trim throughout property Revive - Replace all rotted trim throughout property
147 | 84450 | Security Camera System | Install new Security Cameras | Capex | Year 1 | 35000 | 0 |  |  | N/A |  | Install new Security Cameras
133 | 84208 | Cyber Café upgrade at Lakes | Lakes - Open up the side wall and expand the leasing area | GC | Year 1 | 30000 | 9000 |  |  | 3 |  | Lakes - Open up the side wall and expand the leasing area
26 | 84115 | Sidewalks Trip Hazard | Lakes - Repair trip hazards Revive - Repair trip hazards. A limited sidewalk crack was also observed by Building 2335. Crack routing and sealing are recommended. LRR - A limited area of the sidewalks at Revive was observed to have deterioration and an uneven edge, resulting in a trip hazard. This condition was specifically observed by Building 2335. CBRE recommends grinding down of edges or sectional replacement of sidewalks as necessary to eliminate trip hazards. | GC | Year 1 | 29000 | 8700 |  |  | 3 |  | Lakes - Repair trip hazards Revive - Repair trip hazards. A limited sidewalk crack was also observed by Building 2335. Crack routing and sealing are recommended. LRR - A limited area of the sidewalks | [5 empty] | 2025-12-30
23 | 84201 | Stripe Parking Areas | Lakes - Stripe Parking Lot Revive - Stripe Parking Lot | GC | Year 1 | 28000 | 8400 |  |  | 3 |  | Lakes - Stripe Parking Lot Revive - Stripe Parking Lot
25 | 83520 | ADA Parking & Curb Cuts | Lakes - Concrete Modifications Revive - Concrete Modifications | GC | Year 1 | 26000 | 7800 |  |  | 3 |  | Lakes - Concrete Modifications Revive - Concrete Modifications
29 | 84204 | Pavement | Lakes - R&R 2000 Sf of Potholes Revive - R&R 1500 sq ft pavement | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | Lakes - R&R 2000 Sf of Potholes Revive - R&R 1500 sq ft pavement
43 | 84111 | Dumpster Enclosures | Lakes - Replace fencing on all dumpster enclosures Revive - Replace fencing on all dumpster enclosures | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | Lakes - Replace fencing on all dumpster enclosures Revive - Replace fencing on all dumpster enclosures
68 | 84114 | Repair Exterior Stair Treads and Stringers | Lakes - Repair stair tread and stringers Revive - Repair stair tread and stringers | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | Lakes - Repair stair tread and stringers Revive - Repair stair tread and stringers
121 | 84211 | Fire Stops | Add Fire Stops | Capex | Year 1 | 24696 | 18931 |  |  | N/A |  | Add Fire Stops
69 | 84121 | Repair Exterior Stair Railings | Lakes - Repair and secure stair railings Revive - Repair and secure stair railings | GC | Year 1 | 24000 | 7200 |  |  | 3 |  | Lakes - Repair and secure stair railings Revive - Repair and secure stair railings
27 | 84432 | Storm Sewer Piping | Lakes - Clean Yard Basins of Debris Revive - Clean Yard Basins of Debris | GC | Year 1 | 23000 | 6900 |  |  | 3 |  | Lakes - Clean Yard Basins of Debris Revive - Clean Yard Basins of Debris
82 | 84433 | Flashing | Lakes - Replace damaged drip edge on balconies. Revive - Replace damaged drip edge on balconies. LRR - Damaged balconies were observed at Revive. Significant wood deck and railing damage was observed on the balcony of Unit 2335-7, and limited wood deck damage was observed on the balcony of Unit 2351-8. Repair/ replacement of damaged wood decking and railing is recommended. | GC | Year 1 | 22800 | 6840 |  |  | 3 |  | Lakes - Replace damaged drip edge on balconies. Revive - Replace damaged drip edge on balconies. LRR - Damaged balconies were observed at Revive. Significant wood deck and railing damage was observe | [5 empty] | 2025-12-30
70 | 84104 | Repair Balcony Framing & Decking | Lakes - Repair damaged patio framing Revive - Repair damaged patio framing | GC | Year 1 | 22000 | 6600 |  |  | 3 |  | Lakes - Repair damaged patio framing Revive - Repair damaged patio framing
71 | 84121 | Repair Patio/Balcony Railings | Lakes - Secure all balcony railings Revive - Secure all balcony railings | GC | Year 1 | 22000 | 6600 |  |  | 3 |  | Lakes - Secure all balcony railings Revive - Secure all balcony railings
81 | 84202.0 | Gutters & Downspouts | Lakes - Clean and secure gutters and down spouts Revive - Clean and secure gutters and down spouts | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | Lakes - Clean and secure gutters and down spouts Revive - Clean and secure gutters and down spouts
83 | 84102 | Sealants & Caulking | Lakes - Roof Sealants & Caulking Revive - Roof Sealants & Caulking | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | Lakes - Roof Sealants & Caulking Revive - Roof Sealants & Caulking
38 | 84361 | Pool Area | Lakes - Enhance pool area with turf and a fireplace | GC | Year 1 | 20000 | 6000 |  |  | 3 |  | Lakes - Enhance pool area with turf and a fireplace
36 | 84205 | Fences & Gates - Swimming Pool | Lakes - Repair gate and paint fence Revive - Repair gate and paint fence | GC | Year 1 | 16200 | 4860 |  |  | 3 |  | Lakes - Repair gate and paint fence Revive - Repair gate and paint fence
28 | 84205 | Fences & Gates - Site Perimeter | Revive - Add ~200ft wall between Revive and comp with razor wire | GC | Year 1 | 15000 | 4500 |  |  | 3 |  | Revive - Add ~200ft wall between Revive and comp with razor wire
130 | 83375 | Leasing Golf Cart | Get Leasing Golf Cart | Capex | Year 1 | 15000 | 16200 |  |  | N/A |  | Get Leasing Golf Cart
67 | 84433 | Roof Deck | Revive - Roof Deck Repairs | GC | Year 1 | 13000 | 13000 |  |  | 0 |  | Revive - Roof Deck Repairs
156 | 84385 | Sanitary Sewer Piping | Lakes - Building C - Minor tree root intrusion. Recommended remediation: Dig approximately 4 feet and replace the affected section of the pipe and backfill.$4,800 Building D - Pipe obstruction. Recommended remediation: Hydro jetting to clear the line and verify it's not a structural issue.$1,800 | PMC | Year 1 | 6600 | 0 |  |  | N/A |  | Lakes - Building C - Minor tree root intrusion. Recommended remediation: Dig approximately 4 feet and replace the affected section of the pipe and backfill.$4,800 Building D - Pipe obstruction. Recomm
107 | 82460 | Repair Microbial Growth | LRR - Limited areas of microbial growth was observed in the bedroom corner and closet wall of Unit 2347-1. Affected non-porous surfaces should be cleaned. Affected porous materials, namely drywall, should be removed and replaced if any affected. | PMC | Year 1 | 900 | 0 |  |  | N/A |  | LRR - Limited areas of microbial growth was observed in the bedroom corner and closet wall of Unit 2347-1. Affected non-porous surfaces should be cleaned. Affected porous materials, namely drywall, sh | [5 empty] | 2025-12-30
32 | 83520 | ADA Modifications | Revive - Common area restroom sink is not insulated at clubhouse. LRR- ADA sink insulation | PMC | Year 1 | 350 | 0 |  |  | N/A |  | Revive - Common area restroom sink is not insulated at clubhouse. LRR- ADA sink insulation | [5 empty] | 2025-12-30
PROJECTS subtotal (excl. contingency/CM fee)
174 | 84505 | Construction Management Fee | CM Fee | CMF | CM Fee | 119624 | 443 | 119624 |  | N/A |  | CM Fee
173 | 84510 | Contingency | Contingency Amount | CON | Contingency | 104927 | 0 | 104927 |  | N/A |  | Contingency Amount

## The Vibe
The Vibe — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
52 | 84101 | Exterior building | PNA - Paint community including peal stop on all delaminated cedar LPCA - Faded paint finishes were observed at several locations, most notably on Building E. Reapplication of exterior paint is recommended. HPCA - Replace/epoxy 11 posts with moderate wood rot at base; and Barge Rafters HPCA - Replace/repair dryrot fascia and siding boards at various locations | GC | Year 1 | 592200 | 532980 |  |  | 1 |  | PNA - Paint community including peal stop on all delaminated cedar LPCA - Faded paint finishes were observed at several locations, most notably on Building E. Reapplication of exterior paint is recomm | [5 empty] | 2026-07-14
24 | 84095 | Resurface swimming pool | PNA - contingent amount to work on pool resurface | GC | Year 1 | 70000 | 21000 |  |  | 3 |  | PNA - contingent amount to work on pool resurface
16 | 84204 | Asphalt Coating | PNA - contingent amount to work on parking lot as needed. LPCA - Linear/alligator cracking and pothole formation was observed at various locations, most notably along the drive aisles near Buildings B and N. | GC | Year 1 | 68000 | 40800 |  |  | 2 |  | PNA - contingent amount to work on parking lot as needed. LPCA - Linear/alligator cracking and pothole formation was observed at various locations, most notably along the drive aisles near Buildings B | [5 empty] | 2026-07-14
27 | 84095 | Replace swimming pool deck | PNA - address existing cracking on pool decks and cosmetic enhacement | GC | Year 1 | 40000 | 12000 |  |  | 3 |  | PNA - address existing cracking on pool decks and cosmetic enhacement
45 | 84050 | Asphalt composite shingle roofing | PNA - Roof tune up on 37 buildings | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | PNA - Roof tune up on 37 buildings
59 | 84450 | Security Camera System | Adding 9 security cameras (inc. installation, labor, etc.) | Capex | Year 1 | 37000 | 0 |  |  | N/A |  | Adding 9 security cameras (inc. installation, labor, etc.)
66 | 84210 | Replace electrical panels | HPCA - Replace 8 Electrical Panels (Estimated Potential Recalled Heaters) | GC | Year 1 | 36000 | 10800 |  |  | 3 |  | HPCA - Replace 8 Electrical Panels (Estimated Potential Recalled Heaters)
53 | 84105 | Repair / replace wood trim | PNA - Replace all rotted trim throughout property | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | PNA - Replace all rotted trim throughout property
17 | 84090 | Stripe parking areas | PNA - stripe parking lot | GC | Year 1 | 32000 | 9600 |  |  | 3 |  | PNA - stripe parking lot
46 | 84050 | Gutters & downspouts | PNA - Clean and secure gutters and down spouts HPCA - Repair selective areas of damaged gutter; reconnect Downspouts to underground piping | GC | Year 1 | 32000 | 32000 |  |  | 0 |  | PNA - Clean and secure gutters and down spouts HPCA - Repair selective areas of damaged gutter; reconnect Downspouts to underground piping
38 | 84102 | Concrete deck / floor fill | PNA - seal cracks in landings | GC | Year 1 | 26000 | 18200 |  |  | 2 |  | PNA - seal cracks in landings
48 | 84050 | Sealants & caulking | Roof Sealant & Caulking | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | Roof Sealant & Caulking
55 | 84239 | Fire Protection | Fire Stops | Capex | Year 1 | 24675 | 2798 |  |  | N/A |  | Fire Stops
22 | 84205 | Fences & gates - site perimeter | PNA - Pool fence is vinyl and post holding up the fence are rotting. Repair posts and repair fence | GC | Year 1 | 24000 | 19200 |  |  | 2 |  | PNA - Pool fence is vinyl and post holding up the fence are rotting. Repair posts and repair fence
20 | 84080 | Sidewalks | PNA - Repair trip hazards HPCA - Concrete Walks/Steps - Trip Hazards/ADA | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | PNA - Repair trip hazards HPCA - Concrete Walks/Steps - Trip Hazards/ADA
42 | 84104 | Repair balcony framing & decking | PNA - repair damaged patio framing | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | PNA - repair damaged patio framing
50 | 84105 | Repair / replace wood siding | PNA - Replace rotted siding and scrape and paint Cedar siding | GC | Year 1 | 18000 | 18000 |  |  | 0 |  | PNA - Replace rotted siding and scrape and paint Cedar siding
30 | 84085 | Carports / Garages | PNA - Replace rotted facia on carports | GC | Year 1 | 17000 | 17000 |  |  | 0 |  | PNA - Replace rotted facia on carports
40 | 84114 | Repair exterior stair treads and stringers | PNA - repair stair tread and stringers | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | PNA - repair stair tread and stringers
43 | 84205 | Repair patio/balcony railings | PNA - secure all balcony railings | GC | Year 1 | 16000 | 16000 |  |  | 0 |  | PNA - secure all balcony railings
21 | 84470 | Storm sewer piping | PNA - Clean yard basins of debree | GC | Year 1 | 12000 | 9600 |  |  | 2 |  | PNA - Clean yard basins of debree
29 | 84125 | Dumpster enclosures | PNA - Replace fencing on all dumpster enclosures | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | PNA - Replace fencing on all dumpster enclosures
41 | 84205 | Repair exterior stair railings | PNA - repair and secure stair railings | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | PNA - repair and secure stair railings
47 | 84050 | Flashing | PNA - Replace damaged drip edge on balconies | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | PNA - Replace damaged drip edge on balconies
57 | 84304 | Bathroom cleaning/klitz/painting with organic growth | HPCA - Excessive damage repair and repainting | Capex | Year 1 | 12000 | 0 |  |  | N/A |  | HPCA - Excessive damage repair and repainting
68 | 84210 | Electrical distribution | PNA - Repair electric to pole lights and photo cells | GC | Year 1 | 12000 | 12000 |  |  | 0 |  | PNA - Repair electric to pole lights and photo cells
25 | 84095 | Pool Lift | HPCA - Add ADA lift to 1 pool | GC | Year 1 | 9500 | 2850 |  |  | 3 |  | HPCA - Add ADA lift to 1 pool
26 | 84095 | Pool Pumps | HPCA - Install variable speed pool pumps with VFD control | GC | Year 1 | 8659 | 2598 |  |  | 3 |  | HPCA - Install variable speed pool pumps with VFD control
15 | 84300 | Landscape Cleanup and Enhancements | HPCA - Tree trimming/removal overhanging structures | PMC | Year 1 | 7500 | 4077 |  |  | N/A |  | HPCA - Tree trimming/removal overhanging structures
23 | 84080 | Move topsoil/mulch away from bldg. siding | HPCA - Backfill exposed/undercut concrete steps and foundations | GC | Year 1 | 7500 | 6000 |  |  | 2 |  | HPCA - Backfill exposed/undercut concrete steps and foundations
69 | 84210 | Common area light fixtures | PNA - Replace pole lights around pool | GC | Year 1 | 7500 | 7500 |  |  | 0 |  | PNA - Replace pole lights around pool
63 | 84218 | Inspect defective heaters | HPCA - Review Cadet Heaters and replace any Models installed between 1982 through 1999 Modles: FW, FX, LX, TK, ZA, Z, RA, RK, RLX, RX and ZC. | GC | Year 1 | 5250 | 5250 |  |  | 0 |  | HPCA - Review Cadet Heaters and replace any Models installed between 1982 through 1999 Modles: FW, FX, LX, TK, ZA, Z, RA, RK, RLX, RX and ZC.
64 | 84210 | Inspect defective ITE electrical panels | HPCA - Given the Bldg.'s were constructed between 1985 and 1986 there is the potential some of the Unit ITE Electrical Panels may be defective H2586-H3186, J0186-J3086, or K0186- K2486. Units should be reviewed to confirm no defective panels are on site (we note panels observed were largely F and K from 1985 which do not require replacement. | GC | Year 1 | 5250 | 5250 |  |  | 0 |  | HPCA - Given the Bldg.'s were constructed between 1985 and 1986 there is the potential some of the Unit ITE Electrical Panels may be defective H2586-H3186, J0186-J3086, or K0186- K2486. Units should b
31 | 84432 | Drainage correction | HPCA - Drainage corrections at carports | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | HPCA - Drainage corrections at carports
51 | 84105 | Repair stucco | Exterior Stucco Repair | GC | Year 1 | 5000 | 5000 |  |  | 0 |  | Exterior Stucco Repair
28 | 84122 | Playground area | HPCA - Add ADA path of travel to playground | GC | Year 1 | 3500 | 1050 |  |  | 3 |  | HPCA - Add ADA path of travel to playground
65 | 842220 | Replace recalled heaters | HPCA - Replace 16 Recalled Heaters (Estimated Potential Recalled Heaters) | GC | Year 1 | 3200 | 960 |  |  | 3 |  | HPCA - Replace 16 Recalled Heaters (Estimated Potential Recalled Heaters)
56 | 84470 | Unit Water Leak Repairs | HPCA - Unit P104 Bathroom Water Leak Repairs | PMC | Year 1 | 3000 | 0 |  |  | N/A |  | HPCA - Unit P104 Bathroom Water Leak Repairs
19 | 84090 | ADA parking & curb cuts | Concrete Modifications | GC | Year 1 | 2250 | 675 |  |  | 3 |  | Concrete Modifications
61 | 84470 | Water Distribution and Domestic Hot Water | Discuss with maintenace manager | PMC | Year 1 | 2250 | 0 |  |  | N/A |  | Discuss with maintenace manager
70 | 84210 | Outlets & Dryer Vents | Contingent as needed | PMC | Year 1 | 2000 | 5003 |  |  | N/A |  | Contingent as needed
39 | 84105 | Unit Deck Resurfacing | HPCA - Bldg. M Unit 302 Deck resurfacing. Exposed painted plywood at unit deck surface | GC | Year 1 | 1200 | 360 |  |  | 3 |  | HPCA - Bldg. M Unit 302 Deck resurfacing. Exposed painted plywood at unit deck surface
18 | 84085 | Parking equipment | HPCA - Add ADA van stall at Carport | GC | Year 1 | 500 | 150 |  |  | 3 |  | HPCA - Add ADA van stall at Carport
PROJECTS subtotal (excl. contingency/CM fee)
72 | 84510 | Contingency | Contingency Amount | CON | Contingency | 229733 | 0 | 229733 |  | N/A |  | Contingency Amount
73 | 84505 | Construction Management Fee | CM Fees | CMF | CM Fee | 78333 | 14601 | 78333 |  | N/A |  | CM Fees

## Valera Riverside
Valera Riverside — 2025 acq · GC GL fallback |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
126 | 84103.0 | Signage - Building identification | *Per Kevin for Signage Change/Rebrand | Capex | Year 1 | 50000 | 11160 |  |  | N/A |  | *Per Kevin for Signage Change/Rebrand
120 | 84239.0 | Fire Stops | Fire stops | Capex | Year 1 | 25480 | 3345 |  |  | N/A |  | Fire stops
28 | 84434.0 | Retaining walls | Paint mural on retaining wall outside pool | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | Paint mural on retaining wall outside pool
131 | 84190.0 | Fitness Center Remodel | additional equipment | Capex | Year 1 | 20000 | 1814 |  |  | N/A |  | additional equipment
36 | 84195.0 | Pergola | repair and stain bar and deck | GC | Year 1 | 9500 | 0 |  |  | 4 |  | repair and stain bar and deck
18 | 84361.0 | Repair / replace swimming pool pumps | seal small cracks on pool deck | GC | Year 1 | 6500 | 0 |  |  | 4 |  | seal small cracks on pool deck
145 | 84211.0 | Security/ fire alarm systems | Yellow, Non-Compliance tags were observed affixed to the sprinkler risers, dated May 2025. | PMC | Year 1 | 5000 | 35874 |  |  | N/A |  | Yellow, Non-Compliance tags were observed affixed to the sprinkler risers, dated May 2025. | [5 empty] | 2026-03-15
46 | 84203.0 | Outdoor Kitchen | replace broken gas valve | GC | Year 1 | 3000 | 0 |  |  | 4 |  | replace broken gas valve
PROJECTS subtotal (excl. contingency/CM fee)
173 | 84505.0 | Construction Management Fee | CM Fees | CMF | CM Fee | 7585 | 2396 | 7585 |  | N/A |  | CM Fees
172 | 84510.0 | Contingency | Contingency Amount | CON | Contingency | 7224 | 0 | 7224 |  | N/A |  | Contingency Amount

## Windward
Windward — 2025 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
167 | 84330 | Electrical Panel Disconnects & Meter Banks | Vistria: raise electrical panel replacements up front @ $2,300 a unit | GC | Year 1 | 676200 | 202860 |  |  | 3 |  | Vistria: raise electrical panel replacements up front @ $2,300 a unit
95 | 84206 | Exterior building | Capitalized year 5 work: exterior painting, repairing stucco, replacing wood trim, replacing siding (Decreased by $38,019 and moved to BTL in Yr 3) | Capex | Year 1 | 359000 | 371 |  |  | N/A |  | Capitalized year 5 work: exterior painting, repairing stucco, replacing wood trim, replacing siding (Decreased by $38,019 and moved to BTL in Yr 3)
115 | 84304.0 | Doors | Cost Reallocation from BTL Yr1: replace sliding doors at turnover (40% in Yr 1, 30% in Yr 2, 20% in Yr 3, and 10% in Yr 4) | Capex | Year 1 | 180000 | 1022 |  |  | N/A |  | Cost Reallocation from BTL Yr1: replace sliding doors at turnover (40% in Yr 1, 30% in Yr 2, 20% in Yr 3, and 10% in Yr 4)
16 | 84204 | Asphalt Coating | PNA: Seal Coat and Crack Fill (Decreased by $127380 and moved BTL in Yr 5) | GC | Year 1 | 144000 | 43200 |  |  | 3 |  | PNA: Seal Coat and Crack Fill (Decreased by $127380 and moved BTL in Yr 5)
15 | 84303 | Landscape Cleanup and Enhancements | Tree trimming (Added in after PNA/Site Visit) | Capex | Year 1 | 50000 | 19200 |  |  | N/A |  | Tree trimming (Added in after PNA/Site Visit)
125 | 84103 | Signage - Site | Post: Adding in signage to account for switching from Cortland signage | Capex | Year 1 | 50000 | 24718 |  |  | N/A |  | Post: Adding in signage to account for switching from Cortland signage
106 | 84431.0 | Flooring | Cost Reallocation from BTL Yr1: Adjusted amount to reflect replacing one unit's floors per month ($3k per turn) | Capex | Year 1 | 36000 | 0 |  |  | N/A |  | Cost Reallocation from BTL Yr1: Adjusted amount to reflect replacing one unit's floors per month ($3k per turn)
168 | 84210 | Common area light fixtures | Vistria: address adding exterior lighting around mailbox area (includes other lighting enhancements) | GC | Year 1 | 35000 | 10500 |  |  | 3 |  | Vistria: address adding exterior lighting around mailbox area (includes other lighting enhancements)
105 | 84431.0 | Appliances Package | Cost Reallocation from BTL Yr1: Adjusted amount to reflect appliance actuals on Cortland's past BTL | Capex | Year 1 | 29680 | 0 |  |  | N/A |  | Cost Reallocation from BTL Yr1: Adjusted amount to reflect appliance actuals on Cortland's past BTL
120 | 84211 | Fire Stops | PNA: Fire stops | Capex | Year 1 | 28812 | 24990 |  |  | N/A |  | PNA: Fire stops
21 | 84201 | Stripe parking areas | Stripe Parking Lot Decreased $34,115 and moved BTL in Yr 9 | GC | Year 1 | 28000 | 8400 |  |  | 3 |  | Stripe Parking Lot Decreased $34,115 and moved BTL in Yr 9
162 | 84218.0 | Replace AC condenser | PNA: Add insulation to Condensing unit lines | GC | Year 1 | 26000 | 7800 |  |  | 3 |  | PNA: Add insulation to Condensing unit lines
22 | 84204 | Pavement Repairs | PNA: Repair potholes Lender PCA/Equity PCA: Damaged pavement consisting of linear cracking and alligator cracking, was observed in one high traffic area near the tennis courts and isolated areas at the south side of the property. Potholes and surface raveling was present at the drive aisles. Repairs are recommended. | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | PNA: Repair potholes Lender PCA/Equity PCA: Damaged pavement consisting of linear cracking and alligator cracking, was observed in one high traffic area near the tennis courts and isolated areas at th | [5 empty] | 2026-12-18
75 | 84433 | Asphalt composite shingle roofing | PNA: Standard roof tune up on ridge, vallt and pipe jacks; Equity PCA: Roof replacement - asphalt shingles (Yr 10) (Decreased by $113,211 and moved BTL in Yr 10) | GC | Year 1 | 22000 | 6600 |  |  | 3 |  | PNA: Standard roof tune up on ridge, vallt and pipe jacks; Equity PCA: Roof replacement - asphalt shingles (Yr 10) (Decreased by $113,211 and moved BTL in Yr 10)
109 | 84106 | Clean Dryer vents | Clean vents and replace missing covers (Added in after PNA/Site Visit) | GC | Year 1 | 16170 | 4851 |  |  | 3 |  | Clean vents and replace missing covers (Added in after PNA/Site Visit)
80 | 84202.0 | Gutters & downspouts | PNA: Clean and repitch gutters throughout property | GC | Year 1 | 16000 | 4800 |  |  | 3 |  | PNA: Clean and repitch gutters throughout property
112 | 84476.0 | Water Heaters | Cost Reallocation from BTL Yr1: Adjusted amount to reflect water heater actuals on Cortland's past BTL | Capex | Year 1 | 16000 | 0 |  |  | N/A |  | Cost Reallocation from BTL Yr1: Adjusted amount to reflect water heater actuals on Cortland's past BTL
114 | 84218.0 | HVAC inspection and maintenance | Cost Reallocation from BTL Yr1: Adjusted amount to reflect HVAC actuals on Cortland's past BTL | Capex | Year 1 | 16000 | 7800 |  |  | N/A |  | Cost Reallocation from BTL Yr1: Adjusted amount to reflect HVAC actuals on Cortland's past BTL
150 | 83375 | Golf Cart | Post: Adding in new leasing golf cart | Capex | Year 1 | 15000 | 5814 |  |  | N/A |  | Post: Adding in new leasing golf cart
69 | 84121 | Exterior Stairs - Repair exterior stair railings | Post: Adding in painting of exterior railings | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Post: Adding in painting of exterior railings
146 | 84450 | Security Camera System | Vistria: address adding security cameras to mailbox area | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | Vistria: address adding security cameras to mailbox area
23 | 83520 | ADA parking & curb cuts | Equity PCA: No van-accessible parking space was present at the leasing office. Installation of one van-accessible space is recommended. | PMC | Year 1 | 1000 | 0 |  |  | N/A |  | Equity PCA: No van-accessible parking space was present at the leasing office. Installation of one van-accessible space is recommended.
122 | 83236 | Carbon Monoxide/Smoke Detectors | Lender PCA: Two smoke-only detectors were observed in Units 16014 and 2004. This appeared to be a rare exception, and the remaining observed units had combo smoke/CO detectors. Combo units should be installed where CO detectors are missing. Equity PCA: Smoke detectors were observed detached from the wall and missing in Units 16014, 19012, and 14004. Replacement is recommended. | PMC | Year 1 | 450 | 0 |  |  | N/A |  | Lender PCA: Two smoke-only detectors were observed in Units 16014 and 2004. This appeared to be a rare exception, and the remaining observed units had combo smoke/CO detectors. Combo units should be i | [5 empty] | 2026-01-18
PROJECTS subtotal (excl. contingency/CM fee)
173 | 84505 | Construction Management Fee | CM Fees | CMF | Contingency | 93991 | 17447 | 93991 |  | N/A |  | CM Fees
172 | 84510 | Contingency | Contingency Amount | CON | Contingency | 89516 | 0 | 89516 |  | N/A |  | Contingency Amount

## Almaden 1930
Almaden 1930 — 2026 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
105 | 51080-00 | Paint community | PNA: Paint community - LRR | GC | Year 1 | 239400 | 0 |  |  | 4 |  | PNA: Paint community - LRR
170 | 51140-00 | Electrical Panel Disconnects & Meter Banks | Lender PCA: At unit electric panels, some panels did not have the breakers labeled. Immediate repairs are recommended for all electrical panels be surveyed and breakers to be labeled where missing. No costs are listed in the report, as on-site maintenance can label the breakers and minimal cost. EPCA: The electric subpanels in the units were observed to be Zinsco/Sylvania panels and circuit breakers. There is a history of reports that the breakers would not trip during an over-current, short circuit or similar condition. This condition would then cause the panel to overheat and mau cause fires. Information is reviewed to date is inconclusive and Partner is not aware of recalls or electrical code requirements to replace the panels and breaker; however, some insurance companies may not provide coverage for properties with Zinsco.Sylvania panels. As a conservative measure, replacement of the Zinsco/Sylvania panels and circuit breakers is recommended. | Capex | Year 1 | 150000 | 0 |  |  | N/A |  | Lender PCA: At unit electric panels, some panels did not have the breakers labeled. Immediate repairs are recommended for all electrical panels be surveyed and breakers to be labeled where missing. No
56 | 51072-00 | Concrete deck / floor fill | PNA: Rebuild 20% of balconies | GC | Year 1 | 124488 | 0 |  |  | 4 |  | PNA: Rebuild 20% of balconies
32 | 51043-00 | Landscaping | PNA: Remove dead tree branches and trim trees. EPCA: Trees were observed impeding on the building rooftops and facades of several structures. No portion of any trees should be in contact with the building exterior. It is reccomended that the trees be trimmed back | GC | Year 1 | 91350 | 0 |  |  | 4 |  | PNA: Remove dead tree branches and trim trees. EPCA: Trees were observed impeding on the building rooftops and facades of several structures. No portion of any trees should be in contact with the buil
89 | 51070-00 | Repair / replace wood siding | PNA: Replace rotted siding. EPCA: Partner observed deteriorated siding located below and near dryer vents at the communal laundry room located along east side of the leasing office building. The vents appeared to be blowing hot/wet air directly at the siding causing the deterioration. Replacement of the damaged siding is recommended. As part of the siding replacement, the dryer vents should be angeled away from the siding to prevent future deterioration. | GC | Year 1 | 69250 | 0 |  |  | 4 |  | PNA: Replace rotted siding. EPCA: Partner observed deteriorated siding located below and near dryer vents at the communal laundry room located along east side of the leasing office building. The vents
33 | 51025-00 | Resurface swimming pool | PNA: Repair to pool shell and resurface pool | GC | Year 1 | 68250 | 0 |  |  | 4 |  | PNA: Repair to pool shell and resurface pool
99 | 51070-00 | Repair / replace wood trim | PNA: Replace rotted fascia and trim | GC | Year 1 | 58800 | 0 |  |  | 4 |  | PNA: Replace rotted fascia and trim
78 | 51061-00 | Asphalt composite shingle roofing | PNA: Roof tune up and Roof replacements (Yr. 8): | GC | Year 1 | 40950 | 29675 |  |  | 2 |  | PNA: Roof tune up and Roof replacements (Yr. 8):
84 | 51062-00 | Sealants & caulking | PNA: Seal between T-111 siding | GC | Year 1 | 37800 | 0 |  |  | 4 |  | PNA: Seal between T-111 siding
18 | 51045-00 | Landscape Cleanup and Enhancements | Post: General curb appeal enhancement | GC | Year 1 | 35000 | 96250 |  |  | 0 |  | Post: General curb appeal enhancement
48 | 51992-00 | Termite Remediation | EPCA: Partner engaged Terminix for a termite and fungus/dryrot inspection at the subject property. Based on their findings, approximately 60 areas of termites and dryrot fungus were observed. Terminix recommends a localized treatment for termites and dryrot fungus Lender PCA: The inspection identified widespread evidence of drywood termite activity across multiple areas of the property, including the meter closet interior and framing, balconies (framing and decking), ground floor corner trim, window trim, vertical trim, wood siding, and the exteriors of Buildings 1–10 and the recreation building/office. In several locations, termites have caused observable wood damage. Recommended actions include removal or covering of accessible termite fecal pellets, localized treatmentof accessible infested wood with approved insecticides (noting these are secondary, below–industrystandard measures with limited guarantees), and removal and replacement of damaged wood members where deterioration is present. Due to the extent of exterior termite evidence, full structure fumigation is recommended to eradicate drywood termites. Additionally, fungus infection/ dry rot was observed at wood siding, trim, and balconies due to weather exposure. Recommended repairs include removal and replacement of affected components and sealing with weatherresistant paint or moisture sealant. Finally, evidence of fungus appears to extend into inaccessible areas, warranting further intrusive inspection. A supplemental report recommends following access, including detailed findings and repair/treatment estimates | GC | Year 1 | 35000 | 17500 |  |  | 3 |  | EPCA: Partner engaged Terminix for a termite and fungus/dryrot inspection at the subject property. Based on their findings, approximately 60 areas of termites and dryrot fungus were observed. Terminix
19 | 51051-00 | Asphalt Coating | PNA: Repair asphalt, seal coat, and stripe. Lender PCA: The asphalt pavement has localized alligator cracking, and general surface deterioration. Asphalt repairs are recommended Lender PCA: The parking area sealant and striping is in fair to poor condition, with evidence of wear and deterioration noted throughout EPCA: Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present throughout the asphalt that was not located below the carport structures. In addition, damaged asphalt pavement was noted in spots below the carports. This damage appeared to be associated with uplift from tree roots. Asphalt overlay and crack sealing is recommended. Lender PCA: A cracked walkway was observed. Immediate repairs are recommended to repair the walkway. | GC | Year 1 | 32970 | 700 |  |  | 4 |  | PNA: Repair asphalt, seal coat, and stripe. Lender PCA: The asphalt pavement has localized alligator cracking, and general surface deterioration. Asphalt repairs are recommended Lender PCA: The parkin
131 | 51200-00 | Designer Fees | Post: Leasing office refresh | GC | Year 1 | 32500 | 16250 |  |  | 3 |  | Post: Leasing office refresh
73 | 51072-00 | Repair balcony framing & decking | PNA: Add joist hangers to balcony joists | GC | Year 1 | 30450 | 5000 |  |  | 4 |  | PNA: Add joist hangers to balcony joists
28 | 51045-00 | Landscape irrigation | PNA: Inspect and repair irrigation EPCA: Cracked/broken concrete swals were observed. Repairs to the damaged swales is recommended to ensure proper drainage. | GC | Year 1 | 29400 | 0 |  |  | 4 |  | PNA: Inspect and repair irrigation EPCA: Cracked/broken concrete swals were observed. Repairs to the da
87 | 51062-00 | Flashing | PNA: Add z flash to replacement siding | GC | Year 1 | 29400 | 0 |  |  | 4 |  | PNA: Add z flash to replacement siding
159 | 51131-00 | Sanitary Sewer Piping | Jet main drain lines per scope | GC | Year 1 | 28896 | 11000 |  |  | 3 |  | Jet main drain lines per scope
22 | 51025-00 | Fences & gates - swimming pool | PNA: Repair and paint pool fence EPCA: Deterioration/rust was noted along the base of the metal pool fencing system in several areas. Repair or replacement of the deteriorated metal fencing is recommended in the short term. | GC | Year 1 | 22050 | 0 |  |  | 4 |  | PNA: Repair and paint pool fence EPCA: Deterioration/rust was noted along the base of the metal poo
137 | 51011-00 | Pool Furniture | Post: Pool furniture replacement | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Post: Pool furniture replacement
30 | 51077-00 | Fences & gates - site perimeter | PNA: Overlay wood fence on back of community. Lender PCA: Some of the chain link has been bowed slightly where cars have backed into it, but over all it looks good. Immediate repairs are recommended for fencing repairs. | GC | Year 1 | 19950 | 0 |  |  | 4 |  | PNA: Overlay wood fence on back of community. Lender PCA: Some of the chain link has been bowed slightly where cars have backed into it, but over all it looks good. Immediate repairs are recommended f
35 | 51025-00 | Replace swimming pool deck | PNA: Pressure wash and seal brick pool deck | GC | Year 1 | 18900 | 0 |  |  | 4 |  | PNA: Pressure wash and seal brick pool deck
39 | 51130-00 | Storm sewer piping | PNA: Clean storm drains. EPCA: Debris was observed clogging storm drains. Clearing the debris is recommended | GC | Year 1 | 18900 | 0 |  |  | 4 |  | PNA: Clean storm drains. EPCA: Debris was observed clogging storm drains. Clearing the debris is recommended
173 | 51140-00 | Electrical distribution | PNA: Inspect and repair lighting controllers on all buildings | GC | Year 1 | 18900 | 0 |  |  | 4 |  | PNA: Inspect and repair lighting controllers on all buildings
31 | 51085-00 | Retaining walls | PNA: Rebuild one section of retaining wall | GC | Year 1 | 16800 | 0 |  |  | 4 |  | PNA: Rebuild one section of retaining wall
57 | 51070-00 | Wall framing | PNA: Replace damaged framing in gable ends | GC | Year 1 | 14700 | 0 |  |  | 4 |  | PNA: Replace damaged framing in gable ends
23 | 51172-00 | Carports / Garages | PNA: Repair car ports and paint posts and pearling EPCA: Damaged carport roof panels and carport support beams/posts from suspected vehicular impact were noted in several locations. Repair or replacement of the damaged components is recommended in the short term, as required. | GC | Year 1 | 13650 | 0 |  |  | 4 |  | PNA: Repair car ports and paint posts and pearling EPCA: Damaged carport roof panels
83 | 51071-00 | Gutters & downspouts | PNA: Secure and clean gutters. Lender PCA: Ac cracked concrete gutter was observed at the driveway entrance to the property. The gutter most likely is municipal owned, so no costs are listed in the report. It is recommended that Ownership contact the municipality to repair the cracked gutter. | GC | Year 1 | 10551 | 0 |  |  | 4 |  | PNA: Secure and clean gutters. Lender PCA: Ac cracked concrete gutter was observed at the driveway entrance to the property. The gutter most likely is municipal owned, so no costs are listed in the re
49 | 51134-00 | Water distribution piping | PNA: Install sewer covers | GC | Year 1 | 10500 | 14700 |  |  | 0 |  | PNA: Install sewer covers
72 | 51077-00 | Repair exterior stair railings | PNA: Secure railings | GC | Year 1 | 10500 | 0 |  |  | 4 |  | PNA: Secure railings
70 | 51072-00 | Balcony inspection | Lender PCA: Based on exterior appurtenances, this Property is subject to the State of California Law. According to a recent State of California Law (SB 721), subject properties that contain "exterior elevated elements" must undergo inspections performed by qualified assessors. As such, engaging a qualified professional to perform the required inspection is recommended in the immediate term. Subsequent repairs and/or corrective actions may be required based on the findings of the SB 721 inspection. EPCA: State of California Law (SB 721) exterior elevated elements inspection | GC | Year 1 | 10000 | 0 |  |  | 4 |  | Lender PCA: Based on exterior appurtenances, this Property is subject to the State of California Law. According to a recent State of California Law (SB 721), subject properties that contain "exterior
34 | 51025-00 | Replace swimming pool coping | PNA: Replace decko seal EPCA: Coping sealants around both the pool and spa were observed to be deteriorated and in fair overall condition. Replacement of the coping sealant is recommended. | GC | Year 1 | 9975 | 0 |  |  | 4 |  | PNA: Replace decko seal EPCA: Coping sealants around both the pool and
71 | 51093-00 | Repair exterior stair treads and stringers | PNA: Repair stair treads and stringers | GC | Year 1 | 9975 | 0 |  |  | 4 |  | PNA: Repair stair treads and stringers
76 | 51077-00 | Repair balcony railings | PNA: Secure railings Lender PCA: Small areas of dry rot and damage to the balconies was noted at in a few locations. This areas should be repaired in the immediate term. BBG also recommends periodic inspections for dry rot under routine maintenance. | GC | Year 1 | 9975 | 0 |  |  | 4 |  | PNA: Secure railings Lender PCA: Small areas of dry rot and damage to the b
21 | 51025-00 | Repair / replace swimming pool pumps | PNA: Anti entrapment devices | GC | Year 1 | 7140 | 63158 |  |  | 0 |  | PNA: Anti entrapment devices
171 | 51140-00 | Electrical IR Inspection | EPCA: Based on the age of the property and some of the electrical equipment, an IR survey is recommended. | GC | Year 1 | 6130 | 0 |  |  | 4 |  | EPCA: Based on the age of the property and some of the electrical equipment, an IR survey is recommended.
26 | 51091-00 | ADA parking & curb cuts | Lender PCA: One van accessible space should be added at the leasing office. The restroom at the leasing office has accessories that are mounted too high and should be lowered. Immediate repairs are recommended to lower the accessories. Drain pipe insulation was noted to be absent, and should be installed in the immediate term. EPCA: Damaged curbing was present in several areas along the drive aisles. Sectional replacement of damaged curbing is recommended in the short term. | GC | Year 1 | 2000 | 0 |  |  | 4 |  | Lender PCA: One van accessible space should be added at the leasing office. The restroom at the leasing office has accessories that are mounted too high and should be lowered. Immediate repairs are re
154 | 51990-00 | Smoke/fire detection | Lender PCA: Smoke detectors were generally present where required, however several units were observed where the tenant had removed the detector. The units should be surveyed, and all missing detectors replaced. | GC | Year 1 | 1000 | 1000 |  |  | 0 |  | Lender PCA: Smoke detectors were generally present where required, however several units were observed where the tenant had removed the detector. The units should be surveyed, and all missing detector
27 | 51091-00 | Sidewalks | Lender PCA: A cracked walkway was observed. Immediate repairs are recommended to repair the walkway. | GC | Year 1 | 500 | 0 |  |  | 4 |  | Lender PCA: A cracked walkway was observed. Immediate repairs are recommended to repair the walkway.
PROJECTS subtotal (excl. contingency/CM fee)
175 | 51175-00 | Contingency | Contingency Amount | CON | Contingency | 87089 | 0 | 87089 |  | N/A |  | Contingency Amount
176 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 73654 | 0 | 73654 |  | N/A |  | CM Fee

## Ardmore Springs
Ardmore Springs — 2026 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
95 | 84101.0 | Exterior building | PNA: Paint community, iron will require special treatment | GC | Year 1 | 300000 | 90000 |  |  | 3 |  | PNA: Paint community, iron will require special treatment
105 | 82200.0 | Appliances Package | Post: Washer/Dryer installs | PMC | Year 1 | 272400 | 80321 |  |  | N/A |  | Post: Washer/Dryer installs
129 | 84116.0 | Leasing office floor/wall finishes, Replace Furnitur | Post: Remodel leasing office (Paint - 1st Call & Furniture - PMC) | GC | Year 1 | 119850 | 35910 |  |  | 3 |  | Post: Remodel leasing office (Paint - 1st Call & Furniture - PMC)
43 | 84103.0 | Building entrance | Post: Signage replacements for rebranding | Capex | Year 1 | 75000 | 0 |  |  | N/A |  | Post: Signage replacements for rebranding
134 | 84190.0 | Gym Equipment | Post: Replace gym equipment | Capex | Year 1 | 50000 | 8571 |  |  | N/A |  | Replace Cardio & Weights As Needed |  |  | PMC ordered 2 machines and are awaiting AM walk to pick two more
122 | 84250.0 | Radon remediation | Per ESA: Radon remediation in 9 areas, ($3,500-$4,500 per location) EBI recommends completing pilot testing, building characterization, and system design before mitigation to determine the proper system, at an estimated cost of $4,500–$5,500 Post-mitigation testing should be performed at all treated locations to confirm radon levels are reduced below 4.0 pCi/L, with an estimated cost of $1,000. An Operations, Maintenance, and Monitoring (OM&M) Plan is recommended for all mitigation systems, estimated at $750. Total Radon Costs: $47,750 Mold-impact materials, would cost $250 for moisture management plan (in one unit and in the fire riser room) | GC | Year 1 | 47750 | 14325 |  |  | 3 |  | Per ESA: Radon remediation in 9 areas, ($3,500-$4,500 per location) EBI recommends completing pilot testing, building characterization, and system design before mitigation to determine the proper syst
16 | 84204.0 | Asphalt Coating | PNA: Repair potholes. Lender PCA: One area with a failed asphalt patch was noted in front of Building 11. Priority repairs are recommended for asphalt patching and repairs. | GC | Year 1 | 30000 | 9000 |  |  | 3 |  | Asphalt as repairs per 1st |  | Completed |  |  |  | 2027-02-26
140 | 84280.0 | Unit Model Update | Post: Set up model unit | Capex | Year 1 | 30000 | 0 |  |  | N/A |  | Post: Set up model unit
152 | 84239.0 | Fire stops | PNA: Fire stops | Capex | Year 1 | 24696 | 41880 |  |  | N/A |  | PNA: Fire stops
75 | 84433.0 | Asphalt composite shingle roofing | PNA: Roof inspection and tune up | GC | Year 1 | 22000 | 6600 |  |  | 3 |  | PNA: Roof inspection and tune up
132 | 84190.0 | Fitness Center Remodel | PNA: Repair sheetrock and paint fitness center and package room | GC | Year 1 | 20000 | 6000 |  |  | 3 |  | Paint, & Drywall Repair |  |  | 1st Call will be done 10/10 , ASD 9/15
70 | 84104.0 | Repair balcony framing & decking | PNA: Repair vinyl on balcony band board ($10,000) and secure all patio railings ($6,500) | GC | Year 1 | 16500 | 4950 |  |  | 3 |  | PNA: Repair vinyl on balcony band board ($10,000) and secure all patio railings ($6,500)
84 | 84433.0 | Flashing | PNA: Replace damaged flashing on breezeway roofs Lender PCA: It is likely the cracking at building 9 was caused by a more prevalent design or construction flaw, which exposes the top edge of the plywood plate behind the brick veneer visible from the 2nd floor breezeway. If the plywood becomes saturated and then freezes, this would expand behind the brick face with no additional room for that expansion. The balcony planks abut into the mortar behind and above the plywood edge, so water is able to pass behind the brick. Repairs are recommended to add the proper flashing to prevent this infiltration. | GC | Year 1 | 12000 | 3600 |  |  | 3 |  | PNA: Replace damaged flashing on breezeway roofs Lender PCA: It is likely the cracking at building 9 was caused by a more | [5 empty] | 2027-02-26
80 | 84202.0 | Gutters & downspouts | PNA: Replace damaged gutter and downspouts, clean, re-pitch remaining Lender PCA: Impact damage to the gutter of the G-14 building was observed, and will create drainage problems during heavy rain. Priorty repairs are recommended to replace the damaged guttter. | GC | Year 1 | 11000 | 3300 |  |  | 3 |  | PNA: Replace damaged gutter and downspouts, clean, re-pitch remaining L | [5 empty] | 2027-02-26
26 | 83517.0 | Erosion control | PNA: Add rocks at downspout in eroded areas | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | PNA: Add rocks at downspout in eroded areas
87 | 84206.0 | Repair / replace cement fiber siding | PNA: Replace damaged siding and paint | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | PNA: Replace damaged siding and paint
102 | 84102.0 | Masonry Repairs | PNA: Pressure wash vinyl on posts and balcony head Lender PCA: Mildew growth was noted on the rear elevations of the apartment buildings. Priority repairs are recommended to power and wash and clean the facades. | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | PNA: Pressure wash vinyl on posts and balcony head Lender PCA: Mildew growth was noted on the rear elevations | [5 empty] | 2027-02-26
93 | 84120.0 | Breezeway soffit repairs | PNA: Repair breezeway soffit | GC | Year 1 | 9500 | 2850 |  |  | 3 |  | PNA: Repair breezeway soffit
24 | 84221.0 | Sidewalks | PNA: Repair trip hazards Lender PCA: No observed areas of deterioration were noted in the sidewalks, however, trip hazards were observed. These areas were noted at 3110. Priority repairs are recommended for repair of the concrete sidewalk trip hazards. | GC | Year 1 | 8500 | 2550 |  |  | 3 |  | PNA: Repair trip hazards Lender PCA: No observed areas of deterioration were noted in | [5 empty] | 2026-05-27
69 | 84121.0 | Repair exterior stair railings | PNA: Secure stair rails | GC | Year 1 | 8500 | 2550 |  |  | 3 |  | PNA: Secure stair rails
81 | 84433.0 | Sealants & caulking | Roof Sealants and Caulking | GC | Year 1 | 8500 | 2550 |  |  | 3 |  | Roof Sealants and Caulking
72 | 84206.0 | Expansion joints | Expansion Joints | GC | Year 1 | 8000 | 2400 |  |  | 3 |  | Expansion Joints
88 | 84113.0 | Repair / replace wood shingles | PNA: Replace rotted trim and paint to match | GC | Year 1 | 5000 | 1500 |  |  | 3 |  | PNA: Replace rotted trim and paint to match
156 | 84432.0 | Stormwater Pipe Repair | PNA: Clean storm sewer basins | GC | Year 1 | 4000 | 1200 |  |  | 3 |  | PNA: Clean storm sewer basins
46 | 83160.0 | Mold and water remediation | Lender PCA: Approximately 12 sf of suspect mold was observed at the fire sprinkler room of Building 8, possibly from testing. There were no active leaks observed or reported. Removal of building materials with suspect mold and replacement with new, unaffected materials can be conducted by propertly trained maintenance staff. Priority repairs are recommended for mold remediation. Lender PCA: Approximately 1-2 sf of suspect mold was noted at the ceiling vent of the bathroom of Unit 9109, likely due to poor ventilation. Removal of building materials with the suspect mold and replacement with new, unafffected materials can be conducted by properly trained maintenance staff. | PMC | Year 1 | 2500 | 0 |  |  | N/A |  | Lender PCA: Approximately 12 sf of suspect mold was observed at the fire sprinkler room of Building 8, possibly from testing. There were no active leaks observed or reported. Removal of building mater | [5 empty] | 2026-05-27
27 | 84205.0 | Fences & gates - site perimeter | Lender PCA: The site fencing near the pet wash station near the operable gate is damaged. Priority repairs are recommended for fence repairs. ($500) Lender PCA: The north automatic access/egress gate is inoperable and is stuck in the open position. Priority repairs are recommended to repair the gate. ($1,500) | PMC | Year 1 | 2000 | 0 |  |  | N/A |  | Lender PCA: The site fencing near the pet wash station near the operable gate is damaged. Priority repairs are recommended for fence repairs. ($500) | [5 empty] | 2027-02-26
91 | 83212.0 | Tuck-pointing | Lender PCA: One stairstep cracked area was observed in the central part of an entrance arch of brick masonry facade at building 9. Priority repairs are recommended for brick replacement, tuck pointing, and cleaning. | GC | Year 1 | 1000 | 300 |  |  | 3 |  | Lender PCA: One stairstep cracked area was observed in the central part of an entrance arch of brick masonry facade at building 9. Priority repairs are recommended for brick replacement, tuck pointing | [5 empty] | 2027-02-26
25 | 84302.0 | Landscape irrigation | Lender PCA: A broken irrigation line was observed at Building 6. Priorty repairs are recommended to repair the broken irrigation line | PMC | Year 1 | 500 | 0 |  |  | N/A |  | Lender PCA: A broken irrigation line was observed at Building 6. Priorty repairs are recommended to repair the broken irrigation line | [5 empty] | 2027-02-26
171 | 83217.0 | Replace electric baseboard heater | Lender PCA: One electric baseboard heater located within the sprinkler system closet in building 8 was noted to have disconnected wires and is reportedly inoperable. Priority repairs are recommended to repair or replace the unit to avoide any freeze damage to the sprinkler system | PMC | Year 1 | 500 | 1249 |  |  | N/A |  | Lender PCA: One electric baseboard heater located within the sprinkler system closet in building 8 was noted to have disconnected wires and is reportedly inoperable. Priority repairs are recommended t | [5 empty] | 2026-05-27
90 | 83106.0 | Dryer Vents | Lender PCA: Three locations total, at Building 5 and 10, exhibit missing laundry vent covers which allows for moisture and/or pest infiltration. Priority repairs are recommended for the replacement of the laundry vent covers | PMC | Year 1 | 225 | 0 |  |  | N/A |  | Lender PCA: Three locations total, at Building 5 and 10, exhibit missing laundry vent covers which allows for moisture and/or pest infiltration. Priority repairs are recommended for the replacement of | [5 empty] | 2027-02-26
23 | 84221.0 | ADA parking & curb cuts | Lender PCA: One ADA parking space at the leasing office has a post for an ADA sign, but the face is blank and missing the sign. Priority repairs are recommended for its replacement | PMC | Year 1 | 150 | 0 |  |  | N/A |  | Lender PCA: One ADA parking space at the leasing office has a post for an ADA sign, but the face is blank and missing the sign. Priority repairs are recommended for its replacement | [5 empty] | 2027-02-26
130 | 84116.0 | Leasing office | Lender PCA: The sinks at the leasing office bathroom do not appear to havescald/abrasion protection at the sink piping and ADA signage on the bathroom doors. Priority repairs are recommended for installation. | GC | Year 1 | 150 | 45 |  |  | 3 |  | Lender PCA: The sinks at the leasing office bathroom do not appear to havescald/abrasion protection at the sink piping and ADA signage on the bathroom doors. Priority repairs are recommended for insta | [5 empty] | 2026-05-27
169 | 84210.0 | Replace defective outlet | Lender PCA: One GFCI outlet at unit 4206 in the kitchen does not reset, and priorty repairs are recommended to replace the GFCI outlet. | PMC | Year 1 | 30 | 0 |  |  | N/A |  | Lender PCA: One GFCI outlet at unit 4206 in the kitchen does not reset, and priorty repairs are recommended to replace the GFCI outlet. | [5 empty] | 2026-05-27
PROJECTS subtotal (excl. contingency/CM fee)
174 | 85305 | Construction Management Fee | CM Fee | CMF | CM Fee | 58813 | 0 | 58813 |  | N/A |  | CM Fee
173 | 84510.0 | Contingency | Contingency Amount | CON | Contingency | 56013 | 0 | 56013 |  | N/A |  | Contingency Amount

## Bentley Parke
Bentley Parke — 2026 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
43 | 51080 | Exterior building | PNA - Paint community 100% paintable 3.2.4. Painting, Exterior. The paint finish on the apartment buildings was observed weather worn and stained throughout, with areas of unpainted patched stucco noted typically at roof scupper drains. Reapplication of exterior paint is recommended. | GC | Year 1 | 382800 | 114840 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update |  | Lender | 2027-04-29
97 | 51150 | Interior Upgrades | Raising Y1 of Unit Interior Upgrades upfront | Capex | Year 1 | 260680 | 38010 |  |  | N/A |  | Unit Upgrades on Turns |  |  | PMC led renovation based on UW
55 | 51062 | Modified bitumen membrane roof repairs | PNA - Repairs to flat roofing and repairs with modified bit 3.2.8. - Built-up roof / Modified Bitumen | GC | Year 1 | 75000 | 22800 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update |  | Lender | 2027-04-26
94 | 51141 | Replace breezeway lights | PNA - R&R ceiling lights in breezeways with LED | GC | Year 1 | 38600 | 11580 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
110 | 51150 | Drier vents | PNA - Remove vent covers, clean vent piping, and install new dryer vent covers | GC | Year 1 | 38280 | 11484 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
129 | 51993 | Security/ fire alarm systems | Concept Walk - Add security cameras | Capex | Year 1 | 35000 | 0 |  |  | N/A |  | Cameras to be assess for need |  |  | Bidding Currently
67 | 51075 | Repair stucco | PNA - Repairs to stucco | GC | Year 1 | 26000 | 7800 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
122 | 51169 | Clubhouse / Office remodel | Concept Walk - Convert staff room to a business center/cybercafe | Capex | Year 1 | 25000 | 3750 |  |  | N/A |  | CM & AM to develop scope |  |  | Scoping
150 | 51160 | BBQ Grill Area | Concept Walk - Add BBQ/Grill Area outside swimming pool fence | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
111 | 51180 | Fire Stops | PNA - Fire stops | Capex | Year 1 | 22736 | 1916 |  |  | N/A |  | Firestops to be ordered by CM |  |  | Orderd & Shipped
30 | 51172 | Carports / Garages | PNA - Repair carports | GC | Year 1 | 22000 | 6600 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
56 | 51071 | Gutters & downspouts | PNA - Clean and repatch gutters throughout property | GC | Year 1 | 21000 | 6300 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
58 | 51062 | Sealants & caulking | PNA - Seal windows as part of paint | GC | Year 1 | 20000 | 6000 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
44 | 51070 | Repair exterior stair treads and stringers | PNA - Replace 40 broken stair treads | GC | Year 1 | 18900 | 5670 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
31 | 51163 | Dumpster enclosures | PNA - Repair dumpster enclosures | GC | Year 1 | 16000 | 4800 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
48 | 51090 | Expansion joints | PNA - Seal expansion joints | GC | Year 1 | 16000 | 4800 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
93 | 51140 | Electrical distribution | PNA - Replace lighting controlers | GC | Year 1 | 16000 | 4800 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
32 | 51992 | WDIR | WDIR Treatment per Inspection | Capex | Year 1 | 15900 | 0 |  |  | N/A |  | Termite Treatment for CM |  |  | Bidding Currently
57 | 51062 | Flashing | PNA - Repair parapet wall flashing | GC | Year 1 | 15600 | 4680 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
39 | 51090 | Concrete deck / floor fill | PNA - Repair landings | GC | Year 1 | 15000 | 4500 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
22 | 51091 | Sidewalks and curbs | PNA - Grind trip hazards | GC | Year 1 | 13000 | 3900 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
140 | 51022 | Swimming pool deck | PNA - Presure wash pool deck | GC | Year 1 | 12000 | 3600 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
51 | 51061 | Asphalt composite shingle roofing | PNA - Roof tune up 3.2.8 - Asphalt Shingle (3-tab). The inboard parapet asphalt shingle installation date was not provided and appears to be of original construction (1988). The inboard parapet asphalt shingle roof coverings were observed damaged with areas of warped and missing shingles throughout. Replacement of a portion of the inboard parapet asphalt shingles is recommended and should be perfomed in conjunction with BUR roof replacement activities. | GC | Year 1 | 10260 | 3078 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update |  | Lender | 2027-04-29
113 | 51150 | Unit Deferred Maintenance | Down Unit Refurbishment (Unit 1405) - Damaged bedroom ceiling ($8,000) Roof Leak Repair (Unit 1405) - Repair Roof above down unit ($1,000) | GC | Year 1 | 9000 | 2400 |  |  | 4 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update |  |  | 2026-10-19
115 | 51200 | CA SB-721 Elevated Exterior Elements Inspection | 3.2.7 - According to a recent State of California Law (SB 721), subject properties that contain “exterior elevated elements” must undergo inspections performed by qualified assessors. Related documentation was requested; however, property ownership indicated that the required inspection has not been completed to date. As such, engaging a qualified professional to perform the required inspection is recommended. Subsequent repairs and/or corrective actions may be required and additional funds necessary as needed, pending the results of the inspection. | GC | Year 1 | 6500 | 1950 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update |  | Lender | 2027-04-26
143 | 51076 | Swimming pool fencing / gates | PNA - Repair pool fence | GC | Year 1 | 5600 | 1680 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
17 | 51130 | Storm sewer piping and drains | PNA - Clear drains on pool deck | GC | Year 1 | 5000 | 1500 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
141 | 51026 | Swimming Pool Shower | Concept Walk - Re-tile shower | GC | Year 1 | 5000 | 1500 |  |  | 3 |  | Mobilization has been paid, project is 30% completed |  |  | Based on last 1st Call update
83 | 50050 | Domestic Hot Water Heater, Replace | 3.3.5 - Water Heater Sesimic Strapping. The water heaters lacked one or both seismic bracing straps at observed units 103, 301 and 814. Survey and provision of adequate seismic bracing is recommended. | PMC | Year 1 | 3000 | 0 |  |  | N/A |  | LRR |  |  | Lender repair complete |  | Lender | 2026-07-28
112 | 51169 | ADA - Leasing Office Restrooms | 5.4 - The plumbing under the lavatories within the publicly-accessible toilet rooms did not appear to be configured to protect against contact. Installation of a protection method is recommended. | PMC | Year 1 | 300 | 25 |  |  | N/A |  | LRR |  |  | Will be executed soon |  | Lender | 2027-04-26
PROJECTS subtotal (excl. contingency/CM fee)
158 |  | Construction Management Fee | CM Fee | CMF | CM Fee | 61696 | 0 | 61696 |  | N/A |  | CM Fee
157 |  | Contingency | Contingency Amount | CON | Contingency | 58758 | 0 | 58758 |  | N/A |  | Contingency Amount

## Cherry Creek
Cherry Creek — 2026 acq · GC none ($0)
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
71 | 51080-00 | Exterior paint | Lender PCA: Peeling paint was observed on the exterior stairway wall of building 7. Reapplication of exterior paint is recommended. PNA: Paint Community | GC | Year 1 | 230000 | 0 |  |  | 4 |  | Lender PCA: Peeling paint was observed on the exterior stairway wall of building 7. Reapplication of exterior paint is recommended. PNA: Paint Community | [5 empty] | 2026-04-28
19 | 51053-00 | Asphalt seal coating | Lender PCA: Damaged pavement consisting of linear cracking was present at the drive aisles typical of the conditions noted near the leasing office. Sectional full-depth replacement and crack routing/sealing is recommended. PNA: fill asphalt cracks and seal | GC | Year 1 | 81000 | 0 |  |  | 4 |  | Lender PCA: Damaged pavement consisting of linear cracking was present at the drive aisles typical of the conditions noted near the leasing office. Sectional full-depth replacement and crack routing/s | [5 empty] | 2027-03-01
99 | 51140-00 | Electrical distribution - exterior | PNA: Place Holder for electric meter and load center replacement | GC | Year 1 | 80000 | 0 |  |  | 4 |  | PNA: Place Holder for electric meter and load center replacement
151 | 51023-00 | Swimming pool resurface | PNA: resurface pool | GC | Year 1 | 52000 | 0 |  |  | 4 |  | PNA: resurface pool
66 | 51075-00 | Repair / replace wood shingles | PNA: Replace rotted fascia and trim | GC | Year 1 | 46000 | 0 |  |  | 4 |  | PNA: Replace rotted fascia and trim
86 | 50050-00 | Unit water heaters | PNA: replace two hot water heaters | GC | Year 1 | 42000 | 0 |  |  | 4 |  | PNA: replace two hot water heaters
69 | 51075-00 | Stucco repairs | PNA: Stucco repairs | GC | Year 1 | 40000 | 0 |  |  | 4 |  | PNA: Stucco repairs
32 | 51172-00 | Carports / Garages | PNA: Carport repairs and paint post and pearling | GC | Year 1 | 36000 | 0 |  |  | 4 |  | PNA: Carport repairs and paint post and pearling
60 | 51062-00 | Sealants & caulking | PNA: seal and prep stucco | GC | Year 1 | 36000 | 0 |  |  | 4 |  | PNA: seal and prep stucco
67 | 51159-00 | Wall framing | PNA: damaged framing on stair supports | GC | Year 1 | 35000 | 0 |  |  | 4 |  | PNA: damaged framing on stair supports
157 | 51011-00 | Pool furniture | Pool Furniture Straps, BBQ Grill Upgrade - Concept Walk | Capex | Year 1 | 30000 | 0 |  |  | N/A |  | Pool Furniture Straps, BBQ Grill Upgrade - Concept Walk
20 | 51053-00 | Stripe parking areas | Stripe Parking Lots | GC | Year 1 | 28000 | 0 |  |  | 4 |  | Stripe Parking Lots
47 | 51072-00 | Repair Catwalks | PNA: secure catwalk railings | GC | Year 1 | 28000 | 0 |  |  | 4 |  | PNA: secure catwalk railings
45 | 51077-00 | Repair exterior stair railings | PNA: secure and paint railings | GC | Year 1 | 26000 | 0 |  |  | 4 |  | PNA: secure and paint railings
41 | 51992-00 | Termite Remediation | Lender PCA: Termite remediation - Evidence of drywood termites for areas 2A, 2C, 2E, 2F, 2H, and 2I on the termite map. | Capex | Year 1 | 23250 | 21850 |  |  | N/A |  | Lender PCA: Termite remediation - Evidence of drywood termites for areas 2A, 2C, 2E, 2F, 2H, and 2I on the termite map. | [5 empty] | 2026-04-28
156 | 51076-00 | Swimming pool fencing / gates | PNA: Repair fence and Paint | GC | Year 1 | 22000 | 0 |  |  | 4 |  | PNA: Repair fence and Paint
17 | 51130-00 | Storm sewer piping and drains | PNA: clean storm drains | GC | Year 1 | 20000 | 0 |  |  | 4 |  | PNA: clean storm drains
46 | 51077-00 | Repair patio/balcony railings/fences | Lender PCA: Deteriorated and damaged wood framing and trim were noted at balconies and upper landings including at buildings 4, 5, and 6, and near the leasing office and swimming pool. Repair of the balconies and upper landings by a qualified contractor is recommended. | GC | Year 1 | 20000 | 0 |  |  | 4 |  | Lender PCA: Deteriorated and damaged wood framing and trim were noted at balconies and upper landings including at buildings 4, 5, and 6, and near the leasing office and swimming pool. Repair of the b | [5 empty] | 2026-04-28
58 | 51071-00 | Gutters & downspouts | Lender PCA: Leaf accumulation was noted in gutters across the site. Removal of the leaf debris is recommended. PNA: secure and clean gutters | GC | Year 1 | 19000 | 0 |  |  | 4 |  | Lender PCA: Leaf accumulation was noted in gutters across the site. Removal of the leaf debris is recommended. PNA: secure and clean gutters | [5 empty] | 2027-03-01
23 | 51091-00 | Sidewalks and curbs | PNA: Trip Hazards | GC | Year 1 | 14000 | 0 |  |  | 4 |  | PNA: Trip Hazards
153 | 51022-00 | Swimming pool deck | PNA: deck o seal on pool | GC | Year 1 | 14000 | 0 |  |  | 4 |  | PNA: deck o seal on pool
30 | 51045-00 | Landscape Cleanup & Enhancements | Lender PCA: Trees were observed impeding on the building rooftop and facade between units 54 and 64. No portion of any trees should be in contact with the building exterior. It is recommended that the trees be trimmed back. PNA: remove vines from arbor to repair and paint | Capex | Year 1 | 12000 | 0 |  |  | N/A |  | Lender PCA: Trees were observed impeding on the building rooftop and facade between units 54 and 64. No portion of any trees should be in contact with the building exterior. It is recommended that the | [5 empty] | 2027-03-01
104 | 51141-00 | Pole lighting | Retrofit porch lights to LED - Concept Walk | GC | Year 1 | 12000 | 0 |  |  | 4 |  | Retrofit porch lights to LED - Concept Walk
105 | 51141-00 | Breezeway and patio lights | Concept Walk: there are 13 breezeways (budgeting $750/unit) | GC | Year 1 | 9750 | 0 |  |  | 4 |  | Concept Walk: there are 13 breezeways (budgeting $750/unit)
154 | 51026-00 | Swimming pool pumps repair / replace | PNA: anti entrapment devices | GC | Year 1 | 6800 | 0 |  |  | 4 |  | PNA: anti entrapment devices
48 | 51090-00 | Expansion Joints | PNA: Stucco expansion joints | GC | Year 1 | 6000 | 0 |  |  | 4 |  | PNA: Stucco expansion joints
42 | 51070-00 | Termite damage repairs | Lender PCA: Termite Damage - Repair and replace damaged materials noted on the termite report. Lender PCA: Termite Damage - Repair and replace damaged materials at he base of the second floor wood siding, at the roof fascia of the laundry room, and the exterior of the buildings. | PMC | Year 1 | 5000 | 4100 |  |  | N/A |  | Lender PCA: Termite Damage - Repair and replace damaged materials noted on the termite report. Lender PCA: Termite Damage - Repair and replace damaged materials at he base of the second floor wood sid | [5 empty] | 2026-04-28
65 | 84433.0 | Repair Roof Gambles | Lender PCA: Deteriorated and damaged roof gables were observed at buildings 6 and 7. Repair of the noted issues is recommended. | GC | Year 1 | 3000 | 0 |  |  | 4 |  | Lender PCA: Deteriorated and damaged roof gables were observed at buildings 6 and 7. Repair of the noted issues is recommended. | [5 empty] | 2027-03-01
138 | 51177-00 | Fire monitoring system | Fire Stops: Expire 2031 but some maybe old - approx. 50% - Concept Walk | PMC | Year 1 | 3000 | 0 |  |  | N/A |  | Fire Stops: Expire 2031 but some maybe old - approx. 50% - Concept Walk
142 | 51993-00 | Security alarm systems | Lender PCA: An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recertification of the fire alarm system is recommended. | PMC | Year 1 | 1500 | 0 |  |  | N/A |  | Lender PCA: An annual fire alarm certification tag was not present at the fire alarm control panel. Servicing and recertification of the fire alarm system is recommended. | [5 empty] | 2026-04-28
145 | 51164-00 | Elevators | Lender PCA: Current operation permits were not posted in each elevator cab. Property management should schedule reinspection with the local authority and servicing company. | PMC | Year 1 | 1500 | 0 |  |  | N/A |  | Lender PCA: Current operation permits were not posted in each elevator cab. Property management should schedule reinspection with the local authority and servicing company. | [5 empty] | 2026-04-28
22 | 51091-00 | Sidewalks and curbs | Lender PCA: A potential trip hazard consisting of vertical and horizontal separation was observed to the northeast of building 4 near unit 33. Sectional replacement or grinding is recommended as necessary. | PMC | Year 1 | 500 | 0 |  |  | N/A |  | Lender PCA: A potential trip hazard consisting of vertical and horizontal separation was observed to the northeast of building 4 near unit 33. Sectional replacement or grinding is recommended as nece | [5 empty] | 2027-03-01
33 | 51163-00 | Dumpster enclosures | Lender PCA: The threshold height at the accessible leasing office entrance does not appear to be ADA-compliant. Installation of a compliant threshold is recommended. | PMC | Year 1 | 125 | 0 |  |  | N/A |  | Lender PCA: The threshold height at the accessible leasing office entrance does not appear to be ADA-compliant. Installation of a compliant threshold is recommended. | [5 empty] | 2026-05-28
PROJECTS subtotal (excl. contingency/CM fee)
172 | 51190-00 | Construction Management Fee | CM Fee | CMF | CM Fee | 51630 | 0 | 51630 |  | N/A |  | CM Fee
171 | 51990-00 | Contingency | Contingency Amount | CON | Contingency | 49171 | 4100 | 49171 |  | N/A |  | Contingency Amount

## Clipper Cove
Clipper Cove — 2026 acq · GC pay app
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
108 |  | Interior Upgrades | Concept Walk - Renovate classic units | Capex | Year 1 | 1000000 | 133969 |  |  | N/A |  | Concept Walk - Renovate classic units
18 |  | Parking lot repairs | PNA - Seal coat entire parking lot - add crack fill as needed | GC | Year 1 | 430000 | 129000 |  |  | 3 |  | PNA - Seal coat entire parking lot - add crack fill as needed
70 |  | Exterior paint | PNA - Paint stucco, trim and wood rails | GC | Year 1 | 428000 | 128400 |  |  | 3 |  | PNA - Paint stucco, trim and wood rails
43 |  | Repair exterior stair treads and stringers | PNA - Replace twenty failing exterior stair cases LPCA - Exterior stairs, balconies, and breezeways (near units 104 and 107). Damaged cladding and wood support posts were observed at Building 9. | GC | Year 1 | 360000 | 108000 |  |  | 3 |  | PNA - Replace twenty failing exterior stair cases LPCA - Exterior stairs, balconies, and breezeways (near units 104 and 107). Damaged cladding and wood support posts were observed at Building 9. | [5 empty] | 2026-08-04
128 |  | Patio Fence Enclosure | Concept Walk - Screened in porches for all unit stacks | GC | Year 1 | 270000 | 81000 |  |  | 3 |  | Concept Walk - Screened in porches for all unit stacks
168 |  | Pool Area Upgrades | Concept Walk - Turf installation, landscape cleanup, lighting replacement, palm tree cleanup, etc. | GC | Year 1 | 250000 | 75000 |  |  | 3 |  | Concept Walk - Turf installation, landscape cleanup, lighting replacement, palm tree cleanup, etc.
66 |  | Wall framing | PNA - Repair structural framing in areas that indicate failures | GC | Year 1 | 210000 | 63000 |  |  | 3 |  | PNA - Repair structural framing in areas that indicate failures
159 |  | Tennis / sports court | Concept Walk - Tennis court repurpose ($100k) + repurpose racquetball court to maintenance/storage ($50k) LPCA - Tennis Courts ($10k) LPCA - Racquetball courts ($5k) | GC | Year 1 | 134854 | 40456 |  |  | 3 |  | Concept Walk - Tennis court repurpose ($100k) + repurpose racquetball court to maintenance/storage ($50k) LPCA - Tennis Courts ($10k) LPCA - Racquetball courts ($5k) | [5 empty] | 2027-05-06
134 |  | Clubhouse / Office redecorate (FFE) | Concept Walk - Leasing office / clubhouse redec and furniture | Capex | Year 1 | 105000 | 14962 |  |  | N/A |  | Concept Walk - Leasing office / clubhouse redec and furniture
133 |  | Clubhouse / Office remodel | Concept Walk - Clubhouse repaint, kitchen remodel, & flooring | GC | Year 1 | 95000 | 28500 |  |  | 3 |  | Concept Walk - Clubhouse repaint, kitchen remodel, & flooring
64 |  | Repair / replace siding | PNA - Pressure wash to remove mildew. Repair/replace damaged or broken vinyl siding matching the existing color | GC | Year 1 | 92000 | 27600 |  |  | 3 |  | PNA - Pressure wash to remove mildew. Repair/replace damaged or broken vinyl siding matching the existing color
44 |  | Repair exterior stair railings | PNA - Repair failing stair and catwalk railings | GC | Year 1 | 86000 | 25800 |  |  | 3 |  | PNA - Repair failing stair and catwalk railings
27 |  | Erosion control and drainage | PNA - Erosion control around all buildings | GC | Year 1 | 82500 | 24750 |  |  | 3 |  | PNA - Erosion control around all buildings
68 |  | Stucco repairs | PNA - Failing and damaged stucco was observed throughout the property | GC | Year 1 | 82000 | 24600 |  |  | 3 |  | PNA - Failing and damaged stucco was observed throughout the property
156 |  | Pool furniture | Concept Walk - 1st pool furniture + 2nd pool furniture | Capex | Year 1 | 75000 | 0 |  |  | N/A |  | Concept Walk - 1st pool furniture + 2nd pool furniture
19 |  | Asphalt seal coating | PNA - Repair broken or failing asphalt LPCA - Asphalt pavement | GC | Year 1 | 68000 | 20400 |  |  | 3 |  | PNA - Repair broken or failing asphalt LPCA - Asphalt pavement | [5 empty] | 2027-05-06
57 |  | Gutters & downspouts | PNA - Repair, clean, reattach replace gutters throughout the property | GC | Year 1 | 62500 | 18750 |  |  | 3 |  | PNA - Repair, clean, reattach replace gutters throughout the property
71 |  | Repair / replace wood trim | PNA - Rotted window trim and facia was observed, repairs would include paint to match | GC | Year 1 | 52000 | 15600 |  |  | 3 |  | PNA - Rotted window trim and facia was observed, repairs would include paint to match
29 |  | Landscape Cleanup & Enhancements | Concept Walk - Office landscape enhancements | GC | Year 1 | 50000 | 8572 |  |  | 3 |  | Concept Walk - Office landscape enhancements
153 |  | Swimming pool pumps repair / replace | PNA - Repair the hot tub that is currently not working Concept Walk - Fill in hot tub and make seating area | GC | Year 1 | 50000 | 15000 |  |  | 3 |  | PNA - Repair the hot tub that is currently not working Concept Walk - Fill in hot tub and make seating area
42 |  | Repair balcony framing & decking | PNA - Repair failing lightweight concrete on catwalk | GC | Year 1 | 49000 | 14700 |  |  | 3 |  | PNA - Repair failing lightweight concrete on catwalk
30 |  | Tree Trimming | PNA - Tree trim, get overgrowth off buildings | GC | Year 1 | 48000 | 14400 |  |  | 3 |  | PNA - Tree trim, get overgrowth off buildings
105 |  | Lighing controller system | PNA - Common area light fixtures (building light LED retrofit) | GC | Year 1 | 46000 | 13800 |  |  | 3 |  | PNA - Common area light fixtures (building light LED retrofit)
145 |  | Golf Cart | Concept Walk - 3 golf carts | Capex | Year 1 | 45000 | 0 |  |  | N/A |  | Concept Walk - 3 golf carts |  |  | May need to use some funds for mailboxes
22 |  | Sidewalks and curbs | PNA - Replace failing areas of sidewalk LPCA - Trip hazards at concrete walkway | GC | Year 1 | 42000 | 12600 |  |  | 3 |  | PNA - Replace failing areas of sidewalk LPCA - Trip hazards at concrete walkway | [5 empty] | 2026-08-04
32 |  | Dumpster enclosures | PNA - Repair dumpster enclosures | GC | Year 1 | 42000 | 12600 |  |  | 3 |  | PNA - Repair dumpster enclosures
28 |  | Landscape irrigation | Concept Walk - Irrigation LPCA - Irrigation | GC | Year 1 | 40000 | 300 |  |  | 3 |  | Concept Walk - Irrigation LPCA - Irrigation | [5 empty] | 2027-05-06
103 |  | Pole lighting | PNA - Replace with LED fixture | GC | Year 1 | 39000 | 11700 |  |  | 3 |  | PNA - Replace with LED fixture
150 |  | Swimming pool resurface | PNA - Resurface the pool and hot tub at the leasing office | GC | Year 1 | 38000 | 11400 |  |  | 3 |  | PNA - Resurface the pool and hot tub at the leasing office
126 |  | Stovetop fire suppression | PNA - Fire protection | Capex | Year 1 | 37632 | 0 |  |  | N/A |  | PNA - Fire protection
23 |  | Detention pond fountain | Concept Walk - Installation of 6 lake fountains | GC | Year 1 | 35000 | 0 |  |  | 3 |  | Concept Walk - Installation of 6 lake fountains
135 |  | Model Unit | Concept Walk - Update model to include appliances, cabinetry, flooring, & fixtures | Capex | Year 1 | 35000 | 0 |  |  | N/A |  | Concept Walk - Update model to include appliances, cabinetry, flooring, & fixtures
125 |  | Drier vents | PNA - Drier vents | Capex | Year 1 | 28800 | 0 |  |  | N/A |  | PNA - Drier vents
161 |  | Playground area and equipment | PNA - install fall zone borders and add fall zone material | GC | Year 1 | 28000 | 8400 |  |  | 3 |  | PNA - install fall zone borders and add fall zone material
47 |  | Expansion Joints | PNA - Expansion joints | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | PNA - Expansion joints
17 |  | Storm sewer piping and drains | PNA - Clean storm drains throughout property | GC | Year 1 | 24000 | 7200 |  |  | 3 |  | PNA - Clean storm drains throughout property
20 |  | Stripe parking areas | PNA - Stripe parking areas | GC | Year 1 | 24000 | 7200 |  |  | 3 |  | PNA - Stripe parking areas
59 |  | Sealants & caulking | PNA - Sealants & caulking | GC | Year 1 | 24000 | 7200 |  |  | 3 |  | PNA - Sealants & caulking
94 |  | HVAC pipe insulation | PNA - Install linset insulation | GC | Year 1 | 24000 | 7200 |  |  | 3 |  | PNA - Install linset insulation
41 |  | Termite damage repairs | LPCA - WDO Repairs | GC | Year 1 | 19500 | 5850 |  |  | 3 |  | LPCA - WDO Repairs | [5 empty] | 2027-05-06
21 |  | ADA parking & ramps | PNA - Repairs to failing ADA ramps LPCA - ADA van-accessible parking | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | PNA - Repairs to failing ADA ramps LPCA - ADA van-accessible parking | [5 empty] | 2027-05-06
152 |  | Swimming pool deck | PNA - Powerwash decking on both pools | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | PNA - Powerwash decking on both pools
53 |  | Modified bitumen membrane repairs / replacement | PNA - Replace the modified bit roofing on racquetball structures | GC | Year 1 | 16500 | 4950 |  |  | 3 |  | PNA - Replace the modified bit roofing on racquetball structures
98 |  | Electrical distribution - exterior | PNA - Electrical distribution LPCA - Electrical (open electrical boxes were observed near irrigation piping) | GC | Year 1 | 12000 | 3600 |  |  | 3 |  | PNA - Electrical distribution LPCA - Electrical (open electrical boxes were observed near irrigation piping) | [5 empty] | 2026-08-04
151 |  | Swimming pool coping and tile | PNA - Replace swimming pool coping | GC | Year 1 | 12000 | 3600 |  |  | 3 |  | PNA - Replace swimming pool coping
127 |  | Interior microbial growth treatment | LPCA - Localized water staining was observed at the ceiling of Unit 103.The unit appears to currently be used for miscellaneous storage by site maintenance. Repair of the noted issue and refurbishment of the interior finishes is recommended. | PMC | Year 1 | 1000 | 0 |  |  | N/A |  | LPCA - Localized water staining was observed at the ceiling of Unit 103.The unit appears to currently be used for miscellaneous storage by site maintenance. Repair of the noted issue and refurbishment | [5 empty] | 2027-05-06
PROJECTS subtotal (excl. contingency/CM fee)
171 |  | Construction Management Fee | CM Fee | CMF | CM Fee | 249600 | 0 | 249600 |  | N/A |  | CM Fee
170 |  | Contingency | Contingency Amount | CON | Contingency | 237714 | 0 | 237714 |  | N/A |  | Contingency Amount

## Cypress Ridge
Cypress Ridge — 2026 acq · GC pay app
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
70 |  | Exterior paint | PNA - Paint community | GC | Year 1 | 227400 | 68220 |  |  | 3 |  | PNA - Paint community
29 |  | Landscape Cleanup & Enhancements | Concept Walk - landscape cleanup and ground cover | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | Concept Walk - landscape cleanup and ground cover
50 |  | Asphalt composite shingle roofing | PNA - Tune up roofs (building replacements as needed) TCAC - Asphalt shingle | GC | Year 1 | 50000 | 15000 |  |  | 3 |  | PNA - Tune up roofs (building replacements as needed) TCAC - Asphalt shingle
161 |  | Playground area and equipment | Concept Walk - playground and fall zone | GC | Year 1 | 45000 | 13500 |  |  | 3 |  | Concept Walk - playground and fall zone
68 |  | Stucco repairs | PNA - Patch cracked stucco LPCA - Horizontal cracking was noted at multiple facades including Units 2129, 2159, 2209, and 2225. Repair of the noted issue and sealing of all cracking is recommended. | GC | Year 1 | 40000 | 12000 |  |  | 3 |  | PNA - Patch cracked stucco LPCA - Horizontal cracking was noted at multiple facades including Units 2129, 2159, 2209, and 2225. Repair of the noted issue and sealing of all cracking is recommended. | [5 empty] | 2027-03-18
20 |  | Stripe parking areas | PNA - Stripe parking lot | GC | Year 1 | 28000 | 8400 |  |  | 3 |  | PNA - Stripe parking lot
19 |  | Asphalt Milling/Paving/SealCoat | PNA - Crack fill TCAC - Asphalt seal coat and striping | GC | Year 1 | 27000 | 8100 |  |  | 3 |  | PNA - Crack fill TCAC - Asphalt seal coat and striping
57 |  | Gutters & downspouts | PNA - Repair downspouts and gutters | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | PNA - Repair downspouts and gutters
71 |  | Repair / replace wood trim | PNA - Repair / replace wood trim | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | PNA - Repair / replace wood trim
18 |  | Parking Lots | PNA - repair potholes | GC | Year 1 | 22000 | 6600 |  |  | 3 |  | PNA - repair potholes
47 |  | Expansion Joints | PNA - Expansion joints | GC | Year 1 | 20000 | 6000 |  |  | 3 |  | PNA - Expansion joints
59 |  | Sealants & caulking | PNA - Seal roof cracks LPCA (PR-90) - Evidence of discoloration was noted in the upper bedroom or bathroom ceilings at Units 2 and 45 and is indicative of potential roof leaks. Additionally, deteriorated shingles were observed near Unit 2159. Evaluation and repair by a qualified contractor is recommended. | GC | Year 1 | 20000 | 6000 |  |  | 3 |  | PNA - Seal roof cracks LPCA (PR-90) - Evidence of discoloration was noted in the upper bedroom or bathroom ceilings at Units 2 and 45 and is indicative of potential roof leaks. Additionally, deteriora | [5 empty] | 2026-09-14
61 |  | Roof treatment / cleaning | LPCA - Organic growth including moss was noted on main and secondary asphalt-shingle roofs. Over time the organic material will hasten deterioration and create pathways for water intrusion. Cleaning and removal of the organic material is recommended. | GC | Year 1 | 18900 | 5670 |  |  | 3 |  | LPCA - Organic growth including moss was noted on main and secondary asphalt-shingle roofs. Over time the organic material will hasten deterioration and create pathways for water intrusion. Cleaning a | [5 empty] | 2026-09-14
32 |  | Dumpster enclosures | PNA - Repair enclosures | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | PNA - Repair enclosures
98 |  | Electrical distribution - exterior | PNA - Repair lighting controllers | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | PNA - Repair lighting controllers
108 |  | Partial Renovation | Seller to address: LPCA - Units 65 and 103 are considered down units due to evictions that are currently in progress. Management reported moderate deterioration in the units. Renovation is recommended return the down units to rentable condition. | Capex | Year 1 | 17000 | 0 |  |  | N/A |  | Seller to address: LPCA - Units 65 and 103 are considered down units due to evictions that are currently in progress. Management reported moderate deterioration in the units. Renovation is recommended | [5 empty] | 2027-03-18
22 |  | Sidewalks and curbs | PNA - Grind trip hazards | GC | Year 1 | 16000 | 4800 |  |  | 3 |  | PNA - Grind trip hazards
130 |  | Signage - entry | Concept Walk - replace main ID and add directional signage | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Concept Walk - replace main ID and add directional signage
143 |  | Video systems | Concept Walk - replace inoperable cameras and add in dead zones | Capex | Year 1 | 15000 | 47799 |  |  | N/A |  | Concept Walk - replace inoperable cameras and add in dead zones
21 |  | ADA parking & ramps | PNA - Repair concrete on ramp | GC | Year 1 | 14000 | 4200 |  |  | 3 |  | PNA - Repair concrete on ramp
58 |  | Flashing | PNA - Flashing | GC | Year 1 | 12000 | 3600 |  |  | 3 |  | PNA - Flashing
126 |  | Stovetop fire suppression | PNA - Fire stops | Capex | Year 1 | 11956 | 0 |  |  | N/A |  | PNA - Fire stops
125 |  | Drier vents | PNA - Drier vents | Capex | Year 1 | 11590 | 0 |  |  | N/A |  | PNA - Drier vents
160 |  | Outdoor kitchen, fire pits, and seating area | Concept Walk - outdoor grills and seating area | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Concept Walk - outdoor grills and seating area
41 |  | Termite damage repairs | LPCA - The WDO report also stated fungus/dryrot was observed. Partner recomments repairs. | GC | Year 1 | 5000 | 1500 |  |  | 3 |  | LPCA - The WDO report also stated fungus/dryrot was observed. Partner recomments repairs. | [5 empty] | 2027-03-18
43 |  | Repair exterior stair treads and stringers | LPCA - Subsequent to site inspection activities, Partner was notified that installation of EV charging station caused cracking at exterior steps near Unit 103. Repair recommended. | GC | Year 1 | 5000 | 1500 |  |  | 3 |  | LPCA - Subsequent to site inspection activities, Partner was notified that installation of EV charging station caused cracking at exterior steps near Unit 103. Repair recommended. | [5 empty] | 2026-09-14
127 |  | Interior microbial growth treatment | Seller to address: LPCA (PR-90) - Water damage was observed at ceiling areas in the bathroom and bedroom of Unit 2 and the bedroom of Unit 45. The affected areas were relatively limited (less than 10 square feet) and may be remediated by properly trained maintenance staff. Repair of the noted interior finishes is recommended. All affected materials should be removed, underlying substrates cleaned and dried and finishes replaced | PMC | Year 1 | 3000 | 0 |  |  | N/A |  | Seller to address: LPCA (PR-90) - Water damage was observed at ceiling areas in the bathroom and bedroom of Unit 2 and the bedroom of Unit 45. The affected areas were relatively limited (less than 10 | [5 empty] | 2026-06-16
40 |  | Termite Remediation | LPCA - Partner was provided with a WDO report by Redwood Empire Termite and Pest Control, dated January 25, 2026. The report stated dry wood termites and carpenter bees was observed. The report included recommendations for treatment of the carpenter bees and drywood termites for $920. | PMC | Year 1 | 920 | 0 |  |  | N/A |  | LPCA - Partner was provided with a WDO report by Redwood Empire Termite and Pest Control, dated January 25, 2026. The report stated dry wood termites and carpenter bees was observed. The report includ | [5 empty] | 2027-03-18
25 |  | Site perimeter fencing | LPCA - Minor fence board damage was noted at a single location near Unit 2154. Repair of the noted issue is recommended. | PMC | Year 1 | 750 | 0 |  |  | N/A |  | LPCA - Minor fence board damage was noted at a single location near Unit 2154. Repair of the noted issue is recommended. | [5 empty] | 2027-03-18
136 |  | Fire system - Code Violations | LPCA (PR-90) - There are open There are open fire code violations for expired fire extinguishers at 1815 Meda Ave. At the time of the stie visit, Partner noted the latest fire extinguisher inspection from October 13, 2025. Partner recommends contacting the city and obtaining closure. | PMC | Year 1 | 500 | 0 |  |  | N/A |  | LPCA (PR-90) - There are open There are open fire code violations for expired fire extinguishers at 1815 Meda Ave. At the time of the stie visit, Partner noted the latest fire extinguisher inspection | [5 empty] | 2026-06-16
PROJECTS subtotal (excl. contingency/CM fee)
171 |  | Construction Management Fee | CM Fees | CMF | CM Fee | 40531 | 0 | 40531 |  | N/A |  | CM Fees
170 |  | Contingency | Contingency Amount | CON | Contingency | 38601 | 0 | 38601 |  | N/A |  | Contingency Amount

## Oslo
Oslo — 2026 acq · GC none ($0)
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
108 | 84110 | Staircase |  | Capex | Year 1 | 95000 | 119427 |  |  | N/A
| 84112 | Exterior Lighting |  | PMC | Year 1 | 5000 | 0 |  |  | N/A
| 84115 | Sidewalks |  | PMC | Year 1 | 5000 | 0 |  |  | N/A
| 84190 | Fitness Center & Equipment |  | PMC | Year 1 | 5000 | 0 |  |  | N/A
| 84200 | Common Area & Playground |  | GC | Year 1 | 40000 | 0 |  |  | 4
| 84204 | Asphalt & Paving |  | PMC | Year 1 | 5000 | 0 |  |  | N/A
| 84205 | Fences & gates |  | PMC | Year 1 | 5000 | 0 |  |  | N/A
| 84300 | Landscaping & Irrigation |  | PMC | Year 1 | 5000 | 20125 |  |  | N/A
99 | 83106 | Dryer Vent Cleaning | Dryer Vent Cleaning - Contingency | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Dryer Vent Cleaning - Contingency
100 | 83109 | Gutter Cleaning | Gutter Cleaning - Contingency | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Gutter Cleaning - Contingency
101 | 83209 | Plumbing | Plumbing Repairs - Contingency | PMC | Year 1 | 5000 | 1605 |  |  | N/A |  | Plumbing Repairs - Contingency
106 | 83436 | Windows/Doors | Window/Door Repairs - Contingency | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Window/Door Repairs - Contingency
PROJECTS subtotal (excl. contingency/CM fee)
110 | 85305 | Construction Management Fees | CM Fees | CMF | Year 1 | 4988 | 0 | 4988 |  | N/A |  | CM Fees
109 | 84510 | Contingency Amount | Contingency | CON | Year 1 | 4750 | 0 | 4750 |  | N/A |  | Contingency

## San Regis
San Regis — 2026 acq · GC none ($0)
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
110 |  | ADA Accessibility | ADA Upgrades (responsible for 25 of 43 total required) | Capex | Year 1 | 2321300 | 0 |  |  | N/A |  | ADA Upgrades (responsible for 25 of 43 total required)
70 |  | Exterior paint | PNA - exterior building | GC | Year 1 | 646000 | 0 |  |  | 4 |  | PNA - exterior building
108 |  | Interior Upgrades | 2746679.999999999 | Capex | Year 1 | 425380 | 0 |  |  | N/A |  | 2746679.999999999
69 |  | Interior Hallway flooring / painting | PNA - paint hallways/breezeways | GC | Year 1 | 156000 | 0 |  |  | 4 |  | PNA - paint hallways/breezeways
128 |  | ADA Relocation Costs | ADA Relocation Costs | Capex | Year 1 | 125000 | 0 |  |  | N/A |  | ADA Relocation Costs
133 |  | Clubhouse / Office remodel | Concept Walk - fix water leaks and prevent any continued deterioration in leasing office (2nd and 3rd floor) | GC | Year 1 | 100000 | 0 |  |  | 4 |  | Concept Walk - fix water leaks and prevent any continued deterioration in leasing office (2nd and 3rd floor)
53 |  | Modified bitumen membrane repairs / replacement | PNA - was not able to get on roofs but based on age suspect damage on all roofs and replace roof on office building | GC | Year 1 | 95000 | 0 |  |  | 4 |  | PNA - was not able to get on roofs but based on age suspect damage on all roofs and replace roof on office building
104 |  | Breezeway and patio lights | PNA - replace breezeway and catwalk lighting to LED | GC | Year 1 | 59800 | 0 |  |  | 4 |  | PNA - replace breezeway and catwalk lighting to LED
150 |  | Swimming pool resurface | PNA - resurface pool and hot tub | GC | Year 1 | 58000 | 0 |  |  | 4 |  | PNA - resurface pool and hot tub
159 |  | Tennis / sports court | Concept Walk - sports court furniture | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | Concept Walk - sports court furniture
42 |  | Repair balcony framing & decking | PNA - repair and recoat exposed walkways | GC | Year 1 | 39500 | 0 |  |  | 4 |  | PNA - repair and recoat exposed walkways
126 |  | Stovetop fire suppression | PNA - fire stops | Capex | Year 1 | 38220 | 0 |  |  | N/A |  | PNA - fire stops
152 |  | Swimming pool deck | PNA - repair cracks and seal | GC | Year 1 | 38000 | 0 |  |  | 4 |  | PNA - repair cracks and seal
40 |  | Termite Remediation | WDIR - findings from WDIR (placeholder) | GC | Year 1 | 31500 | 0 |  |  | 4 |  | WDIR - findings from WDIR (placeholder)
17 |  | Storm sewer piping and drains | PNA - clear parking lot drains | GC | Year 1 | 30000 | 0 |  |  | 4 |  | PNA - clear parking lot drains
29 |  | Landscape Cleanup & Enhancements | Concept Walk - tree trim + landscape cleanup | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Concept Walk - tree trim + landscape cleanup
68 |  | Stucco repairs | PNA - patch stucco and paint to match | GC | Year 1 | 30000 | 0 |  |  | 4 |  | PNA - patch stucco and paint to match
156 |  | Pool furniture | Concept Walk - pool furniture | Capex | Year 1 | 30000 | 0 |  |  | N/A |  | Concept Walk - pool furniture
18 |  | Parking lot repairs | PNA - repair potholes | GC | Year 1 | 28000 | 0 |  |  | 4 |  | PNA - repair potholes
20 |  | Stripe parking areas | PNA - stripe parking lot | GC | Year 1 | 27000 | 0 |  |  | 4 |  | PNA - stripe parking lot
57 |  | Gutters & downspouts | PNA - replace crushed down spouts | GC | Year 1 | 21000 | 0 |  |  | 4 |  | PNA - replace crushed down spouts
59 |  | Sealants & caulking | PNA - sealants & caulking | GC | Year 1 | 20000 | 0 |  |  | 4 |  | PNA - sealants & caulking
58 |  | Flashing | PNA - flashing | GC | Year 1 | 19800 | 0 |  |  | 4 |  | PNA - flashing
98 |  | Electrical distribution - exterior | PNA - provide and install can light adapters to catwalk lighting and inspect and replace lighting controllers | GC | Year 1 | 19500 | 0 |  |  | 4 |  | PNA - provide and install can light adapters to catwalk lighting and inspect and replace lighting controllers
19 |  | Asphalt seal coating | PNA - crack fill | GC | Year 1 | 19000 | 0 |  |  | 4 |  | PNA - crack fill
32 |  | Dumpster enclosures | PNA - Prevent damage to hallway to parking lot | GC | Year 1 | 18000 | 0 |  |  | 4 |  | PNA - Prevent damage to hallway to parking lot
21 |  | ADA parking & ramps | PNA - repair concrete on ramp | GC | Year 1 | 14000 | 0 |  |  | 4 |  | PNA - repair concrete on ramp
22 |  | Sidewalks and curbs | PNA - grind trip hazards | GC | Year 1 | 14000 | 0 |  |  | 4 |  | PNA - grind trip hazards
155 |  | Swimming pool fencing / gates | PNA - fences & gates - swimming pool | GC | Year 1 | 14000 | 0 |  |  | 4 |  | PNA - fences & gates - swimming pool
83 |  | Domestic water piping | PNA - insulate hot water lines on office roofs | GC | Year 1 | 10000 | 0 |  |  | 4 |  | PNA - insulate hot water lines on office roofs
87 |  | Common area water heaters / boilers | PNA - insulate boiler lines on office roof | GC | Year 1 | 10000 | 0 |  |  | 4 |  | PNA - insulate boiler lines on office roof
47 |  | Expansion Joints | PNA - seal joint | GC | Year 1 | 8500 | 0 |  |  | 4 |  | PNA - seal joint
136 |  | Fire suppression system | LPCA - The annual inspection and 5-year inspection tags were not current. Partner recommends obtaining current inspection tags. | PMC | Year 1 | 1500 | 0 |  |  | N/A |  | LPCA - The annual inspection and 5-year inspection tags were not current. Partner recommends obtaining current inspection tags. | [5 empty] | 2026-10-12
144 |  | Elevators | LPCA - Current operation permits were not posted in each elevator cab. Partner recommends obtaining current inspection tags. | PMC | Year 1 | 1500 | 0 |  |  | N/A |  | LPCA - Current operation permits were not posted in each elevator cab. Partner recommends obtaining current inspection tags. | [5 empty] | 2026-10-12
PROJECTS subtotal (excl. contingency/CM fee)
171 |  | Construction Management Fee | CM Fee | CMF | CM Fee | 238849 | 0 | 238849 |  | N/A |  | CM Fee
170 |  | Contingency | Contingency Amount | CON | Contingency | 227475 | 0 | 227475 |  | N/A |  | Contingency Amount

## Tribute Verdae
Tribute Verdae — 2026 acq · GC pay app
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
50 | 84250.0 | Radon Long-Term Testing and Remediation | Post-Closing Radon Long-Term Testing and Remediation for 21 units | Capex | Year 1 | 150000 | 0 |  |  | N/A |  | Post-Closing Radon Long-Term Testing and Remediation for 21 units
21 | 84221.0 | Accessibility Exterior accessible route | Please refer to the accessibility report | GC | Year 1 | 132850 | 39855 |  |  | 3 |  | Please refer to the accessibility report
31 | 84435.0 | Erosion control | Additional soil and regional turf to barren areas Barren turf was observed at isolated areas throughout, typical to side and rear building elevations and near condensing units at Buildings 4, 6, 8 and 9. An area of barren turf was observed to exhibit soil erosion exposing irrigation piping at the southwest corner of Building 8. | Capex | Year 1 | 100000 | 9153 |  |  | N/A |  | Additional soil and regional turf to barren areas Barren turf was observed at isolated areas throughout, typical to side and rear building elevations and near condensing units at Buildings 4, 6, 8 an | [5 empty] | 2027-03-31
33 | 84434.0 | Retaining walls | Add additional retaining wall between building 8 and 9 | GC | Year 1 | 75000 | 22500 |  |  | 3 |  | Add additional retaining wall between building 8 and 9
145 | 84130.0 | Dog Park | Purchasing new astroturf, benches, and shade | GC | Year 1 | 75000 | 22500 |  |  | 3 |  | Purchasing new astroturf, benches, and shade
43 | 84195.0 | Playground equipment | New Playground (Find Placement) | GC | Year 1 | 65000 | 19500 |  |  | 3 |  | New Playground (Find Placement)
51 | 84905.0 | Sustainability Improvements | Reserve for post-closing sustainability due diligence review and imrovements | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | Reserve for post-closing sustainability due diligence review and imrovements
60 | 84104.0 | Repair balcony framing & decking | Inspect & repair wood decking on breezeways. Some of the wood-framed upper floor balconies & breezeway landings were observed with warped decking, uneven decking edges, and/or inconsistent spacing/gaps between the decking boards or raised nail heads, all of which can result in slip, trip or fall hazards. Additionally, wood blocking below upper balcony guardrail posts was misaligned with the railing post base fasteners at some locations, resulting in weakened connection. | GC | Year 1 | 50000 | 15000 |  |  | 3 |  | Inspect & repair wood decking on breezeways. Some of the wood-framed upper floor balconies & breezeway landings were observed with warped decking, uneven decking edges, and/or inconsistent spacing/gap
14 | 84204.0 | Asphalt Coating | Asphalt seal coat & striping | GC | Year 1 | 46000 | 13800 |  |  | 3 |  | Asphalt seal coat & striping
89 | 84202.0 | Gutters & downspouts | Inspect and repair downspouts, splash blocks | GC | Year 1 | 45000 | 13500 |  |  | 3 |  | Inspect and repair downspouts, splash blocks
22 | 84201.0 | Accessibility Parking and route from parking | Please refer to the accessibility report | GC | Year 1 | 32000 | 9600 |  |  | 3 |  | Please refer to the accessibility report
161 | 84385.0 | Sanitary Sewer Piping | At sewer scope cleanouts numbers 9 and 2 joint separations were observed. It is recommended to replace or repair the joints via trenchless point repairs or excavation and joint replacement. At several mainline segments grade three joint offsets with debris buildup were observed. It is recommended these be repaired via chemical grout sealing or sectional lining. | Capex | Year 1 | 29500 | 4481 |  |  | N/A |  | At sewer scope cleanouts numbers 9 and 2 joint separations were observed. It is recommended to replace or repair the joints via trenchless point repairs or excavation and joint replacement. At several
59 | 84430.0 | Concrete deck / floor fill | Inspect route and seal concrete cracks The concrete patio in the northwest corner contained exposed and improperly terminated (unlocked) strands. These strands are partially buried, and the exposed sections exhibit surface corrosion. Repairs should be recommended by the EOR and/or contractor, and should include grouting the pockets to enclose the tendons. The repairs may be covered by original building warranty since this appears to be a construction defect or omission. | GC | Year 1 | 28000 | 8400 |  |  | 3 |  | Inspect route and seal concrete cracks The concrete patio in the northwest corner contained exposed and improperly terminated (unlocked) strands. These strands are partially buried, and the exposed s
72 | 84206.0 | Pressure Wash | Pressure wash 1st floor of brick to remove clay spoils | GC | Year 1 | 28000 | 8400 |  |  | 3 |  | Pressure wash 1st floor of brick to remove clay spoils
79 | 84104.0 | Repair balcony support posts | The bases at some balcony support posts are overhanging the concrete patio slab edge and not fully bearing on the concrete patio. The structural posts overhang was measured to be as much as 2” to 3” in some locations. Additionally, the post bases are located less than 8” above exposed earth. | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | The bases at some balcony support posts are overhanging the concrete patio slab edge and not fully bearing on the concrete patio. The structural posts overhang was measured to be as much as 2” to 3” i
29 | 84300.0 | Landscape irrigation | Inspect and repair irrigation prior to installing turf | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Inspect and repair irrigation prior to installing turf
30 | 84435.0 | Erosion control | The grade around a few of the apartment buildings exhibited substantial runoff erosion and/or water ponding adjacent to areas with air conditioning condensing units. Additionally, some downspouts discharge directly at grade next to the foundation walls contributing to the general site erosion. | GC | Year 1 | 15000 | 4500 |  |  | 3 |  | The grade around a few of the apartment buildings exhibited substantial runoff erosion and/or water ponding adjacent to areas with air conditioning condensing units. Additionally, some downspouts disc
19 | 84201.0 | Stripe parking areas | Restripe parking | GC | Year 1 | 14000 | 4200 |  |  | 3 |  | Restripe parking
36 | 84361.0 | Swimming pool deck | Pressure wash deck | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Pressure wash deck
42 | 84385.0 | Storm sewer piping and drains | Add storm drains between bulding 8 and 9 | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | Add storm drains between bulding 8 and 9
25 | 84116.0 | Accessibility Public toilets /common area toilets | Please refer to the accessibility report | GC | Year 1 | 6700 | 2010 |  |  | 3 |  | Please refer to the accessibility report
165 | 84217.0 | Refrigerant linesets insulation | Partner observed that the insulation on the exterior portion of the refrigerant linesets between the condensing units and fan coil units were deteriorated. . Repair of deteriorated refrigerant linesets is recommended as an immediate repair. | GC | Year 1 | 6500 | 1950 |  |  | 3 |  | Partner observed that the insulation on the exterior portion of the refrigerant linesets between the condensing units and fan coil units were deteriorated. . Repair of deteriorated refrigerant lineset
23 | 84221.0 | Accessibility Exterior door approaches | Please refer to the accessibility report | GC | Year 1 | 5250 | 1575 |  |  | 3 |  | Please refer to the accessibility report
37 | 84361.0 | Swimming pool fencing / gates | Repair gate closers | GC | Year 1 | 4000 | 1200 |  |  | 3 |  | Repair gate closers
26 | 84116.0 | Accessibility Access to other items | Please refer to the accessibility report | GC | Year 1 | 3650 | 1095 |  |  | 3 |  | Please refer to the accessibility report
54 | 84435.0 | Jack & underpin foundations | Inspect all building cut post tension cables and seal | GC | Year 1 | 3000 | 900 |  |  | 3 |  | Inspect all building cut post tension cables and seal
78 | 84102.0 | Repair brick pier damage | The brick pier adjacent to garage 2202 was observed with damage, likely resulting from mechanical impact. The observed distress appears to be resulting from vehicular impact and did not appear to have significantly affected the structural integrity of the support structure or the second-floor balcony. It is recommended that all bricks be replaced | GC | Year 1 | 2500 | 750 |  |  | 3 |  | The brick pier adjacent to garage 2202 was observed with damage, likely resulting from mechanical impact. The observed distress appears to be resulting from vehicular impact and did not appear to have
24 | 84221.0 | Accessibility Interior access & access to amenities | Please refer to the accessibility report | GC | Year 1 | 750 | 225 |  |  | 3 |  | Please refer to the accessibility report
PROJECTS subtotal (excl. contingency/CM fee)
176 | 84505.0 | Construction Management Fee | CM Fee | CMF | CM Fee | 51635 | 0 | 51635 |  | N/A |  | CM Fee

## Walnut Square
Walnut Square — 2026 acq · GC pay app
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
95 | 84101.0 | Exterior building Painting | Paint community | GC | Year 1 | 232000 | 69600 |  |  | 3 |  | Paint community
27 | 84205.0 | Fences & gates - site perimeter | Rebuild 2500 lf of wood fence, repair 2000 lf of iron fence and paint both | GC | Year 1 | 192000 | 0 |  |  | 4 |  | Rebuild 2500 lf of wood fence, repair 2000 lf of iron fence and paint both
15 | 84303.0 | Landscape Cleanup and Enhancements | Tree trim and landscape cleanup | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | Tree trim and landscape cleanup
129 | 84208 | Leasing office floor/wall finishes, Replace | Reflooring / repaint in office | GC | Year 1 | 50000 | 0 |  |  | 4 |  | Reflooring / repaint in office
130 | 84306 | Leasing office FF&E, Replace | Leasing office FF&E, Replace | GC | Year 1 | 50000 | 4702 |  |  | 4 |  | Leasing office FF&E, Replace
38 | 84195.0 | Playground area | Turf around playground areas | GC | Year 1 | 45000 | 0 |  |  | 4 |  | Turf around playground areas
23 | 84221.0 | ADA parking & curb cuts | Remove and replace damaged curbs on community | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Remove and replace damaged curbs on community
22 | 84204.0 | Pavement | Remove and replace pothole areas on site | GC | Year 1 | 28000 | 0 |  |  | 4 |  | Remove and replace pothole areas on site
80 | 84202.0 | Gutters & downspouts | Clean and repitch gutters and repair down spouts throughout property | GC | Year 1 | 28000 | 8400 |  |  | 3 |  | Clean and repitch gutters and repair down spouts throughout property
168 | 84112 | Replace breezeway lights | Replace front door lights with mini LED wallpacks | GC | Year 1 | 24000 | 2400 |  |  | 4 |  | Replace front door lights with mini LED wallpacks
87 | 84105.0 | Repair / replace cement fiber siding | Repair or replace damaged siding siding | GC | Year 1 | 19000 | 5700 |  |  | 3 |  | Repair or replace damaged siding siding
72 | 84206.0 | Expansion joints | Exterior Expansion Joints | GC | Year 1 | 17000 | 0 |  |  | 4 |  | Exterior Expansion Joints
96 | 84105.0 | Repair / replace wood trim | Repair / replace wood trim | GC | Year 1 | 16000 | 4800 |  |  | 3 |  | Repair / replace wood trim
109 | 84106.0 | Drier vents | Drier vents | GC | Year 1 | 15675 | 0 |  |  | 4 |  | Drier vents
42 | 84111.0 | Dumpster enclosures | Repair and paint | GC | Year 1 | 14000 | 0 |  |  | 4 |  | Repair and paint
18 | 84470.0 | Water Distribution Piping | Two different water leaks from meter boxes Allowance to repair city water main leaks at the property based on observed condition | GC | Year 1 | 12000 | 0 |  |  | 4 |  | Two different water leaks from meter boxes Allowance to repair city water main leaks at the property based on observed condition
24 | 84221.0 | Sidewalks | Grind trip hazards | GC | Year 1 | 10000 | 0 |  |  | 4 |  | Grind trip hazards
68 | 84114.0 | Repair exterior stair treads and stringers | Resurface stairs to office | GC | Year 1 | 10000 | 0 |  |  | 4 |  | Resurface stairs to office
70 | 84121.0 | Repair patio/balcony railings | Secure balcony railings | GC | Year 1 | 8500 | 0 |  |  | 4 |  | Secure balcony railings
81 | 84433.0 | Flashing | Roof Flashing | GC | Year 1 | 8500 | 2550 |  |  | 3 |  | Roof Flashing
82 | 84433.0 | Sealants & caulking | Roof Sealants & caulking | GC | Year 1 | 8500 | 2550 |  |  | 3 |  | Roof Sealants & caulking
167 | 84112 | Common area light fixtures | Replace 6 missing pole lights Allowance to repair/replace emergency light fixtures in common areas based on expired tags | GC | Year 1 | 8000 | 1800 |  |  | 4 |  | Replace 6 missing pole lights Allowance to repair/replace emergency light fixtures in common areas based on expired tags
166 | 84210 | Electrical distribution | Replace lightning controllers | GC | Year 1 | 6000 | 7200 |  |  | 0 |  | Replace lightning controllers
35 | 84205.0 | Fences & gates - swimming pool | Repair and paint | GC | Year 1 | 5600 | 0 |  |  | 4 |  | Repair and paint
PROJECTS subtotal (excl. contingency/CM fee)
173 | 84505.0 | Construction Management Fee | CM Fee | CMF | CM Fee | 46608 | 0 | 46608 |  | N/A |  | CM Fee
172 | 84510.0 | Contingency | Contingency Amount | CON | Contingency | 44389 | 0 | 44389 |  | N/A |  | Contingency Amount

## Waterford
Waterford — 2026 acq · GC pay app |  |  |  | Repair Reserve | Immediate Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
89 | 84330 | Electrical Panel Disconnects & Meter Banks | Electrical Panel Replacements | GC | Year 1 | 200000 | 0 |  |  | 4 |  | Electrical Panel Replacements
132 | 84095 | Swimming pool resurface | PNA: Outdoor pool covered assume needing resurface hot tub needs resurface Indoor pool has been painted All Four need double main drains | GC | Year 1 | 135000 | 40500 |  |  | 3 |  | PNA: Outdoor pool covered assume needing resurface hot tub needs resurface Indoor pool has been painted All Four need double main drains
38 | 84221 | Concrete deck / floor fill | PNA: Repair catwalks and install new outdoor carpet | GC | Year 1 | 81000 | 21870 |  |  | 4 |  | PNA: Repair catwalks and install new outdoor carpet
117 | 84208 | Clubhouse / Office redecorate (FFE) | Concept Walk - Update clubhouse furniture and fixtures | Capex | Year 1 | 75000 | 0 |  |  | N/A |  | Concept Walk - Update clubhouse furniture and fixtures
91 | 84112 | Common Area Lighting | PNA: replace both pole light on existing post, straiten posts and add a concrete curb, replace wall packs with LED | GC | Year 1 | 73000 | 21900 |  |  | 3 |  | PNA: replace both pole light on existing post, straiten posts and add a concrete curb, replace wall packs with LED
30 | 84303 | Landscape Cleanup and Enhancements | Concept Walk - Tree trim and general curb appeal enhancement; Streetside cleanup around sign | Capex | Year 1 | 50000 | 0 |  |  | N/A |  | Concept Walk - Tree trim and general curb appeal enhancement; Streetside cleanup around sign
143 | 84340 | Playground area and equipment | Concept Walk - Install new playground | GC | Year 1 | 40000 | 22800 |  |  | 3 |  | Concept Walk - Install new playground
19 | 84201 | Parking lot repairs | PNA: repair potholes. Concept Walk - Replace speed bumps as needed | GC | Year 1 | 38000 | 12000 |  |  | 3 |  | PNA: repair potholes. Concept Walk - Replace speed bumps as needed
66 | 84206 | Breezeway soffit repairs | PNA: R&R ceiling lights in breezeways with LED | GC | Year 1 | 33200 | 9960 |  |  | 3 |  | PNA: R&R ceiling lights in breezeways with LED
92 | 84112 | Breezeway Lighting | R&R ceiling lights in breezeway with LED | GC | Year 1 | 33200 | 9960 |  |  | 3 |  | R&R ceiling lights in breezeway with LED
108 | 84106 | Drier vents | PNA: Remove vent covers, clean vent piping, and install new dryer vent covers | GC | Year 1 | 33000 | 9900 |  |  | 3 |  | PNA: Remove vent covers, clean vent piping, and install new dryer vent covers
134 | 84095 | Swimming pool deck | PNA: Repair cracks | GC | Year 1 | 32000 | 9600 |  |  | 3 |  | PNA: Repair cracks
61 | 84206 | Repair / replace siding | PNA: Replace damaged Masonite and paint to match | GC | Year 1 | 30000 | 9000 |  |  | 3 |  | PNA: Replace damaged Masonite and paint to match
90 | 84112 | Breezeway Lighting | PNA - Wiring for pole lights | GC | Year 1 | 30000 | 9000 |  |  | 3 |  | PNA - Wiring for pole lights
20 | 84221 | Asphalt seal coating | PNA: Crack Fill Lender PCA: Damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling was present in various locations, specifically along the south and northwest drive aisles. Sectional full-depth replacement and crack routing/sealing is recommended. | GC | Year 1 | 29000 | 7830 |  |  | 4 |  | PNA: Crack Fill Lender PCA: Damaged pavement consistin | [5 empty] | 2153-08-15
50 | 84433 | Asphalt composite shingle roofing | PNA: roof tune up Lender PCA: Evidence of water damage indicative of roof leaks was observed at the clubhouse indoor pool area consisting of water damaged ceiling finishes. Additionally, a portion of the clubhouse roof was covered with a tarp at the time of inspection. Repair/replacement of the leasing office/clubhouse roof is recommended. | GC | Year 1 | 29000 | 17640 |  |  | 2 |  | PNA: roof tune up Lender PCA: Evidence of water damage indica | [5 empty] | 2153-08-15
142 | 84203 | Outdoor kitchen, fire pits, and seating area | PNA: Replace grill with Charcoal Grill to fit in island (8K). Concept Walk: placeholder for outdoor kitchen and shade structure (20K) | GC | Year 1 | 28000 | 8400 |  |  | 3 |  | PNA: Replace grill with Charcoal Grill to fit in island (8K). Concept Walk: placeholder for outdoor kitchen and shade structure (20K)
140 | 84113 | Pergola / shade covers | PNA: Repair, paint, and pressure was outdoor kitchen area | GC | Year 1 | 26000 | 7800 |  |  | 3 |  | PNA: Repair, paint, and pressure was outdoor kitchen area
141 | 84390 | Tennis / sports court | Concept Walk - Resurface basketball court / replace goals | GC | Year 1 | 25200 | 7560 |  |  | 3 |  | Concept Walk - Resurface basketball court / replace goals
144 | 84130 | Pet park / pet washing station | Concept Walk: placeholder for adding gravel/turf | GC | Year 1 | 25000 | 7500 |  |  | 3 |  | Concept Walk: placeholder for adding gravel/turf
148 | 84280 | Model Unit | Concept Walk - Update model | Capex | Year 1 | 25000 | 0 |  |  | N/A |  | Concept Walk - Update model
21 | 84221 | Curbing Repairs | PNA: Curbing Repairs Lender PCA: Damaged curbing and parking blocks were observed in various locations, specifically near the leasing office and central portion of the property. Repair is recommended. | GC | Year 1 | 24000 | 6480 |  |  | 4 |  | PNA: Curbing Repairs Lender PCA: Damaged curbing and parking b | [5 empty] | 2153-08-15
31 | 84219 | Carports / Garages | PNA: Repair carports | GC | Year 1 | 22000 | 6600 |  |  | 3 |  | PNA: Repair carports
55 | 84202 | Gutters & downspouts | PNA: Clean and repatch gutters throughout property | GC | Year 1 | 21000 | 6300 |  |  | 3 |  | PNA: Clean and repatch gutters throughout property
43 | 84114 | Repair exterior stair treads and stringers | PNA: inspect and secure railings on cat walks | GC | Year 1 | 20000 | 6000 |  |  | 3 |  | PNA: inspect and secure railings on cat walks
56 | 84433 | Sealants & caulking | PNA: At band boards | GC | Year 1 | 20000 | 12000 |  |  | 2 |  | PNA: At band boards
109 | 84239 | Fire Stops | Fire Stops | Capex | Year 1 | 19600 | 0 |  |  | N/A |  | Fire Stops
32 | 84111 | Dumpster enclosures | PNA - Repair dumpster enclosures. Lender PCA: The solid waste compactor enclosure fencing was damaged. Repair is recommended. | GC | Year 1 | 18000 | 5400 |  |  | 3 |  | PNA - Repair dumpster enclosures. Lender PCA: The solid waste compactor enclosure fencing was damaged. Repa | [5 empty] | 2153-08-15
26 | 84205 | Site perimeter fencing | Concept Walk - Stain streetside perimeter fencing. Pressure wash interior perimeter fencing to remove moss buildup. | GC | Year 1 | 16480 | 4944 |  |  | 3 |  | Concept Walk - Stain streetside perimeter fencing. Pressure wash interior perimeter fencing to remove moss buildup.
138 | 84360 | Pool furniture | Concept Walk - Add pool furniture | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Concept Walk - Add pool furniture
146 | 84190 | Fitness Center Remodel | Concept Walk: placeholder for fitness room/flooring paint in the lobby | GC | Year 1 | 15000 | 0 |  |  | 4 |  | Concept Walk: placeholder for fitness room/flooring paint in the lobby
23 | 84221 | Sidewalks and curbs | PNA: grind trip hazards Lender PCA: Cracking and heaving of concrete sidewalks was observed at several locations, specifically at areas adjacent to Building D. Repair is recommended. | GC | Year 1 | 14000 | 3780 |  |  | 4 |  | PNA: grind trip hazards Lender PCA: Cracking and heaving of concrete sidewalks wa | [5 empty] | 2152-11-13
137 | 84205 | Swimming pool fencing / gates | PNA - Repair pool fence and gate. | GC | Year 1 | 14000 | 4200 |  |  | 3 |  | PNA - Repair pool fence and gate.
149 | 83375 | Golf Carts | Concept Walk: need to purchase two new golf carts | Capex | Year 1 | 12500 | 0 |  |  | N/A |  | Concept Walk: need to purchase two new golf carts
68 | 84206 | Repair / replace wood trim | PNA: R&R rotted wood trim and paint to match | GC | Year 1 | 10000 | 3000 |  |  | 3 |  | PNA: R&R rotted wood trim and paint to match
52 | 84433 | Roof treatment / cleaning | PNA: Flashing | GC | Year 1 | 9800 | 3880 |  |  | 3 |  | PNA: Flashing
150 | 84102 | Shed (Storage Space) | Concept Walk: The current shop is only 8x8 and lacks adequate storage space. | PMC | Year 1 | 7500 | 0 |  |  | N/A |  | Concept Walk: The current shop is only 8x8 and lacks adequate storage space.
133 | 84095 | Swimming pool coping and tile | Lender PCA: The pool and spa were down at the time of the site visit. Management reported the pool/spa area was closed due to a roof leak and microbial growth observed at the ceiling over the pool. It is recommended that following roof repair, all affected materials are removed, underlying substrates cleaned and dried and all finishes repaired. | GC | Year 1 | 5000 | 0 |  |  | 4 |  | Lender PCA: The pool and spa were down at the time of the site visit. Management reported the pool/spa area was closed due to a roof leak and microbial growth observed at the ceiling over the pool. It | [5 empty] | 2153-08-15
73 | 84120 | Patio yard enclosures | Concept Walk - Installation of patior fencing where applicable | GC | Year 1 | 3600 | 0 |  |  | 4 |  | Concept Walk - Installation of patior fencing where applicable
123 | 84211 | Security/ fire alarm systems | Lender PCA: Valid inspection certificates were affixed to the fire sprinklers dated September 2025. While the systems were operational, several risers had warnings listing deficiencies, including access was not provided to the units at the time of the inspection. Repair of these items and re-certification is recommended. | PMC | Year 1 | 1500 | 0 |  |  | N/A |  | Lender PCA: Valid inspection certificates were affixed to the fire sprinklers dated September 2025. While the systems were operational, several risers had warnings listing deficiencies, including acce | [5 empty] | 2152-11-13
PROJECTS subtotal (excl. contingency/CM fee)
154 | 85305 | Construction Management Fee | CM Fee | CMF | CM Fee | 70328 | 0 | 70328 |  | N/A |  | CM Fee
153 | 84510 | Contingency | Contingency Amount | CON | Contingency | 66979 | 0 | 66979 |  | N/A |  | Contingency Amount

## Willow Lakes
Willow Lakes — 2026 acq · GC pay app
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
15 | 84303.0 | Landscape Enhancements | Tree trim, Increasing by 50K for curb appeal based on concept walk LPCA - Tree branches were observed in contact at Building 19. Dead hedges observed in parking islands on the northeast of property. | Capex | Year 1 | 95000 | 0 |  |  | N/A |  | Tree trim, Increasing by 50K for curb appeal based on concept walk LPCA - Tree branches were observed in contact at Building 19. Dead hedges observed in parking islands on the northeast of property. | [5 empty] | 2027-03-24
22 | 84221.0 | Concrete Curb/Sidewalk | Repair 2000 sq ft of concrete | GC | Year 1 | 70000 | 96000 |  |  | 0 |  | Repair 2000 sq ft of concrete
131 | 84360.0 | Pool Area Remodel | Refresh area with color and furniture. Split between the two pools | Capex | Year 1 | 60000 | 49907 |  |  | N/A |  | Refresh area with color and furniture. Split between the two pools
166 | 84112.0 | Exterior Lighting | Replace breezeway lights - wall sconce, ceiling and garage lights | GC | Year 1 | 59500 | 59500 |  |  | 0 |  | Replace breezeway lights - wall sconce, ceiling and garage lights
27 | 84205.0 | Fences & gates - site perimeter | repair iron and wood fence and paint | GC | Year 1 | 56000 | 66000 |  |  | 0 |  | repair iron and wood fence and paint
165 | 84112.0 | Exterior Lighting | Common area light fixtures - wall packs and pole light throughout | GC | Year 1 | 39000 | 39000 |  |  | 0 |  | Common area light fixtures - wall packs and pole light throughout
160 | 84218.0 | Replace AC condenser | align condensers and insulate suction lines | GC | Year 1 | 38000 | 38000 |  |  | 0 |  | align condensers and insulate suction lines
118 | 84239.0 | Fire Life Safety Work | Fire stops | Capex | Year 1 | 36456 | 0 |  |  | N/A |  | Fire stops
23 | 83520.0 | ADA Compliance Expense | ADA landings on apartment entrances are cracking up and failing | GC | Year 1 | 36000 | 36000 |  |  | 0 |  | ADA landings on apartment entrances are cracking up and failing
24 | 84115.0 | Sidewalks | repair trip hazards | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | repair trip hazards
26 | 84517.0 | Erosion control | Landscaping Erosion Control | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Landscaping Erosion Control
70 | 84104.0 | Balconies | Repair Balcony Decks | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Repair Balcony Decks
96 | 84113.0 | Exterior Paint, Carpentry, & Misc. Repairs | Repair / replace wood trim - replace rotted wood | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Repair / replace wood trim - replace rotted wood
136 | 84130.0 | Dog Run | Add lighting, dog amenities, and repairs to fencing | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | Add lighting, dog amenities, and repairs to fencing
53 | 84120.0 | Common Corridors Rehab | Grind and seal cracks in breezeways An isolated area of sectional cracking was noted on the main entrance drive and areas of linear cracking were noted at the circle drive in front of the leasing office/clubhouse. | GC | Year 1 | 26000 | 0 |  |  | 4 |  | Grind and seal cracks in breezeways An isolated area of sectional cracking was noted on the main entrance drive and areas of linear cracking were noted at the circle drive in front of the leasing offi | [5 empty] | 2027-03-24
75 | 84433.0 | Roof Replacements/Repairs | Roof tune up - Asphalt composite shingle roofing | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | Roof tune up - Asphalt composite shingle roofing
87 | 84206.0 | Building - Exterior | replace siding that was caulked and painted over | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | replace siding that was caulked and painted over
42 | 84111.0 | Dumpster enclosures | Build an enclosed area around roll off trash set up | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | Build an enclosed area around roll off trash set up
21 | 84204.0 | Asphalt Milling/Paving/Sealcoat | Stripe Parking Areas | GC | Year 1 | 22000 | 22000 |  |  | 0 |  | Stripe Parking Areas
80 | 84202.0 | Roof/Gutters | Clean gutters and downspouts | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | Clean gutters and downspouts
164 | 84210.0 | Electrical/Lighting | Electrical distribution - repair lighting controlers | GC | Year 1 | 21000 | 21000 |  |  | 0 |  | Electrical distribution - repair lighting controlers
90 | 84106.0 | Dryer Vents | Annual Dryer Vent Cleaning | GC | Year 1 | 20460 | 20460 |  |  | 0 |  | Annual Dryer Vent Cleaning
88 | 84102.0 | Building Repairs | Masonry Repairs - Repair areas of damaged stone | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | Masonry Repairs - Repair areas of damaged stone
122 | 84290.0 | Monument Sign | Enhance Signage (cordinate w/ church - add signage on their property) | Capex | Year 1 | 20000 | 0 |  |  | N/A |  | Enhance Signage (cordinate w/ church - add signage on their property)
19 | 84361.0 | Pool Area Repairs & Equipment | Repair pool gates | GC | Year 1 | 19000 | 9500 |  |  | 3 |  | Repair pool gates
119 | 83236.0 | Smoke Alarms | Completed by Seller - Move to Contingency? | Capex | Year 1 | 18600 | 0 |  |  | N/A |  | Completed by Seller - Move to Contingency?
32 | 84361.0 | Pool Area Repairs & Equipment | seal small cracks on pool deck and clean | GC | Year 1 | 16000 | 0 |  |  | 4 |  | seal small cracks on pool deck and clean
129 | 84190.0 | Fitness Center | Moderate upgrades to the fitness center | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Moderate upgrades to the fitness center
148 | 83375.0 | Golf Cart | Add leasing cart | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Add leasing cart
153 | 84432.0 | Stormwater Piping | Clean out basin | GC | Year 1 | 14000 | 14000 |  |  | 0 |  | Clean out basin
68 | 84114.0 | Exterior Stairs | Repair exterior stair treads and stringers - Replace 90 stair treads | GC | Year 1 | 12500 | 12500 |  |  | 0 |  | Repair exterior stair treads and stringers - Replace 90 stair treads
35 | 84205.0 | Fences & gates | Pedestrian and Front Gate Improvements | GC | Year 1 | 10000 | 19000 |  |  | 0 |  | Pedestrian and Front Gate Improvements
102 | 84305.0 | Equipment, baracades and staging | Equipment & Staging (Details of Scope?) | GC | Year 1 | 10000 | 10000 |  |  | 0 |  | Equipment & Staging (Details of Scope?)
127 | 84116.0 | Club House/Leasing Center Addition/Alteration | Leasing office floor/wall finishes - Light leasing office upgrade | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | Leasing office floor/wall finishes - Light leasing office upgrade
31 | 84361.0 | Pool Area Repairs & Equipment | deck o seal | GC | Year 1 | 9500 | 0 |  |  | 4 |  | deck o seal
36 | 84203.0 | Exterior Kitchen | replace grills | GC | Year 1 | 9500 | 9500 |  |  | 0 |  | replace grills
69 | 84121.0 | Handrail / Railings | Repair Exterior Railings | GC | Year 1 | 8500 | 8500 |  |  | 0 |  | Repair Exterior Railings
25 | 84361.0 | Pool Area Repairs & Equipment | LPCA - Excessive algae growth due to an inoperable aeration pump was observed at the south portion of the pond. | GC | Year 1 | 2500 | 16000 |  |  | 0 |  | LPCA - Excessive algae growth due to an inoperable aeration pump was observed at the south portion of the pond. | [5 empty] | 2027-03-24
20 | 84219.0 | Covered Parking & Misc. Parking Items | LPCA - Impact damage was observed at the garage door at the G-30 garage. Repairs are recommended. | PMC | Year 1 | 1500 | 0 |  |  | N/A |  | LPCA - Impact damage was observed at the garage door at the G-30 garage. Repairs are recommended. | [5 empty] | 2027-03-24
PROJECTS subtotal (excl. contingency/CM fee)
169 | 84505.0 | Other CM Fees | Construction Management Fee Amount | CMF | CM Fee | 54509 | 0 | 54509 |  | N/A |  | Construction Management Fee Amount
168 | 84510.0 | Contingency | Contingency Amount | CON | Contingency | 51163 | 0 | 51163 |  | N/A |  | Contingency Amount

## The Retreat
The Retreat — 2022 acq · GC @ budget
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | 3rd Party Requirement | Lender Due Date | Reserve Used
89 | 0900 - FF&E in Units | Appliances Package |  | Capex | Year 1 | 486000 | 0 |  |  | N/A
102 | 0900 - FF&E in Units | Ceramic tile | 324 Backsplash @ $700 | Capex | Year 1 | 226800 | 0 |  |  | N/A |  | 324 Backsplash @ $700
118 | 1100- Specialties, Equipment & Furnishings | Tech Package per unit | 162 units x $700 | Capex | Year 1 | 113400 | 0 |  |  | N/A |  | 162 units x $700
21 | 0200 - Site Utilities & Improvements | Patio fencing | 20 Extended Dog yards @ $5k- Value add | GC | Year 1 | 100000 | 100000 |  |  | 0 |  | 20 Extended Dog yards @ $5k- Value add
115 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Redecorate (FFE) | Clubhouse furniture- quote #PS6143285 from Charter Furniture | Capex | Year 1 | 92000 | 46776 |  |  | N/A |  | Clubhouse furniture- quote #PS6143285 from Charter Furniture
31 | 0200 - Site Utilities & Improvements | Pickleball court | Install pickleball court behind clubhouse | GC | Year 1 | 40000 | 40000 |  |  | 0 |  | Install pickleball court behind clubhouse
121 | 1100- Specialties, Equipment & Furnishings | Pool furniture | Update pool furniture to include cabanas | Capex | Year 1 | 40000 | 37994 |  |  | N/A |  | Update pool furniture to include cabanas
29 | 0200 - Site Utilities & Improvements | Fences & gates - swimming pool | Replace entire dog park fence | GC | Year 1 | 35000 | 35000 |  |  | 0 |  | Replace entire dog park fence
32 | 0200 - Site Utilities & Improvements | Playground equipment | New Playground | GC | Year 1 | 30000 | 30000 |  |  | 0 |  | New Playground
106 | 0900 - FF&E in Units | Range Queen |  | Capex | Year 1 | 29160 | 0 |  |  | N/A
19 | 0200 - Site Utilities & Improvements | Landscape irrigation | inspect and repair irrigation | GC | Year 1 | 26000 | 26000 |  |  | 0 |  | inspect and repair irrigation
23 | 0200 - Site Utilities & Improvements | Landscaping | New palms, bare land, dead bushes, etc.. | GC | Year 1 | 25000 | 25000 |  |  | 0 |  | New palms, bare land, dead bushes, etc..
111 | 1100- Specialties, Equipment & Furnishings | Signage - site |  | Capex | Year 1 | 25000 | 3739 |  |  | N/A
16 | 0200 - Site Utilities & Improvements | Parking equipment | add 15 speed bumps | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | add 15 speed bumps
18 | 0200 - Site Utilities & Improvements | Sidewalks | repair cracked concrete | GC | Year 1 | 20000 | 20000 |  |  | 0 |  | repair cracked concrete
59 | 0700 - Roofing | Asphalt composite shingle roofing | inspect and replace missing or damaged shingles | GC | Year 1 | 16500 | 16500 |  |  | 0 |  | inspect and replace missing or damaged shingles
114 | 1100- Specialties, Equipment & Furnishings | Video Systems | Movie Room refresh | Capex | Year 1 | 15000 | 0 |  |  | N/A |  | Movie Room refresh
123 | 1100- Specialties, Equipment & Furnishings | Golf Cart |  | Capex | Year 1 | 14000 | 24807 |  |  | N/A
107 | 0900 - FF&E in Units | Unit Model Update | New furniture in model unit | Capex | Year 1 | 13000 | 0 |  |  | N/A |  | New furniture in model unit
74 | 0800 - Exterior Wall | Dryer Vents | Clean all dryer vents | GC | Year 1 | 11340 | 11340 |  |  | 0 |  | Clean all dryer vents
119 | 1100- Specialties, Equipment & Furnishings | Audio systems | Audio systems - Game Room | Capex | Year 1 | 10000 | 0 |  |  | N/A |  | Audio systems - Game Room
113 | 1100- Specialties, Equipment & Furnishings | Clubhouse / Office Remodel | Wall and glass door between game/movie rooms | GC | Year 1 | 6500 | 6500 |  |  | 0 |  | Wall and glass door between game/movie rooms
36 | 0200 - Site Utilities & Improvements | Dumpster enclosures | Repair Dumpsters and paint | GC | Year 1 | 6000 | 6000 |  |  | 0 |  | Repair Dumpsters and paint
140 | 1600 - Electrical | Replace Fire Alarm Panel | Fire Alarm Panel Certifications | GC | Year 1 | 1500 | 1500 |  |  | 0
PROJECTS subtotal (excl. contingency/CM fee)

## Anthem Clearwater
Anthem Clearwater — 2026 acq · GC none ($0) |  |  |  | Repair Reserve | Lender Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | Mandate | Lender Due Date
70 | 84101 | Exterior paint | Exterior paint | GC | Year 1 | 624000 | 0 |  |  | 4 |  | Exterior paint
43 | 84114 | Repair exterior stair treads and stringers | Repair exterior stair treads and stringers | GC | Year 1 | 520183 | 0 |  |  | 4 |  | Repair exterior stair treads and stringers
53 | 84433 | Modified bitumen membrane repairs / replacement | Modified bitumen membrane repairs / replacement | GC | Year 1 | 324000 | 0 |  |  | 4 |  | Modified bitumen membrane repairs / replacement
19 | 84201 | Asphalt seal coating | Asphalt seal coating | GC | Year 1 | 272450 | 0 |  |  | 4 |  | Asphalt seal coating
150 | 84095 | Swimming pool resurface | Swimming pool resurface | GC | Year 1 | 130000 | 0 |  |  | 4 |  | Swimming pool resurface
71 | 84206 | Repair / replace wood trim | Repair / replace wood trim | GC | Year 1 | 126000 | 0 |  |  | 4 |  | Repair / replace wood trim
44 | 84114 | Repair exterior stair railings | Repair exterior stair railings | GC | Year 1 | 102520 | 0 |  |  | 4 |  | Repair exterior stair railings |  |  |  |  | Lender | 2027-07-23
29 | 84303 | Landscape Cleanup & Enhancements | Landscape Cleanup & Enhancements | GC | Year 1 | 82500 | 0 |  |  | 4 |  | Landscape Cleanup & Enhancements |  |  |  |  | Lender | 2027-07-23
156 | 84360 | Pool furniture | Pool furniture | PMC | Year 1 | 55000 | 0 |  |  | N/A |  | Pool furniture
57 | 84433 | Gutters & downspouts | Gutters & downspouts | GC | Year 1 | 50220 | 0 |  |  | 4 |  | Gutters & downspouts
103 | 84112 | Pole lighting | Pole lighting | GC | Year 1 | 50000 | 0 |  |  | 4 |  | Pole lighting
28 | 84303 | Landscape irrigation | Landscape irrigation | GC | Year 1 | 45000 | 0 |  |  | 4 |  | Landscape irrigation
18 | 84201 | Parking lot repairs | Parking lot repairs | GC | Year 1 | 42000 | 0 |  |  | 4 |  | Parking lot repairs
136 | 84211 | Fire suppression system | Fire suppression system | PMC | Year 1 | 40768 | 0 |  |  | N/A |  | Fire suppression system
94 | 84220 | HVAC pipe insulation | HVAC pipe insulation | GC | Year 1 | 35360 | 0 |  |  | 4 |  | HVAC pipe insulation
92 | 84220 | HVAC replacement - exterior | HVAC replacement - exterior | PMC | Year 1 | 35000 | 0 |  |  | N/A |  | HVAC replacement - exterior
133 | 84208 | Clubhouse / Office remodel | Clubhouse / Office remodel | GC | Year 1 | 35000 | 0 |  |  | 4 |  | Clubhouse / Office remodel
135 | 84280 | Model Unit | Model Unit | PMC | Year 1 | 35000 | 0 |  |  | N/A |  | Model Unit
152 | 84095 | Swimming pool deck | Swimming pool deck | GC | Year 1 | 34562 | 0 |  |  | 4 |  | Swimming pool deck
161 | 84340 | Playground area and equipment | Playground area and equipment | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Playground area and equipment
126 | 84211 | Unit Smoke/Fire Detectors | Unit Smoke/Fire Detectors | PMC | Year 1 | 29550 | 0 |  |  | N/A |  | Unit Smoke/Fire Detectors |  |  |  |  | Lender | 2027-01-19
102 | 84112 | Wall pack lighting | Wall pack lighting | GC | Year 1 | 28800 | 0 |  |  | 4 |  | Wall pack lighting
68 | 84206 | Stucco repairs | Stucco repairs | GC | Year 1 | 28500 | 0 |  |  | 4 |  | Stucco repairs
162 | 84130 | Pet park / pet washing station | Pet park / pet washing station | GC | Year 1 | 25000 | 0 |  |  | 4 |  | Pet park / pet washing station
20 | 84201 | Stripe parking areas | Stripe parking areas | GC | Year 1 | 24100 | 0 |  |  | 4 |  | Stripe parking areas
17 | 84432 | Storm sewer piping and drains | Storm sewer piping and drains | GC | Year 1 | 24000 | 0 |  |  | 4 |  | Storm sewer piping and drains
50 | 84433 | Asphalt composite shingle roofing | Asphalt composite shingle roofing | GC | Year 1 | 23200 | 0 |  |  | 4 |  | Asphalt composite shingle roofing |  |  |  |  | Lender | 2027-07-23
30 | 83307 | Tree Trimming | Tree Trimming | GC | Year 1 | 20000 | 0 |  |  | 4 |  | Tree Trimming
81 | 84385 | Irrigaton well | Irrigaton well | GC | Year 1 | 20000 | 0 |  |  | 4 |  | Irrigaton well |  |  |  |  | Lender | 2027-07-23
160 | 84203 | Outdoor kitchen, fire pits, and seating area | Outdoor kitchen, fire pits, and seating area | PMC | Year 1 | 20000 | 0 |  |  | N/A |  | Outdoor kitchen, fire pits, and seating area
164 | 84190 | Fitness Center Remodel | Fitness Center Remodel | PMC | Year 1 | 20000 | 0 |  |  | N/A |  | Fitness Center Remodel
69 | 84119 | Interior Hallway flooring / painting | Interior Hallway flooring / painting | GC | Year 1 | 18720 | 0 |  |  | 4 |  | Interior Hallway flooring / painting
60 | 84433 | Pipe jacks / exterior vents | Pipe jacks / exterior vents | GC | Year 1 | 17500 | 0 |  |  | 4 |  | Pipe jacks / exterior vents
77 | 84206 | Pressure wash | Pressure wash | GC | Year 1 | 15000 | 0 |  |  | 4 |  | Pressure wash
167 | 84195 | Misc. Common Area Amenities | Misc. Common Area Amenities | PMC | Year 1 | 15000 | 0 |  |  | N/A |  | Misc. Common Area Amenities
73 | 84215 | Replace unit entry doors - exterior | Replace unit entry doors - exterior | GC | Year 1 | 12000 | 0 |  |  | 4 |  | Replace unit entry doors - exterior
25 | 84205 | Site perimeter fencing | Site perimeter fencing | GC | Year 1 | 11560 | 0 |  |  | 4 |  | Site perimeter fencing |  |  |  |  | Lender | 2027-07-23
58 | 84433 | Flashing | Flashing | GC | Year 1 | 10692 | 0 |  |  | 4 |  | Flashing
59 | 84433 | Sealants & caulking | Sealants & caulking | GC | Year 1 | 3850 | 0 |  |  | 4 |  | Sealants & caulking
22 | 84221 | Sidewalks and curbs | Sidewalks and curbs | GC | Year 1 | 3500 | 0 |  |  | 4 |  | Sidewalks and curbs |  |  |  |  | Lender | 2026-10-21
125 | 84211 | Test Fire Hydrants | Test Fire Hydrants | PMC | Year 1 | 1000 | 0 |  |  | N/A |  | Test Fire Hydrants |  |  |  |  | Lender | 2027-01-19
127 | 84211 | Fire Emergency Lights | Fire Emergency Lights | PMC | Year 1 | 250 | 0 |  |  | N/A |  | Fire Emergency Lights |  |  |  |  | Lender | 2027-01-19
PROJECTS subtotal (excl. contingency/CM fee)
170 | 84510 | Contingency | Contingency | CON | Contingency | 386303 | 0 |  |  | N/A |  | Contingency
171 | 84505 | Construction Management Fee | Construction Management Fee | CMF | CM Fee | 171404 | 0 |  |  | N/A |  | Construction Management Fee

## Forest View
Forest View — 2026 acq · GC none ($0) |  |  |  | Repair Reserve | Lender Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | Mandate | Lender Due Date
70 | 84101 | Exterior paint | PNA: Exterior Paint (property painted in 2024 Scheduled for Year3. Scrape / Paint Railing Year one) | PMC | Year 3 | 140400 | 0 |  |  | N/A |  | PNA: Exterior Paint (property painted in 2024 Scheduled for Year3. Scrape / Paint Railing Year one)
154 | 84095 | Swimming pool resurface | PNA: Resurface two pools & Spa (min 30% quartz) Lender PCA: Plaster surfacing at the north and south pools were observed to be peeling. Property management stated the south pool was leaking in several areas. Resurfacing and repair of the noted issues is recommended. | GC | Year 1 | 130000 | 0 |  |  | 4 |  | PNA: Resurface two pools & Spa (min 30% quartz) Lender PCA: Plaster surfacing at the north and south pools were |  |  |  |  | Lender | 2027-07-16
46 | 84430 | Patio Fence Enclosure | Concept Walk: Placeholder (enclose patios with screen) | GC | Year 1 | 124800 | 0 |  |  | 4 |  | Concept Walk: Placeholder (enclose patios with screen)
30 | 83307 | Tree Trimming | PNA: Tree Trimming / Cut back foilage throughout including Palms and Volleyball Court | GC | Year 1 | 100000 | 0 |  |  | 4 |  | PNA: Tree Trimming / Cut back foilage throughout including Palms and Volleyball Court
160 | 84360 | Pool furniture | Concept Walk: 45K for Main Pool Upgrades (Furniture), 50K for Second Pool / Second Clubhouse Area Improvements | PMC | Year 1 | 95000 | 0 |  |  | N/A |  | Concept Walk: 45K for Main Pool Upgrades (Furniture), 50K for Second Pool / Second Clubhouse Area Improvements
134 | 84208 | Clubhouse / Office redecorate (FFE) | Concept Walk: $20K for furniture, $10K for updating the lighting, $10K for Movie Theatre improvements in the Clubhouse. 20K for Leasing Office Refresh, $8K for Office Computers | PMC | Year 1 | 68000 | 0 |  |  | N/A |  | Concept Walk: $20K for furniture, $10K for updating the lighting, $10K for Movie Theatre improvements in the Clubhouse. 20K for Leasing Office Refresh, $8K for Office Computers
92 | 82209 | Unit Water Heaters | PNA: Currently condensors are located within the minimum 3' from existing meter banks. Unknown if code enforcement will reqire relocation. Budget based on 2500 per building. | PMC | Year 1 | 62500 | 0 |  |  | N/A |  | PNA: Currently condensors are located within the minimum 3' from existing meter banks. Unknown if code enforcement will reqire relocation. Budget based on 2500 per building.
156 | 84095 | Swimming pool deck | PNA: Pressure Wash Main Pool Deck / Seal -Remove / Replace 2nd pool deck (appx.1500sf ) Lender PCA: Linear cracking was observed at the concrete deck of the north pool. Repair of the noted issue is recommended. | GC | Year 1 | 60000 | 0 |  |  | 4 |  | PNA: Pressure Wash Main Pool Deck / Seal -Remove / Replace 2nd pool deck (appx.1500sf ) Lender PCA: Linear cracking was |  |  |  |  | Lender | 2027-07-16
50 | 84433 | Asphalt composite shingle roofing | PNA: Roof Tune Up Lender PCA: Stained asphalt-shingle roofs were observed throughout the site typical of the conditions noted at Building 3. Cleaning is recommended. | GC | Year 1 | 52000 | 0 |  |  | 4 |  | PNA: Roof Tune Up Lender PCA: Stained asphalt-shingle roofs were observed throughout the site typica |  |  |  |  | Lender | 2027-07-16
149 | 84304 | Down units (Units 1524 and 1534) - Fire Damage | Lender PCA: Two of the units were down due to fire damage (Units 1524 and 1534). Ms. Santos reported a fire occurred at Building 15 approximately three years ago. The fire resulted in damage to multiple units within the building. The cause of the fire was reportedly a unit kitchen fire. All but two of the fire damaged units (Units 1524 and 1534) have been repaired. Units 1524 and 1534 have been stripped to the framing members and the framing has been coated. A section of the floor between the units was removed. | PMC | Year 1 | 50000 | 0 |  |  | N/A |  | Lender PCA: Two of the units were down due to fire damage (Units 1524 and 1534). Ms. Santos reported a fire occurred at Building 15 approximately three years ago. The fire resulted in damage to multip |  |  |  |  | Lender
164 | 84203 | Outdoor kitchen, fire pits, and seating area | PNA: Replace two grills / Install 2 Grills and Coutnertops at main pool / Add 50 LF 10 fencing w/ Logo at Rear of Volleyball / Add two Benches / Repair Pavers | GC | Year 1 | 50000 | 0 |  |  | 4 |  | PNA: Replace two grills / Install 2 Grills and Coutnertops at main pool / Add 50 LF 10 fencing w/ Logo at Rear of Volleyball / Add two Benches / Repair Pavers
18 | 84201 | Parking lot repairs | PNA: Patch Asphalt Paving & Crackfill (appx. 3500 SF) Lender PCA: Damaged pavement consisting of linear cracking and alligator cracking was present at the drive aisles consistent with the conditions noted near Building 25. Repair of the noted issue is recommended. | GC | Year 1 | 49000 | 0 |  |  | 4 |  | PNA: Patch Asphalt Paving & Crackfill (appx. 3500 SF) Lender PCA: Damaged pavement consisting of linear cracking and |  |  |  |  | Lender | 2027-07-16
77 | 84206 | Pressure wash | PNA: Pressure Wash Buildings | PMC | Year 3 | 46800 | 0 |  |  | N/A |  | PNA: Pressure Wash Buildings
85 | 84220 | HVAC replacement - exterior | PNA: Clean Condensate Lines at 2nd / 3rd Floors | GC | Year 1 | 41600 | 0 |  |  | 4 |  | PNA: Clean Condensate Lines at 2nd / 3rd Floors
57 | 84433 | Gutters & downspouts | PNA: Repair / Clean Gutters Lender PCA: Vegetative buildup/growth was observed at the gutter of Building 3. Cleaning is recommended. | GC | Year 1 | 39000 | 0 |  |  | 4 |  | PNA: Repair / Clean Gutters Lender PCA: Vegetative buildup/growth was observed at the gutter of Building 3. Cleaning is |  |  |  |  | Lender | 2027-07-16
64 | 84206 | Repair / replace siding | PNA: Remove / Replace Damaged Siding - Paint to match | GC | Year 1 | 39000 | 0 |  |  | 4 |  | PNA: Remove / Replace Damaged Siding - Paint to match
71 | 84206 | Repair / replace wood trim | PNA: Trim Repair / Paint to Match Lender PCA: Areas of deteriorated wood trim and warped siding were noted at Building 5. Repair of the noted issues is recommended. Lender PCA: Damaged trim was observed at some of the patio/balcony unit doors typical of the conditions noted at the balcony door of Unit 611. | GC | Year 1 | 39000 | 0 |  |  | 4 |  | PNA: Trim Repair / Paint to Match Lender PCA: Areas of deteriorated wood trim and warped siding were noted at Building 5. |  |  |  |  | Lender | 2027-07-16
125 | 83106 | Drier vents | PNA: Clean Drier Vents | GC | Year 1 | 39000 | 0 |  |  | 4 |  | PNA: Clean Drier Vents
126 | 84211 | Stovetop fire suppression | PNA: Install Range Queens | PMC | Year 1 | 35880 | 0 |  |  | N/A |  | PNA: Install Range Queens
29 | 84303 | Landscape Cleanup & Enhancements | PNA: Clean up landscape | PMC | Year 1 | 35000 | 0 |  |  | N/A |  | PNA: Clean up landscape
40 | 83301 | Termite Remediation | Concept Walk: WDIR Placeholder (Lexi requesting Quote - 5/18) | PMC | Year 1 | 25000 | 0 |  |  | N/A |  | Concept Walk: WDIR Placeholder (Lexi requesting Quote - 5/18)
132 | 84103 | Signage - building identification | Concept Walk: 25K for Building Signage | PMC | Year 1 | 25000 | 0 |  |  | N/A |  | Concept Walk: 25K for Building Signage
151 | 84304 | Down units (Units 611,) - Current Suspect Microbial Growth | Lender PCA: Three of the units were down due to current suspect microbial growth (Units 611, 813, and 1221). The units with current suspect microbial growth have not been substantially renovated. Partner recommends bringing these units back to rentable condition. | PMC | Year 1 | 25000 | 0 |  |  | N/A |  | Lender PCA: Three of the units were down due to current suspect microbial growth (Units 611, 813, and 1221). The units with current suspect microbial growth have not been substantially renovated. Part |  |  |  |  | Lender
152 | 84304 | Down Unit 621 - Current Suspect Microbial Growth | Lender PCA: Unit 621 is down due to current suspect microbial growth. According to property management, the unit was down due to a previous water leak that occurred at the HVAC closet. The living room subfloor in Unit 621 was observed to be flexible. | PMC | Year 1 | 25000 | 0 |  |  | N/A |  | Lender PCA: Unit 621 is down due to current suspect microbial growth. According to property management, the unit was down due to a previous water leak that occurred at the HVAC closet. The living room |  |  |  |  | Lender
171 | 84195 | Misc. Common Area Amenities | Concept Walk: 20K for the 4x4 unit that is off the rent roll in the clubhouse area, 5K for Exterior Amenity Improvements (Hammocks) | PMC | Year 1 | 25000 | 0 |  |  | N/A |  | Concept Walk: 20K for the 4x4 unit that is off the rent roll in the clubhouse area, 5K for Exterior Amenity Improvements (Hammocks)
102 | 84112 | Wall pack lighting | PNA: Additional Wall Pack Lighting | GC | Year 1 | 17500 | 0 |  |  | 4 |  | PNA: Additional Wall Pack Lighting
166 | 84130 | Pet park / pet washing station | PNA: Clean Up Dog Park / Add Benches - (Foilage captured in tree trim budget) | GC | Year 1 | 15000 | 0 |  |  | 4 |  | PNA: Clean Up Dog Park / Add Benches - (Foilage captured in tree trim budget)
168 | 84190 | Fitness Center Remodel | Concept Walk: $5K for Cardio Gym Improvement. $7.5K for Main Gym Upgrades | PMC | Year 1 | 12500 | 0 |  |  | N/A |  | Concept Walk: $5K for Cardio Gym Improvement. $7.5K for Main Gym Upgrades
24 | 84275 | Controlled access gates | PNA: Allowance for Access Gate Repair | PMC | Year 1 | 10000 | 0 |  |  | N/A |  | PNA: Allowance for Access Gate Repair
103 | 84112 | Pole lighting | PNA: Add Pole Light at Volley Ball Court / Repair Signage Lighting | GC | Year 1 | 10000 | 0 |  |  | 4 |  | PNA: Add Pole Light at Volley Ball Court / Repair Signage Lighting
135 | 84280 | Model Unit | Concept Walk: 10K for Model Refresh | PMC | Year 1 | 10000 | 0 |  |  | N/A |  | Concept Walk: 10K for Model Refresh
137 | 84211 | Fire monitoring system | Lender PCA: Per the February 16, 2026 Fire Inspection Report, there are numerous open fire code violations for fire alarm inspections, smoke detectors inoperable/missing, fueled equipment not allowed to be store in a building, emergency lights not operational or not present, improper venting of clothes dryer, accumulation of combustible materials, electrical wiring, electrical outlets, no hibachis, grills or other similar devices, used for cooking or heating, are allowed on the balcony, stairs/railings, and exit access not maintained. | PMC | Year 1 | 10000 | 0 |  |  | N/A |  | Lender PCA: Per the February 16, 2026 Fire Inspection Report, there are numerous open fire code violations for fire alarm inspections, smoke detectors inoperable/missing, fueled equipment not allowed |  |  |  |  | Lender | 2026-09-14
141 | 84275 | Security alarm systems | Concept Walk: $10K placeholder budget to finish Ambient lock integration project (Currently 75% linked with Ambient for locks at property, would complete the remaining 25%) | PMC | Year 1 | 10000 | 0 |  |  | N/A |  | Concept Walk: $10K placeholder budget to finish Ambient lock integration project (Currently 75% linked with Ambient for locks at property, would complete the remaining 25%)
133 | 84208 | Clubhouse / Office remodel | PNA: Clean / Paint Front & Rear Decking | GC | Year 1 | 7500 | 0 |  |  | 4 |  | PNA: Clean / Paint Front & Rear Decking
163 | 84390 | Tennis / sports court | PNA: Clean Repaint Two Basketball Courts | GC | Year 1 | 7000 | 0 |  |  | 4 |  | PNA: Clean Repaint Two Basketball Courts
58 | 84433 | Flashing | PNA: Flashing | GC | Year 1 | 6500 | 0 |  |  | 4 |  | PNA: Flashing
60 | 84433 | Pipe jacks / exterior vents | PNA: Replace / Boot jacks & Vents as required | GC | Year 1 | 6500 | 0 |  |  | 4 |  | PNA: Replace / Boot jacks & Vents as required
155 | 84095 | Swimming pool coping and tile | PNA: Replace missing Tile on Pool 2 | GC | Year 1 | 5500 | 0 |  |  | 4 |  | PNA: Replace missing Tile on Pool 2
59 | 84433 | Sealants & caulking | PNA: Sealants / Caulking | GC | Year 1 | 5200 | 0 |  |  | 4 |  | PNA: Sealants / Caulking
112 | 84207 | Flooring | Lender PCA: The living room subfloor in Down Unit 621 was observed to be flexible. According to property management, the unit was down due to a previous water leak that occurred at the HVAC closet. Partner recommends evaluation and repair of this unit subflooring by a qualified licensed contractor. | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Lender PCA: The living room subfloor in Down Unit 621 was observed to be flexible. According to property management, the unit was down due to a previous water leak that occurred at the HVAC closet. Pa |  |  |  |  | Lender | 2027-07-16
159 | 84095 | Swimming pool fencing / gates | PNA: Repair Pool / Gate Fencing | GC | Year 1 | 4500 | 0 |  |  | 4 |  | PNA: Repair Pool / Gate Fencing
43 | 84114 | Repair exterior stair treads and stringers | PNA: Remove / Replace Concerete Step Treads Lender PCA: A broken concrete step was observed at the exterior stairway of Building 5. Repair or replacement is recommended. | GC | Year 1 | 3600 | 0 |  |  | 4 |  | PNA: Remove / Replace Concerete Step Treads Lender PCA: A broken concrete step was observed at the exterior stairway of Building 5. Repair or replacement is recommended. |  |  |  |  | Lender | 2026-09-14
22 | 84221 | Sidewalks and curbs | PNA: Repair Damaged / Broken Curbing Lender PCA: Linear cracking was present at the walkway near Building 22. Repair of the noted issue is recommended. | GC | Year 1 | 2500 | 0 |  |  | 4 |  | PNA: Repair Damaged / Broken Curbing Lender PCA: Linear cracking was present at the walkway near Building 22. Repair of the noted issue is recomme |  |  |  |  | Lender | 2026-09-14
157 | 84095 | Swimming pool pumps repair / replace | Lender PCA: The south pool was reported and observed to be in a down condition. The pool water was observed to be murky and green in color. Property management stated the pool pump was not operational. Repair of the noted issue is recommended. | PMC | Year 1 | 2500 | 0 |  |  | N/A |  | Lender PCA: The south pool was reported and observed to be in a down condition. The pool water was observed to be murky and green in color. Property management stated the pool pump was not operational |  |  |  |  | Lender | 2027-07-16
136 | 84211 | Fire suppression system | Lender PCA: Expired certification tags present at the fire extinguishers in north clubhouse. Re-certification of the fire extinguishers is recommended. Lender PCA: A fire alarm horn/strobe wire was loose and fallen at the breezeway near Unit 1524. Repair of the noted issue is recommended | PMC | Year 1 | 2000 | 0 |  |  | N/A |  | Lender PCA: Expired certification tags present at the fire extinguishers in north clubhouse. Re-certification of the fire extinguishers is recommended. Lender PCA: A fire alarm horn/strobe |  |  |  |  | Lender | 2026-09-14
81 | 84470 | Water distribution piping | Lender PCA: A leaking water meter was observed at Building 7. Repair of the noted issue is recommended. | PMC | Year 1 | 1500 | 0 |  |  | N/A |  | Lender PCA: A leaking water meter was observed at Building 7. Repair of the noted issue is recommended. |  |  |  |  | Lender | 2027-01-12
165 | 84340 | Playground area and equipment | PNA: Pressure Wash Basketball Court | GC | Year 1 | 500 | 0 |  |  | 4 |  | PNA: Pressure Wash Basketball Court
21 | 84201 | ADA parking & ramps | Lender PCA: ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at the head of each space. ADA-compliant signage was provided at ADA parking spaces; however, the van-accessible spaces were not observed to have van-accessible signage. | PMC | Year 1 | 300 | 0 |  |  | N/A |  | Lender PCA: ADA-compliant parking spaces are required to have a sign with the International Symbol of Accessibility at the head of each space. ADA-compliant signage was provided at ADA parking spaces; |  |  |  |  | Lender | 2027-01-12
PROJECTS subtotal (excl. contingency/CM fee)
175 | 85305 | Construction Management Fee | CM Fee | CMF | CM Fee | 82823 | 0 |  |  | N/A |  | CM Fee
174 | 84510 | Contingency | Contingency Amount | CON | Contingency | 78879 | 0 |  |  | N/A |  | Contingency Amount

## Almaden Terrace
Almaden Terrace — 2026 acq · GC none ($0) |  |  |  | Repair Reserve | Lender Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | Mandate | Lender Due Date
48 | 51070-00 | Seismic Retrofitting | Retrofit tuck under parking | GC | Year 1 | 1235000 | 0 |  |  | 4 |  | Retrofit tuck under parking |  |  |  |  | Lender | 2027-06-18
64 | 51075-00 | Repair / replace siding | Replace siding with Hardie Areas of siding displaying deterioration were noted including but not limited to the southern sides of buildings H, N, and O and the eastern side of building M. Repairs are recommended. | GC | Year 1 | 865000 | 0 |  |  | 4 |  | Replace siding with Hardie Areas of siding displaying deterioration were noted including but not limited to the southern sides of buildings H, N, and O and the eastern side of building M. Repairs are |  |  |  |  | Lender
70 | 51080-00 | Exterior paint | The paint finish on the apartment buildings was chipping and worn. Survey and as needed reapplication of exterior paint is recommended. | GC | Year 1 | 366000 | 0 |  |  | 4 |  | The paint finish on the apartment buildings was chipping and worn. Survey and as needed reapplication of exterior paint is recommended. |  |  |  |  | Lender
57 | 51071-00 | Gutters & downspouts | Replace gutters and downspouts on 30 buildings (830LF per building Avg.) | GC | Year 1 | 298800 | 0 |  |  | 4 |  | Replace gutters and downspouts on 30 buildings (830LF per building Avg.)
98 | 51140-00 | Electrical distribution - exterior | During site reconnaissance, the maintenance manager reported that combinations of copper and aluminum electrical wiring were present on the subject property. Based on limitedobservations, aluminum branch wiring was not observed. The presence or absence of aluminum branch wiring should be verified by a licensed electrician, and any modifications to aluminum wiring encountered be completed with Consumer Project Safety Commission (CPSC)- approved permanent repair methods (Copalum solution and the ALUMICON solution). | GC | Year 1 | 262000 | 0 |  |  | 4 |  | During site reconnaissance, the maintenance manager reported that combinations of copper and aluminum electrical wiring were present on the subject property. Based on limitedobservations, aluminum bra |  |  |  |  | Lender | 2027-06-18
71 | 51070-00 | Repair / replace wood trim | Replace wood trim | GC | Year 1 | 151960 | 0 |  |  | 4 |  | Replace wood trim
127 | 51150-00 | Hardware package | Add ceiling fans/lights to bathrooms to prevent mold issues | GC | Year 1 | 137400 | 0 |  |  | 4 |  | Add ceiling fans/lights to bathrooms to prevent mold issues
42 | 51072-00 | Repair balcony framing & decking | According to a review of municipal information, it appears that the SB721 Inspection was completed in 2024. A copy of the report and findings as well as information regarding subsequent repairs was requested but not provided. Obtaining a copy of the inspection report is recommended. | GC | Year 1 | 116058 | 0 |  |  | 4 |  | According to a review of municipal information, it appears that the SB721 Inspection was completed in 2024. A copy of the report and findings as well as information regarding subsequent repairs was re |  |  |  |  | Lender | 2027-06-18
40 | 51992-00 | Termite Remediation | Placeholder for full quote from Terminex | GC | Year 1 | 90000 | 0 |  |  | 4 |  | Placeholder for full quote from Terminex
161 | 51029-00 | Playground area and equipment | Playground and BBQ upgrades | GC | Year 1 | 55000 | 0 |  |  | 4 |  | Playground and BBQ upgrades
150 | 51023-00 | Swimming pool resurface | Resurface pool & hottub | GC | Year 1 | 50000 | 0 |  |  | 4 |  | Resurface pool & hottub
102 | 51141-00 | Wall pack lighting | Replace random flood lighting with high lumin LED | GC | Year 1 | 49800 | 0 |  |  | 4 |  | Replace random flood lighting with high lumin LED
52 | 51062-00 | Tile roofing | Tile roof repairs | GC | Year 1 | 45000 | 0 |  |  | 4 |  | Tile roof repairs
66 | 51159-00 | Wall framing | Rplace structural damage | GC | Year 1 | 33000 | 0 |  |  | 4 |  | Rplace structural damage
82 | 51130-00 | Sanitary sewer piping | Jet the sewer lines | GC | Year 1 | 27200 | 0 |  |  | 4 |  | Jet the sewer lines
104 | 51141-00 | Breezeway and patio lights | Replace CFL front door lights with LED | GC | Year 1 | 26200 | 0 |  |  | 4 |  | Replace CFL front door lights with LED
22 | 51091-00 | Sidewalks and curbs | Repair trip hazards Potential trip hazards consisting of vertical and horizontal separation were present throughout the site typical of conditions noted northwest of building T, between buildings U and P, between buildings U and O, west of building M, and northwest of building A. Repairs are recommended. A cracked concrete drainage swale was observed north of building R and cracked stamped concrete was observed at the Canoas Avenue apron. Repairs are recommended. | GC | Year 1 | 21000 | 0 |  |  | 4 |  | Repair trip hazards Potential trip hazards consisting of vertical and horizontal separation were present throughout the site typical of conditions noted northwest of building T, between buildings U an |  |  |  |  | Lender | 2026-09-16
103 | 51141-00 | Pole lighting | Replace pole lights with LED | GC | Year 1 | 19600 | 0 |  |  | 4 |  | Replace pole lights with LED
45 | 51077-00 | Repair patio/balcony railings/fences | Repairs to patio and balcony fencing | GC | Year 1 | 19000 | 0 |  |  | 4 |  | Repairs to patio and balcony fencing | [5 empty] | 2027-06-18
31 | 51172-00 | Carports / Garages | Repair & paint carports Impact damaged roof panels were noted north of building R. Repairs are recommended | GC | Year 1 | 18500 | 0 |  |  | 4 |  | Repair & paint carports Impact damaged roof panels were noted north of building R. Repairs are recommended |  |  |  |  | Lender | 2027-06-18
47 | 51090-00 | Expansion Joints | Seal Landing expansion joins | GC | Year 1 | 15000 | 0 |  |  | 4 |  | Seal Landing expansion joins
60 | 51062-00 | Pipe jacks / exterior vents | Replace and seal damaged | GC | Year 1 | 15000 | 0 |  |  | 4 |  | Replace and seal damaged
39 | 51090-00 | Concrete deck / floor fill | Route and seal landings | GC | Year 1 | 14500 | 0 |  |  | 4 |  | Route and seal landings | [5 empty] | 2027-06-18
32 | 51163-00 | Dumpster enclosures | Tuck Point and Paint | GC | Year 1 | 12000 | 0 |  |  | 4 |  | Tuck Point and Paint
58 | 51062-00 | Flashing | Replace missing or damaged flashing | GC | Year 1 | 12000 | 0 |  |  | 4 |  | Replace missing or damaged flashing
59 | 51062-00 | Sealants & caulking |  | GC | Year 1 | 9000 | 0 |  |  | 4
151 | 51021-00 | Swimming pool coping and tile | Replace deck-o-seal | GC | Year 1 | 8500 | 0 |  |  | 4 |  | Replace deck-o-seal
155 | 51076-00 | Swimming pool fencing / gates | Repair pool gates | GC | Year 1 | 7600 | 0 |  |  | 4 |  | Repair pool gates
18 | 51050-00 | Parking lot repairs | Damaged asphalt pavement consisting of pocketed map cracking was observed west of buildings U and V and north of building R. Repairs are recommended. | GC | Year 1 | 7500 | 0 |  |  | 4 |  | Damaged asphalt pavement consisting of pocketed map cracking was observed west of buildings U and V and north of building R. Repairs are recommended. |  |  |  |  | Lender
21 | 51091-00 | ADA parking & ramps | Repair ADA Ramps (2) | GC | Year 1 | 7500 | 0 |  |  | 4 |  | Repair ADA Ramps (2)
83 | 51130-00 | Domestic water piping | During site reconnaissance, management disclosed a variety of plumbing problems relating to sewer and supply piping. While no evidence of deterioration was observed, several tenants reported low pressure. Inspection of the water service and sanitary systems and repairs, as needed, by a qualified professional isrecommended. This estimated cost also includes an allowance for necessary repairs; however, the actual repair cost may vary depending on recommendations made. | GC | Year 1 | 7500 | 0 |  |  | 4 |  | During site reconnaissance, management disclosed a variety of plumbing problems relating to sewer and supply piping. While no evidence of deterioration was observed, several tenants reported low press |  |  |  |  | Lender | 2026-12-15
101 | 51140-00 | Lighing controller system | Inspect & Replace | GC | Year 1 | 6800 | 0 |  |  | 4 |  | Inspect & Replace
17 | 51130-00 | Storm sewer piping and drains | Clear yard drains | GC | Year 1 | 6500 | 0 |  |  | 4 |  | Clear yard drains
29 | 51045-00 | Landscape Cleanup & Enhancements | Volunteer tree landscaping was noted in close proximity to buildings within patio enclosures. Locations included but were not limited to west of building Q, south of building R, and west of building E. Removal of the vegetation is recommended. | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Volunteer tree landscaping was noted in close proximity to buildings within patio enclosures. Locations included but were not limited to west of building Q, south of building R, and west of building E |  |  |  |  | Lender | 2027-06-18
46 | 51076-00 | Patio Fence Enclosure | Settlement and impact damage was noted at various patio enclosures throughout the site. Repairs are recommended. | GC | Year 1 | 5000 | 0 |  |  | 4 |  | Settlement and impact damage was noted at various patio enclosures throughout the site. Repairs are recommended. |  |  |  |  | Lender
75 | 51073-00 | Storage room doors | Replace 10 storage doors | GC | Year 1 | 5000 | 0 |  |  | 4 |  | Replace 10 storage doors
143 | 51995-00 | Tools | Various Tools for Maintenance Workshop | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Various Tools for Maintenance Workshop
153 | 51026-00 | Swimming pool pumps repair / replace | Add vacume release device | GC | Year 1 | 4800 | 0 |  |  | 4 |  | Add vacume release device
43 | 51070-00 | Repair exterior stair treads and stringers | Replace 10 damaged stair treads and repair landings | GC | Year 1 | 3800 | 0 |  |  | 4 |  | Replace 10 damaged stair treads and repair landings
110 | 51160-00 | Common Area Accessibility | ADA-compliant parking spaces are required to have an adjacent access aisle. Access aisles were not observed at the accessible parking spaces and inclusion is recommended. ADA-compliant door hardware was not observed at the community building entrance and inclusion is recommended. | PMC | Year 1 | 500 | 0 |  |  | N/A |  | ADA-compliant parking spaces are required to have an adjacent access aisle. Access aisles were not observed at the accessible parking spaces and inclusion is recommended. ADA-compliant door hardware w |  |  |  |  | Lender
PROJECTS subtotal (excl. contingency/CM fee)
170 | 51990-00 | Contingency |  | CON | Contingency | 427584 | 0 |  |  | N/A
171 | 51190-00 | Construction Management Fee |  | CMF | CM Fee | 158628 | 0 |  |  | N/A

## Sunterra
Sunterra — 2026 acq · GC none ($0) |  |  |  | Repair Reserve | Lender Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | Mandate | Lender Due Date
52 | 84433 | Modified bitumen membrane repairs / replacement | Modified bitumen membrane repairs / replacement | GC | Year 1 | 650000 | 0 |  |  | 4 |  | Modified bitumen membrane repairs / replacement |  |  |  |  | Lender | 2027-06-12
26 | 84434 | Retaining walls | Retaining walls | GC | Year 1 | 615000 | 0 |  |  | 4 |  | Retaining walls |  |  |  |  | Lender | 2027-06-12
19 | 84204 | Asphalt seal coating | Asphalt seal coating | GC | Year 1 | 426300 | 0 |  |  | 4 |  | Asphalt seal coating |  |  |  |  | Lender | 2027-06-12
69 | 84101 | Exterior paint | Exterior paint | GC | Year 1 | 360000 | 0 |  |  | 4 |  | Exterior paint |  |  |  |  | Lender | 2026-12-09
21 | 84201 | ADA parking & ramps | ADA parking & ramps | GC | Year 1 | 160000 | 0 |  |  | 4 |  | ADA parking & ramps
67 | 84206 | Stucco repairs | Stucco repairs | GC | Year 1 | 135500 | 0 |  |  | 4 |  | Stucco repairs
114 | 84304 | Plumbing, kitchen and baths | Plumbing, kitchen and baths | PMC | Year 1 | 124800 | 0 |  |  | N/A |  | Plumbing, kitchen and baths
27 | 84435 | Erosion control and drainage | Erosion control and drainage | GC | Year 1 | 118500 | 0 |  |  | 4 |  | Erosion control and drainage
40 | 83170 | Termite Remediation | Termite Remediation | Unmarked | Year 1 | 114500 | 0 |  |  | N/A |  | Termite Remediation
161 | 84130 | Pet park / pet washing station | Pet park / pet washing station | GC | Year 1 | 110000 | 0 |  |  | 4 |  | Pet park / pet washing station
42 | 84114 | Repair exterior stair treads and stringers | Repair exterior stair treads and stringers | GC | Year 1 | 102000 | 0 |  |  | 4 |  | Repair exterior stair treads and stringers |  |  |  |  | Lender | 2026-12-09
22 | 84221 | Sidewalks and curbs | Sidewalks and curbs | GC | Year 1 | 85500 | 0 |  |  | 4 |  | Sidewalks and curbs |  |  |  |  | Lender | 2026-08-11
30 | 84300 | Tree Trimming | Tree Trimming | PMC | Year 1 | 75000 | 0 |  |  | N/A |  | Tree Trimming
101 | 84112 | Wall pack lighting | Wall pack lighting | GC | Year 1 | 72500 | 0 |  |  | 4 |  | Wall pack lighting
20 | 84201 | Stripe Parking | Stripe Parking | GC | Year 1 | 51450 | 0 |  |  | 4 |  | Stripe Parking
29 | 84303 | Landscape Cleanup & Enhancements | Landscape Cleanup & Enhancements | GC | Year 1 | 50000 | 0 |  |  | 4 |  | Landscape Cleanup & Enhancements
43 | 84121 | Repair exterior stair railings | Repair exterior stair railings | GC | Year 1 | 48500 | 0 |  |  | 4 |  | Repair exterior stair railings
149 | 84095 | Swimming pool resurface | Swimming pool resurface | GC | Year 1 | 46000 | 0 |  |  | 4 |  | Swimming pool resurface
17 | 84385 | Sewer Systems | Sewer Systems | GC | Year 1 | 45000 | 0 |  |  | 4 |  | Sewer Systems
154 | 84095 | Swimming pool fencing / gates | Swimming pool fencing / gates | GC | Year 1 | 42800 | 0 |  |  | 4 |  | Swimming pool fencing / gates
58 | 84202 | Sealants & caulking | Sealants & caulking | GC | Year 1 | 37500 | 0 |  |  | 4 |  | Sealants & caulking
25 | 84205 | Site perimeter fencing | Site perimeter fencing | GC | Year 1 | 35000 | 0 |  |  | 4 |  | Site perimeter fencing |  |  |  |  | Lender | 2027-06-12
28 | 84302 | Landscape irrigation | Landscape irrigation | PMC | Year 1 | 35000 | 0 |  |  | N/A |  | Landscape irrigation
46 | 84102 | Expansion Joints | Expansion Joints | GC | Year 1 | 32500 | 0 |  |  | 4 |  | Expansion Joints
157 | 84203 | Grills | Grills | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Grills
160 | 84340 | Playground area and equipment | Playground area and equipment | GC | Year 1 | 30000 | 0 |  |  | 4 |  | Playground area and equipment
39 | 84104 | Concrete deck / floor fill | Concrete deck / floor fill | GC | Year 1 | 25000 | 0 |  |  | 4 |  | Concrete deck / floor fill
56 | 84202 | Gutters & downspouts | Gutters & downspouts | GC | Year 1 | 18500 | 0 |  |  | 4 |  | Gutters & downspouts
24 | 84275 | Controlled access gates | Controlled access gates | GC | Year 1 | 15000 | 0 |  |  | 4 |  | Controlled access gates
155 | 84360 | Pool furniture | Pool furniture | PMC | Year 1 | 15000 | 0 |  |  | N/A |  | Pool furniture
32 | 84111 | Dumpster enclosures | Dumpster enclosures | GC | Year 1 | 13500 | 0 |  |  | 4 |  | Dumpster enclosures |  |  |  |  | Lender | 2027-06-12
151 | 84095 | Swimming pool deck | Swimming pool deck | GC | Year 1 | 13500 | 0 |  |  | 4 |  | Swimming pool deck
97 | 84210 | Electrical distribution - exterior | Electrical distribution - exterior | GC | Year 1 | 13000 | 0 |  |  | 4 |  | Electrical distribution - exterior
72 | 84215 | Replace unit entry doors - exterior | Replace unit entry doors - exterior | PMC | Year 1 | 5000 | 0 |  |  | N/A |  | Replace unit entry doors - exterior |  |  |  |  | Lender | 2027-06-12
PROJECTS subtotal (excl. contingency/CM fee)
170 | 85305 | Construction Management | Construction Management | CMF | CM Fee | 188630 | 0 |  |  | N/A |  | Construction Management

## Santa Lucia
Santa Lucia — 2026 acq · GC none ($0) |  |  |  | Repair Reserve | Lender Reserve | Upper Tier
← Back
Row | GL | GL Name | Scope of Work | Responsible | Capital Plan | Budget | Spend | Remaining | % Spent | Draws Remaining | Project % | Budget Notes | Vendor | Status | Status Comments | Capital Year | Mandate | Lender Due Date
70 | 51080-00 | Exterior paint | PNA - Paint Exteriors | GC | Year 3 | 357000 | 0 |  |  | 4 |  | PNA - Paint Exteriors
19 | 51053-00 | Asphalt seal coating | PNA - Seal / Crack Fill | GC | Year 1 | 266800 | 0 |  |  | 4 |  | PNA - Seal / Crack Fill
33 | 51050-00 | Install Wheel Stops at All Parking | PNA - Install Wheel Stops (6' Concrete) | GC | Year 1 | 62800 | 0 |  |  | 4 |  | PNA - Install Wheel Stops (6' Concrete)
77 | 51990-00 | Pressure wash | PNA - Pressure Wash Exteriors | GC | Year 3 | 61200 | 0 |  |  | 4 |  | PNA - Pressure Wash Exteriors
40 | 51992-00 | Termite Remediation | PNA - Termite Remediation | PMC | Year 1 | 58800 | 0 |  |  | N/A |  | PNA - Termite Remediation
30 | 51045-00 | Tree Trimming | PNA - Tree Trimming | PMC | Year 1 | 43200 | 0 |  |  | N/A |  | PNA - Tree Trimming
102 | 51141-00 | Wall pack lighting | PNA - Replace Wall Pack / Carport Lighting w/ LED | GC | Year 1 | 39900 | 0 |  |  | 4 |  | PNA - Replace Wall Pack / Carport Lighting w/ LED
29 | 51045-00 | Landscape Cleanup & Enhancements | PNA - Landscape Enhancements & Repair | PMC | Year 1 | 20000 | 0 |  |  | N/A |  | PNA - Landscape Enhancements & Repair
27 | 51086-00 | Erosion control and drainage | PNA - Erosion Control and Drainage Repair | PMC | Year 1 | 15000 | 0 |  |  | N/A |  | PNA - Erosion Control and Drainage Repair
18 | 51050-00 | Parking lot repairs | PNA - Asphalt Patch (Up to 500 SF) | GC | Year 1 | 14000 | 0 |  |  | 4 |  | PNA - Asphalt Patch (Up to 500 SF)
71 | 51070-00 | Repair / replace wood trim | PNA - Remove / Replace Wood Trim (paint to match) | GC | Year 3 | 11200 | 0 |  |  | 4 |  | PNA - Remove / Replace Wood Trim (paint to match)
31 | 51172-00 | Carports / Garages | PNA - Repair Carports | GC | Year 1 | 10500 | 0 |  |  | 4 |  | PNA - Repair Carports
32 | 51163-00 | Dumpster enclosures | PNA - Repair Dumpster Enclosures | GC | Year 1 | 7500 | 0 |  |  | 4 |  | PNA - Repair Dumpster Enclosures
20 | 51053-00 | Stripe parking areas | PNA - Re-Stripe Parking | GC | Year 1 | 5723 | 0 |  |  | 4 |  | PNA - Re-Stripe Parking
25 | 51076-00 | Site perimeter fencing | PNA - Repair CMU Block Fencing (Hollow Cells) | GC | Year 1 | 3750 | 0 |  |  | 4 |  | PNA - Repair CMU Block Fencing (Hollow Cells)
22 | 51091-00 | Sidewalks and curbs | PNA - Repair Sidewalks / Curbs (Up to 100 SF) | GC | Year 1 | 3500 | 0 |  |  | 4 |  | PNA - Repair Sidewalks / Curbs (Up to 100 SF)
75 | 51073-00 | Storage room doors | PNA - Replace Storage Room Doors (3068 HCWD) | GC | Year 1 | 1100 | 0 |  |  | 4 |  | PNA - Replace Storage Room Doors (3068 HCWD)
PROJECTS subtotal (excl. contingency/CM fee)
171 | 51190-00 | Construction Management Fee | CM Fees | CMF | CM Fee | 51554 | 0 |  |  | N/A |  | CM Fees
170 | 51990-00 | Contingency | Contingency Amount | CON | Contingency | 49099 | 0 |  |  | N/A |  | Contingency Amount